## pc_overview AP
TSMC 新工 | PM Type | Mapped_Category | Scope | Project Number | PO # | Amount | Project Name | PO Description | Vendor/Subcontractor | Accumulated AP (Paid) | AP % | Category | Main/CO/DCR | Actual Pertain | Type | Type2
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2201007A | 94143616.47 | F21P1 Chemical & WCCS package | Chemical Mechanical Work #1 & #2 | Harder Mechanical Contractors, Inc | 94143616.47 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Harder
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2108001A | 86000000 | F21P1 UPW | Mechanical works for UPW package | University Mechanical & Engineering Contractors, Inc. | 85961575 | 0.99955 | Mechanical | Main Contract Scope | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2109003A | 24675557.76 | F21P1 WWT package (Installation and 2 batch tanks) | Mechanical/Installation w/Engineering Support | Lasco Process Systems, LLC. | 24675557.76 | 1 | Mechanical | Main Contract Scope | WWT | WWT | LPS
Base-Build | Chemical | Electrical | M+L | USC21C005 | USCSB2109015A | 17593400.53 | F21P1 Chemical & WCCS package | CDS & WCCS Electrical | Rosendin Electric, Inc. | 17414347.5 | 0.98982 | Electrical | Main Contract Scope | CDS | Chemical | Rosendin
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2111007A | 16493658 | F21P1 UPW | UPW Electrical work | Rosendin Electric, Inc. | 16493657.94 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | WWT | Electrical | M+L | USC21C009 | USCSB2202002A | 15871093.37 | F21P1 WWT package (Installation and 2 batch tanks) | WWT electrical work | Commercial Comm and Electric Inc | 15734929.07 | 0.99142 | Electrical | Main Contract Scope | WWT | WWT | CCE
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2109009A | 15735376.61 | F21P1 Chemical & WCCS package | WCCS Mechanical Work | Southland Industries | 15735376.61 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Southland
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2109005A | 15420592.14 | F21P1 Slurry package | Slurry Mechanical Work | Southland Industries | 15420592.14 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Southland
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2209004A | 12000000 | F21P1 WWT package (Installation and 2 batch tanks) | PSS-WWT mechanic work scope cut from LPS – Part#1 | Process Service Specialists, LLC of Delaware | 12000000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2404165A | 9500000 | Chemical & WCCS B Side Project | Proposal TSMC-014 @ Chemical Piping_Side B_L20 CPVC_GN2_PFA_PULL BOX_RELATED SUPPORTS Installations | CRG International | 9025000 | 0.95 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2112003A | 8912174.27 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Mechanical #2 | Lasco Process Systems, LLC. | 7748947.02 | 0.86948 | Mechanical | Main Contract Scope | WWT | WWT | LPS
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2301036A | 8858760.4 | F21P1 WWT package (Installation and 2 batch tanks) | PSS - Drain system and piping work #2 | Process Service Specialists, LLC of Delaware | 8858760.4 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2109008A | 8497604.48 | F21P1 VOC package （Installation ) | VOC Mechanical Work | Southland Industries | 8497604.22 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | VOC | Southland
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2207007A | 7994980 | F21P1 WWT package (Installation and 2 batch tanks) | WWT & TMAH pipe rack | Greenberry Industrial | 7814921.78 | 0.97748 | Steel | Main Contract Scope | WWT | WWT | Greenberry
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2311119A | 7800000 | WWT Change Order (Piping) | PSS SW-23-DEC Final prepay | Process Service Specialists, LLC of Delaware | 7800000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Electrical | M+L | USC24C006 | USCSB2404042A | 7500000 | WWT B side Project | TSMC WWT Electric BOQ for FAB B side Rev3 | Helix Electric, Inc. | 7072405 | 0.94299 | Electrical | Main Contract Scope | WWT | WWT | Helix
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2404072A | 6200000 | Chemical & WCCS B Side Project | M4支援F21專案材料/BOX Open PO | Marketech International Corp. | 233257.79 | 0.037622 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2202001A | 6153000 | F21P1 Chemical & WCCS package | Rigging for UPW & Chemical Package | Milling Machinery, Inc. | 5845350 | 0.95 | Mechanical | Main Contract Scope | CDS | Chemical | MIMO/Rigging
Base-Build | Water_Sewer | Mechanical | M+L | USC21C010 | USCSB2110008A | 5655525.57 | tsmc AZ sewer and water pipeline installation | TSMC Frontage Water Main | Milling Machinery, Inc. | 5655525.57 | 1 | Mechanical |  |  | Pipeline | MMI
Base-Build | WWT | Electrical | Labor | USC23C045 | USCSB2311041A | 4935846 | WWT Change Order (Piping) | F21 P1 FAB A WWT Electrical Engineering (T&M) | Okland Construction Company, Inc. | 4911102.69 | 0.99499 | Electrical | Main Contract Scope | WWT | WWT | Helix
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2312175A | 4500000 | F21P1 WWT package (Installation and 2 batch tanks) | PSS Dec payment request | Process Service Specialists, LLC of Delaware | 4500000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USC2109014A | 4470815 | F21P1 WWT package (Installation and 2 batch tanks) | FIRST 22 CS TANKS | Alliance Industrial Group, LLC | 4470815 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USC2109003A | 4120988.48 | F21P1 WWT package (Installation and 2 batch tanks) | Tank | Harrington Industrial Plastics LLC | 4120988.4786 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Low Voltage | Electrical | M+L | USC21C007 | USCSB2109010A | 4099969.21 | F21P1 VOC package （Installation ) | VOC Electrical & Controls | Spectra Electrical Services, Inc. | 4099969.21 | 1 | Electrical | CO Scope (adding/additional scope) | Low Voltage | VOC | Labor
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2309035A | 4038170.94 | WWT Change Order (Piping) | PSS WWT scope for invoice SW-23-0107 and SW-23-0134 | Process Service Specialists, LLC of Delaware | 4038170.94 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | UPW | Mechanical | Material | USC21C003 | USC2110005A | 4000000 | F21P1 UPW | UPW FRP Tank | Harrington Industrial Plastics LLC | 3999999.9135 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2310080A | 4000000 | WWT Change Order (Piping) | PSS Per Diem | Process Service Specialists, LLC of Delaware | 3700000 | 0.925 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2401070A | 4000000 | F21P1 Chemical & WCCS package | MIC and Southland reach agreement to modify contract for F21 A side Southland Scope. | Southland Industries | 4000000 | 1 | Mechanical | DCR Scope | CDS | Chemical | Southland
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2305015A | 4000000 | F21P1 WWT package (Installation and 2 batch tanks) | PSS 11M CO 4/4 batch | Process Service Specialists, LLC of Delaware | 4000000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Mechanical | Labor | USC21C011 | USCSB2305014A | 4000000 | F21 TMAH System | PSS 11M CO 3/4 batch | Process Service Specialists, LLC of Delaware | 4000000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2205001A | 3804475 | F21P1 UPW | TSMC UPW Common Supports for Area B of FAB Building | Milling Machinery, Inc. | 3690340.75 | 0.97 | Mechanical | Main Contract Scope | UPW | UPW | MMI
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2306039A | 3730153.88 | WWT Change Order (Piping) | PSS WWT Project. For invoice SW-23-0065 Final | Process Service Specialists, LLC of Delaware | 3730153.88 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | UPW | Mechanical | M+L | USC23C054 | USCSB2308003A | 3678899.78 | UPW Change Order | UMEC UPW Change Order #1 | University Mechanical & Engineering Contractors, Inc. | 3062664 | 0.83249 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2201005A | 3530956 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Platform | Milling Machinery, Inc. | 3354408.2 | 0.95 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | Low Voltage | Electrical | M+L | USC21C008 | USCSB2109016A | 3465068.83 | F21P1 CCTV & Security | CCTV Electrical Field Work | BPG Technologies, LLC | 3465068.83 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Labor
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2210038A | 3243647.71 | F21P1 WWT package (Installation and 2 batch tanks) | Lab Drainpipe installation | Process Service Specialists, LLC of Delaware | 3058089.79 | 0.94279 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | UPW | Mechanical | M+L | USC23C054 | USCSB2308088A | 3202670 | UPW Change Order | UMEC UPW Change Order #2 | University Mechanical & Engineering Contractors, Inc. | 3034614 | 0.94753 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2205022A | 3200000 | F21P1 WWT package (Installation and 2 batch tanks) | Tunnel Common Supports | Greenberry Industrial | 3040000 | 0.95 | Steel | CO Scope (adding/additional scope) | WWT | WWT | Greenberry
Base-Build | UPW | Steel | M+L | USC21C003 | USCSB2108004A | 3000000 | F21P1 UPW | tsmc Basement Equipment Mezzanines | Milling Machinery, Inc. | 2850000 | 0.95 | Steel | Main Contract Scope | UPW | UPW | MMI
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2306031A | 2880222.72 | WWT Change Order (Piping) | PSS WWT Project for invoice SW-23-0086 Final | Process Service Specialists, LLC of Delaware | 2880222.72 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2111006A | 2780000 | F21P1 Chemical & WCCS package | Cold Storage | UHO TECHNIQUE & ENGINEERING CO., LTD. | 2780000 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Others | Project Outsourcing (專案管理外包人力) | USC24C006 | USCSB2405139A | 2759355 | WWT B side Project | F21 FAB B MU management engineer quotation |  | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2403295A | 2742000 | Chemical & WCCS B Side Project | Proposal TSMC-011 @ Chemical Piping_Side B_LB1 CPVC_GN2_PFA_RELAY_VMB_PULL BOX Installations | CRG International | 1782300 | 0.65 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | UPW | Mechanical | Material | USC21C003 | USC2110015A | 2724480 | F21P1 UPW | UPW FRP PP Lining Tanks | An-Cor Industrial Plastics, Inc. | 2724480 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C006 | USCSB2306032A | 2720533 | F21P1 Slurry package | Liberty scaffolding | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 2720533 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Scaffolding
Base-Build | Low Voltage | Mechanical | Material | USC21C013 | USCSB2110004A | 2668000 | F21P1 AMC THC Monitoring System | AMC THC Monitoring System Package Rack & Accessories | Weltall Technology Corporation | 2401200 | 0.9 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Material
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2301037A | 2632901 | F21P1 WWT package (Installation and 2 batch tanks) | F21P1 PSS WWT system #1 | Process Service Specialists, LLC of Delaware | 2632901 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Chemical | Electrical | M+L | USC24C005 | USCSB2404187A | 2495333.54 | Chemical & WCCS B Side Project | REI Proposed Change order | Rosendin Electric, Inc. | 2495333.54 | 1 | Electrical | DCR Scope | CDS | Chemical | Rosendin
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2309036A | 2366258 | WWT Change Order (Piping) | 8-129 WWT LSR FAB-LB2 | University Mechanical & Engineering Contractors, Inc. | 2253922 | 0.95253 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | Low Voltage | Electrical | M+L | USC24C007 | USCSB2404049A | 2341425.36 | Low Voltage B Side Project | F21-P1_B-SIDE CCTV & ACCESS (not Include L20 HPM) | NUUO US Inc. | 1888238.75 | 0.80645 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C008 | USCSB2110013A | 2272119 | F21P1 CCTV & Security | F21P1 FAB Secruity& CCTV System | AEGISTEK SYSTEMS CO., LTD. | 2021968 | 0.8899 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | WWT | Civil | M+L | USC22C011 | USCSB2207015A | 2223500 | WRC Exterior Pads - NH3 and Diesel System | WRC Exterior Pads - NH3 and Diesel System | Sundt Construction, Inc | 2112178 | 0.94993 | Civil | Main Contract Scope | WWT | Exterior Pad | Material
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2311092A | 2200000 | WWT Change Order (Piping) | PSS SW-23-NOV Final prepay | Process Service Specialists, LLC of Delaware | 2200000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2404164A | 2200000 | Chemical & WCCS B Side Project | Proposal TSMC-013 @ Chemical Piping_Side B_L30 CPVC_GN2_PFA_PULL BOX_RELATED SUPPORTS Installations | CRG International | 1034000 | 0.47 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2404074A | 2152918.88 | Chemical & WCCS B Side Project | Invoice No. MICU-009(021824-31624 T&M) | CRG International | 2152918.88 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | WWT | Civil | M+L | USC21C009 | USC2210016A | 2150304 | F21P1 WWT package (Installation and 2 batch tanks) | WRC Chem Room Epoxy/Installation of FRP Membrane | OBR Cooling Towers, Inc. | 2150304 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Electrical | M+L | USC24C006 | USCSB2404112A | 2050000 | WWT B side Project | TSMC WWT Electric BOQ for FAB B side Rev3 - part 2 | Helix Electric, Inc. | 1176567 | 0.57394 | Electrical | Main Contract Scope | WWT | WWT | Helix
Base-Build | WWT | Steel | Material | USC21C009 | USCSB2111003A | 2000000 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Pipe Rack | Lasco Process Systems, LLC. | 2000000 | 1 | Steel | Main Contract Scope | WWT | WWT | LPS
Base-Build | Chemical | Others | M+L | USC21C005 | USC2208005A | 2000000 | F21P1 Chemical & WCCS package | Scaffold | Action Equip & Scaffold Co. Inc | 2000000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | CDS | Base-Build | Scaffolding
Base-Build | Water_Sewer | Civil | M+L | USC21C003 | USCSB2109001A | 2000000 | F21P1 UPW | tsmc 43rd Ave Sewer Line Extension | Milling Machinery, Inc. | 2000000 | 1 | Civil | The budget execution does not pertain to this project | Pipeline | UPW | MMI
Base-Build | WWT | Mechanical | Labor | USC21C006 | USCSB2305013A | 2000000 | F21P1 Slurry package | PSS 11M CO 2/4 batch | Process Service Specialists, LLC of Delaware | 2000000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2205005A | 2000000 | F21P1 UPW | Scaffold for F21 MEP Scaffold work | Action Equip & Scaffold Co. Inc | 1999976 | 0.99999 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Scaffolding
Base-Build | Low Voltage | Electrical | M+L | USC21C012 | USCSB2307096A | 1950462 | F21 Barcode RFID System | F21 P1 Barcode system Engineering | NUUO US Inc. | 1576220.76 | 0.80813 | Electrical | Main Contract Scope | Low Voltage | Barcode | NUUO
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2201010A | 1950339.22 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Housekeeping Pad | Degan Construction LLC | 1950339.22 | 1 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2310146A | 1917083 | WWT Change Order (Piping) | WWT-LSRi-uncompleted lines | University Mechanical & Engineering Contractors, Inc. | 1734669 | 0.90485 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | Base-Build | Others | Site Expense | USC23C045 | USCSB2401067A | 1914858 | WWT Change Order (Piping) | J.T. Thorpe Aug invoice | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 1914858 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Scaffolding
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2206019A | 1909676.1 | F21P1 WWT package (Installation and 2 batch tanks) | PP materials d225 and d180 | Mega Union Technology Global Pte Ltd | 1909676.1 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2207017A | 1890000 | F21P1 WWT package (Installation and 2 batch tanks) | WWT rigging and equipment move in | Milling Machinery, Inc. | 1890000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | MIMO/Rigging
Base-Build | Base-Build | Others | Site Expense | USC21C006 | USCSB2307115A | 1876313.76 | F21P1 Slurry package | Liberty March invoice and April invoice | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 1876313.76 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Scaffolding
Base-Build | Low Voltage | Electrical | M+L | USC23C045 | USCSB2309168A | 1839196.6 | WWT Change Order (Piping) | F21 P1 A site Access Control, ACS Panel interconnection | NUUO US Inc. | 1745473.34 | 0.94904 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC22C022 | USCSB2210043A | 1794999.84 | F21P1 Triazole treatment system | MU-Triazole System | Mega Union Technology Inc. | 784435.72 | 0.43701 | Mechanical | Main Contract Scope | WWT | Triazole | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2206016A | 1756177.47 | F21P1 WWT package (Installation and 2 batch tanks) | WWT add BOM on March | Lasco Process Systems, LLC. | 1352739.95 | 0.77028 | Mechanical | Main Contract Scope | WWT | WWT | LPS
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USC2109002A | 1733380.86 | F21P1 WWT package （USA EQ-FRP tank) | tank,FRP | Harrington Industrial Plastics LLC | 1733380.512 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C001 | USCSB2205008A | 1670175 | F21 P1 Office and WH Security and CCTV | CCTV Office Design and equipment | AEGISTEK SYSTEMS CO., LTD. | 1670175 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2306112A | 1660117 | F21P1 UPW | UMEC-2022 week 60 hour rate difference | University Mechanical & Engineering Contractors, Inc. | 1256301 | 0.75675 | Mechanical | Main Contract Scope | UPW | UPW | UMEC
Base-Build | Chemical | Electrical | M+L | USC21C006 | USCSB2401227A | 1658637 | F21P1 Slurry package | REI CDS CO | Rosendin Electric, Inc. | 1658637 | 1 | Electrical | DCR Scope | CDS | Chemical | Rosendin
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2308089A | 1649670.58 | WWT Change Order (Piping) | PSS WWT Project. For invoice SW-23-0131 Final | Process Service Specialists, LLC of Delaware | 1649670.58 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2205024A | 1633000 | F21P1 WWT package (Installation and 2 batch tanks) | WWT FRP tanks | Shanghai Mega Union Environmental Technology Co., LTD | 1551350 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Electrical | Labor | USC21C005 | USCSB2402133A | 1610000 | F21P1 Chemical & WCCS package | CDS L20 Monitoring piping and cable engineering | DFK Tech, LLC | 1529500 | 0.95 | Electrical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | Base-Build | Others | Site Expense | USC23C045 | USCSB2312108A | 1590281.5 | WWT Change Order (Piping) | JT Thorpe Sep Invoice | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 1590281.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Scaffolding
Base-Build | UPW | Mechanical | M+L | USC23C054 | USCSB2312092A | 1554463 | UPW Change Order | UPW-UMEC-extend GC 2023-Sep to Nov | University Mechanical & Engineering Contractors, Inc. | 1476470 | 0.94983 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Low Voltage | Electrical | Material | USC21C012 | USCSB2110012A | 1550000 | F21 Barcode RFID System | F21P1 Barcode & RFID System | Ying Pao Technology Inc. | 1017474.56 | 0.65644 | Electrical | Main Contract Scope | Low Voltage | Barcode | Material
Base-Build | Base-Build | Others | Site Expense | USC22C024 | USCSB2210018A | 1500000 | UIS Scaffolding | Liberty Industrial Group Scaffold | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 1490921.08 | 0.99395 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Scaffolding
Base-Build | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2301021A | 1500000 | F21P1 Chemical & WCCS package | PDP panel | UCAN Hong Kong Limited | 1500000 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | UPW | Civil | M+L | USC21C003 | USCSB2111008A | 1495365.57 | F21P1 UPW | UPW civil work (Housekeeping Pad) | Degan Construction LLC | 1493744.85 | 0.99892 | Civil | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2301012A | 1492567.83 | F21P1 Chemical & WCCS package | TW Supporting Piping Materials | Marketech International Corp. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC24C010 | USC2408011A | 1484981.27 | General Conditions B Side Project | 15-HPM L30 V Line 及FAB L10 L LINE配合氣化課拆庫板 (MICU) | United Integrated Services (USA) Corp | 1484981.27 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | General Condition | Other Scope
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2205023A | 1442704.28 | F21P1 Chemical & WCCS package | CDS T-box | Pure Plastics, LLC | 1442704.28 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | M+L | USC24C005 | USCSB2403294A | 1435672.3 | Chemical & WCCS B Side Project | TSMC F21 P1 CDS/SDS B side Support | TCELC CO., LTD | 1435672.3 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Electrical | Labor | USC23C045 | USCSB2309165A | 1427459.08 | WWT Change Order (Piping) | WWT Support_HELIX | Okland Construction Company, Inc. | 1398534.33 | 0.97974 | Electrical | Main Contract Scope | WWT | WWT | Helix
Base-Build | Chemical | Electrical | M+L | USC24C005 | USCSB2405096A | 1420000 | Chemical & WCCS B Side Project | DFK Tech F21P1- POWER-B Machine panel power connection Bid No. Item Content Material Designated Vendor Model/Specific-Urgent | DFK Tech, LLC | 710000 | 0.5 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | UPW | Mechanical | Labor | USC21C005 | USCSB2304016A | 1400000 | F21P1 Chemical & WCCS package | Additional Rigging work in the Phase A for UPW scope | Milling Machinery, Inc. | 1400000 | 1 | Mechanical | Main Contract Scope | UPW | UPW | MIMO/Rigging
Base-Build | WWT | Electrical | Labor | USC21C009 | USCSB2402053A | 1400000 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Helix-A side 1/15 + 15 in March (partial 1.4M) | Helix Electric, Inc. | 1399921.49 | 0.99994 | Electrical | Main Contract Scope | WWT | WWT | Helix
Base-Build | WWT | Mechanical | M+L | USC21C014 | USCSB2207020A | 1375375 | F21P1 WH2SO4 | W-H2SO4 Mechanical Work | Trident Mechanical Services | 1375375 | 1 | Mechanical | Main Contract Scope | WWT | W-H2SO4 | Trident
Base-Build | Low Voltage | Electrical | M+L | USC22C001 | USCSB2203001A | 1367378.8 | F21 P1 Office and WH Security and CCTV | Office Building Security & CCTV Electrical Work | Norstan Communications, Inc.dba Black Box Network Services | 1367378.8 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207003A | 1359840 | F21P1 UPW | ESD Jumpsuit With Hood, Sticky Mat, Nitrile Disposable Glove & Face Mask, ESD Safety Shoe… | Super Starnix SDN BHD | 1359840 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2205021A | 1337939.49 | F21P1 WWT package (Installation and 2 batch tanks) | Simona PVDF material for WWT | Lasco Process Systems, LLC. | 1321837.89 | 0.98797 | Mechanical | Main Contract Scope | WWT | WWT | LPS
Base-Build | Base-Build | Others | Site Expense | USC23C045 | USCSB2310180A | 1317346 | WWT Change Order (Piping) | Liberty July invoice | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 1317346 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Scaffolding
Base-Build | Base-Build | Others | Site Expense | USC23C045 | USCSB2309173A | 1316565.5 | WWT Change Order (Piping) | Liberty June Invoice | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 1316565.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Scaffolding
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2211027A | 1305645.46 | F21 TMAH System | F21P1 TMAH | Mega Union Technology Inc. | 580012.96 | 0.44423 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | Chemical | Electrical | Labor | USC22C010 | USCSB2304077A | 1299998.2 | F21 P1 LSC CMS and DPM 5G System | F21P1 Slurry A Electrical/Controls | Hua Yi Construction AZ, Inc | 1299998.2 | 1 | Electrical | 0 | 0 | Slurry | Material
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2404073A | 1291338.73 | Chemical & WCCS B Side Project | Invoice No. MICU-008(1/28/24-2/17/24 T&M) | CRG International | 1291338.73 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | Low Voltage | Mechanical | M+L | USC23C054 | USCSB2308075A | 1290937.49 | UPW Change Order | F21 P1 VOC Extended General Conditions | Southland Industries | 1290937.49 | 1 | Mechanical | The budget execution does not pertain to this project | VOC | VOC | Southland
Base-Build | Low Voltage | Electrical | M+L | USC21C008 | USCSB2306140A | 1288488.34 | F21P1 CCTV & Security | F21 P1 CCTV FAB Camera, Conduit, Cabling and Panel Installation | NUUO US Inc. | 1288488.34 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | UPW | Electrical | Labor | USC23C054 | USCSB2402115A | 1282154.51 | UPW Change Order | PCO 79 Price Adjustment for Incentive Weekend OT and Swing Shift | Rosendin Electric, Inc. | 988872.66 | 0.77126 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Rosendin
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2403275A | 1281921.72 | WWT B side Project | B side MU FAB/HPM LB2 Main Drain | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Labor | USC24C005 | USCSB2404008A | 1260000 | Chemical & WCCS B Side Project | 18 Tanks Quote for Fab 21 | DFK Tech, LLC | 1197000 | 0.95 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USC2111063A | 1251211.84 | F21P1 WWT package (Installation and 2 batch tanks) | Supply Tank | Alliance Industrial Group, LLC | 1242913.35 | 0.99337 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2402209A | 1249493.14 | F21P1 Chemical & WCCS package | CDS REI CO 70/CO 73/CO 79/CO 86 | Rosendin Electric, Inc. | 62474.66 | 0.05 | Electrical | DCR Scope | CDS | Chemical | Rosendin
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2205004A | 1247244.64 | F21P1 Slurry package | 台積電(美國)F21P1防火填塞工程 | Kinpo Co. | 374173 | 0.3 | Mechanical | Main Contract Scope | SDS | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403182A | 1240156.97 | F21P1 WWT package (Installation and 2 batch tanks) | B side MU FAB/HPM+Drain material | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2303046A | 1192357 | F21P1 UPW | GF material raise | University Mechanical & Engineering Contractors, Inc. | 1072152 | 0.89919 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2312037A | 1178171.5 | WWT Change Order (Piping) | WWT_Manpower support _MEGA | Mega Union Technology Inc. | 588647.14 | 0.49963 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Material | USC22C023 | USCSB2210025A | 1129032.26 | AZ GF Agru Material | GF PP&PVDF Material Li Jie | Li Jie Industrial Co.,Ltd | 1129032.26 | 1 | Mechanical |  |  | GF Agru Material | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2212029A | 1104701 | F21P1 WWT package (Installation and 2 batch tanks) | Clamps Lorry – L10-20-30 | Process Service Specialists, LLC of Delaware | 899102.27 | 0.81389 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2402190A | 1103574.8 | F21P1 Chemical & WCCS package | CDS T&M work Jan 2024 | CRG International | 1103574.8 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2402222A | 1096382.54 | WWT Change Order (Piping) | WWT Stripper insulation | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 1096382.54 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2205011A | 1089600 | F21P1 WWT package (Installation and 2 batch tanks) | Outsourcing Foreman | CGS Global Support, LLC | 1089600 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | UPW | Steel | M+L | USC21C003 | USCSB2110016A | 1085250 | F21P1 UPW | UPW common Rack | Milling Machinery, Inc. | 1085250 | 1 | Steel | Main Contract Scope | UPW | UPW | MMI
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2109012A | 1060000 | F21P1 Chemical & WCCS package | Chemical Storage Design, PE Stamp and onsite Work | Milling Machinery, Inc. | 1060000 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Water_Sewer | Civil | M+L | USC22C018 | USCSB2209026A | 1045000 | US Fab Frontage line hydrants | TSMC Hydrant Proposal | Degan Construction LLC | 1045000 | 1 | Civil |  |  | Frontage Line Hydrant | Material
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC23C045 | USCSB2312128A | 1037689.53 | WWT Change Order (Piping) | CGS outsourcing manpower | CGS Global Support, LLC | 1037689.53 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | Chemical | Mechanical | E2 | USC24C005 | USCSB2404021A | 1037400 | Chemical & WCCS B Side Project | F21 Bside 耘起(耘程)塑材人力 | Yun Cheng International Co., Ltd | 570900 | 0.55032 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2312063A | 1036853 | WWT Change Order (Piping) | WWT - Install L30 Drains | BMWC Constructors, INC. | 985010.35 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2310028A | 1012845 | WWT Change Order (Piping) | WWT -LB2-Lab drain | University Mechanical & Engineering Contractors, Inc. | 962923 | 0.95071 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | Low Voltage | Electrical | M+L | USC22C013 | USCSB2401149A | 1000982.17 | F21P1 QR Lab Security & CCTV | F21 AUX and FAB CCTV, Access control and ACS system | NUUO US Inc. | 950933.06 | 0.95 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | WWT | Mechanical | Labor | USC21C004 | USCSB2305012A | 1000000 | F21P1 WWT package （USA EQ-FRP tank) | PSS 11M CO 1/4 batch | Process Service Specialists, LLC of Delaware | 1000000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Chemical | Mechanical | Material | USC21C006 | USC2201005A | 1000000 | F21P1 Slurry package | Sleeve,PFA,1"(PFA tube, Pipe Label) | Marketech International Corp. | 0 | 0 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | Chemical | Others | M+L | USC21C005 | USC2303002A | 1000000 | F21P1 Chemical & WCCS package | Scaffolding | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 1000000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | CDS | Base-Build | Scaffolding
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2304017A | 1000000 | F21P1 Slurry package | Additional Rigging work in the Phase A for Chemical scope | Milling Machinery, Inc. | 1000000 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | MIMO/Rigging
Base-Build | Low Voltage | Mechanical | Material | USC21C013 | USCSB2110005A | 1000000 | F21P1 AMC THC Monitoring System | AMC THC Monitoring System Package Host Equipment | Weltall Technology Corporation | 900000 | 0.9 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Material
Base-Build | UPW | Electrical | Labor | USC24C008 | USCSB2404033A | 1000000 | UPW B Side Project | REI UPW PCO 083 Contract Pricing Adjustment Phase 3, R0 | Rosendin Electric, Inc. | 1000000 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | WWT | Electrical | Labor | USC21C009 | USCSB2401146A | 1000000 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Helix-A side 1/15 + 15 in March (partial 1M) | Helix Electric, Inc. | 1000000 | 1 | Electrical | Main Contract Scope | WWT | WWT | Helix
Base-Build | WWT | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USC2210013A | 1000000 | F21P1 WWT package (Installation and 2 batch tanks) | CM Services | Sundt Construction, Inc | 518549.47 | 0.51855 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Site Expense
Base-Build | UPW | Others | Material | USC21C003 | USCSB2204003A | 987756 | F21P1 UPW | Activated Carbon | Calgon Carbon Corporation | 987756 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Electrical | M+L | USC23C054 | USCSB2308124A | 986866.74 | UPW Change Order | F21 P1 WWT Electric Engineering-CCE | Commercial Comm and Electric Inc | 986866.74 | 1 | Electrical | DCR Scope | WWT | WWT | CCE
Base-Build | Chemical | Electrical | Labor | USC21C006 | USCSB2401219A | 972000 | F21P1 Slurry package | CDS Lorry A 18 Tank | DFK Tech, LLC | 923400 | 0.95 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | E2 | USC24C005 | USCSB2404038A | 966500 | Chemical & WCCS B Side Project | F21 B side 弘東人力 | HONGDONG INTERNATIONAL CO., LTD | 679000 | 0.70253 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2402004A | 962482 | F21P1 WWT package (Installation and 2 batch tanks) | MIC-004-22 X1-Line Cable Tray Supports | Greenberry Industrial | 962482 | 1 | Steel | DCR Scope | WWT | WWT | Greenberry
Base-Build | WWT | Mechanical | Material | USC21C004 | USCSB2205020A | 960814.29 | F21P1 WWT package （USA EQ-FRP tank) | WWT Hopper and Piping Header | Mega Union Technology Inc. | 960814.29 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2403122A | 950000 | F21P1 UPW | PCO 82 Contract Pricing Adjustment, Continuation of Work Phase 2, Revision 0(batch 1/2) | Rosendin Electric, Inc. | 950000 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2306098A | 931858 | F21P1 UPW | UMEC-2022 Sep to Dec incentive | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Low Voltage | Electrical | M+L | USC22C001 | USCSB2303073A | 927440.77 | F21 P1 Office and WH Security and CCTV | Security & CCTV Electrical Work | NUUO US Inc. | 927440.77 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | WWT | Electrical | Material | USC21C009 | USCSB2211012A | 916925 | F21P1 WWT package (Installation and 2 batch tanks) | CCE Redesign Change Order | Commercial Comm and Electric Inc | 916925 | 1 | Electrical | DCR Scope | WWT | WWT | CCE
Base-Build | Low Voltage | Electrical | M+L | USC21C008 | USCSB2301035A | 900000 | F21P1 CCTV & Security | F21P1 Office Secruity CCTV System | Commercial Comm and Electric Inc | 715880 | 0.79542 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | CCE
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C005 | USC2301005A | 896185 | F21P1 Chemical & WCCS package | Kelly Outsourcing | Kelly Services, Inc. | 882540.55 | 0.98477 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Outsourcing
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USC2301004A | 896185 | F21P1 WWT package (Installation and 2 batch tanks) | Kelly Outsourcing | Kelly Services, Inc. | 896185 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2404135A | 889529 | UPW B Side Project | UPW-UMEC-extend GC for 2024 Jan - Feb | University Mechanical & Engineering Contractors, Inc. | 845053 | 0.95 | Mechanical | Main Contract Scope | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2203007A | 880212 | F21P1 WWT package (Installation and 2 batch tanks) | Tanks freight | Harrington Industrial Plastics LLC | 880212 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Low Voltage | Electrical | M+L | USC21C013 | USCSB2204004A | 867959.59 | F21P1 AMC THC Monitoring System | AMC/THC electric and low voltage | Commercial Comm and Electric Inc | 853014.89 | 0.98278 | Electrical | Main Contract Scope | Low Voltage | AMC THC | CCE
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2207010A | 860400 | F21P1 Slurry package | Engineering Design Assistance and Engineer of Record Services | KAEKO, Inc | 848120 | 0.98573 | Mechanical | Main Contract Scope | SDS | Base-Build | Labor
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2404163A | 859100 | WWT B side Project | Megaunion 元富 B side 8m 1 scope + 210 header +120 all | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2407069A | 856637 | UPW B Side Project | UMEC GC for 2024 March & April | University Mechanical & Engineering Contractors, Inc. | 813805 | 0.95 | Mechanical |  |  | UPW
Base-Build | Base-Build | Others | Site Expense | USC22C024 | USCSB2308140A | 851774.5 | UIS Scaffolding | Liberty May 04 | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 851774.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Scaffolding
Base-Build | Low Voltage | Electrical | M+L | USC22C010 | USCSB2312135A | 848096 | F21 P1 LSC CMS and DPM 5G System | F21 CMS & DPM IMP Engineering | NUUO US Inc. | 356100.65 | 0.41988 | Electrical | Main Contract Scope | Low Voltage | 5G | NUUO
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2206021A | 831105 | F21P1 UPW | F21P1 Laboratory scope | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USCSB2312144A | 830000 | F21P1 Slurry package | CDS MICU Equipment-1 | Marketech International Corp. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309178A | 825000 | WWT Change Order (Piping) | WWT -MU Train A rest material | Mega Union Technology Inc. | 825000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2304018A | 800000 | F21 TMAH System | Additional Rigging work in the Phase A for WWT scope | Milling Machinery, Inc. | 800000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | MIMO/Rigging
Base-Build | WWT | Mechanical | Material | USC22C023 | USCSB2211015A | 774105 | AZ GF Agru Material | AZ GF Material Summary Table | SWIFT ENGINEERING CO., LTD. | 774105 | 1 | Mechanical |  |  | GF Agru Material | Material
Base-Build | UPW | Steel | M+L | USC21C003 | USCSB2112005A | 769545 | F21P1 UPW | UPW A-G pipe rack | Milling Machinery, Inc. | 769545 | 1 | Steel | Main Contract Scope | UPW | UPW | MMI
Base-Build | WWT | Mechanical | Labor | USC24C006 | USCSB2404005A | 769450 | WWT B side Project | (A side)YAHO T&M A side work from 11/2023-05/2024 | YAHO System Technology Inc. | 757316.67 | 0.98423 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Electrical | Labor | USC21C009 | USCSB2210026A | 761100 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Panel Move-In and installation | Commercial Comm and Electric Inc | 641145 | 0.84239 | Electrical | Main Contract Scope | WWT | WWT | MIMO/Rigging
Base-Build | UPW | Steel | M+L | USC21C003 | USCSB2201002A | 744188 | F21P1 UPW | UPW blue, purple ,yellow area pipe rack | Milling Machinery, Inc. | 744188 | 1 | Steel | Main Contract Scope | UPW | UPW | MMI
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2312115A | 735000 | F21P1 WWT package (Installation and 2 batch tanks) | INTUMESCENT FIREPROOFING mezz 1 and 2 Fab LB2 (release of second half) | Alpha Insulation and Waterproofing, Inc | 661500.04 | 0.9 | Civil | CO Scope (adding/additional scope) | WWT | Base-Build | Labor
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2309156A | 732452.27 | WWT Change Order (Piping) | WWT-settle cost for AIG | Alliance Industrial Group, LLC | 732452.27 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C001 | USCSB2308125A | 730573 | F21 P1 Office and WH Security and CCTV | F21P1 OFFICE Security and CCTV System | Aegis Technology Inc | 304794 | 0.4172 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2206002A | 721645 | F21P1 UPW | TOC Analyzer and portable | Veolia WTS Analytical Instruments, Inc. | 707497.95 | 0.9804 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2402182A | 717845.48 | F21P1 UPW | UPW Continuation of Work Phase 1 | Rosendin Electric, Inc. | 717845.48 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | Low Voltage | Electrical | M+L | USC22C001 | USCSB2401152A | 709832.25 | F21 P1 Office and WH Security and CCTV | F21 AUX and FAB CCTV, Access control and ACS system 1st portion | NUUO US Inc. | 709832.25 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2403105A | 707171.3 | F21P1 WWT package (Installation and 2 batch tanks) | [B side][Manpower-MU] 元富/宇翔/柯達/3months | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Electrical | Labor | USC23C054 | USCSB2308077A | 705000 | UPW Change Order | F21 P1 UPW/CDS Change Order | Rosendin Electric, Inc. | 705000 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2108003A | 700000 | F21P1 UPW | Modular Site Office | Design Modulars Inc. | 700000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Trailer
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2405041A | 700000 | Chemical & WCCS B Side Project | F21 B side L20/L10 UPW 工程發包_MornstAir | MornstAir Inc. | 665000 | 0.95 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | M+L | USC22C022 | USCSB2306096A | 686619 | F21P1 Triazole treatment system | WWT Triazole | University Mechanical & Engineering Contractors, Inc. | 686619 | 1 | Mechanical | Main Contract Scope | WWT | Triazole | UMEC
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC23C022 | USCSB2311122A | 676020 | F21P1_H_2D/3D drawing | Kelly Outsourcing manpower | Kelly Services, Inc. | 676020 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | General Condition | Outsourcing
Base-Build | Low Voltage | Electrical | M+L | USC23C054 | USCSB2308087A | 670874.78 | UPW Change Order | F21 Warehouse CCTV over time and CO | NUUO US Inc. | 660865.38 | 0.98508 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2207011A | 670653 | F21P1 WWT package (Installation and 2 batch tanks) | d225 drain pipe materials | Mega Union Technology Global Pte Ltd | 670653 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2212025A | 665277.46 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Lab drain pipe materials | Mega Union Technology Global Pte Ltd | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2207009A | 660920 | F21P1 WWT package (Installation and 2 batch tanks) | Kelly outsourcing engineering | Kelly Services, Inc. | 659932.88 | 0.99851 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2308100A | 658791.27 | WWT Change Order (Piping) | RFQ – MIC – Stripper System Piping, Pumps, Outside Tanks - Insulation | Marquis Construction Services LLC | 658791.27 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Low Voltage | Electrical | M+L | USC21C013 | USCSB2306126A | 653553.4 | F21P1 AMC THC Monitoring System | THC electric and low voltage engineering | NUUO US Inc. | 653553.4 | 1 | Electrical | Main Contract Scope | Low Voltage | AMC THC | NUUO
Base-Build | UPW | Mechanical | Labor | USC23C014 | USCSB2304001A | 651855 | F21P1 Labor incentive program-MICU | 2022 holiday incentive (Nov, Dec) | University Mechanical & Engineering Contractors, Inc. | 632823 | 0.9708 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2310099A | 644264 | WWT Change Order (Piping) | WWT-Suction pipes for train A | University Mechanical & Engineering Contractors, Inc. | 612083 | 0.95005 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC23C045 | USCSB2312111A | 638265.04 | WWT Change Order (Piping) | Kelly outsourcing | Kelly Services, Inc. | 638265.04 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2203006A | 630878 | F21P1 UPW | Tanks freight | Harrington Industrial Plastics LLC | 630878 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2401179A | 619121.32 | F21P1 Slurry package | CDS T&M work Nov | CRG International | 619121.32 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | Chemical | Mechanical | E2 | USC24C005 | USCSB2404154A | 615000 | Chemical & WCCS B Side Project | 垚鋐電力人力-點工人力(15人/3個月) | YAHO System Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2404141A | 610000 | Chemical & WCCS B Side Project | Proposal TSMC-012 @ Chemical Piping_Side B_L10 CPVC_GN2_PFA_PULL BOX_RELATED SUPPORTS Installations | CRG International | 494100 | 0.81 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC22C019 | USCSB2210015A | 600000 | AMC monitor 595T0 | MICU-TSMC F21P1 Litho AMC 64CH online monitoring system | Welmade Technology Corporation | 600000 | 1 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Material
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2109004A | 599155.6 | F21P1 WWT package (Installation and 2 batch tanks) | Front-End Engineering Support Service | Lasco Process Systems, LLC. | 599155.6 | 1 | Mechanical | Main Contract Scope | WWT | WWT | LPS
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2404029A | 595712 | F21P1 WWT package (Installation and 2 batch tanks) | WWT UIS Manpower_20240329 | United Integrated Services (USA) Corp | 302240.16 | 0.50736 | Mechanical | DCR Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Material | USC21C003 | USCSB2302044A | 595649.07 | F21P1 UPW | LPS RH materials #2 | Ryan Herco Flow Solutions | 595649.07 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2312047A | 591435 | WWT Change Order (Piping) | WWT_LB2 LSR Scope_BMWC | BMWC Constructors, INC. | 561863.25 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | M+L | USC21C006 | USCSB2305080A | 590648 | F21P1 Slurry package | CDS Solvent Room Conduit & Updated Cable Tray/Supports Constructible BIM Model | Rosendin Electric, Inc. | 590648 | 1 | Electrical | DCR Scope | CDS | Chemical | Rosendin
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2308118A | 590060 | WWT Change Order (Piping) | WWT -BMWC Tunnel Trestle r2 | BMWC Constructors, INC. | 590060 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2406009A | 589183.95 | WWT B side Project | (Chemical Borrowed)澤維實業PVDF 料件0531 | Ze-Wei Industrial Co., Ltd. | 150907.82 | 0.25613 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2407165A | 587428.8 | WWT B side Project | WWT - Brahma A-Side Carboline Flange Coating | BRAHMA GROUP, INC. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2401180A | 582103.64 | F21P1 Slurry package | CDS T&M work Dec | CRG International | 582103.64 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | Chemical | Others | QAQC | USC21C005 | USCSB2204007A | 581700 | F21P1 Chemical & WCCS package | Lorry building engineering services | KAEKO, Inc | 581700 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | CDS | Base-Build | Labor
Base-Build | Chemical | Others | QAQC | USC21C005 | USCSB2307135A | 581400 | F21P1 Chemical & WCCS package | TSMC FAB, Lorry, and WRC Field Observation | KAEKO, Inc | 416179 | 0.71582 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Base-Build | Labor
Base-Build | UPW | Others | Commissioning | USC21C003 | USCSB2206009A | 571949.64 | F21P1 UPW | Commissioning Chemicals | Univar Solutions USA Inc. | 571786.07 | 0.99971 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Material
Base-Build | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2210005A | 569074 | F21P1 VOC package （Installation ) | VOC project Added insulation per Bill of Materials | Southland Industries | 569074 | 1 | Mechanical | Main Contract Scope | Low Voltage | VOC | Southland
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2407087A | 568229 | WWT B side Project | LB2 GIP Blower System_WWT | University Mechanical & Engineering Contractors, Inc. | 278432 | 0.49 | Mechanical |  |  | WWT
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC23C002 | USCSB2309008A | 559797.76 | F21P1-0404_H_Hallway plate install_MICU | Project manpower supply for safety, project management and house keeping | CGS Global Support, LLC | 559797.76 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Outsourcing
Base-Build | Chemical | Others | QAQC | USC21C005 | USCSB2207006A | 557900 | F21P1 Chemical & WCCS package | Engineering Design Assistance and Engineer of Record Services | KAEKO, Inc | 557900 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | CDS | Base-Build | Labor
Base-Build | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2203012A | 547240 | F21P1 VOC package （Installation ) | AMC THC mechanic work | Southland Industries | 536295.54 | 0.98 | Mechanical | The budget execution does not pertain to this project | AMC THC | AMC THC | Southland
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2407154A | 546932 | WWT B side Project | LB2 WWT 60608 & 60110 | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Chemical | Others | Labor | USC21C005 | USCSB2406093A | 542050 | F21P1 Chemical & WCCS package | FAB Chemical Observation - LSW | LSW Engineers Arizona, Inc. | 59080 | 0.10899 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2310068A | 517921.17 | F21P1 Chemical & WCCS package | Southland Co for Chemical team | Southland Industries | 517921.17 | 1 | Mechanical | DCR Scope | CDS | Chemical | Southland
Base-Build | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C013 | USCSB2306079A | 508710 | F21P1 AMC THC Monitoring System | F21P1 EBO AMC+TVOC 16CH online monitoring system | Welmade Technology Corporation | 313284 | 0.61584 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Material
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2303015A | 502320 | F21P1 UPW | UPW system panels installation and linking | Commercial Comm and Electric Inc | 408480 | 0.81319 | Electrical | Main Contract Scope | UPW | UPW | CCE
Base-Build | WWT | Mechanical | Labor | USC24C006 | USCSB2406110A | 500500 | WWT B side Project | LSR MU 元富 scope lump sump | Mega Union Technology Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2110010A | 500000 | F21P1 WWT package (Installation and 2 batch tanks) | Site 3rd Party QC Service | Technical Inspections Group | 500000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | Base-Build | Labor
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC23C002 | USCSB2309111A | 500000 | F21P1-0404_H_Hallway plate install_MICU | Tool Hookup Design/Base Build Design/System/Safety | Kelly Services, Inc. | 421156.11 | 0.84231 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Outsourcing
Base-Build | Low Voltage | Electrical | M+L | USC22C010 | USCSB2308106A | 500000 | F21 P1 LSC CMS and DPM 5G System | BPG termination | BPG Technologies, LLC | 500000 | 1 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | Labor
Base-Build | Base-Build | Others | Housekeeping | USC21C008 | USCSB2210020A | 500000 | F21P1 CCTV & Security | Sunrise Phoenix housekeeping services | Sunrise Phoenix Hi-Tech LLC | 457477.5 | 0.91495 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Housekeeping
Base-Build | Base-Build | Others | Housekeeping | USC23C045 | USCSB2309181A | 500000 | WWT Change Order (Piping) | Sunrise Phoenix housekeeping services | Sunrise Phoenix Hi-Tech LLC | 488382.87 | 0.97677 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Housekeeping
Base-Build | WWT | Electrical | Instrument | USC21C011 | USCSB2211011A | 496063.78 | F21 TMAH System | LC/MS/MS System for TSMC Project | Agilent Technologies, Inc. | 496063.78 | 1 | Electrical | Main Contract Scope | WWT | TMAH | Equipment
Base-Build | WWT | Civil | M+L | USC21C005 | USCSB2305067A | 490292.57 | F21P1 Chemical & WCCS package | Stripper Platform and F21P1 FRP Works | OBR Cooling Towers, Inc. | 490292.57 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2401173A | 480826 | WWT Change Order (Piping) | WWT-Install L20 HPM Drains | BMWC Constructors, INC. | 433945.75 | 0.9025 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405095A | 480000 | Chemical & WCCS B Side Project | l20 model [PROPOSAL STATUS FOR L20 AND L30] | CRG International | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2303001A | 479076.14 | F21P1 UPW | Liberty Scaffolding | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Scaffolding
Base-Build | Base-Build | Others | Housekeeping | USC21C012 | USCSB2304059A | 468465 | F21 Barcode RFID System | General labor and Housekeeping Service/Superintendent Service | Handy Technology Corp. | 468465 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Housekeeping
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2406058A | 467500 | WWT Change Order (Piping) | (A side)YAHO T&M A side work from 05/2024-07/2024 | YAHO System Technology Inc. | 430583.33 | 0.92103 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Others | Commissioning | USC21C009 | USCSB2304035A | 466583.7 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Activated carbon | Calgon Carbon Corporation | 355635.5 | 0.76221 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2402015A | 456000 | WWT Change Order (Piping) | WWT B side Geijinsin Lb1/L20 submain | Gejinsin Enterprise Co., Ltd. | 456000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2207008A | 454451 | F21P1 Chemical & WCCS package | Lorry Common Rack | Milling Machinery, Inc. | 454451 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Low Voltage | Electrical | M+L | USC22C001 | USCSB2307105A | 451916.72 | F21 P1 Office and WH Security and CCTV | F21 P1 CCTV Power Engineering | JB Group of LA, LLC dba Infrastructure Solutions Group | 451916.72 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Material
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2407148A | 451746.57 | WWT B side Project | WWT AWD(O3) system - Okland | Okland Construction Company, Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2406114A | 449679 | WWT B side Project | WWT: CCR System Scope | BMWC Constructors, INC. | 342119.7 | 0.76081 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2308023A | 440215 | WWT Change Order (Piping) | 8-120 WRC NaOH and H2SO4 WWT Chemical Lines | University Mechanical & Engineering Contractors, Inc. | 250923 | 0.57 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2212044A | 434494 | F21P1 Chemical & WCCS package | UB Box | Collabratech Solutions | 434494 | 1 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | Low Voltage | Electrical | M+L | USC21C008 | USCSB2306117A | 423140.27 | F21P1 CCTV & Security | F21 P1 CCTV & Fiber Engineering | Netcom Cabling, Inc | 401820.86 | 0.94962 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2307056A | 420929 | WWT Change Order (Piping) | TSMC UPW – 8-111 WWT WRC L20 Sludge Press System Piping | University Mechanical & Engineering Contractors, Inc. | 420928 | 1 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304046A | 418692.97 | F21P1 WWT package (Installation and 2 batch tanks) | Small pipe reinforcement | Harrington Industrial Plastics LLC | 418372.23 | 0.99923 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2302011A | 417086.58 | F21P1 UPW | WRC media loading | Process Service Specialists, LLC of Delaware | 417086.58 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | PSS
Base-Build | Low Voltage | Electrical | M+L | USC22C010 | USCSB2402051A | 415467.87 | F21 P1 LSC CMS and DPM 5G System | VOC Electric CO#5.6.9.10.12.13.14.15.16.20.22.24.26 | Spectra Electrical Services, Inc. | 415467.87 | 1 | Electrical | CO Scope (adding/additional scope) | Low Voltage | VOC | Labor
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2310148A | 414578 | WWT Change Order (Piping) | WWT-BMWC-Litho drain pipe-Train B | BMWC Constructors, INC. | 414578 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Electrical | M+L | USC23C045 | USCSB2309169A | 407681.85 | WWT Change Order (Piping) | F21 P1 WWT Electric Engineering-CCE | Commercial Comm and Electric Inc | 407681.85 | 1 | Electrical | DCR Scope | WWT | WWT | CCE
Base-Build | Low Voltage | Electrical | M+L | USC22C001 | USCSB2402050A | 405423.43 | F21 P1 Office and WH Security and CCTV | VOC Electric CO#7,8,18,19,21,27,29 | Spectra Electrical Services, Inc. | 405423.43 | 1 | Electrical | CO Scope (adding/additional scope) | Low Voltage | VOC | Labor
Base-Build | Low Voltage | Electrical | Material | USC21C007 | USCSB2308042A | 402952.8 | F21P1 VOC package （Installation ) | 250 MULTI CONDUCTOR (F21 P1 VOC2 and 7 wire order) | Consolidated Electrical Distributors Inc | 402952.8 | 1 | Electrical | DCR Scope | Low Voltage | VOC | Material
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2212051A | 402922.04 | F21P1 Chemical & WCCS package | PTFE Lined Pipe - change order | Southland Industries | 402922 | 1 | Mechanical | DCR Scope | CDS | Chemical | Southland
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406033A | 402666.49 | Chemical & WCCS B Side Project | F21P1 B Side material - PVDF /Ele | Harrington Industrial Plastics LLC | 383107.09 | 0.95143 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2212028A | 401347.41 | F21P1 WWT package (Installation and 2 batch tanks) | 2nd Set of Clamps | Process Service Specialists, LLC of Delaware | 362097.67 | 0.90221 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2210019A | 398400 | F21P1 WWT package (Installation and 2 batch tanks) | Material Coordinator/Superintendent(Tool Hookup Focus/Tool Hookup Focus Track/Tool Hookup Focus DUV) | Teo Services, Inc. DBA TEOPM | 398400 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Hookup | Base-Build | Outsourcing
Base-Build | Base-Build | Others | Housekeeping | USC21C008 | USCSB2303049A | 398270.74 | F21P1 CCTV & Security | Sunrise Phoenix housekeeping services | Sunrise Phoenix Hi-Tech LLC | 368432.5 | 0.92508 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Housekeeping
Base-Build | Low Voltage | Electrical | M+L | USC22C019 | USCSB2312199A | 396434 | AMC monitor 595T0 | F21 AMC B side Engineering Construction | NUUO US Inc. | 343287.3 | 0.86594 | Electrical | The budget execution does not pertain to this project | AMC THC | AMC THC | NUUO
Base-Build | UPW | Civil | M+L | USC24C008 | USCSB2408026A | 385531 | UPW B Side Project | MICU B Side Mezz#3 & #4 Partition Wall | Pride Development & Construction, Inc. | 0 | 0 | Civil |  |  | UPW
Base-Build | WWT | Electrical | M+L | USC21C014 | USCSB2308119A | 384750 | F21P1 WH2SO4 | W-H2SO4 Electrical Work | Hua Yi Construction AZ, Inc | 384750 | 1 | Electrical | Main Contract Scope | WWT | W-H2SO4 | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2306030A | 383185 | F21P1 Chemical & WCCS package | TSMC Offload | Milling Machinery, Inc. | 383185 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2301033A | 380441.05 | F21P1 UPW | Tank Painting | Phoenix House Painting.com LLC dba PHP Commercial Painting | 359334.87 | 0.94452 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C006 | USC2109012A | 379521.12 | F21P1 Slurry package | Diaphragm Valve | Arizona/Albuquerque Valve & Fitting Corp. | 379521.12 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | UPW | Electrical | Material | USC21C005 | USCSB2303082A | 375154.38 | F21P1 Chemical & WCCS package | UPW Panel design change (FUSE AND BREAKER) | Border State Industries, Inc. | 103710.44 | 0.27645 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406095A | 374081.95 | Chemical & WCCS B Side Project | F21P1 B Side Pillar - PFA | Nippon Pillar Corporation of America | 363567.55 | 0.97189 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Electrical | Labor | USC21C005 | USCSB2312166A | 370000 | F21P1 Chemical & WCCS package | CDS Chemical Electrical Power Distribution Engineering Technical Supervision Service | DFK Tech, LLC | 351500 | 0.95 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Others | Labor | USC21C005 | USCSB2406073A | 369824 | F21P1 Chemical & WCCS package | FAB A CO2 System Inspection(The 70% remaining) | Aidant Fire Protection | 129438 | 0.35 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | CDS | Chemical
Base-Build | Base-Build | Others | Site Expense | USC22C024 | USCSB2301055A | 367625.5 | UIS Scaffolding | Action scaffolding | Action Equip & Scaffold Co. Inc | 367625.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Scaffolding
Base-Build | WWT | Civil | M+L | USC23C045 | USCSB2309023A | 367375.96 | WWT Change Order (Piping) | Installation of FRP Membrane (LB2 A side) | OBR Cooling Towers, Inc. | 367375.96 | 1 | Civil | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | WWT | Others | Commissioning | USC24C006 | USCSB2405101A | 365512.5 | WWT B side Project | tsmc support Chemical (55gal/KuritaK0800/Catalase2xConcentrated) | Kurita America Inc | 307030.5 | 0.84 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2212017A | 364908.17 | F21P1 UPW | UPW 4C Wire & Disconnect Switch | Rosendin Electric, Inc. | 364908.16 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2207018A | 360000 | F21P1 WWT package （USA EQ-FRP tank) | WWT rigging and equipment move in | Milling Machinery, Inc. | 360000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | MIMO/Rigging
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309179A | 358306.67 | WWT Change Order (Piping) | WWT -Train A-PP/PVDF on hand | Harrington Industrial Plastics LLC | 358306.2 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2210012A | 355000 | F21P1 WWT package (Installation and 2 batch tanks) | F21P1 – WSR-S H2S04 Steel supports | Milling Machinery, Inc. | 355000 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | WWT | Mechanical | Material | USC22C023 | USCSB2210024A | 353593.12 | AZ GF Agru Material | GF PP&PVDF Material Mega union | Mega Union Technology Inc. | 353593.12 | 1 | Mechanical |  |  | GF Agru Material | Material
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2305058A | 349263.68 | F21P1 UPW | FAB Grounding | Rosendin Electric, Inc. | 331800.5 | 0.95 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | Chemical | Others | Labor | USC21C005 | USCSB2306081A | 348526.86 | F21P1 Chemical & WCCS package | Painting work from PHP T&M work scope (December 2022 to May 2023) | Phoenix House Painting.com LLC dba PHP Commercial Painting | 348526.86 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | CDS | Base-Build | Labor
Base-Build | Low Voltage | Electrical | M+L | USC22C001 | USCSB2202003A | 344373.73 | F21 P1 Office and WH Security and CCTV | CCTV Warehouse Building | Galaxy3 LLC | 344373.73 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Material
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2212040A | 341555.2 | F21P1 UPW | Network & Com | Rosendin Electric, Inc. | 317646.34 | 0.93 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | Low Voltage | Electrical | M+L | USC22C019 | USCSB2310175A | 341453.75 | AMC monitor 595T0 | F21 LITHO AMC Engineering | NUUO US Inc. | 341453.75 | 1 | Electrical | Main Contract Scope | Low Voltage | AMC THC | NUUO
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2211003A | 337906.32 | F21P1 WWT package (Installation and 2 batch tanks) | Tool Team PVD/CVD Project Coordinator/ Superintendent | Teo Services, Inc. DBA TEOPM | 324180.38 | 0.95938 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Hookup | Base-Build | Outsourcing
Base-Build | UPW | Mechanical | M+L | USC22C012 | USCSB2402268A | 337815 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | UPW-UMEC-2023-Dec-extend GC-1 | University Mechanical & Engineering Contractors, Inc. | 320924 | 0.95 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2303096A | 336392.16 | F21P1 Slurry package | F21P1 Slurry Instrument air | NUUO US Inc. | 320757.55 | 0.95352 | Mechanical | DCR Scope | SDS | Slurry | NUUO
Base-Build | Low Voltage | Electrical | M+L | USC22C013 | USCSB2401036A | 329646 | F21P1 QR Lab Security & CCTV | F21 CCTV Over Time and Interconnection | NUUO US Inc. | 329646 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | Low Voltage | Electrical | M+L | USC24C007 | USCSB2404066A | 329623.97 | Low Voltage B Side Project | F21 P1 B side CCTV Power system | NUUO US Inc. | 329623.97 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | UPW | Mechanical | Labor | USC23C014 | USCSB2306040A | 326375 | F21P1 Labor incentive program-MICU | UMEC-2022 labor and Veterans holiday | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2212039A | 325446.02 | F21P1 UPW | X1_Y Line Changes | Rosendin Electric, Inc. | 325436.01 | 0.99997 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Rosendin
Base-Build | Low Voltage | Electrical | Labor | USC22C013 | USCSB2311110A | 325000 | F21P1 QR Lab Security & CCTV | F21 CCTV Engineering | Hua Yi Construction AZ, Inc | 325000 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Material
Base-Build | Low Voltage | Electrical | M+L | USC21C013 | USCSB2310174A | 322460.69 | F21P1 AMC THC Monitoring System | F21 THC PTFE Engineering | NUUO US Inc. | 230830.47 | 0.71584 | Electrical | Main Contract Scope | Low Voltage | AMC THC | NUUO
Base-Build | WWT | Electrical | M+L | USC23C045 | USCSB2311014A | 315713.89 | WWT Change Order (Piping) | WWT CCE Change Orders | Commercial Comm and Electric Inc | 299928 | 0.95 | Electrical | DCR Scope | WWT | WWT | CCE
Base-Build | WWT | Others | QAQC | USC24C006 | USCSB2406050A | 309480 | WWT B side Project | FAB B WWT Observation and CA Service | M Consultants, LLC BDA M-Engineering | 109836 | 0.35491 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | Low Voltage | Mechanical | Housekeeping | USC21C007 | USCSB2304053A | 308247.04 | F21P1 VOC package （Installation ) | LOW NOX VOC Burner Change Out & Clean Harbor | Southland Industries | 308247.04 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | VOC | Southland
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2209033A | 308016.58 | F21P1 Chemical & WCCS package | Manifold Boxes | Pure Plastics, LLC | 305637.1 | 0.99227 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | UPW | Electrical | Material | USC21C003 | USC2109015A | 305828 | F21P1 UPW | tank,FRP | HORIBA Instruments Incorporated | 305828 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Electrical | M+L | USC22C010 | USCSB2208016A | 305397.2 | F21 P1 LSC CMS and DPM 5G System | F21P1 PDS Cabling and equipment installation | Commercial Comm and Electric Inc | 304827.48 | 0.99813 | Electrical | The budget execution does not pertain to this project | LV PDS | 5G | CCE
Base-Build | UPW | Mechanical | Labor | USC24C008 | USCSB2404150A | 305092 | UPW B Side Project | Outstanding Incentive Change Requests | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | Chemical | Mechanical | E2 | USC24C005 | USCSB2404155A | 304000 | Chemical & WCCS B Side Project | 信紘人力-點工人力(8人4個月) | Trusval Technology CO., LTD. | 152000 | 0.5 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2306089A | 303006.77 | F21 TMAH System | WWT-PSS-TrainA material | Harrington Industrial Plastics LLC | 303006.77 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | M+L | USC24C007 | USCSB2406076A | 300779 | Low Voltage B Side Project | F21-P1_B-SIDE CCTV & ACCESS (L20 HPM) | NUUO US Inc. | 0 | 0 | Electrical | Main Contract Scope | Low Voltage | CCTV
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2310081A | 300000 | WWT Change Order (Piping) | Taiwan experienced wrokers-help on WWT pipng fixed in FAB A site. | Gejinsin Enterprise Co., Ltd. | 300000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Electrical | Labor | USC21C011 | USCSB2402117A | 300000 | F21 TMAH System | 2000 Gold T&M-Labor 30days 10ppl | 2000 GOLD LLC | 29850 | 0.0995 | Electrical | Main Contract Scope | WWT | TMAH | Labor
Base-Build | Base-Build | Others | Housekeeping | USC21C006 | USCSB2211009A | 300000 | F21P1 Slurry package | F21 General Labor and Housekeeping Service | BHTC Arizona, LLC | 300000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Housekeeping
Base-Build | Low Voltage | Electrical | Labor | USC22C001 | USCSB2310107A | 300000 | F21 P1 Office and WH Security and CCTV | F21 CCTV Engineering | OE Electric | 300000 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Labor
Base-Build | Base-Build | Others | Housekeeping | USC21C003 | USCSB2205012A | 300000 | F21P1 UPW | General Laborer and Housekeeping Service | Sunrise Phoenix Hi-Tech LLC | 255464 | 0.85155 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Housekeeping
Base-Build | Base-Build | Others | Housekeeping | USC21C011 | USCSB2304045A | 300000 | F21 TMAH System | F21 General Labor and Housekeeping Service | Hua Yi Construction AZ, Inc | 300000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Housekeeping
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405058A | 299445.93 | WWT B side Project | WWT Drain PP_20240508 (B Side) | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2304078A | 298813.47 | F21P1 WWT package （USA EQ-FRP tank) | WWT Triazole tanks | Harrington Industrial Plastics LLC | 298813.47 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2303013A | 295810 | F21P1 WWT package （USA EQ-FRP tank) | CO for Alliance | Alliance Industrial Group, LLC | 295810 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Electrical | Labor | USC21C005 | USCSB2311140A | 295688.64 | F21P1 Chemical & WCCS package | CDS F21 Lorry A Solvent room Aegis/Co2 installation and inspection | DFK Tech, LLC | 280904.21 | 0.95 | Electrical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2308101A | 294133 | WWT Change Order (Piping) | TSMC UPW-8-127 WWT LB2 Chemical Piping-Group 2 | University Mechanical & Engineering Contractors, Inc. | 252955 | 0.86 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | WWT | Others | Site Expense | USC23C045 | USCSB2310169A | 294064 | WWT Change Order (Piping) | Material receiving, off-loading, laydown labor | Milling Machinery, Inc. | 294064 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | MMI
Base-Build | Chemical | Electrical | Labor | USC24C005 | USCSB2404142A | 294000 | Chemical & WCCS B Side Project | F21 B side L20 Tray安裝工程 | DFK Tech, LLC | 279300 | 0.95 | Electrical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Steel | M+L | USC22C022 | USCSB2306101A | 292297 | F21P1 Triazole treatment system | WWT Triazole steels and move-in | Milling Machinery, Inc. | 292297 | 1 | Steel | Main Contract Scope | WWT | Triazole | MIMO/Rigging
Base-Build | Low Voltage | Electrical | M+L | USC22C013 | USCSB2312193A | 292071.62 | F21P1 QR Lab Security & CCTV | F21 CCD Room Security CCTV Engineering | NUUO US Inc. | 292071.62 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406004A | 288643.18 | Chemical & WCCS B Side Project | 彰京SUS-0531 | GOLD STONE DEVELOPMENT CO., LTD. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2404023A | 288517 | Chemical & WCCS B Side Project | B-side L30 SDS scope | CRG International | 288517 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | CRG
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2303054A | 287100 | F21P1 Slurry package | Slurry L10 Model Change | KAEKO, Inc | 279960 | 0.97513 | Mechanical | DCR Scope | SDS | Base-Build | Labor
Base-Build | Chemical | Steel | Labor | USC21C009 | USCSB2312113A | 283945.4 | F21P1 WWT package (Installation and 2 batch tanks) | USC21C006 SLURRY B SIDE L30 bridge support | SDB, Inc. dba SDB Contracting Services | 283945.4 | 1 | Steel | 0 | 0 | Slurry | Labor
Base-Build | WWT | Mechanical | Labor | USC24C006 | USCSB2408020A | 283251.53 | WWT B side Project | T&M to have (達鑫)Daxin involve in A+B side punch fixed(2024/07/01~2024/12/31)(management fee and profit、Miscellaneous expenses | Daxin Energy Engineering Co., Ltd. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | E2 | USC21C009 | USCSB2404122A | 282500 | F21P1 WWT package (Installation and 2 batch tanks) | WWT pipe installation | Full Money Technology Ltd. | 148000 | 0.52389 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2303057A | 280793 | F21P1 UPW | Skid repair & membrane installtion | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | Main Contract Scope | UPW | UPW | UMEC
Base-Build | Chemical | Electrical | Material | USC21C005 | USC2111049A | 277255.58 | F21P1 Chemical & WCCS package | Valves for WCCS | Arizona/Albuquerque Valve & Fitting Corp. | 277255.58 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2404048A | 276676.69 | F21P1 WWT package (Installation and 2 batch tanks) | WWT_ FAB LB2 / WRC L10_Acid/Chemical Area Safety Paint | SD Engineering Technology LLC | 276676.69 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Electrical | M+L | USC22C022 | USCSB2402057A | 275000 | F21P1 Triazole treatment system | WWT-Triazole Electrical | 2000 GOLD LLC | 275000 | 1 | Electrical | Main Contract Scope | WWT | Triazole | Labor
Base-Build | Chemical | Others | Labor | USC21C005 | USCSB2406080A | 274320 | F21P1 Chemical & WCCS package | FAB CO2 System Permit and Inspection | Aidant Fire Protection | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | CDS | Chemical
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2109014A | 274050 | F21P1 Chemical & WCCS package | CDS Mechancial Work Pre-constru Indirect Labor | Harder Mechanical Contractors, Inc | 274050 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Harder
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2408166A | 274022.36 | Chemical & WCCS B Side Project | Proposal TSMC-015 @ ICP_MASS_Side B_ Total Boxes_CPVC_SUS_PFA_Support Installations_Side A. Paint_(Rev.1)_Batch 1/2 | CRG International | 0 | 0 | Mechanical |  |  | Chemical
Base-Build | Chemical | Others | QAQC | USC24C005 | USCSB2404183A | 272520 | Chemical & WCCS B Side Project | Chemical FAB A and Lorry CA and Observation | KAEKO, Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Chemical | Labor
Base-Build | Low Voltage | Electrical | M+L | USC21C007 | USCSB2305064A | 271432.4 | F21P1 VOC package （Installation ) | F21 VOC Low nox Electrical Work | NUUO US Inc. | 271432.4 | 1 | Electrical | Main Contract Scope | Low Voltage | VOC | NUUO
Base-Build | Chemical | Electrical | Labor | USC21C005 | USCSB2406129A | 269677 | F21P1 Chemical & WCCS package | 捨得人力-點工人力(13人 6-8月) | AUCAN INC | 0 | 0 | Electrical |  |  | Chemical
Base-Build | Chemical | Steel | Material | USC21C005 | USCSB2303088A | 269367 | F21P1 Chemical & WCCS package | L20 Unistruts Rack | Milling Machinery, Inc. | 269367 | 1 | Steel | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Others | QAQC | USC23C045 | USCSB2311069A | 269240 | WWT Change Order (Piping) | WWT-HYC air testing manpower | Hua Yi Construction AZ, Inc | 269240 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Electrical | Material | USC21C006 | USCSB2312123A | 266747.64 | F21P1 Slurry package | Urgent: CDS CED MIC A side 1 of 2 per Paul | Consolidated Electrical Distributors Inc | 266747.64 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Electrical | Labor | USC24C006 | USCSB2404114A | 263304.8 | WWT B side Project | MU11304N035-R1-MICU Area B E2 manpower support for electricity personnel | Mega Union Technology Inc. | 105703.52 | 0.40145 | Electrical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Others | QAQC | USC24C006 | USCSB2407108A | 262000 | WWT B side Project | WWT 3rd Party QAQC Services | Independent QA/QC Services Inc. | 101788 | 0.3885 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2403209A | 261357 | F21 TMAH System | WWT009_B 區機台租賃_Mega(8 month) | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Site Expense
Base-Build | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2308060A | 257361 | F21P1 VOC package （Installation ) | F21 P1 VOC Engineering | Southland Industries | 257361 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | VOC | Southland
Base-Build | WWT | Electrical | Labor | USC21C009 | USCSB2403026A | 255000 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Lorry CCB Fiber, Power, Control Pull & Termination | NUUO US Inc. | 255000 | 1 | Electrical | Main Contract Scope | WWT | WWT | NUUO
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2210050A | 254247.61 | F21P1 Slurry package | L30 Raised Floor Pipe Channel | SDB, Inc. dba SDB Contracting Services | 254247.61 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | WWT | Others | QAQC | USC23C045 | USCSB2404176A | 254073 | WWT Change Order (Piping) | WWT-A side EOR CA service for WRC and FAB | Page Southerland Page, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | UPW | Civil | Material | USC21C003 | USCSB2310106A | 250000 | F21P1 UPW | construction of shaft wall on Mezzanine 1and 2 | Performance Contracting Inc | 117163.87 | 0.46866 | Civil | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207021A | 250000 | F21P1 UPW | Painting | Phoenix House Painting.com LLC dba PHP Commercial Painting | 250000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Other Scope
Base-Build | WWT | Mechanical | M+L | USC22C020 | USCSB2210014A | 249618 | F21P1 Penetration Pipe | FAB L10, L20 HPM Drain Piping Penetration | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | Penetration Pipe | UMEC
Base-Build | UPW | Electrical | Material | USC21C003 | USC2111027A | 249454.5 | F21P1 UPW | dissolved oxygen analyzers, Silica Analyzers | Hach Company | 249454.5 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Electrical | M+L | USC22C001 | USCSB2401075A | 248169.53 | F21 P1 Office and WH Security and CCTV | F21 CCTV Engineering | NUUO US Inc. | 208731.91 | 0.84109 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2309098A | 247266 | F21P1 UPW | TSMC Fab 21 Phase Construction Administration Services | Page Southerland Page, Inc. | 222694 | 0.90063 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | UPW | Base-Build | Labor
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2404201A | 245895 | WWT B side Project | WWT - LSR(I)(A side) | University Mechanical & Engineering Contractors, Inc. | 233600 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2205006A | 242719 | F21P1 WWT package (Installation and 2 batch tanks) | SUNDT ICW Tank Piping | Sundt Construction, Inc | 242719 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Water_Sewer | Civil | M+L | USC21C003 | USCSB2203015A | 239659.84 | F21P1 UPW | TSMC Water Frontage Main & 43rd Avenue Sewer Line Extension | Degan Construction LLC | 239659.84 | 1 | Civil | The budget execution does not pertain to this project | Pipeline | UPW | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2202007A | 236820.52 | F21P1 WWT package (Installation and 2 batch tanks) | CS Tank changed order work | Alliance Industrial Group, LLC | 189638.7 | 0.80077 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2307129A | 234226 | F21P1 Chemical & WCCS package | Fall Protection System at Lorry | Milling Machinery, Inc. | 234226 | 1 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | MMI
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2404190A | 234118.03 | WWT B side Project | WWT - B-Side CS Tank FRP Flange Coating and Spool Interconnections | BRAHMA GROUP, INC. | 233935.16 | 0.99922 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Others | Site Expense | USC21C003 | USCSB2211025A | 230320 | F21P1 UPW | X line Temp Power RFQ 11_16 | Commercial Comm and Electric Inc | 230320 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | UPW | CCE
Base-Build | Low Voltage | Mechanical | Material | USC21C013 | USCSB2110007A | 230000 | F21P1 AMC THC Monitoring System | 帆宣_tsmc F21P1 轉輪中THC建置六點 | Weltall Technology Corporation | 207000 | 0.9 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Equipment
Base-Build | Low Voltage | Electrical | M+L | USC22C013 | USCSB2402055A | 229358 | F21P1 QR Lab Security & CCTV | VOC Extending General Conditions(CO # 31) | Spectra Electrical Services, Inc. | 229358 | 1 | Electrical | The budget execution does not pertain to this project | VOC | VOC | Labor
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2306012A | 227783.78 | F21P1 Chemical & WCCS package | Flame arresters | Caltrol Inc. | 227783.78 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2307091A | 226927 | WWT Change Order (Piping) | 8-115 WWT & Reclaim System Chemical Scope | University Mechanical & Engineering Contractors, Inc. | 197428 | 0.87001 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304065A | 226738.04 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Lab Drain design-MU | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2308157A | 225843 | F21P1 VOC package （Installation ) | F21 P1 VOC Change Order (southland)_1 | Southland Industries | 225843 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | VOC | Southland
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2312170A | 225633 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Train B FRP | OBR Cooling Towers, Inc. | 135379.8 | 0.6 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2406071A | 225468.02 | Chemical & WCCS B Side Project | Chemical Team Urgent Materials Wire First Priority (化學系統控制線材0611第一優先級購買) | Consolidated Electrical Distributors Inc | 101962.42 | 0.45223 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2303055A | 224570 | F21P1 WWT package (Installation and 2 batch tanks) | CCB DCR piping | University Mechanical & Engineering Contractors, Inc. | 213342 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2311051A | 224158 | F21P1 Chemical & WCCS package | CDS B side support Racks LB2/L30 | Milling Machinery, Inc. | 224158 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Civil | M+L | USC21C003 | USCSB2211021A | 223915 | F21P1 UPW | Litho Embedded Pipes installation | Process Service Specialists, LLC of Delaware | 210793.75 | 0.9414 | Civil | The budget execution does not pertain to this project | Penetration Pipe | UPW | PSS
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2312044A | 223520 | F21P1 Slurry package | CDS CO2 System, Lorry A, certify design and test. | Aidant Fire Protection | 201168 | 0.9 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | Low Voltage | Mechanical | M+L | USC22C009 | USCSB2206015A | 223292 | F21P1 230kV MTR Oil and Drain Pipe work | F21P1 230kV MTR waste oil drain pipe | Sundt Construction, Inc | 212039.37 | 0.94961 | Mechanical | Main Contract Scope | Low Voltage | Oil drain pipe work | Labor
Base-Build | UPW | Civil | M+L | USC21C003 | USCSB2209019A | 222645 | F21P1 UPW | CWS-TSMC AZ Phase 1 | Commercial Wallboard Systems, Inc | 166473.9 | 0.74771 | Civil | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405171A | 222472.89 | Chemical & WCCS B Side Project | Extremely Urgent_RFQ_MICU Chemical Team Request Material_05232024-1 | NEFCO Construction Supply LLC | 221641.52 | 0.99626 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2402031A | 220941 | F21P1 Chemical & WCCS package | CDS TSMC UPW 8-177 NH4 TMAH | University Mechanical & Engineering Contractors, Inc. | 220941 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | UMEC
Base-Build | Chemical | Electrical | Labor | USC21C005 | USCSB2403242A | 220800 | F21P1 Chemical & WCCS package | CDS Leakage detection tape installation | DFK Tech, LLC | 0 | 0 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2205029A | 220448.25 | F21P1 UPW | Hard support for electrical scope | Rosendin Electric, Inc. | 220447.85 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2303059A | 220244 | F21P1 WWT package (Installation and 2 batch tanks) | IA copper tubing | University Mechanical & Engineering Contractors, Inc. | 209230 | 0.94999 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | Base-Build | Others | Housekeeping | USC21C009 | USCSB2206011A | 220000 | F21P1 WWT package (Installation and 2 batch tanks) | Safety Coordinators and Site Cleanup | CGS Global Support, LLC | 219648.49 | 0.9984 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Housekeeping
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2211007A | 211094.27 | F21P1 WWT package (Installation and 2 batch tanks) | Lorry Bridge brackets Fabrication | Process Service Specialists, LLC of Delaware | 211094.27 | 1 | Steel | Main Contract Scope | WWT | WWT | PSS
Base-Build | Chemical | Electrical | E2 | USC24C005 | USCSB2404157A | 208000 | Chemical & WCCS B Side Project | 捨得人力-點工人力(13人/2個月) | AUCAN INC | 208000 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C001 | USCSB2205015A | 207173 | F21 P1 Office and WH Security and CCTV | F21 Warehouse CCTV equipment | Aegis Technology Inc | 189878 | 0.91652 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | WWT | Electrical | Instrument | USC21C009 | USCSB2211004A | 203447.19 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Discharge box adding | Mega Union Technology Inc. | 0 | 0 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2305059A | 200218.1 | F21P1 UPW | WRC Grounding | Rosendin Electric, Inc. | 200218.1 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | UPW | Civil | M+L | USC22C021 | USCSB2403160A | 200050.78 | F21P1 Chemical Lab setup | UPW-Mezzanine 3 & 4 Epoxy Floor Coating-Degan | Degan Construction LLC | 200050.78 | 1 | Civil | Main Contract Scope | UPW | UPW | Equipment
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2204009A | 200000 | F21P1 UPW | TSMC F21 AZ Structure Design and PE Stamp | SYNERGY Engineering Consultants | 95880 | 0.4794 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Labor
Base-Build | UPW | Steel | Project Outsourcing (專案管理外包人力) | USC22C006 | USCSB2205018A | 200000 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | TSMC F21 AZ Structure Design and PE Stamp | SYNERGY Engineering Consultants | 154000 | 0.77 | Steel |  | UPW | Base-Build | Outsourcing
Base-Build | Low Voltage | Electrical | Labor | USC21C011 | USCSB2310069A | 200000 | F21 TMAH System | F21 P1 CCTV Engineering | OE Electric | 200000 | 1 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | Labor
Base-Build | Low Voltage | Electrical | Labor | USC21C008 | USCSB2308115A | 200000 | F21P1 CCTV & Security | F21 P1 CCTV Engineering | OE Electric | 200000 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Labor
Base-Build | Low Voltage | Electrical | Labor | USC21C007 | USCSB2110002A | 199950 | F21P1 VOC package （Installation ) | Pre-construction | Spectra Electrical Services, Inc. | 199950 | 1 | Electrical | Main Contract Scope | Low Voltage | VOC | Labor
Base-Build | WWT | Electrical | M+L | USC21C009 | USCSB2307133A | 199820.95 | F21P1 WWT package (Installation and 2 batch tanks) | F21 P1 WWT Electric Engineering | Commercial Comm and Electric Inc | 199820.95 | 1 | Electrical | DCR Scope | WWT | WWT | CCE
Base-Build | Chemical | Electrical | Material | USC21C009 | USCSB2312192A | 199528.6 | F21P1 WWT package (Installation and 2 batch tanks) | CDS chemical electric materials | NUUO US Inc. | 199528.6 | 1 | Electrical | 0 | 0 | Chemical | NUUO
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2406031A | 199098.22 | F21P1 Slurry package | F21P1 B Side material Harrington - CPVC fitting | Harrington Industrial Plastics LLC | 199098.22 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Low Voltage | Electrical | M+L | USC21C012 | USC2111010A | 198808.09 | F21 Barcode RFID System | Barcode 系統網路設備 | Galaxy3 LLC | 198808.09 | 1 | Electrical | Main Contract Scope | Low Voltage | Barcode | Material
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2404189A | 198642 | WWT B side Project | WWT - Install (166) Embedded Pipe on B-Side for Litho Drains | BMWC Constructors, INC. | 188709.9 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | Low Voltage | Mechanical | Labor | USC24C007 | USCSB2406126A | 196000 | Low Voltage B Side Project | F21-P1_B-Side mask room gas piping hookup_batch 1/2 | Welmade Technology Corporation | 0 | 0 | Mechanical |  |  | VOC
Base-Build | WWT | Mechanical | Site Expense | USC24C006 | USCSB2403302A | 195000 | WWT B side Project | (B side)WWT Widos Welding Machine_20240329 | Widos Taiwan Ltd. | 195000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Site Expense
Base-Build | Low Voltage | Electrical | M+L | USC21C013 | USCSB2402137A | 194291 | F21P1 AMC THC Monitoring System | F21 EBO AMC Engineering | NUUO US Inc. | 162451.45 | 0.83612 | Electrical | Main Contract Scope | Low Voltage | AMC THC | NUUO
Base-Build | Chemical | Electrical | Labor | USC21C006 | USCSB2401233A | 192691.19 | F21P1 Slurry package | CDS OE electrical work | OE Electric | 192691.19 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2205025A | 192000 | F21P1 WWT package (Installation and 2 batch tanks) | Outsourcing (area superintendent) | Teo Services, Inc. DBA TEOPM | 192000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2208015A | 190627.32 | F21P1 UPW | UPW 500 MCM Cable | Consolidated Electrical Distributors Inc | 190626.69 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2308113A | 188856 | F21P1 WWT package (Installation and 2 batch tanks) | Field Observation for WRC WWT | Page Southerland Page, Inc. | 56656.8 | 0.3 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2211008A | 187120.14 | F21P1 WWT package (Installation and 2 batch tanks) | 4 Trips Plainview, TX | Process Service Specialists, LLC of Delaware | 187120.14 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403158A | 183635.46 | F21P1 WWT package (Installation and 2 batch tanks) | RFQ_Struts & Accessories_Copper State_B side_20240306 | Copper State Bolt & Nut Company | 183635.46 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC24C008 | USCSB2405031A | 183582 | UPW B Side Project | UPW Foxboro A2U | Engineered Process Controls, LLC | 36716.4 | 0.2 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2209020A | 182400 | F21P1 WWT package (Installation and 2 batch tanks) | Logistics coordinator/superintendent(took Hookup focus) | Teo Services, Inc. DBA TEOPM | 182395.11 | 0.99997 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Hookup | Base-Build | Outsourcing
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2407072A | 182350 | WWT B side Project | LB-1 Sump Pump Piping - Train A/Train B_WWT UMEC scope | University Mechanical & Engineering Contractors, Inc. | 126551 | 0.694 | Mechanical |  |  | WWT
Base-Build | WWT | Others | Commissioning | USC21C009 | USCSB2210033A | 180187.87 | F21P1 WWT package (Installation and 2 batch tanks) | commissioning chemical purchase | Univar Solutions USA Inc. | 176384.38 | 0.97889 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Material | USC21C006 | USCSB2210016A | 179999.59 | F21P1 Slurry package | CED Wire | Consolidated Electrical Distributors Inc | 179999.59 | 1 | Electrical | Main Contract Scope | SDS | Slurry | Material
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2310129A | 179876.5 | WWT Change Order (Piping) | WWT FAB/WWT Valves | Mega Union Technology Inc. | 157439.9 | 0.87527 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Material | USC22C013 | USCSB2403233A | 179837.71 | F21P1 QR Lab Security & CCTV | VOC/ B side + control and power wire. | Independent Electric Supply, Inc. | 179837.71 | 1 | Electrical | The budget execution does not pertain to this project | VOC | VOC | Material
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309092A | 179759.08 | WWT Change Order (Piping) | WWT 20% Fab materials for FAB A side | Harrington Industrial Plastics LLC | 179736.08 | 0.99987 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2212049A | 178255 | F21P1 Chemical & WCCS package | F21P1 MIC CDS Plastic Box | Marketech International Corp. | 0 | 0 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | WWT | Others | QAQC | USC23C045 | USCSB2402253A | 178114 | WWT Change Order (Piping) | WWT line leak check T&M work | United Integrated Services (USA) Corp | 178114 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | M+L | USC22C022 | USCSB2312161A | 176243 | F21P1 Triazole treatment system | Chem Pkg 3 WWT Estimate | University Mechanical & Engineering Contractors, Inc. | 167432 | 0.95001 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | Chemical | Mechanical | E2 | USC24C005 | USCSB2405180A | 176000 | Chemical & WCCS B Side Project | [上禾] MICU E2 支援報價單(8人*4 month) | SHANG-HE project company | 11000 | 0.0625 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2406010A | 172999.41 | F21P1 Slurry package | F21P1 IES- Cable Tray B side | Independent Electric Supply, Inc. | 158001.38 | 0.91331 | Mechanical | Main Contract Scope | SDS | Slurry
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2307112A | 172800 | F21P1 Chemical & WCCS package | TSMC Offload July | Milling Machinery, Inc. | 172800 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2308059A | 172111.26 | F21P1 UPW | 500 MCM B Side | Consolidated Electrical Distributors Inc | 172111.26 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | UPW | Civil | M+L | USC21C003 | USCSB2211010A | 171436.4 | F21P1 UPW | WRC control room raised floor | Brycon Corporation | 171436.4 | 1 | Civil | Main Contract Scope | UPW | UPW | Labor
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2112002A | 171351.52 | F21 TMAH System | TMAH Mechanical | Lasco Process Systems, LLC. | 171351.52 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | LPS
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2401114A | 171181.6 | F21P1 Chemical & WCCS package | SDS slurry electrical labor and materials | NUUO US Inc. | 162122.52 | 0.94708 | Mechanical | Main Contract Scope | SDS | Slurry | NUUO
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2212001A | 170580.48 | F21P1 UPW | UPW BIM Modeling of Conduit | Rosendin Electric, Inc. | 170580.48 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2405185A | 170226.91 | Chemical & WCCS B Side Project | F21P1 B side Electrical Materials Purchasing | Independent Electric Supply, Inc. | 170226.91 | 1 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2203003A | 169587.62 | F21P1 Chemical & WCCS package | VMB rack | Pure Plastics, LLC | 169587.61 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | UPW | Civil | M+L | USC21C003 | USCSB2208009A | 169260 | F21P1 UPW | Drill and Epoxy Rebar Hooks for Curb Based on Detail Provided | Degan Construction LLC | 130732.31 | 0.77238 | Civil | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2310140A | 167400 | WWT Change Order (Piping) | MU/Hand welding machines for WWT | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2309138A | 166473 | F21P1 UPW | UPW-CO-trade damage repair | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | Main Contract Scope | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | Labor | USC24C006 | USCSB2406099A | 166400 | WWT B side Project | B side/A side punch fix team (Yi Sheng) | YI-SHENG engineering Co.,Ltd | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2307007A | 165672 | F21 TMAH System | WWT-weld machine rental for PSS | Harrington Industrial Plastics LLC | 159385.82 | 0.96206 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Labor | USC21C005 | USCSB2402060A | 165474 | F21P1 Chemical & WCCS package | CDS Lorry A Add pressure detector piping | DFK Tech, LLC | 157200.3 | 0.95 | Electrical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2311106A | 164620 | F21P1 UPW | FAB B UPW Electrical Permit and CA service | LSW Engineers Arizona, Inc. | 118684 | 0.72096 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2305070A | 161517.16 | F21P1 Chemical & WCCS package | TSMC F21 Solvent room vent | Marketech International Corp. | 112072.33 | 0.69387 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303099A | 161360.62 | F21P1 WWT package (Installation and 2 batch tanks) | 20% bulk order - rush order | Harrington Industrial Plastics LLC | 158411.19 | 0.98172 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406096A | 160828 | Chemical & WCCS B Side Project | F21P1 B side 彰京 - PFA | GOLD STONE DEVELOPMENT CO., LTD. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C013 | USCSB2311144A | 160060 | F21P1 AMC THC Monitoring System | F21 THC B side Equipment | Welmade Technology Corporation | 160060 | 1 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Equipment
Base-Build | UPW | Steel | Project Outsourcing (專案管理外包人力) | USC22C006 | USCSB2209018A | 160000 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | TSMC AZ F21P2 EUV crane structural calculation/design/PE stamp | SYNERGY Engineering Consultants | 160000 | 1 | Steel |  | UPW | Base-Build | Outsourcing
Base-Build | Chemical | Mechanical | Material | USC21C006 | USC2204011A | 159571.38 | F21P1 Slurry package | Diaphragm Valve | Arizona/Albuquerque Valve & Fitting Corp. | 159571.38 | 1 | Mechanical | The budget execution does not pertain to this project | Chemical | UPW | Material
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2408162A | 158181.57 | F21P1 Chemical & WCCS package | REVISED VARTEAGA Invoice No. MICU-010 @ T^0M WORK_CDS L10_L20_L30 Cleanroom CPVC_SS_PFA Chemical System Tubes_ Batch 1/3 | CRG International | 0 | 0 | Mechanical |  |  | Chemical
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2206014A | 155528.35 | F21P1 UPW | UPW tray model | Rosendin Electric, Inc. | 155528.35 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | Low Voltage | Electrical | M+L | USC21C007 | USCSB2204012A | 154671 | F21P1 VOC package （Installation ) | Change Order (for VOC Cable Tray) | Spectra Electrical Services, Inc. | 154671 | 1 | Electrical | CO Scope (adding/additional scope) | Low Voltage | VOC | Labor
Base-Build | UPW | Electrical | M+L | USC22C010 | USCSB2303080A | 153140 | F21 P1 LSC CMS and DPM 5G System | UPW Temporary Power | MMR Constructors, Inc. | 69046.08 | 0.45087 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Site Expense
Base-Build | WWT | Steel | Labor | USC24C006 | USCSB2406067A | 151835 | WWT B side Project | (A side) Support _Hua Yi close PR_ batch 2/2 | Mirador Construction Service, LLC | 0 | 0 | Steel | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USC2112014A | 151360 | F21P1 Slurry package | VMBs for slurry, Valve housing | FusionHPX LLC | 67813.84 | 0.44803 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2402107A | 150625 | F21P1 Slurry package | CDS TSMC 8-181 CUSO4, COSO4, H3PO4 | University Mechanical & Engineering Contractors, Inc. | 150625 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | UMEC
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2402270A | 149419 | WWT Change Order (Piping) | WWT - BMWC L15 Ceiling Work CO | BMWC Constructors, INC. | 121219.15 | 0.81127 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Civil | Labor | USC23C045 | USCSB2310048A | 146485 | WWT Change Order (Piping) | Core Drill In Various Areas | Degan Construction LLC | 146485 | 1 | Civil | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2302040A | 144491 | F21P1 Slurry package | Slurry L10 Model Change | Southland Industries | 144491 | 1 | Mechanical | DCR Scope | SDS | Slurry | Southland
Base-Build | Chemical | Steel | Labor | USC21C005 | USCSB2406131A | 142512.8 | F21P1 Chemical & WCCS package | TSMC / FAB21: SIDE A H202 ROOM ADDITIONAL SUPPORTS | CRG International | 0 | 0 | Steel |  |  | Chemical | CRG
Base-Build | WWT | Mechanical | Instrument | USC21C011 | USCSB2306109A | 141500 | F21 TMAH System | WWT-chemical enclosure | Scenic Industries, LLC | 127350 | 0.9 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | M+L | USC22C013 | USCSB2404051A | 140156 | F21P1 QR Lab Security & CCTV | F21-P1_B-SIDE CCTV & ACCESS Fiber splicing and panel to panel Inner connection | NUUO US Inc. | 136703.2 | 0.97536 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2403104A | 139678 | F21P1 WWT package (Installation and 2 batch tanks) | [B side][Manpower-MU] 協益/1month | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Civil | M+L | USC21C003 | USCSB2302012A | 138900 | F21P1 UPW | Chemical enclosures installation | Scenic Industries, LLC | 138900 | 1 | Civil | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2212004A | 137912 | F21P1 WWT package (Installation and 2 batch tanks) | Alliance - trucking cost | Alliance Industrial Group, LLC | 137912 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Housekeeping | USC24C010 | USC2408016A | 137766.06 | General Conditions B Side Project | Base build-CGS 3&4 opening invoices | CGS Global Support, LLC | 137766.06 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | General Condition | Housekeeping
Base-Build | WWT | Mechanical | Commissioning | USC21C009 | USCSB2212037A | 137212 | F21P1 WWT package (Installation and 2 batch tanks) | WWT- Na2SO3-Formaldehyde | Mega Union Technology Inc. | 137212 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404196A | 137159.87 | WWT B side Project | WWT PVC_PVDF FittingsPipes (B Side)_20240424 | Harrington Industrial Plastics LLC | 137159.87 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Others | QAQC | USC22C001 | USCSB2305071A | 135180 | F21 P1 Office and WH Security and CCTV | TSMC F21P1 Site Security Electronics Permit Assistance | LSW Engineers Arizona, Inc. | 135180 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | CCTV | Labor
Base-Build | UPW | Electrical | Material | USC21C003 | USC2111038A | 133903.8 | F21P1 UPW | electromagnetic flowmeter,pressure transmitter | Azbil North America, Inc. | 133903.8 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405179A | 132742.51 | Chemical & WCCS B Side Project | CHEM_ Ryan Herco Flow Solutions_ CDS/ SDS/ WCCS_ L10/L20_ PVDV+CPVC+PP | Ryan Herco Flow Solutions | 125622.62 | 0.94636 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2406137A | 132224 | WWT B side Project | WRC SS Bypass(UPW SUS fix bypass only) | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404215A | 131920.9 | WWT B side Project | WWT the Drain Remaining Pipes_20240426 (B Side) | Harrington Industrial Plastics LLC | 131920.9 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | M+L | USC21C011 | USCSB2307051A | 131687 | F21 TMAH System | Lamella Installation | Milling Machinery, Inc. | 131687 | 1 | Steel | Main Contract Scope | WWT | TMAH | MMI
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2305103A | 131403 | F21P1 UPW | UPW CO-Distribution | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Others |  | USC24C006 | USCSB2409023A | 131065 | WWT B side Project | MU E2 manpower support for 6 people_B 區suction + A side NaOH 管路 |  | 0 | 0 |  |  |  | WWT
Base-Build | WWT | Steel | Labor | USC21C009 | USCSB2206025A | 130410.27 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Pipe Rack | Lasco Process Systems, LLC. | 130410.27 | 1 | Steel | Main Contract Scope | WWT | WWT | LPS
Base-Build | Low Voltage | Electrical | Labor | USC21C007 | USCSB2209009A | 130000 | F21P1 VOC package （Installation ) | MIC-TSMC-F21P1- VOC DCS SCADA | ACME Control System Corporation | 117000 | 0.9 | Electrical | Main Contract Scope | Low Voltage | VOC | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2204010A | 129799.8 | F21P1 UPW | Project Management Software | Procore Technologies, Inc. | 129799.8 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | Chemical | Mechanical | M+L | USC22C021 | USCSB2307006A | 128754 | F21P1 Chemical Lab setup | 8-66 FAB Gas Chem Lab Hook-Up(GC Lab Piping) | University Mechanical & Engineering Contractors, Inc. | 122317 | 0.95001 | Mechanical | The budget execution does not pertain to this project | Chemical Lab | Chemical Lab | UMEC
Base-Build | Low Voltage | Electrical | M+L | USC21C013 | USCSB2409014A | 128026.61 | F21P1 AMC THC Monitoring System | F21 P1 VOC Electricity Change Order _CO#30_Batch 1/2 | Spectra Electrical Services, Inc. | 82077.61 | 0.6411 | Electrical |  |  | VOC
Base-Build | WWT | Electrical | M+L | USC21C009 | USCSB2312062A | 126710.89 | F21P1 WWT package (Installation and 2 batch tanks) | WWT_CCE CO58 stripper disconnect switch and CO35 RIO Conduit. | Commercial Comm and Electric Inc | 120375.33 | 0.95 | Electrical | DCR Scope | WWT | WWT | CCE
Base-Build | WWT | Others | Commissioning | USC21C003 | USCSB2308155A | 126010 | F21P1 UPW | WWT Testing support | Jettech System Technology Co., Ltd. | 126010 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Labor
Base-Build | Base-Build | Others | Housekeeping | USC23C002 | USC2309041A | 124800 | F21P1-0404_H_Hallway plate install_MICU | Manpower Pay for General Labor for Elsa Nieto | Hua Yi Construction AZ, Inc | 124800 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Housekeeping
Base-Build | Base-Build | Others | Housekeeping | USC23C056 | USCSB2406019A | 122000 | Fab LB2 Trench Cleaning | B side housekeeping(Open PO) |  | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Housekeeping
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2301011A | 121205 | F21P1 WWT package (Installation and 2 batch tanks) | Minor Works CCB-MU | Mega Union Technology Inc. | 68285.93 | 0.56339 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Labor | USC21C012 | USCSB2402267A | 121128 | F21 Barcode RFID System | UPW-UMEC-2023-Dec-extend GC-2 | University Mechanical & Engineering Contractors, Inc. | 115072 | 0.95 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2311111A | 120982.1 | F21P1 QR Lab Security & CCTV | F21 CCD room CCTV & Security Equipment | Aegis Technology Inc | 101562 | 0.83948 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | Low Voltage | Electrical | Labor | USC24C007 | USCSB2405125A | 120057 | Low Voltage B Side Project | F21 P1 VOC system extension GC (JAN.FEB.MAR.APR/2024) | Spectra Electrical Services, Inc. | 120057 | 1 | Electrical | The budget execution does not pertain to this project | VOC | VOC
Base-Build | WWT | Mechanical | Labor | USC22C022 | USCSB2404001A | 119850 | F21P1 Triazole treatment system | WWT - Marquis Carbon Media loading #2 | Marquis Construction Services LLC | 36675 | 0.30601 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Electrical | Material | USC22C013 | USCSB2312003A | 119370.32 | F21P1 QR Lab Security & CCTV | CDS CED DFK Lorry HPM materials | Consolidated Electrical Distributors Inc | 119370.32 | 1 | Electrical | 0 | 0 | Chemical | Material
Base-Build | Low Voltage | Electrical | M+L | USC22C013 | USCSB2409008A | 118515.2 | F21P1 QR Lab Security & CCTV | F21 P1 VOC Electricity Change Order _CO#25_Batch 1/6 | Spectra Electrical Services, Inc. | 118515.2 | 1 | Electrical |  |  | CCTV
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2202009A | 117484 | F21P1 UPW | FRP Tank Changed Order Work | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC21C003 | USCSB2302043A | 117147.53 | F21P1 UPW | LPS RH materials #1 | Ryan Herco Flow Solutions | 117147.53 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C006 | USCSB2308137A | 116678.45 | F21P1 Slurry package | Liberty May 01 | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 116678.45 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Scaffolding
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309176A | 115575.35 | WWT Change Order (Piping) | WWT -Train A-PVC materials | Harrington Industrial Plastics LLC | 115575.35 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C007 | USCSB2308138A | 115322.66 | F21P1 VOC package （Installation ) | Liberty May 02 | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 115322.66 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Scaffolding
Base-Build | Base-Build | Others | Housekeeping | USC23C040 | USCSB2305101A | 115269.06 | TSMC F21 Clean Room Suit | Open PO for Clean Room Suits | Sunrise Phoenix Hi-Tech LLC | 115269.06 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Housekeeping
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309126A | 114768.28 | WWT Change Order (Piping) | TW W1 material 2nd Order | Harrington Industrial Plastics LLC | 114768.28 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2405181A | 114079 | WWT B side Project | WWT - (166) L20 Litho B Side Embedded Pipe Sealing | Greenberry Industrial | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2210008A | 113273.07 | F21P1 UPW | UPW A Side Disconnect Switch Change Order | Rosendin Electric, Inc. | 113273.07 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | UPW | Others | Labor | USC23C054 | USCSB2404177A | 112800 | UPW Change Order | UPW-B side CA/observation service | M Consultants, LLC BDA M-Engineering | 65708 | 0.58252 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Labor
Base-Build | WWT | Electrical | Instrument | USC21C009 | USC2112019A | 112714.39 | F21P1 WWT package (Installation and 2 batch tanks) | Copper, free chlorine, and turbidity analyzers. | Hach Company | 103659.72 | 0.91967 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2312005A | 112500 | WWT Change Order (Piping) | WWT -Stripper-2"packing -Harrington | Harrington Industrial Plastics LLC | 112500 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2301032A | 112011 | F21P1 UPW | LB2-Area A-ACF media loading | Hua Yi Construction AZ, Inc | 112011 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Electrical | Site Expense | USC21C009 | USCSB2209017A | 112010.28 | F21P1 WWT package (Installation and 2 batch tanks) | site Temp power from UIS panel to sub work area | Commercial Comm and Electric Inc | 112010.28 | 1 | Electrical | CO Scope (adding/additional scope) | WWT | Base-Build | CCE
Base-Build | UPW | Mechanical | M+L | USC23C054 | USCSB2401176A | 110074 | UPW Change Order | UPW-UMEC-T&M tickets | University Mechanical & Engineering Contractors, Inc. | 110074 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | Labor | USC24C006 | USCSB2407109A | 110000 | WWT B side Project | WWT_Drain pipeline construction under MU_3weeks | Mega Union Technology Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | UPW | Electrical | Material | USC21C003 | USC2111003A | 109847.32 | F21P1 UPW | Conductivity Meter | Harrington Industrial Plastics LLC | 100398.95 | 0.91399 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2301025A | 109698 | F21P1 WWT package (Installation and 2 batch tanks) | CO Sticker Installation | Process Service Specialists, LLC of Delaware | 85788.6 | 0.78204 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Electrical | M+L | USC21C009 | USCSB2405036A | 109566.81 | F21P1 WWT package (Installation and 2 batch tanks) | Triazole Change Order | 2000 GOLD LLC | 109566.81 | 1 | Electrical | Main Contract Scope | WWT | Triazole | Labor
Base-Build | Chemical | Mechanical | Material | USC21C006 | USC2201006A | 108438.09 | F21P1 Slurry package | Ball Valve, pressure regulating, Diaphragm Valve | Ryan Herco Flow Solutions | 108437.73 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | WWT | Civil | M+L | USC23C045 | USCSB2308005A | 108141 | WWT Change Order (Piping) | Mezzanine Epoxy Coatings (WWT -mezz 4 epoxy) | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 108141 | 1 | Civil | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | Low Voltage | Mechanical | M+L | USC22C010 | USCSB2308158A | 107443 | F21 P1 LSC CMS and DPM 5G System | F21 P1 VOC Change Order(southland)_2 | Southland Industries | 107443 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | VOC | Southland
Base-Build | WWT | Civil | M+L | USC23C045 | USCSB2309058A | 107400 | WWT Change Order (Piping) | Epoxy Pump Pads and Vibration Pads(FAB LB2 and WRC L10) | Degan Construction LLC | 107400 | 1 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2309142A | 106561.5 | F21P1 Chemical & WCCS package | Chemical VMB boxes for Fab B Side of the CDS system. | FusionHPX LLC | 106561.5 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2306016A | 106082.4 | F21P1 WWT package (Installation and 2 batch tanks) | TIG 3rd party inspections | Technical Inspections Group | 106082.4 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | Base-Build | Others | Housekeeping | USC22C031 | USCSB2402273A | 106000 | CAP_E_F21P1 AMHS MML Seismic Foundation | Housekeeping and Equipment maintenance(Open PO) | SEMITEC LLC | 79539.38 | 0.75037 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Housekeeping
Base-Build | WWT | Others | Commissioning | USC21C009 | USCSB2401252A | 104396.2 | F21P1 WWT package (Installation and 2 batch tanks) | WWT commissioning chemical | Kurita America Inc | 81863.88 | 0.78417 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC24C008 | USCSB2404198A | 104387.04 | UPW B Side Project | Materials for Train 2 from Taiwan Supplier | Ze-Wei Industrial Co., Ltd. | 104387.04 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC21C004 | USCSB2211022A | 104000 | F21P1 WWT package （USA EQ-FRP tank) | WWT welding machines rentals from Megaunion | Mega Union Technology Inc. | 104000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406039A | 103121 | Chemical & WCCS B Side Project | CHEM_CDS/ SDS/ WCCS_ SUS project_LINDE_ ARGON, REFRIGERATED LIQUID*200pcs | Linde Gas and Equipment Inc | 15342.46 | 0.14878 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2209023A | 102627.93 | F21P1 QR Lab Security & CCTV | F21P1 MFG_Security&CCTV Package | Aegis Technology Inc | 83421 | 0.81285 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | Base-Build | Others | Housekeeping | USC21C008 | USCSB2303048A | 101729.26 | F21P1 CCTV & Security | Sunrise Phoenix housekeeping services | Sunrise Phoenix Hi-Tech LLC | 101415 | 0.99691 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Housekeeping
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2212038A | 101342.71 | F21P1 UPW | LB2 Wall Redesign Cable Tray Changes | Rosendin Electric, Inc. | 101342.71 | 1 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Rosendin
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2401113A | 101316 | F21P1 Chemical & WCCS package | CDS B side support LB1 | Milling Machinery, Inc. | 5500 | 0.054286 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2203009A | 100800 | F21P1 WWT package (Installation and 2 batch tanks) | Outsourcing Service Superintendent Lead | Teo Services, Inc. DBA TEOPM | 100800 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2310147A | 100297 | WWT Change Order (Piping) | WWT-Chad lab drain-6.5 line | University Mechanical & Engineering Contractors, Inc. | 95282 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2408044A | 100268 | WWT B side Project | LB2 GIP Blower material supplement_WWT | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC22C006 | USCSB2211006A | 100000 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | TSMC F21 AZ On-site Construction Coordination | SYNERGY Engineering Consultants | 100000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Outsourcing
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407064A | 100000 | WWT B side Project | WWT: OPEN PO III | Harrington Industrial Plastics LLC | 93016.68 | 0.93017 | Mechanical |  |  | WWT
Base-Build | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2201008A | 100000 | F21P1 VOC package （Installation ) | tsmc F21P1 VOC 雜項工程 | Desiccant Technology Corporation | 100000 | 1 | Mechanical | Main Contract Scope | Low Voltage | VOC | Material
Base-Build | Base-Build | Others | Housekeeping | USC22C014 | USCSB2403029A | 100000 | F21P1 AMHS Power Panel | General laborer and Housekeeping&Superintendent Service (Open PO) | Sunrise Phoenix Hi-Tech LLC | 64821.62 | 0.64822 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Housekeeping
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2209015A | 100000 | F21P1 Slurry package | TSMC MIC Fab Chemical, Piping and Electrical Design | KAEKO, Inc | 96990 | 0.9699 | Mechanical | Main Contract Scope | SDS | Base-Build | Labor
Base-Build | Base-Build | Others | Site Expense | USC22C006 | USCSB2308139A | 100000 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | Liberty May 03 | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 100000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Scaffolding
Base-Build | WWT | Electrical | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2204002A | 100000 | F21P1 WWT package (Installation and 2 batch tanks) | MICU人力支援 | Marketech International Corp. | 100000 | 1 | Electrical | Main Contract Scope | WWT | WWT | Labor
Base-Build | Low Voltage | Mechanical | M+L | USC21C008 | USCSB2403263A | 99907.93 | F21P1 CCTV & Security | F21 P1 EBO AMC gas hookup | Welmade Technology Corporation | 99907.93 | 1 | Mechanical | The budget execution does not pertain to this project | AMC THC | AMC THC | Equipment
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2306135A | 99625 | F21P1 Chemical & WCCS package | TSMC Offload June | Milling Machinery, Inc. | 99625 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2207022A | 99600 | F21P1 WWT package (Installation and 2 batch tanks) | Water Systems Superintendent _Rod Copas | Teo Services, Inc. DBA TEOPM | 92742.52 | 0.93115 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2403244A | 98660 | F21P1 Chemical & WCCS package | CDS INSTALL VMB WITH SUPPORTS TSMC-008 | CRG International | 84899.61 | 0.86053 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2405166A | 98303 | F21P1 WWT package (Installation and 2 batch tanks) | WSR 廢硫酸缺料接點 | Trusval Technology CO., LTD. | 0 | 0 | Mechanical | Main Contract Scope | WWT | W-H2SO4
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2401177A | 97923.66 | F21P1 UPW | REI PCOs 26,28,37,39,46,52 | Rosendin Electric, Inc. | 97923.66 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USCSB2209032A | 97367 | F21P1 Slurry package | Slurry VMBs | FusionHPX LLC | 74961.12 | 0.76988 | Mechanical | Main Contract Scope | SDS | Slurry | Equipment
Base-Build | WWT | Civil | M+L | USC24C006 | USCSB2408077A | 97275 | WWT B side Project | WWT - FRP membrane atpads- dike walls around Tmah expansion LB2 N.5 | Pride Development & Construction, Inc. | 0 | 0 | Civil |  |  | WWT
Base-Build | WWT | Civil | M+L | USC21C003 | USCSB2211019A | 96460 | F21P1 UPW | Embedded pipes fire sealants | Kinpo Co. | 0 | 0 | Civil | The budget execution does not pertain to this project | Penetration Pipe | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C006 | USC2112016A | 96000 | F21P1 Slurry package | Chemical Resistant Tubing | Harrington Industrial Plastics LLC | 96000 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2403048A | 95913 | F21P1 Chemical & WCCS package | CDS UPW - 8-195 AOR HFC HFD Chem Drains | University Mechanical & Engineering Contractors, Inc. | 95913 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | UMEC
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404166A | 95487 | WWT B side Project | WIDOS WELDING MACH. | Ferguson Enterprises, LLC | 95487 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Site Expense
Base-Build | UPW | Electrical | Material | USC21C003 | USC2111018A | 94829.03 | F21P1 UPW | pressure transmitter | Ashcroft Inc. | 94829.03 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | UPW | Mechanical | M+L | USC21C012 | USCSB2402149A | 94329 | F21 Barcode RFID System | UPW-UMEC-LB2 A.5/L10 Q.5 Design change | University Mechanical & Engineering Contractors, Inc. | 86577 | 0.91782 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USC2111009A | 93800 | F21P1 Chemical & WCCS package | I LINE PANEL,Mains Panel | OEG ISG - Integrated Systems Group | 93800 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2312035A | 93494 | WWT Change Order (Piping) | WWT-UPW RO to T780 and 780 temp plates | University Mechanical & Engineering Contractors, Inc. | 93494 | 1 | Mechanical | Main Contract Scope | WWT | Water | UMEC
Base-Build | Chemical | Others | Labor | USC21C005 | USCSB2406051A | 93450 | F21P1 Chemical & WCCS package | FAB A CDS-WCCS Permit Revision | KAEKO, Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Chemical
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2212027A | 93422.41 | F21P1 WWT package (Installation and 2 batch tanks) | 1st Set of Clamps | Process Service Specialists, LLC of Delaware | 85363.72 | 0.91374 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2404110A | 92838 | Chemical & WCCS B Side Project | CPVC 料補齊.1 | Harrington Industrial Plastics LLC | 92838 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Electrical | M+L | USC21C008 | USCSB2201009A | 92382.74 | F21P1 CCTV & Security | Access Control/Wifi/CCTV in new Office/Warehouse | Galaxy3 LLC | 92382.74 | 1 | Electrical | The budget execution does not pertain to this project | 0 | CCTV | Material
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2308108A | 92340.75 | F21P1 UPW | Page Observation for FAB and WRC UPW | Page Southerland Page, Inc. | 92340.75 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2205027A | 91640 | F21P1 WWT package (Installation and 2 batch tanks) | SYNERGY/MICU tsmc F21 Arizona On-site Engineer | SYNERGY Engineering Consultants | 91640 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406115A | 91105.48 | Chemical & WCCS B Side Project | F21P1 HPM L10B CDU/DHL CDA/GN2 | SEMITORR GROUP, LLC | 75213.52 | 0.82557 | Mechanical |  |  | Chemical
Base-Build | WWT | Civil | M+L | USC23C045 | USCSB2310100A | 91000 | WWT Change Order (Piping) | WWT-Swing gate | Degan Construction LLC | 85670 | 0.94143 | Civil | CO Scope (adding/additional scope) | WWT | WWT | Equipment
Base-Build | Chemical | Electrical | Labor | USC24C005 | USCSB2405132A | 90000 | Chemical & WCCS B Side Project | F21P1A L10 Pump area WLS Aegis panel 工程 | DFK Tech, LLC | 0 | 0 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | Low Voltage | Mechanical | Labor | USC21C007 | USCSB2203005A | 90000 | F21P1 VOC package （Installation ) | 轉輪及煙囪預組裝費用 | Desiccant Technology Corporation | 85500 | 0.95 | Mechanical | Main Contract Scope | Low Voltage | VOC | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407111A | 89625.85 | WWT B side Project | Installation of Drip Pan (PVC Bag) 追加工程 | United Integrated Services (USA) Corp | 0 | 0 | Mechanical |  |  | WWT
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2306056A | 89000 | F21P1 UPW | Mezzanine Doors and Installation | Suncoast Glass & Glazing,LLC dba Mirror Works dba Horn Doors | 89000 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Labor
Base-Build | WWT | Steel | M+L | USC21C011 | USCSB2306118A | 87915 | F21 TMAH System | WRC 2nd floor rack (WWT under TMAH) | Greenberry Industrial | 83519.25 | 0.95 | Steel | Main Contract Scope | WWT | WWT | Greenberry
Base-Build | Low Voltage | Electrical | Labor | USC24C007 | USCSB2405126A | 87354 | Low Voltage B Side Project | F21 P1 VOC system extension GC (MAY/2024) | Spectra Electrical Services, Inc. | 87354 | 1 | Electrical | The budget execution does not pertain to this project | VOC | VOC
Base-Build | UPW | Mechanical | M+L | USC23C045 | USCSB2403249A | 87328 | WWT Change Order (Piping) | UPW-UMEC-COs for MA-137, 162, 172 and 182 | University Mechanical & Engineering Contractors, Inc. | 83804 | 0.95965 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Electrical | Instrument | USC24C006 | USCSB2405068A | 87147.49 | WWT B side Project | WWT B Side Instrument Batch 1 | Mega Union Technology Inc. | 0 | 0 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Others | Site Expense | USC21C003 | USCSB2211024A | 87049.1 | F21P1 UPW | Temp Power Supplier | Consolidated Electrical Distributors Inc | 86027.8 | 0.98827 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2301007A | 87026.68 | F21P1 Chemical & WCCS package | 2023 Pro XD Mid- Size Crew | Iron City Polaris | 87026.68 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | Equipment
Base-Build | UPW | Others | Labor | USC23C054 | USCSB2401240A | 86906 | UPW Change Order | UPW-UMEC-B side ACF loading | University Mechanical & Engineering Contractors, Inc. | 78215 | 0.9 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | UMEC
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2405080A | 86810 | UPW B Side Project | Train 2 ICPMS CO To UMEC | University Mechanical & Engineering Contractors, Inc. | 65159 | 0.75059 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2110001A | 86667 | F21P1 UPW | DIA 200M, Pole, Extension, CPE | Chunghwa Telecom Global, Inc | 86667 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Internet
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2311113A | 86100 | F21 TMAH System | WWT -Stripper-2"packing for 2 towers | LICI PLASTIC INDUSTRY CO. | 86100 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Material | USC21C009 | USCSB2312116A | 85937.06 | F21P1 WWT package (Installation and 2 batch tanks) | CDS CED MIC A side 2 of 2 per Paul | Consolidated Electrical Distributors Inc | 85510.44 | 0.99504 | Electrical | 0 | 0 | Chemical | Material
Base-Build | Low Voltage | Electrical | M+L | USC21C009 | USCSB2312198A | 85830 | F21P1 WWT package (Installation and 2 batch tanks) | F21 AMC B side Network Engineering | NUUO US Inc. | 81522.75 | 0.94982 | Electrical | The budget execution does not pertain to this project | AMC THC | AMC THC | NUUO
Base-Build | Low Voltage | Mechanical | M+L | USC22C013 | USCSB2406127A | 85711.22 | F21P1 QR Lab Security & CCTV | F21-P1_B-Side mask room gas piping hookup_batch 2/2 | Welmade Technology Corporation | 0 | 0 | Mechanical |  |  | VOC
Base-Build | Chemical | Others | QAQC | USC24C005 | USCSB2404184A | 85680 | Chemical & WCCS B Side Project | FAB B Chemical Electrical Permit + CA | LSW Engineers Arizona, Inc. | 56380 | 0.65803 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Chemical | Labor
Base-Build | Low Voltage | Electrical | Labor | USC21C002 | USCSB2103005A | 85570 | TSMC AZ Temp Office Speed Gate | tsmc AZ office speed gate engineering | B&D Industries, Inc. | 85570 | 1 | Electrical | Main Contract Scope | Low Voltage | Speed Gate | Equipment
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2309125A | 85355.14 | F21P1 Chemical & WCCS package | Boxes for bridge/HPM/clean room of CDS system. | Professional Plastics Inc | 85355.14 | 1 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2301059A | 85302 | F21P1 UPW | Temp CP piping labor | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Low Voltage | Electrical | Labor | USC21C014 | USCSB2309080A | 85243.41 | F21P1 WH2SO4 | F21 P1 CCTV Engineering | ELECTRIC OPS LLC DBA E-OPS | 85243.41 | 1 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | Labor
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2206007A | 85200 | F21P1 WWT package (Installation and 2 batch tanks) | DOCK COORDINATOR | Teo Services, Inc. DBA TEOPM | 85200 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401201A | 84512 | F21P1 Chemical & WCCS package | CDS Required maintenance and pressure switches for the CO2 systems, 24 for Lorry and 52 for Fab A | Aidant Fire Protection | 84512 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Others | Site Expense | USC21C011 | USCSB2304004A | 84250 | F21 TMAH System | MIC MAU Generator | Wilson Electric Services Corporation | 84250 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Site Expense
Base-Build | WWT | Mechanical | Labor | USC24C006 | USCSB2408070A | 84115.95 | WWT B side Project | WWT CDA system branch - CRG | CRG International | 0 | 0 | Mechanical |  |  | WWT
Base-Build | UPW | Electrical | QAQC | USC21C003 | USCSB2307070A | 84100 | F21P1 UPW | Shermco Special Inspection Test | Shermco Industries, Inc. | 23200 | 0.27586 | Electrical | Main Contract Scope | UPW | Base-Build | Labor
Base-Build | WWT | Steel | Labor | USC23C045 | USCSB2406066A | 83260 | WWT Change Order (Piping) | Pipe support _Hua Yi close PR_ batch 1/2 | Mirador Construction Service, LLC | 0 | 0 | Steel | Main Contract Scope | WWT | WWT | Labor
Base-Build | Base-Build | Others | Site Expense | USC23C045 | USCSB2308141A | 82841.89 | WWT Change Order (Piping) | Liberty May 05 | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 82841.89 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Scaffolding
Base-Build | UPW | Others | Project Outsourcing (專案管理外包人力) | USC21C003 | USCSB2311013A | 82153.68 | F21P1 UPW | UPW-commissioning manpower | ELECTRIC OPS LLC DBA E-OPS | 35632.51 | 0.43373 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Outsourcing
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208009A | 82057.95 | F21P1 UPW | AECC License | Autodesk, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2403240A | 81734.33 | WWT Change Order (Piping) | WWT PVC Pipes_20240325 (B Side) | Ryan Herco Flow Solutions | 81734.32 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2311095A | 81287.41 | F21P1 WWT package (Installation and 2 batch tanks) | Southwest Fastener Monthly Order for Water Team | Southwest Fastener Division of NEFCO | 81287.41 | 1 | Mechanical | Main Contract Scope | WWT | Water | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404043A | 81064.8 | WWT B side Project | WWT PVC Glue & Primer_20240327_B side | Harrington Industrial Plastics LLC | 81064.8 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2407061A | 80641.31 | Chemical & WCCS B Side Project | CED 化學系統線0710 | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical |  |  | Chemical
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309174A | 80000 | WWT Change Order (Piping) | WWT -Open PO for urgent materials | Harrington Industrial Plastics LLC | 79525.73 | 0.99407 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | E2 | USC21C006 | USCSB2401223A | 80000 | F21P1 Slurry package | CDS Cheng Shing extension open PO | Cheng Shing MEP Taiwan Co. | 45959.33 | 0.57449 | Electrical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2308111A | 78732 | F21P1 WWT package (Installation and 2 batch tanks) | Field Observation for FAB WWT & WWD | Page Southerland Page, Inc. | 47239.2 | 0.6 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2310202A | 78040 | F21P1 WWT package (Installation and 2 batch tanks) | Fabricate,paint & Install 6 NGR Stands | Greenberry Industrial | 74138 | 0.95 | Steel | CO Scope (adding/additional scope) | WWT | WWT | Greenberry
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2311104A | 77874.6 | F21P1 WWT package (Installation and 2 batch tanks) | A side valve lacking, confirmed by MU all valves for A side. | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C006 | USC2112025A | 77500 | F21P1 Slurry package | General hoses | Nippon Pillar Corporation of America | 77500 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | Low Voltage | Electrical | M+L | USC22C009 | USCSB2301050A | 77300 | F21P1 230kV MTR Oil and Drain Pipe work | Electrical room level gauge | Hua Yi Construction AZ, Inc | 57975 | 0.75 | Electrical | Main Contract Scope | Low Voltage | Oil drain pipe work | Material
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2407163A | 77222.59 | F21P1 WWT package (Installation and 2 batch tanks) | CO from tsmc for Enzyme to improve, we take the B side to fill A side need first | Mega Union Technology Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | M+L | USC22C021 | USCSB2210017A | 77055 | F21P1 Chemical Lab setup | FAB L10, L20 HPM Drain Piping Penetration | Silicone Future Manufacturing Company Ltd | 77055 | 1 | Mechanical | The budget execution does not pertain to this project | Penetration Pipe | Chemical Lab | Labor
Base-Build | Chemical | Mechanical | E2 | USC21C005 | USCSB2310065B | 77013 | F21P1 Chemical & WCCS package | Hardware for Chemical YaoHong work at Lorry FNDP, CDA at L20. | JUWEI ENGINEERING CO LTD | 77013 | 1 | Mechanical | Main Contract Scope | CDS | chemical | Equipment
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2302058A | 76700.22 | F21P1 UPW | UPW B Side Disconnect Switch & Stand | Rosendin Electric, Inc. | 76700.22 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2308182A | 75936.12 | F21P1 UPW | Repair damages on site | Rosendin Electric, Inc. | 75936.12 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | UPW | Mechanical | Material | USC21C003 | USC2111033A | 75000 | F21P1 UPW | Flanged Heater | Wattco Inc. | 75000 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Low Voltage | Electrical | Labor | USC22C010 | USCSB2405023A | 74783.1 | F21 P1 LSC CMS and DPM 5G System | F21 P1 parking gates installation-(10/11) | NUUO US Inc. | 74783.1 | 1 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2305099A | 74708.31 | F21 TMAH System | FAB A PVDF | Harrington Industrial Plastics LLC | 71476.47 | 0.95674 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2406084A | 73400 | Chemical & WCCS B Side Project | 化學系統控制線材0613 for priority 3 | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2309170A | 73373.74 | F21P1 UPW | Veolia turbo bed-final | Veolia WTS Services USA, Inc. | 73373.74 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Equipment
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2409040A | 73316.13 | WWT B side Project | WWT - WRC Platform Flashing | Milling Machinery, Inc. | 0 | 0 | Steel |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2302045A | 73260 | F21P1 WWT package (Installation and 2 batch tanks) | Flange fittings | Yingsheng Applied Materials Co., Ltd | 73260 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2405005A | 73158 | UPW B Side Project | FAB LB2 MAU Bypass | University Mechanical & Engineering Contractors, Inc. | 65842 | 0.9 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2402136A | 73038 | F21P1 WWT package (Installation and 2 batch tanks) | WWT FRP coating in WRC&FAB | OBR Cooling Towers, Inc. | 73038 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Steel | M+L | USC23C045 | USCSB2309041A | 72481 | WWT Change Order (Piping) | WWT FAB Install (16) Agitator Installation | Greenberry Industrial | 51375.05 | 0.70881 | Steel | Main Contract Scope | WWT | WWT | Greenberry
Base-Build | WWT | Civil | M+L | USC21C011 | USCSB2306097A | 72000 | F21 TMAH System | WWT Tank Agitator Blade Epoxy | Degan Construction LLC | 49500 | 0.6875 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Civil | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2206024A | 72000 | F21P1 WWT package （USA EQ-FRP tank) | FRP tank Painting | Phoenix House Painting.com LLC dba PHP Commercial Painting | 72000 | 1 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405073A | 71965 | Chemical & WCCS B Side Project | CHEM_WCCS _Consumable hardware C_Cush A clamp_USA_ 01-00167404_ 0510 | Copper State Bolt & Nut Company | 71965 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2304080A | 71927.12 | F21P1 UPW | ORGANO temp resin | Organo USA, Inc | 71927.12 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2203004A | 71730 | F21P1 UPW | FRP/PP Tank Change Order | An-Cor Industrial Plastics, Inc. | 71730 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2406029A | 71600 | Chemical & WCCS B Side Project | F21P1 B Side EES Porder Coating Cable Tray | Elliott Electric Supply, Inc. | 71600 | 1 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2407155A | 71497 | WWT B side Project | LB2 VS1380 steel pipes_WWT | BMWC Constructors, INC. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2301031A | 71287.6 | F21P1 WWT package (Installation and 2 batch tanks) | Harrington Pipe | Harrington Industrial Plastics LLC | 71287.6 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Mechanical | M+L | USC21C009 | USCSB2312201A | 70997.28 | F21P1 WWT package (Installation and 2 batch tanks) | F21 Litho AMC Utility GAS piping Engineering | Welmade Technology Corporation | 70997.28 | 1 | Mechanical | The budget execution does not pertain to this project | AMC THC | AMC THC | Equipment
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2406085A | 70906.95 | F21P1 WWT package (Installation and 2 batch tanks) | Mess remaining painting Jeff | SD Engineering Technology LLC | 67361.6 | 0.95 | Civil | Main Contract Scope | WWT | WWT
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2311141A | 70670 | F21P1 QR Lab Security & CCTV | F21 EBO CCTV & Security Equipment | Aegis Technology Inc | 62587 | 0.88562 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404055A | 70580 | WWT B side Project | WWT Welding machine | Harrington Industrial Plastics LLC | 57169.8 | 0.81 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | QAQC | USC21C003 | USCSB2307098A | 70219.99 | F21P1 UPW | LV 3 – 3rd Party Inspection - June | Technical Inspections Group | 70219.99 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | Base-Build | Labor
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2308072A | 70136 | F21P1 Chemical & WCCS package | Lorry A&B Crossover Steps | Milling Machinery, Inc. | 70136 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Others |  | USC24C006 | USCSB2409072A | 70080 | WWT B side Project | Iron plate installation and positioning |  | 0 | 0 |  |  |  | WWT
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2402013A | 70061 | F21P1 UPW | UPW-UMEC-TSMC-CO for B side ACM-C expansion | University Mechanical & Engineering Contractors, Inc. | 66558 | 0.95 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405047A | 70000 | WWT B side Project | WWT: OPEN PO II | Harrington Industrial Plastics LLC | 69485.71 | 0.99265 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C006 | USC2111052A | 69874.42 | F21P1 Slurry package | Valves for SDS | Arizona/Albuquerque Valve & Fitting Corp. | 69874.42 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2311118A | 69039.23 | F21P1 WWT package (Installation and 2 batch tanks) | L30 PP/PVC Material Needed to Complete B-side | Harrington Industrial Plastics LLC | 69039.23 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2304009A | 68400 | F21P1 UPW | 360 pic battery charge | Gruber Industries | 68400 | 1 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2406112A | 68309.09 | WWT B side Project | WWT - PR Brahma A-Side FRP T-740AA-AB-AC Tank Interconnection Spools(A side) | BRAHMA GROUP, INC. | 68042.31 | 0.99609 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2403221A | 68189.46 | WWT Change Order (Piping) | WWT 009 _B SIDE P clamp | Jinsheng Industrial Co | 68189.46 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Civil | M+L | USC21C003 | USCSB2404101A | 68027 | F21P1 UPW | SUPPLY MATERIAL/ BUILD SHAFT WALL/ APPLY DRYWALL AND SHAFT WALL TO FRAMING/ TAPE AND SAND DRYWALL TO PAINT PREP FINISH/INSTAL | Performance Contracting Inc | 0 | 0 | Civil | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304013A | 68009.6 | F21P1 WWT package (Installation and 2 batch tanks) | WWT SUS CDA all A side material (requested by PSS) | Ferguson Enterprises, LLC | 66984.15 | 0.98492 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Electrical | M+L | USC21C009 | USCSB2207024A | 68000 | F21P1 WWT package (Installation and 2 batch tanks) | CCE Conduit, Cable Tray and Cable label | Commercial Comm and Electric Inc | 68000 | 1 | Electrical | Main Contract Scope | WWT | WWT | CCE
Base-Build | WWT | Electrical | Instrument | USC23C045 | USCSB2406015A | 67302.18 | WWT Change Order (Piping) | T140 discharge panel modification | ACME Control System Corporation | 67302.18 | 1 | Electrical | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2306085A | 67129 | F21P1 Chemical & WCCS package | Slurry Raise Trench Grating | Milling Machinery, Inc. | 63772.55 | 0.95 | Mechanical | Main Contract Scope | SDS | Slurry | MMI
Base-Build | Chemical | Mechanical | E2 | USC21C006 | USCSB2312011A | 66929.4 | F21P1 Slurry package | CDS HongDong 2023 Nov construction work | HONGDONG INTERNATIONAL CO., LTD | 66929.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Steel | M+L | USC21C014 | USCSB2304055A | 66708 | F21P1 WH2SO4 | WSR tank Install | Greenberry Industrial | 0 | 0 | Steel | Main Contract Scope | WWT | W-H2SO4 | Greenberry
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2311102A | 66000 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - 450 welder | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Site Expense
Base-Build | WWT | Civil | M+L | USC21C014 | USCSB2308170A | 65025.05 | F21P1 WH2SO4 | WRC Additional Concrete | Degan Construction LLC | 55025.05 | 0.84621 | Civil | Main Contract Scope | WWT | W-H2SO4 | Material
Base-Build | Base-Build | Others | Housekeeping | USC23C058 | USCSB2311055A | 65024 | F21 EUV Steel Plates | Transparent table mat, PE blue and white canvas and cleanroom tape for A side housekeeping and epoxy protecting. | Xiang Sheng Hardware Enterprise Co., Ltd. | 65024 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Housekeeping
Base-Build | WWT | Mechanical | Material | USC22C022 | USCSB2304073A | 65023.22 | F21P1 Triazole treatment system | Triazole Poly/PVC material | Harrington Industrial Plastics LLC | 65023.22 | 1 | Mechanical | Main Contract Scope | WWT | Triazole | Material
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2311020A | 65000 | F21P1 WWT package (Installation and 2 batch tanks) | Mezzanine shaft wall paint | Phoenix House Painting.com LLC dba PHP Commercial Painting | 41326.16 | 0.63579 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2209012A | 64660.89 | F21P1 WWT package (Installation and 2 batch tanks) | WWT tank welding | Process Service Specialists, LLC of Delaware | 61427.85 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Mechanical | Site Expense | USC24C006 | USCSB2404002A | 64323.97 | WWT B side Project | WWT LJ Tools_20240329 | Li Jie Industrial Co.,Ltd | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2308012A | 64096 | F21P1 WWT package (Installation and 2 batch tanks) | Fab 21 B LB2 (7 Tank Media Loading) Phoenix, Arizona | Marquis Construction Services LLC | 64096 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Low Voltage | Electrical | Labor | USC22C013 | USCSB2405024A | 63539.96 | F21P1 QR Lab Security & CCTV | F21 P1 parking gates installation-(11/11) | NUUO US Inc. | 63539.96 | 1 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2206008A | 63250 | F21P1 UPW | Insulation spec change | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | Main Contract Scope | UPW | UPW | UMEC
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405173A | 63239.02 | Chemical & WCCS B Side Project | Extremely Urgent_RFQ_MICU Chemical Team Request Material_05232024_Semitorr | SEMITORR GROUP, LLC | 63228.63 | 0.99984 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Electrical | M+L | USC21C009 | USCSB2402081A | 63146.26 | F21P1 WWT package (Installation and 2 batch tanks) | TRIAZOLE & NH3 stripper pad scopes | Revolution Industrial LLC | 63146.26 | 1 | Electrical | DCR Scope | WWT | Triazole | Equipment
Base-Build | Low Voltage | Electrical | Labor | USC21C008 | USCSB2402241A | 62593.07 | F21P1 CCTV & Security | F21 CCTV Engineering (T&M) | OE Electric | 62593.07 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Labor
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2406002A | 62544.05 | Chemical & WCCS B Side Project | CED 五金料件0531-1 | Consolidated Electrical Distributors Inc | 41584.84 | 0.66489 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | Low Voltage | Mechanical | M+L | USC21C006 | USCSB2308162A | 62489 | F21P1 Slurry package | F21 P1 VOC Change Order(southland)_3 | Southland Industries | 62489 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | VOC | Southland
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405086A | 62133.4 | Chemical & WCCS B Side Project | CHEM_CDS SDS project for valve_ SemiTorr Group_Qte1526621 | SEMITORR GROUP, LLC | 62133.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Civil | M+L | USC24C006 | USCSB2408140A | 62000 | WWT B side Project | WWT A+B side punch which is paid by tsmc_水泥基座填塞 | SD Engineering Technology LLC | 0 | 0 | Civil |  |  | WWT
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2209021A | 61618.95 | F21P1 QR Lab Security & CCTV | F21P1 QR Lab_Security&CCTV Package | Aegis Technology Inc | 50569 | 0.82067 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405164A | 61556.2 | Chemical & WCCS B Side Project | Swagelok pressure-reducing redgulators and compressionto npt adaptors | Arizona/Albuquerque Valve & Fitting Corp. | 61556.2 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Electrical | Material | USC22C013 | USCSB2406069A | 61428 | F21P1 QR Lab Security & CCTV | F21 Chemical system control cable | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical | The budget execution does not pertain to this project | Chemical | CCTV
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2307085A | 60948.92 | WWT Change Order (Piping) | WWT -L20 Sludge | Harrington Industrial Plastics LLC | 60948.92 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2310183A | 60742.5 | F21P1 Chemical & WCCS package | CDS L10 CPVC chemical pipes | CRG International | 60742.5 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | Low Voltage | Electrical | Labor | USC23C045 | USCSB2310171A | 60460.5 | WWT Change Order (Piping) | F21 CCTV system incentive for CCE | Commercial Comm and Electric Inc | 60460.5 | 1 | Electrical | The budget execution does not pertain to this project | Labor Incentive | CCTV | CCE
Base-Build | Low Voltage | Electrical | Labor | USC22C001 | USCSB2310049A | 60216 | F21 P1 Office and WH Security and CCTV | F21 P1 Security and CCTV Engineering | Onsight Live, LLC | 60216 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Labor
Base-Build | Low Voltage | Electrical | Labor | USC21C008 | USCSB2405016A | 60187.83 | F21P1 CCTV & Security | F21 P1 parking gates installation-(3/11) | NUUO US Inc. | 58676.94 | 0.9749 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | UPW | Others | QAQC | USC21C003 | USCSB2307099A | 60083.66 | F21P1 UPW | LV 3 – 3rd Party Inspection - July | Technical Inspections Group | 60083.66 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | Base-Build | Labor
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2306042A | 60019.55 | F21 TMAH System | FAB A PVDF - 02 | Harrington Industrial Plastics LLC | 47634.98 | 0.79366 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | Chemical | Mechanical | M+L | USC24C005 | USCSB2405034A | 60000 | Chemical & WCCS B Side Project | SDS L3 Add one VMB | Yun Cheng International Co., Ltd | 54000 | 0.9 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Equipment
Base-Build | WWT | Civil | M+L | USC24C006 | USCSB2407051A | 59656.95 | WWT B side Project | Painting mess CO | SD Engineering Technology LLC | 56674.1 | 0.95 | Civil |  |  | WWT
Base-Build | WWT | Mechanical | M+L | USC22C022 | USCSB2404044A | 59604.44 | F21P1 Triazole treatment system | Main CO Trident WSR | Trident Mechanical Services | 48711.73 | 0.81725 | Mechanical | Main Contract Scope | WWT | W-H2SO4 | Trident
Base-Build | WWT | Steel | M+L | USC23C045 | USCSB2403024A | 59468.46 | WWT Change Order (Piping) | WWT Tunnel additional rack on expansion loop | Greenberry Industrial | 59468.46 | 1 | Steel | DCR Scope | WWT | WWT | Greenberry
Base-Build | WWT | Steel | M+L | USC21C011 | USCSB2402085A | 59283 | F21 TMAH System | Tmah ACF expansion Rack for MMI. | Milling Machinery, Inc. | 49048 | 0.82735 | Steel | Main Contract Scope | WWT | TMAH | MMI
Base-Build | Chemical | Others | Labor | USC21C005 | USCSB2406088A | 59110 | F21P1 Chemical & WCCS package | FAB A SDS Observation | LSW Engineers Arizona, Inc. | 2015 | 0.034089 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Slurry
Base-Build | Low Voltage | Mechanical | Labor | USC22C013 | USCSB2407020A | 58950 | F21P1 QR Lab Security & CCTV | F21 P1 VOC duct insulation | Petrochem Insulation, Inc | 53587 | 0.90902 | Mechanical |  |  | VOC
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2304031A | 58931 | F21P1 UPW | UPW Bussman 170M6013 Fuse | Border State Industries, Inc. | 58931 | 1 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2402165A | 58500 | F21P1 Slurry package | SDS HPM L20 H2O2&KOH VMB Control | Mirador Construction Service, LLC | 35100 | 0.6 | Mechanical | Main Contract Scope | SDS | Slurry | Equipment
Base-Build | Low Voltage | Electrical | Labor | USC21C013 | USCSB2405014A | 58327.5 | F21P1 AMC THC Monitoring System | F21 P1 parking gates installation-(1/11 ) | NUUO US Inc. | 0 | 0 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | WWT | Mechanical | Material | USC21C004 | USCSB2210044A | 58232.1 | F21P1 WWT package （USA EQ-FRP tank) | FAB Sump Pit Pump RT Fitting | Mega Union Technology Global Pte Ltd | 58232.1 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | E2 | USC21C005 | USCSB2312010A | 58200 | F21P1 Chemical & WCCS package | CDS IPA Thinner-3 boxes email "Clamp quantity" | HONGDONG INTERNATIONAL CO., LTD | 58200 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2308136A | 58000 | F21P1 Chemical & WCCS package | Additional Dry Type Transformer Testing | Shermco Industries, Inc. | 54157.5 | 0.93375 | Mechanical | Main Contract Scope | CDS | Base-Build | Labor
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309073A | 57823.5 | WWT Change Order (Piping) | TW team material request for LJ | Harrington Industrial Plastics LLC | 57731.1 | 0.9984 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2402219A | 57820 | F21P1 Chemical & WCCS package | CDS TSMC 8-188 M1 Poly 700 | University Mechanical & Engineering Contractors, Inc. | 54929 | 0.95 | Mechanical | Main Contract Scope | CDS | Chemical | UMEC
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2306136A | 57530 | F21P1 UPW | UPW CO-Add | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2303037A | 57263.7 | F21P1 UPW | UPW Panel Material | Service Construction Supply - Division of Darragh Company | 51051.54 | 0.89152 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2406092A | 56795.35 | F21 TMAH System | PR Harrington WWT - TMAH Expansion Material (PP) | Harrington Industrial Plastics LLC | 56795.35 | 1 | Mechanical | Main Contract Scope | WWT | TMAH
Base-Build | WWT | Mechanical | Labor | USC21C014 | USCSB2403213A | 56625.5 | F21P1 WH2SO4 | 2023 H2SO4 Labor Incentive Change Order | Trident Mechanical Services | 0 | 0 | Mechanical | Main Contract Scope | WWT | W-H2SO4 | Trident
Base-Build | Base-Build | Others | Site Expense | USC22C026 | USCSB2401254A | 56500 | F21P1-0423_H_Unistrut Support Frame_MICU | raised floor | CYH TECHNOLOGY USA LLC | 56500 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2306132A | 55981 | F21 TMAH System | WWT Repair Leak T-140AA Tank | Milling Machinery, Inc. | 55981 | 1 | Mechanical | Main Contract Scope | WWT | WWT | MMI
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2310150A | 55825.84 | F21P1 Chemical & WCCS package | Professional Plastics custom the parts for VMB of A side | Professional Plastics Inc | 55825.84 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2308179A | 55500 | WWT Change Order (Piping) | WWT -TW-Maxiplast | Widos Taiwan Ltd. | 55500 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Labor | USC24C008 | USCSB2405168A | 55484 | UPW B Side Project | Horiba Calibration Service | HORIBA Instruments Incorporated | 0 | 0 | Electrical | Main Contract Scope | UPW | UPW
Base-Build | WWT | Steel | M+L | USC23C045 | USCSB2312006A | 55414 | WWT Change Order (Piping) | WWT Tunnel support | Greenberry Industrial | 55414 | 1 | Steel | Main Contract Scope | WWT | WWT | Greenberry
Base-Build | WWT | Others | Commissioning | USC21C009 | USCSB2405090A | 55281.6 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Enzyme for TSMC urgent request on 5/13 | Univar Solutions USA Inc. | 55281.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2209016A | 55125 | F21P1 UPW | Horiba SLIA Reagent | HORIBA Instruments Incorporated | 55125 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2302029A | 54673.09 | F21P1 WWT package (Installation and 2 batch tanks) | PVC fittings for 6.5 | Harrington Industrial Plastics LLC | 53741.24 | 0.98296 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | E2 | USC21C006 | USCSB2402143A | 54626.4 | F21P1 Slurry package | CDS HongDong recent construction work by 02/06/24 | HONGDONG INTERNATIONAL CO., LTD | 54626.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2308001A | 54525 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Tank Crossover Platform Bracket Bonding (112 Bonds Total) | Harrington Industrial Plastics LLC | 54525 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407175A | 54289.81 | WWT B side Project | WWT shortage of fitting materials on the B side | Harrington Industrial Plastics LLC | 33067.63 | 0.60909 | Mechanical |  |  | WWT
Base-Build | Low Voltage | Mechanical | M+L | USC21C014 | USCSB2309136A | 54039 | F21P1 WH2SO4 | F21 P1 VOC DPI Added Material | Southland Industries | 54038.9 | 1 | Mechanical | The budget execution does not pertain to this project | VOC | VOC | Southland
Base-Build | UPW | Others | M+L | USC21C003 | USCSB2305092A | 53862.4 | F21P1 UPW | TSMC EMERGENCY TFMB #2 | Veolia WTS Services USA, Inc. | 49010.75 | 0.90993 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | UPW | UPW | Equipment
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2308021A | 53527.38 | F21P1 Chemical & WCCS package | F21 P1 CDS POWER CABLE | Consolidated Electrical Distributors Inc | 53527.38 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2406146A | 53131.05 | WWT B side Project | WWT - Brahma T-140AC-AC Carboline Flange Coating | BRAHMA GROUP, INC. | 38618.12 | 0.72685 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2310025A | 53075.77 | WWT Change Order (Piping) | 9/19/23 to 10/20/23 Southwest Fastener Monthly Order for Water Team | Southwest Fastener Division of NEFCO | 53075.77 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2302001A | 52780 | F21P1 UPW | X1 Line Temp Power Cable Relocation | Commercial Comm and Electric Inc | 52780 | 1 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | CCE
Base-Build | WWT | Civil | M+L | USC23C045 | USCSB2309057A | 52125 | WWT Change Order (Piping) | Epoxy Misc Pads in Fab LB2 | Degan Construction LLC | 52125 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Material | USC22C023 | USCSB2210023A | 52079.75 | AZ GF Agru Material | GF PP&PVDF Material UANGYIH | Uangyih-Tech Industrial Co., LTD | 52079.75 | 1 | Mechanical |  |  | GF Agru Material | Material
Base-Build | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2212021A | 52049.16 | F21P1 VOC package （Installation ) | VOC Duct/Pipe Labels | Southland Industries | 0 | 0 | Mechanical | Main Contract Scope | Low Voltage | VOC | Southland
Base-Build | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2301060A | 52049.16 | F21P1 VOC package （Installation ) | VOC Duct / Pipe Lables | Southland Industries | 52048.77 | 0.99999 | Mechanical | Main Contract Scope | Low Voltage | VOC | Southland
Base-Build | WWT | Civil | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2210032A | 52000 | F21P1 WWT package (Installation and 2 batch tanks) | PHP-Tank Painting | Phoenix House Painting.com LLC dba PHP Commercial Painting | 52000 | 1 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Electrical | Labor | USC24C005 | USCSB2407004A | 52000 | Chemical & WCCS B Side Project | 泉太 MICU E2 支援報價單(2個月) | CHEN-TAI-ENTERPRISE CO.,LTD. | 0 | 0 | Electrical |  |  | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2301024A | 51498.43 | F21P1 Chemical & WCCS package | Flame Arrester | Caltrol Inc. | 51498.43 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2408071A | 51123.62 | WWT B side Project | WWT - WRC Agitator Support Extensions | Greenberry Industrial | 0 | 0 | Steel |  |  | WWT
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2212033A | 50858 | F21P1 Chemical & WCCS package | Lorry Vertical Support | Milling Machinery, Inc. | 50858 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Low Voltage | Electrical | Material | USC21C008 | USCSB2204011A | 50600 | F21P1 CCTV & Security | TSMC - CCTV Panel Builds | Kelso-Burnett Co. | 50600 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | Chemical | Others | Labor | USC21C005 | USCSB2406054A | 50410 | F21P1 Chemical & WCCS package | FAB A WCCS Observation | LSW Engineers Arizona, Inc. | 14697.5 | 0.29156 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Chemical
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2312173A | 50171.7 | F21P1 WWT package (Installation and 2 batch tanks) | TSMC 12.18 PVDF material item | Harrington Industrial Plastics LLC | 50171.7 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2306072A | 50000 | F21P1 Chemical & WCCS package | TSMC F21 CDS DC Panel | UCAN Hong Kong Limited | 50000 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2406113A | 50000 | WWT B side Project | WWT: CCR Scope Initial Funding to Start Work | BMWC Constructors, INC. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Civil | M+L | USC23C045 | USCSB2402261A | 50000 | WWT Change Order (Piping) | WWT Chemical Area Safety Paint(OPEN PR) | SD Engineering Technology LLC | 50000 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Electrical | Labor | USC23C054 | USCSB2403137A | 50000 | UPW Change Order | PCO 82 Contract Pricing Adjustment, Continuation of Work Phase 2, Revision 0(batch 2/2) | Rosendin Electric, Inc. | 50000 | 1 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Rosendin
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2311022A | 50000 | WWT Change Order (Piping) | WWT-BMWC-LSR -Train A | BMWC Constructors, INC. | 47500 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | M+L | USC21C003 | USCSB2304033A | 49464.61 | F21P1 UPW | TSMC EMERGENCY TFMB | Veolia WTS Services USA, Inc. | 49464.61 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | UPW | UPW | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2304051A | 49452 | F21P1 UPW | Tanks underlayment | Milling Machinery, Inc. | 49452 | 1 | Mechanical | Main Contract Scope | UPW | UPW | MMI
Base-Build | WWT | Others | Labor | USC21C009 | USCSB2208013A | 49350 | F21P1 WWT package (Installation and 2 batch tanks) | TSMC Phoenix Fab Advantech Design Services | Advantech Facility Design Inc. | 49350 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | WWT | Others | QAQC | USC24C006 | USCSB2408024A | 49200 | WWT B side Project | WWT: Farnsworth assist EOR with Design Change Review and Revisions | Farnsworth Group, Inc | 49200 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2302013A | 49000 | F21P1 UPW | Tanks water test | Hua Yi Construction AZ, Inc | 49000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2307037A | 48798 | F21P1 Chemical & WCCS package | 5222338-CO #096 Lorry PTFE Drain Redesign-Material | Southland Industries | 48798 | 1 | Mechanical | DCR Scope | CDS | Chemical | Southland
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2307047A | 48625 | F21P1 Slurry package | TSMC FAB L30 Floor penetration supports Per RFI #034 | Milling Machinery, Inc. | 48625 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | MMI
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2203013A | 48390 | F21P1 WWT package (Installation and 2 batch tanks) | TSMC Trench Cover Plates | Milling Machinery, Inc. | 48390 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2209011A | 48140 | F21P1 UPW | Horiba Conductivity/Resistivity Meter | HORIBA Taiwan, Inc. | 48140 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Electrical | Labor | USC24C005 | USCSB2408134A | 48000 | Chemical & WCCS B Side Project | 支援F21帆宣電力工程-點工(不含機具) for 1 month |  | 0 | 0 | Electrical |  |  | Chemical
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2210034A | 47962.09 | F21P1 WWT package (Installation and 2 batch tanks) | Confined Space Entry manwatch | Process Service Specialists, LLC of Delaware | 40802.09 | 0.85072 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403198A | 47858.4 | F21P1 WWT package (Installation and 2 batch tanks) | [B side] Welding machine rental from Harrington 12”*1/20”*1 - 2nd rental | Harrington Industrial Plastics LLC | 41143.69 | 0.8597 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2204001A | 47674 | F21P1 UPW | Additional Submain 01 | Organo USA, Inc | 47674 | 1 | Mechanical | DCR Scope | UPW | UPW | Material
Base-Build | Chemical | Others | QAQC | USC21C005 | USCSB2302021A | 47500 | F21P1 Chemical & WCCS package | MRT Design- Additional Service amendment | MRT DESIGN LLC | 30000 | 0.63158 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | CDS | Base-Build | Labor
Base-Build | WWT | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C010 | USCSB2210004A | 47294.07 | F21 P1 LSC CMS and DPM 5G System | TSMC-F21P1-Temporary outfall monitoring | ACME Control System Corporation | 44882.71 | 0.94901 | Electrical | The budget execution does not pertain to this project | WWT | 5G | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2308092A | 47217.47 | F21P1 UPW | Veolia turbo bed-3rd | Veolia WTS Services USA, Inc. | 47217.47 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Equipment
Base-Build | Chemical | Steel | M+L | USC21C009 | USCSB2312112A | 47068 | F21P1 WWT package (Installation and 2 batch tanks) | CDS A side platform rail | Milling Machinery, Inc. | 47068 | 1 | Steel | 0 | 0 | Chemical | MMI
Base-Build | Low Voltage | Mechanical | Labor | USC21C013 | USCSB2307076A | 47000 | F21P1 AMC THC Monitoring System | F21 P1 THC DPT flow meter installation | Welmade Technology Corporation | 43605 | 0.92777 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Equipment
Base-Build | UPW | Others | Site Expense | USC21C003 | USCSB2204008A | 46538.7 | F21P1 UPW | MIC trailer office network | Galaxy3 LLC | 46538.7 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | UPW | Material
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2212050A | 46502.72 | F21P1 QR Lab Security & CCTV | F21P1 CCD_Security&CCTV Package | Aegis Technology Inc | 35915 | 0.77232 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | Low Voltage | Electrical | Labor | USC22C012 | USCSB2405020A | 46468.8 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | F21 P1 parking gates installation-(7/11) | NUUO US Inc. | 0 | 0 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2403033A | 46091 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - T&M Proposal to Work Stainless Line in LB2 | BMWC Constructors, INC. | 2861.4 | 0.062082 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2402123A | 46091 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - T&M Proposal to Work Stainless Line in LB2 | BMWC Constructors, INC. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2401192A | 45952 | WWT Change Order (Piping) | WWT -MIC BMWC T&M SUS team 6*60hr | BMWC Constructors, INC. | 43654.4 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405127A | 45566.81 | WWT B side Project | WWT Fittings_20240521 (B Side) | Harrington Industrial Plastics LLC | 45566.81 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2312145A | 45550 | F21P1 Chemical & WCCS package | Pipe, tube and fitting from MIC TW-1 | Marketech International Corp. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2307026A | 45500 | F21P1 UPW | Purchase and Install Safety Gates on Tanks(UPW swing gate) | Degan Construction LLC | 45500 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Equipment
Base-Build | UPW | Others | Material | USC21C003 | USCSB2209006A | 45237.65 | F21P1 UPW | MMF media procurement | Northern Filter Media, Inc. | 44665.25 | 0.98735 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2202008A | 45125 | F21P1 WWT package (Installation and 2 batch tanks) | FRP Tank Color work | Harrington Industrial Plastics LLC | 45125 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Civil | Labor | USC21C009 | USCSB2303033A | 45000 | F21P1 WWT package (Installation and 2 batch tanks) | Agitator Chemical Coating | Degan Construction LLC | 45000 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2406144A | 44781.12 | WWT B side Project | WWT- Brahma T-740Bs FRP Interconnection, T-110Bs Additional Flange Coating | BRAHMA GROUP, INC. | 43754.24 | 0.97707 | Mechanical |  |  | WWT
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2403258A | 44754 | F21P1 Slurry package | TSMC UPW - 8-201 Remote Cabinet Drains (L20) | University Mechanical & Engineering Contractors, Inc. | 42516 | 0.94999 | Mechanical | The budget execution does not pertain to this project | Chemical | UPW | Material
Base-Build | WWT | Others | Site Expense | USC24C006 | USCSB2404010A | 44724 | WWT B side Project | Harness and SRL for WWT x100 | Palo Verde First Aid-Fire-Safety-Shredding | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2407101A | 44712.14 | WWT B side Project | LB2 B 12 Added supports for punch and WRC lab | Greenberry Industrial | 0 | 0 | Steel |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310022A | 44482 | F21P1 Chemical & WCCS package | Acrylic boards used in normal status and used for every each VMB of A/B side. | J A Hansen Company DBA Hansen Supply Company | 44482 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2212032A | 44435 | F21P1 WWT package (Installation and 2 batch tanks) | WRC WWT Stripper Side Foundation | Sundt Construction, Inc | 42196.05 | 0.94961 | Civil | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2210039A | 44368.92 | F21P1 WWT package (Installation and 2 batch tanks) | Tank blinding and davit arm weld | Process Service Specialists, LLC of Delaware | 44368.92 | 1 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Mechanical | Material | USC21C004 | USCSB2210046A | 44343.4 | F21P1 WWT package （USA EQ-FRP tank) | WRC Sump Pit Pump RT Fitting | Mega Union Technology Global Pte Ltd | 44343.4 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2212034A | 44320 | F21P1 UPW | WRC C,7-D,8 UMEC Pipe Support | Milling Machinery, Inc. | 42104 | 0.95 | Mechanical | Main Contract Scope | UPW | UPW | MMI
Base-Build | WWT | Electrical | Labor | USC21C009 | USCSB2405065A | 44126 | F21P1 WWT package (Installation and 2 batch tanks) | WWT A-Side Sand Blast Room Cable Pulling Requirement_20240509 | Helix Electric, Inc. | 44126 | 1 | Electrical | Main Contract Scope | WWT | WWT | Helix
Base-Build | WWT | Mechanical | Labor | USC24C006 | USCSB2408138A | 44000 | WWT B side Project | WWT Flange repair - Belzona | DCP Coatings, LLC | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2307141A | 43660 | F21 TMAH System | WWT Stripper-packing | LICI PLASTIC INDUSTRY CO. | 43660 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Labor | USC23C045 | USCSB2309151A | 43200 | WWT Change Order (Piping) | Provide the manpower only for installation of CCTV on the A side | Alvarado Electric LLC. | 43200 | 1 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | Labor
Base-Build | Low Voltage | Electrical | Material | USC21C012 | USC2201015A | 43061.4 | F21 Barcode RFID System | 19" rack cabinet | Graybar Electric Company, Inc. | 43061.4 | 1 | Electrical | Main Contract Scope | Low Voltage | Barcode | Material
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2408029A | 43003.56 | WWT B side Project | Additional support for punch and emergency pumps_WWT | Greenberry Industrial | 0 | 0 | Steel |  |  | WWT
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2310070A | 42959.15 | F21P1 Slurry package | USC21C006 SLURRY B SIDE VMB Production Engineering | FusionHPX LLC | 42959.15 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Equipment
Base-Build | WWT | Civil | M+L | USC21C011 | USCSB2402231A | 42875 | F21 TMAH System | install house keeping pads and Dike wall in Fab LB2/WRC | Degan Construction LLC | 41560 | 0.96933 | Civil | Main Contract Scope | WWT | TMAH | Labor
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USC2109019A | 42455.71 | F21P1 WWT package （USA EQ-FRP tank) | WASTE Tank (Last 5 tanks) | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2306083A | 42242 | F21P1 UPW | Crating and packing for pipes on site | Crating Technology, INC | 42242 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MIMO/Rigging
Base-Build | UPW | Electrical | M+L | USC21C012 | USCSB2403200A | 42234.76 | F21 Barcode RFID System | PCO 81, Revision 1: Repull One Fiber Optic Cable from CP1 to CP31 | Rosendin Electric, Inc. | 42234.76 | 1 | Electrical | The budget execution does not pertain to this project | UPW | Barcode | Rosendin
Base-Build | Chemical | Electrical | Labor | USC24C005 | USCSB2404116A | 42220 | Chemical & WCCS B Side Project | F21 B side L30 Tray安裝工程 | DFK Tech, LLC | 40109 | 0.95 | Electrical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2406090A | 42178.61 | WWT B side Project | PR Harrington WWT - WRC Material Line Rework Chem Lines 203, 204, 103, 104(A side) | Harrington Industrial Plastics LLC | 42178.61 | 1 | Mechanical | Main Contract Scope | WWT | WWT
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2402005A | 42159 | F21P1 WWT package (Installation and 2 batch tanks) | MIC-009-23 -Fabricate, paint & Install additional X Line to Tunnel supports | Greenberry Industrial | 40051.05 | 0.95 | Steel | DCR Scope | WWT | WWT | Greenberry
Base-Build | Water_Sewer | Civil | M+L | USC22C018 | USCSB2209025A | 42000 | US Fab Frontage line hydrants | TSMC 16" Water Line Re-Chlorination | Degan Construction LLC | 42000 | 1 | Civil |  |  | Frontage Line Hydrant | Material
Base-Build | Low Voltage | Electrical | Labor | USC22C001 | USCSB2308116A | 41938 | F21 P1 Office and WH Security and CCTV | F21 P1 CCTV Engineering (San Tan Fire, LLC) | San Tan Fire, LLC | 41938 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Labor
Base-Build | WWT | Mechanical | Labor | USC24C006 | USCSB2403259A | 41840 | WWT B side Project | WWT: TSMC Approved CO, Design Change to Relocate 18.5 line CuCMP and CWD line | BMWC Constructors, INC. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2308109A | 41760 | F21P1 UPW | Field Observation for FAB UPW | Page Southerland Page, Inc. | 41760 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | Low Voltage | Others | QAQC | USC21C007 | USCSB2308110A | 41760 | F21P1 VOC package （Installation ) | Field Observation for FAB VOC | Page Southerland Page, Inc. | 41760 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | Low Voltage | VOC | Labor
Base-Build | WWT | Electrical | Instrument | USC21C009 | USCSB2212046A | 41388.06 | F21P1 WWT package (Installation and 2 batch tanks) | WWT- DCR-Sulfate analyzer | Hach Company | 41388.06 | 1 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2311019A | 41120.78 | WWT Change Order (Piping) | WWT-FRP-piping-T710AA | BRAHMA GROUP, INC. | 41120.78 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Others | Commissioning | USC21C009 | USCSB2312156A | 40825.4 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Chemical H2SO4/HCl | Univar Solutions USA Inc. | 12795.88 | 0.31343 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Material
Base-Build | WWT | Steel | Labor | USC21C009 | USCSB2402073A | 40824 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Add Litho Drain Pipe Supports | Mirador Construction Service, LLC | 0 | 0 | Steel | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2404109A | 40737.6 | Chemical & WCCS B Side Project | 2吋SUSBA 3280 ft購買 | SEMITORR GROUP, LLC | 40737.6 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2311091A | 40341.23 | F21P1 Chemical & WCCS package | CDS L10 cleanroom SS chemical tubes | CRG International | 40341.23 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2203002A | 40194.97 | F21P1 Chemical & WCCS package | CO2 Bottle Racks | Pure Plastics, LLC | 40194.96 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401199A | 40084 | F21P1 Chemical & WCCS package | CDS 1-1/4 Over Tube and Coax Elbow 90 | GOLD STONE DEVELOPMENT CO., LTD. | 40084 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2203008A | 39900 | F21P1 WWT package (Installation and 2 batch tanks) | Lorry Box | Pure Plastics, LLC | 39900 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2304037A | 39892.89 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Lab Funiture | LabTech Supply Company Inc | 39892.89 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Labor | USC22C021 | USCSB2309032A | 39611.26 | F21P1 Chemical Lab setup | GC Lab Electrical | Hua Yi Construction AZ, Inc | 39611.26 | 1 | Electrical | The budget execution does not pertain to this project | Chemical Lab | Chemical Lab | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2211037A | 39537.5 | F21P1 WWT package (Installation and 2 batch tanks) | PP Material | Mega Union Technology Global Pte Ltd | 39537.5 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2311076A | 39200 | F21P1 WWT package (Installation and 2 batch tanks) | FAB 1A UPW, WWT CA Suppport (Electrical) | LSW Engineers Arizona, Inc. | 5407.5 | 0.13795 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | Water | Labor
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2407084A | 39080.38 | WWT B side Project | LB2 B 24 Added supports for punch_WWT | Greenberry Industrial | 0 | 0 | Steel |  |  | WWT
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2305111A | 39040.44 | F21P1 WWT package （USA EQ-FRP tank) | WWT T196AA | Harrington Industrial Plastics LLC | 39040.44 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | E2 | USC21C005 | USCSB2312152A | 39031.2 | F21P1 Chemical & WCCS package | CDS Day Tank Vent Labor | HONGDONG INTERNATIONAL CO., LTD | 29273.4 | 0.75 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Electrical | Instrument | USC24C006 | USCSB2405094A | 38923 | WWT B side Project | WWT B Side Battery Panel Rigging and Installation | Helix Electric, Inc. | 38923 | 1 | Electrical | Main Contract Scope | WWT | WWT | Helix
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2310162A | 38885 | WWT Change Order (Piping) | stripper pad duct rework (3areas) | Milling Machinery, Inc. | 38885 | 1 | Mechanical | Main Contract Scope | WWT | Base-Build | MMI
Base-Build | Low Voltage | Mechanical | Material | USC22C013 | USCSB2407135A | 38874 | F21P1 QR Lab Security & CCTV | F21 P1 VOC duct material | Ducts, Inc. | 38874 | 1 | Mechanical |  |  | VOC
Base-Build | WWT | Civil | Labor | USC22C020 | USCSB2209031A | 38750 | F21P1 Penetration Pipe | Core Drill and Grouting with Rebar | Degan Construction LLC | 38750 | 1 | Civil | Main Contract Scope | WWT | Penetration Pipe | Material
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2409041A | 38654.87 | WWT B side Project | WWT - WRC Clarifier Platform Compliance Modification | Milling Machinery, Inc. | 0 | 0 | Steel |  |  | WWT
Base-Build | WWT | Steel | M+L | USC23C045 | USCSB2310181A | 38500 | WWT Change Order (Piping) | Provide and install rocking 8 feet tall 42 inch wideth 30 feet long | Hua Yi Construction AZ, Inc | 38500 | 1 | Steel | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2404172A | 38491.25 | F21P1 WWT package (Installation and 2 batch tanks) | WWT blower GIP&SUS material | Ferguson Enterprises, LLC | 38476.62 | 0.99962 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Steel | Labor | USC23C002 | USC2309037A | 38400 | F21P1-0404_H_Hallway plate install_MICU | Manpower Pay for General Labor for Kate Wu | Hua Yi Construction AZ, Inc | 0 | 0 | Steel | 0 | 0 | UPW | Material
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2304015A | 38334 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Center rings extra for A+B (total) | Pure Plastics, LLC | 38333.4 | 0.99998 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2210036A | 38265.86 | F21P1 WWT package (Installation and 2 batch tanks) | PVC SCH80 Pipes-Litho Fab GF/RHFS | Ryan Herco Flow Solutions | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2303087A | 37536 | F21P1 Chemical & WCCS package | CDS system Added BOX Items | Marketech International Corp. | 0 | 0 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2407088A | 37436.5 | F21P1 WWT package (Installation and 2 batch tanks) | CGS Global Support Onsite Manpower | CGS Global Support, LLC | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Outsourcing
Base-Build | WWT | Mechanical | Material | USC21C014 | USCSB2306011A | 37066.92 | F21P1 WH2SO4 | WRC Material temp use + [CO] Sluge expansion Hopper out | Ferguson Enterprises, LLC | 32171.04 | 0.86792 | Mechanical | Main Contract Scope | WWT | W-H2SO4 | Material
Base-Build | WWT | Electrical | M+L | USC21C009 | USCSB2206012A | 37047.6 | F21P1 WWT package (Installation and 2 batch tanks) | X1 cable tray hanger re-install | Commercial Comm and Electric Inc | 37047.6 | 1 | Electrical | Main Contract Scope | WWT | WWT | CCE
Base-Build | UPW | Mechanical | Material | USC24C008 | USCSB2405060A | 36569.82 | UPW B Side Project | Train 2 Materials from ORGANO | Organo USA, Inc | 36569.82 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2408143A | 36475 | WWT B side Project | PR BMWC WWT - CCR CO-1 | BMWC Constructors, INC. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405056A | 36379 | Chemical & WCCS B Side Project | CHEM_WCCS _Consumable hardware A_QT04357379-1 | Copper State Bolt & Nut Company | 36379 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2312048A | 36096.83 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-FRP-piping-T780AA | BRAHMA GROUP, INC. | 36096.83 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2405103A | 35730.22 | F21P1 WWT package (Installation and 2 batch tanks) | WWT A side Heat Exchanger Insulation | Marquis Construction Services LLC | 35730.22 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | Low Voltage | Others | QAQC | USC21C007 | USCSB2306015A | 35689.15 | F21P1 VOC package （Installation ) | TIG 3rd party inspections | Technical Inspections Group | 35689.15 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | Low Voltage | Base-Build | Labor
Base-Build | WWT | Electrical | Instrument | USC24C006 | USCSB2406089A | 35680.03 | WWT B side Project | WWT B Side Instrument Batch 2 | Mega Union Technology Inc. | 0 | 0 | Electrical | Main Contract Scope | WWT | WWT
Base-Build | Low Voltage | Electrical | M+L | USC21C013 | USCSB2404153A | 35004 | F21P1 AMC THC Monitoring System | F21 P1 WRC Building Flow meters & Temp installation engineering of stack | Welmade Technology Corporation | 35004 | 1 | Electrical | DCR Scope | Low Voltage | AMC THC | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2407116A | 34994.9 | Chemical & WCCS B Side Project | F21P1 Bside WCCS-SUS Spare & Combine Valve | Arizona/Albuquerque Valve & Fitting Corp. | 0 | 0 | Mechanical |  |  | Chemical
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2310044A | 34978 | WWT Change Order (Piping) | WWT -BMWC -X123(WWT Tunnel Trestle scope - Change order for continuing priority lines) | BMWC Constructors, INC. | 34978 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Electrical | Material | USC24C006 | USCSB2407041A | 34977.25 | WWT B side Project | A site punch | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical |  |  | WWT
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2212005A | 34810 | F21P1 WWT package (Installation and 2 batch tanks) | Alliance - trucking cost 910AA/AB TANKS | Alliance Industrial Group, LLC | 34810 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403086A | 34789.81 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Bolt Sets_Copper State(B side) | Copper State Bolt & Nut Company | 34789.81 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | M+L | USC21C003 | USCSB2311134A | 34700 | F21P1 UPW | UPW-ladder lock | Scenic Industries, LLC | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2312078A | 34626 | F21P1 Chemical & WCCS package | CDS DHL Upper level walking steps for A side two catwalks | Milling Machinery, Inc. | 34626 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Low Voltage | Electrical | Labor | USC22C001 | USCSB2310104A | 34525 | F21 P1 Office and WH Security and CCTV | F21 Warehouse CCTV Engineering | Hua Yi Construction AZ, Inc | 34525 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Material
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2309068A | 34398 | WWT Change Order (Piping) | WWT -BMWC mobilization and support | BMWC Constructors, INC. | 34398 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | Labor | USC23C045 | USCSB2403272A | 34293 | WWT Change Order (Piping) | WWT: HPM L10/L20 Rack Fabrication and Installation | Milling Machinery, Inc. | 34293 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | Base-Build | Others | Site Expense | USC21C008 | USCSB2210052A | 34272 | F21P1 CCTV & Security | Radio Rental | Code Red Safety & Rental, LLC | 32009.13 | 0.93397 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404064A | 34257.6 | WWT B side Project | WWT PVC Glue & Primer | Harrington Industrial Plastics LLC | 34257.6 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Material | USC21C007 | USCSB2403091A | 34098 | F21P1 VOC package （Installation ) | VOC System K-type wire and temperature controller | Desiccant Technology Corporation | 34098 | 1 | Electrical | Main Contract Scope | Low Voltage | VOC | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401090A | 33942.12 | F21P1 Chemical & WCCS package | CDS ASRS Leakage detector | Marketech International Corp. | 33942.12 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2307084A | 33789 | F21P1 UPW | 8-97 MA-174 Additional Scope L20 to L30 Added Valves | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2303023A | 33476 | F21P1 Chemical & WCCS package | 8-400A breakers in UIS' panels for CDS and SDS PPBs. | LayerZero Power Systems, Inc. | 33476 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Low Voltage | Electrical | Material | USC21C012 | USC2111028A | 33250 | F21 Barcode RFID System | alarm,wall-mounted | Galaxy3 LLC | 33250 | 1 | Electrical | Main Contract Scope | Low Voltage | Barcode | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309139A | 33000 | F21P1 Chemical & WCCS package | 90 deg Coax elbows (Spare parts). | SEMITORR GROUP, LLC | 33000 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2309100A | 33000 | F21P1 WWT package (Installation and 2 batch tanks) | Mini-Line Certificate(batch 1/2) | Page Southerland Page, Inc. | 8250 | 0.25 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | Base-Build | Labor
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2309102A | 33000 | F21P1 UPW | Mini-Line Certificate(batch 2/2) | Page Southerland Page, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | UPW | Base-Build | Labor
Base-Build | Base-Build | Others | Site Expense | USC23C058 | USCSB2310187A | 32813.63 | F21 EUV Steel Plates | MIC EUV Crane Temp Power Final Removal | Commercial Comm and Electric Inc | 32813.63 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Other Scope
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2311094A | 32775.86 | F21P1 Slurry package | Southwest Fastener Monthly Order for Chemical Team 11/2023~01/2024 | Southwest Fastener Division of NEFCO | 31213.36 | 0.95233 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2403050A | 32705.6 | WWT Change Order (Piping) | WWT SUS SCH40 Pipes_20240305 (A Side) | Ferguson Enterprises, LLC | 32705.6 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2404148A | 32584 | F21P1 UPW | UPW-UMEC-COs for CE148 and 157 | University Mechanical & Engineering Contractors, Inc. | 28256 | 0.86717 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Low Voltage | Electrical | M+L | USC21C007 | USCSB2207012A | 32497.3 | F21P1 VOC package （Installation ) | VOC Cable Tray Change Order #2 | Spectra Electrical Services, Inc. | 32497.3 | 1 | Electrical | CO Scope (adding/additional scope) | Low Voltage | VOC | Labor
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2204006A | 32427 | F21P1 Slurry package | Slurry system panels | Kelso-Burnett Co. | 32427 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Equipment
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2305030A | 32388 | F21P1 UPW | UPW CO-PVDF0025 clash | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Civil | M+L | USC22C022 | USCSB2306099A | 32381 | F21P1 Triazole treatment system | WWT Triazole pads | Degan Construction LLC | 30981 | 0.95676 | Civil | Main Contract Scope | WWT | Triazole | Material
Base-Build | WWT | Civil | M+L | USC22C022 | USCSB2307065A | 32051 | F21P1 Triazole treatment system | TSMC WRC Pump Pads(WWT Triazole epoxy) | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 32051 | 1 | Civil | Main Contract Scope | WWT | Triazole | Scaffolding
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2305002A | 31941.1 | F21P1 WWT package (Installation and 2 batch tanks) | WWT material for drain & system | Mega Union Technology Inc. | 31941.1 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2310138A | 31920.87 | F21P1 WWT package (Installation and 2 batch tanks) | 10/21/23 to 11/20/23 Southwest Fastener Monthly Order for Water Team | Southwest Fastener Division of NEFCO | 31920.87 | 1 | Mechanical | Main Contract Scope | WWT | Water | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USC2111051A | 31860 | F21P1 Chemical & WCCS package | Ball Valve | Harrington Industrial Plastics LLC | 31860 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2308010A | 31839.45 | F21P1 UPW | UPW HP1037 & HP1137 Additional DS(TSMC F21P1 UPW Electrical and Controls) | Rosendin Electric, Inc. | 28655.51 | 0.9 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | Chemical | Mechanical | E2 | USC21C005 | USCSB2312007A | 31800 | F21P1 Chemical & WCCS package | CDS expansion joint F1 lorry | HONGDONG INTERNATIONAL CO., LTD | 31800 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402112A | 31582.96 | F21P1 Chemical & WCCS package | CDS Materials for CRG | Southwest Fastener Division of NEFCO | 19413.05 | 0.61467 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2401071A | 31552 | F21P1 UPW | UPW-ORGANO-ACM-C-added PVDF | Organo USA, Inc | 31552 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2202011A | 31200 | F21P1 WWT package (Installation and 2 batch tanks) | Modular pipe support assembly design (Tunnel section) | The Blackfin Group | 31200 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C008 | USCSB2112001A | 31129 | F21P1 CCTV & Security | tsmc security 4th floor | AEGISTEK SYSTEMS CO., LTD. | 31129 | 1 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2307035A | 31004 | F21P1 UPW | TSMC UPW Package-CO-Add | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2307089A | 30843 | F21P1 UPW | 8-112 Sight Glass Reinforcement | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | Main Contract Scope | UPW | UPW | UMEC
Base-Build | UPW | Electrical | Material | USC21C003 | USC2112005A | 30764 | F21P1 UPW | SDI analyzer | MABAT Chemical systems Ltd | 30764 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | UPW | Electrical | Labor | USC22C009 | USCSB2403232A | 30720 | F21P1 230kV MTR Oil and Drain Pipe work | UPW DC Bank Panel to Panel Termination & Cable Pull | Mirador Construction Service, LLC | 30720 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404212A | 30690 | WWT B side Project | WWT PVC Glue & Primer_20240429 | Harrington Industrial Plastics LLC | 30690 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2210009A | 30498.48 | F21P1 UPW | UPW A Side Disconnect Switch Stands Change Order | Rosendin Electric, Inc. | 30498.48 | 1 | Electrical | Main Contract Scope | UPW | UPW | Rosendin
Base-Build | Chemical | Others | Labor | USC21C005 | USCSB2205030A | 30450 | F21P1 Chemical & WCCS package | Lorry Building Rack Design | The Blackfin Group | 30450 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | CDS | Base-Build | Labor
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405176A | 30281.9 | WWT B side Project | WWT Ball Valves Purchase(A & B side) | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Mechanical | Material | USC21C007 | USCSB2307130A | 30080 | F21P1 VOC package （Installation ) | 5222329-059- THC Scope_Added Material | Southland Industries | 30080 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | AMC THC | Southland
Base-Build | WWT | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2209005A | 30000 | F21P1 WWT package (Installation and 2 batch tanks) | MRT Design-Additional Services amendment | MRT DESIGN LLC | 27500 | 0.91667 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | Chemical | Others | QAQC | USC21C005 | USCSB2310057A | 30000 | F21P1 Chemical & WCCS package | FAB B Chemical/ UPW Permitting(batch1/2) | KAEKO, Inc | 30000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Base-Build | Labor
Base-Build | Chemical | Mechanical | Labor | USC24C005 | USCSB2407142A | 29740.47 | Chemical & WCCS B Side Project | CHEM_Addition project for B side DHL's walking path | CRG International | 0 | 0 | Mechanical |  |  | Chemical
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2310074A | 29376 | F21P1 Chemical & WCCS package | CDS Platform 3 Raised Grating | Milling Machinery, Inc. | 29376 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2406124A | 29353.4 | WWT B side Project | F21 A Side Lorry Expansion Joint | United Integrated Services (USA) Corp | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Low Voltage | Electrical | Material | USC21C008 | USCSB2206020A | 29328 | F21P1 CCTV & Security | GOWN Power Panel | Kelso-Burnett Co. | 29328 | 1 | Electrical | The budget execution does not pertain to this project | 0 | CCTV | Equipment
Base-Build | Low Voltage | Others | QAQC | USC22C001 | USCSB2306074A | 29150 | F21 P1 Office and WH Security and CCTV | PD Sensor Installation and Transformer Testing | Shermco Industries, Inc. | 29150 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | CCTV | Labor
Base-Build | Chemical | Mechanical | M+L | USC23C012 | USCSB2306108A | 29119 | F21P1 Hot DI Machine Hookup | Hot DI piping | University Mechanical & Engineering Contractors, Inc. | 27663 | 0.95 | Mechanical | 0 | 0 | Hot DI | UMEC
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2404079A | 28868.8 | Chemical & WCCS B Side Project | PVDF料補齊.1 20240408 | Harrington Industrial Plastics LLC | 28868.8 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Instrument | USC23C045 | USCSB2310071A | 28785 | WWT Change Order (Piping) | WWT FAB/WWT centralizer | Pure Plastics, LLC | 28785 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2407013A | 28521 | Chemical & WCCS B Side Project | F21P1 HPM CDU/DHL CDA/GN2 | SEMITORR GROUP, LLC | 28521 | 1 | Mechanical |  |  | Chemical
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2306084A | 28251 | F21P1 Chemical & WCCS package | 1000 Series Pump Support Base | Milling Machinery, Inc. | 25044.75 | 0.88651 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405115A | 28236.06 | Chemical & WCCS B Side Project | CHEM_B side L20/ L30_R-TEE _GN2 | CRG International | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | WWT | Mechanical | M+L | USC21C009 | USCSB2409032A | 27906.25 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - Brahma A-Side Carboline Flange Coating CO-1 | BRAHMA GROUP, INC. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407130A | 27627.47 | WWT B side Project | WWT Termination Fitting for chem lines and missing material for SL2 | Mega Union Technology Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2306095A | 27616 | F21 TMAH System | WWT-T665AA relocation | Milling Machinery, Inc. | 27616 | 1 | Mechanical | Main Contract Scope | WWT | WWT | MMI
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309114A | 27588 | F21P1 Chemical & WCCS package | 90 deg Coax elbows for Chemical team and Harder | GOLD STONE DEVELOPMENT CO., LTD. | 27588 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Electrical | M+L | USC24C007 | USCSB2405122A | 27500 | Low Voltage B Side Project | F21P1 Gown Office Security PFA area Security & CCTV | NUUO US Inc. | 24750 | 0.9 | Electrical | Main Contract Scope | Low Voltage | CCTV
Base-Build | Chemical | Mechanical | Material | USC23C012 | USCSB2302050A | 27484.71 | F21P1 Hot DI Machine Hookup | Hot DI BOX make | FusionHPX LLC | 27484.71 | 1 | Mechanical | 0 | 0 | Hot DI | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406023A | 27420 | Chemical & WCCS B Side Project | TCELC-F21P1 CDS support 追加 quotation | TCELC CO., LTD | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2403183A | 27215.03 | F21P1 Chemical & WCCS package | prep and epoxy housekepping pads in Fab LB1,L10 and L20 37 PADS TOTAL | SD Engineering Technology LLC | 27215.03 | 1 | Mechanical | Main Contract Scope | CDS | Base-Build | Labor
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2406011A | 27214.5 | Chemical & WCCS B Side Project | F21P1 CED Y-Conduit | Consolidated Electrical Distributors Inc | 8592.1 | 0.31572 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303012A | 27164.13 | F21P1 WWT package (Installation and 2 batch tanks) | 20" stub end | Harrington Industrial Plastics LLC | 27164.13 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2311098A | 27061 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Heat Exchanger Additional Support | Milling Machinery, Inc. | 27061 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | Chemical | Steel | Material | USC24C005 | USCSB2407043A | 26940 | Chemical & WCCS B Side Project | CHEM_WCCS SUS project_ for CDS/ SDS VMB supports | TCELC CO., LTD | 26940 | 1 | Steel |  |  | Chemical
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2211023A | 26884.38 | F21P1 WWT package (Installation and 2 batch tanks) | WWT welding machines rentals from Harrington | Harrington Industrial Plastics LLC | 25162.11 | 0.93594 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2205007A | 26856.34 | F21P1 UPW | 2022 Polaris Pro XD Crew Diesel Com 21, Model D22P4ED4B4 Construction site #2 Polaris | Iron City Polaris | 26856.34 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Equipment
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2309088A | 26733 | F21P1 Chemical & WCCS package | Load cell work at Mixing boxes/tanks | Michelli Measurement Group, Inc. | 26733 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | M+L | USC22C021 | USCSB2307023A | 26560 | F21P1 Chemical Lab setup | GC Lab Anchor and Materials | Milling Machinery, Inc. | 26560 | 1 | Mechanical | The budget execution does not pertain to this project | Chemical Lab | Chemical Lab | MMI
Base-Build | Low Voltage | Electrical | Labor | USC21C012 | USCSB2405018A | 26549.6 | F21 Barcode RFID System | F21 P1 parking gates installation-(5/11) | NUUO US Inc. | 0 | 0 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2309051A | 26304.18 | F21P1 Chemical & WCCS package | Lasair III 110 Particle Counter and HPD II-150 High Pressure Diffuser | Particle Measuring Systems, Inc. | 26304.18 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Base-Build | Others | Housekeeping | USC21C007 | USCSB2305078A | 26070.88 | F21P1 VOC package （Installation ) | BHTC housekeeping | BHTC Arizona, LLC | 26070.88 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Housekeeping
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2212047A | 26056.92 | F21P1 WWT package (Installation and 2 batch tanks) | WWT mini line material | Mega Union Technology Global Pte Ltd | 21255.49 | 0.81573 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2212007A | 26000 | F21P1 WWT package (Installation and 2 batch tanks) | WWT CDA cooper tube and fittings | Chien Tai Valves & Pipe Fittings Co. Ltd | 26000 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2308097A | 26000 | F21P1 Chemical & WCCS package | Lorry tank (CDS+WCCS) self-closing swing door. | Degan Construction LLC | 26000 | 1 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2403303A | 25945.36 | F21 TMAH System | B side remaining pipe MU can't supply . | Harrington Industrial Plastics LLC | 25945.36 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | WWT | Mechanical | Material | USC21C014 | USCSB2306010A | 25937.61 | F21P1 WH2SO4 | WRC Material final from Harrington | Harrington Industrial Plastics LLC | 25937.61 | 1 | Mechanical | Main Contract Scope | WWT | W-H2SO4 | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405149A | 25818.75 | WWT B side Project | WWT materials (B side)_WIDOS INSERTS | Ferguson Enterprises, LLC | 25818.75 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204001A | 25719.01 | F21P1 UPW | 2022 Polaris PRO XD Crew Diesel Com 21 902D PROXD, EPS | Iron City Polaris | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Equipment
Base-Build | Low Voltage | Electrical | M+L | USC22C001 | USCSB2409010A | 25656.57 | F21 P1 Office and WH Security and CCTV | F21 P1 VOC Electricity Change Order _CO#25_Batch 3/6 | Spectra Electrical Services, Inc. | 25656.57 | 1 | Electrical |  |  | CCTV
Base-Build | UPW | Steel | M+L | USC21C005 | USCSB2306086A | 25630 | F21P1 Chemical & WCCS package | WRC Acid Zone UPW Stair | Milling Machinery, Inc. | 25630 | 1 | Steel | Main Contract Scope | UPW | UPW | MMI
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402226A | 25628.6 | F21P1 Chemical & WCCS package | CDS Cush Clamps | Southwest Fastener Division of NEFCO | 25626.6 | 0.99992 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2304056A | 25626 | F21P1 Chemical & WCCS package | CDS Additional EQ Relocation | Milling Machinery, Inc. | 25626 | 1 | Mechanical | DCR Scope | CDS | Chemical | MMI
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2210035A | 25364.67 | F21P1 WWT package (Installation and 2 batch tanks) | PVC SCH80 Fittings Litho Fab Spears | Harrington Industrial Plastics LLC | 25364.67 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Civil | M+L | USC23C045 | USCSB2401218A | 25247.39 | WWT Change Order (Piping) | WWW-HKPs epoxy | SD Engineering Technology LLC | 25247.39 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404225A | 25213.35 | WWT B side Project | WWT Fittings for O3_20240429 (B Side) | Harrington Industrial Plastics LLC | 25213.35 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USC2112028A | 25074.45 | F21P1 UPW | vortex flowmeter | Oval Corporation of America | 25074.45 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2402009A | 25009 | WWT Change Order (Piping) | UMEC overtime for Blackout Testing Sunday Work | University Mechanical & Engineering Contractors, Inc. | 25009 | 1 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | Chemical | Mechanical | Labor | USC23C042 | USCSB2306129A | 25007 | F21P1 Chemical Safety Cabinet Installation | Safety Cabinet Move-in | Milling Machinery, Inc. | 25007 | 1 | Mechanical | Main Contract Scope | Chemical Lab | chemical safety cabinet | MIMO/Rigging
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2403075A | 24859 | F21P1 Chemical & WCCS package | CDS UPW - 8-194 Chem UPW Loops | University Mechanical & Engineering Contractors, Inc. | 24859 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | UMEC
Base-Build | Base-Build | Others | Site Expense | USC21C014 | USCSB2308066A | 24830 | F21P1 WH2SO4 | MIC Three and Seven Trailer Hookup | Wilson Electric Services Corporation | 24830 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Low Voltage | Electrical | M+L | USC24C007 | USCSB2409005A | 24728 | Low Voltage B Side Project | F21 P1 VOC Electricity Change Order _CO#32,CO#33,CO#34,CO#36,CO#40 | Spectra Electrical Services, Inc. | 24728 | 1 | Electrical |  |  | VOC
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2403257A | 24635 | F21P1 Chemical & WCCS package | 24-097 CDS Platform 3 Move Quote (cat work move) | Milling Machinery, Inc. | 24635 | 1 | Mechanical | DCR Scope | CDS | Chemical | MIMO/Rigging
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2301029A | 24616 | F21P1 Chemical & WCCS package | Third - Breaker | Third Enterprise | 24616 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Others | Labor | USC24C005 | USCSB2404060A | 24562.5 | Chemical & WCCS B Side Project | FAB A SDS, CDS, WCCS Pressure Test | LSW Engineers Arizona, Inc. | 18740 | 0.76295 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404216A | 24493.17 | WWT B side Project | WWT Ball Valve&Cap_20240426 (B Side) | Supertung Industrial Co., Ltd. | 24493.17 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2312014A | 24435 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - FRP Bond (55) Post on TMAH Tanks for Handrail | Harrington Industrial Plastics LLC | 24435 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404204A | 24411 | WWT B side Project | WWT DS & LCB (B side material) | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2110011A | 24306 | F21P1 WWT package (Installation and 2 batch tanks) | WWT CS Tank Inspection | Technical Inspections Group | 24306 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C001 | USCSB2111004A | 24299 | tsmc AZ Temporary Office Physical Security | CCTV System | AEGISTEK SYSTEMS CO., LTD. | 24299 | 1 | Electrical | Main Contract Scope | Low Voltage | Speed Gate | Material
Base-Build | Low Voltage | Others | QAQC | USC21C013 | USCSB2312185A | 24195 | F21P1 AMC THC Monitoring System | FAB B VOC Electrical CA service | LSW Engineers Arizona, Inc. | 5718 | 0.23633 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | VOC | Labor
Base-Build | Base-Build | Others | Site Expense | USC23C040 | USCSB2305100A | 23981.12 | TSMC F21 Clean Room Suit | Industrial Coverall with Hood | Sunrise Phoenix Hi-Tech LLC | 23981.12 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2406086A | 23942.3 | WWT B side Project | WWT Ball Valve_20240613 (B Side) | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2401079A | 23928 | F21P1 Slurry package | SDS Slurry A side plates | Milling Machinery, Inc. | 23928 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | MMI
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2206026A | 23901 | F21P1 WWT package (Installation and 2 batch tanks) | 3rd party QC for CS tanks | Weld Spec, Inc. | 23764.38 | 0.99428 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | Base-Build | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USC2112002A | 23872.51 | F21P1 Chemical & WCCS package | Ball Valve | Ryan Herco Flow Solutions | 23872.52 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C002 | USCSB2111005A | 23843 | TSMC AZ Temp Office Speed Gate | Access Systrm | AEGISTEK SYSTEMS CO., LTD. | 23843 | 1 | Electrical | Main Contract Scope | Low Voltage | Speed Gate | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2307101A | 23810 | F21 TMAH System | MIC T-140AA Lining | Milling Machinery, Inc. | 23810 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | MMI
Base-Build | UPW | Electrical | Material | USC21C003 | USC2111034A | 23801.52 | F21P1 UPW | Hydrogen Peroxide Analyzer | Precision Integrated Systems, LLC | 23701.52 | 0.9958 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Others | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2405129A | 23750 | WWT B side Project | WWT T-780BABB Header rigging | Greenberry Industrial | 23750 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | MIMO/Rigging
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2407001A | 23743.52 | Chemical & WCCS B Side Project | CED 化學系統電力訊號五金0627 (CED Chem Signal Cable Hardware) | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical |  |  | Chemical
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2308044A | 23550.84 | WWT Change Order (Piping) | WWT -Sludge/Triazole shortage materials | Ferguson Enterprises, LLC | 13848.24 | 0.58801 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2306131A | 23500 | F21 TMAH System | Taiwan D180/225 MU material | Mega Union Technology Inc. | 23500 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | WWT | Steel | Labor | USC23C014 | USCSB2304005A | 23225 | F21P1 Labor incentive program-MICU | 2022, 2023 holiday incentive (Nov, Dec, Jan) | Greenberry Industrial | 0 | 0 | Steel |  |  | WWT | Greenberry
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2308046A | 23172 | F21P1 UPW | TSMC UPW – 8-128 WRC HCl Flange Break | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2307049A | 23119.22 | F21 TMAH System | Big / Small size bolts | Copper State Bolt & Nut Company | 23119.22 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402146A | 22575.43 | F21P1 WWT package (Installation and 2 batch tanks) | WWT PTFE coating bolt | LIGHTNING BOLT & SUPPLY, INC. | 22575.43 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Mechanical | Material | USC21C013 | USCSB2303022A | 22552.6 | F21P1 AMC THC Monitoring System | Dual-Stage Pressure Regulator | Matheson Tri-Gac Inc. | 22552.6 | 1 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Equipment
Base-Build | Low Voltage | Electrical | Labor | USC21C008 | USCSB2209013A | 22499.56 | F21P1 CCTV & Security | TSMC Dunlap Office turnstile and metal detector installation | BPG Technologies, LLC | 22499.56 | 1 | Electrical | The budget execution does not pertain to this project | 0 | CCTV | Labor
Base-Build | WWT | Electrical | Instrument | USC21C004 | USCSB2306019A | 22178.07 | F21P1 WWT package （USA EQ-FRP tank) | WWT -HACH-lab | Hach Company | 22178.07 | 1 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2311018A | 22098 | WWT Change Order (Piping) | WWT-Ysgasket | Yingsheng Applied Materials Co., Ltd | 22098 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2302055A | 22070.94 | F21P1 Chemical & WCCS package | New box PP make | Pure Plastics, LLC | 22070.94 | 1 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2203011A | 22016 | F21P1 WWT package (Installation and 2 batch tanks) | Outsourcing Service General Worker | CGS Global Support, LLC | 21764.47 | 0.98858 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Outsourcing
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2309082A | 22000 | F21P1 UPW | Battery Charge B Side 10 Cabinets | Gruber Industries | 22000 | 1 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2312018A | 21922 | F21 TMAH System | Tmah ACF expansion EQ move in | Milling Machinery, Inc. | 21922 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | MIMO/Rigging
Base-Build | WWT | Mechanical | M+L | USC24C006 | USCSB2408066A | 21911.91 | WWT B side Project | WWT LSR system - Okland | Okland Construction Company, Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC21C008 | USCSB2205002A | 21616 | F21P1 CCTV & Security | MIC Modular Office Fiber | Chunghwa Telecom Global, Inc | 21616 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | Internet
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2406121A | 21551.14 | F21P1 Chemical & WCCS package | [Pure] SS box door | Pure Plastics, LLC | 15085.8 | 0.7 | Mechanical |  |  | Chemical
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2311027A | 21528.4 | WWT Change Order (Piping) | Hand tools for TW team | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402001A | 21400 | F21P1 Chemical & WCCS package | CDS B side support L30 coating | Milling Machinery, Inc. | 21400 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Chemical | Mechanical | M+L | USC22C021 | USCSB2309048A | 21374 | F21P1 Chemical Lab setup | 8-134 FAB Gas Chem Lab Hook-Up Reroute(GC Lab Piping Change Order) | University Mechanical & Engineering Contractors, Inc. | 20306 | 0.95003 | Mechanical | The budget execution does not pertain to this project | Chemical Lab | Chemical Lab | UMEC
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401263A | 21369.16 | F21P1 Chemical & WCCS package | CDS B side support L30 materials | Southwest Fastener Division of NEFCO | 21369.16 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Electrical | Labor | USC21C001 | USCSB2102001A | 21171 | tsmc AZ Temporary Office Physical Security | AZ temporary office CCTV installation | B&D Industries, Inc. | 0 | 0 | Electrical | Main Contract Scope | Low Voltage | CCTV
Base-Build | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USC2111047A | 21112 | F21P1 Chemical & WCCS package | power panels for Chemical system | OEG ISG - Integrated Systems Group | 21112 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Others | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2306046A | 21074.6 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Tanks diamond labels | Pensacola Hardware Company | 21074.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2209004A | 21031.43 | F21P1 UPW | Cushman Hauler Pro-X Elite 2023 Battery operated type is trail green color hood | Pohle NV Center, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2310043A | 20990.4 | WWT Change Order (Piping) | Material for drain PN6 | Mega Union Technology Inc. | 20990.4 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | Labor | USC21C009 | USCSB2402072A | 20700 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Blind Flange installation | Mirador Construction Service, LLC | 20700 | 1 | Steel | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Electrical | Labor | USC24C005 | USCSB2405131A | 20590 | Chemical & WCCS B Side Project | F21P1A L30 Slurry VMB 訊號及氣源管拉設 | DFK Tech, LLC | 0 | 0 | Electrical | DCR Scope | CDS | Chemical
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2404179A | 20160.61 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Fittings for 60606_20240423 (A Side) | Harrington Industrial Plastics LLC | 20160.61 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2406125A | 20109.6 | WWT B side Project | A區系統區閥件追加_球閥及接頭部分 | Mega Union Technology Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2208002A | 20000 | F21P1 UPW | Signal Booster System installation | Galaxy3 LLC | 20000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Steel | M+L | USC21C003 | USCSB2210051A | 20000 | F21P1 UPW | F21P1-FAB LB2-LOOP 2 STAGE modifications | Milling Machinery, Inc. | 20000 | 1 | Steel | Main Contract Scope | UPW | UPW | MMI
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2305035A | 20000 | F21P1 WWT package (Installation and 2 batch tanks) | Shermco Special Inspection | Shermco Industries, Inc. | 18895 | 0.94475 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2307040A | 19961 | F21P1 Chemical & WCCS package | Pure Plastics Pipe Supports | Milling Machinery, Inc. | 19961 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Civil | M+L | USC24C006 | USCSB2408015A | 19907.14 | WWT B side Project | RE: 8 CTI Stripper Pad duct flange sealing with Vinyl | Pride Development & Construction, Inc. | 0 | 0 | Civil |  |  | WWT
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2404185A | 19800 | F21P1 UPW | FAB A UPW Observation (LB1 to L30) | KAEKO, Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | Low Voltage | Electrical | M+L | USC22C019 | USCSB2401074A | 19800 | AMC monitor 595T0 | F21 AMC Reroute and retest fiber engineering | NUUO US Inc. | 17622.5 | 0.89003 | Electrical | CO Scope (adding/additional scope) | Low Voltage | AMC THC | NUUO
Base-Build | Water_Sewer | Civil | M+L | USC21C010 | USCSB2309001A | 19674 | tsmc AZ sewer and water pipeline installation | Fire Hydrant Remove and Replace | Degan Construction LLC | 19674 | 1 | Civil |  |  | Pipeline | Material
Base-Build | Chemical | Others | QAQC | USC24C005 | USCSB2405100A | 19650 | Chemical & WCCS B Side Project | FAB A and Lorry Chemical Electrical Special Observations | LSW Engineers Arizona, Inc. | 7962.5 | 0.40522 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Chemical
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2309042A | 19635 | F21P1 UPW | MMI temp resin move-in | Milling Machinery, Inc. | 19635 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | MIMO/Rigging
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2405124A | 19560 | F21P1 Chemical & WCCS package | A side Scaffolding building-Waste PVDF Submain add support | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 19560 | 1 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209007A | 19396.88 | F21P1 Chemical & WCCS package | AECC License | Autodesk, Inc. | 19396.88 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | Software
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2210007A | 19391.15 | F21P1 UPW | Horiba Conductivity/Resistivity Meter Batch 3 | HORIBA Taiwan, Inc. | 19391.15 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Mechanical | Material | USC21C013 | USCSB2304044A | 19170 | F21P1 AMC THC Monitoring System | Regulator | Welmade Technology Corporation | 19170 | 1 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403144A | 19090.8 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - Field-12 Rental for (120 days) | Harrington Industrial Plastics LLC | 16227.18 | 0.85 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2401115A | 19000 | F21P1 WWT package (Installation and 2 batch tanks) | FRP repair Fab LB2/WRC | Degan Construction LLC | 19000 | 1 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2306093A | 18948.56 | F21 TMAH System | WWT-MU-PVC Sparger | Harrington Industrial Plastics LLC | 18948.56 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407073A | 18936 | WWT B side Project | WWT CrPVC pipes for dump | Harrington Industrial Plastics LLC | 18936 | 1 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404007A | 18932.5 | WWT B side Project | WWT Bside clamp / Copperstate 1st order | Copper State Bolt & Nut Company | 18932.5 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2212052A | 18929.75 | F21P1 UPW | 12/3C w/ Ground BOYG | Consolidated Electrical Distributors Inc | 18929.75 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | Low Voltage | Electrical | Labor | USC21C007 | USCSB2405022A | 18856.6 | F21P1 VOC package （Installation ) | F21 P1 parking gates installation-(9/11) | NUUO US Inc. | 0 | 0 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309018A | 18840 | WWT Change Order (Piping) | WWT -LJ-Miniplast | Harrington Industrial Plastics LLC | 17064.92 | 0.90578 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Mechanical | M+L | USC21C013 | USCSB2311089A | 18831 | F21P1 AMC THC Monitoring System | F21 P1 VOC WWT line temporary support and THC ICA tack of point valves engineering | Hua Yi Construction AZ, Inc | 18831 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | VOC THC | Material
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2305081A | 18824 | F21P1 Chemical & WCCS package | Modify CDS DHL EQ caster wheels | Milling Machinery, Inc. | 18824 | 1 | Mechanical | DCR Scope | CDS | Chemical | MMI
Base-Build | Chemical | Mechanical | Material | USC21C009 | USCSB2312110A | 18788.56 | F21P1 WWT package (Installation and 2 batch tanks) | CDS ICP Mass CDA GN2 regulators and parts to fix design issue by John Wu | GOLD STONE DEVELOPMENT CO., LTD. | 18788.56 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2401148A | 18769.66 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Weld machines rental for PSS | Harrington Industrial Plastics LLC | 18769.66 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2208004A | 18706.07 | F21P1 Chemical & WCCS package | PFA Tubing | Pure Plastics, LLC | 18706.07 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2406028A | 18603.07 | Chemical & WCCS B Side Project | F21P1 B Side material CED - Eletrical/Signal | Consolidated Electrical Distributors Inc | 13207.27 | 0.70995 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2403188A | 18599.9 | F21P1 QR Lab Security & CCTV | F21 P1 Gown Office IT Room speed gate | Aegis Technology Inc | 0 | 0 | Electrical | Main Contract Scope | Low Voltage | CCTV | Labor
Base-Build | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C013 | USCSB2304043A | 18531 | F21P1 AMC THC Monitoring System | Gas Cylinder | Welmade Technology Corporation | 18531 | 1 | Mechanical | Main Contract Scope | Low Voltage | AMC THC | Equipment
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2210040A | 18500 | F21P1 WWT package (Installation and 2 batch tanks) | Blind Flanges for Hydrostatic Testing | Milling Machinery, Inc. | 18500 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | MMI
Base-Build | Chemical | Mechanical | Labor | USC22C021 | USCSB2305041A | 18220 | F21P1 Chemical Lab setup | GC Lab Move-in | Milling Machinery, Inc. | 18220 | 1 | Mechanical | The budget execution does not pertain to this project | Chemical Lab | Chemical Lab | MIMO/Rigging
Base-Build | Chemical | Electrical | Material | USC21C009 | USCSB2312114A | 18142.08 | F21P1 WWT package (Installation and 2 batch tanks) | USC21C006 SLURRY A&B SIDE HUB BOX | Avex-SG Technology Inc. | 18142.08 | 1 | Electrical | 0 | 0 | Slurry | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405146A | 18097.34 | WWT B side Project | WWT Fittings_20240523 (B Side) | Harrington Industrial Plastics LLC | 18097.34 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303071A | 18068.39 | F21P1 WWT package (Installation and 2 batch tanks) | Bolts/Gaskets | Copper State Bolt & Nut Company | 16095.52 | 0.89081 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | M+L | USC22C019 | USCSB2409015A | 17971.39 | AMC monitor 595T0 | F21 P1 VOC Electricity Change Order _CO#30_Batch 2/2 | Spectra Electrical Services, Inc. | 17971.39 | 1 | Electrical |  |  | VOC
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2401257A | 17961 | WWT Change Order (Piping) | WWT Supplemental Material&WWT Premium Time 11.25-11.26 | University Mechanical & Engineering Contractors, Inc. | 17961 | 1 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | WWT | Mechanical | Material | USC22C022 | USCSB2404032A | 17944 | F21P1 Triazole treatment system | copper tubing |  | 0 | 0 | Mechanical | Main Contract Scope | WWT | Triazole | Material
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2210001A | 17880.48 | F21P1 Chemical & WCCS package | Dell Laptop/Dell 27in Monitor | Dell Technologies | 17880.48 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2308159A | 17850 | F21P1 UPW | Horiba Resistivity Meter B Side | HORIBA Taiwan, Inc. | 17850 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Others | QAQC | USC21C013 | USCSB2310096A | 17710 | F21P1 AMC THC Monitoring System | Puressuring testing certificat for THC (A+B) and AMC (B) | LSW Engineers Arizona, Inc. | 6722 | 0.37956 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | AMC THC | Labor
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2312070A | 17619.4 | WWT Change Order (Piping) | MU/Hand welding machines for WWT | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2201006A | 17494.8 | F21P1 WWT package (Installation and 2 batch tanks) | Modular Pipe Support Assembly Design | The Blackfin Group | 17494.8 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2408067A | 17493.45 | WWT B side Project | WWT_ Copper Tube request for B side_茂迅 | SWIFT ENGINEERING CO., LTD. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Low Voltage | Mechanical | M+L | USC21C012 | USCSB2310091A | 17329 | F21 Barcode RFID System | VOC Unistrut Support | Milling Machinery, Inc. | 17329 | 1 | Mechanical | DCR Scope | Low Voltage | VOC | MMI
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2307039A | 17300 | F21P1 Chemical & WCCS package | CO2 Cylinder Move In | Milling Machinery, Inc. | 17300 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MIMO/Rigging
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2311042A | 17280 | F21P1 WWT package (Installation and 2 batch tanks) | install Dikewall around Tank 1985AA | Degan Construction LLC | 17280 | 1 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Electrical | Instrument | USC21C003 | USCSB2406016A | 17250 | F21P1 UPW | WWT B Side Battery Recharge 2_R2 | Gruber Industries | 17250 | 1 | Electrical | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2312169A | 17134.38 | F21P1 UPW | UPW-XHHW500YELcable | Graybar Electric Company, Inc. | 17134.38 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2310072A | 17008 | F21P1 UPW | UPW-UMEC-L20-Enermech-repair | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2405039A | 16900 | F21P1 Slurry package | CDS B side move in Night shift | Milling Machinery, Inc. | 8450 | 0.5 | Mechanical | DCR Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2401250A | 16794.97 | F21P1 WWT package (Installation and 2 batch tanks) | FAB A&B labels | J A Hansen Company DBA Hansen Supply Company | 16767.03 | 0.99834 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2407042A | 16608.23 | Chemical & WCCS B Side Project | EES 防爆接線盒0708 | Elliott Electric Supply, Inc. | 16608.23 | 1 | Electrical |  |  | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2308149A | 16574.85 | F21P1 Chemical & WCCS package | Lorry FNDP room parts for Chemical welding. | SEMITORR GROUP, LLC | 16256.48 | 0.98079 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Electrical | M+L | USC21C007 | USCSB2409009A | 16567.6 | F21P1 VOC package （Installation ) | F21 P1 VOC Electricity Change Order _CO#25_Batch 2/6 | Spectra Electrical Services, Inc. | 16567.6 | 1 | Electrical |  |  | VOC
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2210013A | 16496.16 | F21P1 WWT package (Installation and 2 batch tanks) | F21P1 WWT urgent Hardware | Yingsheng Applied Materials Co., Ltd | 16496.16 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2408030A | 16465.8 | WWT B side Project | WWT_ Copper Tube request for B side. | McMaster-Carr Supply Company | 16423.9 | 0.99746 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2402024A | 16456.08 | WWT Change Order (Piping) | WWT A side remaining unistrut 2024.1E1 | Copper State Bolt & Nut Company | 16456.08 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303040A | 16297.34 | F21P1 WWT package (Installation and 2 batch tanks) | T140 discharge loop | Mega Union Technology Global Pte Ltd | 16297.34 | 1 | Mechanical | CO Scope (adding/additional scope) | WWT | WWT | Equipment
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2302006A | 16264 | F21P1 WWT package (Installation and 2 batch tanks) | Stripper Pad Dike Modification | Sundt Construction, Inc | 15428 | 0.9486 | Civil | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | WWT | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2403230A | 16203.5 | F21P1 WWT package (Installation and 2 batch tanks) | CGS Global Support Onsite Manpower Tent 1 | CGS Global Support, LLC | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | WWT | Labor
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2309132A | 16203 | F21P1 Chemical & WCCS package | CDS L30 Panel Move-in and install. | Milling Machinery, Inc. | 16203 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MIMO/Rigging
Base-Build | WWT | Civil | M+L | USC21C009 | USC2210017A | 16201 | F21P1 WWT package (Installation and 2 batch tanks) | WRC Chem Room Epoxy | Sundt Construction, Inc | 16201 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2308160A | 16181 | F21P1 Chemical & WCCS package | TSMC drum car*5 and Flush car*2 | Yu Cheng Kid Enterprise Co., | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Low Voltage | Mechanical | M+L | USC21C012 | USCSB2310105A | 16000 | F21 Barcode RFID System | F21 P1 VOC WWT line engineering | YAHO System Technology Inc. | 16000 | 1 | Mechanical | Main Contract Scope | Low Voltage | VOC | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309119A | 15992 | F21P1 Chemical & WCCS package | 90 deg Coax elbows. 2"x 1-1/2" be used by YaHo at Lorry FNDP. | GOLD STONE DEVELOPMENT CO., LTD. | 15992 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2112006A | 15956.13 | F21P1 UPW | Module office cabling Work | Galaxy3 LLC | 15956.13 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2311059A | 15916.8 | WWT Change Order (Piping) | WWT 10T Termination Flange | Mega Union Technology Inc. | 15916.8 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2401217A | 15912 | F21P1 WWT package (Installation and 2 batch tanks) | TMAH expansion tank move in | Milling Machinery, Inc. | 15912 | 1 | Steel | Main Contract Scope | WWT | TMAH | Equipment
Base-Build | WWT | Mechanical | M+L | USC23C045 | USCSB2401189A | 15886 | WWT Change Order (Piping) | WWT -24-096 Stripper Platform FRP Ducting Modifications Quote | Milling Machinery, Inc. | 15886 | 1 | Mechanical | Main Contract Scope | WWT | WWT | MMI
Base-Build | WWT | Civil | M+L | USC23C045 | USCSB2311005A | 15749 | WWT Change Order (Piping) | TSMC CO Work for OBR to Install (2) Spacer on the Stripper Ducting. | OBR Cooling Towers, Inc. | 15749 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Civil | M+L | USC21C003 | USCSB2401171A | 15718.13 | F21P1 UPW | UPW-HKPs epoxy | SD Engineering Technology LLC | 15718.13 | 1 | Civil | Main Contract Scope | UPW | UPW | Labor
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405075A | 15686.9 | Chemical & WCCS B Side Project | CHEM_WCCS SUS project_LINDE_ ARGON, REFRIGERATED LIQUID*30pcs | Linde Gas and Equipment Inc | 15536.12 | 0.99039 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2402278A | 15659 | F21P1 Chemical & WCCS package | CDS UPW - 8-189 TMAH Interface Modification L10 | University Mechanical & Engineering Contractors, Inc. | 15659 | 1 | Mechanical | The budget execution does not pertain to this project | Chemical | UPW and Chemical | UMEC
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402224A | 15633.2 | F21P1 WWT package (Installation and 2 batch tanks) | WWT E2 missing material 202402 | Harrington Industrial Plastics LLC | 15633.2 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Steel | Material | USC21C009 | USCSB2401042A | 15598 | F21P1 WWT package (Installation and 2 batch tanks) | CDS galvanized 4*4 cm-10ft(L) | TCELC CO., LTD | 15598 | 1 | Steel | 0 | 0 | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2212024A | 15545.13 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Mini Line missing material | Harrington Industrial Plastics LLC | 15520.28 | 0.9984 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | M+L | USC21C011 | USCSB2404014A | 15526 | F21 TMAH System | WWT: Fabricate and Install (2) Ladders for TMAH Expansion | Milling Machinery, Inc. | 15526 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | Chemical | Mechanical | M+L | USC24C005 | USCSB2406060A | 15500 | Chemical & WCCS B Side Project | F21P1 B Side Lorry to CDU & DHL to CDU CPVC installation | Aidant Fire Protection | 15500 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402259A | 15490.8 | F21P1 Chemical & WCCS package | CDS VCR parts etc | Arizona/Albuquerque Valve & Fitting Corp. | 15490.8 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Civil | M+L | USC24C006 | USCSB2408078A | 15472 | WWT B side Project | WWT - Lower Level Guage Assembly Tee's | Pride Development & Construction, Inc. | 0 | 0 | Civil |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402131A | 15421.2 | F21P1 Chemical & WCCS package | CDS Pipes and fittings, etc | Harrington Industrial Plastics LLC | 15421.2 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2210053A | 15402.62 | F21P1 WWT package (Installation and 2 batch tanks) | 7 Davit Arms and Manways Install | Process Service Specialists, LLC of Delaware | 14632.49 | 0.95 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2209022A | 15393.94 | F21P1 QR Lab Security & CCTV | F21P1 OWMC_Security&CCTV Package | Aegis Technology Inc | 0 | 0 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | Low Voltage | Electrical | Labor | USC21C001 | USCSB2102002A | 15248 | tsmc AZ Temporary Office Physical Security | Metal gate installation | B&D Industries, Inc. | 0 | 0 | Electrical | Main Contract Scope | Low Voltage | CCTV
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2212043A | 15105 | F21P1 UPW | XHHW 1/0 STR GRN | Consolidated Electrical Distributors Inc | 15105 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Others | QAQC | USC21C005 | USCSB2307134A | 15000 | F21P1 Chemical & WCCS package | Lorry PFD Appeal Chang Order | KAEKO, Inc | 15000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Base-Build | Labor
Base-Build | Chemical | Others | QAQC | USC21C005 | USCSB2307136A | 15000 | F21P1 Chemical & WCCS package | FAB PFD Appeal Change Order | KAEKO, Inc | 15000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Base-Build | Labor
Base-Build | WWT | Others | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2304047A | 14878.3 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Tanks tags | PostNet of Anthem, LLC | 11361.32 | 0.76362 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2211005A | 14770 | F21P1 WWT package (Installation and 2 batch tanks) | TSMC-Grounding & Permitting Herc/MIC Rentals | Wilson Electric Services Corporation | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | WWT | Site Expense
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2408136A | 14700 | WWT B side Project | WWT B Side Electrical DS Stand | Greenberry Industrial | 0 | 0 | Steel |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405134A | 14662.5 | Chemical & WCCS B Side Project | 2" SUS Pipe Bending Reuqest--400R | Chukar SB&F LLC | 14662.5 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2406132A | 14641.06 | WWT B side Project | 0613 缺料明細材料報價 | Mega Union Technology Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Civil | M+L | USC24C006 | USCSB2409080A | 14474.5 | WWT B side Project | WWT change order (Galvanized Bar-Grate) from TSMC in the Fab | Pride Development & Construction, Inc. | 0 | 0 | Civil |  |  | WWT
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2309045A | 14472 | F21P1 UPW | MMI-WRC-L20-RO rack modify | Milling Machinery, Inc. | 14472 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | MMI
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402025A | 14238 | F21P1 Chemical & WCCS package | CDS 1" CPVC and Coupling | Harrington Industrial Plastics LLC | 14238 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2311025A | 14216 | F21P1 UPW | UPW-UMEC-skid repair-3 | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | Main Contract Scope | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2403084A | 14189.19 | F21P1 WWT package （USA EQ-FRP tank) | WWT - T-135AA Repair(MMI will reimburse) | Harrington Industrial Plastics LLC | 14189.19 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405092A | 14175 | Chemical & WCCS B Side Project | CHEM_ HANSEN_ Chemical label | J A Hansen Company DBA Hansen Supply Company | 14175 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Others | QAQC | USC21C013 | USCSB2311077A | 14160 | F21P1 AMC THC Monitoring System | FAB 1A VOC, AMC, THC CA Support (Electrical) | LSW Engineers Arizona, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | VOC THC | Labor
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402022A | 14128.04 | F21P1 Chemical & WCCS package | CDS LB2 SS parts | SEMITORR GROUP, LLC | 14077.5 | 0.99642 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Electrical | QAQC | USC21C005 | USCSB2306026A | 14100 | F21P1 Chemical & WCCS package | Particle Test Service | Propersys Corp | 14100 | 1 | Electrical | DCR Scope | CDS | Chemical | Labor
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2306091A | 14090 | F21P1 Chemical & WCCS package | Lorry Pipe Crossover Platform | Milling Machinery, Inc. | 14090 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2305088A | 14045.1 | F21P1 Chemical & WCCS package | MIC F21 Commission Requirements-Swagelok | Arizona/Albuquerque Valve & Fitting Corp. | 14045.1 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407115A | 13977.68 | WWT B side Project | WWT B區工程缺料 | Harrington Industrial Plastics LLC | 150.36 | 0.010757 | Mechanical |  |  | WWT
Base-Build | Low Voltage | Electrical | M+L | USC21C008 | USCSB2402049A | 13954 | F21P1 CCTV & Security | VOC Electric CO17&CO28 | Spectra Electrical Services, Inc. | 13954 | 1 | Electrical | CO Scope (adding/additional scope) | Low Voltage | VOC | Labor
Base-Build | Chemical | Mechanical | Labor | USC23C042 | USCSB2307072A | 13811.04 | F21P1 Chemical Safety Cabinet Installation | F21 Emergency Cabinets B-2 | Milling Machinery, Inc. | 13811.04 | 1 | Mechanical | Main Contract Scope | Chemical Lab | chemical safety cabinet | MMI
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2303032A | 13736.09 | F21P1 Chemical & WCCS package | 16AWG-3/C 600V Shielded wire | Consolidated Electrical Distributors Inc | 13736.09 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2407028A | 13684.48 | WWT B side Project | Modify 6 Beams on Cable Tray Rack LB2 B side | Greenberry Industrial | 0 | 0 | Steel |  |  | WWT
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2407149A | 13675 | UPW B Side Project | MA 200 Pipe Adjustment_UPW | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical |  |  | UPW
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2403134A | 13654.97 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - GB-PCO 108- Common Rack addition 6/N.5 | Greenberry Industrial | 12972.22 | 0.95 | Steel | DCR Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2403260A | 13626.15 | WWT Change Order (Piping) | WWT-FRP-piping-T780&710 repair (A side) | BRAHMA GROUP, INC. | 13626.15 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Site Expense | USC23C045 | USCSB2403217A | 13585 | WWT Change Order (Piping) | U-Line - Taiwan Installer team | U-Line Corporation | 12350 | 0.90909 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Low Voltage | Electrical | Material | USC21C008 | USCSB2207019A | 13536 | F21P1 CCTV & Security | TSMC Warehouse Panels | Kelso-Burnett Co. | 13536 | 1 | Electrical | The budget execution does not pertain to this project | 0 | CCTV | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407128A | 13446.8 | WWT B side Project | 儀表管路需求 Mateials for pipeline_WWT | SEMITORR GROUP, LLC | 1450.43 | 0.10786 | Mechanical |  |  | WWT
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2407089A | 13355.75 | WWT B side Project | T-780BA/BB handrail fabrication and installation_WWT | Greenberry Industrial | 0 | 0 | Steel |  |  | WWT
Base-Build | WWT | Steel | M+L | USC23C045 | USCSB2309020A | 13345 | WWT Change Order (Piping) | WWT-LB2 rack modification | Greenberry Industrial | 12677.75 | 0.95 | Steel | DCR Scope | WWT | WWT | Greenberry
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2403207A | 13343.35 | WWT Change Order (Piping) | WWT Caps_20240319 | Ferguson Enterprises, LLC | 13343.35 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2312196A | 13300 | F21P1 UPW | UPW-swing gate train B | Degan Construction LLC | 13300 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Mechanical | Labor | USC22C020 | USCSB2309149A | 13281.46 | F21P1 Penetration Pipe | WWT-LB1 embedded pipes | Process Service Specialists, LLC of Delaware | 0 | 0 | Mechanical | Main Contract Scope | WWT | Penetration Pipe | PSS
Base-Build | UPW | Mechanical | M+L | USC22C009 | USCSB2402230A | 13236 | F21P1 230kV MTR Oil and Drain Pipe work | UPW-UMEC-COs for ORGANO180, 183 and 186 | University Mechanical & Engineering Contractors, Inc. | 12574 | 0.94998 | Mechanical | Main Contract Scope | UPW | UPW | UMEC
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2406151A | 13230 | Chemical & WCCS B Side Project | CED 化學系統電力訊號線0627 (CED Cat 6 Plenum Rated Cable) | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical |  |  | Chemical
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2406063A | 13168.2 | F21 TMAH System | WWT - Harrington Fusion Machine Rental TMAH EXP | Harrington Industrial Plastics LLC | 10754.03 | 0.81667 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C010 | USCSB2407110A | 13158 | tsmc AZ sewer and water pipeline installation | CGS Global Support Onsite Manpower | CGS Global Support, LLC | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Outsourcing
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2209001A | 13115.52 | F21P1 UPW | Tunnel GF fix point fitting | Organo USA, Inc | 13115.52 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Others | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2402276A | 13050 | F21 TMAH System | Un install and re install steel for tank move in | Greenberry Industrial | 12397.5 | 0.95 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | WWT | TMAH | MIMO/Rigging
Base-Build | WWT | Mechanical | Labor | USC22C022 | USCSB2403107A | 12999 | F21P1 Triazole treatment system | 03/10 overtime work to finish triazole | University Mechanical & Engineering Contractors, Inc. | 12999 | 1 | Mechanical | Main Contract Scope | WWT | Triazole | UMEC
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2308135A | 12959.18 | F21P1 Chemical & WCCS package | Southwest Fastener Monthly Order | Southwest Fastener Division of NEFCO | 12586.95 | 0.97128 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2308067A | 12950 | F21P1 UPW | WRC UPW Electrical Permit Drawing Revision | KAEKO, Inc | 12900 | 0.99614 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2208010A | 12903.68 | F21P1 UPW | UPW Prominent H2O2 Analyzer | Precision Integrated Systems, LLC | 12903.68 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Electrical | Instrument | USC21C009 | USCSB2304041A | 12854.23 | F21P1 WWT package (Installation and 2 batch tanks) | WWT NH4 analyzer | Winn Marion Barber, LLC | 12854.23 | 1 | Electrical | CO Scope (adding/additional scope) | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2404222A | 12824.48 | Chemical & WCCS B Side Project | CHEM_WCCS SUS project_hardware 240415020003_ (01-00166939) | Carson Sales Co Inc | 12824.48 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2303041A | 12682.26 | F21P1 UPW | UPW Panel Material | Avex-SG Technology Inc. | 12682.07 | 0.99999 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Others | QAQC | USC21C011 | USCSB2303081A | 12650.88 | F21 TMAH System | Mechanical Inspection | Technical Inspections Group | 12650.88 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405183A | 12603.4 | WWT B side Project | WWT Fittings_20240530 (B Side) | Harrington Industrial Plastics LLC | 6798.02 | 0.53938 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Labor | USC21C014 | USCSB2402083A | 12590 | F21P1 WH2SO4 | Tunnel Thermal Expansion 2.7.24 | Trident Mechanical Services | 0 | 0 | Mechanical | Main Contract Scope | WWT | W-H2SO4 | Trident
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310031A | 12581.2 | F21P1 Chemical & WCCS package | 9/19/23 to 10/20/23 Southwest Fastener Monthly Order for Chemical Team | Southwest Fastener Division of NEFCO | 11365.23 | 0.90335 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404075A | 12563 | WWT B side Project | WWT PVC 10_Pipes_20240408 (B Side) | Harrington Industrial Plastics LLC | 12563 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Electrical | Instrument | USC24C006 | USCSB2404167A | 12555.53 | WWT B side Project | WIRE SECURITY CAGE/ COLLAPSIBLE WIRE CONTAINER WITH CASTERS | Global Equipment Company Inc. | 12555.53 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2211018A | 12549 | F21P1 WWT package (Installation and 2 batch tanks) | Custom flanges and bolts | Milling Machinery, Inc. | 12549 | 1 | Mechanical | Main Contract Scope | WWT | WWT | MMI
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2307092A | 12546.18 | F21P1 Chemical & WCCS package | NFPA Diamond Signs Lorry HPM BSGS CUP | Pensacola Hardware Company | 10758.98 | 0.85755 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2312188A | 12542.98 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Material-A side SUS (77 item 12/21list ) | Ferguson Enterprises, LLC | 12542.98 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2403034A | 12518.62 | WWT Change Order (Piping) | WWT - Replacement Couplings for F21P1 WWT Goulds pumps | Phoenix Pumps, Inc. | 12518.62 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2301009A | 12401.41 | F21P1 UPW | UPW TempCP-2” HP-PP pipes | Harrington Industrial Plastics LLC | 12401.41 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402201A | 12365 | F21P1 WWT package (Installation and 2 batch tanks) | Stripper packing procurement | LANTEC PRODUCTS INC. | 12365 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | M+L | USC21C013 | USCSB2409012A | 12271.61 | F21P1 AMC THC Monitoring System | F21 P1 VOC Electricity Change Order _CO#25_Batch 5/6 | Spectra Electrical Services, Inc. | 12271.61 | 1 | Electrical |  |  | VOC
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2306114A | 12216 | F21P1 UPW | Hach Start up | Hach Company | 12216 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC22C022 | USCSB2304074A | 12154.62 | F21P1 Triazole treatment system | Triazole SUS material | Ferguson Enterprises, LLC | 12154.62 | 1 | Mechanical | Main Contract Scope | WWT | Triazole | Material
Base-Build | WWT | Steel | M+L | USC21C011 | USCSB2403218A | 12152.2 | F21 TMAH System | WWT009 - GB-PCO 110- Remove and Reinstall main rack LB2 B-side supports (N.5-P/19-19.5) | Greenberry Industrial | 11544.59 | 0.95 | Steel | DCR Scope | WWT | WWT | Labor
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208004A | 12122.25 | F21P1 UPW | Fire extinguishers, Inspection | Cintas Corporation | 12122.25 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209008A | 12074.01 | F21P1 Chemical & WCCS package | AutoCAD | Autodesk, Inc. | 12074.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | Software
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2301056A | 12000 | F21P1 WWT package (Installation and 2 batch tanks) | Weld Spec inspection | Weld Spec, Inc. | 9496.5 | 0.79138 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | Low Voltage | Mechanical | M+L | USC22C013 | USCSB2406107A | 12000 | F21P1 QR Lab Security & CCTV | B side VOC duct modification | Greenberry Industrial | 8687.62 | 0.72397 | Mechanical | The budget execution does not pertain to this project | VOC | VOC
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2312020A | 11994 | F21P1 Chemical & WCCS package | CDS 1-1/2"x2" 90 ELBOW 316LEP/304AP | GOLD STONE DEVELOPMENT CO., LTD. | 11994 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC22C022 | USCSB2403119A | 11968 | F21P1 Triazole treatment system | WWT: Triazole Tank Anchoring and Crossover Platform Modification | Milling Machinery, Inc. | 11968 | 1 | Steel | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402266A | 11932.16 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Pipes_20240227 (A Side) | Harrington Industrial Plastics LLC | 11932.16 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Steel | M+L | USC21C007 | USCSB2403284A | 11912 | F21P1 VOC package （Installation ) | VOC Additional Welding - Modifications | Milling Machinery, Inc. | 11912 | 1 | Steel | CO Scope (adding/additional scope) | Low Voltage | VOC | MMI
Base-Build | WWT | Electrical | M+L | USC21C011 | USCSB2401175A | 11900 | F21 TMAH System | WWT-TMAH-LCMSMS-Power | 2000 GOLD LLC | 11900 | 1 | Electrical | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2303060A | 11900 | F21P1 UPW | Tanks aeration pipe | Degan Construction LLC | 11900 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2308147A | 11857.9 | F21P1 Slurry package | Cut slurry CDA/GN2(14 ea) caps and reweld | Southland Industries | 0 | 0 | Mechanical | DCR Scope | SDS | Slurry | Southland
Base-Build | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2304057A | 11803.71 | F21P1 Chemical & WCCS package | F21P1 CDS-01-FNN Integration | FusionHPX LLC | 11803.71 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2310041A | 11648.26 | WWT Change Order (Piping) | WWT Drain Pipe PP PN6 | Harrington Industrial Plastics LLC | 11648.26 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407171A | 11605.69 | WWT B side Project | LB2 VS1380 steel pipes material_WWT | Ferguson Enterprises, LLC | 11605.69 | 1 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304072A | 11591.07 | F21P1 WWT package (Installation and 2 batch tanks) | Sump pipe PVC | Harrington Industrial Plastics LLC | 11591.07 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2210006A | 11545.85 | F21P1 UPW | Horiba Conductivity/Resistivity Meter Batch 2 | HORIBA Taiwan, Inc. | 11545.85 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2403285A | 11530.68 | WWT Change Order (Piping) | WWT Fittings_20240328 (B Side) | Harrington Industrial Plastics LLC | 11530.68 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2304007A | 11402.54 | F21P1 WWT package (Installation and 2 batch tanks) | (2) Sediment Tank Boxes for Sandblasting Lab | Pure Plastics, LLC | 11402.54 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2405116A | 11297 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - Material Modify Chemical Tanks Level Guage to Flange Connection | Harrington Industrial Plastics LLC | 11297 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2404137A | 11250 | Chemical & WCCS B Side Project | CPVC 料補齊.T2 | ZHENGTONG INTERNATIONAL LIMITED | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2405013A | 11135 | F21P1 UPW | Kaoten Foxboro Calibration A Side | Kaoten Scientific Co., Ltd | 11135 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | Low Voltage | Electrical | M+L | USC21C008 | USCSB2409007A | 11099 | F21P1 CCTV & Security | F21 P1 VOC Electricity Change Order _CO#35 | Spectra Electrical Services, Inc. | 11099 | 1 | Electrical |  |  | CCTV
Base-Build | WWT | Mechanical | Material | USC21C003 | USCSB2305112A | 11084.61 | F21P1 UPW | WWT CCB materials | Harrington Industrial Plastics LLC | 11024.98 | 0.99462 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Labor | USC22C021 | USCSB2401174A | 11081 | F21P1 Chemical Lab setup | GC Lab Pressure Test | University Mechanical & Engineering Contractors, Inc. | 11081 | 1 | Mechanical | The budget execution does not pertain to this project | Chemical Lab | Chemical Lab | UMEC
Base-Build | Chemical | Electrical | Material | USC21C006 | USCSB2402170A | 11057.3 | F21P1 Slurry package | CDS Divider_HPM_MIC_EA001_24_AZ03 | JY TECHS INC. | 11057.3 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2312059A | 11030.8 | F21P1 Chemical & WCCS package | CDS Argon for Chemical welding. Blanket order | Linde Gas and Equipment Inc | 10862.89 | 0.98478 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2307126A | 11025.8 | F21P1 Chemical & WCCS package | Argon for Chemical welding. | Linde Gas and Equipment Inc | 10925.64 | 0.99092 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2208014A | 11000 | F21P1 UPW | ABB 150A Circuit Breakers | Kelso-Burnett Co. | 11000 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Electrical | Instrument | USC21C014 | USCSB2307058A | 11000 | F21P1 WH2SO4 | WH2SO4 HUB BOX | Marketech International Corp. | 11000 | 1 | Electrical | Main Contract Scope | WWT | W-H2SO4 | Equipment
Base-Build | WWT | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2205014A | 11000 | F21P1 WWT package (Installation and 2 batch tanks) | Modular Pipe Support Assembly Design change order | The Blackfin Group | 11000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2301018A | 10990 | F21P1 WWT package (Installation and 2 batch tanks) | ClearPVC shortage | Harrington Industrial Plastics LLC | 10990 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2308117B | 10965 | F21P1 UPW | TOC Replacement Parts | Veolia WTS Analytical Instruments, Inc. | 10965 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Steel | Material | USC21C009 | USCSB2405150A | 10857.7 | F21P1 WWT package (Installation and 2 batch tanks) | WRC A side platform recover (material) | Fibergrate Composite Structures Inc | 10857.7 | 1 | Steel | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402264A | 10855.74 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Fitting_20240227 (A Side) | Harrington Industrial Plastics LLC | 10855.74 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2405120A | 10841.82 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - T-665AA Tank Repair | Harrington Industrial Plastics LLC | 10841.82 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2310045A | 10800.18 | WWT Change Order (Piping) | WWT- hardware for LJ | Copper State Bolt & Nut Company | 10800.18 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Others | Commissioning | USC21C008 | USCSB2302027A | 10800 | F21P1 CCTV & Security | Speed Gate/Turnstile | TUV SUD America, Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | Speed Gate | Material
Base-Build | WWT | Steel | Labor | USC23C045 | USCSB2310190A | 10775.2 | WWT Change Order (Piping) | WWT FAB drain rigging for common rack installation | Process Service Specialists, LLC of Delaware | 0 | 0 | Steel | Main Contract Scope | WWT | WWT | PSS
Base-Build | WWT | Mechanical | Material | USC21C014 | USCSB2306028A | 10764.51 | F21P1 WH2SO4 | PVDF Material for Vertical Rack | Harrington Industrial Plastics LLC | 10764.51 | 1 | Mechanical | Main Contract Scope | WWT | W-H2SO4 | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2408003A | 10731.44 | WWT B side Project | WWT shortage of Stainless materials on the B side | Ferguson Enterprises, LLC | 7799 | 0.72674 | Mechanical |  |  | WWT
Base-Build | UPW | Mechanical | Material | USC24C008 | USCSB2406055A | 10699.88 | UPW B Side Project | Materials from ORGANO | Organo USA, Inc | 10699.88 | 1 | Mechanical | Main Contract Scope | UPW | UPW
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2306027A | 10691 | F21P1 UPW | MMI -ORGANO-RO Re-rotate | Milling Machinery, Inc. | 10691 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | MMI
Base-Build | Low Voltage | Electrical | Labor | USC22C035 | USCSB2405021A | 10686.2 | CAP_A_90772_F21 Phone call base build and Liquid penetrant testing system | F21 P1 parking gates installation-(8/11) | NUUO US Inc. | 0 | 0 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203019A | 10665.88 | F21P1 UPW | Switch 48 Port、PoE Switch 48 Port、Transceiver Module | Galaxy3 LLC | 10665.88 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2309029A | 10661.19 | F21P1 Chemical & WCCS package | NFPA Diamond Signs support and install | CRG International | 7343.45 | 0.6888 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | CRG
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2405012A | 10654 | WWT Change Order (Piping) | WWT-UMEC-2023Veteran's day_Overtime | University Mechanical & Engineering Contractors, Inc. | 10121 | 0.94997 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2404096A | 10602 | F21P1 WWT package (Installation and 2 batch tanks) | WRC WWT Observation (Change Order) | Page Southerland Page, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2406003A | 10566 | Chemical & WCCS B Side Project | CED Wire 0531-1 | Consolidated Electrical Distributors Inc | 10566 | 1 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405186A | 10494.72 | Chemical & WCCS B Side Project | Ryan Herco CPVC/PP/PVDF 0530 | Ryan Herco Flow Solutions | 10494.72 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2308102A | 10434.99 | WWT Change Order (Piping) | WWT-double pipe certification | Harrington Industrial Plastics LLC | 10234.99 | 0.98083 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Site Expense | USC21C007 | USCSB2305045A | 10428 | F21P1 VOC package （Installation ) | Scaffold for WWT | BrandSafway Solutions, LLC | 10428 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Scaffolding
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2209006A | 10396 | F21P1 UPW | portable fans 48" 120V/1PH 12 foot power cord | Delta T, LLC dba Big Ass Fans | 10396 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2302017A | 10383 | F21P1 UPW | UPW-Seal pot replacement | Organo USA, Inc | 10383 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2402272A | 10355 | F21P1 WWT package (Installation and 2 batch tanks) | Davit Arms and Manway Covers | Milling Machinery, Inc. | 10355 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405121A | 10318.9 | WWT B side Project | WWT Ball Valve_20240521 (B Side) | Harrington Industrial Plastics LLC | 10318.9 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USC2111061A | 10252.19 | F21P1 Chemical & WCCS package | Ball Valve | Ryan Herco Flow Solutions | 10252.19 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2309167A | 10246.5 | F21P1 Chemical & WCCS package | VMB-576A for TS-135 at HPM 20. | Marketech International Corp. | 0 | 0 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2212016A | 10181 | F21P1 Slurry package | TSMC F21P1 MIC | Marketech International Corp. | 0 | 0 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402202A | 10135 | F21P1 Chemical & WCCS package | CDS Air Valves | Marketech International Corp. | 10135 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2308099A | 10119.46 | F21P1 UPW | MCP Bottom Plates | Organo USA, Inc | 10119.46 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2207021A | 10117.89 | F21P1 UPW | Signal amplify equipment | Graybar Electric Company, Inc. | 10117.89 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402067A | 10075.75 | F21P1 WWT package (Installation and 2 batch tanks) | WWT material 01.26 (A Side) | Ferguson Enterprises, LLC | 8936.58 | 0.88694 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | Labor | USC22C021 | USCSB2309104A | 10000 | F21P1 Chemical Lab setup | Page Observation for FAB and WRC UPW Reimbursement | Page Southerland Page, Inc. | 10000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Labor
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2310058A | 10000 | F21P1 UPW | FAB B Chemical/ UPW Permitting(batch2/2) | KAEKO, Inc | 10000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | UPW | Base-Build | Labor
Base-Build | Chemical | Others | QAQC | USC21C005 | USCSB2310059A | 10000 | F21P1 Chemical & WCCS package | Lorry additional 16 RU systems | KAEKO, Inc | 10000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | DCR Scope | CDS | Base-Build | Labor
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2212003A | 10000 | F21P1 WWT package (Installation and 2 batch tanks) | FRP Tank Repairs | Harrington Industrial Plastics LLC | 5647 | 0.5647 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Steel | M+L | USC21C003 | USCSB2311116A | 9968 | F21P1 UPW | UPW-WRCL20-MMI-rack revise | Milling Machinery, Inc. | 9469.6 | 0.95 | Steel | Main Contract Scope | UPW | UPW | MMI
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407112A | 9954.41 | WWT B side Project | WWT stainless steel material for CDA B | Ferguson Enterprises, LLC | 9219.67 | 0.92619 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2305076A | 9900 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Tanks hydrotest | Hua Yi Construction AZ, Inc | 9900 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2401083A | 9834.74 | F21P1 WWT package (Installation and 2 batch tanks) | WWT: Repair (2) 1" Stripper Tank Nozzle Flanges and FRP New Standoff to Relocate Sandblasting Lab Tank T-196AA Ladder | Harrington Industrial Plastics LLC | 4505.69 | 0.45814 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407092A | 9806.9 | WWT B side Project | WWT CCR system SUS material | Ferguson Enterprises, LLC | 9806.9 | 1 | Mechanical |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406104A | 9775 | Chemical & WCCS B Side Project | TSMC / FAB21: BEND 85 EACH 90 DEGREE ELBOWS WITH A 16" RADIUS WITH 2" DIAMETER .065 WALL 316 SS. | CRG International | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | CRG
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2311096A | 9748 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-PP Materials | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209009A | 9643.39 | F21P1 Chemical & WCCS package | AECC License | Autodesk, Inc. | 9643.39 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | Software
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309072A | 9599.67 | F21P1 Chemical & WCCS package | Ball valve to work at H20 and slurry sump | Ze-Wei Industrial Co., Ltd. | 9599.67 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | Base-Build | Others | Site Expense | USC23C058 | USCSB2309091A | 9591 | F21 EUV Steel Plates | Provide 10lb fire extinguisher and bracket at scaffold entrances (required for fire inspection) | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Scaffolding
Base-Build | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2402208A | 9588 | F21P1 WWT package (Installation and 2 batch tanks) | WWT: Fabricate and Install T-1985 Ladder | Milling Machinery, Inc. | 9588 | 1 | Steel | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2408028A | 9483.94 | WWT B side Project | Water seal pot and pump cable box_WWT | Mega Union Technology Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404041A | 9478.26 | WWT B side Project | WWT Hardware_20240402 (B Side) | Copper State Bolt & Nut Company | 9478.26 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2206023A | 9476 | F21P1 Slurry package | F21 Raised Floor Pipe engineering | SDB, Inc. dba SDB Contracting Services | 9476 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402255A | 9459 | F21P1 WWT package (Installation and 2 batch tanks) | WWT materials-2 | Yingsheng Applied Materials Co., Ltd | 9459 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2210021A | 9449.04 | F21P1 UPW | Nagano JM31-1L3 | Ashcroft Inc. | 9449.04 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2403286A | 9412.45 | WWT Change Order (Piping) | WWT SUS Fittings & Pipes_20240328 (A Side) | Ferguson Enterprises, LLC | 8196.37 | 0.8708 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Material | USC21C012 | USC2201003A | 9380.8 | F21 Barcode RFID System | warning light (flashing type) | ADAMS International LLC | 9380.8 | 1 | Electrical | Main Contract Scope | Low Voltage | Barcode | Equipment
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2312036A | 9375.2 | F21 TMAH System | MICU Coating bolts for Tmah. | Mega Union Technology Inc. | 9375.2 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2407133A | 9365 | WWT B side Project | WWT - A-420AA Support Extensions | Greenberry Industrial | 9365 | 1 | Steel |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404224A | 9339.11 | WWT B side Project | WWT Fittings for Remaining Fittings for Drain_20240429 (B Side) | Harrington Industrial Plastics LLC | 9339.11 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2301034A | 9326 | F21P1 WWT package (Installation and 2 batch tanks) | PP Material - fittings | Mega Union Technology Global Pte Ltd | 9326 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Site Expense | USC21C009 | USCSB2401002A | 9254.33 | F21P1 WWT package (Installation and 2 batch tanks) | WWT tools for MU | The Home Depot, Inc | 9206.45 | 0.99483 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310141A | 9243.21 | F21P1 Chemical & WCCS package | Pillar parts used for VMB of B side. | Nippon Pillar Corporation of America | 9243.21 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2403170A | 9200 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - GB PCO #104 / New Misc. Support Modifications on X/2 | Greenberry Industrial | 0 | 0 | Steel | DCR Scope | WWT | WWT | Labor
Base-Build | WWT | Steel | M+L | USC23C045 | USCSB2310164A | 9125 | WWT Change Order (Piping) | 5.5 Missing Rack Steel | Milling Machinery, Inc. | 9125 | 1 | Steel | Main Contract Scope | WWT | Base-Build | MMI
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304029A | 9108.04 | F21P1 WWT package (Installation and 2 batch tanks) | Stainless Steel Pipe in Lorry | Ferguson Enterprises, LLC | 9108.04 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2404197A | 9099.81 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Fittings (A Side)_Ryan Herco_20240424 | Ryan Herco Flow Solutions | 9099.81 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2302015A | 9088.5 | F21P1 WWT package (Installation and 2 batch tanks) | PVC from Harrington | Harrington Industrial Plastics LLC | 9088.5 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2308028A | 9066.6 | F21 TMAH System | WWT material for drain & system | Mega Union Technology Inc. | 5855.1 | 0.64579 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Electrical | Instrument | USC21C009 | USCSB2302014A | 9000 | F21P1 WWT package (Installation and 2 batch tanks) | 40 pic battery charge | Gruber Industries | 9000 | 1 | Electrical | CO Scope (adding/additional scope) | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2301016A | 9000 | F21P1 WWT package (Installation and 2 batch tanks) | FRP Tanks samples | Harrington Industrial Plastics LLC | 6000 | 0.66667 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Others | Commissioning | USC21C003 | USCSB2307090A | 9000 | F21P1 UPW | Aid in Tank Inspection | Degan Construction LLC | 9000 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Mechanical | M+L | USC21C006 | USCSB2308163A | 8990.85 | F21P1 Slurry package | F21 P1 VOC Change Order(southland)_4 | Southland Industries | 8990.85 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | VOC | Southland
Base-Build | Chemical | Mechanical | Labor | USC22C021 | USCSB2306127A | 8988 | F21P1 Chemical Lab setup | GC Lab Move-in | Greenberry Industrial | 8538.6 | 0.95 | Mechanical | The budget execution does not pertain to this project | Chemical Lab | Chemical Lab | MIMO/Rigging
Base-Build | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2212008A | 8977 | F21P1 Chemical & WCCS package | sample box 640 & 645 | Collabratech Solutions | 8977 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Others | Material | USC21C011 | USCSB2402054A | 8949.45 | F21 TMAH System | WWT-TMAH-LCMSMS-set up chemicals | Agilent Technologies, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2305036A | 8948 | F21P1 WWT package (Installation and 2 batch tanks) | 20" EP+PTFE gaskets | Yingsheng Applied Materials Co., Ltd | 8762 | 0.97921 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2306014A | 8892.58 | F21P1 UPW | Motor Rewire | Rosendin Electric, Inc. | 0 | 0 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Rosendin
Base-Build | UPW | Others | Commissioning | USC21C003 | USCSB2308126A | 8802 | F21P1 UPW | UPW-8/20 Sunday work for commissioning check | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | UMEC
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2405079A | 8760 | UPW B Side Project | ICPMS LAB Train 2 CO To ORGANO | Organo USA, Inc | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310056A | 8760 | F21P1 Chemical & WCCS package | Welder equipment for Chemical welding. | Tech South, Inc | 8760 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Low Voltage | Electrical | Labor | USC22C001 | USCSB2405017A | 8663.34 | F21 P1 Office and WH Security and CCTV | F21 P1 parking gates installation-(4/11) | NUUO US Inc. | 0 | 0 | Electrical | Main Contract Scope | Low Voltage | CCTV | NUUO
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304028A | 8624.85 | F21P1 WWT package (Installation and 2 batch tanks) | TMAH bolts / Small size bolts | Copper State Bolt & Nut Company | 8624.6 | 0.99997 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407127A | 8588.7 | WWT B side Project | MIC/BMWC/Okland B side缺料_WWT | Harrington Industrial Plastics LLC | 8588.7 | 1 | Mechanical |  |  | WWT
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2401172A | 8569 | F21P1 WWT package (Installation and 2 batch tanks) | WWT:Design,fabricate,Deliver,and install 2 ladders in FAB/LB2 to replace staircases on platforms that clashing with dike wall | Milling Machinery, Inc. | 8569 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2407120A | 8548 | UPW B Side Project | L20 Loop 3 Pipe Adjustment_UPW | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical |  |  | UPW
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2401078A | 8524 | F21P1 Slurry package | SDS A side expansion two cabinets | Milling Machinery, Inc. | 8524 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | MMI
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403009A | 8506.8 | F21P1 WWT package (Installation and 2 batch tanks) | WWT LSR SUS material | Ferguson Enterprises, LLC | 8506.8 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Electrical | Material | USC23C045 | USCSB2311109A | 8485.34 | WWT Change Order (Piping) | WWT CCE Change Orders_DC 680V cable CO | Commercial Comm and Electric Inc | 8485.34 | 1 | Electrical | DCR Scope | WWT | WWT | CCE
Base-Build | Chemical | Mechanical | M+L | USC24C005 | USCSB2405106A | 8449.1 | Chemical & WCCS B Side Project | CHEM_B side FB1-F20 VMB construction | Consolidated Electrical Distributors Inc | 8449.1 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USC2112017A | 8448 | F21P1 Chemical & WCCS package | Ball Valve | SEMITORR GROUP, LLC | 8448 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2406017A | 8385 | F21P1 Slurry package | FAB A SDS Permit Revision | KAEKO, Inc | 0 | 0 | Mechanical | Main Contract Scope | SDS | Slurry
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2311053A | 8381.9 | F21P1 Chemical & WCCS package | CDS B side anchor plates | TCELC CO., LTD | 8381.9 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405045A | 8360 | Chemical & WCCS B Side Project | CHEM_WCCS _hardware for standing by materials (TCELC) | TCELC CO., LTD | 8360 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2404031A | 8350 | F21P1 Slurry package | 帆宣計價單-美國tsmc CPVC 平接 | JHENGTONG INTERNATIONAL LIMITED | 0 | 0 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308049A | 8298.35 | F21P1 Chemical & WCCS package | TGCM Duty Room items – Tan lockers (Qty:10) | High Density, Inc. | 8298.35 | 1 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC22C012 | USCSB2403014A | 8225 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | UPW-Tomoe valve for train B | Tomoe USA, Inc. | 8225 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209014A | 8214.22 | F21P1 Chemical & WCCS package | Dell Laptop | Dell Technologies | 8214.22 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209010A | 8177.29 | F21P1 Chemical & WCCS package | Dell Laptop | Dell Technologies | 8177.29 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2309044A | 8171 | F21P1 Chemical & WCCS package | 200 ea. CDS Seismic Corner Anchor Brackets. | Milling Machinery, Inc. | 8171 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Steel | M+L | USC23C045 | USCSB2311063A | 8160 | WWT Change Order (Piping) | WWT-Safetystep for HPM | Hua Yi Construction AZ, Inc | 0 | 0 | Steel | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402087A | 8108.79 | F21P1 Chemical & WCCS package | CDS HPM Punch materials | Carson Sales Co Inc | 8108.79 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404076A | 8076.18 | WWT B side Project | WWT Fittings for 60604_20240408 (B Side) | Harrington Industrial Plastics LLC | 8076.18 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Steel | M+L | USC21C003 | USCSB2401203A | 8025 | F21P1 UPW | UPW-mezz 3-egress ladder revise | Milling Machinery, Inc. | 7623.75 | 0.95 | Steel | Main Contract Scope | UPW | UPW | MMI
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2306013A | 8012.83 | F21P1 Chemical & WCCS package | NFPA Diamond Signs for chemical tanks | Pensacola Hardware Company | 8012.83 | 1 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309162A | 8002.24 | WWT Change Order (Piping) | Small order: TW material PVC insert fitting | Harrington Industrial Plastics LLC | 8002.24 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Civil | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2212041A | 8000 | F21P1 WWT package (Installation and 2 batch tanks) | MIC Water Tanks Painting | Phoenix House Painting.com LLC dba PHP Commercial Painting | 8000 | 1 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Others | Commissioning | USC21C003 | USCSB2312016A | 8000 | F21P1 UPW | UPW-Linde-Nitrogen for test(Open PO) | Linde Gas and Equipment Inc | 717.14 | 0.089643 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Electrical | Material | USC21C007 | USCSB2304085A | 7939.06 | F21P1 VOC package （Installation ) | Control wire for VOC 2 & 3 | Consolidated Electrical Distributors Inc | 7939.06 | 1 | Electrical | CO Scope (adding/additional scope) | Low Voltage | VOC | Material
Base-Build | WWT | Mechanical | Material | USC21C004 | USCSB2210045A | 7926.2 | F21P1 WWT package （USA EQ-FRP tank) | TUNNEL Sump Pit Pump RT Fitting | Mega Union Technology Global Pte Ltd | 7926.2 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2307131A | 7891.61 | F21P1 Chemical & WCCS package | Additional for GF price increase | Ryan Herco Flow Solutions | 7891.6 | 1 | Mechanical | DCR Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Others | QAQC | USC21C013 | USCSB2401089A | 7800 | F21P1 AMC THC Monitoring System | FAB EBO AMC Hookup - Permitting | LSW Engineers Arizona, Inc. | 7800 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | AMC THC | Labor
Base-Build | WWT | Others | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2308095A | 7796 | F21 TMAH System | MIC-116-23 Equipment Move in FAB LB2 column A.5/10 | Greenberry Industrial | 7796 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | TMAH | MIMO/Rigging
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2301054A | 7770 | F21P1 UPW | Anchor sensor plates | An-Cor Industrial Plastics, Inc. | 7770 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Others | Safety | USC21C014 | USCSB2310023A | 7709.6 | F21P1 WH2SO4 | VOC 02 & VOC 03 resolve moldy by decontaminating the crates. | Clean Harbors Environmental Services Inc | 7709.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | VOC | VOC | Labor
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2307107A | 7653.9 | F21 TMAH System | (35) Joints PP PN6 D110 for Submains | Ferguson Enterprises, LLC | 7653.9 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405006A | 7605 | WWT B side Project | WWT 4-5/8" Clamps_20240429 (B Side) | Copper State Bolt & Nut Company | 7605 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | Labor | USC21C011 | USCSB2401084A | 7562 | F21 TMAH System | WWT: Manufacture TMAH Handrail Standoffs and Install | Milling Machinery, Inc. | 7562 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2303089A | 7511 | F21P1 Chemical & WCCS package | Chemical Tank Bottom Plate | Milling Machinery, Inc. | 7511 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2312176A | 7500 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Clamp from 8-16” for A side back up. | TCELC CO., LTD | 7500 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | Material | USC21C003 | USCSB2301013A | 7496.5 | F21P1 UPW | UPW-MMF-Anthracite procurement | Northern Filter Media, Inc. | 7496.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2408061A | 7407.77 | WWT B side Project | WWT shortage of fitting materials on the B side Sump Pump | Harrington Industrial Plastics LLC | 5842.97 | 0.78876 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2403031A | 7311 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Center Ring_20240304 (A Side) | Pure Plastics, LLC | 7311 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | Labor | USC23C014 | USCSB2401043A | 7300 | F21P1 Labor incentive program-MICU | Tunnel&WWT_9-5 Holiday pay incentive (Labor Day) | Greenberry Industrial | 0 | 0 | Steel | DCR Scope | WWT | WWT | Greenberry
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2308013A | 7274 | F21 TMAH System | WWT 6in CPVC | Harrington Industrial Plastics LLC | 7274 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403199A | 7266.13 | F21P1 Chemical & WCCS package | CDS LB1 B side supports materials | Carson Sales Co Inc | 7266.13 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2303036A | 7238 | F21P1 UPW | UPW Panel Material | Border State Industries, Inc. | 7238 | 1 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2405035A | 7194.11 | F21P1 WWT package (Installation and 2 batch tanks) | Temporary chemical leak kit_20/45-10 | WW Grainger Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2309144A | 7184.08 | F21P1 Chemical & WCCS package | Circuit Breakers for Fab L10/L20 | WW Grainger Inc | 7184.08 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2306018A | 7150 | F21P1 UPW | UPW Degan tank HKP rev&clean | Degan Construction LLC | 7150 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2402017A | 7130.9 | WWT Change Order (Piping) | Clamps for A side 2024.1.31-1 | Southwest Fastener Division of NEFCO | 7130.9 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309195A | 7129.48 | WWT Change Order (Piping) | material for LJ W339 order#3 | Harrington Industrial Plastics LLC | 6082.08 | 0.85309 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2403178A | 7110 | F21P1 Chemical & WCCS package | CDS Box | FusionHPX LLC | 7110 | 1 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2407003A | 7106 | Chemical & WCCS B Side Project | EES 防爆接線盒0627 (Made-to-Order Explosion Proof Box) | Elliott Electric Supply, Inc. | 7106 | 1 | Electrical |  |  | Chemical
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2402007A | 7085 | F21P1 Chemical & WCCS package | CDS TSMC UPW 8-178 Chemical Scope (T&M) | University Mechanical & Engineering Contractors, Inc. | 7085 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | UMEC
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309030A | 7065.45 | F21P1 Chemical & WCCS package | Manual chemical liquid valve | CKD USA CORPORATION | 7065.45 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2407156A | 7061 | Chemical & WCCS B Side Project | Chem Team Fitting KS23 to Replace KS17 (CED 化學訊號fitting換料0725) | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical |  |  | Chemical
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2301010A | 7051.64 | F21P1 UPW | UPW-skids cover replacement | Pure Plastics, LLC | 7051.64 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Civil | Labor | USC21C009 | USCSB2302031A | 7013.5 | F21P1 WWT package (Installation and 2 batch tanks) | T-130AA/AB Agitator Chemical Coating | Degan Construction LLC | 7013.5 | 1 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Electrical | Instrument | USC21C011 | USCSB2309110A | 7000 | F21 TMAH System | F21 WWT system material (Gibabit) | Marketech International Corp. | 7000 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2312139A | 6975 | F21P1 Chemical & WCCS package | CDS Fix L10 HNO3 ST250 HKP | Degan Construction LLC | 6975 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Steel | Labor | USC23C045 | USCSB2309131A | 6924 | WWT Change Order (Piping) | WRC Rack 215/220 Modification for PSS Clash | Milling Machinery, Inc. | 6924 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2302039A | 6886 | F21P1 Chemical & WCCS package | M1, M2, H2SO4 Design Change | Southland Industries | 6886 | 1 | Mechanical | DCR Scope | CDS | Chemical | Southland
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2310192A | 6868 | F21P1 Chemical & WCCS package | CDS Lorry unistrut cages at Room 13, 12, 30,31 | Milling Machinery, Inc. | 6868 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Steel | Material | USC23C045 | USCSB2311021A | 6858 | WWT Change Order (Piping) | WWT 18" backing ring | Milling Machinery, Inc. | 6858 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2403002A | 6845.83 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - Marquis CO 1 Media loading for for four hour delay and Specialty PPE to work in TMAH | Marquis Construction Services LLC | 6845.83 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2407168A | 6825 | UPW B Side Project | CIP Pump Replacement_UPW | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical |  |  | UPW
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2403176A | 6817.62 | F21P1 Chemical & WCCS package | CDS 6awg 5C | Consolidated Electrical Distributors Inc | 6567.62 | 0.96333 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406021A | 6813.78 | Chemical & WCCS B Side Project | pad prep/epoxy and yellow safety paint of 1 pad in Fab L10 HPM Bside Bed 457*113(inch) | SD Engineering Technology LLC | 6813.78 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405151A | 6773.75 | Chemical & WCCS B Side Project | TSMC F21 B SIDE SDS ATRS Regulator | Flodraulic Group | 6773.75 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Others | Commissioning | USC21C009 | USCSB2307027A | 6760.1 | F21P1 WWT package (Installation and 2 batch tanks) | WRC NaOH Tank Tranfer to Drums (WWT-T615A-empty chemical) | Clean Harbors Environmental Services Inc | 3334.6 | 0.49328 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405147A | 6610.11 | WWT B side Project | WWT Hardware_20240523 (B Side) | Copper State Bolt & Nut Company | 6610.11 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402074A | 6515.1 | F21P1 WWT package (Installation and 2 batch tanks) | Temporary chemical leak kit 10/45-10 | WW Grainger Inc | 6515.1 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Electrical | Material | USC24C006 | USCSB2407014A | 6482.99 | WWT B side Project | Wires for chemical tank area | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2404098A | 6450 | Chemical & WCCS B Side Project | SDS VMB Pneumatic Spare Parts | FusionHPX LLC | 6450 | 1 | Mechanical | 0 | 0 | Slurry | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C006 | USC2112023A | 6420 | F21P1 Slurry package | Bellows Valve | SEMITORR GROUP, LLC | 6420 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | Low Voltage | Others | Commissioning | USC21C013 | USCSB2310034A | 6400 | F21P1 AMC THC Monitoring System | F21 P1 IMS Wipe Test | Welmade Technology Corporation | 6400 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | AMC THC | Equipment
Base-Build | UPW | Others | Site Expense | USC24C008 | USCSB2407105A | 6384 | UPW B Side Project | CGS Global Support Onsite Manpower | CGS Global Support, LLC | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | UPW | Outsourcing
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2301014A | 6368.07 | F21P1 WWT package (Installation and 2 batch tanks) | Mini Line Hardware | Yingsheng Applied Materials Co., Ltd | 6368.07 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Material | USC21C007 | USCSB2310085A | 6330.8 | F21P1 VOC package （Installation ) | VOC MC cable for LowNox | Consolidated Electrical Distributors Inc | 6087.83 | 0.96162 | Electrical | DCR Scope | Low Voltage | VOC | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310021A | 6290 | F21P1 Chemical & WCCS package | Acrylic boards used in chemical in status and used for every each VMB of A/B side. | J A Hansen Company DBA Hansen Supply Company | 6290 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2308132A | 6261.75 | F21P1 Chemical & WCCS package | Lorry A FNDP001 Materials | Marketech International Corp. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2311070A | 6254.1 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-MU-H910/T130 H/A680 | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2402168A | 6254 | F21P1 WWT package (Installation and 2 batch tanks) | ASME IX P8 WPS and Welder Qualification | Phoenix National Laboratories, LLC | 3330 | 0.53246 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Site Expense
Base-Build | Low Voltage | Others | Commissioning | USC21C008 | USCSB2307029A | 6240 | F21P1 CCTV & Security | CCTV speed gates UL on-site inspection/evaluation | TUV SUD America, Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | CCTV | Labor
Base-Build | WWT | Others | Site Expense | USC23C045 | USCSB2309094A | 6238.65 | WWT Change Order (Piping) | WWT -LJ lift training | United Rentals | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Site Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202002A | 6213.7 | F21P1 UPW | Smartsheet Dynamic view Pro-rated license | Teo Services, Inc. DBA TEOPM | 6213.7 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2402159A | 6204.96 | F21P1 Chemical & WCCS package | CDS Pressure tests | BRAHMA GROUP, INC. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403097A | 6196.14 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Fittings_20240308 (A Side) | Harrington Industrial Plastics LLC | 6196.14 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2311057A | 6184 | WWT Change Order (Piping) | WWT: Reposition T-780AA-2 Ladder | Milling Machinery, Inc. | 6184 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | WWT | Electrical | Material | USC24C006 | USCSB2407052A | 6178.61 | WWT B side Project | Onsite Trailers | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical |  |  | WWT
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2309103A | 6172 | F21P1 UPW | LB2-UIS A2.5 spool remove | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | UMEC
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403083A | 6109.2 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Blind Flange_20240307 (A Side) | Harrington Industrial Plastics LLC | 6109.2 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403138A | 6036.8 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - (20) 5" PVC Blind Flanges | Harrington Industrial Plastics LLC | 6036.8 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2209024A | 6025.84 | F21P1 QR Lab Security & CCTV | F21P1 FAB_Security&CCTV Package - 01 | Aegis Technology Inc | 0 | 0 | Electrical | Main Contract Scope | Low Voltage | CCTV | Equipment
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2402228A | 6000 | F21P1 UPW | UPW-ORGANO-L10 Q-6.5 Line Design Mod | Organo USA, Inc | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2406148A | 5985 | WWT B side Project | 儀表採樣箱收缺失之材料 | Yingsheng Applied Materials Co., Ltd | 0 | 0 | Mechanical |  |  | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2307097A | 5968.25 | F21P1 UPW | chemical Room UPW/Tank repairs UPW(sight glass flang) | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Mechanical | Labor | USC24C007 | USCSB2405083A | 5946.48 | Low Voltage B Side Project | F21-P1_B-Side mask room exhaust hookup designs | MornstAir Inc. | 0 | 0 | Mechanical | Main Contract Scope | Low Voltage | 光阻櫃 | Labor
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2311047A | 5932.68 | F21P1 UPW | UPW-Cleanharbor ERC service | Clean Harbors Environmental Services Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Labor
Base-Build | Chemical | Mechanical | Material | USC23C012 | USCSB2307142A | 5887.76 | F21P1 Hot DI Machine Hookup | Hot DI long lead parts from Taiwan | Ze-Wei Industrial Co., Ltd. | 5887.76 | 1 | Mechanical | 0 | 0 | Hot DI | Material
Base-Build | WWT | Steel | M+L | USC22C022 | USCSB2308184A | 5859 | F21P1 Triazole treatment system | 140 DISCHARGE EXTRA SUPPORT AND T125AC/AD MIS SUPPORT | Greenberry Industrial | 0 | 0 | Steel | DCR Scope | WWT | Base-Build | Greenberry
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2406059A | 5792.42 | WWT B side Project | WWT Fittings & Pipes_20240607 (B Side) | Harrington Industrial Plastics LLC | 5792.42 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2212026A | 5789 | F21P1 WWT package （USA EQ-FRP tank) | T-125 tank flanges and gaskets | Milling Machinery, Inc. | 5789 | 1 | Mechanical | Main Contract Scope | WWT | WWT | MMI
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207013A | 5772.65 | F21P1 UPW | Lenovo Laptop | Lenovo Group Ltd | 5772.65 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405161A | 5770 | WWT B side Project | WWT Center Rings_20240528 (B Side) | HSIUNG CHANG Enterprise Co., Ltd. | 5770 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Commissioning | USC21C009 | USCSB2307019A | 5768.1 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-CCB dry-run | Clean Harbors Environmental Services Inc | 5745.2 | 0.99603 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2307017A | 5760 | F21P1 WWT package (Installation and 2 batch tanks) | FRP Resin for welding FRP pipe | Professional Plastics Inc | 5760 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2208005A | 5760 | F21P1 UPW | Harrington Ladder Standoff on the Tank | Harrington Industrial Plastics LLC | 5760 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USC2112011A | 5678.1 | F21P1 Chemical & WCCS package | Straight Union Reducer | Nippon Pillar Corporation of America | 5678.1 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2311033A | 5620.4 | WWT Change Order (Piping) | Swagelok Tubing &connector | Arizona/Albuquerque Valve & Fitting Corp. | 5620.4 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Housekeeping | USC21C011 | USCSB2402041A | 5610 | F21 TMAH System | Cleaning Material(ishine floor finish) | Amazon.com, Inc. | 4537.8 | 0.80888 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | TMAH | Material
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2402234A | 5599.62 | F21P1 Chemical & WCCS package | CDS electrical materials | Consolidated Electrical Distributors Inc | 5599.62 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2401235A | 5590.8 | F21P1 Chemical & WCCS package | WCCS CO#172 W-A515 L20 | Southland Industries | 5590.8 | 1 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Southland
Base-Build | Low Voltage | Mechanical | M+L | USC22C001 | USCSB2404015A | 5576 | F21 P1 Office and WH Security and CCTV | F21 P1 CUP L30 Glass Baffle Railing | Southwest Metalsmiths, Inc. | 5576 | 1 | Mechanical | The budget execution does not pertain to this project | CCTV | CCTV | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2307123A | 5563 | F21P1 UPW | WRC Temp Mixed Bed Resin Temp Hose | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | UMEC
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309034A | 5560 | F21P1 Chemical & WCCS package | Lorry 90 deg Coax elbows | SEMITORR GROUP, LLC | 5560 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407011A | 5553 | WWT B side Project | B side gasket 補料 | Yingsheng Applied Materials Co., Ltd | 0 | 0 | Mechanical |  |  | WWT | Material
Base-Build | WWT | Others | Site Expense | USC21C004 | USCSB2403179A | 5544.35 | F21P1 WWT package （USA EQ-FRP tank) | U-Line - MIMO - Move In/Move Out Team | U-Line Corporation | 5110 | 0.92166 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | MIMO/Rigging
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2311138A | 5534.57 | WWT Change Order (Piping) | WWT LSR CS material | Ferguson Enterprises, LLC | 5534.57 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Instrument | USC21C014 | USCSB2302005A | 5527.5 | F21P1 WH2SO4 | W-H2SO4 2X4 Center rings - Pure Plastix | Pure Plastics, LLC | 5527.5 | 1 | Mechanical | Main Contract Scope | WWT | W-H2SO4 | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405160A | 5502 | WWT B side Project | WWT PP軟管及接頭_20240528 (B Side) | Yingsheng Applied Materials Co., Ltd | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2405064A | 5491.18 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Fittings_20240509 (A Side) | Harrington Industrial Plastics LLC | 5491.18 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2406117A | 5444.44 | F21P1 Chemical & WCCS package | CED-訊號電力材料_20240621 (Signal Wire Material) | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical |  |  | Chemical
Base-Build | UPW | Mechanical | Material | USC22C012 | USCSB2403011A | 5426 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | UPW-Ebro valves for train B | Engineered Process Controls, LLC | 5426 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Low Voltage | Others | QAQC | USC22C019 | USCSB2403301A | 5400 | AMC monitor 595T0 | FAB A+B VOC Plumbing and NG Observation | LSW Engineers Arizona, Inc. | 540 | 0.1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | VOC | Labor
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2311058A | 5378 | WWT Change Order (Piping) | Material request E2 #4 | Harrington Industrial Plastics LLC | 5378 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310149A | 5373 | F21P1 Chemical & WCCS package | CDS 1-1/2"x2" 45 ELBOW 316LEP/304AP | GOLD STONE DEVELOPMENT CO., LTD. | 5373 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC22C022 | USCSB2309002A | 5357 | F21P1 Triazole treatment system | Additional Steel for Catwalk to Tank Connection(Triazole Catwalk) | Milling Machinery, Inc. | 4495 | 0.83909 | Steel | Main Contract Scope | WWT | Triazole | MMI
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2212042A | 5342.85 | F21P1 WWT package (Installation and 2 batch tanks) | CCE Gaskets | Yingsheng Applied Materials Co., Ltd | 5342.85 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Steel | Material | USC24C008 | USCSB2406141A | 5310 | UPW B Side Project | Ladder Safety System Materials | Diversified Products USA | 5310 | 1 | Steel |  |  | UPW | Material
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2305048A | 5300 | F21P1 UPW | MMI temp resin move-in | Milling Machinery, Inc. | 5300 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | MIMO/Rigging
Base-Build | Low Voltage | Others | QAQC | USC22C001 | USCSB2310079A | 5260 | F21 P1 Office and WH Security and CCTV | Gown Access Control Permit Assistance | LSW Engineers Arizona, Inc. | 5260 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | CCTV | Labor
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406061A | 5249.5 | Chemical & WCCS B Side Project | CHEM_R325 bent_ SUS 316L BA tube | Chukar SB&F LLC | 5249.5 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404065A | 5239.84 | WWT B side Project | WWT Ball Valve_20240404(A&B Side) | Ryan Herco Flow Solutions | 5239.84 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402046A | 5203.94 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Hardware for punches | Copper State Bolt & Nut Company | 5203.94 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | Labor | USC21C003 | USCSB2311017A | 5200 | F21P1 UPW | UPW-Degan-ACF-torque | Degan Construction LLC | 5200 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310029A | 5200 | F21P1 Chemical & WCCS package | 45 deg Coax elbows 1 ?” x 1 for Harder work at north mains L20 FAB. | SEMITORR GROUP, LLC | 5200 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2206003A | 5188.48 | F21P1 UPW | GF Chlorine Instrument | Ryan Herco Flow Solutions | 5188.48 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2405071A | 5175 | F21P1 UPW | Fall Protection System | Safe Keeper Safety Products LLC | 0 | 0 | Mechanical | Main Contract Scope | UPW | UPW
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404013A | 5140 | WWT B side Project | B-side_WWT_(25) D225 PN10 Ends Caps of Drains | Harrington Industrial Plastics LLC | 5140 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Labor | USC21C003 | USCSB2212023A | 5100 | F21P1 UPW | UPW-Design tanks repair | Harrington Industrial Plastics LLC | 5100 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2311132A | 5098.4 | F21P1 WWT package (Installation and 2 batch tanks) | Hand tools for TW team | Mega Union Technology Inc. | 5098.4 | 1 | Mechanical | Main Contract Scope | WWT | Water | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2302019A | 5088.75 | F21P1 WWT package (Installation and 2 batch tanks) | Hander bolt | Duncan Bolt Co. | 5088.75 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2404125A | 5055.97 | WWT Change Order (Piping) | WWT Stripper P-1231AA/AC insulation repair | Marquis Construction Services LLC | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2309009A | 5051.69 | WWT Change Order (Piping) | WWT missing material found by tsmc thu inventory | Harrington Industrial Plastics LLC | 5051.69 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2310123A | 5000 | F21P1 WWT package (Installation and 2 batch tanks) | MICU Electrical On-Call Support (UPW amd WWT) | LSW Engineers Arizona, Inc. | 4945 | 0.989 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | Low Voltage | Others | QAQC | USC21C013 | USCSB2310108A | 5000 | F21P1 AMC THC Monitoring System | MICU Electrical On-Call Support | LSW Engineers Arizona, Inc. | 2687.5 | 0.5375 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | AMC THC | Labor
Base-Build | WWT | Others | Site Expense | USC24C006 | USCSB2408144A | 4982 | WWT B side Project | WWT Tent 9 materials container | Thomas Scientific Holdings LLC | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC23C014 | USCSB2401134A | 4970 | F21P1 Labor incentive program-MICU | Laydown Material - U Line | U-Line Corporation | 4970 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | MIMO/Rigging
Base-Build | WWT | Electrical | Instrument | USC21C009 | USCSB2211013A | 4963.2 | F21P1 WWT package (Installation and 2 batch tanks) | Distribution Panels | Larson Electronics LLC | 0 | 0 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2312050A | 4950 | F21P1 WWT package (Installation and 2 batch tanks) | WRC Lab Exhaust Hood | Silicone Future Manufacturing Company Ltd | 4950 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403021A | 4916.22 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Fitting_20240301 (A Side) | Harrington Industrial Plastics LLC | 4916.22 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | Material | USC21C003 | USCSB2303002A | 4874.6 | F21P1 UPW | Tank Diamond Labels | Pensacola Hardware Company | 4874.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2402214A | 4864.6 | F21P1 Chemical & WCCS package | CDS Fire Barrier Sealant materials | NUUO US Inc. | 4864.6 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | NUUO
Base-Build | WWT | Steel | Labor | USC21C009 | USCSB2403171A | 4852 | F21P1 WWT package (Installation and 2 batch tanks) | WWT: Hopper Anchor Modifications | Milling Machinery, Inc. | 4852 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404099A | 4817.18 | WWT B side Project | WWT Fittings_20240409 (B Side) | Harrington Industrial Plastics LLC | 4817.18 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2308166A | 4725 | F21P1 Chemical & WCCS package | Grade Three MIC Laydown Areas / Lots | Degan Construction LLC | 4725 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405182A | 4724.96 | WWT B side Project | WWT Hardware_20240529 (B Side) | Copper State Bolt & Nut Company | 4724.96 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402114A | 4698.9 | F21P1 Chemical & WCCS package | CDS caps and gaskets | Arizona/Albuquerque Valve & Fitting Corp. | 4698.9 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401041A | 4679.78 | F21P1 Chemical & WCCS package | CDS Unions etc. | Arizona/Albuquerque Valve & Fitting Corp. | 4679.78 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406012A | 4648 | Chemical & WCCS B Side Project | F21P1 SUS B-Flange | Ferguson Enterprises, LLC | 4648 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2308015A | 4587 | F21P1 Slurry package | Slurry Room Raised Gratings. | Milling Machinery, Inc. | 4587 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | MMI
Base-Build | Low Voltage | Others | QAQC | USC21C013 | USCSB2312153A | 4570 | F21P1 AMC THC Monitoring System | FAB LITHO AMC Pressure Testing | LSW Engineers Arizona, Inc. | 4570 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | AMC THC | Labor
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2301027A | 4562.91 | F21P1 Chemical & WCCS package | F18P4 Switch Box | Clayton Controls | 0 | 0 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402020A | 4560.23 | F21P1 Chemical & WCCS package | CDS HPM Punch materials | Southwest Fastener Division of NEFCO | 4560.23 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406014A | 4541.8 | Chemical & WCCS B Side Project | Hardware for Chemical System | Copper State Bolt & Nut Company | 4541.8 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402262A | 4529.9 | F21P1 Chemical & WCCS package | CDS strut and hardware | Southwest Fastener Division of NEFCO | 4529.9 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USCSB2211039A | 4491.74 | F21P1 Slurry package | SLURRY VMB INSTALL KIT - SIDE A | FusionHPX LLC | 4491.74 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Equipment
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USCSB2303068A | 4438.85 | F21P1 Slurry package | Add side B slurry box ingredients | FusionHPX LLC | 4438.85 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USC2203001A | 4429.5 | F21P1 Chemical & WCCS package | Short Reducer | SEMITORR GROUP, LLC | 4429.5 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2303038A | 4420 | F21P1 WWT package (Installation and 2 batch tanks) | Low Voltage MCC Special Inspection Testing | Shermco Industries, Inc. | 4420 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Labor
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2305097A | 4400 | F21P1 UPW | UPW T1035B ladder | Harrington Industrial Plastics LLC | 4400 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Steel | M+L | USC21C009 | USCSB2406049A | 4350 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-GB PCO #112_Cut and extend 2 supports on X/2 | Greenberry Industrial | 0 | 0 | Steel | DCR Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2409034A | 4320 | WWT B side Project | P-760AB Removal and Transportation | Phoenix Pumps, Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2404020A | 4317.5 | F21P1 Slurry package | Hot box change | FusionHPX LLC | 4317.5 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Equipment
Base-Build | WWT | Steel | M+L | USC23C045 | USCSB2308176A | 4272 | WWT Change Order (Piping) | WWT-LB2 rack modification | Greenberry Industrial | 0 | 0 | Steel | DCR Scope | WWT | WWT | Greenberry
Base-Build | Low Voltage | Electrical | M+L | USC21C007 | USCSB2302042A | 4268.64 | F21P1 VOC package （Installation ) | Labels | J A Hansen Company DBA Hansen Supply Company | 4264.12 | 0.99894 | Electrical | Main Contract Scope | Low Voltage | VOC | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2212019A | 4260 | F21P1 WWT package (Installation and 2 batch tanks) | WRC Generator Grounding & Permitting | Wilson Electric Services Corporation | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | WWT | Site Expense
Base-Build | Low Voltage | Others | QAQC | USC21C013 | USCSB2310120A | 4250 | F21P1 AMC THC Monitoring System | FAB A Litho Electrical Permit and CA Service | LSW Engineers Arizona, Inc. | 4250 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | AMC THC | Labor
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2306045A | 4243.4 | F21P1 UPW | UPW Train-A-GF valves | Ryan Herco Flow Solutions | 4243.4 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | UPW | Others | Material | USC21C003 | USCSB2310093A | 4198.32 | F21P1 UPW | H2O2 chemical storage in LB2 | WW Grainger Inc | 4198.32 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2403283A | 4176.7 | F21P1 WWT package (Installation and 2 batch tanks) | Apollo Forklift - WWT | Apollo Forklift LLC | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2302022A | 4141.93 | F21P1 WWT package (Installation and 2 batch tanks) | CCB-adding material | Harrington Industrial Plastics LLC | 4141.93 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2308169A | 4125 | F21P1 Chemical & WCCS package | Epoxy Misc Pads in Fab L10 and Lorry 1.5 | Degan Construction LLC | 4125 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2308172A | 4101 | F21P1 Chemical & WCCS package | HNO3 & ST-250 Cabinet Anchoring | Milling Machinery, Inc. | 4101 | 1 | Mechanical | DCR Scope | CDS | Chemical | MMI
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2307060A | 4100.76 | F21P1 UPW | Crating and packing for pipes on site CO | Crating Technology, INC | 4100.76 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MIMO/Rigging
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2406068A | 4091 | F21P1 WWT package (Installation and 2 batch tanks) | install MIC supplied Door hardware on fire doors at mezzanines 1 and 2, (5 sets of doors total) | ISEC Incorporated | 4091 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2306038A | 4075 | F21P1 Chemical & WCCS package | Welder equipment for Chemical welding | Tech South, Inc | 4075 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C006 | USC2112018A | 4068 | F21P1 Slurry package | Ball Valve | SEMITORR GROUP, LLC | 4068 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2403297A | 4055.18 | F21 TMAH System | WWT Hardware_20240329 (B Side) | Copper State Bolt & Nut Company | 4055.18 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Civil | Labor | USC22C022 | USCSB2310005A | 4050 | F21P1 Triazole treatment system | Triazole pad modification in WRC | Degan Construction LLC | 4050 | 1 | Civil | DCR Scope | WWT | Triazole | Labor
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407136A | 4042.61 | WWT B side Project | WWT_B Side Hardware | Copper State Bolt & Nut Company | 4042.61 | 1 | Mechanical |  |  | WWT
Base-Build | Low Voltage | Electrical | M+L | USC21C012 | USCSB2110006A | 4002.14 | F21 Barcode RFID System | F21P1 Barcode & RFID System Electrical | BPG Technologies, LLC | 4002.14 | 1 | Electrical | Main Contract Scope | Low Voltage | Barcode | Labor
Base-Build | WWT | Mechanical | Material | USC21C004 | USCSB2306017A | 3987.42 | F21P1 WWT package （USA EQ-FRP tank) | All-thread stud | Copper State Bolt & Nut Company | 3987.39 | 0.99999 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403149A | 3981.3 | F21P1 Chemical & WCCS package | Amazon - MIMO - Move In/Move Out Team | Amazon.com, Inc. | 3446.04 | 0.86556 | Mechanical | Main Contract Scope | CDS | Base-Build | MIMO/Rigging
Base-Build | WWT | Mechanical | Instrument | USC24C006 | USCSB2405009A | 3978 | WWT B side Project | WWT Center Ring 3x1.5_20240501 (B Side) | Pure Plastics, LLC | 3978 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Safety | USC24C006 | US8SB2408001A | 3975 | WWT B side Project | Electrical Hazards Training required for people working with or around electricity | LC LIND, LLC | 3975 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2409038A | 3936.91 | WWT B side Project | WWT shortage of fitting materials for B Side, Fab Exhaust, LSR Non-Oxidant Biocide, P-810 | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Labor | USC23C045 | USCSB2311082A | 3903.38 | WWT Change Order (Piping) | TW team tool - threaded machine(YAHO) | WW Grainger Inc | 3903.38 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402091A | 3892.26 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Hardware for A side punches | Copper State Bolt & Nut Company | 3892.26 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2409050A | 3891 | UPW B Side Project | T&M WRC L20 Rack Welding | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical |  |  | UPW
Base-Build | Chemical | Mechanical | E2 | USC21C005 | USCSB2309086A | 3889 | F21P1 Chemical & WCCS package | Hardware for Chemical YaoHong work at Lorry FNDP. | YAHO System Technology Co., Ltd. | 3889 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2312109A | 3872.83 | F21P1 WWT package (Installation and 2 batch tanks) | WWT_18" Galvanized P-Clamps | McMaster-Carr Supply Company | 3810.3 | 0.98385 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310117A | 3841.6 | F21P1 Chemical & WCCS package | CDS Unions to replace all Union Box accessories of Lorry to HPM IPA and PFA to SUS. | Arizona/Albuquerque Valve & Fitting Corp. | 3841.6 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2205009A | 3825 | F21P1 UPW | Modular Office Miscellaneous Works | Design Modulars Inc. | 3825 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Electrical | Material | USC24C006 | USCSB2407054A | 3800 | WWT B side Project | To supplement the damage and missing leak sensor cable for site A and site B. | Autotronic Enterprise Co., Ltd | 3800 | 1 | Electrical |  |  | WWT
Base-Build | WWT | Steel | M+L | USC24C006 | USCSB2408010A | 3799.21 | WWT B side Project | HPM Beam removal_WWT | Greenberry Industrial | 0 | 0 | Steel |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208026A | 3798.35 | F21P1 UPW | Dell BIM Laptop | Dell Technologies | 3798.35 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2312126A | 3796.5 | F21P1 WWT package (Installation and 2 batch tanks) | WWT_18" Galvanized P-Clamps_LSD Asiede + Bisde 18” Clamp needed. | Copper State Bolt & Nut Company | 3796.5 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2401228A | 3785.8 | F21P1 WWT package (Installation and 2 batch tanks) | Tmah + L20 Sludge CDA materials | Ferguson Enterprises, LLC | 3785.8 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407044A | 3750 | WWT B side Project | WWT- threaded machine | Ferguson Enterprises, LLC | 3750 | 1 | Mechanical |  |  | WWT
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2406013A | 3749.82 | Chemical & WCCS B Side Project | F21P1 - Electric conduit | Elliott Electric Supply, Inc. | 3749.82 | 1 | Electrical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402135A | 3709 | F21P1 WWT package (Installation and 2 batch tanks) | WWT UMEC copper tubing to instrument | University Mechanical & Engineering Contractors, Inc. | 3709 | 1 | Mechanical | Main Contract Scope | WWT | WWT | UMEC
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2309171A | 3702 | F21P1 UPW | MMI-T1034B-ladder repair | Milling Machinery, Inc. | 3702 | 1 | Mechanical | Main Contract Scope | UPW | UPW | MMI
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2311117A | 3683.55 | F21P1 Chemical & WCCS package | CDS LORRY TO BRIDGE PFA Tin in Swagelok SUS material Insert EP(Electro Polishing) | GOLD STONE DEVELOPMENT CO., LTD. | 3683.55 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2405040A | 3653.67 | F21P1 UPW | Materials for Train 2 from Taiwan Supplier | Ze-Wei Industrial Co., Ltd. | 3653.67 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2406020A | 3610.78 | WWT B side Project | WWT Beam Clamps & Base_20240603 (B Side) | Copper State Bolt & Nut Company | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2408141A | 3608.9 | WWT B side Project | WWT shortage materials on the B side LSR, CCR, and ACF-1928 | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Electrical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407012A | 3598 | WWT B side Project | These instruments will be installed for control system of B site. | Process Technology, Inc | 3598 | 1 | Electrical |  |  | WWT
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2312065A | 3591 | F21P1 Chemical & WCCS package | CDS Lorry Crossover Steps. | Milling Machinery, Inc. | 3591 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2310075A | 3591 | F21P1 Chemical & WCCS package | CDS Lorry Crossover Steps. | Milling Machinery, Inc. | 3591 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2406044A | 3586.55 | WWT B side Project | WWT CDA B SUS material | Ferguson Enterprises, LLC | 3586.55 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2403004A | 3580 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Center Ring_20240228 (A Side) | Pure Plastics, LLC | 3580 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | QAQC | USC21C003 | USCSB2304030A | 3575 | F21P1 UPW | MCP-1,4 Special Inspection | Shermco Industries, Inc. | 3575 | 1 | Electrical | Main Contract Scope | UPW | Base-Build | Labor
Base-Build | UPW | Others | Material | USC21C009 | USCSB2404149A | 3556.74 | F21P1 WWT package (Installation and 2 batch tanks) | Amazon - UPW Clean up and equipment maintenance | A&A Materials | 3233.4 | 0.90909 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | UPW | Housekeeping
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202006A | 3554.47 | F21P1 UPW | Autodesk AECC License | Autodesk, Inc. | 3554.47 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407063A | 3536 | WWT B side Project | WWT FAB Chemical dump centralizer | Pure Plastics, LLC | 3536 | 1 | Mechanical |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2210004A | 3528.33 | F21P1 Chemical & WCCS package | AECC License | Autodesk, Inc. | 3528.33 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | Software
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209013A | 3511.5 | F21P1 Chemical & WCCS package | Lenovo Laptop | Lenovo Group Ltd | 3511.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402006A | 3502 | F21P1 Chemical & WCCS package | CDS pipe labels | J A Hansen Company DBA Hansen Supply Company | 3502 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Others | QAQC | USC22C019 | USCSB2312154A | 3500 | AMC monitor 595T0 | FAB B VOC Mechanical Observation | LSW Engineers Arizona, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | VOC | Labor
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2311039A | 3500 | F21P1 UPW | Prominent H2O2 Starup service | Precision Integrated Systems, LLC | 1750 | 0.5 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2311093A | 3492.06 | WWT Change Order (Piping) | WWT 300lb SUS Flange | Ferguson Enterprises, LLC | 3492.06 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405077A | 3482 | WWT B side Project | WWT Welding Rod_20240510 (B Side) | Supertung Industrial Co., Ltd. | 3482 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402028A | 3442.64 | F21P1 WWT package (Installation and 2 batch tanks) | SUS added to A side 02/01 all drop not finish 1st order(SUS WWTSP1E2024-1) | Ferguson Enterprises, LLC | 3442.64 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2406045A | 3427.2 | F21P1 Chemical & WCCS package | CGS Global Manpower Labor for painting of housekeeping pads | CGS Global Support, LLC | 3427.2 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304026A | 3423.5 | F21P1 WWT package (Installation and 2 batch tanks) | Small pipe reinforcement | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208023A | 3418.27 | F21P1 UPW | Lenovo Laptop | Lenovo Group Ltd | 3418.27 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2211016A | 3408 | F21P1 WWT package (Installation and 2 batch tanks) | Ebro Butterfly Valve | Engineered Process Controls, LLC | 3408 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2311133A | 3360 | F21P1 UPW | UPW-ORGANO-flexible joints | Organo USA, Inc | 3360 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2311137A | 3357.6 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-PSS-motor valve installation | Process Service Specialists, LLC of Delaware | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | PSS
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2210014A | 3355.7 | F21P1 UPW | Lenovo Laptop | Lenovo Group Ltd | 3355.7 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2407086A | 3355 | Chemical & WCCS B Side Project | F21P1 B side 電力訊號貼紙_Chemical | DIABASE TECHNOLOGY CO LTD | 0 | 0 | Electrical |  |  | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2305069A | 3355 | F21P1 Chemical & WCCS package | TSMC F21P1 Items | Marketech International Corp. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2305068A | 3348.64 | F21P1 UPW | UPW pipe pressure test nitrogen | Linde Gas and Equipment Inc | 3348.64 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Others | Site Expense | USC24C006 | USCSB2407140A | 3345 | WWT B side Project | WWT Tent 9 WMS Service Order(12 month) | 3PL Central LLC dba Extensiv | 1371.55 | 0.41003 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2303014A | 3344.96 | F21P1 UPW | UPW tank sight glasses and angle stops | Harrington Industrial Plastics LLC | 3344.96 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2305089A | 3325.52 | F21P1 Chemical & WCCS package | EW NEW BOX ADD | FusionHPX LLC | 3325.52 | 1 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2408006A | 3319 | WWT B side Project | WWT: (400 Total) Centralizer for H2SO2 and NaOH Rework | Pure Plastics, LLC | 3319 | 1 | Mechanical |  |  | WWT
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2401034A | 3304 | F21P1 Chemical & WCCS package | CDS Move C02 Cylinder 不追加 | Milling Machinery, Inc. | 3304 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208021A | 3285.55 | F21P1 UPW | Lenovo Laptop | Lenovo Group Ltd | 3285.55 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USC2112015A | 3282.49 | F21P1 Chemical & WCCS package | Sleeve | Nippon Pillar Corporation of America | 3282.49 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2303061A | 3280 | F21P1 UPW | UPW MCP-1, 4 Engineering Design | LSW Engineers Arizona, Inc. | 3280 | 1 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | UPW | Electrical | Labor | USC21C003 | USCSB2303001A | 3280 | F21P1 UPW | TSMC F21P1 WRC UPW MCP-21 Temp Feed | LSW Engineers Arizona, Inc. | 3280 | 1 | Electrical | CO Scope (adding/additional scope) | UPW | UPW | Labor
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2312177A | 3279.22 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-lab-duct pipe connector | Chern Shuo System Technology Co., Ltd. | 3279.22 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407121A | 3277.69 | WWT B side Project | CDA System Hardware_WWT | Copper State Bolt & Nut Company | 564.93 | 0.17236 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2402014A | 3266 | WWT Change Order (Piping) | WWT Stripper Fan Connection | Mega Union Technology Inc. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Others | Site Expense | USC23C045 | USCSB2402130A | 3246.65 | WWT Change Order (Piping) | WWT 7 Chemical - 1 | Thomas Scientific Holdings LLC | 3111.84 | 0.95848 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2409048A | 3237.92 | F21P1 UPW | Foxboro Instrument Swap A Side T&M | Rosendin Electric, Inc. | 0 | 0 | Electrical |  |  | UPW
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208003A | 3236.97 | F21P1 UPW | Lenovo Laptop | Lenovo Group Ltd | 3236.97 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | M+L | USC21C006 | USCSB2401225A | 3227 | F21P1 Slurry package | CDS WLS SS anchor brackets | Milling Machinery, Inc. | 3227 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402172A | 3200.49 | F21P1 Chemical & WCCS package | CDS HPM Punch materials etc | Southwest Fastener Division of NEFCO | 3199.13 | 0.99958 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2312032A | 3190.2 | F21P1 WWT package (Installation and 2 batch tanks) | Tmah extra bolts requirement (MU) | Copper State Bolt & Nut Company | 3190.2 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405001A | 3173.32 | WWT B side Project | WWT Diaphragm_20240430 (B Side) | Hwa Chi Technology Co., Ltd | 3173.32 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208027A | 3170.1 | F21P1 UPW | Iphones, Ipads | T-Mobile USA Inc | 3170.1 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Civil | Labor | USC21C014 | USCSB2308171A | 3165 | F21P1 WH2SO4 | Modify Trench In WRC L20 | Degan Construction LLC | 3165 | 1 | Civil | Main Contract Scope | WWT | W-H2SO4 | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112009A | 3137.42 | F21P1 UPW | Dell Laptop/Nest Wifi Router and AP | Best Buy Co., Inc. | 3137.42 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Electrical | M+L | USC21C003 | USCSB2408012A | 3102.4 | F21P1 UPW | PCO 89, Foxboro RIAs, Revision 0 | Rosendin Electric, Inc. | 3102.4 | 1 | Electrical |  |  | UPW | Rosendin
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2406143A | 3098.6 | WWT B side Project | WWT Contain-it double pipe | Harrington Industrial Plastics LLC | 2432.4 | 0.785 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2402011A | 3097.89 | F21 TMAH System | HFC/Tmah sealant tool | Southern Industrial Supply, Inc. | 3097.89 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405038A | 3054.12 | Chemical & WCCS B Side Project | CHEM_WCCS WLS CDA/ GN2 _HF1000-10PC2FSM CV=29.0*2ea | SEMITORR GROUP, LLC | 3054.12 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Electrical | Instrument | USC21C009 | USCSB2405105A | 3040 | F21P1 WWT package (Installation and 2 batch tanks) | WWT LC/MS/MS Acrylic Dust Cover | FusionHPX LLC | 3040 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2209007A | 3000 | F21P1 Chemical & WCCS package | Lorry Building Module Rack - change order | The Blackfin Group | 3000 | 1 | Mechanical | DCR Scope | CDS | Base-Build | Labor
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2307034A | 3000 | F21P1 Chemical & WCCS package | MIC assistance FusionHPX help Harder job | FusionHPX LLC | 3000 | 1 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2308069A | 3000 | F21P1 Chemical & WCCS package | Lorry PFD Review and S&S Rupture Disk Calculation | KAEKO, Inc | 3000 | 1 | Mechanical | DCR Scope | CDS | Chemical | Labor
Base-Build | Low Voltage | Electrical | Labor | USC22C009 | USCSB2405019A | 2996.7 | F21P1 230kV MTR Oil and Drain Pipe work | F21 P1 parking gates installation-(6/11) | NUUO US Inc. | 0 | 0 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2304003A | 2993 | F21P1 Chemical & WCCS package | CDS system Added BOX Items | FusionHPX LLC | 2257.5 | 0.75426 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207019A | 2978.04 | F21P1 UPW | Lenovo Laptop | Lenovo Group Ltd | 2978.04 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207020A | 2978.04 | F21P1 UPW | Lenovo Laptop | Lenovo Group Ltd | 2978.04 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209018A | 2973.28 | F21P1 Chemical & WCCS package | Lenovo Laptop | Lenovo Group Ltd | 2973.28 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209015A | 2973.28 | F21P1 Chemical & WCCS package | Lenovo Laptop | Lenovo Group Ltd | 2973.28 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2211001A | 2971.5 | F21P1 WWT package (Installation and 2 batch tanks) | WWT adapter | Harrington Industrial Plastics LLC | 2971.5 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Labor | USC21C006 | USCSB2402119A | 2965 | F21P1 Slurry package | Urgent Lorry Tank Repair | Milling Machinery, Inc. | 2965 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Equipment
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2403246A | 2946.6 | F21P1 WWT package (Installation and 2 batch tanks) | WWT_Premium White T-Shirt Rags | Thomas Scientific Holdings LLC | 2946.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Material | USC21C007 | USCSB2310084A | 2943.5 | F21P1 VOC package （Installation ) | VOC Fiber cable for re-pull | Consolidated Electrical Distributors Inc | 2943.5 | 1 | Electrical | Main Contract Scope | Low Voltage | VOC | Material
Base-Build | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308019A | 2899 | F21P1 Chemical & WCCS package | TGCM Duty Room items – fridge | Zoro Tools, Inc. | 2899 | 1 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Material
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2406043A | 2856 | F21P1 WWT package (Installation and 2 batch tanks) | CGS Global Manpower Labor for painting of housekeeping pads | CGS Global Support, LLC | 2856 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | UPW | Civil | Project Outsourcing (專案管理外包人力) | USC21C003 | USCSB2406038A | 2856 | F21P1 UPW | CGS Global Manpower Labor for painting of housekeeping pads | CGS Global Support, LLC | 1303.06 | 0.45625 | Civil | Main Contract Scope | UPW | UPW
Base-Build | WWT | Others | Site Expense | USC21C004 | USCSB2312080A | 2853.14 | F21P1 WWT package （USA EQ-FRP tank) | WWT - Lab glassware | Laboratory Sales and Service | 2853.14 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203010A | 2850.58 | F21P1 UPW | Laptop | Lenovo Group Ltd | 2850.58 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203011A | 2850.58 | F21P1 UPW | Laptop | Lenovo Group Ltd | 2850.58 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202018A | 2850.58 | F21P1 UPW | Lenovo Laptop | Lenovo Group Ltd | 2850.58 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203005A | 2850.58 | F21P1 UPW | Laptop | Lenovo Group Ltd | 2850.58 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2312021A | 2808 | F21P1 Chemical & WCCS package | CDS MY-TE 100AB Standard Electric Winch-Hoist for Lorry work | Certex USA LLC | 2808 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Low Voltage | Electrical | Labor | USC22C019 | USCSB2405015A | 2803.5 | AMC monitor 595T0 | F21 P1 parking gates installation-(2/11) | NUUO US Inc. | 0 | 0 | Electrical | The budget execution does not pertain to this project | CCTV | CCTV | NUUO
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402043A | 2800 | F21P1 Chemical & WCCS package | CDS Welder rental for Chemical welding. | Tech South, Inc | 2800 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Site Expense
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406026A | 2794.2 | Chemical & WCCS B Side Project | F21P1 B Side material RH- PVDF 1/2"x3/4" ADPT | Ryan Herco Flow Solutions | 2794.2 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405119A | 2793.9 | WWT B side Project | WWT 6X4 Reducing Tee_20240520 (B Side) | Harrington Industrial Plastics LLC | 2793.9 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2307064A | 2788.4 | F21P1 Chemical & WCCS package | Cush Clamps for Chemical welding. | Copper State Bolt & Nut Company | 2788.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2307011A | 2788.16 | F21P1 UPW | UPW-TSMC OP material-harrington | Harrington Industrial Plastics LLC | 2361.16 | 0.84685 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2305120A | 2785 | F21P1 UPW | UPW Ebro | Engineered Process Controls, LLC | 2785 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204006A | 2770.88 | F21P1 UPW | Lenovo Laptop | Lenovo Group Ltd | 2770.88 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405144A | 2767.52 | Chemical & WCCS B Side Project | CHEM_WCCS_Ladder + EXT cord for F21 project use | NEFCO Construction Supply LLC | 2767.52 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Low Voltage | Electrical | M+L | USC21C013 | USCSB2305026A | 2756 | F21P1 AMC THC Monitoring System | Fiber Splicing | Cannon & Wendt Electric | 2756 | 1 | Electrical | Main Contract Scope | Low Voltage | AMC THC | Labor
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2405143A | 2753.64 | WWT B side Project | WWT - Supply (4) 18inch FRP Flanges to Complete T-740BA-BB-BC Interconnection | Harrington Industrial Plastics LLC | 2753.64 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403007A | 2750.08 | F21P1 Chemical & WCCS package | CDS lcp ms CDA parts | GOLD STONE DEVELOPMENT CO., LTD. | 2750.08 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403028A | 2746.88 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Hardware_20240229 (A Side) | Copper State Bolt & Nut Company | 2746.88 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208015A | 2736.3 | F21P1 UPW | 55 inch black zenstyle computer desk | Amazon.com, Inc. | 2736.3 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310026A | 2728.53 | F21P1 Chemical & WCCS package | Coil .093 rd T 316L SS to 1 13/16 od max x 1 17/32 id min 6 pitch for YaHo work at Lorry FNDP. | Chukar PTS LLC | 2728.53 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206005A | 2726.76 | F21P1 UPW | Amazon Zenstyle Black 55 inch desk trailers for subs | Amazon.com, Inc. | 2726.76 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2404138A | 2726 | F21P1 WWT package (Installation and 2 batch tanks) | CGS Global Support Onsite Manpower | CGS Global Support, LLC | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | Outsourcing
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402042A | 2688.58 | F21P1 Chemical & WCCS package | CDS Conduit Tee | Consolidated Electrical Distributors Inc | 2688.58 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2302057A | 2652 | F21P1 UPW | Adapters for Circuit Breakers in uis Panel | LayerZero Power Systems, Inc. | 2652 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Civil | Labor | USC21C003 | USCSB2308061A | 2647 | F21P1 UPW | WRC L20 Lab Island and Fume Hood | Milling Machinery, Inc. | 2647 | 1 | Civil | The budget execution does not pertain to this project | WWT | UPW | MMI
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206008A | 2638.8 | F21P1 UPW | Zenstyle Computer Desk 55 inch sub trailers | Amazon.com, Inc. | 2638.8 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Instrument | USC21C011 | USCSB2402221A | 2625 | F21 TMAH System | TMAH Customized Clear PVC Cover | Professional Plastics Inc | 2625 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2309133A | 2611.25 | F21P1 UPW | UPW-Nagano Pressure Gauge＆Flow Indicator | Organo USA, Inc | 2611.25 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2301046A | 2609.62 | F21P1 WWT package (Installation and 2 batch tanks) | WWT WRC Mini Line D75 fitting/ PVC bushing material | Harrington Industrial Plastics LLC | 2609.62 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206013A | 2606.37 | F21P1 UPW | Dell Laptop | Best Buy Co., Inc. | 2606.37 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206014A | 2606.37 | F21P1 UPW | Dell Laptop | Best Buy Co., Inc. | 2606.37 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206003A | 2606.1 | F21P1 UPW | Zenstyle black 55 inch computer desk for sub trailers construction | Amazon.com, Inc. | 2606.1 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206004A | 2606.1 | F21P1 UPW | Zenstyle black 55 inch computer desk for sub trailers construction | Amazon.com, Inc. | 2606.1 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Others | Site Expense | USC24C006 | USC2408006A | 2605.34 | WWT B side Project | Mobile Computers, Zebra TC22, WiFi 6, SE4710, 6 Display, 6GB64GB, 16MP RFC, 5MP FFC, 2Pin Back IO, Standard Battery, NFC, Bluetooth, USBC, GMS, NA | Barcodes LLC | 938 | 0.36003 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407114A | 2602 | WWT B side Project | sump pump rubber bushing and welding rod_WWT | Yingsheng Applied Materials Co., Ltd | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Electrical | Instrument | USC21C009 | USCSB2312171A | 2594 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-NH3-outdoor cabinet | Wesco Distribution, Inc. | 2594 | 1 | Electrical | CO Scope (adding/additional scope) | WWT | WWT | Equipment
Base-Build | WWT | Electrical | Material | USC21C009 | USCSB2403288A | 2587.34 | F21P1 WWT package (Installation and 2 batch tanks) | Amazon - Waste Water Team | Amazon.com, Inc. | 0 | 0 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112033A | 2567.52 | F21P1 UPW | Lenovo Yoga 7I Laptop | Best Buy Co., Inc. | 2567.52 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402274A | 2545.92 | F21P1 WWT package (Installation and 2 batch tanks) | WWT SUS Weld Pipes_20240227 (A Side) | Ferguson Enterprises, LLC | 2545.92 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | QAQC | USC21C009 | USCSB2404095A | 2526 | F21P1 WWT package (Installation and 2 batch tanks) | FAB A WWT and WWTD Observation (Change Order) | Page Southerland Page, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | WWT | WWT | Labor
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2306104A | 2521.1 | F21P1 WWT package (Installation and 2 batch tanks) | FAB bolts request #2 | Duncan Bolt Co. | 2521.1 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2310101A | 2520 | F21P1 UPW | UPW-AnCor-UT2211B,3111B-ladder modify | An-Cor Industrial Plastics, Inc. | 2520 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | UPW | Others | Commissioning | USC21C003 | USCSB2307008A | 2500 | F21P1 UPW | Remove Water and Chemical from Tanks(UPW Degan tank clean) | Degan Construction LLC | 2500 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Civil | M+L | USC23C045 | USCSB2309143A | 2500 | WWT Change Order (Piping) | WWT T-260 (8) Epoxy Coating Anchors | Degan Construction LLC | 1500 | 0.6 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111032A | 2475.8 | F21P1 UPW | File Cabinet | Amazon.com, Inc. | 2475.8 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203018A | 2462.88 | F21P1 UPW | Zen 55 inch desk for moldular | Amazon.com, Inc. | 2462.88 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Material | USC22C009 | USCSB2403066A | 2455 | F21P1 230kV MTR Oil and Drain Pipe work | UPW-Harrington-U-bent for Brine RO tank | Harrington Industrial Plastics LLC | 2255 | 0.91853 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2302049A | 2451 | F21P1 UPW | Organo Freight and Forwarding Charges/Expenses | Organo USA, Inc | 2451 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | M+L | USC24C005 | USCSB2405184A | 2432.19 | Chemical & WCCS B Side Project | 3 house keeping pads 128"x48" PAD PREP, EPOXY AND YELLOW PERIMETOR PAINT | SD Engineering Technology LLC | 2432.19 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | WWT | Steel | Labor | USC21C009 | USCSB2403054A | 2430 | F21P1 WWT package (Installation and 2 batch tanks) | WWT: Triazole Electrical Panel Anchoring | Milling Machinery, Inc. | 2430 | 1 | Steel | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Instrument | USC24C005 | USCSB2404180A | 2428.27 | Chemical & WCCS B Side Project | Amazon - Chemical Team | Amazon.com, Inc. | 2230.99 | 0.91876 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405130A | 2408.7 | WWT B side Project | WWT RT&Bushing_20240521 (B Side) | Harrington Industrial Plastics LLC | 2408.7 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2404132A | 2400.92 | F21P1 WWT package (Installation and 2 batch tanks) | WWT B side Drain label | J A Hansen Company DBA Hansen Supply Company | 2376.27 | 0.98973 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304050A | 2393.6 | F21P1 WWT package (Installation and 2 batch tanks) | Equalization Line Bolts/Gaskets | Copper State Bolt & Nut Company | 2372.22 | 0.99107 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC24C008 | USCSB2406098A | 2350 | UPW B Side Project | UPW B Side Panel Materials | Organo USA, Inc | 2350 | 1 | Electrical | Main Contract Scope | UPW | UPW
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2312027A | 2300.44 | F21P1 WWT package (Installation and 2 batch tanks) | Chemical Lab Cabinets for WWT lab in WRC | Thomas Scientific Holdings LLC | 2300.44 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC22C023 | USCSB2210022A | 2298.12 | AZ GF Agru Material | GF PP&PVDF Material Organo | Organo Technology CO., LTD | 2298.12 | 1 | Mechanical |  |  | GF Agru Material | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203017A | 2286.96 | F21P1 UPW | 55 inch computer desk for site modular | Amazon.com, Inc. | 2286.96 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Material | USC24C008 | USCSB2405044A | 2278.51 | UPW B Side Project | Sticker | StickerYou Inc. | 2141.99 | 0.94008 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2306103A | 2264.28 | F21P1 WWT package (Installation and 2 batch tanks) | FAB bolts request #1 | Duncan Bolt Co. | 2264.28 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304023A | 2259.02 | F21P1 WWT package (Installation and 2 batch tanks) | Flanges for the Chem Lab connection from L10 to LB2 | Harrington Industrial Plastics LLC | 2259.02 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203012A | 2250.66 | F21P1 UPW | Power Strips surge protectors | Amazon.com, Inc. | 2250.66 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2302030A | 2250 | F21P1 WWT package (Installation and 2 batch tanks) | Spot prime and painting of 30 steel header supports | Phoenix House Painting.com LLC dba PHP Commercial Painting | 2250 | 1 | Civil | Main Contract Scope | WWT | WWT | Labor
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403016A | 2250 | F21P1 Chemical & WCCS package | CDS strut end caps | Southwest Fastener Division of NEFCO | 2250 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402237A | 2244 | F21P1 Chemical & WCCS package | CDS 2" Pipe cush clamps | Southwest Fastener Division of NEFCO | 44.88 | 0.02 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Steel | Labor | USC23C045 | USCSB2310016A | 2239 | WWT Change Order (Piping) | WWT Flange Level Gauge Platform Mod(MU)( T125AC/AD LG clash) | Milling Machinery, Inc. | 2239 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2310002A | 2226.34 | F21P1 Chemical & WCCS package | VMB parts for Chemical team | Nippon Pillar Corporation of America | 2226.34 | 1 | Mechanical | DCR Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2405099A | 2225 | F21P1 WWT package (Installation and 2 batch tanks) | WWT 2" Backing Ring_20240515 (A&B Side) | Harrington Industrial Plastics LLC | 2225 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2312073A | 2194 | F21P1 Chemical & WCCS package | CDS Electronic pressure recorder CR87P requested by Henry | Yih Jiun Enterprise Co., Ltd. | 2194 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2307028A | 2190.8 | F21P1 UPW | UPW sight glass ball valves | Harrington Industrial Plastics LLC | 2190.8 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2405111A | 2177 | F21P1 Chemical & WCCS package | CDS L brackets requested by Alonso in 2023 | Milling Machinery, Inc. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203013A | 2167.5 | F21P1 UPW | Desk for modular toward total needed | Amazon.com, Inc. | 2167.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2312082A | 2149.2 | F21P1 Chemical & WCCS package | CDS 1-1/2"x2" 45 ELBOW 316LEP/304AP | GOLD STONE DEVELOPMENT CO., LTD. | 2149.2 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2405070A | 2125.4 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Blind Flange 4&6_20240510 (A Side) | Harrington Industrial Plastics LLC | 2125.4 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Material | USC24C005 | USCSB2404052A | 2119.1 | Chemical & WCCS B Side Project | 電料補齊.1 20240403 | Consolidated Electrical Distributors Inc | 2119.1 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111058A | 2118.4 | F21P1 UPW | Office Desk | American Furniture Warehouse | 2118.4 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309017A | 2103.75 | F21P1 Chemical & WCCS package | Flanges used for CDU exhaust drain. | FusionHPX LLC | 2103.75 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Others | QAQC | USC24C005 | USCSB2408031A | 2100 | Chemical & WCCS B Side Project | CDA/GN2 Particle testing Equipment Calibration (設備校正0806) | Particle Measuring Systems, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Chemical
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2407005A | 2100 | Chemical & WCCS B Side Project | F21P1 Fab LB2 WWT Tank H2SO4 Header | FusionHPX LLC | 2100 | 1 | Mechanical |  |  | Chemical
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2311028A | 2099.16 | F21P1 WWT package (Installation and 2 batch tanks) | WWT chemical storage in LB2 | WW Grainger Inc | 2099.16 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208016A | 2098.57 | F21P1 UPW | 3 drawer black personal desk files | Amazon.com, Inc. | 2098.57 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2309090A | 2098.5 | F21P1 Chemical & WCCS package | Chemical box&box cover for location of support welding & hole location | FusionHPX LLC | 2098.5 | 1 | Mechanical | DCR Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2306041A | 2084.61 | F21P1 Chemical & WCCS package | Scissor lift for Chemical welding | United Rentals | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Site Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201010A | 2063.38 | F21P1 UPW | Laptop | Best Buy Co., Inc. | 2063.38 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2204015A | 2057.4 | F21P1 UPW | Added Order (Nagano Adapter) | Ashcroft Inc. | 2057.4 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402247A | 2042.83 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Hardware_20240223 (A Side) | Copper State Bolt & Nut Company | 2042.83 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2311100A | 2040 | F21P1 Chemical & WCCS package | CDS M421C0201-54 missing needle valves replacement. | JIM & STEVE INDUSTRIAL CO., LTD | 2040 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403023A | 2016 | F21P1 Chemical & WCCS package | CDS tools for flare | Nippon Pillar Corporation of America | 2016 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202004A | 2009.09 | F21P1 UPW | Desktop Computer | Amazon.com, Inc. | 2009.09 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202005A | 1998.22 | F21P1 UPW | Laptop | Best Buy Co., Inc. | 1998.22 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203016A | 1993.55 | F21P1 UPW | 55 inch computer desk | Amazon.com, Inc. | 1993.55 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Electrical | Material | USC21C006 | USCSB2312167A | 1989.6 | F21P1 Slurry package | CDS MIC A side electrical materials | Independent Electric Supply, Inc. | 1989.6 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2306100A | 1989.35 | F21 TMAH System | WWT-CCB-PVC | Harrington Industrial Plastics LLC | 1989.35 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402250A | 1987.68 | F21P1 Chemical & WCCS package | CDS sealing materials | Consolidated Electrical Distributors Inc | 1987.68 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C005 | USCSB2405037A | 1980 | Chemical & WCCS B Side Project | CHEM_ panel design_20240506_ (12004) | FusionHPX LLC | 1980 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2409095A | 1979.59 | WWT B side Project | WWT shortage materials on the B side NaOH H2SO4, AWD O3 | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2312148A | 1974.7 | F21P1 Chemical & WCCS package | CDS Materials for Lorry requested by Ben and John | Ferguson Enterprises, LLC | 1974.7 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Electrical | Material | USC24C006 | USCSB2405152A | 1973.12 | WWT B side Project | These cables will be installed for control system of WSR. | Crescent Electric Supply Co | 1973.12 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2308052A | 1972 | F21P1 Chemical & WCCS package | Dual Contained Pipe testing(Pressure test tools for Lorry) | M. Caputo Technical Services, Inc. | 1972 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Labor
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403270A | 1965 | F21P1 WWT package (Installation and 2 batch tanks) | WWT PVC Glue & Primer_20240327 | Harrington Industrial Plastics LLC | 1965 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2402008A | 1963.5 | F21P1 Chemical & WCCS package | CDS Sensor FLS-VM-400 | AutomationDirect.com INC | 1785 | 0.90909 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2404174A | 1960.05 | Chemical & WCCS B Side Project | CHEM_Waste System Fab L20 PVDF PIPE USED | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407032A | 1958.08 | WWT B side Project | Materials for B side LB 1 Drain | Harrington Industrial Plastics LLC | 1958.08 | 1 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303044A | 1956.36 | F21P1 WWT package (Installation and 2 batch tanks) | Litho Drain Bolts and Gaskets | Duncan Bolt Co. | 1956.36 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Others | Site Expense | USC21C003 | USC2111007A | 1954.6 | F21P1 UPW | Cabinet | Amazon.com, Inc. | 1954.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | UPW | MISC Expense
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2311024A | 1950.21 | F21P1 UPW | UPW-GF-limitswitch | Ryan Herco Flow Solutions | 1950.21 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Others | Safety | USC21C009 | USCSB2407016A | 1950 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - SCS Lorry to tunnel confined space rescue | Safety Compliance Services, Inc | 1950 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201008A | 1942.99 | F21P1 UPW | Autodesk AECC License | Autodesk, Inc. | 1942.99 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201009A | 1933.77 | F21P1 UPW | Autodesk AECC License | Autodesk, Inc. | 1933.77 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403099A | 1928.71 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Hardware_20240308 (A Side) | Copper State Bolt & Nut Company | 1928.71 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Material | USC21C007 | USCSB2309177A | 1918.57 | F21P1 VOC package （Installation ) | F21 P1 VOC Cable | Consolidated Electrical Distributors Inc | 1918.57 | 1 | Electrical | DCR Scope | Low Voltage | VOC | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2308026A | 1914 | F21P1 UPW | Damaged Instrument Sensors | Organo USA, Inc | 1914 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204003A | 1900.48 | F21P1 UPW | Lenovo Laptop, Dell Laptop | Best Buy Co., Inc. | 1900.48 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Electrical | Material | USC22C021 | USCSB2403115A | 1900 | F21P1 Chemical Lab setup | 2 Hach Dissolved Oxygen Sensor Repair | Hach Company | 1900 | 1 | Electrical | Main Contract Scope | UPW | Chemical Lab | Equipment
Base-Build | WWT | Electrical | Instrument | USC24C006 | USCSB2405156A | 1899.49 | WWT B side Project | WWT Container Covers_20240524 (B Side) | Global Equipment Company Inc. | 1899.49 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407010A | 1875.15 | WWT B side Project | WWT Hardware #1 | Copper State Bolt & Nut Company | 1875.15 | 1 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303100A | 1861.86 | F21P1 WWT package (Installation and 2 batch tanks) | Litho adding Tee material | Harrington Industrial Plastics LLC | 1861.86 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2212020A | 1850 | F21P1 WWT package (Installation and 2 batch tanks) | Grounding for generator and fuel cube | Wilson Electric Services Corporation | 1850 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | WWT | Site Expense
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2409079A | 1849.8 | WWT B side Project | WWT shortage materials on the B side ACF-720BA~BD | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2311080A | 1847.66 | F21 TMAH System | Tmah Hardware request #1(coated bolts not enough) | Copper State Bolt & Nut Company | 0 | 0 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112026A | 1846.18 | F21P1 UPW | Laptop | Best Buy Co., Inc. | 1846.18 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Electrical | Instrument | USC21C004 | USCSB2306020A | 1844 | F21P1 WWT package （USA EQ-FRP tank) | WWT-Lab oven & scale | Global Equipment Company Inc. | 1844 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Electrical | Instrument | USC21C011 | USCSB2402048A | 1840.39 | F21 TMAH System | WWT Leak Detector Accessory-Omron F03-20T | Mouser Electronics | 1840.39 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2305096A | 1836 | F21P1 UPW | UPW test pump | Ferguson Enterprises, LLC | 1836 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | UPW | Steel | Labor | USC21C003 | USCSB2403299A | 1828 | F21P1 UPW | WRC L20 Additional Welding | Milling Machinery, Inc. | 0 | 0 | Steel | Main Contract Scope | UPW | Base-Build | Site Expense
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2312099A | 1825 | F21P1 UPW | UPW-Tomoe-part repair | Tomoe USA, Inc. | 1825 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C002 | USCSB2105001A | 1825 | TSMC AZ Temp Office Speed Gate | Speed gate opeing cover and install | B&D Industries, Inc. | 1825 | 1 | Electrical | Main Contract Scope | Low Voltage | Speed Gate | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2305047A | 1820.62 | F21P1 WWT package (Installation and 2 batch tanks) | Stainless Steel Pipe in Lorry | Ferguson Enterprises, LLC | 1820.62 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Site Expense | USC21C004 | USCSB2403186A | 1804 | F21P1 WWT package （USA EQ-FRP tank) | U-Line - MIMO - Move In/Move Out Team | U-Line Corporation | 1791.9 | 0.99329 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | MIMO/Rigging
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203006A | 1800.86 | F21P1 UPW | Laptop | Lenovo Group Ltd | 1800.86 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC22C013 | USCSB2401139A | 1763.38 | F21P1 QR Lab Security & CCTV | Laydown Material - Grainger | WW Grainger Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | 0 | Base-Build | MIMO/Rigging
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309115A | 1745.58 | F21P1 Chemical & WCCS package | FNDP Material request for YaHo work at Lorry FNDP. | Arizona/Albuquerque Valve & Fitting Corp. | 1745.58 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Others | Commissioning | USC21C003 | USCSB2404171A | 1737.6 | F21P1 UPW | Chemical for commissioning flush | Univar Solutions USA Inc. | 1737.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202017A | 1737.58 | F21P1 UPW | Dell Laptop | Best Buy Co., Inc. | 1737.58 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206012A | 1737.58 | F21P1 UPW | Dell Laptop | Best Buy Co., Inc. | 1737.58 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Material | USC22C012 | USCSB2403085A | 1730 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | UPW-ORGANO BSGN valves | Organo USA, Inc | 1730 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402038A | 1727.5 | F21P1 Chemical & WCCS package | CDS Lorry FNDP parts | SEMITORR GROUP, LLC | 1727.5 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402047A | 1718.93 | F21P1 Chemical & WCCS package | CDS BT union and gasket | Arizona/Albuquerque Valve & Fitting Corp. | 1718.93 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203008A | 1711.76 | F21P1 UPW | Tablet | Amazon.com, Inc. | 1711.76 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Commissioning | USC21C005 | USCSB2310115A | 1700 | F21P1 Chemical & WCCS package | CDS Commission PE tubes requested by Albert Tseng | Harrington Industrial Plastics LLC | 1700 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111055A | 1672.3 | F21P1 UPW | Metal 3 drawer filing cabinets | Amazon.com, Inc. | 1672.3 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204009A | 1672.2 | F21P1 UPW | Sceptre 24IN & 7IN2 | Amazon.com, Inc. | 1672.2 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2405087A | 1664.55 | F21P1 WWT package (Installation and 2 batch tanks) | WWT B side Drain label - batch 2 | J A Hansen Company DBA Hansen Supply Company | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2309095A | 1663 | WWT Change Order (Piping) | WWT (118) Tank Crossover Platform Brackets | Milling Machinery, Inc. | 1663 | 1 | Steel | Main Contract Scope | WWT | WWT | MMI
Base-Build | WWT | Electrical | Instrument | USC24C006 | USCSB2404113A | 1653.08 | WWT B side Project | Megaunion 220V-400V變壓器 | Mega Union Technology Inc. | 0 | 0 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2307117A | 1650 | F21P1 Chemical & WCCS package | Welder equipment (pipe saw) for Chemical welding. | Tech South, Inc | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | UPW | Mechanical | Material | USC22C012 | USCSB2403032A | 1645 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | UPW-train B valves from ORGANO | Organo USA, Inc | 1645 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | UPW | Electrical | QAQC | USC21C003 | USCSB2303051A | 1640 | F21P1 UPW | TSMC F21P1 WRC UPW Special Inspections | LSW Engineers Arizona, Inc. | 1640 | 1 | Electrical | Main Contract Scope | UPW | UPW | Labor
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2404161A | 1639.95 | WWT Change Order (Piping) | WWT blower GIP gasket purchase | Ferguson Enterprises, LLC | 1639.95 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202009A | 1639.11 | F21P1 UPW | Autodesk AECC License | Autodesk, Inc. | 1639.11 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402079A | 1635.28 | F21P1 WWT package (Installation and 2 batch tanks) | WWT SUS Pipes_20240207 (A Side) | Ferguson Enterprises, LLC | 1635.28 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111053A | 1631.36 | F21P1 UPW | Office Chairs | Amazon.com, Inc. | 1631.36 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207011A | 1628.98 | F21P1 UPW | Dell Laptop | Best Buy Co., Inc. | 1628.98 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206009A | 1628.4 | F21P1 UPW | Home Office Ergo black mesh chairs for subs trailers | Amazon.com, Inc. | 1628.4 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206006A | 1628.4 | F21P1 UPW | Ergo black mesh back office chairs for sub trailers | Amazon.com, Inc. | 1628.4 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208001A | 1628.4 | F21P1 UPW | Black mesh ergonomic office desk chairs | Amazon.com, Inc. | 1628.4 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403005A | 1616.73 | F21P1 Chemical & WCCS package | CDS 2" OD cush clamps EG | Southwest Fastener Division of NEFCO | 1616.7 | 0.99998 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Electrical | Material | USC21C007 | USCSB2308073A | 1615 | F21P1 VOC package （Installation ) | F21 P1 VOC 2 k-type wire order | Consolidated Electrical Distributors Inc | 1615 | 1 | Electrical | Main Contract Scope | Low Voltage | VOC | Material
Base-Build | WWT | Civil | M+L | USC21C009 | USCSB2406136A | 1604 | F21P1 WWT package (Installation and 2 batch tanks) | sand,prep,expoxy and yellow safety paint at one house keeping pad. | J.T. Thorpe Industrial DBA: Liberty Industrial Group | 1604 | 1 | Civil |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203024A | 1602.72 | F21P1 UPW | 55 inch Zen Computer desk | Amazon.com, Inc. | 1602.72 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207008A | 1599.58 | F21P1 UPW | 24in& 27in Monitor, Keyboard and Mouse | Amazon.com, Inc. | 1599.58 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207010A | 1596.2 | F21P1 UPW | Pallet Trucks, 2500KG,1220mm long forks,牙叉內 220mm,H-6710 | U-Line Corporation | 1596.2 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Equipment
Base-Build | Low Voltage | Others | Site Expense | USC21C007 | USCSB2212022A | 1595 | F21P1 VOC package （Installation ) | 2 months rental-Light tower | Southland Industries | 1595 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | CO Scope (adding/additional scope) | Low Voltage | VOC | Southland
Base-Build | WWT | Mechanical | Site Expense | USC21C011 | USCSB2312064A | 1583.25 | F21 TMAH System | WWT_Testing tool | WW Grainger Inc | 1583.25 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402095A | 1579.7 | F21P1 Chemical & WCCS package | CDS HPM Punch materials | McMaster-Carr Supply Company | 1579.7 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404213A | 1564.04 | WWT B side Project | WWT Fittings_ZeWei_20240426 (B Side) | Ze-Wei Industrial Co., Ltd. | 1395.26 | 0.89209 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206002A | 1563.3 | F21P1 UPW | Office Ergonomic black mesh chairs for construction sub trailers | Amazon.com, Inc. | 1563.3 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206001A | 1563.3 | F21P1 UPW | Office Ergonomic black mesh chairs for construction sub trailers | Amazon.com, Inc. | 1563.3 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201016A | 1550.4 | F21P1 UPW | Office Chairs | Amazon.com, Inc. | 1550.4 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Electrical | Material | USC21C009 | USCSB2312116B | 1550 | F21P1 WWT package (Installation and 2 batch tanks) | CDS CED MIC A side 2 of 2 per Paul | Consolidated Electrical Distributors Inc | 1550 | 1 | Electrical | 0 | 0 | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2309150A | 1543.05 | F21P1 UPW | UPW sight glass PVC-train B | Harrington Industrial Plastics LLC | 1543.05 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407172A | 1540 | WWT B side Project | WWT - P-780 AB blockage fix | Phoenix Pumps, Inc. | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402254A | 1532 | F21P1 WWT package (Installation and 2 batch tanks) | WWT materials-1 | Yingsheng Applied Materials Co., Ltd | 780 | 0.50914 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208017A | 1520.37 | F21P1 UPW | Samsung 75 inch color tv for conference room 1, Nest security camers | Costco Wholesale Corporation | 1520.37 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Water_Sewer | Civil | M+L | USC21C010 | USCSB2309003A | 1520 | tsmc AZ sewer and water pipeline installation | Modify Handrail Base Plates on Mezz 2 and 3 | Degan Construction LLC | 1520 | 1 | Civil |  |  | Pipeline | Material
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209011A | 1516.06 | F21P1 Chemical & WCCS package | Revu License | Bluebeam, Inc. | 1516.06 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Commissioning | USC21C009 | USCSB2402150A | 1510.55 | F21P1 WWT package (Installation and 2 batch tanks) | WWT 7 Chemical - 2 | Midland Scientific, Inc. | 1510.55 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Civil | Labor | USC21C004 | USCSB2305117A | 1500 | F21P1 WWT package （USA EQ-FRP tank) | Dosing Box Installation | Degan Construction LLC | 1500 | 1 | Civil | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2209003A | 1456 | F21P1 UPW | HDX tan folding tables 8ft, Lifetime tan folding tables 8 ft | The Home Depot, Inc | 1456 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402240A | 1455.6 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Gasket_20240223 (A Side) | Harrington Industrial Plastics LLC | 1455.6 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2404121A | 1437.77 | F21P1 UPW | SS Clamps to repair 14" SS Leaks | Ferguson Enterprises, LLC | 1437.77 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2404220A | 1433.95 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Clamps_20240429 (A Side) | NEFCO Construction Supply LLC | 1433.95 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2401154A | 1414 | F21P1 WWT package (Installation and 2 batch tanks) | WWT tools for MU | The Home Depot, Inc | 1414 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2307094A | 1408.4 | F21P1 Chemical & WCCS package | CPVC purchase | Harrington Industrial Plastics LLC | 1408.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2311125A | 1404.6 | F21P1 Chemical & WCCS package | CDS Nippon Pillar connectors used for PFA tie in on CDU and Tank of B side. | Nippon Pillar Corporation of America | 1404.6 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2310184A | 1400 | F21P1 Chemical & WCCS package | CDS Welder rental for Chemical welding. | Tech South, Inc | 1400 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2403069A | 1400 | F21P1 Chemical & WCCS package | CDS Welder rental for Chemical welding.( RENTAL FROM 1-29-24 TO 2-26-24) | Tech South, Inc | 1400 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Site Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112030A | 1395.75 | F21P1 UPW | AutoCAD License | Autodesk, Inc. | 1395.75 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2403202A | 1391.96 | F21P1 UPW | 8800lb Dolly for MIMO - Move In/Move Out Team | Amazon.com, Inc. | 1160.08 | 0.83341 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MIMO/Rigging
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209012A | 1384.5 | F21P1 Chemical & WCCS package | 27in Monitor | Amazon.com, Inc. | 1384.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304032A | 1379.84 | F21P1 WWT package (Installation and 2 batch tanks) | 780/120 Header Bolts | Duncan Bolt Co. | 1379.84 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208007A | 1368.15 | F21P1 UPW | Zenstyle Computer Desk black 55 inch | Amazon.com, Inc. | 1368.15 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2301051A | 1360 | F21P1 UPW | T1021C handrail replacement | Harrington Industrial Plastics LLC | 1360 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401080A | 1359.45 | F21P1 Chemical & WCCS package | CDS Unions to replace all Union Box accessories of Lorry to HPM IPA and PFA to SUS. | Arizona/Albuquerque Valve & Fitting Corp. | 1359.45 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2309004A | 1350 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Machine PP D63 12” PN10 pipe to PN6 | Harrington Industrial Plastics LLC | 1350 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2212012A | 1350 | F21P1 WWT package （USA EQ-FRP tank) | Flange Gaskets | Milling Machinery, Inc. | 1350 | 1 | Mechanical | Main Contract Scope | WWT | WWT | MMI
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2307033A | 1345.6 | F21P1 UPW | UPW enclosure flange | Harrington Industrial Plastics LLC | 1345.6 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403156A | 1339 | F21P1 Chemical & WCCS package | CDS clamps for the T supports | Milling Machinery, Inc. | 1339 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203023A | 1335.6 | F21P1 UPW | Zenstyle computer desk 55 inch. | Amazon.com, Inc. | 1335.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2309160A | 1334 | F21P1 UPW | TW-UPW-Gaskets | TCELC CO., LTD | 1334 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202010A | 1332.08 | F21P1 UPW | Air Quality Monitor | Amazon.com, Inc. | 1332.08 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2312187A | 1331.45 | F21P1 Slurry package | CDS Snoop and 1/2 Tee's | Arizona/Albuquerque Valve & Fitting Corp. | 1331.45 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207014A | 1330.13 | F21P1 UPW | 24in& 27in Monitor | Amazon.com, Inc. | 1330.13 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201013A | 1324.8 | F21P1 UPW | Office Chairs | Amazon.com, Inc. | 1324.8 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303070A | 1317.58 | F21P1 WWT package (Installation and 2 batch tanks) | Waterfall Bolts/Gaskets | Duncan Bolt Co. | 1317.57 | 0.99999 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2405003A | 1314.25 | F21P1 UPW | BIM and Valves for MAU Bypass | Organo USA, Inc | 1314.25 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | UPW | Mechanical | Material | USC24C008 | USCSB2407039A | 1313 | UPW B Side Project | Valve Handles for B Area | Engineered Process Controls, LLC | 1313 | 1 | Mechanical |  |  | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USC2112004A | 1309.6 | F21P1 Chemical & WCCS package | pressure regulating valve/Straight connector | Flodraulic Group | 1309.6 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308018A | 1295.98 | F21P1 Chemical & WCCS package | TGCM Duty Room items – white board and cabinets | Zoro Tools, Inc. | 1295.98 | 1 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405002A | 1292.9 | WWT B side Project | WWT 2-1/2" & 4-5/8" Clamps (B Side)_20240429 | Copper State Bolt & Nut Company | 1292.9 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2312137A | 1280 | F21P1 UPW | UPW-ORGANO-flexible joints for ICW | Organo USA, Inc | 1280 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403100A | 1264.24 | F21P1 WWT package (Installation and 2 batch tanks) | WWT PVC & PP Pipes_20240308 (A Side) | Harrington Industrial Plastics LLC | 1264.24 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2403022A | 1260 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - Replacement Coupling for P-350 AA/AB | Phoenix Pumps, Inc. | 1228.12 | 0.9747 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111060A | 1247.81 | F21P1 UPW | Free standing refrigerator | Amazon.com, Inc. | 1247.81 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2407025A | 1238.15 | Chemical & WCCS B Side Project | F21P1 B Side PFA - Nylon Line | Amazon.com, Inc. | 1125.59 | 0.90909 | Mechanical |  |  | Chemical
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2404004A | 1237 | F21P1 UPW | Temperature Indicator for Train B | Organo USA, Inc | 1237 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Labor
Base-Build | Chemical | Mechanical | M+L | USC21C005 | USCSB2308093A | 1228 | F21P1 Chemical & WCCS package | L30 PDP Panel Move to clean room | Milling Machinery, Inc. | 1228 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | MMI
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2307116A | 1224.85 | F21P1 WWT package (Installation and 2 batch tanks) | WRC Bolt-PSS request (Double Order) | Duncan Bolt Co. | 1224.84 | 0.99999 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304014A | 1224.85 | F21P1 WWT package (Installation and 2 batch tanks) | WRC Bolt-PSS request (100% paid by Jim) | Duncan Bolt Co. | 1224.85 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2305098A | 1224.7 | F21P1 UPW | UPW sight glass | Harrington Industrial Plastics LLC | 1224.7 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2212010A | 1216.4 | F21P1 WWT package (Installation and 2 batch tanks) | WRC CCB camlocks | CamlockDirect | 1216.4 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404117A | 1216.08 | WWT B side Project | WWT SUS 90Elbow_20240412 (B Side) | Ferguson Enterprises, LLC | 1216.08 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | M+L | USC24C005 | USCSB2404134A | 1206.55 | Chemical & WCCS B Side Project | CHEM_L30 SDS VMB/ piping supports 240415020001_ (QT04350562-1) | Copper State Bolt & Nut Company | 1206.55 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Instrument | USC24C006 | USCSB2404027A | 1193 | WWT B side Project | WWT Center Ring 4x2_20240402 (B Side) | Pure Plastics, LLC | 1193 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2310003A | 1190 | F21P1 Chemical & WCCS package | VMB parts for Chemical team | SEMITORR GROUP, LLC | 1190 | 1 | Mechanical | DCR Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403027A | 1189.25 | F21P1 Chemical & WCCS package | CDS 1/4" ball valve and snoop | Arizona/Albuquerque Valve & Fitting Corp. | 1189.25 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403128A | 1182.55 | F21P1 Chemical & WCCS package | CDS VCR, etc | Arizona/Albuquerque Valve & Fitting Corp. | 1182.55 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2307127A | 1180.5 | F21P1 Slurry package | Slurry H2O2 VMB | SEMITORR GROUP, LLC | 1180.5 | 1 | Mechanical | Main Contract Scope | SDS | Slurry | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203002A | 1170.18 | F21P1 UPW | Desk chairs | Amazon.com, Inc. | 1170.18 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2402281A | 1163.64 | F21P1 Chemical & WCCS package | CDS NZMB1-A25-NA breaker | Consolidated Electrical Distributors Inc | 1163.64 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Labor | USC21C009 | USCSB2312195A | 1147.47 | F21P1 WWT package (Installation and 2 batch tanks) | WWT tools for MU | Abbeon Cal Inc. | 1147.47 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC22C021 | USCSB2307093A | 1144.39 | F21P1 Chemical Lab setup | GC Lab Valve | Ryan Herco Flow Solutions | 1144.39 | 1 | Mechanical | The budget execution does not pertain to this project | Chemical Lab | Chemical Lab | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2404026A | 1136.74 | F21P1 UPW | PP/EPDM PNU 627 DIA VLV 2: FLG | Ryan Herco Flow Solutions | 1136.74 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2208011A | 1136 | F21P1 UPW | UPW MABAT SDI Filter Paper | MABAT Chemical systems Ltd | 1136 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Electrical | Material | USC21C007 | USCSB2307110A | 1133 | F21P1 VOC package （Installation ) | VOC 1 Ground wire | Consolidated Electrical Distributors Inc | 1133 | 1 | Electrical | CO Scope (adding/additional scope) | Low Voltage | VOC | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207005A | 1129 | F21P1 UPW | Black ergominc mesh back office chairs | Amazon.com, Inc. | 1129 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403094A | 1120 | F21P1 Chemical & WCCS package | CDS green screws | Valqua NGC, Inc. | 1120 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404195A | 1115.18 | WWT B side Project | WWT 1-2 Bolts_20240424 (A&B Side) | Copper State Bolt & Nut Company | 1115.18 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405030A | 1105.2 | WWT B side Project | WWT 5_8 Bolt_20240506 (B Side) | Copper State Bolt & Nut Company | 1105.2 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209017A | 1102.64 | F21P1 Chemical & WCCS package | 27in Monitor | Amazon.com, Inc. | 1102.64 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2307059A | 1102.58 | F21P1 Chemical & WCCS package | Argon for Chemical welding. Qty: 2. | Linde Gas and Equipment Inc | 1099.46 | 0.99717 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2307055A | 1102.58 | F21P1 Chemical & WCCS package | Argon for Chemical welding. Qty: 2. | Linde Gas and Equipment Inc | 1102.58 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309043A | 1100 | F21P1 Chemical & WCCS package | NATURAL POLYPRO COVER WITH 1.257" THRU HOLE. | FusionHPX LLC | 1100 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202007A | 1095.13 | F21P1 UPW | Monitor | Amazon.com, Inc. | 1095.13 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402212A | 1088.6 | F21P1 Chemical & WCCS package | CDS 20amp breakers | Consolidated Electrical Distributors Inc | 1088.6 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207015A | 1085.85 | F21P1 UPW | 27in Monitor | Amazon.com, Inc. | 1085.85 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407035A | 1079.74 | WWT B side Project | Sticker | StickerYou Inc. | 1050.79 | 0.97319 | Mechanical |  |  | WWT | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405057A | 1057.43 | WWT B side Project | WWT 1-2 Bolts_20240508 (B Side) | Copper State Bolt & Nut Company | 1057.43 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204014A | 1055.52 | F21P1 UPW | 55 inch zenstyle computer desk | Amazon.com, Inc. | 1055.52 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111059A | 1050.65 | F21P1 UPW | Water dispensers | Amazon.com, Inc. | 1050.65 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208008A | 1049.28 | F21P1 UPW | Black small 3 drawer file cabinets | Amazon.com, Inc. | 1049.28 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2306110A | 1046.87 | F21P1 UPW | UPW skids cover replacement | Pure Plastics, LLC | 1046.87 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Low Voltage | Electrical | M+L | USC21C008 | USCSB2409011A | 1037.99 | F21P1 CCTV & Security | F21 P1 VOC Electricity Change Order _CO#25_Batch 4/6 | Spectra Electrical Services, Inc. | 1037.99 | 1 | Electrical |  |  | CCTV
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402157A | 1035.06 | F21P1 Chemical & WCCS package | Quality Material | Amazon.com, Inc. | 963.11 | 0.93049 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111025A | 1031.69 | F21P1 UPW | Dell Laptop for Engineers | Best Buy Co., Inc. | 1031.69 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Low Voltage | Others | Site Expense | USC22C019 | USCSB2401162A | 1031.36 | AMC monitor 595T0 | Laydown Materials - Zoro | Zoro Tools, Inc. | 952 | 0.92305 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | 0 | 0 | AMC THC | Site Expense
Base-Build | Low Voltage | Electrical | Material | USC22C019 | USCSB2403020B | 1026 | AMC monitor 595T0 | F21 Brcode system _ G-Bit | ACME Control System Corporation | 1026 | 1 | Electrical | The budget execution does not pertain to this project | Barcode | Barcode | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2310103A | 1017.69 | F21P1 UPW | UPW-NaHSO3 cover repair | Pure Plastics, LLC | 1017.69 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402245A | 1016.21 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Narrow flat washer_20240223 (A Side) | Copper State Bolt & Nut Company | 1016.21 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2306124A | 1008 | F21P1 Chemical & WCCS package | Pillar tools for flare | Nippon Pillar Corporation of America | 1008 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2209005A | 1001.88 | F21P1 UPW | Zen style modern desk work station 55" black | Walmart Inc | 1001.88 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Others | Safety | USC24C006 | USCSB2409044A | 1000 | WWT B side Project | WWT: SCS PR - Confined Space Safety Tank T-140AB | Safety Compliance Services, Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | WWT | Mechanical | Commissioning | USC21C009 | USCSB2403120A | 996.82 | F21P1 WWT package (Installation and 2 batch tanks) | WWT 7 Chemical - 3 | Midland Scientific, Inc. | 949.36 | 0.95239 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310061A | 996 | F21P1 Chemical & WCCS package | 2” BA tube for Yaho work at Lorry FNDP | SEMITORR GROUP, LLC | 996 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2407006A | 992 | Chemical & WCCS B Side Project | F21P1 Fab HMP Mixing box | FusionHPX LLC | 992 | 1 | Mechanical |  |  | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310060A | 977.28 | F21P1 Chemical & WCCS package | Material for YaHo at Lorry FNDP. | GOLD STONE DEVELOPMENT CO., LTD. | 977.28 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303042A | 976.84 | F21P1 WWT package (Installation and 2 batch tanks) | Bolts/Gaskets for 6.5 LB2 | Duncan Bolt Co. | 976.84 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | M+L | USC21C003 | USCSB2305075A | 975.1 | F21P1 UPW | UPW skids cover replacement | Pure Plastics, LLC | 975.1 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203020A | 970.73 | F21P1 UPW | AutoCAD License | Autodesk, Inc. | 970.73 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2403262A | 966.72 | F21P1 WWT package (Installation and 2 batch tanks) | WWT WRC laboratory furniture_1 | Amazon.com, Inc. | 862.36 | 0.89205 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402021A | 956.96 | F21P1 Chemical & WCCS package | CDS CDA fittings | Arizona/Albuquerque Valve & Fitting Corp. | 956.96 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208024A | 956.7 | F21P1 UPW | Box License | Box, Inc. | 956.7 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | WWT | Mechanical | Instrument | USC21C011 | USCSB2306139A | 954.36 | F21 TMAH System | WWT-PVC blind flange 20” | Pure Plastics, LLC | 954.36 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USCSB2306082A | 950 | F21P1 UPW | Forklift for the pipe crating project at the TSMC site | Raymond West Intralogistics Solutions | 950 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Equipment
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2305095A | 935.14 | F21P1 UPW | Eaton Broken | Border State Industries, Inc. | 935.14 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204012A | 933.6 | F21P1 UPW | Ergonomic Desk Chair Mesh Cavalier for Sub Trailers | Amazon.com, Inc. | 933.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402186A | 932.84 | F21P1 Chemical & WCCS package | CDS Monstair low b2b pc strut | Southwest Fastener Division of NEFCO | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2312203A | 930 | F21P1 UPW | UPW-earthquake limiters | Harmony Rubber Industry Co., Ltd. | 930 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | UPW | Mechanical | M+L | USC24C008 | USCSB2408161A | 930 | UPW B Side Project | Damaged Valves on A Side, Replacement order through UMEC, TSMC issued PO | University Mechanical & Engineering Contractors, Inc. | 0 | 0 | Mechanical |  |  | UPW
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2312054A | 916.32 | F21P1 WWT package (Installation and 2 batch tanks) | CDA line WRC L20 material revise | WW Grainger Inc | 916.32 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401165A | 910.4 | F21P1 Chemical & WCCS package | CDS ICP Mass CDA GN2 parts | GOLD STONE DEVELOPMENT CO., LTD. | 910.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402027A | 908.9 | F21P1 WWT package (Installation and 2 batch tanks) | Tmah Resin filling | McMaster-Carr Supply Company | 908.9 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403211A | 900 | F21P1 Chemical & WCCS package | CDS Circuit Lockout Kit | Wesco Distribution, Inc. | 900 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2312019A | 898.67 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-lab tech-sink | LabTech Supply Company Inc | 898.67 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2403177A | 898.04 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Cleaning Material | The Home Depot, Inc | 791.69 | 0.88158 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2311002A | 892 | WWT Change Order (Piping) | T-125AC Replacement Top Manway (Include manway, hardware, and gasket) | Harrington Industrial Plastics LLC | 892 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2209019A | 879.6 | F21P1 UPW | Zenstyle desk 55 inch black | Amazon.com, Inc. | 879.6 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203025A | 879.5 | F21P1 UPW | Super Deal 55 inch modern desk | Amazon.com, Inc. | 879.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402077A | 875 | F21P1 Chemical & WCCS package | CDS M6 x 1 x 16 (5/8) Screws PP | Professional Plastics Inc | 875 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111022A | 868.79 | F21P1 UPW | Sony TV for Company owned house | Costco Wholesale Corporation | 868.79 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2303039A | 859.8 | F21P1 UPW | UPW Pressure indicator | Hwa Chi Technology Co., Ltd | 859.8 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303045A | 856.92 | F21P1 WWT package (Installation and 2 batch tanks) | Gaskets | Harrington Industrial Plastics LLC | 856.92 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Commissioning | USC24C006 | USCSB2404178A | 856.8 | WWT B side Project | Safety Filter for LSR ACF | ServAPure Company | 856.8 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2301001A | 856.02 | F21P1 UPW | UPW Copper Connector Bars for MCP | Organo USA, Inc | 856.02 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC23C045 | USCSB2403266A | 849.12 | WWT Change Order (Piping) | WWT: (6) ANSI300 4" Flanges for LSR | Ferguson Enterprises, LLC | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC24C008 | USCSB2406057A | 839.13 | UPW B Side Project | Ashcroft PIA KM31 | Ashcroft Inc. | 0 | 0 | Electrical | Main Contract Scope | UPW | UPW
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2404100A | 838.74 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Gasket_20240410 (A Side) | Harrington Industrial Plastics LLC | 838.74 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC22C012 | USCSB2403015A | 830.76 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | UPW-GF valve for train B | Ryan Herco Flow Solutions | 830.76 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Electrical | M+L | USC21C009 | USCSB2312107A | 826.65 | F21P1 WWT package (Installation and 2 batch tanks) | WWT CCE Change Orders_CO64 | Commercial Comm and Electric Inc | 785.32 | 0.95 | Electrical | DCR Scope | WWT | WWT | CCE
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208006A | 814.2 | F21P1 UPW | Office Chair Black with Mesh | Amazon.com, Inc. | 814.2 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207016A | 802.7 | F21P1 UPW | 24in Monitor | Amazon.com, Inc. | 802.7 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Others | Site Expense | USC24C006 | USCSB2407024A | 799 | WWT B side Project | Storage containers for tools and materials for Fab A side | The Home Depot, Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | WWT | Mechanical | Commissioning | USC21C011 | USCSB2401244A | 798.45 | F21 TMAH System | WWT-TMAH-LCMSMS-Nitrogen | Linde Gas and Equipment Inc | 798.36 | 0.99989 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2402026A | 791 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Cleaning Material | The Home Depot, Inc | 791 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C003 | USCSB2409003A | 788.6 | F21P1 UPW | Horiba SILA Buffer Tank and PFA Tube | HORIBA Instruments Incorporated | 0 | 0 | Mechanical |  |  | UPW
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309172A | 779.7 | F21P1 Chemical & WCCS package | NFPA Diamond Signs for chemical tanks, HPM 20. | Pensacola Hardware Company | 779.7 | 1 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2211028A | 779.52 | F21P1 UPW | UPW WRC Chemical room ball valves (1-1/2”) | Harrington Industrial Plastics LLC | 779.52 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | UPW | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C008 | USCSB2407096A | 774 | UPW B Side Project | Anion Tower Materials_UPW | Organo USA, Inc | 0 | 0 | Mechanical |  |  | UPW
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403255A | 769.85 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Hardware_20240320 (A Side) | Copper State Bolt & Nut Company | 769.85 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2404024A | 765 | F21P1 UPW | Butterfly Valves for Train B | Organo USA, Inc | 765 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208022A | 764.7 | F21P1 UPW | 24in Monitors | Amazon.com, Inc. | 764.7 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111035A | 764.12 | F21P1 UPW | Bulletin Boards | Amazon.com, Inc. | 764.12 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111056A | 762.32 | F21P1 UPW | Double sided white boards | Amazon.com, Inc. | 762.32 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208020A | 758.03 | F21P1 UPW | Revu License | Bluebeam, Inc. | 758.03 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112029A | 758.03 | F21P1 UPW | Bluebeam Revu | Bluebeam, Inc. | 758.03 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208002A | 758.03 | F21P1 UPW | Bluebeam Revu | Bluebeam, Inc. | 758.03 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303035A | 757.58 | F21P1 WWT package (Installation and 2 batch tanks) | Bushings for 6.5 LB2 | Harrington Industrial Plastics LLC | 757.58 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303069A | 756.73 | F21P1 WWT package (Installation and 2 batch tanks) | Bolts/Gaskets | Duncan Bolt Co. | 756.73 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201011A | 755.55 | F21P1 UPW | Monitor | Amazon.com, Inc. | 755.55 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Electrical | Instrument | USC21C011 | USCSB2406062A | 755.28 | F21 TMAH System | F21 WWT industrial media converter | ACME Control System Corporation | 755.28 | 1 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Civil | Labor | USC22C022 | USCSB2312079A | 750 | F21P1 Triazole treatment system | WWT - Remove Unused Triazole Pad in WRC between E14 and D14 | Degan Construction LLC | 750 | 1 | Civil | DCR Scope | WWT | Triazole | Material
Base-Build | UPW | Others | Material | USC21C003 | USCSB2401073A | 749.93 | F21P1 UPW | UPW-Northernmedia-ACF gravels | Northern Filter Media, Inc. | 749.93 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2211040A | 747.8 | F21P1 WWT package (Installation and 2 batch tanks) | wastewater adapter | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2307119A | 747.8 | F21 TMAH System | WWT-PVC material | Harrington Industrial Plastics LLC | 747.8 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206011A | 744.29 | F21P1 UPW | AutoCAD | Autodesk, Inc. | 744.29 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2210002A | 743.8 | F21P1 Chemical & WCCS package | 24in Monitor | Amazon.com, Inc. | 743.8 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207009A | 732.65 | F21P1 UPW | 24in Monitor | Amazon.com, Inc. | 732.65 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207004A | 715.36 | F21P1 UPW | large 72 inch locking file cabinet | Amazon.com, Inc. | 715.36 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2312178A | 706.55 | F21P1 WWT package (Installation and 2 batch tanks) | Laminator Sheets&Mounting Tape | Amazon.com, Inc. | 623 | 0.88175 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201007A | 705.89 | F21P1 UPW | 10.3" Tablet | Amazon.com, Inc. | 705.89 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Others | Material | USC21C003 | USCSB2312194A | 705.84 | F21P1 UPW | UPW-commissioning horse | Bridgestone Hosepower, LLC | 705.84 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2401057A | 703.29 | F21P1 WWT package (Installation and 2 batch tanks) | WWT_pressure gauge | WW Grainger Inc | 703.29 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Mechanical |  | USC22C013 | USCSB2407134A | 700 | F21P1 QR Lab Security & CCTV | F21 P1 VOC duct Label | J A Hansen Company DBA Hansen Supply Company | 700 | 1 | Mechanical |  |  | VOC | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204010A | 693.57 | F21P1 UPW | AutoCAD License | Autodesk, Inc. | 693.57 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202013A | 689.95 | F21P1 UPW | Desks for modular | Walmart Inc | 689.95 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2306025A | 680.02 | F21P1 Chemical & WCCS package | Argon for Chemical welding | Linde Gas and Equipment Inc | 612.52 | 0.90074 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2304048A | 667 | F21P1 UPW | UPW Tomoe angle adjuster | Tomoe USA, Inc. | 667 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Electrical | Material | USC23C045 | USCSB2407027A | 659.84 | WWT Change Order (Piping) | A site LB2 VFD power cable re-pull | Consolidated Electrical Distributors Inc | 0 | 0 | Electrical |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC21C010 | USCSB2402196A | 652.3 | tsmc AZ sewer and water pipeline installation | Laydown, Bins & Rack to organize bolts & elbows | Amazon.com, Inc. | 592.98 | 0.90906 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402189A | 652 | F21P1 Chemical & WCCS package | CDS coax tube | SEMITORR GROUP, LLC | 652 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402185A | 650 | F21P1 Chemical & WCCS package | CDS Welder rental for Chemical welding. | Tech South, Inc | 650 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Site Expense
Base-Build | WWT | Others | Commissioning | USC21C009 | USCSB2306076A | 650 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-CCB dry-run CO | Univar Solutions USA Inc. | 650 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2403017A | 650 | F21P1 Chemical & WCCS package | CDS Welder rental for Chemical welding.(RENTAL FROM 2-2-24 TO 3-1-24) | Tech South, Inc | 650 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Site Expense
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402227A | 650 | F21P1 Chemical & WCCS package | CDS Welder rental for Chemical welding(RENTAL FROM 1-4-24 TO 2-1-24) | Tech South, Inc | 650 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Site Expense
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2311049A | 650 | F21P1 Chemical & WCCS package | CDS Welder rental for Chemical welding. | Tech South, Inc | 650 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | UPW | Others | Commissioning | USC21C003 | USCSB2307140A | 650 | F21P1 UPW | UPW-CCB dry-run | Univar Solutions USA Inc. | 650 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402187A | 650 | F21P1 Chemical & WCCS package | CDS Welder rental for Chemical welding.(RENTAL FROM 11-7-23 TO 12-5-23) | Tech South, Inc | 650 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Site Expense
Base-Build | Low Voltage | Electrical | M+L | USC24C007 | USCSB2409013A | 648.03 | Low Voltage B Side Project | F21 P1 VOC Electricity Change Order _CO#25_Batch 6/6 | Spectra Electrical Services, Inc. | 648.03 | 1 | Electrical |  |  | VOC
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112027A | 647.12 | F21P1 UPW | Sceptre Monitor 24in | Amazon.com, Inc. | 647.12 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208012A | 640.2 | F21P1 UPW | Black metal folding chairs for workers lunchroom at Fab and 8 foot folding tables | Walmart Inc | 640.2 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C003 | USCSB2409001A | 634.55 | F21P1 UPW | CIA Sensor | HORIBA Taiwan, Inc. | 0 | 0 | Mechanical |  |  | UPW
Base-Build | WWT | Others | Site Expense | USC21C011 | USCSB2402010A | 629.87 | F21 TMAH System | HFC/ Tmah tools | The Home Depot, Inc | 629.87 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | TMAH | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207018A | 626.32 | F21P1 UPW | 24in Monitor | Amazon.com, Inc. | 626.32 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2409035A | 624.97 | WWT B side Project | WWT shortage of hardware materials on the B side and WRC | Copper State Bolt & Nut Company | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111057A | 624.22 | F21P1 UPW | Mini fridges | Amazon.com, Inc. | 624.22 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Others | Site Expense | USC22C020 | USCSB2401136A | 623.39 | F21P1 Penetration Pipe | Laydown Material - Home Depot | The Home Depot, Inc | 602.8 | 0.96697 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | Base-Build | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2210012A | 623.18 | F21P1 UPW | Rigid Shop Vacuum 16 gallon dry and wet/yellow jacket extension cords/vacumn filters | The Home Depot, Inc | 623.18 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2310185A | 621.84 | F21P1 WWT package (Installation and 2 batch tanks) | WWT CDA SUS Socket Weld Fittings | Ferguson Enterprises, LLC | 621.84 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2303101A | 619.44 | F21P1 WWT package (Installation and 2 batch tanks) | NFPA labels | Pensacola Hardware Company | 619.44 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Civil | Material | USC24C005 | USCSB2407060A | 619.03 | Chemical & WCCS B Side Project | CHEM_CDS project_Ladder and EXT code | NEFCO Construction Supply LLC | 619.03 | 1 | Civil |  |  | Chemical
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202016A | 608.04 | F21P1 UPW | 24in Monitor | Amazon.com, Inc. | 608.04 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Electrical | Instrument | USC21C004 | USCSB2403181A | 607.09 | F21P1 WWT package （USA EQ-FRP tank) | Global Industrial - MIMO - Move In/Move Out Team | Global Equipment Company Inc. | 551.9 | 0.90909 | Electrical | Main Contract Scope | WWT | Base-Build | MIMO/Rigging
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2210005A | 605.3 | F21P1 UPW | 24in Monitor | Amazon.com, Inc. | 605.3 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403121A | 603.68 | F21P1 WWT package (Installation and 2 batch tanks) | WWT 5_Blind Flange_20240312 (A Side) | Harrington Industrial Plastics LLC | 603.68 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2403040A | 601.82 | F21P1 WWT package (Installation and 2 batch tanks) | WWT - Replacement guard for P-350 AB | Phoenix Pumps, Inc. | 601.82 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2301001A | 600 | F21P1 UPW | Non Woven Shoe Cover | Super Starnix SDN BHD | 600 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401242A | 599.26 | F21P1 Chemical & WCCS package | CDS Tee and Bulkhead. | Arizona/Albuquerque Valve & Fitting Corp. | 599.26 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2402238A | 597.4 | F21P1 UPW | UPW-Harrington-U bolts and tank gaskets | Harrington Industrial Plastics LLC | 597.4 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2210008A | 591.84 | F21P1 UPW | Two Rolling double sided whiteboards 72 x 40 for conference rooms. | Amazon.com, Inc. | 591.84 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC23C014 | USCSB2402166A | 583.22 | F21P1 Labor incentive program-MICU | Laydown Material - U Line | U-Line Corporation | 530.2 | 0.90909 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | MIMO/Rigging
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303103A | 573.84 | F21P1 WWT package (Installation and 2 batch tanks) | WWT SUS CDA TPC port | Ferguson Enterprises, LLC | 546.78 | 0.95284 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Electrical | Instrument | USC21C009 | USCSB2402124A | 568.54 | F21P1 WWT package (Installation and 2 batch tanks) | Sulfate Analyser SO4 reagents | Hach Company | 568.54 | 1 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | WWT | Electrical | Material | USC21C009 | USCSB2401066A | 564.88 | F21P1 WWT package (Installation and 2 batch tanks) | WWT CCE Change Orders | Commercial Comm and Electric Inc | 0 | 0 | Electrical | DCR Scope | WWT | WWT | CCE
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208025A | 562.8 | F21P1 UPW | 24in Monitor | Amazon.com, Inc. | 562.8 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402198A | 562 | F21P1 Chemical & WCCS package | CDS 1" SS EP tube | Banner Industries of N.E. Inc | 562 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2209016A | 561.2 | F21P1 Chemical & WCCS package | 24in Monitor | Amazon.com, Inc. | 561.2 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201012A | 553.8 | F21P1 UPW | Monitor | Amazon.com, Inc. | 553.8 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206015A | 551.01 | F21P1 UPW | AECC License | Autodesk, Inc. | 551.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | Chemical | Mechanical | Commissioning | USC21C005 | USCSB2312028A | 546.4 | F21P1 Chemical & WCCS package | CDS commissioning 20L PE Tank/Bottle - Acid and alkali resistance requested by Steven Chiu. Qty: 20. | Thomas Scientific Holdings LLC | 546.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2305077A | 544.38 | F21P1 UPW | UPW AGRU check valves | Harrington Industrial Plastics LLC | 544.38 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203026A | 542.8 | F21P1 UPW | Cavalier Ergo Mesh Chairs | Amazon.com, Inc. | 542.8 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204004A | 538.63 | F21P1 UPW | 5 Port Switch, Netgear Router | Best Buy Co., Inc. | 538.63 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310122A | 535 | F21P1 Chemical & WCCS package | CDS Paint for W-TANK Scratch Repair | Continental Coatings Inc. | 535 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309135A | 535 | F21P1 Chemical & WCCS package | Paint for Tank Scratch Repair | Continental Coatings Inc. | 535 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112013A | 534.26 | F21P1 UPW | 27" Sceptre Monitor | Amazon.com, Inc. | 534.26 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2307139A | 533.43 | F21P1 Chemical & WCCS package | TGCM Duty Room items – projector | Office Depot Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309117A | 533 | F21P1 Chemical & WCCS package | Tee and elbow for YaHo at Lorry FNDP. | SEMITORR GROUP, LLC | 533 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2404011A | 531.44 | WWT B side Project | WWT SS Fittings_20240401 (B Side) | Ferguson Enterprises, LLC | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2312158A | 528 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-Gripper 2 in. Plastic Mechanical Test Plug | The Home Depot, Inc | 528 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Site Expense | USC23C040 | USCSB2401137A | 522.9 | TSMC F21 Clean Room Suit | Laydown Material - Amazon | Amazon.com, Inc. | 522.9 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | MIMO/Rigging
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2403010A | 515.84 | F21P1 Chemical & WCCS package | CDS Mini circuit breaker, QO, 15A, 2 pole, 240VAC, 22kA, bolt on mount | Graybar Electric Company, Inc. | 515.84 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207006A | 512.33 | F21P1 UPW | AECC License | Autodesk, Inc. | 512.33 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2409054A | 510.04 | WWT B side Project | WWT shortage of hardware materials on the B side and WRC | Copper State Bolt & Nut Company | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2210007A | 502.82 | F21P1 UPW | 55 inch Samsung flat screen TV UHD/one tv stand for new TV | Walmart Inc | 502.82 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Electrical | Instrument | USC21C011 | USCSB2403256A | 493.63 | F21 TMAH System | WWT-Ammonia standards solution | Winn Marion Barber, LLC | 493.63 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402099A | 491.37 | F21P1 Chemical & WCCS package | Chemical Team Material | Amazon.com, Inc. | 446.7 | 0.90909 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401081A | 491.05 | F21P1 Chemical & WCCS package | CDS Reducing Union Adapter | Nippon Pillar Corporation of America | 491.05 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112008A | 485.34 | F21P1 UPW | 24" Monitor | Amazon.com, Inc. | 485.34 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112007A | 481.5 | F21P1 UPW | Office chairs | Amazon.com, Inc. | 481.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2312009A | 480 | F21 TMAH System | Helix bolts Tmah | Copper State Bolt & Nut Company | 480 | 1 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2306142A | 475.52 | F21P1 WWT package (Installation and 2 batch tanks) | Duncan Bolt - unpaid invoice | Duncan Bolt Co. | 475.52 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Instrument | USC21C009 | USCSB2401231A | 468.86 | F21P1 WWT package (Installation and 2 batch tanks) | WWT_pressure gauge QTY:2 | WW Grainger Inc | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204013A | 462.76 | F21P1 UPW | Floor Cord protector for meeting rooms in modular | Amazon.com, Inc. | 462.76 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C009 | USCSB2402191A | 457.11 | F21P1 WWT package (Installation and 2 batch tanks) | (2) Steel Storage cabinets 72" with adjusteable drawers for storing Respitory Equipment and PPE. | Amazon.com, Inc. | 457.11 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111023A | 456.06 | F21P1 UPW | 24" Monitors for Employees | Amazon.com, Inc. | 456.06 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2303097A | 453 | F21P1 UPW | Prominent backpressure valve | Prominent Fluid Controls (Taiwan) Co. Ltd. | 453 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403102A | 452.21 | F21P1 Chemical & WCCS package | CDS JJ Healy CO2 90 elbow | Arizona/Albuquerque Valve & Fitting Corp. | 452.21 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Electrical | Instrument | USC21C009 | USCSB2306053A | 443.54 | F21P1 WWT package (Installation and 2 batch tanks) | WWT NH4 analyzer (Chemical Only) | Winn Marion Barber, LLC | 0 | 0 | Electrical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2310195A | 442.5 | F21P1 Chemical & WCCS package | CDS HPM10 A Side DHL Drain cover PP plates requested | Professional Plastics Inc | 442.5 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402132A | 437.7 | F21P1 Chemical & WCCS package | CDS flare nut 1-1/4 | Harrington Industrial Plastics LLC | 437.7 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406041A | 423.5 | Chemical & WCCS B Side Project | F21P1 B Side material Harrington - PVC Conduit fitting for PP | Harrington Industrial Plastics LLC | 423.5 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111064A | 412.66 | F21P1 UPW | L-shaped office desks | Amazon.com, Inc. | 412.66 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Electrical | Material | USC22C012 | USCSB2404045A | 410 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | pH Sensor Accessories & Control Net Adapters from Organo | Organo USA, Inc | 410 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2403184A | 409.68 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-lab tech-hood sash weight | LabTech Supply Company Inc | 324.45 | 0.79196 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406005A | 407.4 | Chemical & WCCS B Side Project | F21P1 WCCS PVDF ADPT | Ryan Herco Flow Solutions | 407.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402120A | 406.87 | F21P1 Chemical & WCCS package | Tools for chemical team | Amazon.com, Inc. | 326.15 | 0.80161 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402197A | 405 | F21P1 Chemical & WCCS package | CDS 5/8 Screw sets | Southwest Fastener Division of NEFCO | 405 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2402128A | 404.04 | F21P1 UPW | FIQ Sensor Cable x2 for FIQCWS9034 | Organo USA, Inc | 404.04 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2312023A | 392 | F21P1 UPW | DO Power Supply | Hach Company | 392 | 1 | Electrical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2407083A | 390.96 | WWT B side Project | Sticker | StickerYou Inc. | 356 | 0.91058 | Mechanical |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406042A | 389.9 | Chemical & WCCS B Side Project | F21P1 B Side material Amz - RS-232 Connector | Amazon.com, Inc. | 389.9 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Others | Labor | USC21C005 | USCSB2403298A | 388.25 | F21P1 Chemical & WCCS package | Amazon - MIMO - Move In/Move Out Team | Amazon.com, Inc. | 347.3 | 0.89453 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | CDS | Base-Build | MIMO/Rigging
Base-Build | Chemical | Mechanical | Material | USC21C005 | USC2112001A | 383.92 | F21P1 Chemical & WCCS package | Ball Valve | Ryan Herco Flow Solutions | 285.8 | 0.74443 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111054A | 382.06 | F21P1 UPW | Cork Boards | Amazon.com, Inc. | 382.06 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203004A | 380.09 | F21P1 UPW | Router | Best Buy Co., Inc. | 380.09 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208011A | 379.56 | F21P1 UPW | Black Metal Chairs for Fab lunchroom | Walmart Inc | 379.56 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2209002A | 379.56 | F21P1 UPW | Black metal folding chairs | Walmart Inc | 379.56 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202014A | 379.01 | F21P1 UPW | Bluebeam Revu | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204005A | 379.01 | F21P1 UPW | Revu License | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2206010A | 379.01 | F21P1 UPW | Bluebeam Revu | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207007A | 379.01 | F21P1 UPW | Bluebeam Revu | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111020A | 379.01 | F21P1 UPW | Revu | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203007A | 379.01 | F21P1 UPW | Bluebeam Revu | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111021A | 379.01 | F21P1 UPW | Revu | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207012A | 379.01 | F21P1 UPW | Bluebeam Revu | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202015A | 379.01 | F21P1 UPW | Bluebeam Revu | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2207017A | 379.01 | F21P1 UPW | Bluebeam Revu | Bluebeam, Inc. | 379.01 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2312138A | 367.56 | F21P1 UPW | UPW-ORGANO-WRC BPV | Organo USA, Inc | 367.56 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208019A | 361.47 | F21P1 UPW | Revit License | Autodesk, Inc. | 361.47 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | UPW | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C003 | USCSB2409002A | 355.94 | F21P1 UPW | PIA KM31-584_Broken PIA instrument replacement | Organo USA, Inc | 0 | 0 | Mechanical |  |  | UPW
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2404151A | 353.05 | F21P1 UPW | PSAT L Bracket | Organo USA, Inc | 353.05 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2403093A | 350 | F21P1 Chemical & WCCS package | CDS Welder rental for Chemical welding.(RENTAL FROM 2-27-24 To 3-8-24) | Tech South, Inc | 350 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Site Expense
Base-Build | WWT | Others | Commissioning | USC21C009 | USCSB2306044A | 350 | F21P1 WWT package (Installation and 2 batch tanks) | WWT-CCB dry-run | Univar Solutions USA Inc. | 350 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2312030A | 349 | F21P1 Chemical & WCCS package | CDS 1/4 in. x 800 ft. Nylon Solid Braid Rope, White for JuWei PFA line work requested by Jay Huang. | The Home Depot, Inc | 313.57 | 0.89848 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402225A | 348.9 | F21P1 WWT package (Installation and 2 batch tanks) | WWT E2 missing SUS material | Ferguson Enterprises, LLC | 348.9 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2210011A | 347.5 | F21P1 UPW | 3 drawer black file cabinet | Amazon.com, Inc. | 347.5 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2311073A | 347.2 | F21P1 Chemical & WCCS package | CDS:adapters for Fab CDU drain port at B side. | SEMITORR GROUP, LLC | 347.2 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111019A | 345.28 | F21P1 UPW | Autodesk Revit | Autodesk, Inc. | 345.28 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304002A | 342.3 | F21P1 WWT package (Installation and 2 batch tanks) | Sump pump/SUS bolt | Duncan Bolt Co. | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2305046A | 342.13 | F21P1 UPW | ORGANO isolation valves | Organo USA, Inc | 342.13 | 1 | Mechanical | CO Scope (adding/additional scope) | UPW | UPW | Material
Base-Build | WWT | Mechanical | Material | USC21C014 | USCSB2305109A | 339.73 | F21P1 WH2SO4 | Hardware for Dosing Boxes | Copper State Bolt & Nut Company | 339.73 | 1 | Mechanical | Main Contract Scope | WWT | W-H2SO4 | Material
Base-Build | WWT | Others | Site Expense | USC24C006 | USCSB2406111A | 339.4 | WWT B side Project | WWT Cleaning Material | The Home Depot, Inc | 329 | 0.96936 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304019A | 337 | F21P1 WWT package (Installation and 2 batch tanks) | CCB Box Label | J A Hansen Company DBA Hansen Supply Company | 312 | 0.92582 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2311048A | 328.72 | F21P1 Chemical & WCCS package | CDS blind flanges requested by Ben Chuang for pressure test. | WW Grainger Inc | 328.72 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Electrical | Instrument | USC24C006 | USCSB2405140A | 320.67 | WWT B side Project | 氨氮標準液 | Winn Marion Barber, LLC | 320.67 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2304038A | 318.7 | F21P1 UPW | Seismic snubber YS-90EA | Organo USA, Inc | 318.7 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2404118A | 314.66 | F21P1 Chemical & WCCS package | Quality Material | Amazon.com, Inc. | 278.25 | 0.88429 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Electrical | M+L | USC21C007 | USCSB2306113A | 311.1 | F21P1 VOC package （Installation ) | VOC Electrical:TSMC-MIC VOC Pipe -VEX | J A Hansen Company DBA Hansen Supply Company | 311.1 | 1 | Electrical | Main Contract Scope | Low Voltage | VOC | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112006A | 309.48 | F21P1 UPW | Printer cart with storage | Amazon.com, Inc. | 309.48 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201014A | 304.92 | F21P1 UPW | Solid State Drive | Amazon.com, Inc. | 304.92 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2201001A | 304.61 | F21P1 UPW | Office Chair | Amazon.com, Inc. | 304.61 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406040A | 300.12 | Chemical & WCCS B Side Project | F21P1 B Side material Mcmaster-carr - SUS Y-Strainers | McMaster-Carr Supply Company | 300.12 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402129A | 296 | F21P1 Chemical & WCCS package | CDS plastic clamp | Pure Plastics, LLC | 296 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2401013A | 295.98 | F21P1 WWT package (Installation and 2 batch tanks) | WWT tools and office supplies for MU | Amazon.com, Inc. | 260.4 | 0.87979 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Low Voltage | Mechanical | M+L | USC22C013 | USCSB2406078A | 288.96 | F21P1 QR Lab Security & CCTV | F21-P1_B-SIDE Photoresist cabinet exhaust hookup | HUENG LUEI PROCESS INDUSTRY CO., LTD. | 0 | 0 | Mechanical | The budget execution does not pertain to this project | 光阻櫃 | CCTV
Base-Build | Base-Build | Others | Site Expense | USC21C005 | USC2210003A | 276.9 | F21P1 Chemical & WCCS package | 27in Monitor | Amazon.com, Inc. | 276.9 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Office Supplies | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112031A | 276.49 | F21P1 UPW | LG 34" Monitor | Best Buy Co., Inc. | 276.49 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Others | Housekeeping | USC21C003 | USCSB2404085A | 275.37 | F21P1 UPW | Home Depot - Cleaning and equipment maintenance | The Home Depot, Inc | 248.35 | 0.90188 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Housekeeping
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2312057A | 258.13 | F21P1 Chemical & WCCS package | CDS CED DFK Lorry HPM materials additional quote | Consolidated Electrical Distributors Inc | 258.13 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2409059A | 257.5 | WWT B side Project | WWT shortage materials on the B side NaOH | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Low Voltage | Electrical | Material | USC22C001 | USCSB2405123A | 256.5 | F21 P1 Office and WH Security and CCTV | F21 Barcode system _G-Bit | ACME Control System Corporation | 256.5 | 1 | Electrical | The budget execution does not pertain to this project | 0 | Barcode
Base-Build | UPW | Others | Material | USC21C009 | USCSB2404147A | 251.9 | F21P1 WWT package (Installation and 2 batch tanks) | Amazon - UPW Clean up and equipment maintenance | Amazon.com, Inc. | 229 | 0.90909 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | UPW | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2208018A | 249.67 | F21P1 UPW | VIZ PRO Dry Erase Whiteboard Non Magnetic pack of 2 5x3' | Amazon.com, Inc. | 249.67 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2409058A | 246.2 | WWT B side Project | WWT shortage materials on the B side NaOH | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical |  |  | WWT
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2402093A | 245.76 | F21P1 WWT package (Installation and 2 batch tanks) | WWT SUS Pipes_20240208 (A Side) | Ferguson Enterprises, LLC | 245.76 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Electrical | Material | USC24C006 | USCSB2405091A | 244.89 | WWT B side Project | The electrical pipe installation for power and control of WSR. | Consolidated Electrical Distributors Inc | 244.89 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2308114A | 242.25 | F21P1 Chemical & WCCS package | 1/2" union Qty 5/1/4" gasket Qty 50 For Chemical welding | Arizona/Albuquerque Valve & Fitting Corp. | 242.05 | 0.99917 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Labor | USC21C005 | USCSB2403068A | 241.24 | F21P1 Chemical & WCCS package | CDS NZM1-XTVD DOOR COUPLING ROTARY HDL LOCK | RS AMERICAS, INC | 241.24 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2304027A | 235.2 | F21P1 WWT package (Installation and 2 batch tanks) | NFPA labels | Pensacola Hardware Company | 235.2 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308017A | 234.78 | F21P1 Chemical & WCCS package | TGCM Duty Room items – screen | Office Depot Inc. | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2311128A | 233.4 | F21P1 Chemical & WCCS package | CDS Lorry Exhaust. Elbow 3/4" Super 300 Type | Harrington Industrial Plastics LLC | 233.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2205002A | 228.74 | F21P1 UPW | Construction site modular office supplies | Amazon.com, Inc. | 228.74 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111065A | 220.78 | F21P1 UPW | Office chair | Amazon.com, Inc. | 220.78 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2405174A | 216 | WWT B side Project | WWT PVC PP Unions_20240529 (B Side) | Delpha Plastics Co., Ltd. | 216 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2403203A | 214.5 | F21P1 WWT package (Installation and 2 batch tanks) | WWT WRC laboratory furniture_2 | Ramo Trading & Consulting Inc. | 185.25 | 0.86364 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2403300A | 211.75 | F21P1 UPW | LB2 Train-A Anchor Tank Safety Supplies | Safety Solutions & Supply | 0 | 0 | Mechanical | Main Contract Scope | UPW | Base-Build | Site Expense
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2306075A | 210.6 | F21 TMAH System | WWT ICW-4” SUS flange | Ferguson Enterprises, LLC | 210.6 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2403025A | 207.14 | F21P1 Slurry package | Chem PVDF Fittings_20240229 | Harrington Industrial Plastics LLC | 207.14 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204015A | 206.33 | F21P1 UPW | Compact refrigerator for sub contractors trailer | Amazon.com, Inc. | 206.33 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2202008A | 206.33 | F21P1 UPW | Portable Monitor | Amazon.com, Inc. | 206.33 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2312067A | 204 | F21P1 UPW | UPW-Horiba adaptor | HORIBA Taiwan, Inc. | 204 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2403227A | 199.12 | F21P1 WWT package (Installation and 2 batch tanks) | S-11545 Draw ULINE - Cord Bags – 20X24X4 Clear 250/Per Carton | U-Line Corporation | 197.26 | 0.99066 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2309158A | 196.75 | F21P1 Chemical & WCCS package | MILWAUKEE Portable Shop Vacuum. | WW Grainger Inc | 196.75 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402023A | 195.83 | F21P1 Chemical & WCCS package | CDS cush clamp, screw | Southwest Fastener Division of NEFCO | 195.83 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111068A | 194.39 | F21P1 UPW | Drone for F21 Project. | Walmart Inc | 194.39 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2306111A | 193.99 | F21P1 UPW | UPW-PP-HP-Zewei | Ze-Wei Industrial Co., Ltd. | 193.99 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2210010A | 191.12 | F21P1 UPW | Black 3 drawer file cabinet | Amazon.com, Inc. | 191.12 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Base-Build | Others | Site Expense | USC23C059 | USCSB2401140A | 180.32 | F21P1 Foundation T&M | Laydown Material - Global Industrial | Global Equipment Company Inc. | 150.94 | 0.83707 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | Base-Build | MIMO/Rigging
Base-Build | Low Voltage | Mechanical | Material | USC21C007 | USCSB2308024A | 179.52 | F21P1 VOC package （Installation ) | 4” and 6” FNW gaskets | Ferguson Enterprises, LLC | 179.52 | 1 | Mechanical | CO Scope (adding/additional scope) | Low Voltage | VOC | Material
Base-Build | WWT | Others | Material | USC21C011 | USCSB2405053A | 177.55 | F21 TMAH System | 5191-8121 vials and 5191-8151 caps for LS_MS/MS TMAH room device | Agilent Technologies, Inc. | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | TMAH | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403241A | 176.9 | F21P1 Chemical & WCCS package | CDS CO2 system warning signs | Compliance Signs, LLC | 176.9 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111050A | 172.65 | F21P1 UPW | Webcam for meeting rooms | Amazon.com, Inc. | 172.65 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Electrical | Instrument | USC21C011 | USCSB2403057A | 170.64 | F21 TMAH System | WWT-Ammonia-High concentration standards solution | Winn Marion Barber, LLC | 170.64 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2312031A | 167.07 | F21P1 Chemical & WCCS package | CDS #36 Rosary cord twine for JuWei PFA line work requested by Jay Huang. | The Fish Net Company, LLC | 161.75 | 0.96816 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308020A | 154.99 | F21P1 Chemical & WCCS package | TGCM Duty Room items – Microwave | The Home Depot, Inc | 0 | 0 | Mechanical | CO Scope (adding/additional scope) | CDS | Chemical | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2402127A | 152.72 | F21P1 WWT package (Installation and 2 batch tanks) | Cabinet door in TM room | The Home Depot, Inc | 0 | 0 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2401098A | 150 | F21P1 UPW | UPW-GF-electrolyte solution | Ryan Herco Flow Solutions | 150 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402193A | 149.94 | F21P1 Chemical & WCCS package | CDS 1" 90 elbow | Arizona/Albuquerque Valve & Fitting Corp. | 149.94 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Commissioning | USC21C005 | USCSB2310191A | 147.64 | F21P1 Chemical & WCCS package | CDS Nippon Pillar Fittings for commission flushing | Nippon Pillar Corporation of America | 147.64 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402239A | 146.67 | F21P1 Chemical & WCCS package | CDS Ring Terminals | Consolidated Electrical Distributors Inc | 121.67 | 0.82955 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Electrical | Material | USC21C011 | USCSB2403251A | 144.77 | F21 TMAH System | Additional wiring material for Ammonia analyzer_WWT | WW Grainger Inc | 144.77 | 1 | Electrical | Main Contract Scope | WWT | WWT | Material
Base-Build | UPW | Electrical | Material | USC21C003 | USCSB2402258A | 144 | F21P1 UPW | Foxboro A1U Enclosure Sample | Black Label Services Inc. | 144 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403140A | 140 | F21P1 Chemical & WCCS package | CDS plastic clamp tube OD 1 | Pure Plastics, LLC | 140 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2211032A | 136 | F21P1 UPW | UPW Mark-up RO skids limit switch | Azbil North America, Inc. | 136 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2304008A | 136 | F21P1 WWT package (Installation and 2 batch tanks) | Gasket for WRC mini line | Duncan Bolt Co. | 136 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2405093A | 132.02 | Chemical & WCCS B Side Project | CHEM_ puch list for A side_John | Copper State Bolt & Nut Company | 132.02 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204008A | 130.56 | F21P1 UPW | X-Change Pro | Digital River, Inc. | 130.56 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402076A | 130 | F21P1 Chemical & WCCS package | CDS M6 x 1 x 16 (5/8) Screws | Harrington Industrial Plastics LLC | 130 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Others | Site Expense | USC21C009 | USCSB2403204A | 129.36 | F21P1 WWT package (Installation and 2 batch tanks) | WWT WRC laboratory furniture_3 | Mega Depot, LLC | 117.6 | 0.90909 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2311056A | 127.43 | F21P1 UPW | UPW-test kits | Hach Company | 0 | 0 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Electrical | Material | USC21C005 | USCSB2404009A | 125 | F21P1 Chemical & WCCS package | Request for Quote_Please Purchase a Breaker_CED_20240325 | Consolidated Electrical Distributors Inc | 125 | 1 | Electrical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2403018A | 120.34 | F21P1 WWT package (Installation and 2 batch tanks) | WWT Threaded Plug_20240229 (A Side) | Arizona/Albuquerque Valve & Fitting Corp. | 120.34 | 1 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Material | USC21C001 | USC2107008A | 119.93 | tsmc AZ Temporary Office Physical Security | Metal gate壓邊條及配件 | The Home Depot, Inc | 119.93 | 1 | Electrical | Main Contract Scope | Low Voltage | Speed Gate | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204007A | 119.45 | F21P1 UPW | Netgear Switch | Amazon.com, Inc. | 119.45 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2303034A | 119.2 | F21P1 WWT package (Installation and 2 batch tanks) | TEM LAB PP 90 Elbows Fittings | Harrington Industrial Plastics LLC | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | WWT | Mechanical | Material | USC21C009 | USCSB2312045A | 119.04 | F21P1 WWT package (Installation and 2 batch tanks) | WWT _7/8 washer extra | Copper State Bolt & Nut Company | 0 | 0 | Mechanical | Main Contract Scope | WWT | WWT | Material
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402213A | 111 | F21P1 Chemical & WCCS package | CDS SMC pressure gauges | Yih Jiun Enterprise Co., Ltd. | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Site Expense | USC21C009 | USCSB2401025A | 110.05 | F21P1 WWT package (Installation and 2 batch tanks) | WWT office supplies for PSS support doc. | Walmart Inc | 107.85 | 0.98001 | Mechanical | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403172A | 108.78 | F21P1 Chemical & WCCS package | CDS electrical tape and tool | Amazon.com, Inc. | 107.48 | 0.98805 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2111024A | 107.36 | F21P1 UPW | PDF-XChange Pro | Digital River, Inc. | 107.36 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | Software
Base-Build | WWT | Others | Site Expense | USC24C006 | USCSB2405154A | 105.86 | WWT B side Project | WWT WRC laboratory furniture_Sensor | Mega Depot, LLC | 105.28 | 0.99452 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204018A | 104.51 | F21P1 UPW | set of 4 hand soap | Amazon.com, Inc. | 104.51 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Low Voltage | Others | Site Expense | USC21C009 | USCSB2404084A | 104.16 | F21P1 WWT package (Installation and 2 batch tanks) | Zoro - Clean and equipment maintenance | Zoro Tools, Inc. dba Zoro | 94.69 | 0.90908 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | 0 | 0 | VOC | Labor
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2112032A | 93.15 | F21P1 UPW | Dell G15 Laptop | Best Buy Co., Inc. | 93.15 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402148A | 89.62 | F21P1 Chemical & WCCS package | CDS Sealing Compound Powder, Qty 2 | Walmart Inc | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204016A | 86.87 | F21P1 UPW | Multi purpose paper 11 x 17 | Amazon.com, Inc. | 86.87 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Others | Site Expense | USC24C006 | USCSB2408069A | 85.74 | WWT B side Project | WWT Tent 9 WMS Barcode Paper Label | Barcodes LLC | 85.74 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) |  |  | WWT
Base-Build | Chemical | Mechanical | Material | USC24C005 | USCSB2406022A | 85.43 | Chemical & WCCS B Side Project | 1-1/2 SS 304L 法蘭洗孔 | Ferguson Enterprises, LLC | 85.43 | 1 | Mechanical | Main Contract Scope | CDS | Chemical
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2308098A | 82.4 | F21P1 Chemical & WCCS package | Unions to Correct MIC Taiwan M4 cabinets | Arizona/Albuquerque Valve & Fitting Corp. | 82.4 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2209020A | 80 | F21P1 UPW | microwave 1.1 chrome and black hamilton beach | Walmart Inc | 80 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Others | Site Expense | USC21C011 | USCSB2404200B | 78.5 | F21 TMAH System | WWT-ammonia 1000 ppm standards solution for stripper | Thomas Scientific Holdings LLC | 58.5 | 0.74522 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Main Contract Scope | WWT | WWT | Material
Base-Build | Low Voltage | Electrical | Material | USC21C002 | USC2107005A | 78.17 | TSMC AZ Temp Office Speed Gate | Adopter and mount for speed gate | Staples Inc. | 78.17 | 1 | Electrical | Main Contract Scope | Low Voltage | Speed Gate | Equipment
Base-Build | WWT | Mechanical | Material | USC21C011 | USCSB2306119A | 76.67 | F21 TMAH System | WRC Ammonia nitrogen CO -2 | Ferguson Enterprises, LLC | 0 | 0 | Mechanical | Main Contract Scope | WWT | TMAH | Material
Base-Build | Chemical | Mechanical | Material | USC21C006 | USCSB2403046A | 75.18 | F21P1 Slurry package | Chem Gasket_20240305 | Harrington Industrial Plastics LLC | 75.18 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203027A | 74.91 | F21P1 UPW | Sarood Laptop stand in adjustable size | Amazon.com, Inc. | 74.91 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2309093A | 73.59 | F21P1 UPW | UPW-PVDF valve handle | Ryan Herco Flow Solutions | 73.59 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2303095A | 73.4 | F21P1 UPW | DG tower pressure gauge | Hwa Chi Technology Co., Ltd | 73.4 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2308134A | 72.25 | F21P1 Chemical & WCCS package | Unions For Chemical welding. | Arizona/Albuquerque Valve & Fitting Corp. | 72.25 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Mechanical | Material | USC21C003 | USCSB2401072A | 66.5 | F21P1 UPW | UPW-Harrington-Sight glass Orings | Harrington Industrial Plastics LLC | 66.5 | 1 | Mechanical | Main Contract Scope | UPW | UPW | Equipment
Base-Build | WWT | Electrical | Instrument | USC21C011 | USCSB2404063A | 65 | F21 TMAH System | Cast Iron Conduit box for TATUNG MOTOR WH0202FEJ SN14063611 in STRIPPER PAD | Tatung Company | 65 | 1 | Electrical | Main Contract Scope | WWT | TMAH | Equipment
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2204017A | 56.46 | F21P1 UPW | hand soap package of 4 | Amazon.com, Inc. | 56.46 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | WWT | Electrical | Material | USC21C011 | USCSB2402101A | 54.52 | F21 TMAH System | TMAH MS/HS receptacle | WW Grainger Inc | 54.52 | 1 | Electrical | Main Contract Scope | WWT | TMAH | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2205001A | 52.93 | F21P1 UPW | paper for copier | Amazon.com, Inc. | 52.93 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Instrument | USC21C005 | USCSB2308181A | 45.52 | F21P1 Chemical & WCCS package | Connectors for Chemical team to conduct pressure test. | Arizona/Albuquerque Valve & Fitting Corp. | 45.52 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Electrical | Material | USC21C007 | USCSB2309007A | 40 | F21P1 VOC package （Installation ) | VOC system signal wire termination | Graybar Electric Company, Inc. | 40 | 1 | Electrical | Main Contract Scope | Low Voltage | VOC | Material
Base-Build | Base-Build | Others | Site Expense | USC21C003 | USC2203003A | 37.99 | F21P1 UPW | Switch | Best Buy Co., Inc. | 37.99 | 1 | Others (commissioning, QAQC, Safety, Outsourcing, etc) | The budget execution does not pertain to this project | Shared Cost | Base-Build | MISC Expense
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401056A | 36.95 | F21P1 Chemical & WCCS package | WCCS Cutter | The Home Depot, Inc | 36.95 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | UPW | Electrical | Commissioning | USC21C003 | USCSB2311083A | 31 | F21P1 UPW | UPW_Sulfuric Acid 96% | Thomas Scientific Holdings LLC | 31 | 1 | Electrical | Main Contract Scope | UPW | UPW | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2403191A | 29.69 | F21P1 Chemical & WCCS package | CDS Punch list SS screws | The Home Depot, Inc | 0 | 0 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402045A | 27.24 | F21P1 Chemical & WCCS package | CDS 1/2 GROUNDING PIGTAIL | Consolidated Electrical Distributors Inc | 27.24 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | WWT | Mechanical | Material | USC24C006 | USCSB2409085A | 25.63 | WWT B side Project | WWT shortage of hardware materials on the B side sump pump at TIMA | Copper State Bolt & Nut Company | 0 | 0 | Mechanical |  |  | WWT
Base-Build | Low Voltage | Electrical | Material | USC21C002 | USC2107006A | 20.97 | TSMC AZ Temp Office Speed Gate | Adaptor for speed gate and bults for mounting | The Home Depot, Inc | 20.97 | 1 | Electrical | Main Contract Scope | Low Voltage | Speed Gate | Equipment
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2402215A | 17.82 | F21P1 Chemical & WCCS package | CDS 5/8 Hex nut, EG | Southwest Fastener Division of NEFCO | 17.82 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material
Base-Build | Low Voltage | Electrical | Material | USC21C001 | USC2107007A | 16.22 | tsmc AZ Temporary Office Physical Security | Furniture D (Metal gate壓邊條及配件) | Walmart Inc | 16.22 | 1 | Electrical | Main Contract Scope | Low Voltage | Speed Gate | Material
Base-Build | Chemical | Mechanical | Material | USC21C005 | USCSB2401055A | 11.22 | F21P1 Chemical & WCCS package | WCCS weld tube cap 2" | SEMITORR GROUP, LLC | 11.22 | 1 | Mechanical | Main Contract Scope | CDS | Chemical | Material

## pc_overview AR
Type | Project # | Project Name | PO # | Total Contract $ | Main Page | CO/Added | Amy PO
Mechanical | USC21C003 | F21P1 Tunnel/lorry common support | 4590006744 | 5795851 | WWT | Added
GC | USC21C003 | F21P1 Tunnel/lorry common support | 4590006744 | 240481.244 | WWT | Added
Management | USC21C003 | F21P1 Tunnel/lorry common support | 4590006744 | 463668.056 | WWT | Added
Mechanical | USC21C003 | F21P1 UPW Temporary CP and piping | 4590009036 | 108600 | UPW | Added
GC | USC21C003 | F21P1 UPW Temporary CP and piping | 4590009036 | 6515 | UPW | Added
Management | USC21C003 | F21P1 UPW Temporary CP and piping | 4590009036 | 10860 | UPW | Added
Scope | USC21C003 | F21P1 QR Lab UPW | 4590004028 | 668561 | UPW
GC | USC21C003 | F21P1 QR Lab UPW | 4590004028 | 40114 | UPW
Management | USC21C003 | F21P1 QR Lab UPW | 4590004028 | 53484.9281 | UPW
Mechanical | USC21C003 | F21P1 UPW Temporary Resin and piping | 4590010557 | 144432 | UPW | Added
GC | USC21C003 | F21P1 UPW Temporary Resin and piping | 4590010557 | 7222 | UPW | Added
Management | USC21C003 | F21P1 UPW Temporary Resin and piping | 4590010557 | 14346 | UPW | Added
Others | USC21C003 | F21P1 CUP L20 Transformer Pads | 4590011254 | 135514.66 | UPW | Added
GC | USC21C003 | F21P1 CUP L20 Transformer Pads | 4590011254 | 0 | UPW | Added
Management | USC21C003 | F21P1 CUP L20 Transformer Pads | 4590011254 | 9485.34 | UPW | Added
Electrical | USC21C003 | F21P1 UPW temp power and MAU DI solution | 4590012982 | 540198.34 | UPW | Added
GC | USC21C003 | F21P1 UPW temp power and MAU DI solution | 4590012982 | 7448.66 | UPW | Added
Management | USC21C003 | F21P1 UPW temp power and MAU DI solution | 4590012982 | 71195 | UPW | Added
Steel Work | USC21C003 | F21P1 UPW Tank Swing Gate | 4590013482 | 70400 | UPW | Added
GC | USC21C003 | F21P1 UPW Tank Swing Gate | 4590013482 | 3520 | UPW | Added
Management | USC21C003 | F21P1 UPW Tank Swing Gate | 4590013482 | 9152 | UPW | Added
Electrical | USC21C003 | F21P1 UPW & WWT Battery Charge | 4590013633 | 228000 | UPW | Added
GC | USC21C003 | F21P1 UPW & WWT Battery Charge | 4590013633 | 2280 | UPW | Added
Management | USC21C003 | F21P1 UPW & WWT Battery Charge | 4590013633 | 34542 | UPW | Added
Electrical | USC21C005 | F21P1 CR temp lighting | 4590012687 | 70264 | Chemical | Added
GC | USC21C005 | F21P1 CR temp lighting | 4590012687 | 3513.2 | Chemical | Added
Management | USC21C005 | F21P1 CR temp lighting | 4590012687 | 11066.58 | Chemical | Added
Mechanical | USC21C005 | F21P1 Chemical Solvent day tank add vent | 4590012855 | 425434.49 | Chemical | Added
GC | USC21C005 | F21P1 Chemical Solvent day tank add vent | 4590012855 | 22591.7 | Chemical | Added
Management | USC21C005 | F21P1 Chemical Solvent day tank add vent | 4590012855 | 41973.81 | Chemical | Added
Steel Work | USC21C005 | F21P1 Lorry area fall protection tie off | 4590013430 | 272948.58 | Chemical | Added
GC | USC21C005 | F21P1 Lorry area fall protection tie off | 4590013430 | 13647.43 | Chemical | Added
Management | USC21C005 | F21P1 Lorry area fall protection tie off | 4590013430 | 40942.29 | Chemical | Added
Steel Work | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 4590013480 | 20559.01 | Chemical | Added
GC | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 4590013480 | 1027.95 | Chemical | Added
Management | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 4590013480 | 3083.85 | Chemical | Added
Steel Work | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 4590013481 | 29700 | Chemical | Added
GC | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 4590013481 | 1485 | Chemical | Added
Management | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 4590013481 | 4455 | Chemical | Added
Others | USC21C005 | F21P1 Lorry RU Chemical Filtration Impro | 4590013675 | 108900 | Chemical | Added
Management | USC21C005 | F21P1 Lorry RU Chemical Filtration Impro | 4590013675 | 16335 | Chemical | Added
Mechanical | USC21C009 | F21P1 CCB Lorry in drain system | 4590006293 | 594063.11 | WWT | Added
GC | USC21C009 | F21P1 CCB Lorry in drain system | 4590006293 | 63551.47 | WWT | Added
Scope | USC21C003 | F21P1 UPW A5 Backup Line Modification | 4590016257 | 62844.17 | UPW |  | x
GC | USC21C003 | F21P1 UPW A5 Backup Line Modification | 4590016257 | 3770 | UPW |  | x
Management | USC21C003 | F21P1 UPW A5 Backup Line Modification | 4590016257 | 9992 | UPW |  | x
Scope | USC21C003 | F21P1 EBO UPW package | 4590004026_100 | 329079.4071 | UPW |  | x
GC | USC21C003 | F21P1 EBO UPW package | 4590004026_100 | 19745 | UPW |  | x
Management | USC21C003 | F21P1 EBO UPW package | 4590004026_100 | 26326.3686 | UPW |  | x
Scope | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 4590004027_100 | 277627.18 | UPW |  | x
GC | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 4590004027_100 | 16657.63 | UPW |  | x
Management | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 4590004027_100 | 22210.1743 | UPW |  | x
Scope | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 4590004557_001 | 300853 | UPW |  | x
GC | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 4590004557_001 | 18051 | UPW |  | x
Management | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 4590004557_001 | 24068.34 | UPW |  | x
Management | USC21C009 | F21P1 CCB Lorry in drain system | 4590006293 | 49631.289 | WWT | Added
Mechanical | USC21C009 | F21P1 Formaldehyde treatment system | 4590006720 | 625199.16 | WWT | Added
GC | USC21C009 | F21P1 Formaldehyde treatment system | 4590006720 | 26000 | WWT | Added
Management | USC21C009 | F21P1 Formaldehyde treatment system | 4590006720 | 48800.84 | WWT | Added
Electrical | USC21C009 | F21P1 WWT construction temp power | 4590012872 | 363852 | WWT | Added
Management | USC21C009 | F21P1 WWT construction temp power | 4590012872 | 44148 | WWT | Added
Steel Work | USC21C009 | F21P1 230KV MTR NGR stand | 4590013495 | 78042 | WWT | Added
GC | USC21C009 | F21P1 230KV MTR NGR stand | 4590013495 | 9365.04 | WWT | Added
Management | USC21C009 | F21P1 230KV MTR NGR stand | 4590013495 | 11706.3 | WWT | Added
Steel Work | USC21C009 | F21P1 WWT Tank Swing Gate | 4590013571 | 119350 | WWT | Added
GC | USC21C009 | F21P1 WWT Tank Swing Gate | 4590013571 | 5968 | WWT | Added
Management | USC21C009 | F21P1 WWT Tank Swing Gate | 4590013571 | 15516 | WWT | Added
Electrical | USC21C009 | F21P1 WWT Electrical Testing Support | 4590013603 | 163735 | WWT | Added
Management | USC21C009 | F21P1 WWT Electrical Testing Support | 4590013603 | 18892.5 | WWT | Added
Steel Work | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 4590013803 | 1502984.58 | WWT | Added
GC | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 4590013803 | 102653.85 | WWT | Added
Management | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 4590013803 | 128451.07 | WWT | Added
Electrical | USC21C013 | F21P1 EBO AMC Monitor system | 4590006871 | 918126 | Low Voltage | Added
GC | USC21C013 | F21P1 EBO AMC Monitor system | 4590006871 | 23000 | Low Voltage | Added
Electrical | USC21C013 | F21P1 AMC package-IMS wipe test | 4590013433 | 7680 | Low Voltage | Added
Management | USC21C013 | F21P1 AMC package-IMS wipe test | 4590013433 | 1152 | Low Voltage | Added
Electrical | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 4590013669 | 38004 | Low Voltage | Added
GC | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 4590013669 | 2280.24 | Low Voltage | Added
Management | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 4590013669 | 6042.64 | Low Voltage | Added
Mechanical | USC22C009 | F21P1 MTR oil & drain pipe work | 4590000624 | 358335 | WWT | Added
GC | USC22C009 | F21P1 MTR oil & drain pipe work | 4590000624 | 21361 | WWT | Added
Management | USC22C009 | F21P1 MTR oil & drain pipe work | 4590000624 | 28304 | WWT | Added
Electrical | USC22C010 | F21P1 LV PDS on site installation | 4590000334 | 165168 | Low Voltage | Added
GC | USC22C010 | F21P1 LV PDS on site installation | 4590000334 | 9910.08 | Low Voltage | Added
Management | USC22C010 | F21P1 LV PDS on site installation | 4590000334 | 13213.44 | Low Voltage | Added
Electrical | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 4590002291 | 57083.38 | Low Voltage | Added
GC | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 4590002291 | 548.52 | Low Voltage | Added
Management | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 4590002291 | 6907.53 | Low Voltage | Added
Others | USC22C021 | F21P1 Chemical Lab setup | 4590004281 | 414401.66 | Chemical | Added
GC | USC22C021 | F21P1 Chemical Lab setup | 4590004281 | 54616.55 | Chemical | Added
Management | USC22C021 | F21P1 Chemical Lab setup | 4590004281 | 35397.6012 | Chemical | Added
Mechanical | USC22C021 | F21P1 Chemical Lab Hookup | 4590008170 | 393600 | Chemical | Added
GC | USC22C021 | F21P1 Chemical Lab Hookup | 4590008170 | 76451 | Chemical | Added
Management | USC22C021 | F21P1 Chemical Lab Hookup | 4590008170 | 37599 | Chemical | Added
Mechanical | USC22C023 | F21P1 Piping Material Collaboration | 4590008240 | 2811729.15 | UPW | Added
Management | USC22C023 | F21P1 Piping Material Collaboration | 4590008240 | 231172.915 | UPW | Added
Steel Work | USC22C031 | F21P1 High-speed rolling door frame | 4590013431 | 22779.71 | WWT | Added
GC | USC22C031 | F21P1 High-speed rolling door frame | 4590013431 | 1139 | WWT | Added
Management | USC22C031 | F21P1 High-speed rolling door frame | 4590013431 | 3109 | WWT | Added
Mechanical | USC23C012 | F21P1 Hot DI Machine Hookup | 4590008229_001 | 196587 | Chemical | Added
GC | USC23C012 | F21P1 Hot DI Machine Hookup | 4590008229_001 | 38608 | Chemical | Added
Management | USC23C012 | F21P1 Hot DI Machine Hookup | 4590008229_001 | 4805 | Chemical | Added
Steel Work | USC23C042 | F21P1 Chemical safety cabinet installation | 4590004117 | 42873 | Chemical | Added
GC | USC23C042 | F21P1 Chemical safety cabinet installation | 4590004117 | 2572 | Chemical | Added
Management | USC23C042 | F21P1 Chemical safety cabinet installation | 4590004117 | 3429.824 | Chemical | Added
Electrical | USC23C043 | Electric Tiger Team_Fisk Support & Temp Power | 4590012300 | 376459 | WWT | Added
Management | USC23C043 | Electric Tiger Team_Fisk Support & Temp Power | 4590012300 | 48939.67 | WWT | Added
Electrical | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 4590012310 | 117700 | WWT | Added
GC | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 4590012310 | 5885 | WWT | Added
Management | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 4590012310 | 11770 | WWT | Added
Electrical | USC24C006 | F21P1 Cast Resin PD Sensor Install/Test | 4590013944 | 58000 | UPW | Added
Management | USC24C006 | F21P1 Cast Resin PD Sensor Install/Test | 4590013944 | 11600 | UPW | Added
Others | USC23C056 | F21P1 WWT FAB LB2 Trench Cleanning | 4590014676 | 104312 | WWT | Added
Management | USC23C056 | F21P1 WWT FAB LB2 Trench Cleanning | 4590014676 | 36816 | WWT | Added
Steel Work | USC21C003 | F21P1 WRC L20 RACK Modification | 4590013928 | 15984 | WWT | CO
GC | USC21C003 | F21P1 WRC L20 RACK Modification | 4590013928 | 959 | WWT | CO
Management | USC21C003 | F21P1 WRC L20 RACK Modification | 4590013928 | 2541 | WWT | CO
Electrical | USC21C003 | F21P1 UPW Control Panel Temp Cable | 4590014674 | 699981.89 | UPW | CO
Scope | USC21C009 | F21P1 QR Lab WWT | 4590004029 | 2531199.59 | WWT |  | x
GC | USC21C009 | F21P1 QR Lab WWT | 4590004029 | 283786.83 | WWT |  | x
Management | USC21C009 | F21P1 QR Lab WWT | 4590004029 | 212453.35 | WWT |  | x
GC | USC21C003 | F21P1 UPW Control Panel Temp Cable | 4590014674 | 34999.0945 | UPW | CO
Management | USC21C003 | F21P1 UPW Control Panel Temp Cable | 4590014674 | 95547.528 | UPW | CO
Mechanical | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 4590014675 | 177120.35 | UPW | CO
GC | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 4590014675 | 10627 | UPW | CO
Management | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 4590014675 | 28162 | UPW | CO
Mechanical | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 83646 | Chemical | CO
Electrical | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 38568 | Chemical | CO
GC | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 5597.28 | Chemical | CO
Management | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 19171.69 | Chemical | CO
Management | USC21C007 | F21P1 VOC Burner NOx improve-installatio | 4590011320 | 88238.83 | Low Voltage | CO
Mechanical | USC21C007 | F21P1 VOC Burner NOx improve-installatio | 4590011320 | 678760.27 | Low Voltage | CO
GC | USC21C009 | F21P1 Discharge monitoring change | 4590004971 | 36436 | WWT | CO
Management | USC21C009 | F21P1 Discharge monitoring change | 4590004971 | 57090 | WWT | CO
Electrical | USC21C009 | F21P1 Discharge monitoring change | 4590004971 | 532474 | WWT | CO
Steel Work | USC21C009 | F21P1 WWT cable tray relo & add support | 4590013804 | 2078912.7 | WWT | CO
GC | USC21C009 | F21P1 WWT cable tray relo & add support | 4590013804 | 141990 | WWT | CO
Management | USC21C009 | F21P1 WWT cable tray relo & add support | 4590013804 | 177672 | WWT | CO
Steel Work | USC21C009 | F21P1 WWT LB2 Support Modification | 4590014187 | 16376 | WWT | CO
GC | USC21C009 | F21P1 WWT LB2 Support Modification | 4590014187 | 819 | WWT | CO
Management | USC21C009 | F21P1 WWT LB2 Support Modification | 4590014187 | 2580 | WWT | CO
Mechanical | USC21C009 | F21P1 WWT Per Diem and Acceleration | 4590014401 | 6264381 | WWT | CO
Mechanical | USC21C009 | F21P1 WWT AWR Drain to LSR System | 4590014629 | 51797.04 | WWT | CO
GC | USC21C009 | F21P1 WWT AWR Drain to LSR System | 4590014629 | 3107.82 | WWT | CO
Management | USC21C009 | F21P1 WWT AWR Drain to LSR System | 4590014629 | 8235.73 | WWT | CO
Electrical | USC21C009 | F21P1 WWT Panel Butten Change | 4590014630 | 86528 | WWT | CO
GC | USC21C009 | F21P1 WWT Panel Butten Change | 4590014630 | 865.28 | WWT | CO
Management | USC21C009 | F21P1 WWT Panel Butten Change | 4590014630 | 13108.99 | WWT | CO
Mechanical | USC21C009 | F21P1 WWT Per Diem and Acceleration | 4590015058 | 4142540.4 | WWT | CO
Electrical | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 4590015143 | 493675 | WWT | CO
GC | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 4590015143 | 29621 | WWT | CO
Management | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 4590015143 | 78494 | WWT | CO
Mechanical | USC23C045 | F21P1 UPW Design Change (UMEC) | 4590013572 | 388723 | UPW | CO
GC | USC23C045 | F21P1 UPW Design Change (UMEC) | 4590013572 | 3887.23 | UPW | CO
Management | USC23C045 | F21P1 UPW Design Change (UMEC) | 4590013572 | 58891.5345 | UPW | CO
GC | USC23C054 | F21P1 WCCS Extend GC and Labor Incentive | 4590013806 | 661674 | Base-Build | CO
GC | USC23C054 | F21P1 Slurry Extend GC & Labor Incentive | 4590013807 | 1313687.25 | Base-Build | CO
GC | USC23C054 | F21P1 VOC Extend GC & Labor Incentive | 4590013808 | 104910 | Base-Build | CO
GC | USC23C054 | F21P1 CDS Extend GC & Labor Incentive | 4590013809 | 7083604.02 | Base-Build | CO
GC | USC23C054 | F21P1 UPW Extend GC & Labor Incentive | 4590013810 | 5008794.91 | Base-Build | CO
Scope | USC21C009 | F21P1 EBO WWT package | 4590004026_200 | 891848.65 | WWT |  | x
GC | USC21C009 | F21P1 EBO WWT package | 4590004026_200 | 53510.92 | WWT |  | x
Management | USC21C009 | F21P1 EBO WWT package | 4590004026_200 | 71347.8922 | WWT |  | x
Scope | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 4590004027_200 | 359598 | WWT |  | x
GC | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 4590004027_200 | 53861 | WWT |  | x
Management | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 4590004027_200 | 32819 | WWT |  | x
GC | USC23C054 | F21P1 WWT Extend GC & Labor Incentive | 4590013811 | 577980.02 | Base-Build | CO
Mechanical | USC21C003 | F21P1 UPW | 4503290109 | 87980103 | UPW | Main
Electrical | USC21C003 | F21P1 UPW | 4503290109 | 20327458 | UPW | Main
Steel Work | USC21C003 | F21P1 UPW | 4503290109 | 28037246 | UPW | Main
Others | USC21C003 | F21P1 UPW | 4503290109 | 295650 | UPW | Main
GC | USC21C003 | F21P1 UPW | 4503290109 | 7618520 | UPW | Main
Management | USC21C003 | F21P1 UPW | 4503290109 | 12041023 | UPW | Main
Mechanical | USC21C004 | F21P1 WWT package (USA EQ - FRP tank) | 4503312319 | 6158273 | WWT | Main
Management | USC21C005 | F21P1 CDS package (B.10) | 4590009808 | 56024.4 | Chemical | Main
GC | USC21C005 | F21P1 CDS package (B.10) | 4590009808 | 109737.6 | Chemical | Main
Mechanical | USC21C005 | F21P1 CDS package (B.10) | 4590009808 | 1104238 | Chemical | Main
Mechanical | USC21C005 | F21P1 Chemical package | 4503446631_100 | 116849536.85 | Chemical | Main
Electrical | USC21C005 | F21P1 Chemical package | 4503446631_100 | 19303769.72 | Chemical | Main
Steel Work | USC21C005 | F21P1 Chemical package | 4503446631_100 | 11603571.43 | Chemical | Main
Others | USC21C005 | F21P1 Chemical package | 4503446631_100 | 2190000 | Chemical | Main
Management | USC21C005 | F21P1 Chemical package | 4503446631_100 | 10704880 | Chemical | Main
GC | USC21C005 | F21P1 Chemical package | 4503446631_100 | 840165 | Chemical | Main
Mechanical | USC21C005 | F21P1 WCCS package | 4503446631_200 | 28148814.3 | Chemical | Main
Electrical | USC21C005 | F21P1 WCCS package | 4503446631_200 | 493566.7 | Chemical | Main
Steel Work | USC21C005 | F21P1 WCCS package | 4503446631_200 | 500000 | Chemical | Main
Others | USC21C005 | F21P1 WCCS package | 4503446631_200 | 0 | Chemical | Main
GC | USC21C005 | F21P1 WCCS package | 4503446631_200 | 143197 | Chemical | Main
Management | USC21C005 | F21P1 WCCS package | 4503446631_200 | 4552754 | Chemical | Main
GC | USC21C005 | F21P1 TGCM Room | 4590008229_002 | 2311 | Chemical | Main
Management | USC21C005 | F21P1 TGCM Room | 4590008229_002 | 1476 | Chemical | Main
Others | USC21C005 | F21P1 TGCM Room | 4590008229_002 | 46213 | Chemical | Main
Mechanical | USC21C006 | F21P1 Slurry package | 4503428513 | 24635187 | Chemical | Main
Electrical | USC21C006 | F21P1 Slurry package | 4503428513 | 2723181 | Chemical | Main
Steel Work | USC21C006 | F21P1 Slurry package | 4503428513 | 740642 | Chemical | Main
Others | USC21C006 | F21P1 Slurry package | 4503428513 | 7219990 | Chemical | Main
GC | USC21C006 | F21P1 Slurry package | 4503428513 | 193000 | Chemical | Main
Management | USC21C006 | F21P1 Slurry package | 4503428513 | 3088000 | Chemical | Main
Management | USC21C006 | F21P1 Slurry Package support frame | 4590003895 | 87144 | Chemical | Main
Steel Work | USC21C006 | F21P1 Slurry Package support frame | 4590003895 | 580960 | Chemical | Main
Mechanical | USC21C006 | F21P1 SDS installation (B.10) | 4590009963 | 1829620 | Chemical | Main
GC | USC21C006 | F21P1 SDS installation (B.10) | 4590009963 | 9149 | Chemical | Main
Management | USC21C006 | F21P1 SDS installation (B.10) | 4590009963 | 110327 | Chemical | Main
Mechanical | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 8678203.9 | Low Voltage | Main
Electrical | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 4038484.1 | Low Voltage | Main
Others | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 3043495 | Low Voltage | Main
Management | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 2077130.37 | Low Voltage | Main
GC | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 844686.11 | Low Voltage | Main
Management | USC21C008 | F21 CCTV & Security | 4503441102 | 1741245 | Low Voltage | Main
GC | USC21C008 | F21 CCTV & Security | 4503441102 | 110638 | Low Voltage | Main
Electrical | USC21C008 | F21 CCTV & Security | 4503441102 | 10828117 | Low Voltage | Main
Management | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 11397325 | WWT | Main
Mechanical | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 79852928 | WWT | Main
Electrical | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 15724572.5 | WWT | Main
Steel Work | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 28940662.8 | WWT | Main
Others | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 3740308 | WWT | Main
GC | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 8766883.7 | WWT | Main
Steel Work | USC21C010 | Water pipeline installation (size>4") | 4503398624 | 5723522 | Water_Sewer | Main
Steel Work | USC21C010 | Water pipeline installation (size<4") | 4503423409 | 776478 | Water_Sewer | Main
Mechanical | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 4503432152 | 6753583.34 | WWT | Main
GC | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 4503432152 | 36367.35 | WWT | Main
Management | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 4503432152 | 519886.3134 | WWT | Main
Mechanical | USC21C011 | TMAH ACF system expansion | 4590008082 | 4146068 | WWT | Main
GC | USC21C011 | TMAH ACF system expansion | 4590008082 | 242858 | WWT | Main
Management | USC21C011 | TMAH ACF system expansion | 4590008082 | 382003.8 | WWT | Main
Electrical | USC21C012 | F21P1 Barcode & RFID for manufacturing | 4503441308 | 4819590 | Low Voltage | Main
GC | USC21C012 | F21P1 Barcode & RFID for manufacturing | 4503441308 | 249941 | Low Voltage | Main
Management | USC21C012 | F21P1 Barcode & RFID for manufacturing | 4503441308 | 722760 | Low Voltage | Main
Electrical | USC21C013 | F21P1 AMC | 4503448339_100 | 3401994 | Low Voltage | Main
Others | USC21C013 | F21P1 AMC | 4503448339_100 | 927549 | Low Voltage | Main
GC | USC21C013 | F21P1 AMC | 4503448339_100 | 66000 | Low Voltage | Main
Management | USC21C013 | F21P1 AMC | 4503448339_100 | 610000 | Low Voltage | Main
Mechanical | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 1205462 | Low Voltage | Main
Electrical | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 1118008 | Low Voltage | Main
Others | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 101456 | Low Voltage | Main
GC | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 11250 | Low Voltage | Main
Management | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 258280.2 | Low Voltage | Main
Mechanical | USC21C014 | F21P1 W-H2SO4 package | 4503489979 | 2568895 | WWT | Main
GC | USC21C014 | F21P1 W-H2SO4 package | 4503489979 | 388920 | WWT | Main
Management | USC21C014 | F21P1 W-H2SO4 package | 4503489979 | 312779 | WWT | Main
Others | USC22C018 | US Fab Frontage line hydrants | 4590005093 | 1087000 | Water_Sewer | Main
GC | USC22C018 | US Fab Frontage line hydrants | 4590005093 | 54040 | Water_Sewer | Main
Management | USC22C018 | US Fab Frontage line hydrants | 4590005093 | 86960 | Water_Sewer | Main
Mechanical | USC22C020 | F21P1 Penetration Pipe | 4590005240 | 917975 | UPW | Main
GC | USC22C020 | F21P1 Penetration Pipe | 4590005240 | 40227 | UPW | Main
Management | USC22C020 | F21P1 Penetration Pipe | 4590005240 | 91798 | UPW | Main
Mechanical | USC22C022 | F21P1 Triazole treatment system | 4590006189 | 3859622 | WWT | Main
GC | USC22C022 | F21P1 Triazole treatment system | 4590006189 | 103063 | WWT | Main
Management | USC22C022 | F21P1 Triazole treatment system | 4590006189 | 377315 | WWT | Main
Others | USC23C014 | F21P1 Labor incentive program-MICU | 4590008319 | 1625000 | UPW | Main
Steel Work | USC21C003 | F21P1 UPW WRC L10 Add Supports | 4590016147 | 10449.2 | UPW | CO
Management | USC21C003 | F21P1 UPW WRC L10 Add Supports | 4590016147 | 1567.38 | UPW | CO
Mechanical | USC24C014 | F21P1 CDS Pressure Test Appeal for PFC | 4590019011 | 30000 | Chemical | CO
Management | USC24C014 | F21P1 CDS Pressure Test Appeal for PFC | 4590019011 | 4500 | Chemical | CO
Mechanical | USC24C006 | F21P1 CDS & WCCS CO2 Suppression System | 4590019083 | 732426.9565 | Chemical | CO
Management | USC24C006 | F21P1 CDS & WCCS CO2 Suppression System | 4590019083 | 109864.0435 | Chemical | CO
Mechanical |  | F21P1 CDS Labor Incentive Nov 2023 | 4590019372 | 36000 | Chemical | CO
Mechanical | USC24C006 | F21P1 WWT Labor Incentive Nov 2023 | 4590019487 | 60000 | WWT | CO
Mechanical | USC23C045 | F21P1 UPW Labor Incentive Nov 2023 | 4590019488 | 15000 | UPW | CO
Electrical | USC24C006 | F21P1 UPW Fiber Repull from Damage | 4590019489 | 136610.7043 | UPW | CO
Management | USC24C006 | F21P1 UPW Fiber Repull from Damage | 4590019489 | 20491.6057 | UPW | CO
Electrical | USC24C006 | F21P1 Add Card Reader at Material Gate | 4590019490 | 17654 | Low Voltage | CO
Management | USC24C006 | F21P1 Add Card Reader at Material Gate | 4590019490 | 2634 | Low Voltage | CO
Civil | USC24C006 | F21P1 WWT Doors &Triazole HK Pad Mod | 4590019491 | 12093.913 | WWT | CO
Management | USC24C006 | F21P1 WWT Doors &Triazole HK Pad Mod | 4590019491 | 1814.087 | WWT | CO
Mechanical | USC24C006 | F21P1 WWT Temp Chem. Leak Diverter Tarp | 4590019492 | 66780 | WWT | CO
Management | USC24C006 | F21P1 WWT Temp Chem. Leak Diverter Tarp | 4590019492 | 10017 | WWT | CO
Electrical | USC24C006 | F21P1 Speed Gate at Tent and CR Entrance | 4590019493 | 596110.44 | Low Voltage | CO
Management | USC24C006 | F21P1 Speed Gate at Tent and CR Entrance | 4590019493 | 88877 | Low Voltage | CO
Civil |  | F21P1 Hallway Plate Install | 4590019495 | 220500 | WWT | CO
Management |  | F21P1 Hallway Plate Install | 4590019495 | 33075 | WWT | CO
Mechanical | USC24C006 | F21P1 UPW ABG-A Submain Modification | 4590019922 | 67395.7913 | UPW | CO
Management | USC24C006 | F21P1 UPW ABG-A Submain Modification | 4590019922 | 10109.3687 | UPW | CO
Mechanical | USC24C006 | F21P1 UPW WRC NFPA Sign Installation | 4590019923 | 8055.9913 | UPW | CO
Management | USC24C006 | F21P1 UPW WRC NFPA Sign Installation | 4590019923 | 1208.3987 | UPW | CO
Electrical | USC24C006 | F21P1 Seismic Monitor | 4590019924 | 217165.2261 | Low Voltage | CO
Management | USC24C006 | F21P1 Seismic Monitor | 4590019924 | 32574.7839 | Low Voltage | CO
Electrical | USC24C006 | F21P1 UPW Cable Tray Reroute per Code | 4590019925 | 382152.513 | UPW | CO
Management | USC24C006 | F21P1 UPW Cable Tray Reroute per Code | 4590019925 | 57322.877 | UPW | CO
Mechanical | USC24C006 | F21P1 UPW Piping Damaged by Others | 4590019926 | 14504.7217 | UPW | CO
Management | USC24C006 | F21P1 UPW Piping Damaged by Others | 4590019926 | 2175.7083 | UPW | CO
Mechanical | USC24C006 | F21P1 UPW B Side MAU DI Temp Solution | 4590019927 | 104585.713 | UPW | CO
Management | USC24C006 | F21P1 UPW B Side MAU DI Temp Solution | 4590019927 | 15687.857 | UPW | CO
Civil | USC24C006 | F21P1 UPW WRC L20 Trench Modification | 4590019928 | 2914.7826 | UPW | CO
Management | USC24C006 | F21P1 UPW WRC L20 Trench Modification | 4590019928 | 437.2174 | UPW | CO
Mechanical | USC24C006 | F21P1 UPW Temp UPW Supply for ICPMS | 4590019929 | 143456.4783 | UPW | CO
Management | USC24C006 | F21P1 UPW Temp UPW Supply for ICPMS | 4590019929 | 21518.4717 | UPW | CO
Electrical | USC23C045 | F21P1 VOC MC Cable | 4590019947 | 453824.687 | Low Voltage | CO
Management | USC23C045 | F21P1 VOC MC Cable | 4590019947 | 68073.703 | Low Voltage | CO
Scope | USC23C045 | F21P1 MICU Settlement 1st_UPW | 4590020154 | 15117265.415 | UPW | CO
Management | USC23C045 | F21P1 MICU Settlement 1st_UPW | 4590020154 | 2189385.135 | UPW | CO
Mechanical | USC24C006 | F21P1 UPW Distribution Repair | 4590020155 | 82079.5565 | UPW | CO
Management | USC24C006 | F21P1 UPW Distribution Repair | 4590020155 | 12311.9335 | UPW | CO
Scope | USC23C045 | F21P1 MICU Settlement 1st_WWT | 4590020156 | 30215374.53 | WWT | CO
Management | USC23C045 | F21P1 MICU Settlement 1st_WWT | 4590020156 | 2116405.63 | WWT | CO
Scope | USC23C045 | F21P1 MICU Settlement 1st_CDS | 4590020157 | 12426921.31 | Chemical | CO
Management | USC23C045 | F21P1 MICU Settlement 1st_CDS | 4590020157 | 2262364.64 | Chemical | CO
Scope | USC23C045 | F21P1 MICU Settlement 1st_WCCS | 4590020158 | 2857297.975 | Chemical | CO
Management | USC23C045 | F21P1 MICU Settlement 1st_WCCS | 4590020158 | 437877.025 | Chemical | CO
Scope | USC23C045 | F21P1 MICU Settlement 1st_VOC | 4590020159 | 1805214.78 | Low Voltage | CO
Management | USC23C045 | F21P1 MICU Settlement 1st_VOC | 4590020159 | 291918.02 | Low Voltage | CO
Mechanical | USC24C006 | F21P1 UPW P1B Submain Expansion | 4590020160 | 134178.8261 | UPW | CO
Management | USC24C006 | F21P1 UPW P1B Submain Expansion | 4590020160 | 20126.8239 | UPW | CO
Mechanical | USC23C045 | F21P1 WWT AWN Enzyme Dosing Improvement | 4590020228 | 285836.5217 | WWT | CO
Management | USC23C045 | F21P1 WWT AWN Enzyme Dosing Improvement | 4590020228 | 42875.4783 | WWT | CO
Electrical | USC23C045 | F21P1 Security & CCTV DCR | 4590020230 | 237450.4348 | Low Voltage | CO
Management | USC23C045 | F21P1 Security & CCTV DCR | 4590020230 | 35617.5652 | Low Voltage | CO
Civil | USC24C006 | F21P1 UPW Mezzanine Modification | 4590020235 | 1311078.2609 | UPW | CO
Management | USC24C006 | F21P1 UPW Mezzanine Modification | 4590020235 | 196661.7391 | UPW | CO
Mechanical | USC24C006 | F21P1 WWT CWR System Improvement | 4590020236 | 579022.4783 | WWT | CO
Management | USC24C006 | F21P1 WWT CWR System Improvement | 4590020236 | 86853.3717 | WWT | CO
| USC24C006 | F21P1 MICU Settlement 2nd_UPW | 4590020302 | 7249177.3 | UPW | CO
| USC24C006 | F21P1 MICU Settlement 2nd_WWT | 4590020303 | 7007538.06 | WWT | CO
| USC24C006 | F21P1 MICU Settlement 2nd_CDS | 4590020304 | 7490816.54 | Chemical | CO
| USC24C006 | F21P1 MICU Settlement 2nd_WCCS | 4590020305 | 1449835.46 | Chemical | CO
| USC24C006 | F21P1 MICU Settlement 2nd_VOC | 4590020306 | 966556.97 | Low Voltage | CO
Civil | USC22C011 | WRC Exterior Pads - NH3 and Diesel System/F21P1 WRC Exterior Pad (NH3&Diesel tank) | 4590007599 | 2296327 | WWT | CO
Management | USC22C011 | WRC Exterior Pads - NH3 and Diesel System/F21P1 WRC Exterior Pad (NH3&Diesel tank) | 4590007599 | 183706 | WWT | CO
| USC21C001 | AZ temp office CCTV and metal gate | 4503045358 | 110660.61 | Low Voltage | CO
| USC21C002 | AZ Temp Office Access Control System/Sp | 4503243471 | 145958.4 |  | CO
| USC22C001 | US Fab Warehouse Security & CCTV | 4590000539 | 1906859 | Low Voltage | CO
| USC22C001 | F21P1 Office Security & CCTV Packag | 4590000540 | 7311604 | Low Voltage | CO
| USC22C010 | F21P1_LSC-CMS 5G System | 4590001181_100 | 5642423.15 | Low Voltage | CO
| USC22C010 | F21P1_DPM 5G System | 4590001181_200 | 5786087.37 | Low Voltage | CO
| USC22C013 | F21P1 QR Lab Security & CCTV | 4590002290 | 424087.84 | Low Voltage | CO
| USC22C013 | Security&CCTV Package_CCD | 4590002292 | 306397.9 | Low Voltage | CO
| USC21C009 | F21P1 Fab Lab WWT_Stage2 | 4590004557_002 | 195433 | WWT | CO
| USC22C013 | F21P1 FAB Lab Security & CCTV_Stage2 | 4590004610 | 112375.63 | Low Voltage | CO
| USC23C040 | F21P1_H_construction gown suit | 4590012251 | 130000 |  | CO
| USC21C006 | F21P1 Slurry 2 Additional Set Install | 4590014805 | 1590000 | Chemical | CO
| USC22C013 | MISC_(TAX/T0)_(LB1 CCTV QTY6/MIC) | 4590015164 | 47320 | Low Voltage | CO
| USC22C013 | Pull 108 cable | 4590018358 | 30019 | Low Voltage | CO
|  | MIC Chemical Support Team Jul 5FTE | 4590020023 | 93854.08 | Chemical | CO
|  | F21P1 SDS Function Change Expansion V1.6 | 4590021323 | 684093.85 | Chemical | CO
|  | F21P1 CDS/WCCS Expansion V1.6 | 4590021934 | 7189476.52 | Chemical | CO
|  | F21P1 VMB & Piping Expansion V1.6 | 4590021935 | 4536009.3 | Chemical | CO
|  | Emergency work | 4590021972 | 8972.68 | WWT | CO
|  | F21P1 UPW Submain Expansion V1.6 | 4590021973 | 1686849.69 | UPW | CO
|  | F21P1 WWT AWN System 2nd Source Enzyme | 4590022280 | 462873.51 | WWT | CO
|  | F21P1 TCO and non-TCO access control | 4590022428_001 | 159798.46 | Low Voltage | CO
|  | F21 P1 Egress motion requirement | 4590022428_002 | 110013.4 | Low Voltage | CO
|  | F21-P1_ Relocation speed gate at west te | 4590022428_003 | 99501 | Low Voltage | CO
|  | GC_Consumables_F21P1 GC 6" Rupture Disk | 4590023708 | 9585.5 | Chemical | CO
|  | F21 P1 WH CCTV / ACS System requirement | 4590023789 | 53354.76 | Low Voltage | CO
|  | GC_Consumables_F21P1 GC TS135 Valve | 4590023864 | 7008 | Chemical | CO

## Combined PM Types
Chemical
Category | Amount | TSMC PO Total $
Mechanical | 194614674.33
Electrical | 36432724.85
Steel | 785431.2
Civil | 619.03
Others | 7011541.61
Total | 238844991.02 | 282351237.6952
UPW
Category | Amount | TSMC PO Total $
Mechanical | 118234692.89
Electrical | 28131750.92
Steel | 6068144
Civil | 3266274.88
Others | 3829472.47
Total | 159530335.16 | 195877296.3501
WWT
Category | Amount | TSMC PO Total $
Mechanical | 178505994.14
Electrical | 41236704.29
Steel | 20368296.21
Civil | 10272577.92
Others | 8625033.09
Total | 259008605.65 | 248493245.1447
Low Voltage
Category | Amount | TSMC PO Total $
Mechanical | 18378054.17
Electrical | 40519858.77
Steel | 11912
Civil | 0
Others | 367504.27
Total | 59277329.21 | 73784578.34
Water_Sewer
Category | Amount | TSMC PO Total $
Mechanical | 5655525.57
Electrical | 0
Steel | 0
Civil | 3347853.84
Others | 0
Total | 9003379.41 | 7728000
Base-Build
Category | Amount | TSMC PO Total $
Mechanical | 0
Electrical | 0
Steel | 0
Civil | 0
Others | 33655689.27
Total | 33655689.27 | 14750650.2

## Detailed Combined PM Types
Chemical
Category | Scope | Amount | TSMC PO Total $
Mechanical | Commissioning | 2394.04
Mechanical | E2 | 3430389
Mechanical | Equipment ( Tank 等工程相關的設備) | 3484630.15
Mechanical | Instrument | 127053.58
Mechanical | Labor | 32130158.22
Mechanical | M+L | 139980923.25
Mechanical | Material | 15445709.56
Mechanical | Site Expense | 13416.53
Electrical | E2 | 288000
Electrical | Equipment ( Tank 等工程相關的設備) | 1685692.71
Electrical | Labor | 7242750.29
Electrical | M+L | 23758019.07
Electrical | Material | 3444162.78
Electrical | QAQC | 14100
Steel | Labor | 426458.2
Steel | M+L | 47068
Steel | Material | 311905
Civil | Material | 619.03
Others | Labor | 1793091.61
Others | M+L | 3000000
Others | QAQC | 2218450
Total |  | 238844991.02 | 282351237.6952
UPW
Category | Scope | Amount | TSMC PO Total $
Mechanical | Equipment ( Tank 等工程相關的設備) | 2553.09
Mechanical | Labor | 6222459.05
Mechanical | M+L | 102795079.33
Mechanical | Material | 9214601.42
Electrical | Commissioning | 31
Electrical | Labor | 4975057.67
Electrical | M+L | 19557709.97
Electrical | Material | 3509637.28
Electrical | QAQC | 89315
Steel | Labor | 40228
Steel | M+L | 5662606
Steel | Material | 5310
Steel | Project Outsourcing (專案管理外包人力) | 360000
Civil | Labor | 146485
Civil | M+L | 2866933.88
Civil | Material | 250000
Civil | Project Outsourcing (專案管理外包人力) | 2856
Others | Commissioning | 602639.24
Others | Labor | 1449275.01
Others | M+L | 138027.01
Others | Material | 1054827.48
Others | Project Outsourcing (專案管理外包人力) | 82153.68
Others | QAQC | 130303.65
Others | Site Expense | 372246.4
Total |  | 159530335.16 | 195877296.3501
WWT
Category | Scope | Amount | TSMC PO Total $
Mechanical | Commissioning | 141374.62
Mechanical | E2 | 282500
Mechanical | Equipment ( Tank 等工程相關的設備) | 22901008.88
Mechanical | Instrument | 303226.65
Mechanical | Labor | 75692767.61
Mechanical | M+L | 54538729.28
Mechanical | Material | 24362530.5
Mechanical | Site Expense | 283856.6
Electrical | Equipment ( Tank 等工程相關的設備) | 50892.07
Electrical | Instrument | 1195762.5
Electrical | Labor | 10386835.88
Electrical | M+L | 28408125.01
Electrical | Material | 983078.55
Electrical | Project Outsourcing (專案管理外包人力) | 100000
Electrical | Site Expense | 112010.28
Steel | Equipment ( Tank 等工程相關的設備) | 61027
Steel | Labor | 526629.47
Steel | M+L | 17762924.04
Steel | Material | 2017715.7
Civil | Equipment ( Tank 等工程相關的設備) | 132000
Civil | Labor | 102875.5
Civil | M+L | 10037702.42
Others | Commissioning | 1352325.47
Others | Equipment ( Tank 等工程相關的設備) | 80548.9
Others | Housekeeping | 5885.37
Others | Labor | 49350
Others | Material | 9127
Others | Project Outsourcing (專案管理外包人力) | 3865253.3
Others | QAQC | 2506971.39
Others | Safety | 6925
Others | Site Expense | 547501.66
Total |  | 258807460.65 | 248493245.1447
Low Voltage
Category | Scope | Amount | TSMC PO Total $
Mechanical | Equipment ( Tank 等工程相關的設備) | 1287301
Mechanical | Housekeeping | 308247.04
Mechanical | Labor | 397896.48
Mechanical | M+L | 12375053.53
Mechanical | Material | 4008856.12
Electrical | Equipment ( Tank 等工程相關的設備) | 5403557.38
Electrical | Labor | 2468888.67
Electrical | M+L | 30277930.29
Electrical | Material | 2369482.43
Steel | M+L | 11912
Civil | N/A | 0
Others | Commissioning | 23440
Others | QAQC | 333624.15
Others | Safety | 7709.6
Others | Site Expense | 2730.52
Total |  | 59276629.21 | 73784578.34
Water_Sewer
Category | Scope | Amount | TSMC PO Total $
Mechanical | M+L | 5655525.57
Electrical | N/A | 0
Steel | N/A | 0
Civil | M+L | 3347853.84
Others | N/A | 0
Total |  | 9003379.41 | 7728000
Base-Build
Category | Scope | Amount | TSMC PO Total $
Mechanical | N/A | 0
Electrical | N/A | 0
Steel | N/A | 0
Civil | N/A | 0
Others | Housekeeping | 3885395
Others | Project Outsourcing (專案管理外包人力) | 8526305.15
Others | Site Expense | 21243989.12
Total |  | 33655689.27 | 14750650.2
From APN
Scope | Amount
Equipment Rental | 15825966.38
Scaffolding | 7518635.47
Outsourcing | 5489811.8
Shipping | 4724422.98
Housekeeping | 4297414.56
Lease | 3284642.55
PPE | 1410130.34
Office Spending | 623008.98
Move In | 435447.04
Water & Ice | 407089.16
Construction | 79533.31
Office/ Trailer Cleaning | 54758.4
Service | 36148.96
Fuel | 16822.95
Total | 44203832.88

## Base-Build_breakdown
Scope | Type2 | Amount
Housekeeping | Housekeeping | 3885395
Project Outsourcing (專案管理外包人力) | Outsourcing | 8526305.15
Site Expense | Scaffolding | 16358807.9
Site Expense | Other Scope | 1767794.9
Site Expense | MISC Expense | 1766947.67
Site Expense | Trailer | 700000
Site Expense | Software | 278553.45
Site Expense | Equipment | 207847.66
Site Expense | Internet | 108283
Site Expense | MIMO/Rigging | 55754.54
Total | 0 | 33655689.27