## PO Amount By Category
Type | Project # | Project Name | PO # | Total Contract $ | Main Page | CO/Added | Amy PO
Mechanical | USC21C003 | F21P1 Tunnel/lorry common support | 4590006744 | 5795851 | WWT | Added
GC | USC21C003 | F21P1 Tunnel/lorry common support | 4590006744 | 240481.244 | WWT | Added
Management | USC21C003 | F21P1 Tunnel/lorry common support | 4590006744 | 463668.056 | WWT | Added
Mechanical | USC21C003 | F21P1 UPW Temporary CP and piping | 4590009036 | 108600 | UPW | Added
GC | USC21C003 | F21P1 UPW Temporary CP and piping | 4590009036 | 6515 | UPW | Added
Management | USC21C003 | F21P1 UPW Temporary CP and piping | 4590009036 | 10860 | UPW | Added
Scope | USC21C003 | F21P1 QR Lab UPW | 4590004028 | 668561
GC | USC21C003 | F21P1 QR Lab UPW | 4590004028 | 40114
Management | USC21C003 | F21P1 QR Lab UPW | 4590004028 | 53484.9281
Mechanical | USC21C003 | F21P1 UPW Temporary Resin and piping | 4590010557 | 144432 | UPW | Added
GC | USC21C003 | F21P1 UPW Temporary Resin and piping | 4590010557 | 7222 | UPW | Added
Management | USC21C003 | F21P1 UPW Temporary Resin and piping | 4590010557 | 14346 | UPW | Added
Others | USC21C003 | F21P1 CUP L20 Transformer Pads | 4590011254 | 135514.66 | UPW | Added
GC | USC21C003 | F21P1 CUP L20 Transformer Pads | 4590011254 | 0 | UPW | Added
Management | USC21C003 | F21P1 CUP L20 Transformer Pads | 4590011254 | 9485.34 | UPW | Added
Electrical | USC21C003 | F21P1 UPW temp power and MAU DI solution | 4590012982 | 540198.34 | UPW | Added
GC | USC21C003 | F21P1 UPW temp power and MAU DI solution | 4590012982 | 7448.66 | UPW | Added
Management | USC21C003 | F21P1 UPW temp power and MAU DI solution | 4590012982 | 71195 | UPW | Added
Steel Work | USC21C003 | F21P1 UPW Tank Swing Gate | 4590013482 | 70400 | UPW | Added
GC | USC21C003 | F21P1 UPW Tank Swing Gate | 4590013482 | 3520 | UPW | Added
Management | USC21C003 | F21P1 UPW Tank Swing Gate | 4590013482 | 9152 | UPW | Added
Electrical | USC21C003 | F21P1 UPW & WWT Battery Charge | 4590013633 | 228000 | UPW | Added
GC | USC21C003 | F21P1 UPW & WWT Battery Charge | 4590013633 | 2280 | UPW | Added
Management | USC21C003 | F21P1 UPW & WWT Battery Charge | 4590013633 | 34542 | UPW | Added
Electrical | USC21C005 | F21P1 CR temp lighting | 4590012687 | 70264 | Chemical | Added
GC | USC21C005 | F21P1 CR temp lighting | 4590012687 | 3513.2 | Chemical | Added
Management | USC21C005 | F21P1 CR temp lighting | 4590012687 | 11066.58 | Chemical | Added
Mechanical | USC21C005 | F21P1 Chemical Solvent day tank add vent | 4590012855 | 425434.49 | Chemical | Added
GC | USC21C005 | F21P1 Chemical Solvent day tank add vent | 4590012855 | 22591.7 | Chemical | Added
Management | USC21C005 | F21P1 Chemical Solvent day tank add vent | 4590012855 | 41973.81 | Chemical | Added
Steel Work | USC21C005 | F21P1 Lorry area fall protection tie off | 4590013430 | 272948.58 | Chemical | Added
GC | USC21C005 | F21P1 Lorry area fall protection tie off | 4590013430 | 13647.43 | Chemical | Added
Management | USC21C005 | F21P1 Lorry area fall protection tie off | 4590013430 | 40942.29 | Chemical | Added
Steel Work | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 4590013480 | 20559.01 | Chemical | Added
GC | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 4590013480 | 1027.95 | Chemical | Added
Management | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 4590013480 | 3083.85 | Chemical | Added
Steel Work | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 4590013481 | 29700 | Chemical | Added
GC | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 4590013481 | 1485 | Chemical | Added
Management | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 4590013481 | 4455 | Chemical | Added
Others | USC21C005 | F21P1 Lorry RU Chemical Filtration Impro | 4590013675 | 108900 | Chemical | Added
Management | USC21C005 | F21P1 Lorry RU Chemical Filtration Impro | 4590013675 | 16335 | Chemical | Added
Mechanical | USC21C009 | F21P1 CCB Lorry in drain system | 4590006293 | 594063.11 | WWT | Added
GC | USC21C009 | F21P1 CCB Lorry in drain system | 4590006293 | 63551.47 | WWT | Added
Scope | USC21C003 | F21P1 UPW A5 Backup Line Modification | 4590016257 | 62844.17 |  |  | x
GC | USC21C003 | F21P1 UPW A5 Backup Line Modification | 4590016257 | 3770 |  |  | x
Management | USC21C003 | F21P1 UPW A5 Backup Line Modification | 4590016257 | 9992 |  |  | x
Scope | USC21C003 | F21P1 EBO UPW package | 4590004026_100 | 329079.4071 |  |  | x
GC | USC21C003 | F21P1 EBO UPW package | 4590004026_100 | 19745 |  |  | x
Management | USC21C003 | F21P1 EBO UPW package | 4590004026_100 | 26326.3686 |  |  | x
Scope | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 4590004027_100 | 277627.18 |  |  | x
GC | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 4590004027_100 | 16657.63 |  |  | x
Management | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 4590004027_100 | 22210.1743 |  |  | x
Scope | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 4590004557_001 | 300853 |  |  | x
GC | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 4590004557_001 | 18051 |  |  | x
Management | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 4590004557_001 | 24068.34 |  |  | x
Management | USC21C009 | F21P1 CCB Lorry in drain system | 4590006293 | 49631.289 | WWT | Added
Mechanical | USC21C009 | F21P1 Formaldehyde treatment system | 4590006720 | 625199.16 | WWT | Added
GC | USC21C009 | F21P1 Formaldehyde treatment system | 4590006720 | 26000 | WWT | Added
Management | USC21C009 | F21P1 Formaldehyde treatment system | 4590006720 | 48800.84 | WWT | Added
Electrical | USC21C009 | F21P1 WWT construction temp power | 4590012872 | 363852 | WWT | Added
Management | USC21C009 | F21P1 WWT construction temp power | 4590012872 | 44148 | WWT | Added
Steel Work | USC21C009 | F21P1 230KV MTR NGR stand | 4590013495 | 78042 | WWT | Added
GC | USC21C009 | F21P1 230KV MTR NGR stand | 4590013495 | 9365.04 | WWT | Added
Management | USC21C009 | F21P1 230KV MTR NGR stand | 4590013495 | 11706.3 | WWT | Added
Steel Work | USC21C009 | F21P1 WWT Tank Swing Gate | 4590013571 | 119350 | WWT | Added
GC | USC21C009 | F21P1 WWT Tank Swing Gate | 4590013571 | 5968 | WWT | Added
Management | USC21C009 | F21P1 WWT Tank Swing Gate | 4590013571 | 15516 | WWT | Added
Electrical | USC21C009 | F21P1 WWT Electrical Testing Support | 4590013603 | 163735 | WWT | Added
Management | USC21C009 | F21P1 WWT Electrical Testing Support | 4590013603 | 18892.5 | WWT | Added
Steel Work | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 4590013803 | 1502984.58 | WWT | Added
GC | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 4590013803 | 102653.85 | WWT | Added
Management | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 4590013803 | 128451.07 | WWT | Added
Electrical | USC21C013 | F21P1 EBO AMC Monitor system | 4590006871 | 918126 | Low Voltage | Added
GC | USC21C013 | F21P1 EBO AMC Monitor system | 4590006871 | 23000 | Low Voltage | Added
Electrical | USC21C013 | F21P1 AMC package-IMS wipe test | 4590013433 | 7680 | Low Voltage | Added
Management | USC21C013 | F21P1 AMC package-IMS wipe test | 4590013433 | 1152 | Low Voltage | Added
Electrical | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 4590013669 | 38004 | Low Voltage | Added
GC | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 4590013669 | 2280.24 | Low Voltage | Added
Management | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 4590013669 | 6042.64 | Low Voltage | Added
Mechanical | USC22C009 | F21P1 MTR oil & drain pipe work | 4590000624 | 358335 | WWT | Added
GC | USC22C009 | F21P1 MTR oil & drain pipe work | 4590000624 | 21361 | WWT | Added
Management | USC22C009 | F21P1 MTR oil & drain pipe work | 4590000624 | 28304 | WWT | Added
Electrical | USC22C010 | F21P1 LV PDS on site installation | 4590000334 | 165168 | Low Voltage | Added
GC | USC22C010 | F21P1 LV PDS on site installation | 4590000334 | 9910.08 | Low Voltage | Added
Management | USC22C010 | F21P1 LV PDS on site installation | 4590000334 | 13213.44 | Low Voltage | Added
Electrical | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 4590002291 | 57083.38 | Low Voltage | Added
GC | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 4590002291 | 548.52 | Low Voltage | Added
Management | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 4590002291 | 6907.53 | Low Voltage | Added
Others | USC22C021 | F21P1 Chemical Lab setup | 4590004281 | 414401.66 | Chemical | Added
GC | USC22C021 | F21P1 Chemical Lab setup | 4590004281 | 54616.55 | Chemical | Added
Management | USC22C021 | F21P1 Chemical Lab setup | 4590004281 | 35397.6012 | Chemical | Added
Mechanical | USC22C021 | F21P1 Chemical Lab Hookup | 4590008170 | 393600 | Chemical | Added
GC | USC22C021 | F21P1 Chemical Lab Hookup | 4590008170 | 76451 | Chemical | Added
Management | USC22C021 | F21P1 Chemical Lab Hookup | 4590008170 | 37599 | Chemical | Added
Mechanical | USC22C023 | F21P1 Piping Material Collaboration | 4590008240 | 2811729.15 | UPW | Added
Management | USC22C023 | F21P1 Piping Material Collaboration | 4590008240 | 231172.915 | UPW | Added
Steel Work | USC22C031 | F21P1 High-speed rolling door frame | 4590013431 | 22779.71 | WWT | Added
GC | USC22C031 | F21P1 High-speed rolling door frame | 4590013431 | 1139 | WWT | Added
Management | USC22C031 | F21P1 High-speed rolling door frame | 4590013431 | 3109 | WWT | Added
Mechanical | USC23C012 | F21P1 Hot DI Machine Hookup | 4590008229_001 | 196587 | Chemical | Added
GC | USC23C012 | F21P1 Hot DI Machine Hookup | 4590008229_001 | 38608 | Chemical | Added
Management | USC23C012 | F21P1 Hot DI Machine Hookup | 4590008229_001 | 4805 | Chemical | Added
Steel Work | USC23C042 | F21P1 Chemical safety cabinet installation | 4590004117 | 42873 | Chemical | Added
GC | USC23C042 | F21P1 Chemical safety cabinet installation | 4590004117 | 2572 | Chemical | Added
Management | USC23C042 | F21P1 Chemical safety cabinet installation | 4590004117 | 3429.824 | Chemical | Added
Electrical | USC23C043 | Electric Tiger Team_Fisk Support & Temp Power | 4590012300 | 376459 | WWT | Added
Management | USC23C043 | Electric Tiger Team_Fisk Support & Temp Power | 4590012300 | 48939.67 | WWT | Added
Electrical | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 4590012310 | 117700 | WWT | Added
GC | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 4590012310 | 5885 | WWT | Added
Management | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 4590012310 | 11770 | WWT | Added
Electrical |  | F21P1 Cast Resin PD Sensor Install/Test | 4590013944 | 58000 | UPW | Added
Management |  | F21P1 Cast Resin PD Sensor Install/Test | 4590013944 | 11600 | UPW | Added
Others |  | F21P1 WWT FAB LB2 Trench Cleanning | 4590014676 | 104312 | WWT | Added
Management |  | F21P1 WWT FAB LB2 Trench Cleanning | 4590014676 | 36816 | WWT | Added
Steel Work | USC21C003 | F21P1 WRC L20 RACK Modification | 4590013928 | 15984 | WWT | CO
GC | USC21C003 | F21P1 WRC L20 RACK Modification | 4590013928 | 959 | WWT | CO
Management | USC21C003 | F21P1 WRC L20 RACK Modification | 4590013928 | 2541 | WWT | CO
Electrical | USC21C003 | F21P1 UPW Control Panel Temp Cable | 4590014674 | 699981.89 | UPW | CO
Scope | USC21C009 | F21P1 QR Lab WWT | 4590004029 | 2531199.59 |  |  | x
GC | USC21C009 | F21P1 QR Lab WWT | 4590004029 | 283786.83 |  |  | x
Management | USC21C009 | F21P1 QR Lab WWT | 4590004029 | 212453.35 |  |  | x
GC | USC21C003 | F21P1 UPW Control Panel Temp Cable | 4590014674 | 34999.0945 | UPW | CO
Management | USC21C003 | F21P1 UPW Control Panel Temp Cable | 4590014674 | 95547.528 | UPW | CO
Mechanical | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 4590014675 | 177120.35 | UPW | CO
GC | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 4590014675 | 10627 | UPW | CO
Management | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 4590014675 | 28162 | UPW | CO
Mechanical | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 83646 | Chemical | CO
Electrical | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 38568 | Chemical | CO
GC | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 5597.28 | Chemical | CO
Management | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 19171.69 | Chemical | CO
Management | USC21C007 | F21P1 VOC Burner NOx improve-installatio | 4590011320 | 88238.83 | Low Voltage | CO
Mechanical | USC21C007 | F21P1 VOC Burner NOx improve-installatio | 4590011320 | 678760.27 | Low Voltage | CO
GC | USC21C009 | F21P1 Discharge monitoring change | 4590004971 | 36436 | WWT | CO
Management | USC21C009 | F21P1 Discharge monitoring change | 4590004971 | 57090 | WWT | CO
Electrical | USC21C009 | F21P1 Discharge monitoring change | 4590004971 | 532474 | WWT | CO
Steel Work | USC21C009 | F21P1 WWT cable tray relo & add support | 4590013804 | 2078912.7 | WWT | CO
GC | USC21C009 | F21P1 WWT cable tray relo & add support | 4590013804 | 141990 | WWT | CO
Management | USC21C009 | F21P1 WWT cable tray relo & add support | 4590013804 | 177672 | WWT | CO
Steel Work | USC21C009 | F21P1 WWT LB2 Support Modification | 4590014187 | 16376 | WWT | CO
GC | USC21C009 | F21P1 WWT LB2 Support Modification | 4590014187 | 819 | WWT | CO
Management | USC21C009 | F21P1 WWT LB2 Support Modification | 4590014187 | 2580 | WWT | CO
Mechanical | USC21C009 | F21P1 WWT Per Diem and Acceleration | 4590014401 | 6264381 | WWT | CO
Mechanical | USC21C009 | F21P1 WWT AWR Drain to LSR System | 4590014629 | 51797.04 | WWT | CO
GC | USC21C009 | F21P1 WWT AWR Drain to LSR System | 4590014629 | 3107.82 | WWT | CO
Management | USC21C009 | F21P1 WWT AWR Drain to LSR System | 4590014629 | 8235.73 | WWT | CO
Electrical | USC21C009 | F21P1 WWT Panel Butten Change | 4590014630 | 86528 | WWT | CO
GC | USC21C009 | F21P1 WWT Panel Butten Change | 4590014630 | 865.28 | WWT | CO
Management | USC21C009 | F21P1 WWT Panel Butten Change | 4590014630 | 13108.99 | WWT | CO
Mechanical | USC21C009 | F21P1 WWT Per Diem and Acceleration | 4590015058 | 4142540.4 | WWT | CO
Electrical | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 4590015143 | 493675 | WWT | CO
GC | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 4590015143 | 29621 | WWT | CO
Management | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 4590015143 | 78494 | WWT | CO
Mechanical | USC23C045 | F21P1 UPW Design Change (UMEC) | 4590013572 | 388723 | UPW | CO
GC | USC23C045 | F21P1 UPW Design Change (UMEC) | 4590013572 | 3887.23 | UPW | CO
Management | USC23C045 | F21P1 UPW Design Change (UMEC) | 4590013572 | 58891.5345 | UPW | CO
GC | USC23C054 | F21P1 WCCS Extend GC and Labor Incentive | 4590013806 | 661674 | Base-Build | CO
GC | USC23C054 | F21P1 Slurry Extend GC & Labor Incentive | 4590013807 | 1313687.25 | Base-Build | CO
GC | USC23C054 | F21P1 VOC Extend GC & Labor Incentive | 4590013808 | 104910 | Base-Build | CO
GC | USC23C054 | F21P1 CDS Extend GC & Labor Incentive | 4590013809 | 7083604.02 | Base-Build | CO
GC | USC23C054 | F21P1 UPW Extend GC & Labor Incentive | 4590013810 | 5008794.91 | Base-Build | CO
Scope | USC21C009 | F21P1 EBO WWT package | 4590004026_200 | 891848.65 |  |  | x
GC | USC21C009 | F21P1 EBO WWT package | 4590004026_200 | 53510.92 |  |  | x
Management | USC21C009 | F21P1 EBO WWT package | 4590004026_200 | 71347.8922 |  |  | x
Scope | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 4590004027_200 | 359598 |  |  | x
GC | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 4590004027_200 | 53861 |  |  | x
Management | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 4590004027_200 | 32819 |  |  | x
GC | USC23C054 | F21P1 WWT Extend GC & Labor Incentive | 4590013811 | 577980.02 | Base-Build | CO
Mechanical | USC21C003 | F21P1 UPW | 4503290109 | 87980103 | UPW | Main
Electrical | USC21C003 | F21P1 UPW | 4503290109 | 20327458 | UPW | Main
Steel Work | USC21C003 | F21P1 UPW | 4503290109 | 28037246 | UPW | Main
Others | USC21C003 | F21P1 UPW | 4503290109 | 295650 | UPW | Main
GC | USC21C003 | F21P1 UPW | 4503290109 | 7618520 | UPW | Main
Management | USC21C003 | F21P1 UPW | 4503290109 | 12041023 | UPW | Main
Mechanical | USC21C004 | F21P1 WWT package (USA EQ - FRP tank) | 4503312319 | 6158273 | WWT | Main
Management | USC21C005 | F21P1 CDS package (B.10) | 4590009808 | 56024.4 | Chemical | Main
GC | USC21C005 | F21P1 CDS package (B.10) | 4590009808 | 109737.6 | Chemical | Main
Mechanical | USC21C005 | F21P1 CDS package (B.10) | 4590009808 | 1104238 | Chemical | Main
Mechanical | USC21C005 | F21P1 Chemical package | 4503446631_100 | 116849536.85 | Chemical | Main
Electrical | USC21C005 | F21P1 Chemical package | 4503446631_100 | 19303769.72 | Chemical | Main
Steel Work | USC21C005 | F21P1 Chemical package | 4503446631_100 | 11603571.43 | Chemical | Main
Others | USC21C005 | F21P1 Chemical package | 4503446631_100 | 2190000 | Chemical | Main
Management | USC21C005 | F21P1 Chemical package | 4503446631_100 | 10704880 | Chemical | Main
GC | USC21C005 | F21P1 Chemical package | 4503446631_100 | 840165 | Chemical | Main
Mechanical | USC21C005 | F21P1 WCCS package | 4503446631_200 | 28148814.3 | Chemical | Main
Electrical | USC21C005 | F21P1 WCCS package | 4503446631_200 | 493566.7 | Chemical | Main
Steel Work | USC21C005 | F21P1 WCCS package | 4503446631_200 | 500000 | Chemical | Main
Others | USC21C005 | F21P1 WCCS package | 4503446631_200 | 0 | Chemical | Main
GC | USC21C005 | F21P1 WCCS package | 4503446631_200 | 143197 | Chemical | Main
Management | USC21C005 | F21P1 WCCS package | 4503446631_200 | 4552754 | Chemical | Main
GC | USC21C005 | F21P1 TGCM Room | 4590008229_002 | 2311 | Chemical | Main
Management | USC21C005 | F21P1 TGCM Room | 4590008229_002 | 1476 | Chemical | Main
Others | USC21C005 | F21P1 TGCM Room | 4590008229_002 | 46213 | Chemical | Main
Mechanical | USC21C006 | F21P1 Slurry package | 4503428513 | 24635187 | Chemical | Main
Electrical | USC21C006 | F21P1 Slurry package | 4503428513 | 2723181 | Chemical | Main
Steel Work | USC21C006 | F21P1 Slurry package | 4503428513 | 740642 | Chemical | Main
Others | USC21C006 | F21P1 Slurry package | 4503428513 | 7219990 | Chemical | Main
GC | USC21C006 | F21P1 Slurry package | 4503428513 | 193000 | Chemical | Main
Management | USC21C006 | F21P1 Slurry package | 4503428513 | 3088000 | Chemical | Main
Management | USC21C006 | F21P1 Slurry Package support frame | 4590003895 | 87144 | Chemical | Main
Steel Work | USC21C006 | F21P1 Slurry Package support frame | 4590003895 | 580960 | Chemical | Main
Mechanical | USC21C006 | F21P1 SDS installation (B.10) | 4590009963 | 1829620 | Chemical | Main
GC | USC21C006 | F21P1 SDS installation (B.10) | 4590009963 | 9149 | Chemical | Main
Management | USC21C006 | F21P1 SDS installation (B.10) | 4590009963 | 110327 | Chemical | Main
Mechanical | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 8678203.9 | Low Voltage | Main
Electrical | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 4038484.1 | Low Voltage | Main
Others | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 3043495 | Low Voltage | Main
Management | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 2077130.37 | Low Voltage | Main
GC | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 844686.11 | Low Voltage | Main
Management | USC21C008 | F21 CCTV & Security | 4503441102 | 1741245 | Low Voltage | Main
GC | USC21C008 | F21 CCTV & Security | 4503441102 | 110638 | Low Voltage | Main
Electrical | USC21C008 | F21 CCTV & Security | 4503441102 | 10828117 | Low Voltage | Main
Management | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 11397325 | WWT | Main
Mechanical | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 79852928 | WWT | Main
Electrical | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 15724572.5 | WWT | Main
Steel Work | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 28940662.8 | WWT | Main
Others | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 3740308 | WWT | Main
GC | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 8766883.7 | WWT | Main
Steel Work | USC21C010 | Water pipeline installation (size>4") | 4503398624 | 5723522 | Water_Sewer | Main
Steel Work | USC21C010 | Water pipeline installation (size<4") | 4503423409 | 776478 | Water_Sewer | Main
Mechanical | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 4503432152 | 6753583.34 | WWT | Main
GC | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 4503432152 | 36367.35 | WWT | Main
Management | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 4503432152 | 519886.3134 | WWT | Main
Mechanical | USC21C011 | TMAH ACF system expansion | 4590008082 | 4146068 | WWT | Main
GC | USC21C011 | TMAH ACF system expansion | 4590008082 | 242858 | WWT | Main
Management | USC21C011 | TMAH ACF system expansion | 4590008082 | 382003.8 | WWT | Main
Electrical | USC21C012 | F21P1 Barcode & RFID for manufacturing | 4503441308 | 4819590 | Low Voltage | Main
GC | USC21C012 | F21P1 Barcode & RFID for manufacturing | 4503441308 | 249941 | Low Voltage | Main
Management | USC21C012 | F21P1 Barcode & RFID for manufacturing | 4503441308 | 722760 | Low Voltage | Main
Electrical | USC21C013 | F21P1 AMC | 4503448339_100 | 3401994 | Low Voltage | Main
Others | USC21C013 | F21P1 AMC | 4503448339_100 | 927549 | Low Voltage | Main
GC | USC21C013 | F21P1 AMC | 4503448339_100 | 66000 | Low Voltage | Main
Management | USC21C013 | F21P1 AMC | 4503448339_100 | 610000 | Low Voltage | Main
Mechanical | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 1205462 | Low Voltage | Main
Electrical | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 1118008 | Low Voltage | Main
Others | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 101456 | Low Voltage | Main
GC | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 11250 | Low Voltage | Main
Management | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 258280.2 | Low Voltage | Main
Mechanical | USC21C014 | F21P1 W-H2SO4 package | 4503489979 | 2568895 | WWT | Main
GC | USC21C014 | F21P1 W-H2SO4 package | 4503489979 | 388920 | WWT | Main
Management | USC21C014 | F21P1 W-H2SO4 package | 4503489979 | 312779 | WWT | Main
Others | USC22C018 | US Fab Frontage line hydrants | 4590005093 | 1087000 | Water_Sewer | Main
GC | USC22C018 | US Fab Frontage line hydrants | 4590005093 | 54040 | Water_Sewer | Main
Management | USC22C018 | US Fab Frontage line hydrants | 4590005093 | 86960 | Water_Sewer | Main
Mechanical | USC22C020 | F21P1 Penetration Pipe | 4590005240 | 917975 | UPW | Main
GC | USC22C020 | F21P1 Penetration Pipe | 4590005240 | 40227 | UPW | Main
Management | USC22C020 | F21P1 Penetration Pipe | 4590005240 | 91798 | UPW | Main
Mechanical | USC22C022 | F21P1 Triazole treatment system | 4590006189 | 3859622 | WWT | Main
GC | USC22C022 | F21P1 Triazole treatment system | 4590006189 | 103063 | WWT | Main
Management | USC22C022 | F21P1 Triazole treatment system | 4590006189 | 377315 | WWT | Main
Others | USC23C014 | F21P1 Labor incentive program-MICU | 4590008319 | 1625000 | UPW | Main
Steel Work |  | F21P1 UPW WRC L10 Add Supports | 4590016147 | 10449.2 | UPW | CO
Management |  | F21P1 UPW WRC L10 Add Supports | 4590016147 | 1567.38 | UPW | CO
Mechanical |  | F21P1 CDS Pressure Test Appeal for PFC | 4590019011 | 30000 | Chemical | CO
Management |  | F21P1 CDS Pressure Test Appeal for PFC | 4590019011 | 4500 | Chemical | CO
Mechanical |  | F21P1 CDS & WCCS CO2 Suppression System | 4590019083 | 732426.9565 | Chemical | CO
Management |  | F21P1 CDS & WCCS CO2 Suppression System | 4590019083 | 109864.0435 | Chemical | CO
Mechanical |  | F21P1 CDS Labor Incentive Nov 2023 | 4590019372 | 36000 | Chemical | CO
Mechanical |  | F21P1 WWT Labor Incentive Nov 2023 | 4590019487 | 60000 | WWT | CO
Mechanical |  | F21P1 UPW Labor Incentive Nov 2023 | 4590019488 | 15000 | UPW | CO
Electrical |  | F21P1 UPW Fiber Repull from Damage | 4590019489 | 136610.7043 | UPW | CO
Management |  | F21P1 UPW Fiber Repull from Damage | 4590019489 | 20491.6057 | UPW | CO
Electrical |  | F21P1 Add Card Reader at Material Gate | 4590019490 | 17654 | Low Voltage | CO
Management |  | F21P1 Add Card Reader at Material Gate | 4590019490 | 2634 | Low Voltage | CO
Civil |  | F21P1 WWT Doors &Triazole HK Pad Mod | 4590019491 | 12093.913 | WWT | CO
Management |  | F21P1 WWT Doors &Triazole HK Pad Mod | 4590019491 | 1814.087 | WWT | CO
Mechanical |  | F21P1 WWT Temp Chem. Leak Diverter Tarp | 4590019492 | 66780 | WWT | CO
Management |  | F21P1 WWT Temp Chem. Leak Diverter Tarp | 4590019492 | 10017 | WWT | CO
Electrical |  | F21P1 Speed Gate at Tent and CR Entrance | 4590019493 | 596110.44 | Low Voltage | CO
Management |  | F21P1 Speed Gate at Tent and CR Entrance | 4590019493 | 88877 | Low Voltage | CO
Civil |  | F21P1 Hallway Plate Install | 4590019495 | 220500 | WWT | CO
Management |  | F21P1 Hallway Plate Install | 4590019495 | 33075 | WWT | CO
Mechanical |  | F21P1 UPW ABG-A Submain Modification | 4590019922 | 67395.7913 | UPW | CO
Management |  | F21P1 UPW ABG-A Submain Modification | 4590019922 | 10109.3687 | UPW | CO
Mechanical |  | F21P1 UPW WRC NFPA Sign Installation | 4590019923 | 8055.9913 | UPW | CO
Management |  | F21P1 UPW WRC NFPA Sign Installation | 4590019923 | 1208.3987 | UPW | CO
Electrical |  | F21P1 Seismic Monitor | 4590019924 | 217165.2261 | Low Voltage | CO
Management |  | F21P1 Seismic Monitor | 4590019924 | 32574.7839 | Low Voltage | CO
Electrical |  | F21P1 UPW Cable Tray Reroute per Code | 4590019925 | 382152.513 | UPW | CO
Management |  | F21P1 UPW Cable Tray Reroute per Code | 4590019925 | 57322.877 | UPW | CO
Mechanical |  | F21P1 UPW Piping Damaged by Others | 4590019926 | 14504.7217 | UPW | CO
Management |  | F21P1 UPW Piping Damaged by Others | 4590019926 | 2175.7083 | UPW | CO
Mechanical |  | F21P1 UPW B Side MAU DI Temp Solution | 4590019927 | 104585.713 | UPW | CO
Management |  | F21P1 UPW B Side MAU DI Temp Solution | 4590019927 | 15687.857 | UPW | CO
Civil |  | F21P1 UPW WRC L20 Trench Modification | 4590019928 | 2914.7826 | UPW | CO
Management |  | F21P1 UPW WRC L20 Trench Modification | 4590019928 | 437.2174 | UPW | CO
Mechanical |  | F21P1 UPW Temp UPW Supply for ICPMS | 4590019929 | 143456.4783 | UPW | CO
Management |  | F21P1 UPW Temp UPW Supply for ICPMS | 4590019929 | 21518.4717 | UPW | CO
Electrical |  | F21P1 VOC MC Cable | 4590019947 | 453824.687 | Low Voltage | CO
Management |  | F21P1 VOC MC Cable | 4590019947 | 68073.703 | Low Voltage | CO
Scope |  | F21P1 MICU Settlement 1st_UPW | 4590020154 | 15117265.415 | UPW | CO
Management |  | F21P1 MICU Settlement 1st_UPW | 4590020154 | 2189385.135 | UPW | CO
Mechanical |  | F21P1 UPW Distribution Repair | 4590020155 | 82079.5565 | UPW | CO
Management |  | F21P1 UPW Distribution Repair | 4590020155 | 12311.9335 | UPW | CO
Scope |  | F21P1 MICU Settlement 1st_WWT | 4590020156 | 30215374.53 | WWT | CO
Management |  | F21P1 MICU Settlement 1st_WWT | 4590020156 | 2116405.63 | WWT | CO
Scope |  | F21P1 MICU Settlement 1st_CDS | 4590020157 | 12426921.31 | Chemical | CO
Management |  | F21P1 MICU Settlement 1st_CDS | 4590020157 | 2262364.64 | Chemical | CO
Scope |  | F21P1 MICU Settlement 1st_WCCS | 4590020158 | 2857297.975 | Chemical | CO
Management |  | F21P1 MICU Settlement 1st_WCCS | 4590020158 | 437877.025 | Chemical | CO
Scope |  | F21P1 MICU Settlement 1st_VOC | 4590020159 | 1805214.78 | Low Voltage | CO
Management |  | F21P1 MICU Settlement 1st_VOC | 4590020159 | 291918.02 | Low Voltage | CO
Mechanical |  | F21P1 UPW P1B Submain Expansion | 4590020160 | 134178.8261 | UPW | CO
Management |  | F21P1 UPW P1B Submain Expansion | 4590020160 | 20126.8239 | UPW | CO
Mechanical |  | F21P1 WWT AWN Enzyme Dosing Improvement | 4590020228 | 285836.5217 | WWT | CO
Management |  | F21P1 WWT AWN Enzyme Dosing Improvement | 4590020228 | 42875.4783 | WWT | CO
Electrical |  | F21P1 Security & CCTV DCR | 4590020230 | 237450.4348 | Low Voltage | CO
Management |  | F21P1 Security & CCTV DCR | 4590020230 | 35617.5652 | Low Voltage | CO
Civil |  | F21P1 UPW Mezzanine Modification | 4590020235 | 1311078.2609 | UPW | CO
Management |  | F21P1 UPW Mezzanine Modification | 4590020235 | 196661.7391 | UPW | CO
Mechanical |  | F21P1 WWT CWR System Improvement | 4590020236 | 579022.4783 | WWT | CO
Management |  | F21P1 WWT CWR System Improvement | 4590020236 | 86853.3717 | WWT | CO
|  | F21P1 MICU Settlement 2nd_UPW | 4590020302 | 7249177.3 | UPW | CO
|  | F21P1 MICU Settlement 2nd_WWT | 4590020303 | 7007538.06 | WWT | CO
|  | F21P1 MICU Settlement 2nd_CDS | 4590020304 | 7490816.54 | Chemical | CO
|  | F21P1 MICU Settlement 2nd_WCCS | 4590020305 | 1449835.46 | Chemical | CO
|  | F21P1 MICU Settlement 2nd_VOC | 4590020306 | 966556.97 | Low Voltage | CO
Civil |  | WRC Exterior Pads - NH3 and Diesel System/F21P1 WRC Exterior Pad (NH3&Diesel tank) | 4590007599 | 2296327 | WWT | CO
Management |  | WRC Exterior Pads - NH3 and Diesel System/F21P1 WRC Exterior Pad (NH3&Diesel tank) | 4590007599 | 183706 | WWT | CO
| USC21C001 | AZ temp office CCTV and metal gate | 4503045358 | 110660.61 | Low Voltage | CO
| USC21C002 | AZ Temp Office Access Control System/Sp | 4503243471 | 145958.4 |  | CO
| USC22C001 | US Fab Warehouse Security & CCTV | 4590000539 | 1906859 | Low Voltage | CO
| USC22C001 | F21P1 Office Security & CCTV Packag | 4590000540 | 7311604 | Low Voltage | CO
| USC22C010 | F21P1_LSC-CMS 5G System | 4590001181_100 | 5642423.15 | Low Voltage | CO
| USC22C010 | F21P1_DPM 5G System | 4590001181_200 | 5786087.37 | Low Voltage | CO
| USC22C013 | F21P1 QR Lab Security & CCTV | 4590002290 | 424087.84 | Low Voltage | CO
| USC22C013 | Security&CCTV Package_CCD | 4590002292 | 306397.9 | Low Voltage | CO
| USC21C009 | F21P1 Fab Lab WWT_Stage2 | 4590004557_002 | 195433 | WWT | CO
| USC22C013 | F21P1 FAB Lab Security & CCTV_Stage2 | 4590004610 | 112375.63 | Low Voltage | CO
| USC23C040 | F21P1_H_construction gown suit | 4590012251 | 130000 |  | CO
| USC21C006 | F21P1 Slurry 2 Additional Set Install | 4590014805 | 1590000 | Chemical | CO
| USC22C013 | MISC_(TAX/T0)_(LB1 CCTV QTY6/MIC) | 4590015164 | 47320 | Low Voltage | CO
| USC22C013 | Pull 108 cable | 4590018358 | 30019 | Low Voltage | CO
|  | MIC Chemical Support Team Jul 5FTE | 4590020023 | 93854.08 | Chemical | CO
|  | F21P1 SDS Function Change Expansion V1.6 | 4590021323 | 684093.85 | Chemical | CO
|  | F21P1 CDS/WCCS Expansion V1.6 | 4590021934 | 7189476.52 | Chemical | CO
|  | F21P1 VMB & Piping Expansion V1.6 | 4590021935 | 4536009.3 | Chemical | CO
|  | Emergency work | 4590021972 | 8972.68 | WWT | CO
|  | F21P1 UPW Submain Expansion V1.6 | 4590021973 | 1686849.69 | UPW | CO
|  | F21P1 WWT AWN System 2nd Source Enzyme | 4590022280 | 462873.51 | WWT | CO
|  | F21P1 TCO and non-TCO access control | 4590022428_001 | 159798.46 | Low Voltage | CO
|  | F21 P1 Egress motion requirement | 4590022428_002 | 110013.4 | Low Voltage | CO
|  | F21-P1_ Relocation speed gate at west te | 4590022428_003 | 99501 | Low Voltage | CO
|  | GC_Consumables_F21P1 GC 6" Rupture Disk | 4590023708 | 9585.5 | Chemical | CO
|  | F21 P1 WH CCTV / ACS System requirement | 4590023789 | 53354.76 | Low Voltage | CO
|  | GC_Consumables_F21P1 GC TS135 Valve | 4590023864 | 7008 | Chemical | CO

## AR & AP Real 0804
Type | TSMC Depart | Type 2 | Main Page | PM | Engineer | Sponsor | PO # | Project # | Project Name | Total Contract $ | Tax | PO Date | Tax Code | Payment Term | Total AR (Sent) | Total AR (till Mar | Total AR (Received) | AR % | Open Balance | Before Sep Real | Before Sep Real Tax | 21-Sep Real | 21-Sep Real Tax | Oct-21 Real | Oct-22 tax | Nov-21 Real | Nov-21 Tax | Dec-21 Real | Dec-21 Tax | Dec-21 Draft invoice (first time draft invoice-- 12/22/2021 submitted) Jan Formal Invoice | Dec-21 Draft invoice Tax | Jan-22 Draft invoice Real | Jan-22 Real Tax | Feb-22 Draft | Feb-22 Draft Tax | Mar-22 Draft | Mar-22 Draft Tax | Apr-22 Draft | April-22 Draft Tax | May-22 Draft Plan | May-22 Draft Tax | Jun-22 Draft Plan | Jun-22 Draft Tax | Jul-22 Draft Plan | Jul-22 Draft Tax | Aug-22 Draft Plan | Aug-22 Draft Tax | Sep-22 Draft Plan | Sep-22 Draft Tax2 | Oct-22 Draft Plan | Oct-22 Draft Tax | Nov-22 Draft Plan | Nov-22 Draft Tax | Dec-22 Draft Plan | Dec-22 Draft Tax2 | Jan-23 Draft Plan | Jan-23 Draft Tax | Feb-23 Draft Plan | Feb-23 Draft Tax | Mar-23 Draft Plan | Mar-23 Draft Tax | Apr-23 Draft Plan | Apr-23 Draft Tax | May-23 Draft Plan | May-23 Draft Tax | Jun-23 Draft Plan | June-23 Draft Tax | July-23 Draft Plan | July-23 Draft Tax | Aug-23 Draft Plan | Aug-23 Draft Tax | Sep-23 Draft Plan | Sep-23 Draft Tax | Oct-23 Draft Plan | Oct-23 Draft Tax | Nov-23 Draft Plan | Nov-23 Draft Tax | Dec-23 Draft Plan | Dec-23 Draft Tax | Jan-24 Draft Plan | Jan-24 Draft Tax | Feb-24 Draft Plan | Feb-24 Draft Tax | Mar-24 Draft Plan | Mar-24 Draft Tax | Apr-24 Draft Plan | Apr-24 Draft Tax | May-24 Draft Plan | May-24 Draft Tax | Jun-24 Draft Plan | Jun-24 Draft Tax | Jul-24 Draft Plan | Jul-24 Draft Tax | Aug-24 Draft | Aug-24 Draft Tax | Sep-24 Draft | Sep-24 Draft Tax
Others | Non-TSMC |  |  | Cheng-Chi Yeh |  | 宸沅國際股份有限公司 | 330 | USC22L002 | Diaphragm Valve | 179319.7 |  |  |  |  | 179319.7 | 179319.7 | 179319.7 | 1 | 0 | [30 empty] | 179319.7 | [37 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | Elaine Ma |  | Fu Energy | 2957 | USC22C003 | TSMC Fiber Optic Electrical to CUP | 85382 |  | 1/8/2024 |  | 100% by progress, T/T 35 days | 85382 | 0 | 42691 | 1 | 0 | [66 empty] | 8538.2 |  | 0 | 0 | 0 | 0 | 34152.8 | 0 | 0 | 0 | 42691 | 0
Base Build | Non-TSMC |  |  | Elaine Ma | Sam Yan | Fu Energy | 4370 | Expect to add in USC22C003 | TSMC Diesel Pump Power Circuit Relocate(Option#2) | 35911.7 |  | 08/07/2024 |  | 100% by progress, T/T 35 days | 35911.7 | 0 | 35911.7 | 1 | 0 | [73 empty] | 0 | 35911.7 | 0 | 0 | 0
Base Build | Non-TSMC |  |  | Elaine Ma | Sam Yan | Fu Energy | 4371 | Expect to add in USC22C003 | CUP Fiber termination, installation and testing report project | 5830 |  | 08/07/2024 |  | 100% by progress, T/T 35 days | 5538.5 | 0 | 5538.5 | 0.95 | 291.5 | [73 empty] | 0 | 5538.5 | 0 | 0 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC | 4503045358 | USC21C001 | AZ temp office CCTV and metal gate | 110660.61 | Excluded | 2021-01-29 | T9 $5,760.67 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 85997.17 | 85997.17 | 85997.17 | 0.77713 | 24663.44 | 69931.93 | 2329.4 | 0 |  | 13735.84 | 1178.51 | 2329.4 | 200.33 | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  |  |  | Debby | TSMC | 4503243471 | USC21C002 | AZ Temp Office Access Control System/Sp | 145958.4 | Included | 2021-06-03 | U9 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 145958.4 | 145958.4 | 145958.4 | 1 | 0 | 12163.2 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  |  |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 6081.6 |  | 18244.8 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | UPW | Emon | Emon/Chihhao | TSMC, 得威 | 4503290109 | USC21C003 | F21P1 UPW | 156300000 | Exempted | 2021-07-01 | T0 | PU53:95% on progress,5% 1 month after acceptance | 137331490 | 123536555 | 136620731 | 0.87864 | 18968510 |  |  | 6276241 |  |  |  | 5065513 |  | 1487521 |  | 379647 |  | 4036610 |  | 516878 |  | 317828 |  | 7096144 |  | 2987853 |  | 7837545 |  | 4616733 |  | 5550939 |  | 4081209 |  | 11973093 |  | 8085514 |  | 5626352 |  | 10066637 |  | 5047629 |  | 3365898 |  | 4810771 |  | 2863211 |  | 3367236 |  | 2303531 |  | 1479982 |  | 2215779 |  | 1432965 |  | 2266418 |  | 2162761 |  | 1783000 |  | 2158063 |  | 2277054 |  | 2753476 |  | 3367559 | 0 | 3932821 | 0 | 2398799 | 0 | 631521 | 0 | 710759 | 0
Base Build | 新工 |  | WWT | Jim Chiang | Thomas | TSMC, 得威 | 4503312319 | USC21C004 | F21P1 WWT package (USA EQ - FRP tank) | 6158273 | Exempted | 2021-07-14 | T0 | PU53:95% on progress,5% 1 month after acceptance | 5841555 | 5806030 | 5841555 | 0.94857 | 316718 |  |  | 0 |  | 487307 |  | 495498 |  | 199596 |  |  |  | 128965 |  | 16562 |  | 179823 |  | 134233 |  | 321235 |  | 0 |  | 429331 |  | 96518 |  | 709523 |  | 554350 |  | 312613 |  | 828523 |  |  |  | 427572 |  | 25093 |  |  |  | 15442 |  | 406933 |  | 30038 | [13 empty] | 6875 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 35525 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Shannon | Shannon | TSMC, 得威 | 4503398624 | USC21C010 | Water pipeline installation (size>4") | 5723522 | Exempted | 2021-09-01 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 5723522 | 5432755 | 5723522 | 1 | 0 |  |  | 0 |  | 448439 |  | 872546 |  | 506260 |  |  |  | 1933308 |  |  |  | 1363400 |  | 308802 | [47 empty] | 290757 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Shannon | Shannon | TSMC, 得威 | 4503423409 | USC21C010 | Water pipeline installation (size<4") | 776478 | Excluded | 2021-09-14 | T5 $43,405.12 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 776478 | 711409 | 776478 | 1 | 0 |  |  | 0 |  | 42121 | 2355 | 69335 | 3876 | 220657 | 12335 |  |  | 67848 | 3793 |  |  | 170593 | 9536 | 140855 | 7874 | [46 empty] | 65069 | 3637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu | Herny | TSMC, 敏宏 | 4503428513 | USC21C006 | F21P1 Slurry package | 38600000 | Exempted | 2021-09-16 | T0 | AP03:Pay in month end - 1 month after acceptance month | 27085687 | 17590353 | 27085687 | 0.7017 | 11514313 |  |  | 0 |  |  |  | 2842182 |  | 615582 | [9 empty] | 1814673 |  |  |  | 0 |  | 186997 |  | 429332 |  | 92956 |  | 368183 |  | 961562 |  | 448503 |  | 743804 |  | 1737663 |  | 1457780 |  | 1205933 |  | 474955 |  | 305019 |  | 668418 |  | 682143 |  | 832221 |  | 356993 |  | 274002 |  | 594077 |  |  |  | 497375 |  |  |  | 254357 |  | 3716767 | 0 | 3216752 | 0 | 1138303 | 0 | 1169155 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Jim Chiang | Thomas/Grant/呂方仁 | TSMC, 得威 | 4503432118 | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 148422680 | Exempted | 2021-09-17 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 133123705.53 | 108160436.72 | 130547468.38 | 0.89692 | 15298974.47 |  |  | 0 |  |  |  | 5659407.87 |  | 3446491.85 |  | 2546942 |  |  |  | 3745119 |  | 429850 |  | 3061109 |  | 1239891 |  | 7300329 |  | 1611191 |  | 922329 |  | 8199264 |  | 6713178 |  | 9229107 |  | 2943530 |  | 9312377 |  | 9959442 |  | 4272044 |  | 3410516 |  | 3130489 |  | 3274236 |  | 3191079 |  | 2642440 |  | 2532686 |  | 2117488 |  | 2076652 |  | 1879030 |  | 1296094 |  | 1385684 |  | 632441 |  | 3866171 |  | 10560920 | 0 | 4315186 | 0 | 962959.46 | 0 | 2681795.2 | 0 | 2576237.15 | 0
Base Build | 新工 |  | WWT | Jim Chiang | Jim | TSMC, 得威 | 4503432152 | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 7309837 | Exempted | 2021-09-17 | T0 | PU53:95% on progress,5% 1 month after acceptance | 6780900 | 6681569 | 6780900 | 0.92764 | 528937 |  |  | 0 |  |  |  | 72391 |  |  |  | 280642 |  |  |  | 290846 | [7 empty] | 0 |  | 0 |  | 558808 |  | 324161 |  | 505269 |  | 203422 |  | 511978 |  | 270268 |  | 72680 |  | 214996 |  | 85984 |  | 4875 |  | 1035087 |  | 47716 |  | 1069415 |  | 83419 |  | 153210 |  | 156441 |  |  |  | 311760 |  | 337419 |  | 90782 |  |  |  | 99331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4503441102 | USC21C008 | F21 CCTV & Security | 12680000 | Excluded | 2021-09-24 | T5 $708,812 | PU53:95% on progress,5% 1 month after acceptance | 10255565 | 8948545 | 10190780 | 0.8088 | 2424435 |  |  | 0 | [5 empty] | 1479412 | 82699 | [10 empty] | 588386 | 32890.7774 | 283308 | 15837 | 108202 | 6048 |  |  | 143300 | 8010 | 101643 | 5682 | 108039 | 6039 |  |  | 952851 | 53264 | 1208945 | 67580 | 764496 | 42735 | 729037 | 40753 | 623811 | 34871 | 140984 | 7881 | 220920 | 12349 | 49185 | 2749 | 402028 | 22473 | 319150 | 17840 | 225390 | 12599 |  |  | 281975 | 15762 | 108839 | 6084 | 108644 | 6073 | 181902 | 10168 | 387660 | 21670 | 183655 | 10266 | 178362 | 9970 | 310656 | 17366 | 64785 | 3622
Base Build | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4503441308 | USC21C012 | F21P1 Barcode & RFID for manufacturing | 5792291 | Exempted | 2021-09-24 | T0 | PU53:95% on progress,5% 1 month after acceptance | 2551826 | 2240327 | 2551826 | 0.44056 | 3240465 |  |  | 0 | [5 empty] | 825712 | [7 empty] | 344428 | [5 empty] | 399685 | [21 empty] | 301844 | [13 empty] | 368658 | [7 empty] | 202144 |  | 0 | 0 | 0 | 0 | 109355 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu | Dahlia | TSMC, Grant Shih <YUSHIH@TSMC.COM> | 4503448403 | USC21C007 | F21P1 VOC package (Installation) | 18681999 | Exempted | 2021-09-29 | T0 | PU53:95% on progress,5% 1 month after acceptance | 17747899.4923 | 15500010.3123 | 17747899.49 | 0.95 | 934099.5077 |  |  | 0 |  |  |  | 1366240 | [15 empty] | 0 |  | 0 |  | 337426 |  | 359447 |  | 1192072 |  | 2473832 |  | 1059498.1123 |  | 1333111.13 |  | 1570604.13 |  | 1237227.13 |  | 1196108.18 |  | 596599.54 |  | 238553 |  | 31469 | [9 empty] | 1814716 |  |  |  | 693107.09 | [5 empty] | 2247889.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Jim Chiang | Jim | TSMC, 得威 | 4503489979 | USC21C014 | F21P1 W-H2SO4 package | 3270594 | Exempted | 2021-11-02 | T0 | PU53:95% on progress,5% 1 month after acceptance | 3107114 | 2552717 | 3065445 | 0.95002 | 163480 |  |  | 0 | [5 empty] | 122338 | [17 empty] | 142970 |  | 0 |  | 95196 |  | 75482 |  | 0 |  | 0 |  | 0 |  | 169120 |  | 380781 |  | 219971 |  | 545283 |  |  |  | 83783 |  | 325414 |  |  |  | 60193 | [7 empty] | 332186 |  |  |  | 176108 | 0 | 0 | 0 | 0 | 0 | 336620 | 0 | 41669 | 0
Others | Non-TSMC |  | Micron | Elaine Ma |  | Micron US | 4513455889 | USC24C001 | SOLBLE RN3000 - 250KG DRUM for Boise ID | 32397.42 |  | 01/08/2024 |  | Current Month End +60 days | 32397.42 | 32397.42 | 32397.42 | 1 | 0 | [64 empty] | 32397.42 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  | Micron | Elaine Ma |  | Micron US | 4513459035 | USC24C001 | SOLBLE RN3000 - 500KG,DRUM for Manassas VA | 63748.8 |  | 01/05/2024 |  | Current Month End +60 days | 63748.8 | 63748.8 | 63748.8 | 1 | 0 | [64 empty] | 63748.8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  | Micron | Elaine Ma |  | Micron US | 4514041973 | USC24C001 | SOLBLE RN3000 - 1000KG,DRUM for Manassas VA | 127497.6 |  | 06/05/2024 |  | Current Month End +60 days | 127497.6 | 0 | 127497.6 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 127497.6 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  | Micron | Elaine Ma |  | Micron US | 4514043525 | USC24C001 | SOLBLE RN3000 - 2024 forecast for Manassas VA | 318744 |  | 06/18/2024 |  | Current Month End +60 days | 0 | 0 | 0 | 0 | 318744 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 | Settlement | Low Voltage | Paul Hsu | Shawn | TSMC, Edward | 4590000334 | USC22C010 | F21P1 LV PDS on site installation | 188291.52 | Excluded | 2022-03-24 | T2 $10525.495968 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 188291.52 | 175584 | 188291.52 | 1 | 0 | [28 empty] | 37662 | 2105.31 | 115148 | 6436.77 | 22774 | 1273.07 | [34 empty] | 12707.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma | Ning | TSMC, Michael Lin/Lim | 4590000425 | USC22C005 | F21P1-0404_H_UPW_MIC | 2372512 | Excluded | 2022-03-30 | U0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 2359620 | 2359620 | 2359620 | 0.99457 | 12892 | [30 empty] | 474502 | 26525 |  |  |  |  | 341589 |  | 536466 |  |  |  | 563888 |  | 172568 | [5 empty] | 270607 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma | Ning | TSMC, Michael Lin/Dennis | 4590000428 | USC22C005 | F21P1-0404_H_Chemical_MIC | 4892414.09 |  | 2022-03-30 | U0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 4096793.06 | 3969727 | 4096793.06 | 0.83738 | 795621.03 | [36 empty] | 1471475 |  | 146491 |  | 120254 |  | 1283526 |  | 218714 |  |  |  | 729267 | [19 empty] | 44868.16 | 0 | 82197.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590000539 | USC22C001 | US Fab Warehouse Security & CCTV | 1906859 | Excluded | 2022-04-08 | T5 $106593 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 1735978 | 1530535 | 1686610 | 0.91039 | 170881 | [20 empty] | 43656 | 2440 | 216614 | 12109 | [12 empty] | 56875 | 3179 |  |  |  |  | 585562 | 32733 | 475204 | 26564 | 100565 | 5622 | 52059 | 2910 | [6 empty] | 0 | 0 | [8 empty] | 53021 | 2964 | 0 | 0 | 47531 | 2657 | 0 | 0 | 55523 | 3104 | 49368 | 2760
Base Build | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590000540 | USC22C001 | F21P1 Office Security & CCTV Packag | 7311604 | Excluded | 2022-04-08 | T5 $408718.66 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 6021517 | 5384498 | 5891827 | 0.82356 | 1290087 | [20 empty] | 333768 | 18658 | 869352 | 48597 | 195224 | 10913 |  |  | 931566 | 52075 | 673864 | 37669 | 606925 | 33927 | 451712 | 25251 | 379174 | 21196 | 273104 | 15267 | 232977 | 13023 |  |  |  |  | 248175 | 13873 | 111220 | 6217 | 0 | 0 | [10 empty] | 60184 | 3364 | 17253 | 964 | 17865 |  | 0 | 0 | 489464 | 27361 | 0 | 0 | 0 | 0 | 129690 | 7250
Base Build | 新工 | Settlement | Low Voltage | Paul Hsu | Shawn | TSMC, Edward | 4590000624 | USC22C009 | F21P1 MTR oil & drain pipe work | 408000 | Excluded | 2022-04-14 | T5 $22807.2 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 393603 | 393603 | 393603 | 0.96471 | 14397 | [28 empty] | 31440 | 1758 |  |  |  |  | 147874 | 8266 | [22 empty] | 214289 | 11979 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  |  | Kate | Wan-chun | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590000896 | Expect to add in USC22C017 | CAP_SP1_3D繪圖人力 | 86940 | Excluded | 2022-05-02 | UX | PU53:95% on progress,5% 1 month after acceptance | 86940 | 86940 | 86940 | 1 | 0 | [32 empty] | 0 |  | 0 |  | 0 | [5 empty] | 86940 | [21 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma | Ning | TSMC, Michael Lin/Lim | 4590001034 | USC22C005 | F21P1-0404E2_H_UPW_MIC | 293365 |  | 2022-05-12 | U0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 272543 | 272543 | 272543 | 0.92902 | 20822 | [32 empty] | 54516 |  |  |  | 128017 |  | 63888 |  |  |  | 23717 |  | 2405 | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Chihhao | TSMC, 威昂 | 4590001827 | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃exhasut (labor) | 400241.45 | Exempted | 2022-06-14 | T0 | PU53:95% on progress,5% 1 month after acceptance | 299830.94 | 108812 | 108812 | 0.74913 | 100410.51 | [44 empty] | 5443 |  | 103369 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 191018.94 | 0 | 0 | 0
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Chihhao | TSMC, 威昂 | 4590001828 | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃exhasut (material) | 250352.96 | Excluded | 2022-06-14 | T1 | PU53:95% on progress,5% 1 month after acceptance | 147065.63 | 107236 | 107236 | 0.58743 | 103287.33 | [48 empty] | 107236 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 39829.63 | 0 | 0 | 0
HK | HK |  |  | Kate | Wan-chun | TSMC, Kenneth Toliver | 4590002149 | USC23C022 | F21P1_H_2D/3D drawing | 964420.34 | Excluded | 2022-06-22 | TX | AZ03:Pay in month end - 1 month after acceptance month | 964420 | 964420 | 964420 | 1 | 0.34 | [34 empty] | 150107 |  | 128264 |  | 134693 |  | 187266 |  | 130056 | [13 empty] | 234034 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590002290 | USC22C013 | F21P1 QR Lab Security & CCTV | 424087.84 | Excluded | 2022-06-24 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 393331.02 | 281599.4 | 370417.39 | 0.92748 | 30756.82 | [52 empty] | 144305 | 8067 | 42087 | 2353 |  |  | 17252.74 | 964.43 | 67914.65 | 3796.43 | 10040.01 | 561.24 |  |  |  |  | 0 | 0 | 34986.85 | 1955.76 | 23506.37 | 1314.01 | 30324.77 | 1695.15 | 22913.63 | 1280.87
FAB Requirement (FAC) | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590002291 | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 64539.43 | Excluded | 2022-06-24 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 61957.85 | 56033.69 | 61957.85 | 0.96 | 2581.58 | [56 empty] | 23331.42 | 1304.23 |  |  |  |  | 12199.89 | 681.97 | 20502.38 | 1146.08 |  |  | 0 | 0 | 0 | 0 | 5924.16 | 331.16 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 杜之雄 | 4590002292 | USC22C013 | Security&CCTV Package_CCD | 306397.9 |  | 2022-06-24 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 288630.39 | 258616.28 | 279250.93 | 0.94201 | 17767.51 | [52 empty] | 142893 | 7988 |  |  |  |  | 46614.39 | 2605.74 | 69108.89 | 3863.19 | [6 empty] | 20634.65 | 1153.48 | 0 | 0 | 0 | 0 | 0 | 0 | 9379.46 | 524.31
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Chihhao | TSMC, 威昂 | 4590002743 | USC22C012 | CAP_A_MFG_freight and labor fee for F21 | 385345.09 | Excluded | 2022-06-28 | T1 & TX | PU53:95% on progress,5% 1 month after acceptance | 41434.12 | 38663.94 | 38663.94 | 0.10752 | 343910.97 | [44 empty] | 14815.65 | [13 empty] | 23848.29 | [9 empty] | 0 | 0 | 0 | 0 | 2770.18 | 0 | 0 | 0 | 0 | 0
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Chihhao | TSMC, 威昂 | 4590002744 | USC22C012 | CAP_A_MFG_F21 mask room related stainles | 457826.04 | Excluded | 2022-06-28 | T1 | PU53:95% on progress,5% 1 month after acceptance | 67676.66 | 59333.3 | 67676.66 | 0.14782 | 390149.38 | [44 empty] | 43093.63 | [13 empty] | 16239.67 | [9 empty] | 0 | 0 | 0 | 0 | 8343.36 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Tony Clark |  | TSMC | 4590002851 | USC23C023 | F21P1_H_pre-construction_MICU | 100880.34 | Excluded | 2022-06-30 | TX | AZ03:Pay in month end - 1 month after acceptance month | 100880.34 | 100880.34 | 100880.34 | 1 | 0 | [38 empty] | 100880.34 | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 製造 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 威昂 | 4590002960 | USC22C013 | CAP_A_MFG_F21P1 All 零星工程_SecurityCCTV Pa (labor) | 537636.33 | Included (labor exempt and material taxable) | 2022-06-30 | TX | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 191773.16 | 0 | 191773.16 | 0.3567 | 345863.17 | [56 empty] | 0 | 0 | [10 empty] | 0 | 0 | 191773.16 | 10720.12 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 製造 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 威昂 | 4590002961 | USC22C013 | CAP_A_MFG_F21P1 All 零星工程_SecurityCCTV Pa (material) | 318208.52 | Included (labor exempt and material taxable) | 2022-06-30 | TX | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 123024.65 | 0 | 123024.65 | 0.38662 | 195183.87 | [56 empty] | 0 | [11 empty] | 0 | 0 | 123024.65 | 6877.08 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Chihhao | TSMC, 威昂 | 4590003431 | USC22C012 | CAP_A_MFG_F21 不鏽鋼儲放光罩二門單面氣體排氣櫃 (labor) | 86306.18 | Included (labor exempt and material taxable) |  | T5 | AZ03:Pay in month end - 1 month after acceptance month | 32144 | 32144 | 32144 | 0.37244 | 54162.18 | [44 empty] | 5100 | [9 empty] | 27044 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Chihhao | TSMC, 威昂 | 4590003432 | USC22C012 | CAP_A_MFG_F21 不鏽鋼儲放光罩二門單面氣體排氣櫃 (material) | 47935.47 | Included (labor exempt and material taxable) |  | T5 | AZ03:Pay in month end - 1 month after acceptance month | 18486 | 0 | 0 | 0.38564 | 29449.47 | [54 empty] | 0 | [11 empty] | 18486 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, 陳嘉宏/Stanley Chen/052598/F21-AMHS/7713511 | 4590003763 | USC22C017 | CAP_E_F21P1_AMHS Power Design | 174794.05 | Exempted | 2022-07-28 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 174794.05 | 126287.92 | 174794.05 | 1 | 0 | [32 empty] | 0 |  | 83027.38 | [5 empty] | 0 | [5 empty] | 32773.44 | [17 empty] | 10487.1 |  | 0 |  | 0 | 0 | 0 | 0 | 48506.13 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu | Herny | TSMC, 曜安 | 4590003895 | USC21C006 | F21P1 Slurry Package support frame | 668104 | Exempted | 2022-08-03 | T0 | AZ53:95% on progress,5% 1 month after acceptance | 668104 | 599505 | 668103.61 | 1 | 0 | [36 empty] | 36498 |  |  |  | 270748 | [23 empty] | 292259 |  |  |  | 34621 | 0 | 0 | 0 | 33978 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma | Ning | TSMC, Michael Lin/Lim | 4590003912 | USC22C005 | F21P1-0420E4_H_UPW_MIC | 586718.13 | Exempted | 2022-08-03 | T0 | AZ03:Pay in month end - 1 month after acceptance month | 586718.13 | 586718.13 | 586718.13 | 1 | 0 | [40 empty] | 117343.63 |  | 77330.3 |  | 170487.1 |  | 21584.31 |  | 134405 |  | 46189.95 |  | 19377.84 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 製造 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 蘇明秋/Vince | 4590003997 | USC22C013 | Security & CCTV Package OWMC | 179299.89 | Excluded | 2022-08-09 | T1 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 90541.86 | 90541.86 | 90541.86 | 0.50497 | 88758.03 | [54 empty] | 0 | 0 | 48335.76 |  |  |  | 42206.1 | 2359.32 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Dahlia | TSMC,Anson Lin 林國聖 | 4590003998 | USC22C019 | CAP_A_90431 AMC monitor 595T0 | 1648034.25 | Exempted | 2022-08-09 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 1648034.25 | 1648034.25 | 1648034.25 | 1 | 0 | [54 empty] | 0 |  | 0 |  | 0 |  | 1469390.15 |  |  |  | 178644.1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | UPW | Emon | Emon | TSMC, 得威 | 4590004028 | USC21C003 | F21P1 QR Lab UPW | 762160.23 | Exempted | 2022-08-11 | T0 | AZ03:Pay in month end - 1 month after acceptance month | 685961.92 | 558420.28 | 685961.92 | 0.90002 | 76198.31 | [30 empty] | 104411.2 |  | 238101.12 | [7 empty] | 159324.52 | [9 empty] | 56583.44 | [17 empty] | 89716.63 | 0 | 21676.79 | 0 | 16148.22 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | WWT | Jim Chiang | Grant | TSMC, 得威 | 4590004029 | USC21C009 | F21P1 QR Lab WWT | 3027439.77 | Exempted | 2022-08-11 | T0 | AZ03:Pay in month end - 1 month after acceptance month | 2760174.15 | 2751323.91 | 2760174.15 | 0.91172 | 267265.62 | [38 empty] | 298305 |  | 764067 | [19 empty] | 500770 |  | 1059798 |  | 128383.91 |  | 8850.24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, 陳嘉宏/Stanley Chen/052598/F21-AMHS/7713511 | 4590004044 | USC22C014 | F21P1_AMHS_Power Panel | 2118750 | Exempted | 2022-08-12 | T0 | AZ53:95% on progress,5% 1 month after acceptance | 2118750 | 1101750 | 2118750 | 1 | 0 | [32 empty] | 423750 |  | 211875 | [11 empty] | 466125 | [17 empty] | 0 |  | 0 |  | 1017000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | Chemical | Steven Chiu | Johnny Wan | TSMC, 敏宏 | 4590004117 | USC23C042 | F21P1 Chemical safety cabinet installation | 48875 | Exempted | 2022-08-17 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 43988 | 43988 | 43988 | 0.90001 | 4887 | [48 empty] | 26722 |  |  |  | 17266 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590004118 | USC22C034 | F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/N2/APK/UPK/ASRS | 106129.6 | Exempted | 2022-08-17 | T0 | AZ53:95% on progress,5% 1 month after acceptance | 81871.19 | 47758.32 | 81871.19 | 0.77143 | 24258.41 | [34 empty] | 47758.32 |  |  |  | 0 | [25 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 34112.87 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590004119 | USC22C031 | CAP_E_F21P1 APKUPK Foundation | 26897.02 | Exempted | 2022-08-17 | T0 | AZ53:95% on progress,5% 1 month after acceptance | 26897.02 | 26897.02 | 26897.02 | 1 | 0 | [62 empty] | 26897.02 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | UPW | Steven Chiu | Johnny Wan/Sun Ling | TSMC, 敏宏 | 4590004281 | USC22C021 | F21P1 Chemical Lab setup | 504415.82 | Exempted | 2022-08-25 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 461855.4867 | 461855.4867 | 461855.49 | 0.91562 | 42560.3333 | [42 empty] | 74192 | [11 empty] | 336271.4867 |  | 51392 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 吳光鈞 | 4590004606 | USC22C013 | F21 Pump storage area CCTV construction | 10738 |  |  |  |  | 0 | 0 | 0 | 0 | 10738 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | 光阻櫃 | Paul Hsu | Johnny Yang | TSMC, 張盈淳 | 4590004607 | USC22C013 | F21 Pump storage area construction | 26933.83 |  |  |  |  | 0 | 0 | 0 | 0 | 26933.83 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | 光阻櫃 | Paul Hsu | Johnny Yang | TSMC, 張盈淳 | 4590004608 | USC22C013 | F21 Pump storage area construction | 3364.56 |  |  |  |  | 0 | 0 | 0 | 0 | 3364.56 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590004610 | USC22C013 | F21P1 FAB Lab Security & CCTV_Stage2 | 112375.63 |  | 2022-09-01 | TX | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 67615 | 67615 | 67615 | 0.60169 | 44760.63 | [64 empty] | 67615 | 3779.68 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn | TSMC, 戴宇平<YPTAIA@tsmc.com> | 4590004636 | USC22C035 | CAP_A_90772_簡訊平台 | 224414.81 |  |  |  |  | 219227.77 | 0 | 219227.77 | 0.97689 | 5187.04 | [66 empty] | 219227.77 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Johnny Yang | TSMC, 威昂 | 4590004646 | USC22C012 | (522/0%) F21 barcode reader 搬運定位 | 5300 |  |  |  |  | 0 | 0 | 0 | 0 | 5300 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Chihhao | TSMC, 威昂 | 4590004647 | USC22C012 | 光罩讀取機搬運安裝定位_buyer 洪薇甯 | 2172.5 |  | 2022-09-01 | T0 | AP01:Pay in month end - 1 month after delivery month | 0 | 0 | 0 | 0 | 2172.5 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | WWT | Jim Chiang | Thomas | TSMC, 得威 | 4590004971 | USC21C009 | F21P1 Discharge monitoring change | 626000 |  | 2022-09-13 | U9 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 441418 | 409882 | 441418 | 0.70514 | 184582 | [32 empty] | 33076 | 1849 | [6 empty] | 54072 |  |  |  | 0 |  | 244801 |  |  |  | 5592 | [5 empty] | 72341 | [11 empty] | 0 | 0 | 0 | 0 | 31536 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement |  | Shannon | Debby/Shannon | TSMC, 得威 | 4590005093 | USC22C018 | US Fab Frontage line hydrants | 1228000 | Exempted | 2022-09-15 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 1228000 | 1228000 | 1228000 | 1 | 0 | [28 empty] | 190340 |  | 14641 | [5 empty] | 839966 |  |  |  | 183053 | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, 傅至傑 | 4590005159 | USC22C028 | CAP_E_F21P1 Autoshelf Foundation | 51628.05 |  |  |  |  | 21277.96 | 21277.96 | 21277.96 | 0.41214 | 30350.09 | [56 empty] | 0 | [7 empty] | 21277.96 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590005167 | USC22C027 | CAP_E_F21P1 Autoshelf Installation 4 set | 225446.4 |  |  |  |  | 112722.88 | 11272 | 112722.88 | 0.5 | 112723.52 | [32 empty] | 11272 | [15 empty] | 0 | [15 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 101450.88 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Chin-Yu Wan/Jeremy Wan/115918/F21-AMHS/7713507 | 4590005172 | USC22C031 | CAP_E_F21P1A_Grating Floor Opening | 1113677.02 |  |  |  |  | 721517.13 | 222735 | 721517.13 | 0.64787 | 392159.89 | [56 empty] | 222735 | [7 empty] | 0 |  | 498782.13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | WWT | Jim Chiang | Grant | TSMC, 得威 | 4590005240 | USC22C020 | F21P1 Penetration Pipe | 1050000 | Excluded | 2022-09-15 | U9 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 621472.81 | 604130.18 | 621472.81 | 0.59188 | 428527.19 | [28 empty] | 176648 | 9874.62 | 132082 | 7383.38 | 42200 | 2358.98 | [18 empty] | 223978 | 12520.37 | 24898.53 | 1391.83 | [8 empty] | 4323.65 | 241.69 |  |  | 0 | 0 | 17342.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Jim Chiang | Jim | TSMC, 得威 | 4590006189 | USC22C022 | F21P1 Triazole treatment system | 4340000 | Exempted | 2022-09-29 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 3895546 | 2095586 | 3895546 | 0.89759 | 444454 | [32 empty] | 258520 | [17 empty] | 248691 |  | 596404 |  | 91781 |  | 118993 |  | 27303 |  | 190243 |  |  |  | 563651 |  | 1636643 |  | 11661 | 0 | 132983 | 0 | 0 | 0 | 18673 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Jim Chiang | Jim | TSMC, Joy/得威 | 4590006293 | USC21C009 | F21P1 CCB Lorry in drain system | 707246 |  |  |  |  | 327541 | 327541 | 327541 | 0.46312 | 379705 | [36 empty] | 42476 | [5 empty] | 87212 |  |  |  | 38596 |  | 159257 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QR | QR |  |  | Hank Su | Hank Su | TSMC, 賴易鋒 | 4590006323 |  | F21_AZQR_Hookup_FdtnLabor | 359204 |  |  |  |  | 0 | 0 | 0 | 0 | 359204 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Chin-Yu Wan/Jeremy Wan/115918/F21-AMHS/7713507 | 4590006628 | USC22C013 | CAP_E_F21 P1 EUV STK CCTV Package_Labor | 290688.3 |  |  |  |  | 57922.32 | 33419.73 | 57922.32 | 0.19926 | 232765.98 | [56 empty] | 33419.73 | 1868.16 | [6 empty] | 0 |  | 0 |  | 24502.59 | 1369.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Chin-Yu Wan/Jeremy Wan/115918/F21-AMHS/7713507 | 4590006629 | USC22C013 | CAP_E_F21 P1 EUV STK CCTV Package 6 sets | 128799.71 |  |  |  |  | 19085.93 | 10901.21 | 19085.93 | 0.14818 | 109713.78 | [56 empty] | 10901.21 | 609.38 | [6 empty] | 0 |  | 0 |  | 8184.72 | 457.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Edwards/Ian/Poh | Michelle H | TSMC, Chien-Hao Hsu | 4590006707 | USC22C026 | F21P1-0423_H_Unistrut Support Frame_MICU | 10906774.78 | Excluded | 2022-10-12 | T9 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 10848813.17 | 10848813.17 | 10848813.17 | 0.99469 | 57961.61 | [30 empty] | 871165 | 74920.24 |  |  |  |  | 3367834.67 |  |  |  | 2766325.5 |  | 3843488 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Jim Chiang | Thomas | TSMC, Joy/得威 | 4590006720 | USC21C009 | F21P1 Formaldehyde treatment system | 700000 | Exempted | 2022-10-12 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 132846 | 132846 | 132846 | 0.18978 | 567154 | [36 empty] | 34259 | [23 empty] | 98587 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Chihhao | TSMC, 威昂 | 4590006743 | USC22C012 | CAP_A_MFG_AZP1 F21 Mask room 集塵罩 + Exhau | 47326.37 |  |  |  |  | 23122 | 23122 | 23122 | 0.48856 | 24204.37 | [48 empty] | 23122 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Tylor | Tylor | TSMC, Fred/Chester | 4590006744 | USC21C003 | F21P1 Tunnel/lorry common support | 6500000 | Exempted | 2022-10-13 | T0 | AZ53:95% on progress,5% 1 month after acceptance | 6500000 | 6175000 | 6500000 | 1 | 0 | [32 empty] | 6175000 | [35 empty] | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, 陳嘉宏/Stanley Chen/052598/F21-AMHS/7713511 | 4590006750 | USC22C025 | CAP_E_F12P1 AMHS Power system_Instrustructure and Branch Circuits | 24500000 | Exempted | 2022-10-13 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 20882965 | 14375488 | 19871841 | 0.85237 | 3617035 | [32 empty] | 2868170 |  | 0 |  |  |  | 0 |  | 0 |  |  |  | 7119456 |  |  |  | 0 |  |  |  | 0 |  | 4134250 |  |  |  | 253612 |  | 0 |  |  |  | 0 |  | 2785485 |  | 992071 | 0 | 1228501 | 0 | 0 | 0 | 490296 | 0 | 1011124 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590006814 | USC22C031 | F21P1 Partition Opening Panel Tray | 437000 |  |  |  |  | 357880 | 296095 | 353740 | 0.81895 | 79120 | [56 empty] | 158250 |  |  |  | 0 |  |  |  | 137845 |  | 27055 |  | 0 | 0 | 25300 | 0 | 5290 | 0 | 0 | 0 | 4140 | 0
EBO | EBO |  | Low Voltage | Paul Hsu | Jaivan | TSMC, Chih Ching Lin | 4590006871 | USC21C013 | F21P1 EBO AMC Monitor system | 941126 |  |  |  |  | 941126 | 218639 | 821446 | 1 | 0 | [64 empty] | 218639 |  | 259718 |  | 212785 | 0 | 130304 | 0 | 0 | 0 | 119680 | 0 | 0 | 0
Fab Work | 製造 |  |  | Hank Su | Hank Su | TSMC, 威昂 | 4590007564 | USC22C012 | CAP_A_MFG_AZP1 F21 Mask room P1A + P1B f | 1557 |  |  |  |  | 0 | 0 | 0 | 0 | 1557 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | WWT | Jim Chiang | Jim | TSMC, Joy/得威 | 4590007599 | USC22C011 | F21P1 WRC Exterior Pad (NH3&Diesel tank) | 2480033 | Exempted | 2022-10-21 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 2380831.78 | 2380831.78 | 2380831.78 | 0.96 | 99201.22 | [32 empty] | 2124000 |  | 232030 | [27 empty] | 24801.78 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590007785 | USC22C031 | CAP_E_F21P1 AMHS MML seismic foundation design | 47460 | Exempted | 2022-10-28 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 47460 | 47460 | 47460 | 1 | 0 | [40 empty] | 0 | [5 empty] | 47460 | [17 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, 鄭宇倢/Josie Cheng/108938/F21-AMHS/7713512 | 4590007798 | USC22C031 | CAP_E_F21P1 AMHS non-MML seismic foundation install | 377825.6 |  | 2022-10-28 | T0 |  | 111872 | 0 | 111872 | 0.29609 | 265953.6 | [40 empty] | 0 | [5 empty] | 0 | [9 empty] | 0 | [7 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 111872 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | WWT | Jim Chiang | Jim | TSMC, Joy/得威 | 4590008082 | USC21C011 | TMAH ACF system expansion | 4770930 |  | 2022-11-04 | U9 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 2278211 | 838436 | 1494630 | 0.47752 | 2492719 | [36 empty] | 543706 | [21 empty] | 177982 |  |  |  | 116748 |  |  |  | 148812 |  | 119205 | 0 | 388177 | 0 | 0 | 0 | 0 | 0 | 783581 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590008087 | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation Material | 162769 |  |  |  |  | 162769 | 162769 | 162769 | 1 | 0 | [36 empty] | 32554 | [21 empty] | 130215 | [5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBO | EBO |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590008115 | USC22C013 | F21P1 EBO Security & CCTV system | 164514.36 |  |  |  |  | 119231.3 | 69266 | 119231.3 | 0.72475 | 45283.06 | [56 empty] | 69266 | 3872 | [8 empty] | 13358.49 | 716.85 | 6732.13 | 0 | 0 | 0 | 0 | 0 | 29874.68 | 1664.65 | 0 | 0
EBO | EBO |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590008116 | USC22C013 | F21P1 EBO Security CCTV system_material | 99351.1 |  |  |  |  | 88925.86 | 55726 | 88925.86 | 0.89507 | 10425.24 | [56 empty] | 55726 | 3115 | [8 empty] | 12206.62 | 647.54 | 0 | 0 | 0 | 0 | 0 | 0 | 20993.24 | 1169.63 | 0 | 0
QR | QR |  |  | Hank Su | Hank Su | TSMC | 4590008129 | USC22C030 | F21_AZCHAD_Hookup_ temp PVC curtain | 23257.83 |  |  |  |  | 23257.83 | 23257.83 | 23257.83 | 1 | 0 | [38 empty] | 23257.83 | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590008147 |  | CAP_E_F21 P1 APK UPK PV CV GEX | 19201 |  |  |  |  | 0 | 0 | 0 | 0 | 19201 | [64 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | UPW | Emon | Chihhao | TSMC, Sabrina Cervante | 4590008170 | USC22C021 | F21P1 Chemical Lab Hookup | 507650 |  |  |  |  | 197729.21 | 139168.01 | 197729.21 | 0.3895 | 309920.79 | [56 empty] | 14852 |  | 75865.81 |  | 8925.39 |  | 39524.81 | [5 empty] | 0 | 0 | 0 | 0 | 58561.2 | 0 | 0 | 0 | 0 | 0
Logistic | HK |  |  | Paul Verna | Paul Verna | TSMC | 4590008191 | USC22C008 | MISC_(TAX/U1)_Onsite crating job | 6340 |  |  |  |  | 6340 | 6340 | 6340 | 1 | 0 | [40 empty] | 6340 | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ISEP | ISEP |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 黃士軒 | 4590008207 | USC22C033 | F21 ESP equipment(include labor fee) | 12226 | Excluded | 2022-11-14 | T1 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 5506 | 5506 | 5506 | 0.45035 | 6720 | [48 empty] | 5506 | 1051 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | WWT | Elaine Ma | Ning | TSMC, 得威 | 4590008240 | USC22C023 | F21P1 Piping Material Collaboration | 3042902.07 |  |  |  |  | 3042902.07 | 3042902.07 | 3042902.07 | 1 | 0 | [34 empty] | 2492280.07 |  |  |  | 550622 | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement |  | Elaine Ma | Kuanchun | TSMC, 崔紘瑞 | 4590008319 | USC23C014 | F21P1 Labor incentive program-MICU | 1625000 |  |  |  |  | 821051 | 821051 | 821051 | 0.50526 | 803949 | [36 empty] | 355581 | [5 empty] | 293555 |  | 171915 | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBO | EBO | Foundation |  | Hank Su | Hank Su | TSMC, A.C. Lee 黎安成 <ACLEE@TSMC.COM> | 4590008486 | USC23C002 | EBO-21 Tool foundation installation labo | 954136.5 |  |  |  |  | 561100 | 270404 | 561100 | 0.58807 | 393036.5 | [50 empty] | 270404 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290696 | 0
HK | HK | Foundation |  | Hank Su | Hank Su | TSMC, Grant | 4590008674 | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 327419.43 |  |  |  |  | 300145 | 300145 | 300145 | 0.9167 | 27274.43 | [38 empty] | 61129 | [5 empty] | 239016 | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma | Ning | TSMC, Han Deng/NFCD | 4590008827 | USC22C005 | F21P1-0423_H_UPW_MICU | 926011.72 |  | 2023-01-11 | T0 | AZ03:Pay in month end - 1 month after acceptance month | 923604.72 | 923604.72 | 923604.72 | 0.9974 | 2407 | [40 empty] | 185202.34 |  | 4405.02 |  | 99676.09 |  | 29325.47 |  | 97673.16 |  | 300813.71 |  | 206508.93 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Emon | Kate | TSMC, 得威 | 4590009036 | USC21C003 | F21P1 UPW Temporary CP and piping | 125975 |  | 2023-01-19 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 125975 | 125975 | 125975 | 1 | 0 | [38 empty] | 8973 |  | 72888 |  | 10155 | [13 empty] | 33959 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 | Foundation |  | Hank Su | Hank Su | TSMC | 4590009148 | USC23C002 | MISC_(522/U0)SU3200 foundation | 35767.3 |  | 2023-02-01 | T0 | AZ03:Pay in month end - 1 month after acceptance month | 35767 | 35767 | 35767 | 0.99999 | 0.3 | [44 empty] | 35767 | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK | Foundation |  | Hank Su | Hank Su | TSMC, Samuel | 4590009466 | USC23C047 | F21P1-0423_H_Seismic installation_MICU | 3463200 |  |  |  |  | 3139500 | 3139500 | 3139500 | 0.90653 | 323700 | [50 empty] | 402225 | [5 empty] | 650478 |  | 0 |  | 375238 |  | 1711559 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBO | EBO | Foundation |  | Hank Su |  | TSMC, 黎安成 | 4590009735 | USC23C047 | EBOAZ Foundation Seismic Installation | 133900 |  |  |  |  | 0 | 0 | 0 | 0 | 133900 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QR | QR | Foundation |  | Hank Su |  | TSMC, 賴易鋒 | 4590009792 | USC23C047 | F21_AZQR_Hookup_Seismic installation | 161320 |  |  |  |  | 0 | 0 | 0 | 0 | 161320 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-Cheng | 4590009808 | USC21C005 | F21P1 CDS package (B.10) | 1270000 |  |  |  |  | 1270000 | 1069803 | 1270000 | 1 | 0 | [46 empty] | 671430 |  | 210597 |  | 69835 |  | 54721 | [11 empty] | 63220 |  |  |  | 0 | 0 | 75742 | 0 | 124455 | 0 | 0 | 0 | 0 | 0
Module Interconnection | 設備 |  | AMHS | David Nystrom | David Short | TSMC, H.H. Pan 潘信華 <HHPAN@TSMC.COM> | 4590009958 | USC23C058 | (RM)_F21_EUV_Steel Plates_1 tool set | 147089.6 |  |  |  |  | 147089.6 | 147089.6 | 147089.6 | 1 | 0 | [42 empty] | 147089.6 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu | Henry Yang | TSMC, 敏宏 | 4590009963 | USC21C006 | F21P1 SDS installation (B.10) | 1949096 |  | 2023-03-23 |  | 95% on progress,5% 1 month after acceptance of the date | 1702853 | 1017194 | 1702853 | 0.87366 | 246243 | [60 empty] | 1017194 | [5 empty] | 615595 |  | 70064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Module Interconnection | 設備 | Foundation |  | Hank Su | Hank Su | TSMC, 張盈淳 | 4590010046 | USC23C002 | KXME02 foundation & seismic installation | 31044.8 |  |  |  |  | 0 | 0 | 0 | 0 | 31044.8 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Module Interconnection | 設備 |  |  | Hank Su | Hank Su | TSMC, 黃國威/CVD | 4590010362 | USC23C002 | F21CVD1+2 barricade request | 6429.12 |  |  |  |  | 6429.12 | 6429.12 | 6429.12 | 1 | 0 | [64 empty] | 6429.12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, 鄭宇智/DIF < | 4590010363 | USC23C002 | MISC_(TAX/U1)single tile barricade | 3214.58 |  |  |  |  | 0 | 0 | 0 | 0 | 3214.58 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Module Interconnection | 設備 |  |  | Hank Su | Hank Su | TSMC, 劉宜鈞/WET | 4590010393 | USC23C002 | MISC_(TAX/T1) WET single barricade | 4821.87 |  |  |  |  | 0 | 0 | 0 | 0 | 4821.87 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, 林國聖/LITHO <kslinb@tsmc.com> | 4590010394 | USC23C002 | MISC_(21417931_tax/T1)Single barricade | 4821.87 |  |  |  |  | 4821.87 | 4821.87 | 4821.87 | 1 | 0 | [62 empty] | 4821.87 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Module Interconnection | 設備 |  |  | Hank Su | Hank Su | TSMC, 連凱泓/ME | 4590010395 | USC23C002 | MISC_AZ TPT(Tax/U1) ME Barricade | 3214.58 |  |  |  |  | 0 | 0 | 0 | 0 | 3214.58 | [62 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, 沈富群/DIF | 4590010397 | USC23C002 | MISC_(TAX/U1)single tile barricade | 3214.58 |  |  |  |  | 3214.58 | 3214.58 | 3214.58 | 1 | 0 | [64 empty] | 3214.58 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, 業富文/ETC | 4590010398 | USC23C002 | MISC_(TAX/T1)_MICU Barricade | 4821.87 |  |  |  |  | 0 | 0 | 0 | 0 | 4821.87 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBO | EBO |  |  | Ning |  | TSMC | 4590010418 | USC22C005 | EBO21-UPW DP parts | 32459.14 |  | 2023-04-25 |  | Pay in month end - 1 month after acceptance month of the date | 32459.14 | 32459.14 | 32459.14 | 1 | 0 | [46 empty] | 6491.83 |  | 2372.78 |  | 11383.67 |  |  |  | 12210.86 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, LWWANG@TSMC.COM | 4590010419 |  | MISC_TAX/U1_Barricade | 3491.02 |  |  |  |  | 0 | 0 | 0 | 0 | 3491.02 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Module Interconnection | 設備 |  |  | Hank Su | Hank Su | TSMC, 吳宗諺/PVD | 4590010420 | USC23C002 | PVD2_Barricade for open tile use | 3491.02 |  |  |  |  | 3491.02 | 3491.02 | 3491.02 | 1 | 0 | [64 empty] | 3491.02 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO_r, Settlement | UPW | Emon | Kate | TSMC, 得威 | 4590010557 | USC21C003 | F21P1 UPW Temporary Resin and piping | 166000 |  | 2023-04-27 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 166000 | 166000 | 166000 | 1 | 0 | [44 empty] | 57388 | [11 empty] | 108612 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, Rosemarie BISQUERA@TSMC.COM | 4590010739 |  | Single Tile Barricade | 4821.84 |  |  |  |  | 0 | 0 | 0 | 0 | 4821.84 | [62 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | IPMD |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 劉啟生 | 4590010774 | USC22C013 | AZ TPT,(565/T0)F21P1_CDC_CCTV(material) | 765747.69 |  |  | tax exempted | 95% on progress,5% 1 month after acceptance of the date | 538489.49 | 489494.45 | 538489.49 | 0.70322 | 227258.2 | [64 empty] | 489494.45 | 27362.74 |  |  | 48995.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | IPMD |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 劉啟生 | 4590010913 | USC22C013 | AZ TPT,(565/T0)F21P1_CDC_CCTV(labor) | 184504.51 |  |  | tax exempted | Pay on 28 next month: 90% on prog, 10 acpt of the date | 143132.66 | 134211.51 | 143132.66 | 0.77577 | 41371.85 | [64 empty] | 134211.51 | 7502.42 |  |  | 8921.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBO | EBO |  |  | Hank Su | Hank Su | TSMC, A.C. Lee 黎安成 <ACLEE@TSMC.COM> | 4590011081 | USC23C002 | EBO21-Single barricade without toe board | 1607.29 |  | 2023-05-18 |  | Pay in month end - 1 month after acceptance month of the date | 1607.29 | 0 | 1607.29 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 1607.29 | 0 | 0 | 0 | 0 | 0
Module Interconnection | 設備 |  |  | Hank Su | Hank Su | TSMC, JJLUA JJLUA@TSMC.COM | 4590011082 | USC23C002 | PVD1_Barricade for open tile use | 3214.58 |  | 2023-05-18 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 3214.58 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, H.H. Pan 潘信華 <HHPAN@TSMC.COM> | 4590011083 | USC23C002 | MISC_[TAX/U1]_F21_EUV_Single barricade_ | 3214.56 |  | 2023-05-18 |  | Pay in month end - 1 month after acceptance month of the date | 3214.56 | 3214.56 | 3214.56 | 1 | 0 | [64 empty] | 3214.56 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, FCSHEN@TSMC.COM | 4590011084 | USC23C002 | MISC_(522/U0) ADI-C-01 Shift foundation | 967.93 |  | 2023-05-18 |  | Pay in month end - 1 month after acceptance month of the date | 967.93 | 967.93 | 967.93 | 1 | 0 | [62 empty] | 967.93 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QR | QR |  |  |  | Ning | TSMC, 賴易鋒 | 4590011098 | USC22C005 | F21 AZQR_Hookup_PVDF material_DP panel | 116175.85 |  |  |  |  | 116175.85 | 112678.08 | 116175.85 | 1 | 0 | [46 empty] | 23235.17 |  | 0 |  | 89442.91 | [17 empty] | 3497.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ISEP | ISEP |  | Low Voltage | Emon | Chihhao | TSMC, Scott Smith/F21-ISEP | 4590011208 | USC23C049 | cabinets transport and installation | 88379 |  | 2023-05-25 |  | Pay in month end - 1 month after acceptance month of the date | 83963 | 34816 | 58328 | 0.95003 | 4416 | [48 empty] | 34816 | [17 empty] | 23512 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25635 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, 黃郁誠/ETC3 | 4590011215 |  | Single barricade | 4821.87 |  | 2023-05-25 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 4821.87 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW |  |  | TSMC, Chi-Wei | 4590011254 | USC21C003 | F21P1 CUP L20 Transformer Pads | 145000 |  | 2023-05-26 |  | 95% on progress,5% 1 month after acceptance of the date | 145000 | 145000 | 145000 | 1 | 0 | [46 empty] | 132459 |  | 12541 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO_r, Settlement | Low Voltage | Paul Hsu | Dahlia | TSMC, 王鄧安 | 4590011320 | USC21C007 | F21P1 VOC Burner NOx improve-installatio | 766999.1 |  | 2023-05-31 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 728614.22 | 603831.63 | 728614.22 | 0.94995 | 38384.88 | [46 empty] | 103519.94 |  | 145337.31 |  | 48145.15 |  | 96525.06 | [5 empty] | 163956.87 | [5 empty] | 46347.3 |  |  |  | 114862.28 | 0 | 9920.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Module Interconnection | 設備 |  |  |  | Boris | TSMC, 莊鎧瑋 | 4590011384 | USC23C048 | F21P1-0423_H_LSC connectors_MICU | 102343.84 |  | 2023-06-02 |  | Pay in month end - 1 month after acceptance month of the date | 102343.84 | 102343.84 | 0 | 1 | 0 | [62 empty] | 102343.84 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, Han Deng/NFCD | 4590012221 |  | F21P1-0423_H_single barricade_MICU | 72698.4 |  | 2023-06-28 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 72698.4 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 | CO_r |  |  | Ning | TSMC | 4590012251 | USC23C040 | F21P1_H_construction gown suit | 130000 |  | 2023-06-29 |  | Pay in month end - 1 month after acceptance month of the date | 130000 | 130000 | 130000 | 1 | 0 | [46 empty] | 121712.5 | 10467.28 | 8287.5 | 712.72 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Hank Su | Hank Su | TSMC, 邱奕豪 | 4590012280 | USC23C002 | MISC_(Tax / U1)_RS200_foundation modify | 4899 |  | 2023-07-04 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 4899 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO_r, Settlement |  |  | Ning | TSMC | 4590012300 | USC23C043 | Electric Tiger Team_Fisk Support & Temp Power | 425398.67 |  | 2023-07-06 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 425398.67 | 425398.67 | 425398.67 | 1 | 0 | [48 empty] | 425398.67 | 23779.79 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO_r, Settlement |  |  | Ning | TSMC, K.H. Pan | 4590012310 | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 135355 |  | 2023-07-06 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 135355 | 135355 | 135355 | 1 | 0 | [48 empty] | 0 |  | 0 |  | 135355 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Hank Su |  | TSMC, 楊力潤 <LJJONG@TSMC.COM> | 4590012460 | USC23C002 | FAC_(600/T9) FX200 Seismic holes enlarge | 1892.66 |  | 2023-07-14 |  | Pay in month end - 1 month after acceptance month of the date` | 0 | 0 | 0 | 0 | 1892.66 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Stanley Chen 陳嘉宏 CHENCHZW@TSMC.COM/ David C.C. Fu 傅至傑 CCFUC@TSMC.COM | 4590012467 | USC23C052 | CAP_E_F21P1_AMHS_Power Panel SWB fingers | 564725.9 |  | 2023-07-14 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 564725.9 | 564725.9 | 564725.9 | 1 | 0 | [62 empty] | 564725.9 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  |  |  | TSMC | 4590012674 | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 10313881 |  |  |  |  | 10313881 | 10313881 | 10313881 | 1 | 0 | [48 empty] | 6500000 | [9 empty] | 3813881 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO_r, Settlement | Chemical |  |  | TSMC, K.S TUNG 董冠昇 <KSTUNG@TSMC.COM> | 4590012687 | USC21C005 | F21P1 CR temp lighting | 84843.78 |  | 2023-07-25 |  | Pay in month end - 1 month after acceptance month of the date | 84843.78 | 84843.78 | 84843.78 | 1 | 0 | [56 empty] | 84843.78 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  |  |  | TSMC, BC<BCTSOU@TSMC.COM> | 4590012793 | USC23C055 | F21P1-0404_H_labor&mobiliz. for 50 tools | 11000000 |  | 2023-08-02 |  | Pay in month end - 1 month after acceptance month of the date | 11000000 | 11000000 | 11000000 | 1 | 0 | [48 empty] | 11000000 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, David C.C. Fu 傅至傑 <CCFUC@TSMC.COM> | 4590012802 | USC22C014 | CAP_E_F21 AMHS L40 Relocation | 21199.81 |  | 2023-08-04 |  | 95% on progress,5% 1 month after acceptance of the date | 21199.81 | 21199.81 | 21199.81 | 1 | 0 | [50 empty] | 21199.81 | [8 empty] | 21199.81 |  |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO_r, Settlement | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-Cheng | 4590012855 | USC21C005 | F21P1 Chemical Solvent day tank add vent | 490000 |  | 2023-08-10 |  | 95% on progress,5% 1 month after acceptance of the date | 451251 | 227355 | 397242 | 0.92092 | 38749 | [62 empty] | 227355 | [5 empty] | 0 | 0 | 0 | 0 | 118691 | 0 | 51196 | 0 | 54009 | 0
Base Build | 新工 | CO, Settlement | WWT | Andy Chen | Jim | TSMC | 4590012872 | USC21C009 | F21P1 WWT construction temp power | 408000 |  | 2023-08-15 |  | 95% on progress,5% 1 month after acceptance of the date | 408000 | 408000 | 408000 | 1 | 0 | [52 empty] | 408000 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Edward |  | TSMC, Michael Lin <MLINL@TSMC.COM> | 4590012881 | USC23C041 | F21P1-0404_H_cable tray/AC box install | 508031.05 |  | 2023-08-16 |  | Pay in month end - 1 month after acceptance month of the date | 508031.05 | 508031.05 | 508031.05 | 1 | 0 | [50 empty] | 508031.05 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | AMHS | David Nystrom | David Short | TSMC, 潘信華 | 4590012923 | USC23C058 | RM_F21_EUV_Crane Power Cable Reroute | 95964 |  | 2023-08-22 |  | Pay in month end - 1 month after acceptance month of the date | 95964 | 95964 | 95964 | 1 | 0 | [54 empty] | 95964 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | UPW | Emon | Emon | TSMC, Chih Ching Lin | 4590012982 | USC21C003 | F21P1 UPW temp power and MAU DI solution | 618842 |  | 2023-08-29 |  | 95% on progress,5% 1 month after acceptance of the date | 436391 | 436391 | 436391 | 0.70517 | 182451 | [52 empty] | 416916 |  |  |  | 19475 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QR | QR |  |  | Hank su | Hank Su | TSMC | 4590013010 | USC23C002 | F21_AZFAD_Hookup_Drilling for Metrios enclosure installation | 13959.6 |  | 2023-09-02 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 13959.6 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 設備 |  | AMHS | David Nystrom | David Short | TSMC, 潘信華 | 4590013059 | USC23C058 | RM_F21_EUV_Crane power panel material | 116443.25 |  | 2023-09-08 |  | Pay in month end - 1 month after acceptance month of the date | 116443.25 | 116443.25 | 116443.25 | 1 | 0 | [58 empty] | 116443.25 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | AMHS | David Nystrom | David Short | TSMC, 潘信華 | 4590013060 | USC23C058 | RM_F21_Crane temp, power generator 2 M | 76766.73 |  | 2023-09-08 |  | Pay in month end - 1 month after acceptance month of the date | 76767 | 76767 | 76766.73 | 1 | -0.27 | [56 empty] | 76767 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | AMHS | David Nystrom | David Short | TSMC | 4590013061 | USC23C058 | RM_EUV_temp. power generator 3 M | 115150.1 |  | 2023-09-08 |  | Pay in month end - 1 month after acceptance month of the date | 115150 | 115150 | 115150.1 | 1 | 0.1 | [56 empty] | 115150 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | AMHS | David Nystrom | David Short | TSMC | 4590013062 | USC23C058 | RM_F21_EUV_Crane power panel labor-bay1 | 93809.87 |  | 2023-09-08 |  | Pay in month end - 1 month after acceptance month of the date | 93810 | 93810 | 93809.87 | 1 | -0.13 | [56 empty] | 93810 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | AMHS | David Nystrom | David Short | TSMC | 4590013063 | USC23C058 | RM_F21_EUV_Crane_PowerPanel_Bay2 | 93809.87 |  | 2023-09-08 |  | Pay in month end - 1 month after acceptance month of the date | 93810 | 93810 | 93809.87 | 1 | -0.13 | [56 empty] | 93810 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su | Hank Su | TSMC, 吳宗諺/F21-PVD2 | 4590013089 | USC23C002 | ABS-A03 Onsite modification for RMF | 8047.2 |  |  |  |  | 0 | 0 | 0 | 0 | 8047.2 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK | Foundation |  |  | Hank Su | TSMC | 4590013324 | USC23C059 | F21P1-0404_H_T&M_MICU | 793000 |  |  |  |  | 700483 | 589598 | 700483 | 0.88333 | 92517 | [64 empty] | 589598 |  | 108772 |  | 2113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma | Sam | TSMC, Kevin Liu | 4590013345 | USC22C026 | F21P1-0420_H_Unistrut Support Frame_MICU | 2164306.4 |  |  |  |  | 2164306.4 | 2164306.4 | 2164306.4 | 1 | 0 | [62 empty] | 2164306.4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Hank Su | Hank Su | TSMC, 趙世安 | 4590013410 | USC23C002 | CAP_F_ PVD WAT angle support fee_P1A | 105218.1 |  |  |  |  | 32263.07 | 32263.07 | 0 | 0.30663 | 72955.03 | [62 empty] | 32263.07 | 1803.51 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma | Ning | TSMC | 4590013412 | USC22C005 | F21P1-0404_H_UPW DP Panel_MICU | 541839.33 |  |  |  |  | 533120.59 | 459470.44 | 533120.59 | 0.98391 | 8718.74 | [58 empty] | 0 |  | 0 |  | 357732.59 |  | 101737.85 |  |  |  | 73650.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 | CO_r, Settlement | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-Cheng | 4590013430 | USC21C005 | F21P1 Lorry area fall protection tie off | 327538.3 |  |  |  |  | 327538.3 | 294784 | 327538.3 | 1 | 0 | [58 empty] | 196523 |  | 98261 | [7 empty] | 32754.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement |  |  |  | TSMC | 4590013431 | USC22C031 | F21P1 High-speed rolling door frame | 27027.71 |  |  |  |  | 27027.71 | 27027.71 | 27027.71 | 1 | 0 | [54 empty] | 27027.71 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 | CO_r, Settlement | Low Voltage | Paul Hsu | Dahlia | TSMC, Kevin Chou | 4590013433 | USC21C013 | F21P1 AMC package-IMS wipe test | 8832 |  |  |  |  | 6635.52 | 0 | 5525.76 | 0.7513 | 2196.48 | [64 empty] | 0 |  | 5525.76 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1109.76 | 0
HK | HK |  |  | Hank Su | Hank Su | TSMC | 4590013462 | USC23C002 | F21P1-0423E3_H_fdn intall(L10 pump)_MICU | 326221.65 |  |  |  |  | 0 | 0 | 0 | 0 | 326221.65 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 | CO_r, Settlement | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-cheng | 4590013480 | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 24670.81 |  |  |  |  | 19737 | 19737 | 19737 | 0.80001 | 4933.81 | [58 empty] | 19737 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 | CO_r, Settlement | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-cheng | 4590013481 | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 35640 |  |  |  |  | 35640 | 35640 | 35640 | 1 | 0 | [58 empty] | 35640 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | UPW | Emon | Emon | TSMC, 得威 | 4590013482 | USC21C003 | F21P1 UPW Tank Swing Gate | 83072 |  |  |  |  | 83072 | 45430 | 83072 | 1 | 0 | [56 empty] | 20768 |  | 24662 | [9 empty] | 37642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 | CO | WWT | Jim Chiang | Grant | TSMC, 楊子青 | 4590013485 | USC21C009 | Sandblasting room extended drain line | 11489.84 |  | 2023-10-07 |  | Pay in month end - 1 month after acceptance month of the date | 10915.35 | 0 | 10915.35 | 0.95 | 574.49 | [66 empty] | 10915.35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, 潘信華/H.H. Pan/077373/F21-LIT2/7712514 | 4590013486 | USC22C031 | RM_F21_EUV_tap and drill support | 31408 |  | 2023-10-07 |  | Pay in month end - 1 month after acceptance month of the date | 31408 | 0 | 31408 | 1 | 0 | [64 empty] | 0 |  | 0 |  | 31408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Jim Chiang | Jack | TSMC | 4590013495 | USC21C009 | F21P1 230KV MTR NGR stand | 99113.34 |  | 2023-10-11 |  | Pay in month end - 1 month after acceptance month of the date | 99113.34 | 79291 | 99113.34 | 1 | 0 | [58 empty] | 79291 | [9 empty] | 19822.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, 陳嘉宏 | 4590013561 | USC22C031 | CAP_E_F21 P1 AMHS Cross Floor Hole Cover | 64464.4 |  |  |  |  | 64464.4 | 25786 | 64464.4 | 1 | 0 | [58 empty] | 25786 | [5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 38678.4 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Ning | Ning | TSMC | 4590013563 | USC22C005 | F21P1-0423_H_UPW_MICU | 289387.85 |  |  |  |  | 289387.86 | 277483.55 | 289387.85 | 1 | -0.01 | [58 empty] | 57877.57 |  | 0 |  | 49323.18 |  | 170282.8 |  |  |  | 11904.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Jim Chiang | Manuel | TSMC, 得威 | 4590013571 | USC21C009 | F21P1 WWT Tank Swing Gate | 140834 |  | 2023-10-18 |  | Pay in month end - 1 month after acceptance month of the date | 98648.46 | 78529.32 | 92807.42 | 0.70046 | 42185.54 | [58 empty] | 20119 | 20119 | 13629 |  |  |  | 44781.32 |  | 7788.06 |  | 1947.01 | 0 | 0 | 0 | 0 | 0 | 4543.03 | 0 | 5841.04 | 0
Base Build | 新工 | CO, Settlement | UPW | Emon | Emon | TSMC, 得威 | 4590013572 | USC23C054 | F21P1 UPW Design Change (UMEC) | 451501.76 |  |  |  |  | 395409.44 | 395409.44 | 395409.44 | 0.87577 | 56092.32 | [54 empty] | 256705.9 | [5 empty] | 138703.54 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 製造 |  | 光阻櫃 | Paul Hsu | Chihhao | TSMC | 4590013602 | USC22C012 | CAP_A_MFG_F21-TSMC F21P1 A Side Cabinet | 16274.95 |  | 2023-10-24 |  | Pay in month end - 1 month after acceptance month of the date | 16274.95 | 0 | 16274.95 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 16274.95 | 0 | 0 | 0
Base Build | 新工 | CO_r, Settlement | WWT | Andy Chen | Jim | TSMC, 得威 | 4590013603 | USC21C003 | F21P1 WWT Electrical Testing Support | 182627.5 |  | 2023-10-24 |  | Pay in month end - 1 month after acceptance month of the date | 182627.5 | 182627.5 | 182627.5 | 1 | 0 | [56 empty] | 182627.5 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | Operation | CO_r | Low Voltage | Paul Hsu | Shawn | TSMC, 莊鎧瑋 | 4590013632 | USC22C010 | F21P1_A_CMS_O3 analyzer adapter | 16859.19 |  | 2023-10-27 |  | Pay in month end - 1 month after acceptance month of the date | 16859.19 | 16016.23 | 16859.19 | 1 | 0 | [54 empty] | 0 | [7 empty] | 16016.23 |  |  |  | 842.96 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | UPW | Emon | Chihhao | TSMC, 得威 | 4590013633 | USC21C003 | F21P1 UPW & WWT Battery Charge | 264822 |  | 2023-10-27 |  | Pay in month end - 1 month after acceptance month of the date | 211857.6 | 132411 | 211858 | 0.8 | 52964.4 | [56 empty] | 88274 | [5 empty] | 44137 |  |  |  | 8827 |  | 0 | 0 | 70619.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | Low Voltage | Paul Hsu | Dahlia | TSMC | 4590013669 | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 46326.88 |  | 2023-11-01 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 44010.54 | 0 | 44010.54 | 0.95 | 2316.34 | [68 empty] | 0 | 0 | 0 | 0 | 44010.54 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO_r | Chemical | Kate | Wan-chun | TSMC, Chong-Cheng | 4590013675 | USC21C005 | F21P1 Lorry RU Chemical Filtration Impro | 125235 |  | 2023-11-02 |  | Pay in month end - 1 month after acceptance month of the date | 39675 | 39675 | 39675 | 0.3168 | 85560 | [56 empty] | 23101 |  | 13607 |  | 2967 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Jim Chiang | Jeffrey | TSMC, 得威 | 4590013803 | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 1734089.5 |  | 2023-11-03 |  | Pay in month end - 1 month after acceptance month of the date | 1647385.86 | 1184569 | 1647385.86 | 0.95 | 86703.64 | [58 empty] | 689784 |  |  |  | 93604 |  | 401181 |  |  |  | 283169.89 | 0 | 179646.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Jim Chiang | Jack | TSMC, 得威 | 4590013804 | USC21C009 | F21P1 WWT cable tray relo & add support | 2398574.7 |  | 2023-11-03 |  | Pay in month end - 1 month after acceptance month of the date | 2398574.7 | 2178485 | 2398574.7 | 1 | 0 | [56 empty] | 749171 |  | 1238808 |  |  |  | 190506 | [5 empty] | 220089.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement |  | Steven Chiu | Johnny Wan | TSMC | 4590013806 | USC23C054 | F21P1 WCCS Extend GC and Labor Incentive | 661674 |  | 2023-11-03 |  | Pay in month end - 1 month after acceptance month of the date | 661674 | 661674 | 661674 | 1 | 0 | [54 empty] | 661674 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | Chemical | Steven Chiu | Henry | TSMC | 4590013807 | USC23C054 | F21P1 Slurry Extend GC & Labor Incentive | 1313687.25 |  | 2023-11-03 |  | Pay in month end - 1 month after acceptance month of the date | 1313687.25 | 1313687.25 | 1313687.25 | 1 | 0 | [54 empty] | 1313687.25 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | Low Voltage | Paul Hsu | Paul Hsu | TSMC | 4590013808 | USC23C054 | F21P1 VOC Extend GC & Labor Incentive | 104910 |  | 2023-11-03 |  | Pay in month end - 1 month after acceptance month of the date | 104910 | 104910 | 104910 | 1 | 0 | [54 empty] | 104910 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement |  | Steven Chiu | Johnny Wan | TSMC | 4590013809 | USC23C054 | F21P1 CDS Extend GC & Labor Incentive | 7083604.02 |  | 2023-11-03 |  | Pay in month end - 1 month after acceptance month of the date | 7083604.02 | 7083604.02 | 7083604.02 | 1 | 0 | [54 empty] | 7083604.02 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement |  | Andy Chen | Jim | TSMC | 4590013810 | USC23C054 | F21P1 UPW Extend GC & Labor Incentive | 5008794.91 |  | 2023-11-03 |  | Pay in month end - 1 month after acceptance month of the date | 5008794.91 | 5008794.91 | 5008794.91 | 1 | 0 | [54 empty] | 5008794.91 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Andy Chen | Jim | TSMC | 4590013811 | USC23C054 | F21P1 WWT Extend GC & Labor Incentive | 577980.02 |  | 2023-11-03 |  | Pay in month end - 1 month after acceptance month of the date | 577980.02 | 577980.02 | 577980.02 | 1 | 0 | [54 empty] | 577980.02 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | QR |  |  | Hank Su | Hank Su | TSMC, Y.F. Lai <yflai@tsmc.com> | 4590013886 |  | F21_AZFAD_Hookup_seismic for Metrios cab | 1428 |  |  |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 1428 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Emon | Emon | TSMC, 得威 | 4590013928 | USC21C003 | F21P1 WRC L20 RACK Modification | 19484 |  |  |  | Pay in month end - 1 month after acceptance month of the date | 18509.8 | 16198 | 16198 | 0.95 | 974.2 | [56 empty] | 1726 |  |  |  | 14472 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2311.8 | 0
Others | 設備 |  |  | Hank Su | Hank Su | TSMC, H.H. Pan 潘信華 <HHPAN@TSMC.COM> | 4590013942 | USC23C002 | MISC_(TAX/U1)_EUV_Guard Rail | 21440.6 |  |  |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 21440.6 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 | CO_r, Settlement |  | Shannon |  | TSMC, K.S TUNG 董冠昇 <KSTUNG@TSMC.COM> | 4590013944 | USC24C006 | F21P1 Cast Resin PD Sensor Install/Test | 69600 |  |  |  | 95% on progress,5% 1 month after acceptance of the date | 64992.48 | 0 | 55680 | 0.9338 | 4607.52 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 55680 | 0 | 9312.48 | 0
HK | HK |  |  | John Gauci |  | TSMC, May | 4590014008 | USC23C055 | Hook UP 3 Month Labor | 33576323 |  | 2023-11-17 |  |  | 33576323 | 33576323 | 33576323 | 1 | 0 | [56 empty] | 23431574.06 |  | 10144748.94 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | HK |  |  |  |  | TSMC | 4590014062 | USC22C008 | Fab Cleanroom Expansion Phase 2 | 44712 |  | 2023-11-18 |  |  | 0 | 0 | 0 | 0 | 44712 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Ning | Ning | TSMC | 4590014102 | USC22C005 | TSMC F21P1 0423 Chemical | 1181815.55 |  | 11/22/2023 |  |  | 1017726.7 | 633296.66 | 1017726.7 | 0.86116 | 164088.85 | [58 empty] | 236363.11 | [5 empty] | 396933.55 |  |  |  | 96506.47 | 0 | 256257.06 | 0 | 31666.51 | 0 | 0 | 0 | 0 | 0
Others | 設備 |  |  | George Gaspar |  | TSMC, H.H. Pan 潘信華 <HHPAN@TSMC.COM> | 4590014161 | USC24C002 | [RM]F21_EUV_Crane_service contract | 20000 |  | 11/23/2023 |  | Pay in month end - 1 month after acceptance month of the date | 20000 | 20000 | 20000 | 1 | 0 | [62 empty] | 20000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Jim Chiang | Thomas | TSMC, 得威 | 4590014187 | USC21C009 | F21P1 WWT LB2 Support Modification | 19774.5 |  | 2023-12-31 |  |  | 19774.5 | 0 | 19774.5 | 1 | 0 | [66 empty] | 15970.88 |  | 0 | 0 | 3803.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  |  |  | TSMC | 4590014284 | USC22C005 | EBOAZ ZASC5-1 UPW Hook Up Material | 16252.5 |  | 01/14/2023 |  |  | 16252.5 | 15767.05 | 16252.5 | 1 | 0 | [58 empty] | 3250.5 |  |  |  | 12516.55 | [5 empty] | 485.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  |  |  | TSMC | 4590014289 | USC23C055 | F21P1 0404 H Hardware for 3 Months | 26892986.89 |  | 2023-12-31 |  |  | 23209333.16 | 13146417.06 | 23009012.42 | 0.86303 | 3683653.73 | [56 empty] | 5637347.33 |  | 2577968.13 |  | 2054460.19 |  | 1520116.89 |  | 1356524.52 |  | 5440319.69 |  | 2524721.4 | 0 | 0 | 0 | 1710084.83 | 0 | 187469.44 | 0 | 200320.74 | 0
Base Build | 新工 | CO, Settlement | WWT | Andy Chen | Jim | TSMC, 得威 | 4590014401 | USC21C009 | F21P1 WWT Per Diem and Acceleration | 6264381 |  | 12/7/2023 |  | Pay in month end - 1 month after acceptance month of the date | 6264381 | 6264381 | 6264381 | 1 | 0 | [58 empty] | 6264381 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | EBO |  |  | John Gauci |  | TSMC | 4590014625 | USC23C055 | ZKT6-1 Electrics hookup installation | 17130.05 |  | 12/14/2023 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 17130.05 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Jim Chiang | Thomas | TSMC, 得威 | 4590014629 | USC21C009 | F21P1 WWT AWR Drain to LSR System | 63140.59 |  | 12/14/2023 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 63140.59 | 12628 | 63140.59 | 1 | 0 | [58 empty] | 12628 | [9 empty] | 50512.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Jim Chiang | Arunas | TSMC, 得威 | 4590014630 | USC21C009 | F21P1 WWT Panel Butten Change | 100502.27 |  | 12/14/2023 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 100502.27 | 89649.42 | 100502.27 | 1 | 0 | [60 empty] | 58279.42 |  | 31370 | [5 empty] | 0 | 0 | 0 | 0 | 10852.85 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590014651 | USC22C031 | CAP_E_F21P1 AMHS EUV Area Scaffolding | 433365 |  | 12/15/2023 |  | Pay in month end - 1 month after acceptance month of the date | 433365 | 433365 | 433365 | 1 | 0 | [58 empty] | 0 |  |  |  | 433365 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | UPW | Emon | Emon | TSMC, 得威 | 4590014674 | USC21C009 | F21P1 UPW Control Panel Temp Cable | 830528.51 |  | 12/16/2023 |  | Pay in month end - 1 month after acceptance month of the date | 830528.51 | 830528.51 | 830528.51 | 1 | 0 | [58 empty] | 830528.51 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | UPW | Emon | Emon | TSMC, 得威 | 4590014675 | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 215909.35 |  | 12/16/2023 |  | Pay in month end - 1 month after acceptance month of the date | 215909.35 | 215909.35 | 215909.35 | 1 | 0 | [58 empty] | 215909.35 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO_r, Settlement | WWT | Shannon |  | TSMC, 得威 | 4590014676 | USC23C056 | F21P1 WWT FAB LB2 Trench Cleanning | 141128 |  | 12/16/2023 |  | Pay in month end - 1 month after acceptance month of the date | 141128 | 141128 | 141128 | 1 | 0 | [60 empty] | 141128 | 7889.06 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 | CO_r | Chemical | Steven Chiu | Henry | TSMC, 吳曜安 | 4590014805 | USC21C006 | F21P1 Slurry 2 Additional Set Install | 1590000 |  | 12/21/2023 |  | Payment by Progress of the date | 318918 | 0 | 318918 | 0.20058 | 1271082 | [68 empty] | 318918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | John Gauci |  | TSMC | 4590014878 | USC23C055 | elec. cable for KXPTR1/2 | 4600 |  | 12/28/2023 |  | Pay in month end - 1 month after acceptance month of the date | 4600 | 0 | 0 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 0
AMHS | AMHS |  |  | David Nystrom | David Short | TSMC, 鄭宇倢/Josie Cheng/108938/F21-AMHS/7713512 | 4590014879 | USC22C025 | CAP_E_F21P1 MML Anchor Permit Paperwork | 23345 |  | 12/28/2023 |  | Pay in month end - 1 month after acceptance month of the date | 23345 | 23345 | 23345 | 1 | 0 | [62 empty] | 23345 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Hank Su | Hank Su | TSMC | 4590014914 | USC23C002 | FAC_(600/T9) FX200 Seismic holes enlarge | 1792.46 |  | 1/4/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 1792.46 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBO | 設備 | Interconnection |  | Hank Su |  | TSMC | 4590014960 | USC23C002 | CAP_F_ 91016 Strength Raised Floor insta | 26318.31 |  | 1/6/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 26318.31 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | HK |  |  | Hank Su |  | TSMC | 4590014961 | USC23C002 | CAP_F_ 91016 Strength Raised Floor insta | 26318.31 |  | 1/6/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 26318.31 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Stanley Chen | 4590015038 | USC22C034 | CAP_E_F21P1A AMHS Electrical revise Design for MML | 48962.4 |  | 1/11/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 48962.4 | 0 | 48962.4 | [62 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, 鄭宇倢/Josie Cheng/108938/F21-AMHS/7713512 | 4590015039 | USC22C034 | CAP_E_F21P1 AMHS AC BOX Addition Design | 30042.6 |  | 1/11/2024 |  | Pay in month end - 1 month after acceptance month of the date | 30042.6 | 30042.6 | 30042.6 | 1 | 0 | [62 empty] | 30042.6 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Andy Chen | Jim | TSMC, 得威 | 4590015058 | USC21C009 | F21P1 WWT Per Diem and Acceleration | 4142540.4 |  | 01/12/2024 |  | Pay in month end - 1 month after acceptance month of the date | 4142540.4 | 4142540.4 | 4142540.4 | 1 | 0 | [60 empty] | 4142540.4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | WWT | Jim Chiang | Thomas/CH | TSMC, 得威 | 4590015143 | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 601790 |  | 01/19/2024 |  | Pay in month end - 1 month after acceptance month of the date | 601790 | 577718 | 601790 | 1 | 0 | [60 empty] | 571700 |  | 6018 | [5 empty] | 24072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO_r | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Analicia | 4590015164 | USC22C013 | MISC_(TAX/T0)_(LB1 CCTV QTY6/MIC) | 47320 |  | 01/23/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 47320 | 42854.63 | 47320 | 1 | 0 | [64 empty] | 42854.63 |  | 4465.37 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  |  |  | TSMC, Michael Lin <MLINL@TSMC.COM> | 4590015297 | USC23C063 | Hook UP Time and Material HardWare | 500000 |  | 11/18/2023 |  |  | 475646.12 | 175847.1 | 475646.12 | 0.95129 | 24353.88 | [62 empty] | 79589.67 |  | 96257.43 |  | 289096.98 |  | 0 | 0 | 10702.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma | Sam | TSMC, wchenm@tsmc.com | 4590015309 | USC22C026 | F21P1-0423_H_Unistrut Support Frame_MICU | 150354.41 |  | 01/30/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 150354.41 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QR | QR |  |  |  | Ning | TSMC, Y.F. Lai 賴易鋒 <YFLAI@TSMC.COM> | 4590015367 | USC22C005 | power drain material | 577.2 |  | 02/01/2024 |  | Pay in month end - 1 month after acceptance month of the date | 577.22 | 577.22 | 577.2 | 1 | -0.02 | [64 empty] | 577.22 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Kate |  | TSMC, Luke Pan <JTPAN@TSMC.COM> | 4590015373 | USC23C022 | F21P1-0423_H_3D modeling(MICU) | 3312795.31 |  | 02/01/2024 |  | Pay in month end - 1 month after acceptance month of the date | 2831964 | 2356722 | 2831964 | 0.85486 | 480831.31 | [62 empty] | 2356722 |  | 0 |  |  |  | 475242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590015432 | USC22C031 | CAP_E_F21P1 L10 Scaffold for Stocker Install | 9259 |  | 02/07/2024 |  | Pay in month end - 1 month after acceptance month of the date | 9259 | 9259 | 9259 | 1 | 0 | [64 empty] | 9259 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interconnection | 設備 |  |  | Hank Su | Hank Su | TSMC, H.H. Pan 潘信華 <HHPAN@TSMC.COM> | 4590015533 | USC23C002 | EUV_Hard barricade | 21440.6 |  | 02/14/2024 |  | Pay in month end - 1 month after acceptance month of the date | 21440.6 | 0 | 0 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21440.6 | 0
FAB Requirement (FAC) | 設備 |  |  |  |  | TSMC, H.H. Pan 潘信華 <HHPAN@TSMC.COM> | 4590015793 | USC24C002 | (RM)F21_EUV_Crane service labor | 60000 |  | 02/22/2024 |  | Pay in month end - 1 month after acceptance month of the date | 60000 | 30000 | 60000 | 1 | 0 | [62 empty] | 30000 | [5 empty] | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | UPW | Emon | Chihhao | TSMC, Sabrina Cervante | 4590015828 | USC21C003 | F21P1 Gas Chemical Lab Additional Work | 146982.97 |  | 02/23/2024 |  | Pay in month end - 1 month after acceptance month of the date | 146982.97 | 139633.82 | 146982.97 | 1 | 0 | [64 empty] | 139633.82 | 7805.53 |  |  | 7349.15 | 410.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Ning and Victoria |  | TSMC | 4590015933 | USC22C005 | F21P1-0404_H_UPW_MICU | 204832.03 |  | 02/29/2024 |  | Pay in month end - 1 month after acceptance month of the date | 204832.03 | 0 | 204832.03 | 1 | 0 | [68 empty] | 204832.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Ning and Victoria |  | TSMC | 4590015934 | USC22C005 | F21P1-0404_H_UPW DP Panel_MICU | 379624.13 |  | 2024-02-29 |  | Pay in month end - 1 month after acceptance month of the date | 107954.2 | 0 | 90776.65 | 0.28437 | 271669.93 | [68 empty] | 0 | 0 | 75924.83 | 0 | 0 | 0 | 14851.82 | 0 | 17177.55 | 0
HK | HK |  |  | John Gauci |  | TSMC | 4590015978 | USC23C055 | F21P1-0404_H_E2 Incentive | 400707 |  | 2024-03-01 |  | Pay in month end - 1 month after acceptance month of the date | 400707 | 400707 | 400707 | 1 | 0 | [64 empty] | 400707 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | IT |  | Low Voltage | Paul Hsu |  | TSMC, 王靖尊 | 4590016125 | USC22C013 | 4F IT Service Center Speed Gate | 104491.39 |  | 2024-03-08 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 104491.39 | 104491.39 | 104491.39 | 1 | 0 | [64 empty] | 104491.39 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Hank Su |  | TSMC | 4590016141 | USC23C059 | F21P1-0423_H_T&M_MICU_MISC | 799388 |  | 2024-03-08 |  | Pay in month end - 1 month after acceptance month of the date | 152507 | 0 | 152507 | 0.19078 | 646881 | [68 empty] | 0 | 0 | 152507 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Hank Su |  | TSMC | 4590016142 | USC23C002 | F21P1-0404_H_Foundation Seismic Support | 225800.25 |  | 2024-03-08 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 225800.25 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | UPW | Emon | Emon | TSMC, 得威 | 4590016147 | USC21C003 | F21P1 UPW WRC L10 Add Supports | 12016.58 |  | 2024-03-08 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 11415.75 | 0 | 11415.75 | 0.95 | 600.83 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 11415.75 | 0 | 0 | 0
Base Build | 新工 | CO, Settlement | UPW | Emon | Emon | TSMC, 得威 | 4590016257 | USC21C003 | F21P1 UPW A5 Backup Line Modification | 76606.17 |  | 2024-03-12 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 71274.57 | 68026.33 | 71274.57 | 0.9304 | 5331.6 | [64 empty] | 68026.33 |  | 3248.24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Hank Su |  | TSMC | 4590016630 | USC23C047 | F21P1-0404_H_Seismic Install_MICU | 1629593.3 |  | 03/23/2024 |  | Pay in month end - 1 month after acceptance month of the date | 1629593.3 | 1124519 | 1629593.3 | 1 | 0 | [64 empty] | 1124519 |  | 245510 |  | 203907 | 0 | 0 | 0 | 0 | 0 | 55657.3 | 0 | 0 | 0
Interconnection | LIT2 |  |  |  |  | TSMC | 4590016715 | USC23C058 | (RM)F21_EUV_Crane generator rent | 115150.08 |  | 03/27/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 115150.08 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | IT |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 王靖尊 | 4590016975 | USC22C013 | F21_PDPFA lab add two CCTV for OWMC requ | 14660.72 |  | 04/05/2024 |  | ` | 14660.72 | 0 | 14660.72 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 14660.72 | 819.53 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | IT |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 王靖尊 | 4590016977 | USC22C013 | F21_PDPFA_security facility for security | 84682.25 |  | 04/05/2024 |  | Pay in month end - 1 month after acceptance month of the date | 84682.25 | 0 | 84682.25 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 84682.25 | 4733.74 | 0 | 0
FAB Requirement (FAC) | IT |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, 王靖尊 | 4590017093 | USC22C013 | F21P1 Office Security IT Room CCTV | 36374.57 |  | 04/11/2024 |  | Pay in month end - 1 month after acceptance month of the date | 36374.57 | 0 | 36374.57 | 1 | 0 | [66 empty] | 36374.57 | 2033.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590017205 | USC22C031 | CAP_E_F21 VL14 Scaffold for Rail Adjustm | 9259 |  | 04/16/2024 |  | Pay in month end - 1 month after acceptance month of the date | 9259 | 0 | 9259 | 1 | 0 | [64 empty] | 0 |  | 9259 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | LIT2 |  |  | George Gaspar |  | TSMC, H.H. Pan 潘信華 <HHPAN@TSMC.COM> | 4590017212 | Expect to add in USC24C002 | TSMC F21P1 EUV Crane Maintenance | 60000 |  | 04/16/2024 |  | Pay in month end - 1 month after acceptance month of the date | 60000 | 0 | 0 | 1 | 0 | [69 empty] | 0 |  | 0 | 50000 | 0 | 0 | 0 | 10000 | 0
FAB Requirement (FAC) | IT |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, Jimmy Tang 湯仁義 <jytang@TSMC.COM> | 4590017354 | USC22C013 | CMS System IT Support | 28520 |  | 04/23/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 28520 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, Jonathan Kang <HSUANK@TSMC.COM> | 4590017604 | USC22C031 | CAP_E_F21P1 AMHS EUV Area 2 Scaffolding | 324069 |  | 05/02/2024 |  | Pay in month end - 1 month after acceptance month of the date | 324069 | 0 | 324069 | 1 | 0 | [64 empty] | 0 |  | 0 |  | 0 | 0 | 324069 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma |  | TSMC, Yeng-Chen Chang 張晏誠 <YCCHANGZC@TSMC.COM> | 4590017765 | USC23C055 | F21P1-0404_H_E2 Incentive | 18400 |  | 2024-05-08 |  | Pay in month end - 1 month after acceptance month of the date | 18400 | 0 | 0 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18400 | 0
HK | HK |  |  |  |  | TSMC, Samuel Mokdad <SAMUELM@TSMC.COM> | 4590017784 | USC23C047 | F21P1-0404E2_H_Seismic Install_MICU | 481285 |  | 2024-05-08 |  | Pay in month end - 1 month after acceptance month of the date | 365636.75 | 0 | 162146.57 | 0.75971 | 115648.25 | [68 empty] | 19470.88 | 0 | 0 | 0 | 0 | 0 | 142675.69 | 0 | 203490.18 | 0
HK | HK |  |  |  |  | TSMC, WENZHI(WENZHI@TSMC.COM | 4590018032 | USC22C005 | F21P1-0423_H_UPW_MICU | 1668571.43 |  | 2024-05-16 |  | Pay in month end - 2 month after acceptance month of the date | 852994.63 | 0 | 670621.29 | 0.51121 | 815576.8 | [68 empty] | 0 | 0 | 333714.29 | 0 | 225851.57 | 0 | 111055.43 | 0 | 182373.34 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince Tsai <TCTSAIJ@TSMC.COM> | 4590018358 | USC22C013 | Pull 108 cable | 30019 |  | 2024-05-30 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 30019 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | HK |  | AMHS | David Nystrom | David Short | TSMC, Pang Hsun Chu 朱邦巡 <PHCHUF@TSMC.COM> | 4590018645 | USC22C031 | CAP_E_F21 P1 HPM Panel Hole Filling | 243952.02 |  | 06/07/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 243952.02 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | EBO |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, A.C. Lee 黎安成 <ACLEE@TSMC.COM> | 4590018652 | USC22C013 | EBOAZ-F21P1 Require CCTV&ACS (Labor) | 39627.9 |  | 06/07/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 39627.9 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC | 4590018678 | USC22C014 | CAP_E_F21_Power_Project. MIC Power Project combined A+B side. Includes added 8 DP panels. | 2418381.82 |  | 06/08/2024 |  | Pay in month end - 1 month after acceptance month of the date | 2418381.82 | 0 | 2418381.82 | 1 | 0 | [64 empty] | 0 |  | 0 |  |  | 0 | 2418381.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | EBO |  | Low Voltage | Paul Hsu | Johnny Yang | TSMC, A.C. Lee 黎安成 <ACLEE@TSMC.COM> | 4590018680 | USC22C013 | EBOAZ-F21P1 Require CCTV&ACS (material) | 27306.55 |  | 06/08/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 27306.55 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | 設備 |  |  | Hank Su |  | TSMC | 4590018877 | USC23C002 | CONSTR_(TAX/T5) KDSET1 floor | 6544.8 |  | 06/14/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 6544.8 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | Chemical | Kate | Wanchun | TSMC, Chong-Cheng | 4590019011 | USC24C014 | F21P1 CDS Pressure Test Appeal for PFC | 34500 |  | 06/19/2024 |  | 90% 1 mth aft delivery, 10% 1 mth aft acceptance of the date | 34500 | 0 | 34500 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 34500 | 0 | 0 | 0 | 0 | 0
HK | HK |  | UPW | Elaine Ma | Victoria Chao | TSMC, Marios Christofides <MCHRISTO@TSMC.COM> | 4590019069 | USC22C005 | TSMC UPW P1B materials_panels | 2668813.47 |  | 06/21/2024 |  | Pay in month end - 1 month after acceptance month of the date | 569669.08 | 0 | 533762.69 | 0.21345 | 2099144.39 | [69 empty] | 0 | 0 | 0 | 533762.69 | 0 | 0 | 0 | 35906.39 | 0
Base Build | 新工 | Settlement | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-Cheng | 4590019083 | USC24C006 | F21P1 CDS & WCCS CO2 Suppression System | 842291 |  | 06/21/2024 |  | Pay in month end - 1 month after acceptance month of the date | 683668 | 0 | 424296 | 0.81168 | 158623 | [69 empty] | 0 | 424296 | 0 | 0 | 0 | 0 | 0 | 259372 | 0
Base Build | 新工 | Settlement | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-Cheng | 4590019372 |  | F21P1 CDS Labor Incentive Nov 2023 | 36000 |  | 2024-06-28 |  | Pay in month end - 1 month after acceptance month of the date | 36000 | 0 | 36000 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | WWT | Andy Chen |  | TSMC, 得威 | 4590019487 | USC24C006 | F21P1 WWT Labor Incentive Nov 2023 | 60000 |  | 2024-07-01 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 60000 | 0 | 60000 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Andy Chen |  | TSMC, 得威 | 4590019488 | USC23C045 | F21P1 UPW Labor Incentive Nov 2023 | 15000 |  | 2024-07-01 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 15000 | 0 | 15000 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Andy Chen |  | TSMC, 得威 | 4590019489 | USC24C006 | F21P1 UPW Fiber Repull from Damage | 157102.31 |  | 2024-07-01 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 157102.31 | 0 | 157102.31 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 157102.31 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590019490 | USC24C006 | F21P1 Add Card Reader at Material Gate | 20288 |  | 2024-07-01 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 18259.2 | 0 | 18259.2 | 0.9 | 2028.8 | [69 empty] | 0 | 0 | 0 | 18259.2 | 1020.69 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | WWT | Paul Hsu | Johnny Yang | TSMC, 得威 | 4590019491 | USC24C006 | F21P1 WWT Doors &Triazole HK Pad Mod | 13908 |  | 2024-07-01 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 12920.4 | 0 | 12920.4 | 0.92899 | 987.6 | [69 empty] | 0 | 0 | 0 | 12920.4 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Jim Chiang | Jim Chiang | TSMC, 得威 | 4590019492 | USC24C006 | F21P1 WWT Temp Chem. Leak Diverter Tarp | 76797 |  | 2024-07-01 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 15359.4 | 0 | 15359.4 | 0.2 | 61437.6 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 15359.4 | 0 | 0 | 0
Base Build | 新工 | Settlement | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590019493 | USC24C006 | F21P1 Speed Gate at Tent and CR Entrance | 684987.44 |  | 2024-07-01 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 650738.07 | 0 | 650738.07 | 0.95 | 34249.37 | [69 empty] | 0 | 0 | 0 | 650738.07 | 36376.26 | 0 | 0 | 0 | 0
Base Build | NFDD | Settlement |  | Chao Chia | Alex | TSMC | 4590019495 | USC24C006 | F21P1 Hallway Plate Install | 253575 |  | 2024-07-02 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 203705.25 | 0 | 203705.25 | 0.80333 | 49869.75 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 203705.25 | 0 | 0 | 0
HK | HK |  |  | John Gauci |  | TSMC | 4590019499 | USC24C015 | F21P1-0423_H_E2 Management 4 Months | 3288054 |  | 2024-07-02 |  | Pay in month end - 1 month after acceptance month of the date | 2189432.97 | 0 | 1395384.38 | 0.66588 | 1098621.03 | [69 empty] | 0 | 0 | 0 | 690848.55 | 0 | 704535.83 | 0 | 794048.59 | 0
HK | HK |  |  | John Gauci |  | TSMC | 4590019500 | USC24C015 | F21P1-0423_H_E2 Labor 4 Months | 49274190 |  | 2024-07-02 |  | Pay in month end - 1 month after acceptance month of the date | 39204474.8 | 0 | 39204474.8 | 0.79564 | 10069715.2 | [69 empty] | 0 | 24390056.25 | 0 | 8218447.6 | 0 | 6595970.95 | 0 | 0 | 0
O&M | LIT2 |  |  | George Gaspar |  | TSMC, Kai Kao ckkaoc@tsmc.com | 4590019601 |  | (T5) F21_EUV crane encoder cable | 4048.28 |  | 2024-07-04 |  | Pay in month end - 1 month after delivery month of the date | 0 | 0 | 0 | 0 | 4048.28 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC | 4590019688 | USC22C031 | CAP_E_F21 P1B_Seismic_RMF_Hole_Cuts | 3425396.82 |  | 2024-07-09 |  | Pay in month end - 1 month after acceptance month of the date | 1027802.71 | 0 | 1027802.71 | 0.30005 | 2397594.11 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 1027802.71 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC, David C.C. Fu 傅至傑 <CCFUC@TSMC.COM> | 4590019702 | USC22C031 | CAP_E_F21 P1B_Cross Floor Hole Covering | 64464.4 |  | 2024-07-09 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 25785.76 | 0 | 25785.76 | 0.4 | 38678.64 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 25785.76 | 0 | 0 | 0
AMHS | AMHS |  | AMHS | David Nystrom | David Short | TSMC | 4590019730 | USC22C014 | CAP_E_F21 AMHS_P1 A&B VT Network Cable Wiring | 705343 |  | 2024-07-10 |  | Pay in month end - 1 month after acceptance month of the date | 343391 | 0 | 343391 | 0.48684 | 361952 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 343391 | 0 | 0 | 0
HK | HK |  |  | Elaine Ma |  | TSMC, Marios Christofides <MCHRISTO@TSMC.COM> | 4590019895 | USC22C005 | F21P1-0423_H_UPW Material_MICU | 4981041.48 |  | 2024-07-16 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 4981041.48 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Emon Roy | Emon Roy | TSMC, 得威 | 4590019922 | USC24C006 | F21P1 UPW ABG-A Submain Modification | 77505.16 |  | 2024-07-16 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 77505.16 | 0 | 77505.16 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 69754.65 | 0 | 7750.51 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Emon Roy |  | TSMC, 得威 | 4590019923 | USC24C006 | F21P1 UPW WRC NFPA Sign Installation | 9264.39 |  | 2024-07-16 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 9264.39 | 0 | 9264.39 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 9264.39 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | Low Voltage | Paul Hsu | Chihhao | TSMC, Amy | 4590019924 | USC24C006 | F21P1 Seismic Monitor | 249740.01 |  | 2024-07-16 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 116624.66 | 0 | 116624.66 | 0.46698 | 133115.35 | [69 empty] | 0 | 0 | 0 | 116624.66 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Chihhao |  | TSMC, 得威 | 4590019925 | USC24C006 | F21P1 UPW Cable Tray Reroute per Code | 439475.39 |  | 2024-07-16 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 439475.39 | 0 | 439475.39 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 439475.39 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Emon Roy |  | TSMC, 得威 | 4590019926 | USC24C006 | F21P1 UPW Piping Damaged by Others | 16680.43 |  | 2024-07-16 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 16680.43 | 0 | 16680.43 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 16680.43 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Emon | Emon | TSMC, 得威 | 4590019927 | USC24C006 | F21P1 UPW B Side MAU DI Temp Solution | 120273.57 |  |  |  |  | 114257 | 0 | 114257 | 0.94998 | 6016.57 | [69 empty] | 0 | 0 | 0 | 114257 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Emon Roy | Emon Roy | TSMC, 得威 | 4590019928 | USC24C006 | F21P1 UPW WRC L20 Trench Modification | 3352 |  | 2024-07-16 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 1676.13 | 0 | 1676.13 | 0.50004 | 1675.87 | [69 empty] | 0 | 0 | 0 | 1676.13 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Emon Roy | Emon Roy | TSMC, 得威 | 4590019929 | USC24C006 | F21P1 UPW Temp UPW Supply for ICPMS | 164974.95 |  | 2024-07-16 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 82487.47 | 0 | 82487.47 | 0.5 | 82487.48 | [69 empty] | 0 | 0 | 0 | 82487.47 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | Low Voltage | Paul Hsu | Dahlia | TSMC, Grant Shih <YUSHIH@TSMC.COM> | 4590019947 | USC23C045 | F21P1 VOC MC Cable | 521898.39 |  | 2024-07-17 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 521898.39 | 0 | 495803.47 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 495803.47 | 27715.41 | 0 | 0 | 26094.92 | 1458.71
O&M | 新工 |  | Chemical | Steven Chiu | Johnny Wan | TSMC | 4590020023 |  | MIC Chemical Support Team Jul 5FTE | 93854.08 |  | 07/24/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 93854.08 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Emon | Emon/Wanchun | TSMC, 得威 | 4590020154 | USC23C045 | F21P1 MICU Settlement 1st_UPW | 17306650.55 |  | 2024-07-23 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 17306650.55 | 0 | 15918173.53 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 15918173.53 | 0 | 0 | 0 | 1388477.02 | 0
Base Build | 新工 | Settlement | UPW | Emon | Emon | TSMC, 得威 | 4590020155 | USC24C006 | F21P1 UPW Distribution Repair | 94391.49 |  | 07/23/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 94391.49 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | WWT | Jim Chiang | Thomas/Jim/Wanchun | TSMC, 得威 | 4590020156 | USC23C045 | F21P1 MICU Settlement 1st_WWT | 32331780.16 |  | 07/23/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 32331780.16 | 0 | 28232740.55 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 26821220.8 | 0 | 1411519.75 | 0 | 4099039.61 | 0
Base Build | 新工 | Settlement | Chemical | Steven Chiu | Johnny Wan/Wanchun | TSMC, Chong-Cheng | 4590020157 | USC23C045 | F21P1 MICU Settlement 1st_CDS | 14689285.95 |  | 2024-07-23 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 14689285.95 | 0 | 14043630.02 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 14043630.02 | 0 | 0 | 0 | 645655.93 | 0
Base Build | 新工 | Settlement | Chemical | Steven Chiu | Johnny Wan/Wanchun | TSMC, Chong-Cheng | 4590020158 | USC23C045 | F21P1 MICU Settlement 1st_WCCS | 3295175 |  | 07/23/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 3295175 | 0 | 3151456.57 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 3151456.57 | 0 | 0 | 0 | 143718.43 | 0
Base Build | 新工 | Settlement | Low Voltage | Paul Hsu | Dahlia/Wanchun | TSMC, 鄧安 | 4590020159 | USC23C045 | F21P1 MICU Settlement 1st_VOC | 2097132.8 |  | 07/23/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 2097132.8 | 0 | 1951714.25 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 1944124.1 | 0 | 7590.15 | 0 | 145418.55 | 0
Base Build | 新工 | Settlement | UPW | Emon | Emon | TSMC, 得威 | 4590020160 | USC24C006 | F21P1 UPW P1B Submain Expansion | 154305.65 |  | 07/23/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 154305.65 | 0 | 0 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154305.65 | 0
Base Build | 新工 | Settlement | WWT | Jim Chiang | Jim Chiang | TSMC, 得威 | 4590020228 | USC23C045 | F21P1 WWT AWN Enzyme Dosing Improvement | 328712 |  | 07/24/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 222848.79 | 0 | 109986.26 | 0.67795 | 105863.21 | [69 empty] | 0 | 0 | 0 | 109986.26 | 0 | 0 | 0 | 112862.53 | 0
Base Build | 新工 | Settlement | Low Voltage | Paul Hsu | Johnny Yang | TSMC, Vince | 4590020230 | USC23C045 | F21P1 Security & CCTV DCR | 273068 |  | 07/24/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 232107.8 | 0 | 232107.8 | 0.85 | 40960.2 | [69 empty] | 0 | 0 | 0 | 232107.8 | 12974.83 | 0 | 0 | 0 | 0
Base Build | 新工 |  | UPW | Emon Roy | Emon Roy | TSMC, 得威 | 4590020235 | USC24C006 | F21P1 UPW Mezzanine Modification | 1507740 |  | 07/25/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 1017145.01 | 0 | 541191.83 | 0.67462 | 490594.99 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 541191.83 | 0 | 475953.18 | 0
Base Build | 新工 |  | WWT | Jim Chiang | Jim Chiang | TSMC, 得威 | 4590020236 | USC24C006 | F21P1 WWT CWR System Improvement | 665875.85 |  | 07/25/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 105571.52 | 0 | 105571.52 | 0.15855 | 560304.33 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 105571.52 | 0 | 0 | 0
Base Build | 新工 | Settlement | UPW | Emon Roy | Emon Roy | TSMC, 得威 | 4590020302 | USC24C006 | F21P1 MICU Settlement 2nd_UPW | 7249177.3 |  | 07/27/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 6600000 | 0 | 3135000 | 0.91045 | 649177.3 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 3135000 | 0 | 3465000 | 0
Base Build | 新工 | Settlement | WWT | Jim Chiang | Thomas/Jim Chiang | TSMC, 得威 | 4590020303 | USC24C006 | F21P1 MICU Settlement 2nd_WWT | 7007538.06 |  | 07/27/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 3300000 | 0 | 990000 | 0.47092 | 3707538.06 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 990000 | 0 | 2310000 | 0
Base Build | 新工 | Settlement | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-Cheng | 4590020304 | USC24C006 | F21P1 MICU Settlement 2nd_CDS | 7490816.54 |  | 07/27/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 6600000 | 0 | 3300000 | 0.88108 | 890816.54 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 3300000 | 0 | 3300000 | 0
Base Build | 新工 | Settlement | Chemical | Steven Chiu | Henry Yang | TSMC, Chong-Cheng | 4590020305 | USC24C006 | F21P1 MICU Settlement 2nd_WCCS | 1449835.46 |  | 07/27/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 1449835.46 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 | Settlement | Low Voltage | Paul Hsu | Dahlia | TSMC | 4590020306 | USC24C006 | F21P1 MICU Settlement 2nd_VOC | 966556.97 |  | 07/27/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 966556.97 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) |  |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC | 4590020568 | Expect to add in USC24C007 | 522/T0 5G DPM Additional Construction | 8562.32 |  | 07/31/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 8562.32 | [73 empty] | 0 | 0 | 0 | 0 | 0
O&M |  |  |  | George Gaspar |  | TSMC | 4590020635 | Expect to add in USC24C002 | TSMC F21P1 EUV Crane Maintenance | 60000 |  | 08/01/2024 |  | Pay in month end - 1 month after acceptance month of the date | 50000 | 0 | 0 | 0.83333 | 10000 | [73 empty] | 0 | 0 | 0 | 50000 | 0
AMHS | AMHS |  |  | David Nystrom | David Short | TSMC | 4590020779 |  | CAP_E_F21 P1B AMHS Infrastructure 8 additional DP Panel | 2529738.97 |  | 08/06/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 2529738.97 | [73 empty] | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Serena Deng |  | TSMC | 4590020794 |  | F21P1-0423_H_MIC Warehouse Management | 27343521 |  | 08/06/2024 |  | Pay in month end - 1 month after acceptance month of the date | 19896212.02 | 0 | 18203634.94 | 0.72764 | 7447308.98 | [73 empty] | 0 | 18203634.94 | 0 | 1692577.08 | 0
HK | HK |  |  | John Gauci |  | TSMC | 4590020844 | USC24C015 | F21P1-0423_H_E2 Hardware_MICU | 12035415.39 |  | 08/07/2024 |  | Pay in month end - 1 month after acceptance month of the date | 75497.37 | 0 | 0 | 0.0062729 | 11959918.02 | [73 empty] | 0 | 0 | 0 | 75497.37 | 0
HK | HK |  |  | John Gauci |  | TSMC | 4590020940 | USC24C015 | F21P1-0423_H_E2 Hardware_MICU | 12724409.45 |  | 08/07/2024 |  | Pay in month end - 1 month after acceptance month of the date | 651978.55 | 0 | 0 | 0.051238 | 12072430.9 | [73 empty] | 0 | 0 | 0 | 651978.55 | 0
Others | Non-TSMC |  |  | David Nystrom | Tzuhao Kuo | 崇濬 | 20230315002 | USC23C035 | TSMC F21 Heating Jacket Installation | 3677257.57 |  | 3/15/2023 |  | T/T Net 45 days | 2137999.73 | 0 | 1369843.71 | 0.58141 | 1539257.84 | [66 empty] | 1097529.92 |  | 149580.24 | 0 | 518213.85 | 0 | 170909.62 | 0 | 122733.55 | 0 | 79032.55 | 0
Base Build | Non-TSMC |  | UPW | Emon |  | Organo USA, Inc | 0000000065 | USC24C013 | HP1037 & HP1137 Add Disconnect | 38207.34 |  |  |  |  | 19103.67 | 19103.67 | 0 | 0.5 | 19103.67 | [56 empty] | 19103.67 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | George Gaspar |  | Lumax | 1MUQOC2312011 | USC22C007 | STRAND FIBER SM ARMORED CABLES | 20280.25 |  |  |  |  | 20280.25 | 20280.25 | 20280.25 | 1 | 0 | [62 empty] | 20280.25 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | Kate |  | Kanken | 1MUQOC2401019 |  | Kanken Storage for 2023 December | 1575 |  | 1/4/2024 |  | 100% by invoice, Net 30 Days | 1575 | 1575 | 4662.5 | 1 | 0 | [58 empty] | 1575 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | Non-TSMC |  |  |  |  | Lumax | 1MUQOC2403077 | USC22C007 | Overtime for Fiber Cable Pulls & Splicers 3 Weeks | 65616.7 |  |  |  |  | 65616.7 | 0 | 65616.7 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 65616.7 | 0 | 0 | 0
Others | Non-TSMC |  |  |  |  | Lumax | 1MUQTR2205002 | USC22C007 | TSMC F21 FMCS Installation | 1115500 |  |  |  |  | 1097244.1 | 1035322.85 | 1097244.1 | 0.98363 | 18255.9 | [30 empty] | 157620 |  | 65670 |  | 71446 |  | 94071 | [5 empty] | 337890 |  | 123971.61 |  |  |  | 102161.4 |  |  |  | 45275.27 | [7 empty] | 37217.57 | [5 empty] | 32001.85 |  | 29919.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  |  | MIC | 1MUQTR2211013 | USC22C016 | Asahi Valve from Harrington | 3446.08 |  |  |  |  | 3446.0804 | 3446.0804 | 3446.08 | 1 | -0.0004 | [38 empty] | 2246.01 |  | 1200.0704 | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | Boris |  | MIC | 1MUQTR2301003 | USC22C016 | Gasket from Harrington | 1929.25 |  |  |  |  | 1929.25 | 1929.25 | 1929.25 | 1 | 0 | [38 empty] | 1929.25 | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  |  | JeouFwu | 1MUQTR2301008 | USC23C050 | DIF Foundation Modification | 5467.1 |  |  |  |  | 5467.1 | 5467.1 | 5467.1 | 1 | 0 | [40 empty] | 5467.1 | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  |  | MIC | 1MUQTR2310020 | USC22C016 | Gasket from Harrington_1018 request | 1389.21 |  |  |  |  | 1389.21 | 1389.21 | 0 | 1 | 0 | [56 empty] | 1389.21 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  |  | MIC | 1MUQTR2312012 | USC22C016 | Gasket from Harrington_1207 request | 7394.52 |  |  |  |  | 7394.52 | 7394.52 | 0 | 1 | 0 | [64 empty] | 7394.52 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | Chihhao | Sam | Lumax | 1MUQTS2308055_03 | USC22C007 | TSMC F21P1 FMCS Cycber Security _Onshore | 75356.05 |  |  |  |  | 48816.35 | 0 | 48816.35 | 0.64781 | 26539.7 | [68 empty] | 48816.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | Non-TSMC |  |  | Elaine Ma |  | Lumax, 王錫文(Steven_Wang) <Steven_Wang@elumax.com> | 1MUQTS2407009 | USC22C007 | LB pull back, conduit and repull & CUP ATS to FMCS | 27608.05 |  | 2024-07-10 |  | 100% by progress, T/T 30 Days | 0 | 0 | 0 | 0 | 27608.05 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | Elaine Ma |  | Fu Energy | 2958 | USC22C003 | Generator Upgrade | 174130 |  | 1/10/2024 |  | 100% by progress, T/T 35 days | 174130 | 0 | 174130 | 1 | 0 | [66 empty] | 17413 |  | 17413 | 0 | 34826 | 0 | 104478 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  |  | Fu energy | 408&1939&1958&1239&1256&1486&1619&1639&1719&2117 | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 16839902.57 |  |  |  |  | 15985353.25 | 15973721.65 | 15989403.79 | 0.94925 | 854549.32 | [22 empty] | 384408.18 |  | 16139.52 |  | 23353.38 |  | 402176.64 |  | 605481.78 |  | 2246205.09 |  | 2618760.97 |  | 802636.68 |  | 2807539.53 |  | 705887.74 |  | 3626615.08 |  | 792318.99 |  | 4471.74 |  | 485691.54 |  | 345110.15 |  | 98221.46 |  |  |  | 2326.32 |  | 6376.86 | [7 empty] | 2326.32 |  | 2326.32 | 0 | 0 | 0 | 0 | 0 | 6978.96 | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-Cheng | 4503446631_100 | USC21C005 | F21P1 Chemical package | 161491923 | Exempted | 2021-09-28 | T0 | PU53:95% on progress,5% 1 month after acceptance | 140764153 | 120131007 | 140764153 | 0.87165 | 20727770 |  |  | 0 |  |  |  | 6357154 |  | 8267774 |  | 37098 |  |  |  | 330830 |  | 6773215 |  | 138429 |  | 436333 |  | 3645524 |  | 2643193 |  | 5099104 |  | 6538191 |  | 14271658 |  | 10918065 |  | 8936549 |  | 7748104 |  | 2922004 |  | 3080184 |  | 2002915 |  | 1502663 |  | 1485139 |  | 2133453 |  | 5526885 |  | 2927140 |  | 1248187 |  | 2013345 |  | 2148731 |  | 1845069 |  | 6441702 |  | 2712369 |  | 2486799 |  | 5058396 | 0 | 8096816 | 0 | 1765962 | 0 | 3225173 | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu | Johnny Wan | TSMC, Chong-Cheng | 4503446631_200 | USC21C005 | F21P1 WCCS package | 33838332 | Exempted | 2021-09-28 | T0 | PU53:95% on progress,5% 1 month after acceptance | 29001780 | 22570523 | 29001780 | 0.85707 | 4836552 |  |  | 0 |  |  |  | 3179807 | [11 empty] | 2451350 |  |  |  | 0 |  | 0 |  | 341919 |  | 970270 |  | 3022943 |  | 1650539 |  | 365712 |  | 2657657 |  | 399184 |  | 341816 |  | 917809 |  | 369805 |  | 703124 |  | 902167 |  | 728284 |  | 1089594 |  | 945765 |  | 866726 |  | 340175 |  | 325877 | [5 empty] | 365100 |  | 2651042 | 0 | 0 | 0 | 1712720 | 0 | 1702395 | 0 | 0 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu | Dahlia | TSMC, 昱安 | 4503448339_100 | USC21C013 | F21P1 AMC | 5005543 | Exempted | 2021-09-29 | T0 | PU53:95% on progress,5% 1 month after acceptance | 4154386.71 | 3714209.48 | 4154386.71 | 0.82996 | 851156.29 | [6 empty] | 439256 | [13 empty] | 652637.48 |  | 0 |  | 672636 |  | 0 |  |  |  | 633325 |  | 0 |  | 0 |  | 423674 |  | 247322 |  | 129455 |  | 186209 |  | 183957 |  | 14718 | [15 empty] | 131020 | [5 empty] | 226865.7 | 0 | 213311.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu | Jaivan | TSMC, 昱安 | 4503448339_200 | USC21C013 | F21P1 THC | 2694457 | Exempted | 2021-09-29 | T0 | PU53:95% on progress,5% 1 month after acceptance | 2576070.26 | 1972112.82 | 2536275.9 | 0.95606 | 118386.74 |  |  | 0 |  |  |  | 235239 | [13 empty] | 351481.57 |  | 0 |  | 221686.93 |  | 0 |  |  |  | 454983.32 |  | 0 |  | 0 |  | 235377 |  | 86047 |  | 36012 |  | 0 | [5 empty] | 17516 | [9 empty] | 222627 |  |  |  | 111143 |  |  |  | 235720.5 |  | 110883.64 | 0 | 217558.94 | 0 | 0 | 0 | 0 | 0 | 39794.36 | 0
FAB Requirement (FAC) | 新工 |  | Low Voltage | Paul Hsu | Shawn | TSMC, Grant Shih <YUSHIH@TSMC.COM> | 4590001181_100 | USC22C010 | F21P1_LSC-CMS 5G System | 5642423.15 | Excluded | 2022-05-22 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 4895912.96 | 4599383.75 | 4773421.61 | 0.8677 | 746510.19 | [28 empty] | 688208 |  |  |  | 148994 | [7 empty] | 2605938 | [17 empty] | 808949 |  | 107025 |  | 181915 |  | 58354.75 |  | 60082.96 |  | 28704.26 | 0 | 16420 | 0 | 8668.75 | 0 | 60161.89 | 0 | 122491.35 | 0
FAB Requirement (FAC) | 新工 |  | Low Voltage | Paul Hsu | Shawn | TSMC, Grant Shih <YUSHIH@TSMC.COM> | 4590001181_200 | USC22C010 | F21P1_DPM 5G System | 5786087.37 | Excluded | 2022-05-22 | T0 | APB2:Pay on 28 next month: 90% on prog, 10 acpt | 4700172.71 | 4333176.47 | 4610793.43 | 0.81232 | 1085914.66 | [28 empty] | 778836 |  |  |  | 122562 | [7 empty] | 2920636 | [17 empty] | 310138 |  | 40683 |  | 121588 |  | 38733.47 |  | 139281.13 |  | 72254.75 | 0 | 50041.52 | 0 | 3844.93 | 0 | 12194.63 | 0 | 89379.28 | 0
FAB Requirement (FAC) | 新工 |  | UPW | Emon | Emon | TSMC, 得威 | 4590004026_100 | USC21C003 | F21P1 EBO UPW package | 375151 | Exempted | 2022-08-11 | T0 | AZ03:Pay in month end - 1 month after acceptance month | 356385 | 300771 | 356385 | 0.94998 | 18766 | [30 empty] | 74489 | [5 empty] | 114541 |  |  |  | 75647 | [9 empty] | 36094 | [15 empty] | 34253 |  | 0 | 0 | 0 | 0 | 21361 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | WWT | Jim Chiang | Grant | TSMC, 得威 | 4590004026_200 | USC21C009 | F21P1 EBO WWT package | 1016707 | Exempted | 2022-08-11 | T0 | AZ03:Pay in month end - 1 month after acceptance month | 855855 | 855855 | 855855 | 0.84179 | 160852 | [36 empty] | 81528 |  | 428150 |  | 2825 | [9 empty] | 302421 |  |  |  | 40931 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | UPW | Emon | Emon | TSMC, 得威 | 4590004027_100 | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 316495 | Exempted | 2022-08-11 | T0 | AZ03:Pay in month end - 1 month after acceptance month | 300674 | 285222 | 300674 | 0.95001 | 15821 | [30 empty] | 38397 | [7 empty] | 202105 | [11 empty] | 44720 | [17 empty] | 15452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | WWT | Jim Chiang | Grant | TSMC, 得威 | 4590004027_200 | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 446279 | Exempted | 2022-08-11 | T0 | AZ03:Pay in month end - 1 month after acceptance month | 414971.87 | 329192 | 414971.87 | 0.92985 | 31307.13 | [38 empty] | 38937 | [17 empty] | 32478 |  |  |  | 170796 |  | 86981 |  |  |  | 43712.78 |  | 0 | 0 | 42067.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | UPW | Emon | Emon | TSMC, 得威 | 4590004557_001 | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 342973.89 |  |  |  |  | 284673.38 | 43341 | 284673.38 | 0.83001 | 58300.51 | [42 empty] | 43341 | [25 empty] | 147056 | 0 | 20495.71 | 0 | 73780.67 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | WWT | Jim Chiang | Thomas | TSMC, 得威 | 4590004557_002 | USC21C009 | F21P1 Fab Lab WWT_Stage2 | 195433 |  |  |  |  | 0 | 0 | 0 | 0 | 195433 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QR | QR |  |  | Hank Su | Hank Su | TSMC | 4590006236_001 | USC23C013 | F21_AZQR_Hookup_Leak Panel | 2641194 |  |  |  |  | 0 | 0 | 0 | 0 | 2641194 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EBO | EBO |  |  | Hank Su | Hank Su | TSMC, A.C. Lee 黎安成 <ACLEE@TSMC.COM> | 4590006236_002 | USC23C013 | EBO21-Leak Panel | 389928 |  |  |  |  | 0 | 0 | 0 | 0 | 389928 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_001 | USC22C010 | CAP_F_ 91258 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_002 | USC22C010 | CAP_F_ 91259 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_003 | USC22C010 | CAP_F_ 91260 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_004 | USC22C010 | CAP_F_ 91261 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_005 | USC22C010 | CAP_F_ 91262 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_006 | USC22C010 | CAP_F_ 91263 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_007 | USC22C010 | CAP_F_ 91264 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_008 | USC22C010 | CAP_F_ 91265 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_009 | USC22C010 | CAP_F_ 91266 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_010 | USC22C010 | CAP_F_ 91268 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_011 | USC22C010 | CAP_F_ 90760 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 4200 | 0 | 4200 | 1 | 0 | [66 empty] | 4200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_012 | USC22C010 | CAP_F_ 90761 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_013 | USC22C010 | CAP_F_ 90762 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 4200 | 4200 | 4200 | 1 | 0 | [60 empty] | 4200 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_014 | USC22C010 | CAP_F_ 90763 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_015 | USC22C010 | CAP_F_ 90764 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 4200 | 0 | 4200 | 1 | 0 | [66 empty] | 4200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_016 | USC22C010 | CAP_F_ 90765 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 4200 | 0 | 4200 | 1 | 0 | [66 empty] | 4200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_017 | USC22C010 | CAP_F_ 90766 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 4200 | 0 | 4200 | 1 | 0 | [66 empty] | 4200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_018 | USC22C010 | CAP_F_ 90767 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 4200 | 0 | 4200 | 1 | 0 | [66 empty] | 4200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_019 | USC22C010 | CAP_F_ 90768 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 0 | 0 | 0 | 0 | 4200 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fab Work | 設備 |  | Low Voltage | Paul Hsu | Shawn Liu | TSMC, 楊子青 | 4590007694_020 | USC22C010 | CAP_F_ 90769 DPM Connection Project | 4200 |  | 2022-10-26 | T0 | AZB2:Pay on 28 next month: 90% on prog, 10 acpt | 4200 | 4200 | 4200 | 1 | 0 | [60 empty] | 4200 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistic | HK |  | Warehouse | Elaine Ma | Michelle H | TSMC, Jennifer | 4590008159_00100 | USC22C008 | F21P1-0420E4_H_Logistic_MIC | 2680642 |  | 2022-11-10 | T9 | AP03:Pay in month end - 1 month after acceptance month | 2680571.27 | 2680571.27 | 2680571.27 | 0.99997 | 70.73 | [32 empty] | 2645069.49 | [23 empty] | 35501.78 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistic | HK |  | Warehouse | Elaine Ma | Michelle H | TSMC, Jennifer | 4590008159_00200 | USC22C008 | F21P1-0420_H_Logistic_MIC | 21688833 |  | 2022-11-10 | T9 | AP03:Pay in month end - 1 month after acceptance month | 21688160.317 | 21688160.317 | 21688160.32 | 0.99997 | 672.683 | [34 empty] | 714772.61 |  | 46322.09 |  | 1826511.29 |  | 0 |  | 0 |  | 3204636.269 |  | 3349337.76 |  | 0 |  | 5709214.748 |  | 3909695.68 |  | 1852533.56 |  | 1075136.31 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | Chemical | Steven Chiu | Johnny Wan | TSMC, Chris Grider <CGRIDER@TSMC.COM>; SCKUOE@TSMC.COM | 4590008229_001 | USC23C012 | F21P1 Hot DI Machine Hookup | 240000 |  |  |  |  | 120041 | 82883 | 107789 | 0.50017 | 119959 | [48 empty] | 12884 |  | 32209 |  | 37790 | [13 empty] | 24906 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12252 | 0 | 0 | 0
FAB Requirement (FAC) | 新工 |  | Chemical | Steven Chiu | Johnny Wan | TSMC | 4590008229_002 | USC21C005 | F21P1 TGCM Room | 50000 |  |  |  |  | 45064 | 4705 | 35865 | 0.90128 | 4936 | [50 empty] | 4705 | [15 empty] | 31160 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9199 | 0 | 0 | 0
HK | HK | Foundation |  | Hank Su | Hank Su | TSMC, Samuel | 4590009384_100 | USC23C002 | F21P1-0404E4_H_foundation install_MICU | 1749804.22 |  | 2023-02-08 | T9 | AZ03:Pay in month end - 1 month after acceptance month | 1749804 | 1749804 | 1749804 | 1 | 0.22 | [40 empty] | 177829 |  | 347112 |  | 306216 |  |  |  | 767770 |  | 150877 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK | Foundation |  | Hank Su | Hank Su | TSMC, Samuel | 4590009384_200 | USC23C002 | F21P1-0423_H_foundation install_MICU | 32050195.78 |  | 2023-02-08 | T9 | AZ03:Pay in month end - 1 month after acceptance month | 21999801.49 | 18285535.47 | 20789475.67 | 0.68642 | 10050394.29 | [46 empty] | 4162068.28 |  | 1696480.68 |  | 4149440.52 |  | 4122495.69 |  | 1994686.39 |  | 381841.85 |  | 0 |  | 1277163 |  | 358843.52 |  | 142515.54 |  | 139155.54 |  | 1075150.66 | 0 | 0 | 0 | 0 | 0 | 1289634 | 0 | 1210325.82 | 0
HK | HK |  |  | John Gauci |  | TSMC | 4590015150_001 | USC23C055 | F21P1-0404_H_Labor 4 months_MICU | 39033874.97 |  | 01/20/2024 |  | Pay in month end - 1 month after acceptance month of the date | 39033874.97 | 39033874.97 | 39033874.97 | 1 | 0 | [60 empty] | 23025366.88 |  | 12210895.4 |  | 3797612.69 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | John Gauci |  | TSMC | 4590015150_002 | USC23C055 | F21P1-0404E2_H_Labor 4 months_MICU | 9750000 |  | 01/20/2024 |  | Pay in month end - 1 month after acceptance month of the date | 9750000 | 9750000 | 9750000 | 1 | 0 | [64 empty] | 9750000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | ME |  |  | Hank Su |  | TSMC | 4590016162_001 | USC23C055 | KKSV02 AMC-B10 Outlet Install material | 756.64 |  | 2024-03-09 |  | Pay in month end - 1 month after acceptance month of the date | 756.64 | 0 | 0 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 756.64 | 0
HK | ME |  |  | Hank Su |  | TSMC | 4590016162_002 | USC23C055 | KKSV04 AMC-B12 Outlet Install material | 2082.22 |  | 2024-03-09 |  | Pay in month end - 1 month after acceptance month of the date | 2082.22 | 0 | 0 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2082.22 | 0
HK | HK |  |  | John Gauci |  | TSMC, B.Y. Chang <BYCHANG@TSMC.COM> | 4590017712_001 | USC23C055 | F21P1-0423_H_Labor 1 months_MICU | 11494921.94 |  | 05/07/2024 |  | Pay in month end - 1 month after acceptance month of the date | 10725019.36 | 0 | 10725019.36 | 0.93302 | 769902.58 | [66 empty] | 10725019.36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | John Gauci |  | TSMC, B.Y. Chang <BYCHANG@TSMC.COM> | 4590017712_002 | USC23C055 | F21P1-0423E2_H_Labor 1 months_MICU | 1500000 |  | 05/07/2024 |  | Pay in month end - 1 month after acceptance month of the date | 1500000 | 0 | 1500000 | 1 | 0 | [66 empty] | 1500000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Hank Su |  | TSMC, Samuel Mokdad <SAMUELM@TSMC.COM> | 4590018007_001 | USC23C002 | F21P1-0423E4_H_FDN Seismic Support | 180000 |  | 2024-05-16 |  | Pay in month end - 3 month after acceptance month of the date | 0 | 0 | 0 | 0 | 180000 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | Hank Su |  | TSMC, Samuel Mokdad <SAMUELM@TSMC.COM> | 4590018007_002 | USC23C002 | F21P1-0423_H_FDN Seismic Support | 213905.04 |  | 2024-05-16 |  | Pay in month end - 2 month after acceptance month of the date | 0 | 0 | 0 | 0 | 213905.04 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  |  |  | TSMC, Pang Hsun Chu 朱邦巡 <PHCHUF@TSMC.COM> | 4590018396_100 | USC23C055 | F21P1-0404_H_E2 Management | 5454764 |  | 2024-05-31 |  | Pay in month end - 1 month after acceptance month of the date | 5454764 | 0 | 5454764 | 1 | 0 | [68 empty] | 5454764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HK | HK |  |  |  |  | TSMC, Pang Hsun Chu 朱邦巡 <PHCHUF@TSMC.COM> | 4590018396_200 | USC23C055 | F21P1-0404E2_H_E2 Management | 700000 |  | 2024-05-31 |  | Pay in month end - 1 month after acceptance month of the date | 700000 | 0 | 700000 | 1 | 0 | [68 empty] | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | Tylor | Sam | Zinter | 53584 & 53899 | USC22C006 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 3533920 |  |  |  |  | 3533920 | 3533920 | 3533920 | 1 | 0 | [32 empty] | 1060176 |  |  |  | 1060176 |  | 353392 |  |  |  | 530088 |  | 530088 | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | Kun An Liu |  | 伊思艾股份有限公司 | IMUQTS2206001-C |  | TSMC AZ Inlne ICPMS fire system control piping | 108800 |  |  |  |  | 0 | 0 | 0 | 0 | 108800 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  |  | Kanken | KTUS 20230321-1 | USC23C030 | Address Mapping | 2028 |  | 2023-03-21 |  |  | 2028 | 2028 | 2028 | 1 | 0 | [40 empty] | 2028 | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | Boris |  | Kanken | KTUS232311_001 |  | 2023 November Storage | 1575 |  | 11/28/2023 |  |  | 1575 | 1575 | 0 | 1 | 0 | [58 empty] | 1575 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  | UPW | Emon |  | Organo USA, Inc | LH0110023 | USC24C013 | Outsource Electrical Work | 40977.81 |  | 2/13/2024 |  | 100% BY PROGRESS | 0 | 0 | 0 | 0 | 40977.81 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | Non-TSMC |  | UPW | Kate |  | Organo USA, Fukawa, Jumpei (Jack) <Jack.Fukawa@OrganoUSA.com> | LH0170001 | Expect to add in USC24C013 | Panel Materials | 655000 |  | 2024-07-10 |  | Net 30 days | 655000 | 0 | 655000 | 1 | 0 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 655000 | 0 | 0 | 0
Base Build | Non-TSMC |  | UPW | Emo |  | Organo, Allen Tsai <allen-tsai@organo.com.tw> | LH0300001 | USC24C013 | WRC Pump Changes | 140434.63 |  | 2024-05-08 |  |  | 140434.63 | 0 | 140434.63 | 1 | 0 | [68 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140434.63 | 0
Base Build | Non-TSMC |  | UPW |  |  | Organo, Fukawa, Jumpei (Jack) <Jack.Fukawa@OrganoUSA.com> | LH0310001 | USC24C013 | TOC Analyzer | 795000 |  | 2024-05-08 |  |  | 715500 | 0 | 715500 | 0.9 | 79500 | [68 empty] | 0 | 0 | 715500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | Non-TSMC |  | UPW | Emon Roy |  | Organo USA | LH0370001 | Expect to add in USC24C013 | CIP Pump Change Out | 11726.98 |  | 07/29/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 11726.98 | [69 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  | Sam | MIC | M4SB1912072A | USC20C001 | Bidding proposal writing | 50000 |  |  |  |  | 50000 | 50000 | 50000 | 1 | 0 |  |  | 50000 | [65 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  | Sam | MIC | M52209038A | USC22C016 | Asahi Valve and Positioner from Harrington | 66751.38 |  |  |  |  | 66751.76 | 66751.76 | 66751.76 | 1 | -0.38 | [34 empty] | 66751.76 | [33 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  | Sam | MIC | M52212042A | USC22C016 | Asahi Valve and Positioner from Harrington - 3 | 926.3 |  |  |  |  | 926.3 | 926.3 | 926.3 | 1 | 0 | [38 empty] | 926.3 | [29 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  |  | Okland | nan | USC23C044 | Hookup Management | [5 empty] | 2116491.76 | 2112441.22 | 982412.34 | 1 | -2116491.76 | [38 empty] | 385510.54 |  | 146149.65 |  | 172549.65 |  | 146149.65 |  | 257691.06 |  | 188152.85 |  | 182152.85 |  | 247191.06 |  | 171952.85 |  | 214941.06 | [11 empty] | 0 | 0 | 4050.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | Non-TSMC |  | AMHS | David Nystrom | David Short | Murata(US) | PO048876 | USC23C011 | F21 P1 Power Design | 180000 |  |  |  |  | 125640 | 125640 | 125640 | 0.698 | 54360 | [40 empty] | 125640 | [27 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | Non-TSMC |  | AMHS | David Nystrom | David Short | Muratech-JP, T.Yashiro <toru.yashiro@nan.muratec.co.jp> | TV2301206274-7 | USC23C015 | F21 P1 Electrical Installation | 38479828.13 |  | 01/26/2024 |  | T/T 30 days after receipt of original invoice | 27278806.42 | 25698640.75 | 27278806.42 | 0.70891 | 11201021.71 | [40 empty] | 5295236.74 | [13 empty] | 6456886.2 |  | 6713230.71 |  | 1231340.92 | 12001.39 | 1413643.39 |  | 3928173.19 | 173262.36 | 660129.6 |  | 84299.46 |  | 0 | 0 | 823062.05 | 22525.46 | 637195.6 | 17654.2 | 0 | 0 | 35608.56 | 0
AMHS | Non-TSMC |  | AMHS | Martin |  | Muratech-JP, T.Yashiro <toru.yashiro@nan.muratec.co.jp> | TV2301206274-8 | USC23C015 | TSMC F21 AZP1 AMHS Wiring work outline | 1864987.5 |  | 2024-07-04 |  | T/T 30 days after receipt of original invoice | 1266929.63 | 0 | 1266929.63 | 0.67932 | 598057.87 | [69 empty] | 0 | 585640.95 | 32737.33 | 315817.53 | 17654.2 | 0 | 0 | 365471.15 | 20429.83
AMHS | Non-TSMC |  | AMHS | David Nystrom | David Short | Muratech-JP, T.Yashiro <toru.yashiro@nan.muratec.co.jp> | TV2301206274-9 | Expect to add in USC23C015 | TSMC F21 AZP1 AMHS Wiring work outline | 2998028.97 |  | 08/02/2024 |  | T/T 30 days after receipt of original invoice | 1083653.52 | 0 | 1083653.52 | 0.36146 | 1914375.45 | [72 empty] | 0 | 0 | 540343.24 | 30205.19 | 543310.28 | 30371.04
Others | Non-TSMC |  |  | Kate |  | Ma-Tek | UB00_230424001 | USC23C037 | MA-TEK AZ Lab Project | 277190 |  | 2023-04-24 |  | 100% by progress, net 30 days | 55438 | 55438 | 0 | 0.2 | 221752 | [54 empty] | 55438 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base Build | Non-TSMC |  |  | Martin |  | UIS | US100-O-0065 | USC22C024 | Grating materials for AAS system city inspection | 11878.35 |  | 1/2/2024 |  | Net 30 Days from invoice date | 11878.35 | 11878.35 | 0 | 1 | 0 | [62 empty] | 11878.35 | 664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  | Shannon | Sam | UIS | US120-Z-0064-A | USC22C024 | UIS Scaffolding | 3005096 |  |  |  |  | 3005096.07 | 3005096.07 | 3005096.07 | 1 | -0.07 | [22 empty] | 1286713.08 |  | 177670.88 |  | 1051201.52 |  | 489510.59 | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Non-TSMC |  |  |  |  | 大同聯合建築師事務所 | USCCT2111001 | USC22L001 | TSMC US Fab Architecture 施工駐地服務 | 351500 |  |  |  |  | 351500 | 351500 | 351500 | 1 | 0 | [8 empty] | 29174.5 |  |  |  | 29174.5 |  | 29174.5 |  | 29174.5 |  | 29174.5 |  | 29174.5 |  | 29174.5 |  | 29174.5 |  | 29174.5 |  | 29174.5 |  | 29174.5 |  | 30580.5 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMHS | AMHS |  |  | David Nystrom |  | TSMC | 4590021213 |  | CAP_E_F21 P1B AMHS HPM cable tray re-work | 522588.59 |  | 08/15/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 522588.59 | [73 empty] | 0 | 0 | 0 | 0 | 0
HK | HK |  |  | John Gauci |  | TSMC | 4590021215 | Expect to add in USC22C005 | F21P1-0423_H_UPW Material_MICU | 4831717.95 |  | 08/15/2024 |  | Pay in month end - 1 month after acceptance month of the date | 1327766.83 | 0 | 1125969.1 | 0.2748 | 3503951.12 | [73 empty] | 0 | 1125969.1 | 0 | 201797.73 | 0
Base Build | 新工 |  | Chemical | Steven Chiu |  | TSMC, Chong-Cheng | 4590021323 |  | F21P1 SDS Function Change Expansion V1.6 | 684093.85 |  | 08/16/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 684093.85 | [73 empty] | 0 | 0 | 0 | 0 | 0
O&M |  |  | Chemical | Steven Chiu |  | TSMC, Robert Serrano <SERRANOR@TSMC.COM> | 4590021332 |  | F21 MICU TCM Support - Aug 2024 | 374559.6 |  | 08/17/2024 |  | Pay in month end - 1 month after acceptance month of the date | 374559.6 | 0 | 0 | 1 | 0 | [73 empty] | 0 | 374559.6 | 0 | 0 | 0
HK |  |  |  | Kate |  | TSMC | 4590021581 |  | F21P1-0423_H_23K Tool Design US ManPower | 511456 |  | 08/22/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 511456 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build |  |  | Low Voltage | Paul Hsu |  | TSMC | 4590021580 |  | F21P1-0423_A_5G DPM CMS Support | 1010419.34 |  | 08/22/2024 |  | Pay in month end - 1 month after acceptance month of the date | 471889.25 | 0 | 0 | 0.46702 | 538530.09 | [73 empty] | 0 | 0 | 0 | 471889.25 | 0
Others |  |  |  | Elaine Ma |  | Micron | 4514231475 |  | HTF RN3000 (20 Kg) | 17910.55 |  | 08/20/2024 |  | Current Month End +60 days | 0 | 0 | 0 | 0 | 17910.55 | [73 empty] | 0 | 0 | 0 | 0 | 0
HK |  |  |  | Hank Su |  | TSMC, Samuel Mokdad <SAMUELM@TSMC.COM> | 4590021791 |  | F21P1-0423_H_Unit_MIC Foundation | 3841900 |  | 2024-08-27 |  | Pay in month end - 1 month after acceptance month of the date | 142536.84 | 0 | 0 | 0.037101 | 3699363.16 | [73 empty] | 0 | 0 | 0 | 142536.84 | 0
O&M |  |  | Chemical | Steven Chiu |  | TSMC | 4590021815 |  | F21P1 MIC Chemical Support Team July~Sep 24 | 1016002.05 |  | 2024-08-28 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 1016002.05 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build |  |  | UPW | Emon Roy alread contract out |  | TSMC, David Fugiel <DFUGIELA@TSMC.COM> | 4590021643 |  | UPW_MIC_EMERGENCY VALVE REPLACE | 1284 |  | 2024-08-23 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 1284 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Jim Chiang |  | TSMC, 得威/Joy | 4590021972 |  | Emergency work | 8972.68 |  | 2024-08-30 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 8972.68 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu |  | TSMC, Chong-Cheng | 4590021934 |  | F21P1 CDS/WCCS Expansion V1.6 | 7189476.52 |  | 2024-08-29 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 7189476.52 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu |  | TSMC, Chong-Cheng | 4590021935 |  | F21P1 VMB & Piping Expansion V1.6 | 4536009.3 |  | 2024-08-29 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 4536009.3 | [73 empty] | 0 | 0 | 0 | 0 | 0
AMHS |  |  | AMHS | David Nystrom |  | TSMC, David C.C. Fu 傅至傑 <CCFUC@TSMC.COM> | 4590022059 |  | CAP_E_F21 P1B L10 Scaffolding for Tunnel | 9120 |  | 2024-09-04 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 9120 | [73 empty] | 0 | 0 | 0 | 0 | 0
AMHS |  |  | AMHS | David Nystrom |  | TSMC, Josie Cheng <YJCHENGM@TSMC.COM> | 4590022060 |  | RLD_(522/T0)_F21 ZIP Cable Removal | 31680 |  | 2024-09-04 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 31680 | [73 empty] | 0 | 0 | 0 | 0 | 0
HK |  |  | HK | John Gauci |  | TSMC, Chang En Jiang 江長恩 <CEJIANG@TSMC.COM> | 4590022061 |  | Labor_IR machine repair | 3922 |  | 2024-09-04 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 3922 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | UPW | Emon Roy | Emon Roy | TSMC, 得威 | 4590021973 |  | F21P1 UPW Submain Expansion V1.6 | 1686849.69 |  | 2024-08-30 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 1686849.69 | [73 empty] | 0 | 0 | 0 | 0 | 0
HK | HK |  | HK | John Gauci |  | TSMC, Eric Chen 陳亮宇 <LYCHENT@TSMC.COM> | 4590022052 |  | F21P1-0404_H_MIC Equipment Rental | 9705841.43 |  | 2024-09-04 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 9705841.43 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build |  |  | Low Voltage | Paul Hsu |  | TSMC, <Megan Elmore MELMORE@TSMC.COM | 4590022271 | USC24C020 | F21P1-0423_H_CCTV_P1B | 51831.9 |  | 2024-09-07 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 51831.9 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build |  |  | WWT | Jim Chiang |  | TSMC, Joy | 4590022278 |  | CAP_F_ Sand blasting drain filter enhanc | 31565.2 |  | 2024-09-07 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 31565.2 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build |  |  | WWT | Paul Hsu |  | TSMC | 4590022283 | USC24C020 | CCTV and ACS for HPM(A&B) & pump room | 68953.83 |  | 2024-09-07 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 68953.83 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build |  |  | Low Voltage | Paul Hsu |  | TSMC, Vince Tsai <TCTSAIJ@TSMC.COM> | 4590022284 |  | MISC_F21_P1A_CCTV_Relocation | 156372 |  | 2024-09-07 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 156372 | [73 empty] | 0 | 0 | 0 | 0 | 0
Base Build | 新工 |  | WWT | Andy Chen |  | TSMC, Hung-Ruei Tsuei 崔紘瑞 <hrtsuei@tsmc.com> | 4590022280 |  | F21P1 WWT AWN System 2nd Source Enzyme | 462873.51 |  | 2024-09-07 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 462873.51 | [73 empty] | 0 | 0 | 0 | 0 | 0
HK |  |  | Warehouse | Ian Wong |  | TSMC, Wei Lin Yang <wlyangf@tsmc.com> | 4590022346 | USC24C017 | F21P1-0423_H_Glendale workshop HVAC | 38854.2 |  | 2024-09-10 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 38854.2 | [73 empty] | 0 | 0 | 0 | 0 | 0
AMHS |  |  | AMHS | David Nystrom | David Short | TSMC, David C.C. Fu 傅至傑 <CCFUC@TSMC.COM> | 4590022461 | USC22C025 | CAP_E_F21 P1 Sorter/BWBS AC Box Clash Rework | 61162.61 |  | 2024-09-12 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 61162.61 | [73 empty] | 0 | 0 | 0 | 0 | 0
HK |  |  | HK | John Gauci |  | TSMC, B.Y. Chang <BYCHANG@TSMC.COM> | 4590022549 | USC24C015 | F21P1-0423_H_E2_Labor_2024Q4 | 36850416.75 |  | 2024-09-13 |  | Pay in month end - 1 month after acceptance month of the date | 12270405 | 0 | 0 | 0.33298 | 24580011.75 | [73 empty] | 0 | 0 | 0 | 12270405 | 0
HK |  |  | Design | Kate Wu |  | TSMC, Arthur Chen <JSCHENZE@TSMC.COM> | 4590022558 |  | F21P1-0423_H_3D/2D Model_Oct.2024 | 133166 |  | 2024-09-13 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 133166 | [73 empty] | 0 | 0 | 0 | 0 | 0
HK |  |  | Foundation | Hank Su |  | TSMC, 王正富 <cfwangc@tsmc.com> | 4590022800 |  | CONSTR_(522/U0)KDSTSH foundation | 22199 |  | 2024-09-17 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 22199 | [73 empty] | 0 | 0 | 0 | 0 | 0
HK |  |  | HK | John Gauci |  | TSMC, Eric Chen 陳亮宇 <LYCHENT@TSMC.COM> | 4590022803 | USC24C015 | F21P1-0423_H_E2_Management_2024Q4 | 2484994.05 |  | 2024-09-18 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 2484994.05 | [73 empty] | 0 | 0 | 0 | 0 | 0
AMHS | Non-TSMC |  | AMHS | David Nystrom |  | Muratech-JP, T.Yashiro <toru.yashiro@nan.muratec.co.jp> | TV2301206274-10 |  | Muratec AMHS E2 Support_Sinfonia_2nd batch | 1525609.46 |  | 2024-09-19 |  | T/T 30 | 596445.66 | 0 | 596445.66 | 0.39096 | 929163.8 | [73 empty] | 0 | 0 | 0 | 596445.66 | 33341.32
AMHS |  |  |  | David Nystrom |  | Muratech-JP, T.Yashiro <toru.yashiro@nan.muratec.co.jp> | TV2301206274-11 |  | Muratec AMHS E2 Support_ALPS | 698883.33 |  | 09/30/2024 |  | T/T 30 | 0 | 0 | 0 | 0 | 698883.33 | [73 empty] | 0 |  | 0 | 0 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu |  | TSMC, Vince Tsai <TCTSAIJ@TSMC.COM> | 4590022428_001 |  | F21P1 TCO and non-TCO access control | 159798.46 |  | 09/11/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 159798.46 | [73 empty] | 0 |  | 0 | 0 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu |  | TSMC, Vince Tsai <TCTSAIJ@TSMC.COM> | 4590022428_002 |  | F21 P1 Egress motion requirement | 110013.4 |  | 09/11/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 110013.4 | [73 empty] | 0 |  | 0 | 0 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu |  | TSMC, Vince Tsai <TCTSAIJ@TSMC.COM> | 4590022428_003 |  | F21-P1_ Relocation speed gate at west te | 99501 |  | 09/11/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 99501 | [73 empty] | 0 |  | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu |  | TSMC, Chong-Cheng | 4590023708 |  | GC_Consumables_F21P1 GC 6" Rupture Disk | 9585.5 |  | 10/3/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 9585.5 | [73 empty] | 0 |  | 0 | 0 | 0
Base Build |  |  |  | Shannon |  | Ogano | A240010001 |  | Furniture for Organo | 4826.32 |  | 10/3/2024 |  | 30 Days | 0 | 0 | 0 | 0 | 4826.32 | [73 empty] | 0 |  | 0 | 0 | 0
Base Build | 新工 |  | Low Voltage | Paul Hsu |  | TSMC, Vince Tsai <TCTSAIJ@TSMC.COM> | 4590023789 |  | F21 P1 WH CCTV / ACS System requirement | 53354.76 |  | 10/3/2024 |  | Pay on 28 next month: 90% on prog, 10 acpt of the date | 0 | 0 | 0 | 0 | 53354.76 | [73 empty] | 0 |  | 0 | 0 | 0
Base Build | 新工 |  | Chemical | Steven Chiu |  | TSMC, Jamie Hsieh <schsiehm@tsmc.com > | 4590023864 |  | GC_Consumables_F21P1 GC TS135 Valve | 7008 |  | 10/05/2024 |  | Pay in month end - 1 month after acceptance month of the date | 0 | 0 | 0 | 0 | 7008 | [73 empty] | 0 |  | 0 | 0 | 0

## Updated PO Data
Type | Project # | Project Name | PO # | Total Contract $ | Main Page | CO/Added | Amy PO
Mechanical | USC21C003 | F21P1 Tunnel/lorry common support | 4590006744 | 5795851 | WWT | Added
GC | USC21C003 | F21P1 Tunnel/lorry common support | 4590006744 | 240481.244 | WWT | Added
Management | USC21C003 | F21P1 Tunnel/lorry common support | 4590006744 | 463668.056 | WWT | Added
Mechanical | USC21C003 | F21P1 UPW Temporary CP and piping | 4590009036 | 108600 | UPW | Added
GC | USC21C003 | F21P1 UPW Temporary CP and piping | 4590009036 | 6515 | UPW | Added
Management | USC21C003 | F21P1 UPW Temporary CP and piping | 4590009036 | 10860 | UPW | Added
Scope | USC21C003 | F21P1 QR Lab UPW | 4590004028 | 668561 | UPW
GC | USC21C003 | F21P1 QR Lab UPW | 4590004028 | 40114 | UPW
Management | USC21C003 | F21P1 QR Lab UPW | 4590004028 | 53484.9281 | UPW
Mechanical | USC21C003 | F21P1 UPW Temporary Resin and piping | 4590010557 | 144432 | UPW | Added
GC | USC21C003 | F21P1 UPW Temporary Resin and piping | 4590010557 | 7222 | UPW | Added
Management | USC21C003 | F21P1 UPW Temporary Resin and piping | 4590010557 | 14346 | UPW | Added
Others | USC21C003 | F21P1 CUP L20 Transformer Pads | 4590011254 | 135514.66 | UPW | Added
GC | USC21C003 | F21P1 CUP L20 Transformer Pads | 4590011254 | 0 | UPW | Added
Management | USC21C003 | F21P1 CUP L20 Transformer Pads | 4590011254 | 9485.34 | UPW | Added
Electrical | USC21C003 | F21P1 UPW temp power and MAU DI solution | 4590012982 | 540198.34 | UPW | Added
GC | USC21C003 | F21P1 UPW temp power and MAU DI solution | 4590012982 | 7448.66 | UPW | Added
Management | USC21C003 | F21P1 UPW temp power and MAU DI solution | 4590012982 | 71195 | UPW | Added
Steel Work | USC21C003 | F21P1 UPW Tank Swing Gate | 4590013482 | 70400 | UPW | Added
GC | USC21C003 | F21P1 UPW Tank Swing Gate | 4590013482 | 3520 | UPW | Added
Management | USC21C003 | F21P1 UPW Tank Swing Gate | 4590013482 | 9152 | UPW | Added
Electrical | USC21C003 | F21P1 UPW & WWT Battery Charge | 4590013633 | 228000 | UPW | Added
GC | USC21C003 | F21P1 UPW & WWT Battery Charge | 4590013633 | 2280 | UPW | Added
Management | USC21C003 | F21P1 UPW & WWT Battery Charge | 4590013633 | 34542 | UPW | Added
Electrical | USC21C005 | F21P1 CR temp lighting | 4590012687 | 70264 | Chemical | Added
GC | USC21C005 | F21P1 CR temp lighting | 4590012687 | 3513.2 | Chemical | Added
Management | USC21C005 | F21P1 CR temp lighting | 4590012687 | 11066.58 | Chemical | Added
Mechanical | USC21C005 | F21P1 Chemical Solvent day tank add vent | 4590012855 | 425434.49 | Chemical | Added
GC | USC21C005 | F21P1 Chemical Solvent day tank add vent | 4590012855 | 22591.7 | Chemical | Added
Management | USC21C005 | F21P1 Chemical Solvent day tank add vent | 4590012855 | 41973.81 | Chemical | Added
Steel Work | USC21C005 | F21P1 Lorry area fall protection tie off | 4590013430 | 272948.58 | Chemical | Added
GC | USC21C005 | F21P1 Lorry area fall protection tie off | 4590013430 | 13647.43 | Chemical | Added
Management | USC21C005 | F21P1 Lorry area fall protection tie off | 4590013430 | 40942.29 | Chemical | Added
Steel Work | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 4590013480 | 20559.01 | Chemical | Added
GC | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 4590013480 | 1027.95 | Chemical | Added
Management | USC21C005 | F21P1 NFPA Diamond Sign for Chemical Rm | 4590013480 | 3083.85 | Chemical | Added
Steel Work | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 4590013481 | 29700 | Chemical | Added
GC | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 4590013481 | 1485 | Chemical | Added
Management | USC21C005 | F21P1 Lorry Tank Swing Gates for Safety | 4590013481 | 4455 | Chemical | Added
Others | USC21C005 | F21P1 Lorry RU Chemical Filtration Impro | 4590013675 | 108900 | Chemical | Added
Management | USC21C005 | F21P1 Lorry RU Chemical Filtration Impro | 4590013675 | 16335 | Chemical | Added
Mechanical | USC21C009 | F21P1 CCB Lorry in drain system | 4590006293 | 594063.11 | WWT | Added
GC | USC21C009 | F21P1 CCB Lorry in drain system | 4590006293 | 63551.47 | WWT | Added
Scope | USC21C003 | F21P1 UPW A5 Backup Line Modification | 4590016257 | 62844.17 | UPW |  | x
GC | USC21C003 | F21P1 UPW A5 Backup Line Modification | 4590016257 | 3770 | UPW |  | x
Management | USC21C003 | F21P1 UPW A5 Backup Line Modification | 4590016257 | 9992 | UPW |  | x
Scope | USC21C003 | F21P1 EBO UPW package | 4590004026_100 | 329079.4071 | UPW |  | x
GC | USC21C003 | F21P1 EBO UPW package | 4590004026_100 | 19745 | UPW |  | x
Management | USC21C003 | F21P1 EBO UPW package | 4590004026_100 | 26326.3686 | UPW |  | x
Scope | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 4590004027_100 | 277627.18 | UPW |  | x
GC | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 4590004027_100 | 16657.63 | UPW |  | x
Management | USC21C003 | F21P1 IMP/CMP組頭間/噴砂間 UPW | 4590004027_100 | 22210.1743 | UPW |  | x
Scope | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 4590004557_001 | 300853 | UPW |  | x
GC | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 4590004557_001 | 18051 | UPW |  | x
Management | USC21C003 | F21P1 FAB Lab UPW_Stage2 | 4590004557_001 | 24068.34 | UPW |  | x
Management | USC21C009 | F21P1 CCB Lorry in drain system | 4590006293 | 49631.289 | WWT | Added
Mechanical | USC21C009 | F21P1 Formaldehyde treatment system | 4590006720 | 625199.16 | WWT | Added
GC | USC21C009 | F21P1 Formaldehyde treatment system | 4590006720 | 26000 | WWT | Added
Management | USC21C009 | F21P1 Formaldehyde treatment system | 4590006720 | 48800.84 | WWT | Added
Electrical | USC21C009 | F21P1 WWT construction temp power | 4590012872 | 363852 | WWT | Added
Management | USC21C009 | F21P1 WWT construction temp power | 4590012872 | 44148 | WWT | Added
Steel Work | USC21C009 | F21P1 230KV MTR NGR stand | 4590013495 | 78042 | WWT | Added
GC | USC21C009 | F21P1 230KV MTR NGR stand | 4590013495 | 9365.04 | WWT | Added
Management | USC21C009 | F21P1 230KV MTR NGR stand | 4590013495 | 11706.3 | WWT | Added
Steel Work | USC21C009 | F21P1 WWT Tank Swing Gate | 4590013571 | 119350 | WWT | Added
GC | USC21C009 | F21P1 WWT Tank Swing Gate | 4590013571 | 5968 | WWT | Added
Management | USC21C009 | F21P1 WWT Tank Swing Gate | 4590013571 | 15516 | WWT | Added
Electrical | USC21C009 | F21P1 WWT Electrical Testing Support | 4590013603 | 163735 | WWT | Added
Management | USC21C009 | F21P1 WWT Electrical Testing Support | 4590013603 | 18892.5 | WWT | Added
Steel Work | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 4590013803 | 1502984.58 | WWT | Added
GC | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 4590013803 | 102653.85 | WWT | Added
Management | USC21C009 | F21P1 WWT Mezzanines fireproof coating | 4590013803 | 128451.07 | WWT | Added
Electrical | USC21C013 | F21P1 EBO AMC Monitor system | 4590006871 | 918126 | Low Voltage | Added
GC | USC21C013 | F21P1 EBO AMC Monitor system | 4590006871 | 23000 | Low Voltage | Added
Electrical | USC21C013 | F21P1 AMC package-IMS wipe test | 4590013433 | 7680 | Low Voltage | Added
Management | USC21C013 | F21P1 AMC package-IMS wipe test | 4590013433 | 1152 | Low Voltage | Added
Electrical | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 4590013669 | 38004 | Low Voltage | Added
GC | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 4590013669 | 2280.24 | Low Voltage | Added
Management | USC21C013 | F21P1 THC Extension for WRC Scrubbers | 4590013669 | 6042.64 | Low Voltage | Added
Mechanical | USC22C009 | F21P1 MTR oil & drain pipe work | 4590000624 | 358335 | WWT | Added
GC | USC22C009 | F21P1 MTR oil & drain pipe work | 4590000624 | 21361 | WWT | Added
Management | USC22C009 | F21P1 MTR oil & drain pipe work | 4590000624 | 28304 | WWT | Added
Electrical | USC22C010 | F21P1 LV PDS on site installation | 4590000334 | 165168 | Low Voltage | Added
GC | USC22C010 | F21P1 LV PDS on site installation | 4590000334 | 9910.08 | Low Voltage | Added
Management | USC22C010 | F21P1 LV PDS on site installation | 4590000334 | 13213.44 | Low Voltage | Added
Electrical | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 4590002291 | 57083.38 | Low Voltage | Added
GC | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 4590002291 | 548.52 | Low Voltage | Added
Management | USC22C013 | F21P1 IMP/CMP組頭間/噴砂間 Security & CCTV | 4590002291 | 6907.53 | Low Voltage | Added
Others | USC22C021 | F21P1 Chemical Lab setup | 4590004281 | 414401.66 | Chemical | Added
GC | USC22C021 | F21P1 Chemical Lab setup | 4590004281 | 54616.55 | Chemical | Added
Management | USC22C021 | F21P1 Chemical Lab setup | 4590004281 | 35397.6012 | Chemical | Added
Mechanical | USC22C021 | F21P1 Chemical Lab Hookup | 4590008170 | 393600 | Chemical | Added
GC | USC22C021 | F21P1 Chemical Lab Hookup | 4590008170 | 76451 | Chemical | Added
Management | USC22C021 | F21P1 Chemical Lab Hookup | 4590008170 | 37599 | Chemical | Added
Mechanical | USC22C023 | F21P1 Piping Material Collaboration | 4590008240 | 2811729.15 | UPW | Added
Management | USC22C023 | F21P1 Piping Material Collaboration | 4590008240 | 231172.915 | UPW | Added
Steel Work | USC22C031 | F21P1 High-speed rolling door frame | 4590013431 | 22779.71 | WWT | Added
GC | USC22C031 | F21P1 High-speed rolling door frame | 4590013431 | 1139 | WWT | Added
Management | USC22C031 | F21P1 High-speed rolling door frame | 4590013431 | 3109 | WWT | Added
Mechanical | USC23C012 | F21P1 Hot DI Machine Hookup | 4590008229_001 | 196587 | Chemical | Added
GC | USC23C012 | F21P1 Hot DI Machine Hookup | 4590008229_001 | 38608 | Chemical | Added
Management | USC23C012 | F21P1 Hot DI Machine Hookup | 4590008229_001 | 4805 | Chemical | Added
Steel Work | USC23C042 | F21P1 Chemical safety cabinet installation | 4590004117 | 42873 | Chemical | Added
GC | USC23C042 | F21P1 Chemical safety cabinet installation | 4590004117 | 2572 | Chemical | Added
Management | USC23C042 | F21P1 Chemical safety cabinet installation | 4590004117 | 3429.824 | Chemical | Added
Electrical | USC23C043 | Electric Tiger Team_Fisk Support & Temp Power | 4590012300 | 376459 | WWT | Added
Management | USC23C043 | Electric Tiger Team_Fisk Support & Temp Power | 4590012300 | 48939.67 | WWT | Added
Electrical | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 4590012310 | 117700 | WWT | Added
GC | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 4590012310 | 5885 | WWT | Added
Management | USC23C051 | Tiger Team for CUP Cable Tray and Grounding Wiring for Transformers | 4590012310 | 11770 | WWT | Added
Electrical | USC24C006 | F21P1 Cast Resin PD Sensor Install/Test | 4590013944 | 58000 | UPW | Added
Management | USC24C006 | F21P1 Cast Resin PD Sensor Install/Test | 4590013944 | 11600 | UPW | Added
Others | USC23C056 | F21P1 WWT FAB LB2 Trench Cleanning | 4590014676 | 104312 | WWT | Added
Management | USC23C056 | F21P1 WWT FAB LB2 Trench Cleanning | 4590014676 | 36816 | WWT | Added
Steel Work | USC21C003 | F21P1 WRC L20 RACK Modification | 4590013928 | 15984 | WWT | CO
GC | USC21C003 | F21P1 WRC L20 RACK Modification | 4590013928 | 959 | WWT | CO
Management | USC21C003 | F21P1 WRC L20 RACK Modification | 4590013928 | 2541 | WWT | CO
Electrical | USC21C003 | F21P1 UPW Control Panel Temp Cable | 4590014674 | 699981.89 | UPW | CO
Scope | USC21C009 | F21P1 QR Lab WWT | 4590004029 | 2531199.59 | WWT |  | x
GC | USC21C009 | F21P1 QR Lab WWT | 4590004029 | 283786.83 | WWT |  | x
Management | USC21C009 | F21P1 QR Lab WWT | 4590004029 | 212453.35 | WWT |  | x
GC | USC21C003 | F21P1 UPW Control Panel Temp Cable | 4590014674 | 34999.0945 | UPW | CO
Management | USC21C003 | F21P1 UPW Control Panel Temp Cable | 4590014674 | 95547.528 | UPW | CO
Mechanical | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 4590014675 | 177120.35 | UPW | CO
GC | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 4590014675 | 10627 | UPW | CO
Management | USC21C003 | F21P1 UPW Damage by Other Trade Repair | 4590014675 | 28162 | UPW | CO
Mechanical | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 83646 | Chemical | CO
Electrical | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 38568 | Chemical | CO
GC | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 5597.28 | Chemical | CO
Management | USC21C003 | F21 P1 GC LAB HOOKUP Change Order | 4590015828 | 19171.69 | Chemical | CO
Management | USC21C007 | F21P1 VOC Burner NOx improve-installatio | 4590011320 | 88238.83 | Low Voltage | CO
Mechanical | USC21C007 | F21P1 VOC Burner NOx improve-installatio | 4590011320 | 678760.27 | Low Voltage | CO
GC | USC21C009 | F21P1 Discharge monitoring change | 4590004971 | 36436 | WWT | CO
Management | USC21C009 | F21P1 Discharge monitoring change | 4590004971 | 57090 | WWT | CO
Electrical | USC21C009 | F21P1 Discharge monitoring change | 4590004971 | 532474 | WWT | CO
Steel Work | USC21C009 | F21P1 WWT cable tray relo & add support | 4590013804 | 2078912.7 | WWT | CO
GC | USC21C009 | F21P1 WWT cable tray relo & add support | 4590013804 | 141990 | WWT | CO
Management | USC21C009 | F21P1 WWT cable tray relo & add support | 4590013804 | 177672 | WWT | CO
Steel Work | USC21C009 | F21P1 WWT LB2 Support Modification | 4590014187 | 16376 | WWT | CO
GC | USC21C009 | F21P1 WWT LB2 Support Modification | 4590014187 | 819 | WWT | CO
Management | USC21C009 | F21P1 WWT LB2 Support Modification | 4590014187 | 2580 | WWT | CO
Mechanical | USC21C009 | F21P1 WWT Per Diem and Acceleration | 4590014401 | 6264381 | WWT | CO
Mechanical | USC21C009 | F21P1 WWT AWR Drain to LSR System | 4590014629 | 51797.04 | WWT | CO
GC | USC21C009 | F21P1 WWT AWR Drain to LSR System | 4590014629 | 3107.82 | WWT | CO
Management | USC21C009 | F21P1 WWT AWR Drain to LSR System | 4590014629 | 8235.73 | WWT | CO
Electrical | USC21C009 | F21P1 WWT Panel Butten Change | 4590014630 | 86528 | WWT | CO
GC | USC21C009 | F21P1 WWT Panel Butten Change | 4590014630 | 865.28 | WWT | CO
Management | USC21C009 | F21P1 WWT Panel Butten Change | 4590014630 | 13108.99 | WWT | CO
Mechanical | USC21C009 | F21P1 WWT Per Diem and Acceleration | 4590015058 | 4142540.4 | WWT | CO
Electrical | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 4590015143 | 493675 | WWT | CO
GC | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 4590015143 | 29621 | WWT | CO
Management | USC21C009 | F21P1 WWT Discharge Temp Power/Redesign | 4590015143 | 78494 | WWT | CO
Mechanical | USC23C045 | F21P1 UPW Design Change (UMEC) | 4590013572 | 388723 | UPW | CO
GC | USC23C045 | F21P1 UPW Design Change (UMEC) | 4590013572 | 3887.23 | UPW | CO
Management | USC23C045 | F21P1 UPW Design Change (UMEC) | 4590013572 | 58891.5345 | UPW | CO
GC | USC23C054 | F21P1 WCCS Extend GC and Labor Incentive | 4590013806 | 661674 | Base-Build | CO
GC | USC23C054 | F21P1 Slurry Extend GC & Labor Incentive | 4590013807 | 1313687.25 | Base-Build | CO
GC | USC23C054 | F21P1 VOC Extend GC & Labor Incentive | 4590013808 | 104910 | Base-Build | CO
GC | USC23C054 | F21P1 CDS Extend GC & Labor Incentive | 4590013809 | 7083604.02 | Base-Build | CO
GC | USC23C054 | F21P1 UPW Extend GC & Labor Incentive | 4590013810 | 5008794.91 | Base-Build | CO
Scope | USC21C009 | F21P1 EBO WWT package | 4590004026_200 | 891848.65 | WWT |  | x
GC | USC21C009 | F21P1 EBO WWT package | 4590004026_200 | 53510.92 | WWT |  | x
Management | USC21C009 | F21P1 EBO WWT package | 4590004026_200 | 71347.8922 | WWT |  | x
Scope | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 4590004027_200 | 359598 | WWT |  | x
GC | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 4590004027_200 | 53861 | WWT |  | x
Management | USC21C009 | F21P1 IMP/CMP組頭間/噴砂間 WWT | 4590004027_200 | 32819 | WWT |  | x
GC | USC23C054 | F21P1 WWT Extend GC & Labor Incentive | 4590013811 | 577980.02 | Base-Build | CO
Mechanical | USC21C003 | F21P1 UPW | 4503290109 | 87980103 | UPW | Main
Electrical | USC21C003 | F21P1 UPW | 4503290109 | 20327458 | UPW | Main
Steel Work | USC21C003 | F21P1 UPW | 4503290109 | 28037246 | UPW | Main
Others | USC21C003 | F21P1 UPW | 4503290109 | 295650 | UPW | Main
GC | USC21C003 | F21P1 UPW | 4503290109 | 7618520 | UPW | Main
Management | USC21C003 | F21P1 UPW | 4503290109 | 12041023 | UPW | Main
Mechanical | USC21C004 | F21P1 WWT package (USA EQ - FRP tank) | 4503312319 | 6158273 | WWT | Main
Management | USC21C005 | F21P1 CDS package (B.10) | 4590009808 | 56024.4 | Chemical | Main
GC | USC21C005 | F21P1 CDS package (B.10) | 4590009808 | 109737.6 | Chemical | Main
Mechanical | USC21C005 | F21P1 CDS package (B.10) | 4590009808 | 1104238 | Chemical | Main
Mechanical | USC21C005 | F21P1 Chemical package | 4503446631_100 | 116849536.85 | Chemical | Main
Electrical | USC21C005 | F21P1 Chemical package | 4503446631_100 | 19303769.72 | Chemical | Main
Steel Work | USC21C005 | F21P1 Chemical package | 4503446631_100 | 11603571.43 | Chemical | Main
Others | USC21C005 | F21P1 Chemical package | 4503446631_100 | 2190000 | Chemical | Main
Management | USC21C005 | F21P1 Chemical package | 4503446631_100 | 10704880 | Chemical | Main
GC | USC21C005 | F21P1 Chemical package | 4503446631_100 | 840165 | Chemical | Main
Mechanical | USC21C005 | F21P1 WCCS package | 4503446631_200 | 28148814.3 | Chemical | Main
Electrical | USC21C005 | F21P1 WCCS package | 4503446631_200 | 493566.7 | Chemical | Main
Steel Work | USC21C005 | F21P1 WCCS package | 4503446631_200 | 500000 | Chemical | Main
Others | USC21C005 | F21P1 WCCS package | 4503446631_200 | 0 | Chemical | Main
GC | USC21C005 | F21P1 WCCS package | 4503446631_200 | 143197 | Chemical | Main
Management | USC21C005 | F21P1 WCCS package | 4503446631_200 | 4552754 | Chemical | Main
GC | USC21C005 | F21P1 TGCM Room | 4590008229_002 | 2311 | Chemical | Main
Management | USC21C005 | F21P1 TGCM Room | 4590008229_002 | 1476 | Chemical | Main
Others | USC21C005 | F21P1 TGCM Room | 4590008229_002 | 46213 | Chemical | Main
Mechanical | USC21C006 | F21P1 Slurry package | 4503428513 | 24635187 | Chemical | Main
Electrical | USC21C006 | F21P1 Slurry package | 4503428513 | 2723181 | Chemical | Main
Steel Work | USC21C006 | F21P1 Slurry package | 4503428513 | 740642 | Chemical | Main
Others | USC21C006 | F21P1 Slurry package | 4503428513 | 7219990 | Chemical | Main
GC | USC21C006 | F21P1 Slurry package | 4503428513 | 193000 | Chemical | Main
Management | USC21C006 | F21P1 Slurry package | 4503428513 | 3088000 | Chemical | Main
Management | USC21C006 | F21P1 Slurry Package support frame | 4590003895 | 87144 | Chemical | Main
Steel Work | USC21C006 | F21P1 Slurry Package support frame | 4590003895 | 580960 | Chemical | Main
Mechanical | USC21C006 | F21P1 SDS installation (B.10) | 4590009963 | 1829620 | Chemical | Main
GC | USC21C006 | F21P1 SDS installation (B.10) | 4590009963 | 9149 | Chemical | Main
Management | USC21C006 | F21P1 SDS installation (B.10) | 4590009963 | 110327 | Chemical | Main
Mechanical | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 8678203.9 | Low Voltage | Main
Electrical | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 4038484.1 | Low Voltage | Main
Others | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 3043495 | Low Voltage | Main
Management | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 2077130.37 | Low Voltage | Main
GC | USC21C007 | F21P1 VOC package (Installation) | 4503448403 | 844686.11 | Low Voltage | Main
Management | USC21C008 | F21 CCTV & Security | 4503441102 | 1741245 | Low Voltage | Main
GC | USC21C008 | F21 CCTV & Security | 4503441102 | 110638 | Low Voltage | Main
Electrical | USC21C008 | F21 CCTV & Security | 4503441102 | 10828117 | Low Voltage | Main
Management | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 11397325 | WWT | Main
Mechanical | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 79852928 | WWT | Main
Electrical | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 15724572.5 | WWT | Main
Steel Work | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 28940662.8 | WWT | Main
Others | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 3740308 | WWT | Main
GC | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4503432118 | 8766883.7 | WWT | Main
Steel Work | USC21C010 | Water pipeline installation (size>4") | 4503398624 | 5723522 | Water_Sewer | Main
Steel Work | USC21C010 | Water pipeline installation (size<4") | 4503423409 | 776478 | Water_Sewer | Main
Mechanical | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 4503432152 | 6753583.34 | WWT | Main
GC | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 4503432152 | 36367.35 | WWT | Main
Management | USC21C011 | F21P1 TMAH package (USA EQ + Installation) | 4503432152 | 519886.3134 | WWT | Main
Mechanical | USC21C011 | TMAH ACF system expansion | 4590008082 | 4146068 | WWT | Main
GC | USC21C011 | TMAH ACF system expansion | 4590008082 | 242858 | WWT | Main
Management | USC21C011 | TMAH ACF system expansion | 4590008082 | 382003.8 | WWT | Main
Electrical | USC21C012 | F21P1 Barcode & RFID for manufacturing | 4503441308 | 4819590 | Low Voltage | Main
GC | USC21C012 | F21P1 Barcode & RFID for manufacturing | 4503441308 | 249941 | Low Voltage | Main
Management | USC21C012 | F21P1 Barcode & RFID for manufacturing | 4503441308 | 722760 | Low Voltage | Main
Electrical | USC21C013 | F21P1 AMC | 4503448339_100 | 3401994 | Low Voltage | Main
Others | USC21C013 | F21P1 AMC | 4503448339_100 | 927549 | Low Voltage | Main
GC | USC21C013 | F21P1 AMC | 4503448339_100 | 66000 | Low Voltage | Main
Management | USC21C013 | F21P1 AMC | 4503448339_100 | 610000 | Low Voltage | Main
Mechanical | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 1205462 | Low Voltage | Main
Electrical | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 1118008 | Low Voltage | Main
Others | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 101456 | Low Voltage | Main
GC | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 11250 | Low Voltage | Main
Management | USC21C013 | F21P1 THC monitoring system | 4503448339_200 | 258280.2 | Low Voltage | Main
Mechanical | USC21C014 | F21P1 W-H2SO4 package | 4503489979 | 2568895 | WWT | Main
GC | USC21C014 | F21P1 W-H2SO4 package | 4503489979 | 388920 | WWT | Main
Management | USC21C014 | F21P1 W-H2SO4 package | 4503489979 | 312779 | WWT | Main
Others | USC22C018 | US Fab Frontage line hydrants | 4590005093 | 1087000 | Water_Sewer | Main
GC | USC22C018 | US Fab Frontage line hydrants | 4590005093 | 54040 | Water_Sewer | Main
Management | USC22C018 | US Fab Frontage line hydrants | 4590005093 | 86960 | Water_Sewer | Main
Mechanical | USC22C020 | F21P1 Penetration Pipe | 4590005240 | 917975 | UPW | Main
GC | USC22C020 | F21P1 Penetration Pipe | 4590005240 | 40227 | UPW | Main
Management | USC22C020 | F21P1 Penetration Pipe | 4590005240 | 91798 | UPW | Main
Mechanical | USC22C022 | F21P1 Triazole treatment system | 4590006189 | 3859622 | WWT | Main
GC | USC22C022 | F21P1 Triazole treatment system | 4590006189 | 103063 | WWT | Main
Management | USC22C022 | F21P1 Triazole treatment system | 4590006189 | 377315 | WWT | Main
Others | USC23C014 | F21P1 Labor incentive program-MICU | 4590008319 | 1625000 | UPW | Main
Steel Work | USC21C003 | F21P1 UPW WRC L10 Add Supports | 4590016147 | 10449.2 | UPW
Management | USC21C003 | F21P1 UPW WRC L10 Add Supports | 4590016147 | 1567.38 | UPW
Mechanical | USC24C014 | F21P1 CDS Pressure Test Appeal for PFC | 4590019011 | 30000 | Chemical
Management | USC24C014 | F21P1 CDS Pressure Test Appeal for PFC | 4590019011 | 4500 | Chemical
Mechanical | USC24C006 | F21P1 CDS & WCCS CO2 Suppression System | 4590019083 | 732426.9565 | Chemical
Management | USC24C006 | F21P1 CDS & WCCS CO2 Suppression System | 4590019083 | 109864.0435 | Chemical
Mechanical |  | F21P1 CDS Labor Incentive Nov 2023 | 4590019372 | 36000 | Chemical
Mechanical | USC24C006 | F21P1 WWT Labor Incentive Nov 2023 | 4590019487 | 60000 | WWT
Mechanical | USC23C045 | F21P1 UPW Labor Incentive Nov 2023 | 4590019488 | 15000 | UPW
Electrical | USC24C006 | F21P1 UPW Fiber Repull from Damage | 4590019489 | 136610.7043 | UPW
Management | USC24C006 | F21P1 UPW Fiber Repull from Damage | 4590019489 | 20491.6057 | UPW
Electrical | USC24C006 | F21P1 Add Card Reader at Material Gate | 4590019490 | 17654 | Low Voltage
Management | USC24C006 | F21P1 Add Card Reader at Material Gate | 4590019490 | 2634 | Low Voltage
Civil | USC24C006 | F21P1 WWT Doors &Triazole HK Pad Mod | 4590019491 | 12093.913 | WWT
Management | USC24C006 | F21P1 WWT Doors &Triazole HK Pad Mod | 4590019491 | 1814.087 | WWT
Mechanical | USC24C006 | F21P1 WWT Temp Chem. Leak Diverter Tarp | 4590019492 | 66780 | WWT
Management | USC24C006 | F21P1 WWT Temp Chem. Leak Diverter Tarp | 4590019492 | 10017 | WWT
Electrical | USC24C006 | F21P1 Speed Gate at Tent and CR Entrance | 4590019493 | 596110.44 | Low Voltage
Management | USC24C006 | F21P1 Speed Gate at Tent and CR Entrance | 4590019493 | 88877 | Low Voltage
Civil |  | F21P1 Hallway Plate Install | 4590019495 | 220500 | WWT
Management |  | F21P1 Hallway Plate Install | 4590019495 | 33075 | WWT
Mechanical | USC24C006 | F21P1 UPW ABG-A Submain Modification | 4590019922 | 67395.7913 | UPW
Management | USC24C006 | F21P1 UPW ABG-A Submain Modification | 4590019922 | 10109.3687 | UPW
Mechanical | USC24C006 | F21P1 UPW WRC NFPA Sign Installation | 4590019923 | 8055.9913 | UPW
Management | USC24C006 | F21P1 UPW WRC NFPA Sign Installation | 4590019923 | 1208.3987 | UPW
Electrical | USC24C006 | F21P1 Seismic Monitor | 4590019924 | 217165.2261 | Low Voltage
Management | USC24C006 | F21P1 Seismic Monitor | 4590019924 | 32574.7839 | Low Voltage
Electrical | USC24C006 | F21P1 UPW Cable Tray Reroute per Code | 4590019925 | 382152.513 | UPW
Management | USC24C006 | F21P1 UPW Cable Tray Reroute per Code | 4590019925 | 57322.877 | UPW
Mechanical | USC24C006 | F21P1 UPW Piping Damaged by Others | 4590019926 | 14504.7217 | UPW
Management | USC24C006 | F21P1 UPW Piping Damaged by Others | 4590019926 | 2175.7083 | UPW
Mechanical | USC24C006 | F21P1 UPW B Side MAU DI Temp Solution | 4590019927 | 104585.713 | UPW
Management | USC24C006 | F21P1 UPW B Side MAU DI Temp Solution | 4590019927 | 15687.857 | UPW
Civil | USC24C006 | F21P1 UPW WRC L20 Trench Modification | 4590019928 | 2914.7826 | UPW
Management | USC24C006 | F21P1 UPW WRC L20 Trench Modification | 4590019928 | 437.2174 | UPW
Mechanical | USC24C006 | F21P1 UPW Temp UPW Supply for ICPMS | 4590019929 | 143456.4783 | UPW
Management | USC24C006 | F21P1 UPW Temp UPW Supply for ICPMS | 4590019929 | 21518.4717 | UPW
Electrical | USC23C045 | F21P1 VOC MC Cable | 4590019947 | 453824.687 | Low Voltage
Management | USC23C045 | F21P1 VOC MC Cable | 4590019947 | 68073.703 | Low Voltage
Scope | USC23C045 | F21P1 MICU Settlement 1st_UPW | 4590020154 | 15117265.415 | UPW
Management | USC23C045 | F21P1 MICU Settlement 1st_UPW | 4590020154 | 2189385.135 | UPW
Mechanical | USC24C006 | F21P1 UPW Distribution Repair | 4590020155 | 82079.5565 | UPW
Management | USC24C006 | F21P1 UPW Distribution Repair | 4590020155 | 12311.9335 | UPW
Scope | USC23C045 | F21P1 MICU Settlement 1st_WWT | 4590020156 | 30215374.53 | WWT
Management | USC23C045 | F21P1 MICU Settlement 1st_WWT | 4590020156 | 2116405.63 | WWT
Scope | USC23C045 | F21P1 MICU Settlement 1st_CDS | 4590020157 | 12426921.31 | Chemical
Management | USC23C045 | F21P1 MICU Settlement 1st_CDS | 4590020157 | 2262364.64 | Chemical
Scope | USC23C045 | F21P1 MICU Settlement 1st_WCCS | 4590020158 | 2857297.975 | Chemical
Management | USC23C045 | F21P1 MICU Settlement 1st_WCCS | 4590020158 | 437877.025 | Chemical
Scope | USC23C045 | F21P1 MICU Settlement 1st_VOC | 4590020159 | 1805214.78 | Low Voltage
Management | USC23C045 | F21P1 MICU Settlement 1st_VOC | 4590020159 | 291918.02 | Low Voltage
Mechanical | USC24C006 | F21P1 UPW P1B Submain Expansion | 4590020160 | 134178.8261 | UPW
Management | USC24C006 | F21P1 UPW P1B Submain Expansion | 4590020160 | 20126.8239 | UPW
Mechanical | USC23C045 | F21P1 WWT AWN Enzyme Dosing Improvement | 4590020228 | 285836.5217 | WWT
Management | USC23C045 | F21P1 WWT AWN Enzyme Dosing Improvement | 4590020228 | 42875.4783 | WWT
Electrical | USC23C045 | F21P1 Security & CCTV DCR | 4590020230 | 237450.4348 | Low Voltage
Management | USC23C045 | F21P1 Security & CCTV DCR | 4590020230 | 35617.5652 | Low Voltage
Civil | USC24C006 | F21P1 UPW Mezzanine Modification | 4590020235 | 1311078.2609 | UPW
Management | USC24C006 | F21P1 UPW Mezzanine Modification | 4590020235 | 196661.7391 | UPW
Mechanical | USC24C006 | F21P1 WWT CWR System Improvement | 4590020236 | 579022.4783 | WWT
Management | USC24C006 | F21P1 WWT CWR System Improvement | 4590020236 | 86853.3717 | WWT
| USC24C006 | F21P1 MICU Settlement 2nd_UPW | 4590020302 | 7249177.3 | UPW
| USC24C006 | F21P1 MICU Settlement 2nd_WWT | 4590020303 | 7007538.06 | WWT
| USC24C006 | F21P1 MICU Settlement 2nd_CDS | 4590020304 | 7490816.54 | Chemical
| USC24C006 | F21P1 MICU Settlement 2nd_WCCS | 4590020305 | 1449835.46 | Chemical
| USC24C006 | F21P1 MICU Settlement 2nd_VOC | 4590020306 | 966556.97 | Low Voltage
Civil | USC22C011 | WRC Exterior Pads - NH3 and Diesel System/F21P1 WRC Exterior Pad (NH3&Diesel tank) | 4590007599 | 2296327 | WWT
Management | USC22C011 | WRC Exterior Pads - NH3 and Diesel System/F21P1 WRC Exterior Pad (NH3&Diesel tank) | 4590007599 | 183706 | WWT
| USC21C001 | AZ temp office CCTV and metal gate | 4503045358 | 110660.61 | Low Voltage
| USC21C002 | AZ Temp Office Access Control System/Sp | 4503243471 | 145958.4
| USC22C001 | US Fab Warehouse Security & CCTV | 4590000539 | 1906859 | Low Voltage
| USC22C001 | F21P1 Office Security & CCTV Packag | 4590000540 | 7311604 | Low Voltage
| USC22C010 | F21P1_LSC-CMS 5G System | 4590001181_100 | 5642423.15 | Low Voltage
| USC22C010 | F21P1_DPM 5G System | 4590001181_200 | 5786087.37 | Low Voltage
| USC22C013 | F21P1 QR Lab Security & CCTV | 4590002290 | 424087.84 | Low Voltage
| USC22C013 | Security&CCTV Package_CCD | 4590002292 | 306397.9 | Low Voltage
| USC21C009 | F21P1 Fab Lab WWT_Stage2 | 4590004557_002 | 195433 | WWT
| USC22C013 | F21P1 FAB Lab Security & CCTV_Stage2 | 4590004610 | 112375.63 | Low Voltage
| USC23C040 | F21P1_H_construction gown suit | 4590012251 | 130000
| USC21C006 | F21P1 Slurry 2 Additional Set Install | 4590014805 | 1590000 | Chemical
| USC22C013 | MISC_(TAX/T0)_(LB1 CCTV QTY6/MIC) | 4590015164 | 47320 | Low Voltage
| USC22C013 | Pull 108 cable | 4590018358 | 30019 | Low Voltage
|  | MIC Chemical Support Team Jul 5FTE | 4590020023 | 93854.08 | Chemical
|  | F21P1 SDS Function Change Expansion V1.6 | 4590021323 | 684093.85 | Chemical
|  | F21P1 CDS/WCCS Expansion V1.6 | 4590021934 | 7189476.52 | Chemical
|  | F21P1 VMB & Piping Expansion V1.6 | 4590021935 | 4536009.3 | Chemical
|  | Emergency work | 4590021972 | 8972.68 | WWT
|  | F21P1 UPW Submain Expansion V1.6 | 4590021973 | 1686849.69 | UPW
|  | F21P1 WWT AWN System 2nd Source Enzyme | 4590022280 | 462873.51 | WWT
|  | F21P1 TCO and non-TCO access control | 4590022428_001 | 159798.46 | Low Voltage
|  | F21 P1 Egress motion requirement | 4590022428_002 | 110013.4 | Low Voltage
|  | F21-P1_ Relocation speed gate at west te | 4590022428_003 | 99501 | Low Voltage
|  | GC_Consumables_F21P1 GC 6" Rupture Disk | 4590023708 | 9585.5 | Chemical
|  | F21 P1 WH CCTV / ACS System requirement | 4590023789 | 53354.76 | Low Voltage
|  | GC_Consumables_F21P1 GC TS135 Valve | 4590023864 | 7008 | Chemical