Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2855 | C | USCSB2310156A |  | Wire THNN | 45223 | 45229 | 129032.71 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 129032.71 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 129032.71 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 2856 | C | USCSB2310157A |  | HK UPW PVDF PP Materials | 45223 | 45227 | 255034.54 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 255034.54 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 5906.73 | 76765.6 |  |  | 19374.32 | 76746.82 | 35137.49 |  | 38557.08 |  | 2525.38 |  | 21.12 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2857 | C | USCSB2310158A | -01 | QC stickers shared by different trades | 45223 | 2023/10/26 2023/11/1 | 1343.75 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved | R1:Trade Term Correction Per Request |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 1343.75 | 0 | 1343.75 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2858 | C | USCSB2310160A |  | Tripod light & batteries | 45223 | 45230 | 1097.99 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1097.99 | 0 | 1097.99 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2859 | C | USCSB2310161A |  | MATERIAL HANDLERS (5) (Contract Staffing) | 45224 | 45237 | 366409.31 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 364303.22 | 0.99425 | 2106.09 | 0 | 2106.09 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 2946.88 | 13952.88 | 27393.5 |  | 0 | 0 | 34517.34 |  | 47355.41 |  | 46653.49 |  |  |  | 52324.7 |  |  |  | 47037.24 |  |  |  | 57542.97 | 0 | 34578.81 | - | 0 | - | 0 | 0
Base-Build | Base-Build | MMI | USC23C045 | WWT Change Order (Piping) | 2860 | C | USCSB2310162A |  | stripper pad duct rework (3areas) | 45224 | 45232 | 38885 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 38885 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 38885 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2861 | C | USCSB2310163A |  | FRP Grating Urgent Request | 45224 | 45225 | 9390 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9390 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 8920.5 | 0 | 0 | 0 |  |  | 469.5 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | MMI | USC23C045 | WWT Change Order (Piping) | 2862 | C | USCSB2310164A |  | 5.5 Missing Rack Steel | 45224 | 45224 | 9125 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9125 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 8668.75 | 0 | 0 | 0 |  |  | 456.25 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2863 | C | USCSB2310165A |  | QC Labels Yaho. shared by different trades | 45224 | 45225 | 37500 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 37500 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 34200 | 0 |  | 3300 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2864 | C | USCSB2310166A |  | Swagelok 90 Elbows | 45225 | 45225 | 766.24 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 766.24 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 | 766.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C059 | F21P1 Foundation T&M | 2865 | C | USCSB2310167A | -01 | 3000 T-Bolts | 45225 | 2023/10/26 2023/11/03 | 680 | -1300 | 1980 | V |  |  |  | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | Negotiate new rate and change packaging |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 680 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 680 | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2866 | C | USCSB2310168A |  | CED Bur terminal for Third | 45225 | 45225 | 5331.05 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5331.05 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 5331.05 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | MMI | USC23C045 | WWT Change Order (Piping) | 2867 | C | USCSB2310169A |  | Material receiving, off-loading, laydown labor | 45225 | 45233 | 294064 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 294064 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 | 294064 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2868 | C | USCSB2310170A |  | CDS Lorry A CO2 Offsets CO parts | 45225 | 45229 | 426.9 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 414.1 | 0.97002 | 12.8 | 0 | 12.8 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 143.3 |  | 0 |  | 270.8 | [6 empty] | 12.8 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | CCE | USC23C045 | WWT Change Order (Piping) | 2869 | C | USCSB2310171A |  | F21 CCTV system incentive for CCE | 10/27/2023 9/25/2024 | 11/8/2023 9/26/2024 | 60460.5 | -85880.5 | 146341 |  |  |  |  | Commercial Comm and Electric Inc | PR Approved | PO Approved | R1: As per PM Paul to close out this PO. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 60460.5 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 60460.5 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2870 | C | USCSB2310172A |  | Liquid argon for welding. Mainly shared by CYH, Tunyi. | 45226 | 45230 | 20890.32 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20833.42 | 0.99728 | 56.9 | 0 | 56.9 | 0 | [42 empty] | 0 | 0 |  | 3450 | 0 | 0 | 0 | 0 |  | 2419.26 | 0 | 0 | 1183.47 |  | 12202.99 |  |  |  | 591.25 |  | 986.45 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | NUUO | USC21C013 | F21P1 AMC THC Monitoring System | 2871 | C | USCSB2310174A |  | F21 THC PTFE Engineering | 2023/10/27 2024/8/1 | 2023/11/2 2024/8/7 | 322460.69 | -16971.61 | 339432.3 | V |  |  |  | NUUO US Inc. | PR Approved | PO Approved | R1: Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 230830.47 | 0.71584 | 91630.22 | 0 | 91630.22 | 122535.06 | [42 empty] | 0 | 0 |  | 0 | 212764.94 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 67887 |  |  | 18065.53 | 41819 |  | 29021.46 |  | - | 29021.46 | - | 32246.07 | 32246.07
Base-Build | AMC THC | NUUO | USC22C019 | AMC monitor 595T0 | 2872 | C | USCSB2310175A |  | F21 LITHO AMC Engineering | 45226 | 2023/10/31 2024/8/5 | 341453.75 | -17971.25 | 359425 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | R1: Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 341453.75 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 274634.8 |  | 0 | 0 | 0 |  | 0 |  | 66818.95 |  |  | 66818 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2873 | C | USCSB2310176A |  | cap/sus 304L for Tunyi. | 45226 | 45240 | 9398.92 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9398.92 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 9398.92 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 2874 | C | USCSB2310177A |  | San Tan Fire KSMGS1 Hot N2 | 45226 | 45230 | 2177.91 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 2177.91 | 0 | 2177.91 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2875 | C | USCSB2310178A |  | CED cable tray ground clamp for Third | 45226 | 45230 | 6330 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6330 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 6330 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC23C045 | WWT Change Order (Piping) | 2876 | C | USCSB2310180A |  | Liberty July invoice | 45227 | 45233 | 1317346 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1317346 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 1317346 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2877 | C | USCSB2310181A |  | Provide and install rocking 8 feet tall 42 inch wideth 30 feet long | 45227 | 45246 | 38500 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 38500 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 38500 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2878 | C | USCSB2310182A |  | AMHS Floor Recovery | 45227 | 45253 | 188000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 188000 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 71440 | 0 |  |  | 35720 | 0 | 35720 |  | 0 | [13 empty] | 45120 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC21C005 | F21P1 Chemical & WCCS package | 2879 | C | USCSB2310183A |  | CDS L10 CPVC chemical pipes | 45227 | 45241 | 60742.5 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 60742.5 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 60742.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2880 | C | USCSB2310184A |  | CDS Welder rental for Chemical welding. | 45227 | 45229 | 1400 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1400 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 1400 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2881 | C | USCSB2310185A |  | WWT CDA SUS Socket Weld Fittings | 45227 | 45229 | 621.84 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 621.84 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 621.84 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2882 | C | USCSB2310186A |  | MC Cable for Third | 2023/10/28 2023/11/7 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1:zero out USCSB2310186 |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | CCE | USC23C058 | F21 EUV Steel Plates | 2883 | C | USCSB2310187A |  | MIC EUV Crane Temp Power Final Removal | 45227 | 45238 | 32813.63 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 32813.63 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 32813.63 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2884 | C | USCSB2310188A | -01 | Harting crimpers and extraction for Third | 45227 | 2023/11/2 2023/11/4 | 1506.48 | [6 empty] | Mouser Electronics | PR Approved | PO Approved | R1: Ship-to Address Change |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1506.48 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 | 1506.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2885 | C | USCSB2310189A |  | Banner Industries Welding Equipment Pre Fab Construction | 45228 | 45230 | 2560 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2560 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 2560 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC23C045 | WWT Change Order (Piping) | 2886 | C | USCSB2310190A |  | WWT FAB drain rigging for common rack installation | 45230 | 45232 | 10775.2 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1616.28 |  |  |  | 1616.28 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2887 | C | USCSB2310191A |  | CDS Nippon Pillar Fittings for commission flushing | 45230 | 45231 | 147.64 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 147.64 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 96.31 |  |  |  |  | 51.33 |  |  |  |  | 51.33 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2888 | C | USCSB2310192A |  | CDS Lorry unistrut cages at Room 13, 12, 30,31 | 45230 | 45231 | 6868 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6868 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 6524.6 | 0 | 0 | 0 |  |  | 343.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C003 | F21P1 Module Tool Interconnection CVD | 2889 | C | USCSB2310193A |  | Rebuild KCANN1 Loa Lock Lines: -Orbital Weld VCR Micro Glands and Corresponding Male/Female Connector (MICU Provided) 3/8"Mal | 45230 | 45232 | 3800 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3800 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 3800 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2890 | C | USCSB2310195A |  | CDS HPM10 A Side DHL Drain cover PP plates requested | 45230 | 45231 | 442.5 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 442.5 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 442.5 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2891 | C | USCSB2310196A |  | EBO: CDA CABINET: INTERCONNECT MATERIAL FEMALE CONNECTOR | 45230 | 45231 | 25.62 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 25.62 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 25.62 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C003 | F21P1 Module Tool Interconnection CVD | 2892 | C | USCSB2310197A | -02 | Rebuild KCANN2 Loa Lock Lines: -Orbital Weld VCR Micro Glands and Corresponding Male/Female Connector (MICU Provided) 3/8"Mal | 45230 | 2023/11/1 2023/11/8 | 3800 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | PO R1:Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3800 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 3800 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2893 | C | USCSB2310198A |  | straight tee fittings w/ flanges for HL | 45230 | 45237 | 65745.05 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 65745.05 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 40957.45 | 0 | 0 | 1009.5 |  | 0 | 0 | 23778.1 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment | USC23C036 | F21P1 AMAT Interconnection | 2894 | C | USCSB2310199A |  | AMAT Shark Cages & Locks | 45230 | 45232 | 5427 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 5427 | 0 | 5427 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2895 | C | USCSB2310200A |  | Blank off Flange in various sizes for pumping line QC test. Tunyi | 45230 | 45232 | 22615 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 20015 | 0.88503 | 2600 | 0 | 2600 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 20015 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2896 | C | USCSB2310201A |  | grainger hardware shared materials | 45230 | 45232 | 8436.65 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8436.65 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 | 8424.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 12.42 | - | 0 | - | 0 | 0
Base-Build | WWT | Greenberry | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2897 | C | USCSB2310202A |  | Fabricate,paint & Install 6 NGR Stands | 45230 | 45232 | 78040 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 74138 | 0.95 | 3902 | 0 | 3902 | 3706.9 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 74138 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 3706.9
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2898 | C | USCSB2310203A |  | CMP: MSK1-4: INTERCONNECTION MATERIAL 3/8" EP PIPE | 45230 | 45233 | 108 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 108 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 108 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2899 | C | USCSB2310204A | -01 | AMHS Hole Framing and Cover Removal | 2023/10/31 2023/11/29 | 2023/11/10 2023/12/29 | 0 | -28028 | 28028 |  |  |  | V | Milling Machinery, Inc. | PR Approved | PO Approved | Cancelled as scope is covered in another order. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2900 | C | USCSB2311001A |  | EUV Foundation Drilling and Tapping | 45231 | 45259 | 19800 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 19800 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 19800 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2901 | C | USCSB2311002A |  | T-125AC Replacement Top Manway (Include manway, hardware, and gasket) | 45231 | 45232 | 892 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 892 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 892 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2902 | C | USCSB2311003A |  | EBO: ZFP3-1: INTERCONNECTION MATERIAL SUS304 DUCT & ELBOW | 45231 | 45233 | 2931.52 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2931.52 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 2931.52 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2903 | C | USCSB2311004A |  | mobile bar and pipe rack, wire mesh bins for UPW offsite construction | 45231 | 45233 | 4589.55 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 4589.55 | 0 | 4589.55 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 2904 | C | USCSB2311005A |  | TSMC CO Work for OBR to Install (2) Spacer on the Stripper Ducting. | 45231 | 45233 | 15749 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15749 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 15749 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 2905 | C | USCSB2311006A |  | (20) Epoxy kit to complete agitator installation | 2023/11/1 2023/11/3 2023/11/28 | X | 0 | [7 empty] | PR Approved | PO Approved | PR R2: Request to be canceled by Grant PR R1:add freight charge |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2906 | C | USCSB2311007A |  | test pipe pout under different sizes for Yaho | 45231 |  | 10800 | [7 empty] | PR Approved | PO Processing |  |  | 0 | [11 empty] | 0 | 0 | 10800 | 0 | 10800 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2907 | C | USCSB2311008A |  | Apex Precision Welding Mobil Welding LLC TSMC Unistrut Hanger Hole Rework | 45231 | 45232 | 26000 | [6 empty] | Apex Precision Mobile Welding, LLC DBA Apex Precision | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 17370 | 0.66808 | 8630 | 0 | 8630 | 0 | [42 empty] | 0 | 10000 |  | 0 | 0 | 6370 | 1000 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2908 | C | USCSB2311009A |  | Flexible Type UL approval, UA/LA style, Gray jacket color steel coore material | 45232 | 45244 | 31388.9 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31388.9 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 31388.9 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment | USC23C036 | F21P1 AMAT Interconnection | 2909 | C | USCSB2311010A |  | SHARK CAGES & LOCKS | 45232 | 45237 | 5481 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 5481 | 0 | 5481 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2910 | C | USCSB2311011A |  | COND/EMT Universal Clamp for Third | 45232 | 45236 | 419.03 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 419.03 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 419.03 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2911 | C | USCSB2311012A | -01 | Mesh bins, shoe covers & racks | 45232 | 2023/11/6 2023/11/14 | 7860 | -190 | 8050 |  | V |  |  | U-Line Corporation | PR Approved | PO Approved | PO R1:tax exempt, no longer need shoe cover |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 7860 | 0 | 7860 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Outsourcing | USC21C003 | F21P1 UPW | 2912 | C | USCSB2311013A |  | UPW-commissioning manpower | 45232 | 45237 | 82153.68 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 35632.51 | 0.43373 | 46521.17 | 0 | 46521.17 | 0 | [42 empty] | 0 | 0 |  | 0 | 22082.88 | 9282.38 | 0 | 4267.25 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC23C045 | WWT Change Order (Piping) | 2913 | C | USCSB2311014A |  | WWT CCE Change Orders | 45233 | 45237 | 315713.89 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 299928 | 0.95 | 15785.89 | 0 | 15785.89 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 299928 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2914 | C | USCSB2311015A |  | Electric Ops Electrical Work within Glendale Whs OSC Prefab-Taiwan Vendor Support | 45233 | 45236 | 22319.84 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 22319.84 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 22319.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2915 | C | USCSB2311016A |  | Plastic Submersible Cord Grip, NPT Threads for Third | 45233 | 45241 | 8113.92 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8113.92 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 8113.92 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2916 | C | USCSB2311017A |  | UPW-Degan-ACF-torque | 45234 | 45240 | 5200 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5200 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 5200 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2917 | C | USCSB2311018A |  | WWT-Ysgasket | 2023/11/4 2023/11/9 | 45239 | 22098 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | PR R1:Renew quotation |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 22098 | 1 | 0 | 0 | 0 | 22098 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3314.7 |  |  |  | 3314.7 |  |  | 22098 | 3314.7 |  | 5524.5 |  | - | 5524.5 | - | 5524.5 | 5524.5 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 2918 | C | USCSB2311019A |  | WWT-FRP-piping-T710AA | 45234 | 45241 | 41120.78 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 41120.78 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 41120.78 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2919 | C | USCSB2311020A |  | Mezzanine shaft wall paint | 45234 | 45248 | 65000 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 41326.16 | 0.63579 | 23673.84 | 0 | 23673.84 | 65000 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 9750 |  |  |  | 9750 |  |  | 41326.16 | 9750 |  | 16250 |  | - | 16250 | - | 16250 | 16250 | 0
Base-Build | WWT | MMI | USC23C045 | WWT Change Order (Piping) | 2920 | C | USCSB2311021A |  | WWT 18" backing ring | 45234 | 45241 | 6858 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6858 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 6515.1 | 0 | 0 | 0 |  |  | 342.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2921 | C | USCSB2311022A |  | WWT-BMWC-LSR -Train A | 45234 | 45258 | 50000 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 47500 | 0.95 | 2500 | 0 | 2500 | 2375 | [43 empty] | 0 |  | 0 | 0 | 47500 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 2375
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 2922 | C | USCSB2311023A |  | KEMEA5 ETC iPUP Mechanical R2 | 45234 | 45241 | 19131 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 19131 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 19131 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2923 | C | USCSB2311024A |  | UPW-GF-limitswitch | 45237 | 45237 | 1950.21 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1950.21 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 1950.21 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2924 | C | USCSB2311025A |  | UPW-UMEC-skid repair-3 | 45237 | 45239 | 14216 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 14216 | 0 | 14216 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 13505.2 |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2925 | C | USCSB2311026A |  | Panduit Terminal for Third for tool ATF-B07, AET-F14, ATF-C15, ATF-A04 | 45237 | 45240 | 3914.6 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3914.6 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 3914.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2926 | C | USCSB2311027A |  | Hand tools for TW team | 45237 | 45241 | 21528.4 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 21528.4 | 0 | 21528.4 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3229.26 |  |  |  | 3229.26 |  |  |  | 3229.26 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2927 | C | USCSB2311028A |  | WWT chemical storage in LB2 | 45237 | 45237 | 2099.16 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2099.16 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 2099.16 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2928 | C | USCSB2311029A | -01 | cleanroom backpack | 45237 | 2023/11/15 2023/11/26 | 965 | [6 empty] | S-TURBO D.I.Y. and HARDWARE CO., LTD. | PR Approved | PO Approved | PO R1: Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 965 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 965 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2929 | C | USCSB2311030A |  | Wire THNN 500Foot, copper conductor material for Third for ATF-BO7, AET-F14, ATF-C15, and ATF-A04 | 45237 | 45239 | 62850 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 62850 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 62850 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2930 | C | USCSB2311031A |  | Wire TCXH6/4G for Third for ATF-BO7, AET-F14, ATF-C15, and ATF-A04 | 45237 | 45239 | 12239.26 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 12239.26 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 12239.26 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Housekeeping | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2931 | C | USCSB2311032A |  | Materials for detail clean | 2023/11/8 2023/12/19 | 45293 | 76370 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | Higher amount includes Freight Charges of $6,370 ie 70% of Shipping Fee |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 76370 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 76370 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2932 | C | USCSB2311033A |  | Swagelok Tubing &connector | 45238 | 45240 | 5620.4 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5620.4 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 5620.4 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Outsourcing | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2933 | C | USCSB2311034A |  | TEOPM Functional Area Staffing Proposal for Coordinator Emmanuel Urias | 11/8/2023 10/4/2024 | 11/14/2023 10/11/2024 | 77276.2 | -22323.8 | 99600 |  |  |  |  | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 77276.2 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 35645.02 | 18121 | 7553 | 0 | 15957.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C003 | F21P1 Module Tool Interconnection CVD | 2934 | C | USCSB2311035A |  | Rebuild KCWNCN1 Loa Lock Lines: -Orbital Weld VCR Micro Glands and Corresponding Male/Female Connector (MICU Provided) 3/8"Ma | 45238 | 45253 | 5400 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5400 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 5400 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C003 | F21P1 Module Tool Interconnection CVD | 2935 | C | USCSB2311036A |  | Rebuild KCOXN4 Loa Lock Lines: -Orbital Weld VCR Micro Glands and Corresponding Male/Female Connector (MICU Provided) 3/8"Mal | 45238 | 45241 | 1800 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1800 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1800 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2936 | C | USCSB2311037A |  | Flex cable for Third. Tool id KDIGA3 KECOT1 KETRT7 KKDB03 KPOV04 KKDB04 KKSV02 | 45238 | 45245 | 14145.6 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 14145.6 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 14145.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2937 | C | USCSB2311038A |  | Pan Lug terminal for Third. Tool id KDIGA3 KECOT1 KETRT7 KKDB03 KPOV04 KKDB04 KKSV02 | 45238 | 45244 | 35460 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 35460 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 19643 | 1197 |  |  | 0 | 0 | 0 |  | 14620 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2938 | C | USCSB2311039A |  | Prominent H2O2 Starup service | 45238 | 45240 | 3500 | [6 empty] | Precision Integrated Systems, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1750 | 0.5 | 1750 | 0 | 1750 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 1750 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2939 | C | USCSB2311040A |  | Label Ribbon Kit For Printer, Shared product, Tool ID:KDSTS2, KDSTL1, KDSTS1 | 45239 | 45240 | 14121.2 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10645.54 | 0.75387 | 3475.66 | 0 | 3475.66 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 8923.54 | [5 empty] | 1722 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Helix | USC23C045 | WWT Change Order (Piping) | 2940 | C | USCSB2311041A |  | F21 P1 FAB A WWT Electrical Engineering (T&M) | 45239 | 45240 | 4935846 | [6 empty] | Okland Construction Company, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4911102.69 | 0.99499 | 24743.31 | 0 | 24743.31 | 49111.0269 | [43 empty] | 0 |  | 0 | 2202659.59 | 0 | 0 | 0 |  |  | 0 | 2217332.83 | 0 |  | 0 |  | 491110.27 |  |  | 246792.3 | [9 empty] | 0 |  | - | 0 | - | 0 | 0 | 49111.0269
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2941 | C | USCSB2311042A |  | install Dikewall around Tank 1985AA | 45239 | 45240 | 17280 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 17280 | 1 | 0 | 0 | 0 | 820.8 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 16416 | 0 | 0 | 0 |  | 0 | [13 empty] | 864 | 0 |  | - | 0 | - | 0 | 0 | 820.8
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2942 |  | USCSB2311043A |  | Fittings flange blind for Third. Tool id: KDIGA3 KECOT1 KETRT7 KKDB03 KPOV04 KKDB04 KKSV02 | 45239 | 45276 | 25969.31 | [6 empty] | Apollo Sheet Metal, Inc. DBA Apollo Mechanical Contractors | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 25969.31 | 0 | 25969.31 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2943 | C | USCSB2311044A |  | EBO: ZOCD-1: CDA CABINET INSTALL | 45239 | 45245 | 2400 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2400 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 2400 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2944 | C | USCSB2311045A |  | QR: KXMS01: EDGE TRIM | 11/9/2023 9/24/2024 | 11/16/2023 9/26/2024 | 230.06 | -0.03 | 230.09 |  |  |  |  | McMaster-Carr Supply Company | PR Approved | PO Approved | R1: Returning the rest of the funds back to the account. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 230.06 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 230.06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2945 | C | USCSB2311046A |  | EBO: ZCENT-1: CABLE TRAY | 45240 | 45246 | 516.17 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 516.17 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 516.17 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 2946 | C | USCSB2311047A |  | UPW-Cleanharbor ERC service | 45240 | 45240 | 5932.68 | [6 empty] | Clean Harbors Environmental Services Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 5932.68 | 0 | 5932.68 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2947 | C | USCSB2311048A |  | CDS blind flanges requested by Ben Chuang for pressure test. | 45240 | 45240 | 328.72 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 328.72 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 328.72 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2948 | C | USCSB2311049A |  | CDS Welder rental for Chemical welding. | 45240 | 45240 | 650 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 650 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2949 |  | USCSB2311050A |  | HK welding handle and tools | 45240 | 45249 | 349012.76 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 349012.76 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 172746.74 |  |  | 176266.02 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2950 | C | USCSB2311051A |  | CDS B side support Racks LB2/L30 | 45240 | 45266 | 224158 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 224158 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 106475.04 | 72094.33 | 0 | 45588.63 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Material | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2951 | C | USCSB2311052A |  | DP-B06 N2-NOZ 15A-2P Breaker | 45240 | 45239 | 680.19 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 680.19 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 680.19 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2952 | C | USCSB2311053A |  | CDS B side anchor plates | 45240 | 45251 | 8381.9 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8381.9 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 8381.9 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2953 | C | USCSB2311054A |  | Wire TCXH For Third KDIGA3 KECOT1 KETRT7 KKDB03 KPOV04 KKDB04 KKSV02 | 45241 | 45251 | 11402.7 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11402.7 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 11402.7 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC23C058 | F21 EUV Steel Plates | 2954 | C | USCSB2311055A |  | Transparent table mat, PE blue and white canvas and cleanroom tape for A side housekeeping and epoxy protecting. | 45241 | 45264 | 65024 | [6 empty] | Xiang Sheng Hardware Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 65024 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 65024 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2955 | C | USCSB2311056A |  | UPW-test kits | 45241 | 45245 | 127.43 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 127.43 | 0 | 127.43 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC23C045 | WWT Change Order (Piping) | 2956 | C | USCSB2311057A |  | WWT: Reposition T-780AA-2 Ladder | 45241 | 45246 | 6184 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6184 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 5581.06 | 0 | 0 |  | 0 | [5 empty] | 602.94 |  |  | 185.52 |  |  |  | 123.68 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2957 | C | USCSB2311058A | -01 | Material request E2 #4 | 45244 | 2023/11/20 2023/11/22 | 5378 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | PO R1: Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5378 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 5378 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2958 | C | USCSB2311059A |  | WWT 10T Termination Flange | 45244 | 45251 | 15916.8 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15916.8 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 15916.8 |  |  |  |  | 2387.52 |  |  |  | 2387.52 |  |  |  | 2387.52 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2959 | C | USCSB2311060A |  | KSSBA3 Wire Demo and Repull | 45245 | 45246 | 9955.83 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9955.83 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 9955.83 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C053 | AMAT Interconnection (TSMC) | 2960 | C | USCSB2311061A |  | KECOA1 Core Hole Sleeve Installation, Cable Tray and Dividers | 45245 | 45271 | 6140.05 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6140.05 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 6140.05 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2961 | C | USCSB2311062A | -01 | Hex for Tunyi. Tool id: ACM-B06 AMC-B03 AMC-B10 AIB-B02 APH-B11 AET-C13 ATF- | 45245 | 2023/12/11 2023/12/15 | 578 | -49.71 | 627.71 |  |  |  |  | Carson Sales Co Inc | PR Approved | PO Approved | PO R1: Tax Exempt |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 578 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 578 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2962 | C | USCSB2311063A |  | WWT-Safetystep for HPM | 45245 | 45250 | 8160 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 8160 | 6738 | 1422 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1224 |  |  |  | 1224 |  |  |  | 1224 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2963 | C | USCSB2311064A |  | AMAT CMP，Interconnection material Primer, 1 3/8" cush clamp | 45245 | 45246 | 695.36 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 695.36 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 695.36 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2964 | C | USCSB2311065A |  | Change Order total for KCENA1 | 45245 | 45246 | 1543.2 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1543.2 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 1543.2 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2965 | C | USCSB2311067A |  | change order: KCBDA1 Wire Demo and Repull | 45245 | 45260 | 11034.5 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11034.5 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 11034.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2966 | C | USCSB2311068A |  | WWT-misc support-HYC | 2023/11/16 2024/3/1 | 45262 | 0 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PR R1:The Supplier is suspended. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2967 | C | USCSB2311069A | -01 | WWT-HYC air testing manpower | 2023/11/16 2024/4/30 | 2023/11/27 2024/5/1 | 269240 | -129520 | 398760 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: As per Sam talked with Hua Yi:Shulan to descope PR USCSB2311069,其餘工程分其他下包，不得再請款 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 269240 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 269240 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 13462 |  |  |  | 13462 |  |  |  | 19938 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2968 | C | USCSB2311070A |  | WWT-MU-H910/T130 H/A680 | 45246 | 45251 | 6254.1 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 6254.1 | 0 | 6254.1 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 938.115 |  |  |  | 938.115 |  |  |  | 938.115 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2969 | C | USCSB2311071A |  | Vern Nut, regulator for | 45246 | 45252 | 7121.99 | [6 empty] | Vern Lewis Welding Supply, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7042.99 | 0.98891 | 79 | 0 | 79 | 0 | [43 empty] | 0 |  | 0 | 0 | 4630.09 | 0 | 0 |  | 2412.9 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2970 | C | USCSB2311072A |  | Liquid Argon for CHY PCW. Tool id: KCANN1, KDALS1, KCENA1 KECOA1 KCEPA1 KDPOT2 KEMEL1 KECOT2 KPAE01-S KESRT4 | 45246 | 45267 | 52134.12 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 52076.22 | 0.99889 | 57.9 | 0 | 57.9 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 50245.27 | 0 | 0 | 0 |  | 0 | [5 empty] | 1830.95 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2971 | C | USCSB2311073A |  | CDS:adapters for Fab CDU drain port at B side. | 45246 | 45248 | 347.2 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 347.2 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 125 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 222.2 |  |  |  |  | 222.2 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2972 | C | USCSB2311074A |  | Border States Electrical Work Material PreFab Area Open Statement Invoices | 45246 | 45252 | 22673.37 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20823.38 | 0.91841 | 1849.99 | 4665.6 | -2815.61 | 0 | [43 empty] | 0 | 20823.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2973 | C | USCSB2311075A |  | Tool Hook Up ManPower- 6 general workers | 45246 | 45251 | 38400 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 38400 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 38400 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Water | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2974 | C | USCSB2311076A |  | FAB 1A UPW, WWT CA Suppport (Electrical) | 45246 | 45251 | 39200 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5407.5 | 0.13795 | 33792.5 | 0 | 33792.5 | 4583.8 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 1610 | 0 | 0 |  | 1075 |  | 460 |  |  | 5880 | 2185 |  |  | 5880 |  |  | 77.5 | 5880 |  | 0 |  | - | 4583.8 | - | 0 | 0 | 0
Base-Build | VOC THC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 2975 | C | USCSB2311077A |  | FAB 1A VOC, AMC, THC CA Support (Electrical) | 45246 | 45250 | 14160 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 14160 | 0 | 14160 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 14160 |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2976 | C | USCSB2311078A |  | Magnum Hopper Bin for Trusval Chemical. KECOT5 KECOT1 KESTL3 | 45246 | 45248 | 1800 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1800 | 0 | 1800 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 2977 | C | USCSB2311080A |  | Tmah Hardware request #1(coated bolts not enough) | 45247 | 45248 | 1847.66 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 1847.66 | 0 | 1847.66 | 1847.66 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 1847.66 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2978 | C | USCSB2311081A |  | Turnlok Recept for Third. Tool id: ACM-B06, AMC-B03, AMC-B10, AIB-B02, APH-B11, AET-C13, ATF-B07, ATF-C15, ATF-E1 AE | 45247 | 45271 | 665.67 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 665.67 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 665.67 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2979 | C | USCSB2311082A |  | TW team tool - threaded machine(YAHO) | 45247 | 45248 | 3903.38 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3903.38 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 3903.38 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2980 | C | USCSB2311083A |  | UPW_Sulfuric Acid 96% | 45247 | 45248 | 31 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 31 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2981 | C | USCSB2311084A |  | Change Order: KECOA1 AC Box Cover Plate Notch. | 45247 | 45246 | 937.39 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 937.39 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 937.39 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2982 | C | USCSB2311086A |  | Change Order: KESDA1 AC Box Cover Plate Notch. | 45247 | 45246 | 937.39 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 937.39 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 937.39 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2983 | C | USCSB2311087A |  | Bay Alarm Company CCTV System Relocation | 45247 | 45247 | 1350 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 675 |  | 0 | [14 empty] | 0 | 675 | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2984 | C | USCSB2311088A |  | Change Order: KSSBA3 Wire Demo and Repull | 45247 | 45250 | 3441.93 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 3441.93 | 0 | 3441.93 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC THC | Material | USC21C013 | F21P1 AMC THC Monitoring System | 2985 | C | USCSB2311089A |  | F21 P1 VOC WWT line temporary support and THC ICA tack of point valves engineering | 45247 | 45251 | 18831 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18831 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 18831 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC21C005 | F21P1 Chemical & WCCS package | 2986 | C | USCSB2311091A |  | CDS L10 cleanroom SS chemical tubes | 45248 | 45253 | 40341.23 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 40341.23 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 40341.23 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC23C045 | WWT Change Order (Piping) | 2987 | C | USCSB2311092A |  | PSS SW-23-NOV Final prepay | 45248 | 45249 | 2200000 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2200000 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 2200000 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2988 | C | USCSB2311093A |  | WWT 300lb SUS Flange | 45248 | 45252 | 3492.06 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3492.06 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 3492.06 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C006 | F21P1 Slurry package | 2989 | C | USCSB2311094A |  | Southwest Fastener Monthly Order for Chemical Team 11/2023~01/2024 | 45250 | 45337 | 32775.86 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 31213.36 | 0.95233 | 1562.5 | 0 | 1562.5 | 0 | [49 empty] | 0 | 31213.36 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1562.5 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Water | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2990 | C | USCSB2311095A |  | Southwest Fastener Monthly Order for Water Team | 45250 | 45335 | 81287.41 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 81287.41 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 14457 | 66830.41 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2991 | C | USCSB2311096A |  | WWT-PP Materials | 45251 | 45253 | 9748 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 9748 | 0 | 9748 | 9748 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1462.2 |  |  |  | 1462.2 |  |  |  | 1462.2 |  | 2924.4 |  | - | 2924.4 | - | 3899.2 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2992 | C | USCSB2311097A |  | Progressive Commercial Interiors LLC- PCI Draper Roller Shade Installation | 45251 | 45252 | 3225 | [6 empty] | Progressive Commercial Interiors, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3225 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 3225 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2993 | C | USCSB2311098A |  | WWT Heat Exchanger Additional Support | 45251 | 45252 | 27061 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 27061 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 25707.95 | 0 |  |  | 1353.05 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2994 | C | USCSB2311099A | -01 | 100 tools Terminal demand | 45278 | 2023/12/18 2023/12/20 | 356731.48 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Change Completion Date from 12/31/2023 to 02/29/2024 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 356731.48 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 88640.17 | 9698.03 | 46508.74 |  | 130519.41 | 0 | 81365.13 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2995 | C | USCSB2311100A |  | CDS M421C0201-54 missing needle valves replacement. | 45251 | 45258 | 2040 | [6 empty] | JIM & STEVE INDUSTRIAL CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2040 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 | 2040 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 2040 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2996 | C | USCSB2311101A |  | 100 tools hard wares demand | 2023/11/21 2023/12/1 | X | 0 | [7 empty] | PR Approved | PO Approved | PR R1:canceled order |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Site Expense | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2997 | C | USCSB2311102A |  | WWT - 450 welder | 45251 | 45252 | 66000 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 66000 | 0 | 66000 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 9900 |  |  |  | 9900 |  |  |  | 9900 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2998 | C | USCSB2311103A | -02 | Industries pipe label, shared material | 2023/11/22 2024/1/17 | 2023/12/12 2023/12/16 2024/1/24 | 273885.6 | -2133.4 | 276019 |  |  |  |  | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved | R1: Remark Information Correction: Quotation No., Completion Date, Trade Term. R2: The price of this order has been decreased due to actual quantity changes. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 273885.6 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 273885.6 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2999 | C | USCSB2311104A | -01 | A side valve lacking, confirmed by MU all valves for A side. | 2023/11/22 2023/11/29 2023/12/15 | 2023/12/2 2023/12/29 | 77874.6 | 3597.3 | 74277.3 |  | V |  |  | Mega Union Technology Inc. | PR Approved | PO Approved | PR R1:Renew quotation PO R1: Renew quotation |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 77874.6 | 0 | 77874.6 | 77874.6 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 11681.19 |  |  |  | 11681.19 |  |  |  | 11681.19 |  | 19468.65 |  | - | 19468.65 | - | 19468.65 | 19468.65 | 0
Base-Build | VOC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 3000 | C | USCSB2311105A | -02 | FAB B VOC Electrical Permit and CA service | 2023/11/23 2023/12/14 | 2023/11/30 2023/12/5 2023/12/28 | 0 | -57905 | 57905 |  |  |  |  | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | R2: As per WanChun,the scope of this work order needs to revise it. So close this PR, and create a new PR. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 3001 | C | USCSB2311106A |  | FAB B UPW Electrical Permit and CA service | 45253 | 45259 | 164620 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 118684 | 0.72096 | 45936 | 0 | 45936 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 96318 | 0 |  | 0 |  | 15367.6 |  |  |  | 2332.8 | [5 empty] | 2332.8 |  |  | 0 |  | 2332.8 | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C060 | F21 CT Local Scrubber Interconnection | 3002 | C | USCSB2311107A |  | PCA: SEE LIST OF TOOLS: INTERCONNECT MATERIAL SIGNAL CABLE | 45253 | 45258 | 444.29 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 444.29 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 444.29 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 3003 | C | USCSB2311108A |  | CMP: MKS1-4: INTERCONNECT MATERIALS - STRUT, CUSH CLAMPS, 90 UNISTRUT BRACKET SS, HEX NUT | 45253 | 45268 | 778.45 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 778.16 | 0.99963 | 0.29 | 0 | 0.29 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 778.16 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC23C045 | WWT Change Order (Piping) | 3004 | C | USCSB2311109A |  | WWT CCE Change Orders_DC 680V cable CO | 45253 | 45259 | 8485.34 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8485.34 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 8485.34 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | Material | USC22C013 | F21P1 QR Lab Security & CCTV | 3005 | C | USCSB2311110A |  | F21 CCTV Engineering | 45253 | 45267 | 325000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 325000 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 325000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC22C013 | F21P1 QR Lab Security & CCTV | 3006 | C | USCSB2311111A |  | F21 CCD room CCTV & Security Equipment | 45253 | 45279 | 120982.1 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 101562 | 0.83948 | 19420.1 | 0 | 19420.1 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 28210 | 0 |  | 0 | [9 empty] | 73352 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3007 | C | USCSB2311112A |  | F21 Hookup保壓材料, KEMEL7, KSSBA1 | 45253 | 45264 | 132067.3 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 132067.3 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 132067.3 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 3008 | C | USCSB2311113A |  | WWT -Stripper-2"packing for 2 towers | 45258 | 45260 | 86100 | [6 empty] | LICI PLASTIC INDUSTRY CO. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 86100 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 9828 | 0 | 0 | 0 | 0 |  |  | 55692 | 0 | 0 |  | 0 |  |  |  |  | 4305 |  |  |  | 4305 | 20580 |  |  | 4305 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | FMCS | Material | USC22C007 | TSMC F21 FMCS Installation | 3009 | C | USCSB2311114A |  | tsmc F21P1 FMCS Cycber Security_Onshore | 45258 | 45260 | 65527 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 42449 | 0.64781 | 23078 | 0 | 23078 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 42449 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3010 | C | USCSB2311115A | -01 | Border States Electrical Work Material PreFab Area | 2023/11/28 2023/12/13 | 2023/11/28 2023/12/14 | 0 | -1780.67 | 1780.67 |  |  |  | V | Border State Industries, Inc. | PR Approved | PO Approved | PO R1:Since our work order was not acknowledged by Border States yet because of the account hold, we will cancel our order directly |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 3011 | C | USCSB2311116A |  | UPW-WRCL20-MMI-rack revise | 45258 | 45258 | 9968 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9469.6 | 0.95 | 498.4 | 0 | 498.4 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 9469.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3012 | C | USCSB2311117A | -01 | CDS LORRY TO BRIDGE PFA Tin in Swagelok SUS material Insert EP(Electro Polishing) | 45258 | 2023/11/30 2023/12/5 | 3683.55 | 705.6 | 2977.95 | V |  |  |  | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | PO R1:Renew quotation |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3683.55 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 3683.55 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3013 | C | USCSB2311118A |  | L30 PP/PVC Material Needed to Complete B-side | 45258 | 45265 | 69039.23 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 69039.23 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 61152.91 | 7886.32 |  | 0 | [8 empty] | 2071.1769 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC23C045 | WWT Change Order (Piping) | 3014 | C | USCSB2311119A |  | PSS SW-23-DEC Final prepay | 45258 | 45259 | 7800000 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7800000 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 7800000 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | interconnection | Labor | USC23C032 | F21_AZQR_Hookup_ Interconnection | 3015 | C | USCSB2311120A |  | EBO: CHAD/FAD LABS - CHANGE ORDER OF THE ORIGINAL CONTRACT C23331D | 45258 | 45259 | 16992 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 16992 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 16992 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 3016 | C | USCSB2311121A |  | QR: KXFX01, KXPS01: INTERCONNECT MATERIAL - 3 CONDUCTORS, 2 AWG WIRE | 45259 | 45265 | 36.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 36.12 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 36.12 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | General Condition | Outsourcing | USC23C022 | F21P1_H_2D/3D drawing | 3017 | C | USCSB2311122A |  | Kelly Outsourcing manpower | 45259 | 45266 | 676020 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 676020 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 | 676020 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3018 | C | USCSB2311123A |  | Items for Surprise warehouse | 45259 | 45261 | 4761.54 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4761.54 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 4761.54 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3019 | C | USCSB2311124A |  | Tool Hook Up Electrical labor | 45259 | 45267 | 186600.65 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 186148.63 | 0.99758 | 452.02 | 0 | 452.02 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 12054.38 |  | 0 | 0 | 57386.26 |  | 25347.38 |  |  |  | 28252.5 |  | 20151.2 |  |  |  | 23333.72 |  |  |  | 16510.69 | 0 | 3112.5 | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3020 | C | USCSB2311125A |  | CDS Nippon Pillar connectors used for PFA tie in on CDU and Tank of B side. | 45259 | 45260 | 1404.6 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1404.6 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 728.97 | 0 |  | 675.63 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3021 | C | USCSB2311127A |  | Electrolyte Gold, Replenishment solution | 45259 | 45262 | 752.36 | [6 empty] | Servomex Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 752.36 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 752.36 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3022 | C | USCSB2311128A |  | CDS Lorry Exhaust. Elbow 3/4" Super 300 Type | 45259 | 45260 | 233.4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 233.4 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 233.4 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3023 | C | USCSB2311129A |  | HK Hydraulic pipe bender for orientation/training | 45259 | 45260 | 1955.13 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1955.13 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1057.69 |  |  | 897.44 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3024 | C | USCSB2311130A |  | Unistrut for conduit installation KEMEL1 | 45259 | 45264 | 145.34 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 145.34 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 145.34 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | 5G | Material | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 3025 | C | USCSB2311131A |  | F21 CMS & DPM IMP Engineering | 2023/11/29 2023/12/5 | X | 0 | [7 empty] | PR Approved | PO Approved | PR R1:cancelled the PO |  | 0 | [11 empty] | 0 | 1 | 0 | 578.21 | -578.21 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Water | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3026 | C | USCSB2311132A |  | Hand tools for TW team | 45259 | 45261 | 5098.4 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5098.4 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 5098.4 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3027 | C | USCSB2311133A |  | UPW-ORGANO-flexible joints | 45259 | 45261 | 3360 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3360 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 3028 | C | USCSB2311134A |  | UPW-ladder lock | 45259 | 45261 | 34700 | [6 empty] | Scenic Industries, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 34700 | 0 | 34700 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C029 | EBO21- Tool interconnection | 3029 | C | USCSB2311135A |  | EBO: ZCOAT-1: CABLE TRAY INSTALL | 45259 | 45265 | 14400 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 14400 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 14400 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C029 | EBO21- Tool interconnection | 3030 | C | USCSB2311136A |  | EBO: ZASCS5-1: CABLE TRAY INSTALL | 45259 | 45265 | 15820 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 15820 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 15820 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3031 | C | USCSB2311137A |  | WWT-PSS-motor valve installation | 45259 | 45261 | 3357.6 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 503.64 |  |  |  | 503.64 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3032 | C | USCSB2311138A |  | WWT LSR CS material | 45259 | 45260 | 5534.57 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5534.57 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 5534.57 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3033 | C | USCSB2311139A |  | Snoop, Liquid Leak Detector, 1 gal (3.8 L) Bottle, shared material for gas system | 45259 | 45264 | 504.54 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 504.54 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 504.54 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 3034 | C | USCSB2311140A |  | CDS F21 Lorry A Solvent room Aegis/Co2 installation and inspection | 45260 | 45276 | 295688.64 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 280904.21 | 0.95 | 14784.43 | 0 | 14784.43 | 14784.43 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 236550.91 | 0 |  | 0 |  |  |  |  | 44353.3 | 44353.3 | [8 empty] | 14784.43 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC22C013 | F21P1 QR Lab Security & CCTV | 3035 | C | USCSB2311141A |  | F21 EBO CCTV & Security Equipment | 45260 | 45261 | 70670 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 62587 | 0.88562 | 8083 | 0 | 8083 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 25620 | 0 |  | 0 | [7 empty] | 36967 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Labor | USC23C032 | F21_AZQR_Hookup_ Interconnection | 3036 | C | USCSB2311142A |  | QR: KXPTR1, KXPTR2: INSTALL ELECTROPOLISHED STAINLESS STEEL (EP SS) & PFA TUBING TO SUPPORT GAS LINE INSTALL. | 11/30/2023 9/24/2024 | 12/11/2023 9/26/2024 | 42100.97 | -195.34 | 42296.31 |  |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: Returning the rest of the funds back to the account. Close PO. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 42100.97 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 42100.97 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3037 | C | USCSB2311143A | -01 | KCWCN1 | 45260 | 2023/12/4 2023/12/6 | 523.2 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 523.2 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 523.2 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 3038 | C | USCSB2311144A |  | F21 THC B side Equipment | 45260 | 45273 | 160060 | -55260 | 215320 |  |  |  |  | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 160060 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 20640 | 73680 |  | 0 |  | 65740 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3039 | C | USCSB2311145A | -01 | CDA line WRC L20 material | 2023/11/30 2023/12/8 | 2023/11/30 2023/12/8 | 0 | -874.32 | 874.32 |  |  |  |  | WW Grainger Inc | PR Approved | PO Approved | PO R1:As per responsible engineer to cancel the PR |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 3040 | C | USCSB2312001A | -01 | HK Chemical PVDF and PP Materials_aditional request | 45261 | 2023/12/6 2023/12/15 | 1017869.91 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | PO R1:remark revised based on Supplier feedback and confirm with Legal |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1016451.49 | 0.99861 | 1418.42 | 0 | 1418.42 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 34310.72 | 478990.91 | 0 |  | 42132.52 |  | 64472.16 |  | 3448.97 |  |  |  | 226776.16 |  | 154998.96 |  |  |  |  | 0 | 11321.09 | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 3041 | C | USCSB2312002A |  | HK Chemical PVDF HP Adaptor | 45261 | 45266 | 19082.4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 19082.4 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 19082.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC22C013 | F21P1 QR Lab Security & CCTV | 3042 | C | USCSB2312003A |  | CDS CED DFK Lorry HPM materials | 45261 | 45264 | 119370.32 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 119370.32 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 57254.36 | 0 | 62115.96 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3043 | C | USCSB2312004A |  | Connector, KRWRS6, KMOPA4-C | 2023/12/1 2023/12/12 | X | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Using the wrong budget/ project code. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3044 | C | USCSB2312005A |  | WWT -Stripper-2"packing -Harrington | 45261 | 45269 | 112500 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 112500 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 112500 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Greenberry | USC23C045 | WWT Change Order (Piping) | 3045 | C | USCSB2312006A |  | WWT Tunnel support | 45261 | 45269 | 55414 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 55414 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8312.1 | 55414 |  |  | 8312.1 |  |  |  | 8312.1 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3046 | C | USCSB2312007A |  | CDS expansion joint F1 lorry | 45261 | 45273 | 31800 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 31800 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 31800 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3047 | C | USCSB2312008A |  | Tool hookup Plastic material, KRWRS6, KMOPA4-C | 2023/12/1 2023/12/12 | X | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Using the wrong budget/ project code. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 3048 | C | USCSB2312009A |  | Helix bolts Tmah | 45261 | 45267 | 480 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 480 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 480 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3049 | C | USCSB2312010A |  | CDS IPA Thinner-3 boxes email "Clamp quantity" | 45261 | 45273 | 58200 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 58200 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 58200 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C006 | F21P1 Slurry package | 3050 | C | USCSB2312011A |  | CDS HongDong 2023 Nov construction work | 45262 | 45274 | 66929.4 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 66929.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 66929.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Equipment | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 3051 | C | USCSB2312013A | -01 | YAHO System Technology | 2023/12/2 2024/6/20 | 2023/12/16 2024/6/21 | 124000 | 12400 | 111600 |  |  | V |  | YAHO System Technology Co., Ltd. | PR Approved | PO Approved | Amount change is to add 1 additional tool. Change supplier's US-based company i.e. YAHO System Technology Inc. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 124000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 24800 |  | 0 | 0 | 12400 |  | 49600 | [13 empty] | 24800 | 0 | 12400 | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3052 | C | USCSB2312014A |  | WWT - FRP Bond (55) Post on TMAH Tanks for Handrail | 45265 | 45268 | 24435 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 24435 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3665.25 |  |  | 24435 | 3665.25 |  |  |  | 3665.25 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3053 | C | USCSB2312015A |  | ETC2，Interconnection material Cable Tray Divider | 45265 | 45267 | 726.75 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 726.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 726.75 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 3054 | C | USCSB2312016A |  | UPW-Linde-Nitrogen for test(Open PO) | 45265 | 45268 | 8000 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 717.14 | 0.089643 | 7282.86 | 0 | 7282.86 | 0 | [45 empty] | 0 | 0 | 568.81 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 148.33 | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3055 | C | USCSB2312017A |  | Tool Hook Up warehouse supplies | 45265 | 45266 | 38869.5 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 38869.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 38869.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | MIMO/Rigging | USC21C011 | F21 TMAH System | 3056 | C | USCSB2312018A |  | Tmah ACF expansion EQ move in | 45265 | 45269 | 21922 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21922 | 1 | 0 | 0 | 0 | 1041.295 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 3123.88 |  | 8933.22 | 0 | 8768.8 |  | 0 | [13 empty] | 1096.1 | 0 |  | - | 0 | - | 0 | 0 | 1041.295
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3057 | C | USCSB2312019A |  | WWT-lab tech-sink | 45265 | 45268 | 898.67 | [6 empty] | LabTech Supply Company Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 898.67 | 1 | 0 | 0 | 0 | 898.67 | [44 empty] | 898.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 134.8005 |  |  |  | 134.8005 |  |  |  | 134.8005 |  | 898.67 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3058 | C | USCSB2312020A |  | CDS 1-1/2"x2" 90 ELBOW 316LEP/304AP | 2023/12/5 2023/12/7 | 45268 | 11994 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11994 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 11994 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3059 | C | USCSB2312021A | -01 | CDS MY-TE 100AB Standard Electric Winch-Hoist for Lorry work | 45265 | 2023/12/7 2023/12/12 | 2808 | [6 empty] | Certex USA LLC | PR Approved | PO Approved | change payment term from 45 day to 30 day |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2808 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 2808 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | interconnection | Equipment | USC23C036 | F21P1 AMAT Interconnection | 3060 | C | USCSB2312022A |  | SHARK CAGES & LOCKS | 45265 | 45267 | 3143.19 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3143.19 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 79.12 | 0 | 0 |  |  | 0 | 0 | 0 |  | 3064.07 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 3061 | C | USCSB2312023A |  | DO Power Supply | 45265 | 45266 | 392 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 392 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 392 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Interconnection | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 3062 | C | USCSB2312025A |  | ASML Special barricade for TSMC EUV team | 45265 | 45365 | 18089.81 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 18089.81 | 1 | 0 | -58.53 | 58.53 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 18089.81 | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3063 | C | USCSB2312026A |  | Hex Head Bolt, Washer, Strut Channel Nut | 45265 | 45268 | 68.97 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 68.97 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 68.97 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3064 | C | USCSB2312027A |  | Chemical Lab Cabinets for WWT lab in WRC | 45266 | 45267 | 2300.44 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2300.44 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 2300.44 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3065 | C | USCSB2312028A |  | CDS commissioning 20L PE Tank/Bottle - Acid and alkali resistance requested by Steven Chiu. Qty: 20. | 45266 | 45290 | 546.4 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 546.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 546.4 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3066 | C | USCSB2312029A |  | Fork terminal for Third. Top 100 tools | 45266 | 45271 | 1350 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1350 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3067 | C | USCSB2312030A |  | CDS 1/4 in. x 800 ft. Nylon Solid Braid Rope, White for JuWei PFA line work requested by Jay Huang. | 45266 | 45271 | 349 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 313.57 | 0.89848 | 35.43 | 0 | 35.43 | 0 | 313.57 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 34.9 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3068 | C | USCSB2312031A |  | CDS #36 Rosary cord twine for JuWei PFA line work requested by Jay Huang. | 45266 | 45273 | 167.07 | [6 empty] | The Fish Net Company, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 161.75 | 0.96816 | 5.32 | 0 | 5.32 | 0 | 161.75 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3069 | C | USCSB2312032A |  | Tmah extra bolts requirement (MU) | 45266 | 45268 | 3190.2 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3190.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 2830.67 | 0 | 0 |  | 359.53 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3070 | C | USCSB2312033A |  | Change Order KCEPA1 AC Cover Modifications & Insulated Cable Clamps | 45266 | 45269 | 1790.82 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1790.82 | 0 | 1790.82 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C053 | AMAT Interconnection (TSMC) | 3071 | C | USCSB2312034A |  | Change Order total for KKDB04 | 45266 | 45267 | 2020.78 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2020.78 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 2020.78 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Water | UMEC | USC23C045 | WWT Change Order (Piping) | 3072 | C | USCSB2312035A |  | WWT-UPW RO to T780 and 780 temp plates | 45288 | 45288 | 93494 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 93494 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 88819 | 0 | 0 | 0 |  | 4675 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 3073 | C | USCSB2312036A |  | MICU Coating bolts for Tmah. | 45266 | 45269 | 9375.2 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9375.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 9375.2 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3074 | C | USCSB2312037A |  | WWT_Manpower support _MEGA | 45267 | 45273 | 1178171.5 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 588647.14 | 0.49963 | 589524.36 | 0 | 589524.36 | 1178171.5 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 176725.725 |  |  |  | 176725.725 |  |  | 588647.14 | 176725.725 |  | 235634.3 |  | - | 235634.3 | - | 235634.3 | 235634.3 | 235634.3
Interconnection | interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3075 | C | USCSB2312038A |  | KCSNA1 Material Request for Seal-Tite conduit and supporting hardware | 45267 | 45269 | 166.01 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 166 | 0.99994 | 0.01 | 0 | 0.01 | 0 | [45 empty] | 0 | 0 | 0 | 166 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 3076 | C | USCSB2312039A |  | F21EBO ZASC5-1 UPW hookup material | 45267 | 45271 | 14382.74 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 14382.74 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 13845.74 | [5 empty] | 537 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3077 | C | USCSB2312040A |  | KCSOA4 Material request for Seal-Tite conduit, supporting hardware, rigid EMT conduit, and grounding hardware | 45267 | 45269 | 1002.08 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1002.08 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1002.08 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3078 | C | USCSB2312041A |  | LSW Engineers Additional electrical installation to support TSMC & Taiwan Vendors | 45267 | 45271 | 5100 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5100 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 4100 |  |  | 0 | 1000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3079 | C | USCSB2312042A |  | KCSOA4, KCSNA1 Material request from WESCO for Seal-Tite cable conduit and hardware | 45267 | 45272 | 6859.58 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6859.58 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 6100.26 | 759.32 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3080 | C | USCSB2312043A |  | Shared material. labels and label makers. Open PO | 45267 | 45275 | 100000 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 98559.81 | 0.9856 | 1440.19 | 0 | 1440.19 | 0 | [45 empty] | 0 | 0 | 0 | 534 | 0 | 1419.39 | 9856 | 0 | 0 | 33335.8 |  | 0 |  | 1567.92 |  |  |  | 12542.75 |  |  |  | 89.99 |  | 37824 |  | 1389.96 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C006 | F21P1 Slurry package | 3081 | C | USCSB2312044A |  | CDS CO2 System, Lorry A, certify design and test. | 45267 | 45273 | 223520 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 201168 | 0.9 | 22352 | 0 | 22352 | 0 | [45 empty] | 0 | 67056 | 0 | 0 | 0 | 134112 |  | 0 | 0 | 0 |  | 0 | [8 empty] | 22352 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3082 | C | USCSB2312045A |  | WWT _7/8 washer extra | 45267 | 45267 | 119.04 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 119.04 | 0 | 119.04 | 119.04 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 17.856 |  |  |  | 17.856 |  |  |  | 17.856 |  | 119.04 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3083 | C | USCSB2312046A |  | PowerStudies, Inc. agrees to furnish training materials and an instructor to teach the Low Voltage Qualified (Arc Flash and NFPA 70E) | 45267 | 45274 | 19800 | [6 empty] | PowerStudies, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 19800 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 19800 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3084 | C | USCSB2312047A |  | WWT_LB2 LSR Scope_BMWC | 45268 | 45294 | 591435 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 561863.25 | 0.95 | 29571.75 | 0 | 29571.75 | 28093.1625 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 365211.11 | 50567.79 |  | 0 |  | 146084.35 |  |  | 29571.75 |  |  |  | 59143.5 |  |  |  | 59143.5 |  | 0 |  | - | 0 | - | 0 | 0 | 28093.1625
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3085 | C | USCSB2312048A |  | WWT-FRP-piping-T780AA | 45268 | 45271 | 36096.83 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 36096.83 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 36096.83 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3086 | C | USCSB2312049A |  | MK Products Welding equipment in support of OSC & TSMC | 45268 | 45287 | 4341.32 | [6 empty] | MK Products, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4341.32 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 4341.32 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3087 | C | USCSB2312050A |  | WRC Lab Exhaust Hood | 45268 | 45271 | 4950 | [6 empty] | Silicone Future Manufacturing Company Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4950 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 4950 |  |  | 742.5 |  |  |  | 742.5 |  |  |  | 742.5 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3088 | C | USCSB2312051A |  | Cable tie for high pressure hose. Trade: CYH PCW. Top 100 tools | 45268 | 45272 | 6625 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 6625 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 6625 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3089 | C | USCSB2312052A |  | Discount Saw Cut LLC Concrete core drilling in support of Taiwan Vendors | 45268 | 45300 | 650 | [6 empty] | DISCOUNT SAW CUT, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 650 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3090 | C | USCSB2312053A |  | office supplies for tool hookup department | 2023/12/8 2024/7/25 | 2023/12/11 2024/7/26 | 2951.71 | 245.2 | 2706.51 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1 - Inclusion of sales tax |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2720.4 | 0.92164 | 231.31 | 0 | 231.31 | 0 | 2720.4 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3091 | C | USCSB2312054A |  | CDA line WRC L20 material revise | 45268 | 45267 | 916.32 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 916.32 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 235.68 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 45.816 |  |  |  | 91.632 | 680.64 |  |  | 91.632 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3092 | C | USCSB2312055A |  | Amazon order for James McCormick | 45268 | 45271 | 1974.6 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1466 | 0.74243 | 508.6 | 0 | 508.6 | 0 | 1466 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Equipment | USC23C058 | F21 EUV Steel Plates | 3093 | C | USCSB2312056A |  | Provide generator rental for temporary power staged outside of Fab building on West side. | 45268 | 45271 | 119203 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 119203 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 119203 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3094 | C | USCSB2312057A |  | CDS CED DFK Lorry HPM materials additional quote | 45268 | 45268 | 258.13 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 258.13 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 258.13 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3095 | C | USCSB2312059A |  | CDS Argon for Chemical welding. Blanket order | 45268 | 45273 | 11030.8 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10862.89 | 0.98478 | 167.91 | 0 | 167.91 | 0 | [45 empty] | 0 | 0 | 0 | 989.04 | 1994.04 | 2230.4 |  | 0 | 0 | 1208.83 |  | 191.25 |  | 2960.5 |  | 1027.58 | 429.16 | 261.25 | [8 empty] | 0 |  | - | 0 | 155 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3096 | C | USCSB2312060A | -01 | Stackable Plastic Bin Box, shared materials with upw system | 2023/12/8 2023/12/18 | 2023/12/11 2023/12/18 | 1802.54 | 265.85 | 1536.69 | V |  |  |  | McMaster-Carr Supply Company | PR Approved | PO Approved | PR R1: Shipping fee increased due to expedition |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1320.8 | 0.73274 | 481.74 | 0 | 481.74 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1320.8 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3097 | C | USCSB2312061A |  | Lee Collins Air Conditioning Installation of HVAC Systems mini split configuration clean rooms | 45269 | 45272 | 8955.18 | [6 empty] | Lee Collins Air Conditioning | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8955.18 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 8955.18 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3098 | C | USCSB2312062A |  | WWT_CCE CO58 stripper disconnect switch and CO35 RIO Conduit. | 45269 | 45273 | 126710.89 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 120375.33 | 0.95 | 6335.56 | 0 | 6335.56 | 0 | [45 empty] | 0 | 0 | 0 | 120375.33 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3099 | C | USCSB2312063A |  | WWT - Install L30 Drains | 2023/12/9 2024/3/6 | 2024/1/3 2024/3/6 | 1036853 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | Amount revised to settle actual work completed and release excess budget |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 985010.35 | 0.95 | 51842.65 | 0 | 51842.65 | 194539.575 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 98475.1 |  | 0 | 0 | 305273.95 |  | 265883.15 |  | 39575.1 |  |  | 155527.95 |  |  |  | 155527.95 | 68951 |  |  | 155527.95 |  | 38907.915 | 206852.05 | - | 38907.915 | - | 38907.915 | 38907.915 | 38907.915
Base-Build | WWT | Equipment | USC21C011 | F21 TMAH System | 3100 | C | USCSB2312064A |  | WWT_Testing tool | 45269 | 45271 | 1583.25 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1583.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1583.25 |  | 0 |  |  |  |  | 237.4875 |  |  |  | 237.4875 |  |  |  | 237.49 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 3101 | C | USCSB2312065A |  | CDS Lorry Crossover Steps. | 45269 | 45273 | 3591 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3591 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 3411.45 |  | 0 |  | 179.55 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Equipment | USC23C058 | F21 EUV Steel Plates | 3102 | C | USCSB2312066A |  | EUV Temp Power Generator Rental 4 M | 45269 | 45275 | 92660 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 92660 | 0 | 92660 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3103 | C | USCSB2312067A | -01 | UPW-Horiba adaptor | 2023/12/9 2023/12/15 | 2023/12/12 2023/12/15 | 204 | 2 | 202 | V |  |  |  | HORIBA Taiwan, Inc. | PR Approved | PO Approved | PR R1: Unit rate round up to $34 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 204 | 1 | 0 | -60.3 | 60.3 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 204 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3104 | C | USCSB2312068A |  | Connector, KRWRS6, KMOPA4-C | 45272 | 45273 | 2228.4 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2228.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 2228.4 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3105 | C | USCSB2312069A |  | Tool hookup Plastic material, KRWRS6, KMOPA4-C | 45272 | 45274 | 1283.72 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1283.72 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 806.8 | 0 | 476.92 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3106 | C | USCSB2312070A |  | MU/Hand welding machines for WWT | 45272 | 45294 | 17619.4 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 17619.4 | 0 | 17619.4 | 17619.4 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 2642.91 |  |  |  | 2642.91 |  |  |  | 2642.91 |  | 5285.82 |  | - | 5285.82 | - | 7047.76 | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3107 | C | USCSB2312071A |  | 400CL-005H 1/2" PIPE P/E CLR PVC SCH40, | 45272 | 45274 | 316 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 316 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 316 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 3108 | C | USCSB2312072A |  | AMAT_ME_KKSV02_CGB 2" connector, 2" to 1" reduec washer | 45272 | 45273 | 1767.6 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1767.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 1767.6 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3109 | C | USCSB2312073A |  | CDS Electronic pressure recorder CR87P requested by Henry | 45273 | 45275 | 2194 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2194 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 2194 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3110 | C | USCSB2312074A | -01 | Tool Hookup Terminals a Replacement for USCSB2311101 | 45273 | 2023/12/15 2023/12/19 | 97468.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Change Comletion Date |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 97468.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 74476.4 |  |  | 0 | 0 | 6114.1 |  | 9860.4 |  | 7017.6 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3111 | C | USCSB2312075A |  | E-OPS Installers for 3 Months | 45273 | 45274 | 137659.41 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 132907.78 | 0.96548 | 4751.63 | 0 | 4751.63 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 11852.51 |  | 0 | 0 | 87075.42 |  | 33979.85 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3112 | C | USCSB2312076A |  | Home Depot tools for 永旗. New arrival trade new tools request | 45273 | 45276 | 2063.23 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1899.84 | 0.92081 | 163.39 | 0 | 163.39 | 0 | 1899.84 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3113 | C | USCSB2312077A |  | Home Depot tools for 漢科. New arrival trade new tools request | 45273 | 45276 | 7199.22 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7199.22 | 1 | 0 | 0 | 0 | 0 | 7199.22 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 3114 | C | USCSB2312078A |  | CDS DHL Upper level walking steps for A side two catwalks | 45273 | 45274 | 34626 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 34626 | 1 | 0 | 0 | 0 | 3376.04 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 31249.96 | 0 | 0 |  | 0 | [5 empty] | 3376.04 | [8 empty] | 0 |  | - | 0 | - | 0 | 3376.04
Base-Build | Triazole | Material | USC22C022 | F21P1 Triazole treatment system | 3115 | C | USCSB2312079A |  | WWT - Remove Unused Triazole Pad in WRC between E14 and D14 | 45273 | 45274 | 750 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 750 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 750 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 3116 | C | USCSB2312080A | -01 | WWT - Lab glassware | 45273 | 2023/12/14 2023/12/19 | 2853.14 | [6 empty] | Laboratory Sales and Service | PR Approved | PO Approved | PO R1:Changing payment options from NET 30 to Prepayments |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2853.14 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 2853.14 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 3117 | C | USCSB2312081A |  | F21 EBO PVC MET UNION ADPT | 45273 | 45275 | 97.15 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 97.15 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 97.15 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3118 | C | USCSB2312082A |  | CDS 1-1/2"x2" 45 ELBOW 316LEP/304AP | 45274 | 45273 | 2149.2 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2149.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 2149.2 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3119 | C | USCSB2312083A |  | Terminals for Third. Alternative Vendor | 45274 | 45276 | 1813.98 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1813.98 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1813.98 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3120 | C | USCSB2312084A |  | 2" OD STRUT CLAMP for Tunyi PPL top 100 tools. | 45274 | 45275 | 183.67 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 183.67 | 1 | 0 | 73499.96 | -73499.96 | 0 | [45 empty] | 0 | 0 | 0 | 183.67 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3121 | C | USCSB2312085A |  | Brother printer, share materials, tool hook up | 45274 | 45276 | 969.32 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 944.32 | 0.97421 | 25 | 0 | 25 | 0 | 944.32 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3122 | C | USCSB2312086A |  | Consolidated Electrical Distributors material for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45274 | 45275 | 1725 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1725 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1725 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3123 | C | USCSB2312087A |  | Tube clamp, | 45274 | 45275 | 37200 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 37200 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 28200 | 9000 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3124 | C | USCSB2312088A |  | RS Payroll Services contracted labor/staffing of material handlers, general laborers & various skill sets | 45274 | 45279 | 152382.62 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 152135.96 | 0.99838 | 246.66 | 0 | 246.66 | 0 | [45 empty] | 0 | 0 | 91085.07 | 0 | 61050.89 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3125 | C | USCSB2312089A |  | Shared materials for plastic system, tool hook up | 45274 | 45279 | 8732.4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8732.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 5157.5 | 0 | 1682.99 |  | 938.61 | 578.1 | 375.2 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3126 | C | USCSB2312091A |  | cleanroom tapes shared by all hk trades | 45274 | 45275 | 847.68 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 847.68 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 847.68 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC23C054 | UPW Change Order | 3127 | C | USCSB2312092A |  | UPW-UMEC-extend GC 2023-Sep to Nov | 45274 | 45282 | 1554463 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1476470 | 0.94983 | 77993 | 0 | 77993 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 1476470 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3128 | C | USCSB2312093A |  | HK Yaho engineer assistants. | 2023/12/14 2024/1/9 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:need to clarify scope |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3129 | C | USCSB2312094A |  | Quick-Clamp High-Vacuum Fitting for Stainless Steel Tubing, Straight Reducer for 1-1/2" x 1" Tube | 45274 | 45279 | 2047.91 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2036.1 | 0.99423 | 11.81 | 0 | 11.81 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 2036.1 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3130 | C | USCSB2312095A |  | Labor to Install and Route of (7) signal cables on KIHIT2 | 45274 | 45276 | 3238 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3076.1 | 0.95 | 161.9 | 0 | 161.9 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1083 |  | 0 | 0 | 1993.1 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3131 | C | USCSB2312096A |  | Greenberry’s Time and Materials pricing for the KIHIT3 Signal Cable Install at TSMC | 45274 | 45275 | 5088 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4833.6 | 0.95 | 254.4 | 0 | 254.4 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 3610 |  | 0 | 0 | 1223.6 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3132 | C | USCSB2312097A |  | Boxes for shipping out material and supplies | 45274 | 45275 | 3633.9 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 468.2 | 0.12884 | 3165.7 | 0 | 3165.7 | 0 | [45 empty] | 0 | 0 | 0 | 72.9 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 395.3 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3133 | C | USCSB2312098A |  | urgent wire request for Third top 100 tools. USCSB2311090 Replacement | 45275 | 45278 | 1696396.84 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1696396.84 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 173654.65 | 345091.74 |  | 499534.28 | 31017.5 | 380800.48 | 266298.19 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3134 | C | USCSB2312099A |  | UPW-Tomoe-part repair | 45275 | 45275 | 1825 | [6 empty] | Tomoe USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1825 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1825 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3135 | C | USCSB2312100A | -01 | Copper State Bolt & Nut Co outstanding account invoices of materials | 45275 | 2023/12/18 2023/12/28 | 15967.75 | 39.7 | 15928.05 | V |  |  |  | Copper State Bolt & Nut Company | PR Approved | PO Approved | PO R1: Tax amount change for invoice I05599590 and I05688809 |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 15967.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 15967.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3136 | C | USCSB2312101A |  | Consolidated Electrical Distributors material for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45275 | 45275 | 488.65 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 488.65 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 488.65 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3137 | C | USCSB2312102A |  | Shared materials for plastic system, tool hook up | 45275 | 45278 | 5123.2 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5123.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 3888.08 | 0 | 965.12 |  | 270 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3138 | C | USCSB2312104A |  | Time and Materials pricing for the KIHIT4 Signal Cable Install | 45275 | 45279 | 5550 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5550 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 5550 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3139 | C | USCSB2312105A |  | security cart for漢科 | 45275 | 45279 | 15262.2 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15262.2 | 1 | 0 | 36791.12 | -36791.12 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 15262.2 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3140 | C | USCSB2312106A |  | Time and Materials pricing for the KIHIT5 Signal Cable Install | 45275 | 45281 | 3238 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3076.1 | 0.95 | 161.9 | 0 | 161.9 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1624.5 |  | 0 | 0 | 1451.6 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3141 | C | USCSB2312107A |  | WWT CCE Change Orders_CO64 | 45276 | 45278 | 826.65 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 785.32 | 0.95 | 41.33 | 0 | 41.33 | 0 | [45 empty] | 0 | 0 | 0 | 785.32 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | USC23C045 | WWT Change Order (Piping) | 3142 | C | USCSB2312108A |  | JT Thorpe Sep Invoice | 45276 | 45279 | 1590281.5 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1590281.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 1590281.5 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3143 | C | USCSB2312109A |  | WWT_18" Galvanized P-Clamps | 45276 | 45278 | 3872.83 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3810.3 | 0.98385 | 62.53 | 0 | 62.53 | 76.206 | [45 empty] | 0 | 0 | 0 | 275.88 | 0 |  |  | 1731.03 | 1803.39 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 76.206
Base-Build | Chemical | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3144 | C | USCSB2312110A |  | CDS ICP Mass CDA GN2 regulators and parts to fix design issue by John Wu | 45276 | 45279 | 18788.56 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 18788.56 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 18788.56 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC23C045 | WWT Change Order (Piping) | 3145 | C | USCSB2312111A |  | Kelly outsourcing | 45276 | 45279 | 638265.04 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 638265.04 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 638265.04 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3146 | C | USCSB2312112A |  | CDS A side platform rail | 45276 | 45288 | 47068 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 47068 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 22357.3 | 23534 |  | 0 |  | 1176.7 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3147 | C | USCSB2312113A |  | USC21C006 SLURRY B SIDE L30 bridge support | 45276 | 45281 | 283945.4 | [6 empty] | SDB, Inc. dba SDB Contracting Services | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 283945.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 227156.32 |  |  |  | 42591.81 |  |  | 56789.08 | 14197.27 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3148 | C | USCSB2312114A |  | USC21C006 SLURRY A&B SIDE HUB BOX | 45276 | 45282 | 18142.08 | [6 empty] | Avex-SG Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 18142.08 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 18142.08 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3149 | C | USCSB2312115A |  | INTUMESCENT FIREPROOFING mezz 1 and 2 Fab LB2 (release of second half) | 45276 | 45279 | 735000 | [6 empty] | Alpha Insulation and Waterproofing, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 661500.04 | 0.9 | 73499.96 | 0 | 73499.96 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 283664.97 | 0 | 0 | 0 |  | 0 |  |  |  | 148722.26 | [7 empty] | 163652 |  |  | 0 | 65460.81 | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3150 | C | USCSB2312116A |  | CDS CED MIC A side 2 of 2 per Paul | 45276 | 45280 | 85937.06 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 85510.44 | 0.99504 | 426.62 | 0 | 426.62 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 16072.57 | 5133.67 |  | 0 | 0 | 0 |  | 0 |  | 64304.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3151 | C | USCSB2312116B |  | CDS CED MIC A side 2 of 2 per Paul | 45276 | 45293 | 1550 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1550 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 800 | 750 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2968 | C | USCSB2312117A |  | QR LABS: CHAD/FAD LAN TRAY MATERIALS | 2023/12/16 | 45443 | 1948.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1948.12 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 1948.12 | [12 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C006 | F21P1 Module Tool Interconnection EPI | 2969 | C | USCSB2312118A |  | EPI: KCEPS1: COND CLAMPS, BUSHINGS, & CONNECTORS | 45276 |  | 1582.89 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1: canceled order | [13 empty] | 1582.89 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 1582.89 | [12 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C006 | F21P1 Module Tool Interconnection EPI | 2970 | C | USCSB2312119A |  | EPI: KCEPS1: PIPE CLAMPS | 45276 |  | 26.4 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1: canceled order | [13 empty] | 26.4 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 26.4 | [12 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C006 | F21P1 Module Tool Interconnection EPI | 2975 | C | USCSB2312120A |  | EPI: KCEPS1: CONNECTORS & BUSHINGS | 45276 | 45455 | 701.55 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 701.55 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 701.55 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 3156 |  | USCSB2312121A |  | DIFF2: KDALS1: CONNECTORS | 2024/6/12 | 45457 | 175.14 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 175.14 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 175.14 | [12 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C006 | F21P1 Module Tool Interconnection EPI | 2971 | C | USCSB2312122A |  | EPI: KCEPS1: LIQ-TITE, BUSHINGS, & CONNECTORS | 45276 |  | 86.06 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1: canceled order | [13 empty] | 86.06 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 86.06 | [12 empty] | - |  | - |  | 0
Base-Build | Chemical | Material | USC21C006 | F21P1 Slurry package | 3158 | C | USCSB2312123A |  | Urgent: CDS CED MIC A side 1 of 2 per Paul | 45276 | 45282 | 266747.64 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 266747.64 | 1 | 0 | 3150 | -3150 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 266620.65 | 126.99 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | FMCS | Material | USC22C007 | TSMC F21 FMCS Installation | 3159 | C | USCSB2312124A |  | Strand fiber SM armored cables | 45276 | 45279 | 17635 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 17635 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 17635 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3160 | C | USCSB2312126A |  | WWT_18" Galvanized P-Clamps_LSD Asiede + Bisde 18” Clamp needed. | 45276 | 45278 | 3796.5 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3796.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 3796.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3161 | C | USCSB2312127A |  | AZ F21 Pumping Line hardware for Tunyi | 2023/12/16 2024/3/31 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: zero out |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC23C045 | WWT Change Order (Piping) | 3162 | C | USCSB2312128A |  | CGS outsourcing manpower | 45277 | 45278 | 1037689.53 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1037689.53 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 1037689.53 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3163 | C | USCSB2312130A |  | erasable pens, wet floor signs, clipboards, cleanroom bags, pointer pen, and storage shelves shared by all system | 2023/12/18 2024/1/3 | 45294 | 4790.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | PR R1:tax was not included |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4255.42 | 0.8883 | 535.08 | 0 | 535.08 | 0 | 4255.42 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3164 | C | USCSB2312131A |  | ULINE Welding screens in support of TSMC & Taiwan Vendors Prefab Work | 45279 | 45280 | 4080 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 4080 | 0 | 4080 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3165 | C | USCSB2312132A |  | Flow/reg 356-ar/he-580 dual, gas 300 tools, tool hookup | 45279 | 45280 | 1746.8 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1746.8 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1746.8 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3166 | C | USCSB2312133A |  | weatherproof bell boxes, for 100 tools demand, TOOL HOOKUP TEAM | 45279 | 45280 | 2712.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2712.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 1117.44 | 1595.06 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 3167 | C | USCSB2312134A |  | EBO: ZFP3-1: GEX INTERCONNECT MATERIAL | 45279 | 45281 | 328.27 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 328.27 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 328.27 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | 5G | NUUO | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 3168 | C | USCSB2312135A |  | F21 CMS & DPM IMP Engineering | 45279 | 45280 | 848096 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 356100.65 | 0.41988 | 491995.35 | 0 | 491995.35 | 424048 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 95890.36 | 53906 | 0 |  | 0 |  | 110350.9 |  |  | 169620 | 47168.1 |  |  | 42405 | [5 empty] | 84809.6 |  | 48785.29 | 84809.6 | - | 84809.6 | 84809.6 | 84809.6
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3169 | C | USCSB2312136A |  | RMJ ELECTRICAL CONTRACTORS TRASH COMPACTOR | 45279 | 45286 | 6225 | [6 empty] | RMJ Electrical Contractors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 6225 | 0 | 6225 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3170 | C | USCSB2312137A |  | UPW-ORGANO-flexible joints for ICW | 45279 | 45279 | 1280 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1280 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1280 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3171 | C | USCSB2312138A |  | UPW-ORGANO-WRC BPV | 45279 | 45279 | 367.56 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 367.56 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 367.56 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3172 | C | USCSB2312139A | -01 | CDS Fix L10 HNO3 ST250 HKP | 2023/12/19 2023/12/26 | 2023/12/20 2023/12/26 | 6975 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved | Ship-to address cgange |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 6975 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 6626.25 | 0 | 0 |  | 0 | [8 empty] | 348.75 |  |  |  |  | 348.75 | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3173 | C | USCSB2312140A |  | Pallet truck, jobsite box, storage for third | 45279 | 45288 | 23381.3 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 23381.3 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 23381.3 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3174 | C | USCSB2312141A |  | Brother label tape, gas and UPW share materials, Tool hookup team | 45279 | 45280 | 2724.27 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2470.14 | 0.90672 | 254.13 | 0 | 254.13 | 0 | 2470.14 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3175 | C | USCSB2312142A |  | HK Fixture Latch for welding training | 45279 | 45295 | 9206 | [6 empty] | Potex Technologies Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 9206 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 9206 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3176 | C | USCSB2312143A |  | 3M Chemical Sorbent Pad for UPW System, Tool hookup team | 45279 | 45280 | 1588.1 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1175.66 | 0.74029 | 412.44 | 0 | 412.44 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 618.66 |  | 557 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C006 | F21P1 Slurry package | 3177 | C | USCSB2312144A |  | CDS MICU Equipment-1 | 45279 | 45280 | 830000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 830000 | 0 | 830000 | 830000 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 830000
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3178 | C | USCSB2312145A |  | Pipe, tube and fitting from MIC TW-1 | 45279 | 45281 | 45550 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 45550 | 0 | 45550 | 45550 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 45550
Base-Build | Chemical | Labor | USC21C006 | F21P1 Slurry package | 3179 | C | USCSB2312146A |  | CDS H20 Caustic electrical work T&M | 2023/12/20 2024/3/27 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:As per PM:Johnny Wan to cancel the PR. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | EUV Steel Plate | Equipment | USC23C058 | F21 EUV Steel Plates | 3180 | C | USCSB2312147A |  | DP-213/221/223/B06 Door kits | 45280 | 45281 | 32510 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 32510 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 32510 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3181 | C | USCSB2312148A |  | CDS Materials for Lorry requested by Ben and John | 45280 | 45280 | 1974.7 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1974.7 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1974.7 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC21C005 | F21P1 Chemical & WCCS package | 3182 | C | USCSB2312149A |  | CDS pressure test materials | 45280 | 45282 | 32359.45 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 32262.55 | 0.99701 | 96.9 | 0 | 96.9 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 32262.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3183 | C | USCSB2312150A |  | Consolidated Electrical Distributors material for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45280 | 45280 | 4564.29 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4564.29 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 4564.29 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3184 | C | USCSB2312151A | -01 | Hex bolt and nut for Pumping Line trade | 2023/12/21 2024/3/30 | 2023/12/27 2024/4/5 | 0 | -281.49 | 281.49 |  |  |  |  | Carson Sales Co Inc | PR Approved | PO Approved | R1: zero out (but this is a mistake that need to be fixed) |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 3185 | C | USCSB2312152A |  | CDS Day Tank Vent Labor | 45281 | 45282 | 39031.2 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 29273.4 | 0.75 | 9757.8 | 0 | 9757.8 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 29273.4 |  | 0 | [12 empty] | 9757.8 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 3186 | C | USCSB2312153A |  | FAB LITHO AMC Pressure Testing | 45281 | 45286 | 4570 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4570 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 4570 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC22C019 | AMC monitor 595T0 | 3187 | C | USCSB2312154A |  | FAB B VOC Mechanical Observation | 45281 | 45280 | 3500 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 3500 | 1143.6 | 2356.4 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 3500 |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3188 | C | USCSB2312155A |  | KCANN3,KCAPN1,KCSCN5 SOOW 10-4 Power cable run from L30 to L20 | 45281 | 45281 | 443.75 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 443.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 443.75 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3189 | C | USCSB2312156A |  | WWT-Chemical H2SO4/HCl | 45281 | 45286 | 40825.4 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 12795.88 | 0.31343 | 28029.52 | 0 | 28029.52 | 5337.728 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 6123.81 |  |  |  | 6123.81 | 6279.68 |  | 6516.2 | 6123.81 |  | 0 |  | - | 0 | - | 5337.728 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3190 | C | USCSB2312157A |  | Vern and Lewis unincluded taxes and services fee | 45281 | 45300 | 714.04 | [6 empty] | Vern Lewis Welding Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 605.72 | 0.8483 | 108.32 | 0 | 108.32 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 605.72 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3191 | C | USCSB2312158A |  | WWT-Gripper 2 in. Plastic Mechanical Test Plug | 45281 | 45280 | 528 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 528 | 1 | 0 | 0 | 0 | 0 | 528 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3192 | C | USCSB2312159A |  | IDEAL 31601 1LB DUCT SEAL for power trade | 45281 | 45282 | 1296 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1296 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 1296 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC22C022 | F21P1 Triazole treatment system | 3193 | C | USCSB2312161A |  | Chem Pkg 3 WWT Estimate | 45281 | 45293 | 176243 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 167432 | 0.95001 | 8811 | 0 | 8811 | 8371.6 | [45 empty] | 0 | 0 | 0 | 0 | 114558 |  |  | 31724 | 7050 | 0 |  | 14100 |  |  |  |  | 5287.29 |  |  |  | 8812.15 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 8371.6
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3194 | C | USCSB2312162A |  | Steel Passing Link Chain, lock, cutting machine, shared materials for all system, tool hook up team. | 45282 | 45287 | 2289.18 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2081.18 | 0.90914 | 208 | 0 | 208 | 0 | 2081.18 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3195 | C | USCSB2312163A |  | chemical system materials, for the next 300 machines, tool hookup | 2023/12/22 2024/9/18 | 2023/12/26 2024/9/18 | 52005.25 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | PR R1: To match the requisition amount and the PO amount |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 52005.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 52005.25 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3196 | C | USCSB2312164A | -01 | ground clamp, wall receptacle for power trade | 45282 | 2023/12/27 2024/1/4 | 65808.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Remark Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 65808.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 1501.5 |  |  | 0 | 0 | 64307 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3197 | C | USCSB2312165A |  | HK strut clamp for PPL trade | 45282 | 45288 | 557.61 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 557.61 | 0 | 557.61 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3198 | C | USCSB2312166A |  | CDS Chemical Electrical Power Distribution Engineering Technical Supervision Service | 45282 | 45308 | 370000 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 351500 | 0.95 | 18500 | 0 | 18500 | 18500 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 185000 | 0 | 0 |  | 0 |  |  |  |  | 166500 | 166500 | [8 empty] | 18500 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C006 | F21P1 Slurry package | 3199 | C | USCSB2312167A |  | CDS MIC A side electrical materials | 45282 | 45282 | 1989.6 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1989.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1989.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 3200 | C | USCSB2312168A |  | CMP: MKS1: INTERCONNECT MATERIAL PEDESTAL CLAMPS | 45282 | 45287 | 208 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 208 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 208 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3201 | C | USCSB2312169A |  | UPW-XHHW500YELcable | 45282 | 45282 | 17134.38 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 17134.38 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 17134.38 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3202 | C | USCSB2312170A |  | WWT-Train B FRP | 45282 | 45286 | 225633 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 135379.8 | 0.6 | 90253.2 | 0 | 90253.2 | 54151.92 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 135379.8 |  | 0 |  |  |  |  | 33844.95 |  |  |  | 33844.95 |  |  |  | 33844.95 |  | 13537.98 |  | - | 13537.98 | - | 13537.98 | 13537.98 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3203 | C | USCSB2312171A |  | WWT-NH3-outdoor cabinet | 45282 | 45287 | 2594 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2594 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 2594 |  |  | 389.1 |  |  |  | 389.1 |  |  |  | 389.1 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3204 | C | USCSB2312172A |  | CVD2_KCANN3_WIRE SO10/4 | 45283 | 45289 | 542.14 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 542.14 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 542.14 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3205 | C | USCSB2312173A |  | TSMC 12.18 PVDF material item | 45283 | 44929 | 50171.7 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 50171.7 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 50171.7 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3206 | C | USCSB2312175A | -01 | PSS Dec payment request | 45283 | 2023/12/24 2023/12/25 | 4500000 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | R1: Change Payment Terms to 100% Prepayment by 12/28/2023 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4500000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 4500000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3207 | C | USCSB2312176A |  | WWT-Clamp from 8-16” for A side back up. | 45283 | 45288 | 7500 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7500 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 7500 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3208 | C | USCSB2312177A |  | WWT-lab-duct pipe connector | 45283 | 45303 | 3279.22 | [6 empty] | Chern Shuo System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3279.22 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 3279.22 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3209 | C | USCSB2312178A |  | Laminator Sheets&Mounting Tape | 45283 | 45287 | 706.55 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 623 | 0.88175 | 83.55 | 0 | 83.55 | 27.036 | 623 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 27.036
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3210 | C | USCSB2312179A |  | Stainless Steel VCR Face Seal Fitting, Gas system, Tool hookup | 45287 | 45286 | 2687.5 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2687.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 2687.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3211 | C | USCSB2312180A |  | 1/4 " 凸緣螺母, shared material for gas system, tool hook up | 45287 | 45289 | 1800 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1800 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1800 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3212 | C | USCSB2312181A |  | Locknut for hk power trade. steel UL | 45287 | 45293 | 6249.95 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6249.95 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 1271.25 |  | 0 |  | 4058.9 | [5 empty] | 279.3 |  |  |  | 574 |  |  | 0 |  | 66.5 | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3213 | C | USCSB2312182A |  | office supplies for tool hookup department | 12/27/2023 8/8/2024 | 12/28/2023 8/28/2024 | 123.29 | 13.33 | 109.96 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: change price |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 123.29 | 1 | 0 | 0 | 0 | 0 | 123.29 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Scaffolding | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3214 | C | USCSB2312183A |  | scaffold services labor, material, and equipment for hook up shared by all system | 45287 | 45296 | 127383 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 127383 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 127383 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Scaffolding | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3215 | C | USCSB2312184A |  | OPEN PO scaffold services labor, material, and equipment for hook up shared by all system | 45287 | 45315 | 50000 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 32500 | 0.65 | 17500 | 0 | 17500 | 0 | [47 empty] | 0 | 0 | 0 | 32500 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 3216 | C | USCSB2312185A |  | FAB B VOC Electrical CA service | 45288 | 45302 | 24195 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5718 | 0.23633 | 18477 | 0 | 18477 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 2287.2 |  |  |  | 1143.6 | [5 empty] | 1143.6 |  |  |  | 1143.6 | - |  | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 3217 | C | USCSB2312186A |  | TMAH Addition and WRC Pads | 2023/12/28 2024/1/5 |  | 0 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved | PR R1:Scope Change |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C006 | F21P1 Slurry package | 3218 | C | USCSB2312187A |  | CDS Snoop and 1/2 Tee's | 45288 | 45293 | 1331.45 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1331.45 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1331.45 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3219 | C | USCSB2312188A |  | WWT-Material-A side SUS (77 item 12/21list ) | 45288 | 45293 | 12542.98 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 12542.98 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 11727.45 |  | 0 | 0 | 815.53 |  | 0 | [8 empty] | 250.8596 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3220 | C | USCSB2312189A |  | Grainger invoice report, shared material, tool hook up team | 45288 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:zero out per Yi-Kang request. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3221 | C | USCSB2312190A |  | Grainger anchor for PPL trade. Urgent per TSMC sponsor 陳俊源's request | 45289 | 45289 | 4562.82 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4562.82 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 4498.5 |  | 0 | 0 | 0 |  | 0 | [9 empty] | 64.32 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3222 | C | USCSB2312191A |  | brother label tape, for UPW and power system, tool hookup team | 45289 | 44929 | 688.18 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 579.18 | 0.84161 | 109 | 0 | 109 | 0 | 579.18 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | NUUO | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3223 | C | USCSB2312192A |  | CDS chemical electric materials | 45289 | 45300 | 199528.6 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 199528.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 199528.6 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C013 | F21P1 QR Lab Security & CCTV | 3224 | C | USCSB2312193A |  | F21 CCD Room Security CCTV Engineering | 2023/12/29 2024/8/12 | 2024/3/6 2024/8/12 | 292071.62 | -91076.06 | 383147.68 | V |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PR R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Ta Wei Wang | [11 empty] | 292071.62 | 1 | 0 | 0 | 0 | 72798.05 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 210378.79 |  |  |  |  | 30652 | 81692.83 |  |  | 30652 |  |  |  | 38315 |  | 19157.38 |  | - | 19157.38 | - | 19157.38 | 15325.91
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3225 | C | USCSB2312194A |  | UPW-commissioning horse | 45289 | 45296 | 705.84 | [6 empty] | Bridgestone Hosepower, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 705.84 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 705.84 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3226 | C | USCSB2312195A | -01 | WWT tools for MU | 45289 | 2024/1/3 2024/1/8 | 1147.47 | -119.53 | 1267 |  | V |  |  | Abbeon Cal Inc. | PR Approved | PO Approved | R1: Original item is out of stock so switch to another available product which is also qualified for user's requirements |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1147.47 | 1 | 0 | 0 | 0 | 0 | 1147.47 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3227 | C | USCSB2312196A |  | UPW-swing gate train B | 45290 | 45306 | 13300 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 13300 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 12740 |  | 0 |  | 560 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3228 | C | USCSB2312197A |  | markers, dish soap, security cart, suction cup, and wire cart for PCW trade CYH | 45290 | 45293 | 8174.12 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8174.12 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 8174.12 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | NUUO | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3229 | C | USCSB2312198A |  | F21 AMC B side Network Engineering | 45290 | 45357 | 85830 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 81522.75 | 0.94982 | 4307.25 | 0 | 4307.25 | 4422.25 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 51498 | 73230.75 |  |  | 17166 | 8166 |  |  | 126 |  | - |  | 0 | 4422.25
Base-Build | AMC THC | NUUO | USC22C019 | AMC monitor 595T0 | 3230 | C | USCSB2312199A |  | F21 AMC B side Engineering Construction | 45290 | 45357 | 396434 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 343287.3 | 0.86594 | 53146.7 | 0 | 53146.7 | 65415.2 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 75597.5 |  | 0 | [8 empty] | 122895 | 153066.7 |  |  | 79287 | 102354.6 | 6541.52 |  | 12268.5 | 13083.04 | - | 13083.04 | 27750.38 | 4957.22
Base-Build | AMC THC | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3231 | C | USCSB2312201A |  | F21 Litho AMC Utility GAS piping Engineering | 45290 | 45324 | 70997.28 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Yikang Wang (Ta Wei Wang) | [11 empty] | 70997.28 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 70997.28 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3232 | C | USCSB2312202A |  | HK cleanroom printing paper shared by all system | 45290 | 45294 | 1472.2 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1472.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 1472.2 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 3233 | C | USCSB2312203A | -01 | UPW-earthquake limiters | 45290 | 2024/1/16 2024/1/30 | 930 | -200 | 1130 |  | V |  |  | Harmony Rubber Industry Co., Ltd. | PR Approved | PO Approved | PR R1: Change trade terms and payment terms |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 930 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 930 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3234 | C | USCSB2312204A |  | United Rentals for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45290 | 45294 | 12908.64 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11975.74 | 0.92773 | 932.9 | 0 | 932.9 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 3494.62 |  | 8481.12 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3235 | C | USCSB2312205A |  | thread sealing plumber's tape for PCW | 45290 | 45294 | 400 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 374 | 0.935 | 26 | 0 | 26 | 0 | 374 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3236 | C | USCSB2312206A |  | Phone Locker 16 door (4h*4w) 4 dial combination lock for Hook up | 2023/12/31 2024/1/5 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Australian vendor |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3237 | C | USCSB2401001A |  | United Rentals Manpower Associates Scissor Lift & Fall Protection Certification & Training | 45293 | 45294 | 2708.04 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2708.04 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 2708.04 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3238 | C | USCSB2401002A |  | WWT tools for MU | 45294 | 45296 | 9254.33 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9206.45 | 0.99483 | 47.88 | 0 | 47.88 | 92.0645 | 9206.45 | [44 empty] | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 92.0645
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3239 | C | USCSB2401003A |  | flowmeter regulator for HK PPL trade | 45294 | 45296 | 3122.76 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3122.76 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 3122.76 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3240 | C | USCSB2401004A |  | Stretch Wrap and Dry Wipe, for UPW system, tool hookup team | 45294 | 45295 | 1146.4 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1146.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 728.87 |  | 0 | 0 | 0 |  | 0 | [11 empty] | 417.53 |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3241 | C | USCSB2401005A |  | WIRE, for Chemical system, Tool hookup team | 45294 | 45296 | 6798.77 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6798.77 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 6765.07 | 33.7 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3242 | C | USCSB2401006A | -01 | T.W. Evans Cordage and Bucket, shared material for Gas and chemical system, tool hoop up team | 2024/1/3 2024/1/17 | 2024/1/4 2025/1/17 | 598.72 | -287.36 | 886.08 |  |  |  |  | The Home Depot, Inc | PR Approved | PO Approved | PO R1:Home depot out of stock, we can only purchase 1 quantity. |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 465.58 | 0.77763 | 133.14 | 0 | 133.14 | 0 | 465.58 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3243 | C | USCSB2401008A |  | Cable wire stripper kit for HK power trade | 45295 | 45296 | 6824.64 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6824.64 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 6824.64 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3244 | C | USCSB2401009A |  | HK Carson Sales 11 invoices Oct and Nov | 45295 | 45297 | 43184.2 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 43184.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 43184.2 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3245 | C | USCSB2401010A |  | gas storage tools. Tool hookup team | 45295 | 45300 | 24703.97 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 24703.97 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 24703.97 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3246 | C | USCSB2401011A |  | HK Huengluei Equipment Rental for 3 months | 45295 |  | 33900 | [7 empty] | PR Approved | PO Processing |  |  | 0 | [11 empty] | 0 | 0 | 33900 | 0 | 33900 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3247 | C | USCSB2401012A |  | HK Laien Parts Equipment Rental for 3 months | 45449 | 45449 | 29600 | [6 empty] | Laien Parts Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 29600 | 0 | 29600 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3248 | C | USCSB2401013A |  | WWT tools and office supplies for MU | 45295 | 45295 | 295.98 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 260.4 | 0.87979 | 35.58 | 0 | 35.58 | 31.248 | 260.4 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 8.8794 |  |  |  | 8.8794 |  | 31.248 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3249 | C | USCSB2401014A |  | HK TUN YI Equipment Rental for 3 months | 45295 | 45310 | 257124.72 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 257124.72 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 64281.18 |  |  |  | 192843.54 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3250 | C | USCSB2401015A |  | HK Chuan Ta Equipment Rental for 3 months | 2024/1/4 2024/1/17 | 2024/1/26 | 21000 | [6 empty] | Chuan Ta Technology Corp. | PR Approved | PO Approved | PR R1: Adjusting the PR to align with actual rental date. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 21000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 21000 | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3251 | C | USCSB2401016A |  | HK Da Yi Chen Equipment Rental for 3 months | 45295 | 45310 | 40000 | [6 empty] | DA YI CHENG Technology Co., Ltd. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 40000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 40000 |  |  | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Site Expense | USC23C052 | F21 P1A AMHS PSP & DP Power source breakers | 3252 | C | USCSB2401017A |  | CPE Shoe Covers | 45295 | 45309 | 2740 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2740 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2740 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3253 | C | USCSB2401018A |  | replacement of USCSB2312206. Phone lockers for HK shared by all system | 45296 | 45297 | 2516 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2516 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 2516 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3254 | C | USCSB2401019A |  | HK Maohsun Equipment Rental for 3 months | 2024/1/5 2024/8/7 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Zeroing out this PR per request from Ning and Yikang. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3255 | C | USCSB2401020A |  | HK YAHO Equipment Rental for 3 months | 45296 | 45317 | 601000 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 601000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 601000 |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3256 | C | USCSB2401021A |  | HK CYH Equipment Rental for 3 months | 45296 | 45310 | 324000 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 324000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 324000 |  |  | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C053 | AMAT Interconnection (TSMC) | 3257 | C | USCSB2401022A |  | Change Order for KCEPA1: power cables, PVC coated clamps, Tray dividers | 45296 | 45300 | 1331.2 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 1331.2 | 0 | 1331.2 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 3258 | C | USCSB2401023A |  | Cordless Cable Cutter | 45296 | 45301 | 651.98 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 651.98 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 651.98 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3259 | C | USCSB2401024A |  | Male Connector, for plastic QA/QC testing, Tool hookup team | 45296 | 45300 | 425.5 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 425.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 425.5 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3260 | C | USCSB2401025A |  | WWT office supplies for PSS support doc. | 45296 | 45300 | 110.05 | [6 empty] | Walmart Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 107.85 | 0.98001 | 2.2 | 0 | 2.2 | 0.9304 | 107.85 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 5.5025 |  |  |  | 11.005 |  |  |  | 16.5075 |  | 0 |  | - | 0 | - | 0 | 0 | 0.9304
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 3261 | C | USCSB2401026A |  | EBO: ZASC5-1: INTERCON. MATERIAL. CABLE TRAY | 45296 | 45303 | 274.68 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 274.68 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 274.68 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 3262 | C | USCSB2401027A |  | QR: FAD/CHAD LABS: INTERCON. MATERIAL LAN CABLE TRAY | 45296 | 45316 | 545.98 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 545.98 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 545.98 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Scaffolding | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3263 | C | USCSB2401028A |  | Proposal for Fab L30 EUV crane scaffolding | 45296 | 45321 | 172043 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 172043 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 172043 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3264 | C | USCSB2401029A |  | HK Parking for exhaust dust for trade HR. TSMC Polyethylene Foam Gasket | 45296 | 45299 | 2958 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2958 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 2958 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3265 | C | USCSB2401030A |  | Grainger EUV Crane Maintenance Service | 45296 | 45299 | 2761.66 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2751.6 | 0.99636 | 10.06 | 0 | 10.06 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 2751.6 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3266 | C | USCSB2401031A |  | Braided Steel security cable and brass combination padlock. shared by all system/trades | 45297 | 45300 | 189.1 | [6 empty] | Harbor Freight Tools USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 118.63 | 0.62734 | 70.47 | 0 | 70.47 | 0 | 118.63 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3267 | C | USCSB2401032A |  | CDS Lorry A 18 Tanks | 2024/1/6 2024/1/23 |  | 0 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | PR R1:Renew quotation and change budget code, so cancel the PR. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3268 | C | USCSB2401033A |  | HK Cable tie for Exhaust trade HL, Cleanroom tapes shared by all system | 45297 | 45300 | 1196 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1196 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 1196 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 3269 | C | USCSB2401034A |  | CDS Move C02 Cylinder 不追加 | 45297 | 45299 | 3304 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3304 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 3138.8 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3304 |  |  |  |  | 165.2 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3270 | C | USCSB2401035A |  | High Accuracy Digital Pressure Gauge, Gas and plastic system, Tool hookup team | 45297 | 45311 | 1175 | [6 empty] | Richwell Instrument Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1175 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 1175 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C013 | F21P1 QR Lab Security & CCTV | 3271 | C | USCSB2401036A |  | F21 CCTV Over Time and Interconnection | 45297 | 45301 | 329646 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 329646 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 329646 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3272 | C | USCSB2401037A |  | Interconnect Installer 6 months installers | 45297 | 45302 | 159887.7 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 92088.14 | 0.57596 | 67799.56 | 0 | 67799.56 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 6765.04 |  | 31044.72 |  | 54278.38 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3273 | C | USCSB2401039A |  | shared materials for UPW and chemical system first 100 Tools, Tool hook up | 45297 | 45302 | 4156.91 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3783.62 | 0.9102 | 373.29 | 0 | 373.29 | 0 | 3783.62 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3274 | C | USCSB2401040A |  | office supplies for tool hookup department | 45298 | 45299 | 1416.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1122.7 | 0.79259 | 293.8 | 0 | 293.8 | 0 | 1122.7 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3275 | C | USCSB2401041A |  | CDS Unions etc. | 45300 | 45301 | 4679.78 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4679.78 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 4679.78 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3276 | C | USCSB2401042A |  | CDS galvanized 4*4 cm-10ft(L) | 45299 | 45314 | 15598 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 15598 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 15598 |  |  | 15598 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Greenberry | USC23C014 | F21P1 Labor incentive program-MICU | 3277 | C | USCSB2401043A |  | Tunnel&WWT_9-5 Holiday pay incentive (Labor Day) | 45300 | 45306 | 7300 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 7300 | 0 | 7300 | 7300 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1095 |  |  |  | 1095 |  |  |  | 1095 |  | 3650 |  | - | 3650 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3278 | C | USCSB2401044A |  | WCCS Thread locker | 45300 | 45300 | 9.99 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 8.89 | 0.88989 | 1.1 | 0 | 1.1 | 0 | 8.89 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3279 | C | USCSB2401045A |  | D-ring anchorage for PPL trade | 45300 | 45300 | 3054.2 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3054.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 3054.2 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3280 | C | USCSB2401046A |  | Day & Night shift Laborers | 45300 | 45306 | 120000 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 120000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 69525 | 0 | 0 | 0 |  | 50475 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 3281 | C | USCSB2401047A |  | CMP: MKS-2 & MKS-3: INSTALL PVC & PFA TUBING TO NEWLY INSTALLED LAB EQUIP. TOOLS & INSTALL GEX. | 2024/1/9 2024/8/5 | 2024/1/19 2024/8/5 | 29188.16 | -11950.1 | 41138.26 | V |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: Returned remaining funds as the invoice was smaller than the quote. Revised to actual invoices. |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 29188.16 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 9262.65 |  | 0 | 0 | 0 |  | 0 |  |  |  | 19925.51 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment | USC23C036 | F21P1 AMAT Interconnection | 3282 | C | USCSB2401048A |  | square Shark Cages | 45300 | 45302 | 1830 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1830 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 1830 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3283 | C | USCSB2401049A |  | office supplies for tool hookup department | 45300 | 45302 | 142 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 129.52 | 0.91211 | 12.48 | 0 | 12.48 | 0 | 129.52 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3284 | C | USCSB2401050A |  | Bucket: 3/4 gal Capacity, 7 in Overall Wd, 5 in Overall Ht, Galvanized Steel, Graduated, shared materials for Gas system | 45300 | 45301 | 147.3 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 147.3 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 147.3 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3285 | C | USCSB2401051A |  | Tool for trade HL | 45300 | 45306 | 3164.22 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3164.22 | 1 | 0 | 0 | 0 | 0 | 3164.22 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3286 | C | USCSB2401052A |  | overtime for Day & Night workers | 45301 | 45306 | 90000 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 90000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 29700 | 0 | 60300 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3287 | C | USCSB2401054A |  | 5 traditional Shark Cages | 45301 | 45301 | 4235 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4235 | 1 | 0 | 5329.05 | -5329.05 | 0 | [45 empty] | 0 |  | 4235 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3288 | C | USCSB2401055A |  | WCCS weld tube cap 2" | 45301 | 45303 | 11.22 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 11.22 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 11.22 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3289 | C | USCSB2401056A |  | WCCS Cutter | 45301 | 45306 | 36.95 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 36.95 | 1 | 0 | 0 | 0 | 0 | 36.95 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3290 | C | USCSB2401057A |  | WWT_pressure gauge | 45301 | 45303 | 703.29 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 703.29 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 703.29 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C053 | AMAT Interconnection (TSMC) | 3291 | C | USCSB2401058A |  | KDIGA3 DIF2 (Install a 4/0W Tray Cable from the Mainframe transformers to the MF AC Rack.) | 45301 | 45303 | 3094.48 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 3094.48 | 131964 | -128869.52 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3292 | C | USCSB2401059A |  | Cleanroom tapes shared by all hk trades. Elias's request | 45302 | 45302 | 696 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 696 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 696 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 3293 | C | USCSB2401060A |  | PVD，Interconnection material 36" Zip Tie | 45302 | 45302 | 405 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 375 | 0.92593 | 30 | 0 | 30 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 375 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3294 | C | USCSB2401061A |  | Border States Electrical Work Material PreFab Area Open Statement Invoices | 45302 | 45303 | 2016.88 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2016.88 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 2016.88 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3295 | C | USCSB2401062A |  | Locknut for power trade jeryih and third | 45302 | 45306 | 1619.6 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1619.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 1619.6 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Material | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3296 | C | USCSB2401063A |  | Housekeeping Material | 45302 | 45313 | 3790.44 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3407.64 | 0.89901 | 382.8 | 0 | 382.8 | 0 | 3407.64 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3297 | C | USCSB2401064A |  | Consolidated Electrical Distributors material for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45302 | 45303 | 94.38 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 94.38 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 94.38 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3298 | C | USCSB2401065A |  | Office supplies for tool hookup Alex's team | 45302 | 45302 | 281.7 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 220.65 | 0.78328 | 61.05 | 0 | 61.05 | 0 | 220.65 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3299 | C | USCSB2401066A |  | WWT CCE Change Orders | 45302 | 45304 | 564.88 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 564.88 | 0 | 564.88 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 84.732 |  |  |  | 84.732 |  |  |  | 84.732 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | USC23C045 | WWT Change Order (Piping) | 3300 | C | USCSB2401067A |  | J.T. Thorpe Aug invoice | 45302 | 45307 | 1914858 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1914858 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 1914858 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3301 | C | USCSB2401068A |  | office supplies for tool hookup department shared by all systems | 1/11/2024 8/22/2024 | 1/13/2024 8/28/2024 | 619.99 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 608.88 | 0.98208 | 11.11 | 0 | 11.11 | 0 | 608.88 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3302 | C | USCSB2401069A |  | 第四批短期需求用料[MIC代採購_T&M] | 45302 | 45308 | 19881 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 19881 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 159.3 |  | 15293.85 | 3516.8 | 0 |  | 911.05 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Southland | USC21C005 | F21P1 Chemical & WCCS package | 3303 | C | USCSB2401070A |  | MIC and Southland reach agreement to modify contract for F21 A side Southland Scope. | 45303 | 45309 | 4000000 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4000000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 1212933.74 | 1076265.19 | 1710801.07 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3304 | C | USCSB2401071A |  | UPW-ORGANO-ACM-C-added PVDF | 45303 | 45307 | 31552 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31552 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 31552 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 3305 | C | USCSB2401072A | -01 | UPW-Harrington-Sight glass Orings | 45303 | 2024/1/12 2024/1/16 | 66.5 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: trade term changes from DDP to FOB |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 66.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 66.5 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 3306 | C | USCSB2401073A |  | UPW-Northernmedia-ACF gravels | 45303 | 45317 | 749.93 | [6 empty] | Northern Filter Media, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 749.93 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 749.93 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | NUUO | USC22C019 | AMC monitor 595T0 | 3307 | C | USCSB2401074A |  | F21 AMC Reroute and retest fiber engineering | 45303 | 45359 | 19800 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 17622.5 | 0.89003 | 2177.5 | 0 | 2177.5 | 2177.5 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 17622.5 |  | 0 | [14 empty] | 594 |  | - | 594 | - | 0 | 0 | 989.5
Base-Build | CCTV | NUUO | USC22C001 | F21 P1 Office and WH Security and CCTV | 3308 | C | USCSB2401075A |  | F21 CCTV Engineering | 45303 | 45356 | 248169.53 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 208731.91 | 0.84109 | 39437.62 | 0 | 39437.62 | 27298.66 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 235762 | 208731.91 | [8 empty] | 7445.09 |  | - | 7445.09 | - | 7445.09 | 0 | 4963.39
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3309 | C | USCSB2401076A |  | Galvanized Steel Pail 1-1/4 Gallon Capacity, Shared for all system for materials carriage. | 45303 | 45307 | 750.4 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 750.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 750.4 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3310 | C | USCSB2401077A | -01 | Plastic_第四批短期需求用料[MIC代採購_T&M] | 2024/1/12 2024/2/2 | 2024/1/17 2024/2/2 | 1683.6 |  | 1825.2 |  | V |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | Revision to replace with Stainless Steel Hose Connectors |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1683.6 | 1 | 0 | 1096.9 | -1096.9 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 1067.76 |  |  |  | 615.84 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | MMI | USC21C006 | F21P1 Slurry package | 3311 | C | USCSB2401078A |  | SDS A side expansion two cabinets | 45303 | 45303 | 8524 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8524 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 8097.8 | 0 | 0 |  | 0 |  | 426.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | MMI | USC21C006 | F21P1 Slurry package | 3312 | C | USCSB2401079A |  | SDS Slurry A side plates | 45303 | 45304 | 23928 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 23928 | 1 | 0 | 0 | 0 | 1196.4 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 22731.6 |  |  |  | 1196.4 | [8 empty] | 0 |  | - | 0 | - | 0 | 1196.4
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3313 | C | USCSB2401080A |  | CDS Unions to replace all Union Box accessories of Lorry to HPM IPA and PFA to SUS. | 45303 | 45303 | 1359.45 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1359.45 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1359.45 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3314 | C | USCSB2401081A |  | CDS Reducing Union Adapter | 45303 | 45303 | 491.05 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 491.05 | 1 | 0 | 1984 | -1984 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 491.05 | [8 empty] | 491.05 | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 3315 | C | USCSB2401082A |  | UPW-HKPs epoxy | 2024/1/12 2024/1/23 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Renew the quotation and scope, so cancel this PR, |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3316 | C | USCSB2401083A |  | WWT: Repair (2) 1" Stripper Tank Nozzle Flanges and FRP New Standoff to Relocate Sandblasting Lab Tank T-196AA Ladder | 45303 | 45303 | 9834.74 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 4505.69 | 0.45814 | 5329.05 | 0 | 5329.05 | 360.4552 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1475.211 | 4505.69 |  |  | 1475.211 |  |  |  | 1475.211 |  | 0 |  | - | 0 | - | 0 | 0 | 360.4552
Base-Build | WWT | MMI | USC21C011 | F21 TMAH System | 3317 | C | USCSB2401084A |  | WWT: Manufacture TMAH Handrail Standoffs and Install | 45303 | 45307 | 7562 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7562 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 7183.9 | 0 | 0 |  | 0 |  | 378.1 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3318 | C | USCSB2401085A |  | labels and ribbons for Brady M610 label printer for HK power trade QAQC | 45303 | 45307 | 37086.24 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 36978.95 | 0.99711 | 107.29 | 0 | 107.29 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 36978.95 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3319 | C | USCSB2401086A |  | Padlocks order for HK James M | 45303 | 45306 | 40.69 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 36.99 | 0.90907 | 3.7 | 0 | 3.7 | 0 | 36.99 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3320 | C | USCSB2401087A |  | MICU HK Power Hardware quote for Third next 100 tools | 45304 | 45309 | 650310 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 30240 | 0.046501 | 620070 | 0 | 620070 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 30240 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Equipment | USC22C014 | F21P1 AMHS Power Panel | 3321 | C | USCSB2401088A |  | AMHS B SIDE extra 8 DP Panels | 45304 | 45320 | 223600 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 223600 | 0 | 223600 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 3322 | C | USCSB2401089A |  | FAB EBO AMC Hookup - Permitting | 45304 | 45307 | 7800 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7800 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 3305 | [9 empty] | 4495 | 4496 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3323 | C | USCSB2401090A |  | CDS ASRS Leakage detector | 45304 | 45306 | 33942.12 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 33942.12 | 1 | 0 | 0 | 0 | 33942.12 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 33942.12 | 0 |  | - | 0 | - | 0 | 33942.12
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3324 | C | USCSB2401092A |  | 6 additional Hot air welding gun requested by SC Chen | 45304 | 45303 | 810.98 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 638.28 | 0.78705 | 172.7 | 0 | 172.7 | 0 | 638.28 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 3325 | C | USCSB2401093A |  | QR LABS: KXPS/KXFX/KXSM: 1/4" VCR HARDWARE FOR CABLE TRAY | 45304 | 45308 | 419.36 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 419.36 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 419.36 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3326 | C | USCSB2401095A |  | DAQ KECOT5 Install E-sensors and route cables/PFA tubing to Prime Controls supplied AC box. | 2024/1/13 2024/8/22 | 2024/3/8 2024/8/22 | 0 | -777.45 | 777.45 |  |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 3327 | C | USCSB2401096A |  | EBO: ZMERIT1: ARMAFLEX 3/8"*1/2" INSULATION FOR THE CHILLER HOSES | 45304 | 45309 | 112.91 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 112.91 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 112.91 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Equipment | USC22C017 | AMHS MML Power Design | 3328 | C | USCSB2401097A | -01 | QAQC | 1/13/2024 2/15/2024 | 1/16/2024 3/27/2024 | 262.6 | 14.88 | 247.72 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: Adjusting the amount to align with the credit card write off record. |  | Jen-Ping Tsai Yikang Wang |  |  |  | Jen-Ping Tsai | [7 empty] | 262.6 | 1 | 0 | 0 | 0 | 0 | 262.6 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3329 | C | USCSB2401098A |  | UPW-GF-electrolyte solution | 45304 | 45307 | 150 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 150 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 3330 | C | USCSB2401099A | -01 | AMAT_ME_KKDB04/KKSV02/KKSS03/KPCD16_6x14" flexible duct | 45304 | 2024/1/16 2024/1/25 | 36.98 | -5.8 | 42.78 |  | V | V |  | Amazon.com, Inc. | PR Approved | PO Approved | Amazon order amount to return "10% buffer" |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 36.98 | 1 | 0 | 0 | 0 | 0 | 36.98 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3331 | C | USCSB2401100A |  | HK Exhaust material for next 100 tools. Special specification | 45304 | 45313 | 343913.5 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 343913.5 | 0 | 343913.5 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3332 | C | USCSB2401101A |  | HK Exhaust material for next 100 tools. Special specifications only available in Taiwan. | 45304 | 45313 | 623987 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 623987 | 0 | 623987 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3333 | C | USCSB2401102A |  | Brother P-Touch PT- D610BT label maker, For plastic system, tool hook up team for 100 tools | 45305 | 45307 | 769.93 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 699.93 | 0.90908 | 70 | 0 | 70 | 0 | 699.93 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3334 | C | USCSB2401103A |  | Cord grip locknut O-Ring for HK Power trade | 45306 | 45307 | 18680.22 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 18679.04 | 0.99994 | 1.18 | 0 | 1.18 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 18031.6 | 0 |  | 0 | [5 empty] | 647.44 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3335 | C | USCSB2401104A |  | cart for UPW 20 tools, cutting saw blade for GAS 50 tools, tape for PCW 5o tools, Tool hookup team | 45307 | 45310 | 1869.11 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1837.3 | 0.98298 | 31.81 | 0 | 31.81 | 0 | 1837.3 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3336 | C | USCSB2401105A |  | Male cord grip for HK Power trade | 45307 | 45351 | 7830.28 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 7830.28 | 1 | 0 | 0 | 0 | 0 | 7830.28 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3337 | C | USCSB2401106A |  | One-Hole Lug Compression Connector for HK power trade | 45307 | 45307 | 1831 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1831 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 128.17 | [5 empty] | 1702.83 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3338 | C | USCSB2401107A |  | brother tape replacement for HK daily QAQC | 45307 | 45307 | 1108.68 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 957.24 | 0.86341 | 151.44 | 0 | 151.44 | 0 | 957.24 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3339 | C | USCSB2401108A |  | HK power trade materials | 45307 | 45308 | 18235.74 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 17138.84 | 0.93985 | 1096.9 | 0 | 1096.9 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 6679.8 |  | 4104.61 |  |  |  | 6354.43 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3340 | C | USCSB2401109A |  | office supplies for tool hookup department | 1/16/2024 8/22/2024 | 1/16/2024 8/28/2024 | 323.94 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 309.46 | 0.9553 | 14.48 | 0 | 14.48 | 0 | 309.46 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 3341 | C | USCSB2401110A | -01 | Single& Dual Vent Line Scope | 45308 | 2024/1/26 2024/2/22 | 0 | -100000 | 100000 |  |  |  |  | YAHO System Technology Co., Ltd. | PR Approved | PO Approved | PO R1:Change Vendor to YAHO USA |  | Yikang Wang (Ta Wei Wang) |  |  |  | Yikang Wang (Ta Wei Wang) | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 3342 | C | USCSB2401111A |  | 316L VAR VCR FITTING, SHORT TUBE BUTT WELD GLAND,1/2 VCR X 3/8 X 0.035 TBW, 0.75 (19.1 MM) EXT | 45308 | 45309 | 3014.4 | -9.29 | 3023.69 |  |  |  |  | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3014.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 3014.4 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Scaffolding | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3343 | C | USCSB2401112A |  | AMHS MML Scaffold | 45308 | 45309 | 4960 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2976 | 0.6 | 1984 | 394884.5 | -392900.5 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 2976 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 3344 | C | USCSB2401113A |  | CDS B side support LB1 | 45308 | 45328 | 101316 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 5500 | 0.054286 | 95816 | 0 | 95816 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 5500 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | NUUO | USC21C005 | F21P1 Chemical & WCCS package | 3345 | C | USCSB2401114A |  | SDS slurry electrical labor and materials | 45308 | 45355 | 171181.6 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 162122.52 | 0.94708 | 9059.08 | 0 | 9059.08 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 162122.52 | [6 empty] | 8559.08 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3346 | C | USCSB2401115A |  | FRP repair Fab LB2/WRC | 45308 | 45310 | 19000 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 19000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 19000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3347 | C | USCSB2401116A |  | HK scope for welding training, Tool hookup team | 45308 | 45310 | 1218.75 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 928.18 | 0.76158 | 290.57 | 0 | 290.57 | 0 | 928.18 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3348 | C | USCSB2401117A |  | Cable tie and cleanroom tapes for HK Exhaust trade HL | 45308 | 45308 | 1156 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1156 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 1156 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3349 | C | USCSB2401118A | -01 | D-ring anchorage for PPL trade | 45308 | 2024/1/18 2024/1/22 | 8506.39 | [5 empty] | V | WW Grainger Inc | PR Approved | PO Approved | R1: Due to Grainger line of credit limit, change the payment terms from Net 30 Days to 100% prepayment by Credit Card |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8506.39 | 1 | 0 | 0 | 0 | 0 | 8506.39 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3350 | C | USCSB2401119A |  | HK GENII IDEAS Equipment Rental_1st PO_End date 12/31/2023 | 45308 | 45310 | 59500 | [6 empty] | GENII IDEAS Co., Ltd. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 59500 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 37720 | 0 |  |  | 0 | 21780 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3351 | C | USCSB2401120A |  | United Rentals train the trainer certification for boom, scissor, reach & whs forks | 45308 | 45308 | 2399 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2399 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 2399 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3352 | C | USCSB2401121A |  | Southwest Fastener Open Statement Orders | 45309 | 45309 | 10750 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10750 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 10750 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 3353 | C | USCSB2401122A |  | KCANN3 Mechanical CIP work. YAHO completing chamber-divert lines and returning completed parts for installation | 45309 | 45328 | 12000 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 12000 | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3354 | C | USCSB2401123A |  | Pumping Line Material Order_Tungyi | 45309 | 45315 | 74477.41 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 73247.02 | 0.98348 | 1230.39 | 0 | 1230.39 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 3766.2 | 26689.08 |  | 0 | [7 empty] | 42791.74 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 3355 | C | USCSB2401124A | -01 | Labor and Material Quote for 16 tools | 45309 | 1/20/2024 2/22/2024 | 0 | -20552.68 | 20552.68 |  |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: PR was submitted under Main Tool so this order is cancelled |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3356 | C | USCSB2401125A | -01 | Gas 五金三百台補充第一批不足部分,Tool hookup team | 45309 | 2024/1/23 2024/2/1 | 323660 |  |  |  |  | V |  | Jinsheng Industrial Co | PR Approved | PO Approved | R1: item 10: 鍍鋅型鋼變向L片(E616) : 數量從50 改 500, ITEM 37: ST?十字丸頭螺絲?(OG0220100004) M4*12: 單價從0.6735改成 0.03 |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 323660 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 153190 | [8 empty] | 0 | 151040 | 19430 | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3357 | C | USCSB2401126A |  | Gasket and seal for HK Power trade | 45309 | 45314 | 8001.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8001.2 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 5301 |  | 0 | [14 empty] | 0 |  | 2700.2 | 0 | - | 0 | 0
Non-TSMC | Micron - Material | Material | USC24C001 | Micron - Chemical SOLBLE RN3000 | 3358 | C | USCSB2401128A |  | Chemical SOLBLE RN3000 for Micron Boise faclity, Idaho | 45309 | 45310 | 23200 | [6 empty] | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 23200 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 23200 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | Micron - Material | Material | USC24C001 | Micron - Chemical SOLBLE RN3000 | 3359 | C | USCSB2401129A |  | Chemical SOLBLE RN3000 for Micron Manassas facility, Virginia | 45309 | 45310 | 46250 | [6 empty] | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 46250 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 46250 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3360 | C | USCSB2401130A |  | equipment for all systems, Tool hook up team | 45309 | 45310 | 16456.78 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 16456.78 | 1 | 0 | 0 | 0 | 0 | 16456.78 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Site Expense | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 3361 | C | USCSB2401131A | -01 | TSMC Fiber Optic Electrical to CUP | 45309 | 2024/2/13 2024/2/15 | 77620 | [5 empty] | V | D.P. Electric, Inc. | PR Approved | PO Approved | R1: completion date change |  | Ta Wei Wang | [11 empty] | 38810 | 0.5 | 38810 | 0 | 38810 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 7762 | [13 empty] | 31048 | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Site Expense | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 3362 | C | USCSB2401132A |  | Generator upgrade | 45309 | 45335 | 158300 | [6 empty] | D.P. Electric, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 158300 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 15830 |  | 15830 | [7 empty] | 31660 |  | 94980 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC23C014 | F21P1 Labor incentive program-MICU | 3363 | C | USCSB2401134A |  | Laydown Material - U Line | 45309 | 45314 | 4970 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4970 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 4970 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3364 | C | USCSB2401135A |  | Wire for HK Power trade next 100 tools | 45309 | 45318 | 4238904.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4238222.86 | 0.99984 | 681.34 | 0 | 681.34 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 929060 |  | 679888.8 |  | 477850.4 |  | 655357 |  | 462823.66 |  | 453223 | 0 | 580020 | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC22C020 | F21P1 Penetration Pipe | 3365 | C | USCSB2401136A |  | Laydown Material - Home Depot | 45309 | 45314 | 623.39 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 602.8 | 0.96697 | 20.59 | 0 | 20.59 | 0 | 602.8 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC23C040 | TSMC F21 Clean Room Suit | 3366 | C | USCSB2401137A |  | Laydown Material - Amazon | 45310 | 1/24/2024 9/13/2024 | 522.9 | -85.05 | 607.95 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: Adjusting the PR amount to align with the actual PO and close out this PO. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 522.9 | 1 | 0 | 0 | 0 | 0 | 522.9 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 3367 | C | USCSB2401138A |  | EBO: ZCENT-1: INSTALL CABLE TRAY - LB1 | 45310 | 45331 | 1842 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1842 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 1842 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC22C013 | F21P1 QR Lab Security & CCTV | 3368 | C | USCSB2401139A |  | Laydown Material - Grainger | 2024/1/19 2024/1/24 | 45330 | 1763.38 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | PR R1:Total contains shipping cost, added 10% buffer |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 1763.38 | 0 | 1763.38 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC23C059 | F21P1 Foundation T&M | 3369 | C | USCSB2401140A |  | Laydown Material - Global Industrial | 45310 | 45397 | 180.32 | [6 empty] | Global Equipment Company Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 150.94 | 0.83707 | 29.38 | 0 | 29.38 | 0 | 150.94 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3370 | C | USCSB2401141A |  | Terminal for HK power trade | 45310 | 45310 | 98379 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 79794 | 0.81109 | 18585 | 0 | 18585 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 58296 |  | 4053 |  | 4218 | [12 empty] | 0 |  | 13227 | 0 | 13500 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3371 | C | USCSB2401142A |  | Steel core material Flex for HK Power trade | 45310 | 45315 | 1169995.9 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1169995.9 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 526430.82 |  | 290940.33 |  | 159870.66 |  | 134971.38 | [5 empty] | 46372.9 |  |  |  |  | 0 |  | 11409.81 | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3372 | C | USCSB2401143A |  | HK PCW 2nd 100 order | 1/19/2024 8/23/2024 | 1/31/2024 8/29/2024 | 394884.5 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Yikang Wang (Ta Wei Wang) |  |  |  | Yikang Wang (by David Wang) | [7 empty] | 0 | 0 | 394884.5 | 0 | 394884.5 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3373 | C | USCSB2401144A |  | KESDM2 DAQ | 1/19/2024 8/15/2024 | 2/24/2024 8/28/2024 | 0 | -103.66 | 103.66 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3374 | C | USCSB2401145A |  | divider box for 永旗 PPL, Cleanroom tapes shared by all system | 45310 | 45328 | 874.5 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 874.5 | 1 | 0 | 0 | 0 | 0 | 874.5 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [16 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Helix | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3375 | C | USCSB2401146A |  | WWT-Helix-A side 1/15 + 15 in March (partial 1M) | 45310 | 45310 | 1000000 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 975025 | 0 | 24975 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3376 | C | USCSB2401147A |  | KEPRL7 DAQ | 45310 | 45346 | 119.21 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 119.21 | 0 | 119.21 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3377 | C | USCSB2401148A |  | WWT-Weld machines rental for PSS | 45310 | 45315 | 18769.66 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 18769.66 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 18769.66 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | USC22C013 | F21P1 QR Lab Security & CCTV | 3378 | C | USCSB2401149A |  | F21 AUX and FAB CCTV, Access control and ACS system | 45310 | 45316 | 1000982.17 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 950933.06 | 0.95 | 50049.11 | 0 | 50049.11 | 50049.11 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 872868.31 | 0 |  | 0 | [13 empty] | 78064.75 | 15014.73 |  | - | 15014.73 | - | 15014.73 | 5004.92
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3379 | C | USCSB2401150A |  | KECOL4 DAQ Install E-sensors and route cables/PFA tubing to Prime Controls supplied AC box. | 2024/1/19 2024/8/14 | 2024/3/7 2024/8/16 | 0 | -350.74 | 350.74 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | PO R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3380 | C | USCSB2401151A |  | KEPCH2 DAQ | 1/19/2024 8/15/2024 | 2/24/2024 8/28/2024 | 0 | -103.66 | 103.66 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C001 | F21 P1 Office and WH Security and CCTV | 3381 | C | USCSB2401152A |  | F21 AUX and FAB CCTV, Access control and ACS system 1st portion | 45310 | 2024/1/25 2024/8/6 | 709832.25 | -290194.42 | 1000026.67 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PO R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 709832.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 632333.61 |  | 0 |  |  |  |  | 90803 | 77498.64 |  |  | 50002 |  |  |  | 50002 |  |  |  | - |  | - |  | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3382 | C | USCSB2401153A |  | materials for all systems, tool hookup team | 45310 | 45310 | 3714 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3330 | 0.89661 | 384 | 0 | 384 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 3330 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3383 | C | USCSB2401154A |  | WWT tools for MU | 45310 | 45310 | 1414 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1414 | 1 | 0 | 0 | 0 | 0 | 1414 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3384 | C | USCSB2401155A |  | IR Welding Machine for UPW system for 20 tools | 45310 | 45315 | 144590.09 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 144590.09 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 144590.09 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3385 | C | USCSB2401156A | -01 | John was cornered by TSMC today to purchase hand tools asap. | 45310 | 45311 | 765.68 | -258.75 | 1024.43 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: PR amendment on this to reflect the actual cost. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 765.68 | 1 | 0 | 0 | 0 | 0 | 765.68 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3386 | C | USCSB2401157A |  | Wire MC AL Bare Ground for HK Power trade | 45311 | 45315 | 193530 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 193530 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 193530 | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3387 | C | USCSB2401158A |  | Cable Tray clamp request for HK Power trade | 45311 | 45316 | 44220 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 44220 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 39360 |  | 0 |  | 4860 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3388 | C | USCSB2401159A |  | Electrolyte Gold, Replenishment solution | 45311 | 45315 | 2493 | [6 empty] | Servomex Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2493 | 0 | 2493 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3389 | C | USCSB2401160A |  | HK Power Trade Amazon order: Poly bags, tapes, and connectors for QAQC | 45311 | 45327 | 10630.34 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 8831.46 | 0.83078 | 1798.88 | 0 | 1798.88 | 0 | 8831.46 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3390 | C | USCSB2401161A |  | Amazon office supplies for HK Alex's team | 45311 | 45317 | 450.04 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 401.88 | 0.89299 | 48.16 | 0 | 48.16 | 0 | 401.88 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Site Expense | USC22C019 | AMC monitor 595T0 | 3391 | C | USCSB2401162A |  | Laydown Materials - Zoro | 45311 | 45336 | 1031.36 | [6 empty] | Zoro Tools, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 952 | 0.92305 | 79.36 | 0 | 79.36 | 0 | 952 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3392 | C | USCSB2401163A |  | WELDING and fragile welding label for QAQC, tool hookup team | 45311 | 45313 | 3950 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3950 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 3950 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3393 | C | USCSB2401164A |  | Scissorlift Invoice and Controller Quote for James McCormick shared by all system | 45311 | 45313 | 2395.5 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2395.5 | 0 | 2395.5 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3394 | C | USCSB2401165A |  | CDS ICP Mass CDA GN2 parts | 45311 | 45313 | 910.4 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 910.4 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 910.4 |  |  |  |  | 910.4 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 3395 | C | USCSB2401166A |  | WELD PIPE for KEMEA3 | 2024/1/20 2024/1/25 |  | 0 | [6 empty] | 0 | PR Approved | PO Approved | PR R1:wrong account code |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3396 | C | USCSB2401167A |  | Panduit Terminal for HK power trade | 1/21/2024 8/22/2024 | 2/14/2024 8/28/2024 | 2264 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Yikang Wang | [11 empty] | 2264 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 2264 | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3397 | C | USCSB2401168A |  | steel step drill bit set and 3-plane laser level kit for HK PCW trade | 45312 | 45313 | 748.7 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 748.7 | 1 | 0 | 0 | 0 | 0 | 748.7 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3398 | C | USCSB2401169A |  | Non-metallic twin screw for HK Power trade | 45312 | 45313 | 4306.7 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4306.7 | 1 | 0 | 0 | 0 | 0 | 4306.7 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3399 | C | USCSB2401170A |  | Cord grip for power trade | 45314 | 45314 | 28147.3 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 26860.6 | 0.95429 | 1286.7 | 0 | 1286.7 | 0 | 26860.6 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 3400 | C | USCSB2401171A |  | UPW-HKPs epoxy | 45314 | 45314 | 15718.13 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15718.13 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 15718.13 | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3401 | C | USCSB2401172A |  | WWT:Design,fabricate,Deliver,and install 2 ladders in FAB/LB2 to replace staircases on platforms that clashing with dike wall | 45314 | 45314 | 8569 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 8569 | 1 | 0 | 0 | 0 | 407.0275 | [47 empty] | 0 | 0 | 0 |  |  | 8140.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 428.45 | 0 | - | 0 | 0 | 407.0275
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3402 | C | USCSB2401173A |  | WWT-Install L20 HPM Drains | 45314 | 45315 | 480826 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 433945.75 | 0.9025 | 46880.25 | 0 | 46880.25 | 43394.575 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 45678.85 | 0 |  | 0 |  | 246663.7 |  |  | 72123.9 | 95924.35 |  |  | 72123.9 | 45678.85 |  |  | 72123.9 |  | 0 |  | - | 0 | - | 0 | 0 | 43394.575
Base-Build | Chemical Lab | UMEC | USC22C021 | F21P1 Chemical Lab setup | 3403 | C | USCSB2401174A |  | GC Lab Pressure Test | 45314 | 45315 | 11081 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11081 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 10527 | 0 | 0 |  | 554 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C011 | F21 TMAH System | 3404 | C | USCSB2401175A |  | WWT-TMAH-LCMSMS-Power | 45314 | 45317 | 11900 | [6 empty] | 2000 GOLD LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11900 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 11900 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | UMEC | USC23C054 | UPW Change Order | 3405 | C | USCSB2401176A |  | UPW-UMEC-T&M tickets | 45314 | 45316 | 110074 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 110074 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 104570 | 0 | 0 |  | 5504 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 3406 | C | USCSB2401177A |  | REI PCOs 26,28,37,39,46,52 | 45314 | 45316 | 97923.66 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 97923.66 | 1 | 0 | 0 | 0 | 195847.32 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 97923.66 |  | 97923.66 | 0 | - | 97923.66 | 0
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 3407 | C | USCSB2401178A | -01 | DIFF，Interconnection material Flexible Duct | 45314 | 2024/1/24 2024/1/31 | 2877 | [5 empty] | V | Marketech International Corp. | PR Approved | PO Approved | PR R1: Change Trade Term |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2877 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 2877 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC21C006 | F21P1 Slurry package | 3408 | C | USCSB2401179A |  | CDS T&M work Nov | 2024/1/23 2024/1/26 | 45315 | 619121.32 | [6 empty] | CRG International | PR Approved | PO Approved | PR R1:As per Purchasing team's David Wang,due to update the price and quote. |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 619121.32 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  | 619121.32 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC21C006 | F21P1 Slurry package | 3409 | C | USCSB2401180A |  | CDS T&M work Dec | 2024/1/23 2024/1/26 | 45315 | 582103.64 | [6 empty] | CRG International | PR Approved | PO Approved | PR R1:As per Purchasing team's David Wang,due to update the price and quote. |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 582103.64 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 582103.64 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C034 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/N2/APK/UPK/ASRS | 3410 | C | USCSB2401181A |  | AMHS Additional 140 AC Boxes Design | 45314 | 45314 | 21770 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 21770 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 21770 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C034 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/N2/APK/UPK/ASRS | 3411 | C | USCSB2401182A |  | FAB-1A Post IFP Owner Revisions | 45340 | 45342 | 35480 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 35480 | 0 | 35480 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3412 | C | USCSB2401183A |  | MOBILE BAR AND PIPE RACK, 18 for Gas, 10 for Plastic and 2 for UPW | 45314 | 45315 | 32069.58 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 32040.06 | 0.99908 | 29.52 | 0 | 29.52 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 32040.06 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3413 | C | USCSB2401184A |  | office supplies for tool hookup department | 45314 | 45315 | 145 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 132.86 | 0.91628 | 12.14 | 4509.2 | -4497.06 | 0 | 132.86 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3414 | C | USCSB2401185A |  | storage equipment for plastic system | 45314 | 45314 | 510.49 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 510.49 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 510.49 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3415 | C | USCSB2401186A |  | D-Ring for Safety, Weld-On PVC Cement for plastic and chemical system as hardware, tool hookup team | 45314 | 45315 | 4863.16 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4490.89 | 0.92345 | 372.27 | 0 | 372.27 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 4490.89 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3416 | C | USCSB2401187A |  | Filing cabinet, speaker, and protector sheet for safety PPE shared by all trades | 45314 | 45314 | 366 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 355.84 | 0.97224 | 10.16 | 0 | 10.16 | 0 | 355.84 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3417 | C | USCSB2401188A |  | 1221 Plastic儲存工具到貨核對 | 45314 | 45316 | 6662.42 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6662.42 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 6662.42 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC23C045 | WWT Change Order (Piping) | 3418 | C | USCSB2401189A |  | WWT -24-096 Stripper Platform FRP Ducting Modifications Quote | 45314 | 45314 | 15886 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 15886 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 15091.7 | 0 | 0 |  | 0 |  | 794.3 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3419 | C | USCSB2401190A |  | Cord grip for power trade | 45315 | 45324 | 10388 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 10388 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 9548 | [7 empty] | 840 |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3420 | C | USCSB2401191A |  | Global Solutions LLC Scissor lift EUV Crane Maintenance | 45315 | 45322 | 10520.27 | [6 empty] | Global Solutions LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10520.27 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 10520.27 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3421 | C | USCSB2401192A |  | WWT -MIC BMWC T&M SUS team 6*60hr | 45315 | 45315 | 45952 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 43654.4 | 0.95 | 2297.6 | 0 | 2297.6 | 2182.72 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 43654.4 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 2182.72
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3422 | C | USCSB2401193A | -01 | TSMC F21P1 STK#KCSK97 Height Change | 45315 | 2024/2/28 2024/3/7 | 80122.43 | [6 empty] | Murata Machinery, Ltd. | PR Approved | PO Approved | R1: Trade Term and Payment Term Change |  | Yikang Wang | [11 empty] | 0 | 0 | 80122.43 | 0 | 80122.43 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 80122.43 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3423 | C | USCSB2401194A |  | headlamp for Plastic system, Drill bit and lock shared for all system | 45315 | 45316 | 2521.67 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2478.7 | 0.98296 | 42.97 | 0 | 42.97 | 0 | 2478.7 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3424 | C | USCSB2401195A |  | Locknut for hk power trade | 45315 | 45316 | 26302.38 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 26302.38 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 26302.38 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3425 | C | USCSB2401196A |  | Global Roofing Glendale Warehouse roof inspection and roof repair | 45315 | 45352 | 4260 | [6 empty] | Sprayfoam Southwest Inc, DBA Global Roofing Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 4260 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  | 4260 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3426 | C | USCSB2401197A |  | Southwestern Scale Company EUV Crane Maintenance Mennen Annual Inspection | 2024/1/25 2024/3/6 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Cancelled, went with a different vendor |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3427 | C | USCSB2401198A |  | UPW hardware for JACO, customized hose connector, tool hook up team | 45316 | 45323 | 18735.37 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 18735.37 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 18735.37 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3428 | C | USCSB2401199A |  | CDS 1-1/4 Over Tube and Coax Elbow 90 | 45316 | 45316 | 40084 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 40084 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 40084 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3429 | C | USCSB2401200A |  | Brycon 6 mnths Electrical work for AMAT Team | 45316 | 45356 | 456146.57 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 456146.57 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 456146.57 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 3430 | C | USCSB2401201A |  | CDS Required maintenance and pressure switches for the CO2 systems, 24 for Lorry and 52 for Fab A | 45316 | 45320 | 84512 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 84512 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 21128 | 63384 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3431 | C | USCSB2401202A |  | office supplies for tool hookup department | 45316 | 45316 | 138 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 125.94 | 0.91261 | 12.06 | 0 | 12.06 | 0 | 125.94 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 3432 | C | USCSB2401203A |  | UPW-mezz 3-egress ladder revise | 45316 | 45321 | 8025 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7623.75 | 0.95 | 401.25 | 0 | 401.25 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 7623.75 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 401.25 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3433 | C | USCSB2401204A |  | AMAT Amazon order | 45316 | 45316 | 490.39 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 430.78 | 0.87844 | 59.61 | 0 | 59.61 | 0 | 430.78 | [46 empty] | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3434 | C | USCSB2401205A |  | scrubber mat for hk department shared by all system | 45316 | 45317 | 351.96 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 313.56 | 0.8909 | 38.4 | 0 | 38.4 | 0 | 313.56 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3435 | C | USCSB2401206A |  | Wesco Panduit | 45316 | 45317 | 551.99 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 551.99 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 551.99 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3436 | C | USCSB2401207A |  | WELD PIPE for KEMEA3 | 45316 | 45329 | 345.72 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 345.72 | 1 | 0 | 4345 | -4345 | 0 | [47 empty] | 0 | 0 | 0 |  | 345.72 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3437 | C | USCSB2401208A |  | Hardware request for HK Power/PPL trade | 45316 | 45316 | 11575 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11575 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 11575 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 3438 | C | USCSB2401210A |  | trim edge, spring nut, hex nut, washer, cleanroom tape. | 45316 | 45316 | 337.85 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 337.85 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 337.85 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3439 | C | USCSB2401212A |  | Contractor drill bit for hk power, ppl, and exhaust trade | 45316 | 45316 | 544.2 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 494.7 | 0.90904 | 49.5 | 0 | 49.5 | 0 | 494.7 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3440 | C | USCSB2401213A |  | Portable band saw blade for HK Power trade | 45317 | 45320 | 1071.2 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1071.2 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 1071.2 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3441 | C | USCSB2401214A |  | Galvanized Loose flat ring flange for HK exhaust | 45317 | 45317 | 2407.2 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2407.2 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 2407.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3442 | C | USCSB2401216A |  | Spiral pipe and flat flange for HK Exhaust trade | 45317 | 45317 | 47980 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 22048.8 | 0.45954 | 25931.2 | 0 | 25931.2 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 12164 |  | 0 |  | 9884.8 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3443 | C | USCSB2401217A |  | TMAH expansion tank move in | 45317 | 45321 | 15912 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 15912 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 15912 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3444 | C | USCSB2401218A |  | WWW-HKPs epoxy | 45317 | 45320 | 25247.39 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 25247.39 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 25247.39 |  | 0 |  |  |  |  | 3787.1085 |  |  |  | 3787.1085 |  |  |  | 3787.11 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C006 | F21P1 Slurry package | 3445 | C | USCSB2401219A |  | CDS Lorry A 18 Tank | 45317 | 45320 | 972000 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 923400 | 0.95 | 48600 | 0 | 48600 | 48600 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 777600 |  | 0 |  |  |  |  | 145800 | 145800 | [8 empty] | 48600 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3446 | C | USCSB2401220A |  | Quick-Clamp High-Vacuum Fitting for Stainless Steel Tubing, Straight Reducer for 1-1/2" x 1" Tube | 45317 | 45321 | 2533.05 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2508.8 | 0.99043 | 24.25 | 0 | 24.25 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 2508.8 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C006 | F21P1 Slurry package | 3447 | C | USCSB2401221A |  | CDS B side support L20 | 2024/1/26 2024/3/28 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:As per PM:Johnny Wan to cancel the PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3448 | C | USCSB2401222A |  | RS Labor for Tool Hookup: October- December | 45317 | 45320 | 29212.94 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 29212.94 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 29212.94 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C006 | F21P1 Slurry package | 3449 | C | USCSB2401223A |  | CDS Cheng Shing extension open PO | 45317 | 45323 | 80000 | [6 empty] | Cheng Shing MEP Taiwan Co. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 45959.33 | 0.57449 | 34040.67 | 0 | 34040.67 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 45959.33 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3450 | C | USCSB2401224A |  | Saw blade for gas system, tool hookup team | 45317 | 45367 | 580 | [6 empty] | Orbitalum North America | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 0 | 0 | 580 | 0 | 580 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C006 | F21P1 Slurry package | 3451 | C | USCSB2401225A |  | CDS WLS SS anchor brackets | 45317 | 45320 | 3227 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3227 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 3227 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3452 | C | USCSB2401226A |  | KECOT1 DAQ RS Payroll | 2024/1/26 2024/8/15 | 2024/1/27 2024/8/15 | 923.69 | -631.21 | 1554.9 |  |  | V |  | RS PAYROLL SERVICES | PR Approved | PO Approved | To release excess bugdet |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 923.69 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 923.69 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Rosendin | USC21C006 | F21P1 Slurry package | 3453 | C | USCSB2401227A |  | REI CDS CO | 45317 | 45331 | 1658637 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1658637 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 1658637 | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3454 | C | USCSB2401228A |  | Tmah + L20 Sludge CDA materials | 45317 | 45318 | 3785.8 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3785.8 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  | 3785.8 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 3455 | C | USCSB2401229A |  | QR Lab Drain and UPW construction parts | 45317 | 45317 | 510.82 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 510.82 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 510.82 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3456 | C | USCSB2401230A |  | Narrow size washers | 2024/1/26 2024/1/29 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:cancel this PR | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3457 | C | USCSB2401231A |  | WWT_pressure gauge QTY:2 | 45317 | 45317 | 468.86 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 468.86 | 0 | 468.86 | 468.86 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 70.329 |  |  |  | 70.329 |  |  |  | 70.329 |  | 468.86 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 3458 | C | USCSB2401232A |  | TSMC F21 E2 VISA Yisin manpower for maruta | 45317 | 45324 | 14000 | [6 empty] | Yi Sin Mechanical LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 14000 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 14000 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C006 | F21P1 Slurry package | 3459 | C | USCSB2401233A |  | CDS OE electrical work | 45317 | 45323 | 192691.19 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 192691.19 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 192691.19 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C032 | F21_AZQR_Hookup_ Interconnection | 3460 | C | USCSB2401234A |  | QR LAB: KXPS/KXFX/KXSM: CABLE TRAY CLAMPS, STRUT NUT, WEDGE ANCHOR | 45317 | 45330 | 3867.61 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3867.61 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 3867.61 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Southland | USC21C005 | F21P1 Chemical & WCCS package | 3461 | C | USCSB2401235A |  | WCCS CO#172 W-A515 L20 | 45318 | 45322 | 5590.8 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5590.8 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 5590.8 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3462 | C | USCSB2401236A |  | 40 – 8/8/4 Shoe Tee fittings with flat flanges for HK Exhaust trade | 45318 | 45320 | 4288 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 4288 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 4288 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C053 | AMAT Interconnection (TSMC) | 3463 | C | USCSB2401238A |  | KESDA3.1 Tray Dividers, & Insulated Clamps | 45318 | 45324 | 2006.65 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2006.65 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 2006.65 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3464 | C | USCSB2401239A |  | CVD2_KCANN3_316L union Tee, 1/4 in. OD | 45321 | 45322 | 487.25 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 487.25 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  | 487.25 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC23C054 | UPW Change Order | 3465 | C | USCSB2401240A |  | UPW-UMEC-B side ACF loading | 45321 | 45321 | 86906 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 78215 | 0.9 | 8691 | 0 | 8691 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 69525 | 0 |  | 8690 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 3466 | C | USCSB2401241A |  | KCANN1 CIP re-work | 45321 | 45322 | 1944.64 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1944.64 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 1944.64 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3467 | C | USCSB2401242A |  | CDS Tee and Bulkhead. | 45321 | 45321 | 599.26 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 599.26 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 | 599.26 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3468 | C | USCSB2401243A |  | hole saw for Tsmc training center, tool hookup team | 45321 | 45323 | 716.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 634.1 | 0.88524 | 82.2 | 0 | 82.2 | 0 | 634.1 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C011 | F21 TMAH System | 3469 | C | USCSB2401244A |  | WWT-TMAH-LCMSMS-Nitrogen | 45321 | 45320 | 798.45 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 798.36 | 0.99989 | 0.09 | 0 | 0.09 | 0 | [48 empty] | 0 | 0 | 798.36 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 3470 | C | USCSB2401245A |  | KDALS2 re-work to fulfill CIP signal cables | 45321 | 45322 | 972.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 972.32 | 0 | 972.32 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3471 | C | USCSB2401246A |  | Poly bags for HK Power trade Third | 45321 | 45321 | 11022 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 11022 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 11022 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 3472 | C | USCSB2401247A |  | KCSNA1 re-work to fulfill CIP signal cables | 45321 | 45322 | 972.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 972.32 | 1 | 0 | 3266 | -3266 | 0 | [48 empty] | 0 | 0 |  |  | 972.32 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3473 | C | USCSB2401248A |  | 625 psi high pressure regulators and N2 cylinder | 45321 | 45323 | 2663.15 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 2663.15 | 0 | 2663.15 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 3474 | C | USCSB2401249A |  | KCANN2 re-work to fulfill CIP gasline heater jacket and AC boxes. | 45321 | 45322 | 1944.64 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1944.64 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 1944.64 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3475 | C | USCSB2401250A |  | FAB A&B labels | 45321 | 45336 | 16794.97 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 16767.03 | 0.99834 | 27.94 | 0 | 27.94 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 16767.03 |  | 0 |  |  |  |  | 2519.2455 |  |  |  | 2519.2455 |  |  |  | 2519.2455 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3476 | C | USCSB2401251A |  | Aluminum foil duct for exhaust | 45322 | 45322 | 64.96 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 64.96 | 1 | 0 | 0 | 0 | 0 | 64.96 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3477 | C | USCSB2401252A |  | WWT commissioning chemical | 45322 | 45328 | 104396.2 | [6 empty] | Kurita America Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 81863.88 | 0.78417 | 22532.32 | 0 | 22532.32 | 18010.0536 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 15659.43 | 81863.88 |  |  | 15659.43 |  |  |  | 15659.43 |  | 4093.194 |  | - | 4093.194 | - | 4093.194 | 5730.4716 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3478 | C | USCSB2401253A |  | Cord grips for HK Power trade | 45322 | 45330 | 4324.2 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 4324.2 | 0 | 4324.2 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC22C026 | F21P1-0423_H_Unistrut Support Frame_MICU | 3479 | C | USCSB2401254A |  | raised floor | 45322 | 45327 | 56500 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 56500 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 56500 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3480 | C | USCSB2401255A |  | HK QAQC labels | 45322 | 45324 | 10704.3 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 10704.3 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 10704.3 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 3481 | C | USCSB2401257A |  | WWT Supplemental Material&WWT Premium Time 11.25-11.26 | 45322 | 45325 | 17961 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 17961 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 17063 | 0 | 0 |  | 0 |  | 898 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS | Labor | USC22C014 | F21P1 AMHS Power Panel | 3482 | C | USCSB2401258A |  | Chi-Yang manpower for interconnection(Feb-May) and AMHS(June-Oct) | 2024/1/31 2024/3/8 |  | 0 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | PR R1:As per Martin to cancel the PR. |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3483 | C | USCSB2401259A |  | KNAACK Cabinet Workbench, Tool hookup team | 45322 | 45323 | 4363.42 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 4363.42 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 4363.42 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3484 | C | USCSB2401260A | -01 | Consumables for HK exhaust trade | 45322 | 2024/1/31 2024/2/1 | 1447 | [5 empty] | V | U-Line Corporation | PR Approved | PO Approved | R1: Payment Term changed from NET 30 to Credit Card as the Uline account reaches credit limit |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1447 | 1 | 0 | 0 | 0 | 0 | 1447 | [47 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3485 | C | USCSB2401261A |  | Pressure Recorder | 45322 | 45323 | 1750 | [6 empty] | Richwell Instrument Co., Ltd. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1750 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 1750 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Equipment | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3486 | C | USCSB2401262A | -01 | I-Line USE PLUG-IN NFB 15A 2-Pole AC breaker | 45322 | 2024/4/1 2024/6/18 | 0 | -603 | 603 | V | V |  |  | Third Enterprise | PR Approved | PO Approved | R1: As per engineer Tzuhao to cancel this PR. |  | Ta Wei Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3487 | C | USCSB2401263A |  | CDS B side support L30 materials | 45322 | 45324 | 21369.16 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 21369.16 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 1766.13 | 19603.03 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 3488 | C | USCSB2402001A |  | CDS B side support L30 coating | 45323 | 45324 | 21400 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 21400 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 21400 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C014 | F21P1 AMHS Power Panel | 3489 | C | USCSB2402002A | -01 | He Dain(和電) Manpower for Hookup Interconnection | 2024/2/1 2024/3/8 | 2024/2/28 2024/3/11 | 0 | -740520 | 740520 |  |  |  | V | He Dain Automation Equipment Co.,Ltd. | PR Approved | PO Approved | PO R1: As per Martin to cancel the PR. (Change to Sinfo Engineering) |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3490 | C | USCSB2402003A |  | 100% DI Water Cleanroom wipes for HK shared by all trades | 2024/2/1 2024/2/29 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:need dry wipes instead |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Greenberry | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3491 | C | USCSB2402004A |  | MIC-004-22 X1-Line Cable Tray Supports | 45323 | 45337 | 962482 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 962482 | 1 | 0 | 0 | 0 | 962482 | [48 empty] | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  |  | 48124.1 |  |  |  | 144372.3 |  |  | 962482 | 144372.3 |  | 192496.4 |  | - | 192496.4 | - | 192496.4 | 192496.4 | 192496.4
Base-Build | WWT | Greenberry | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3492 | C | USCSB2402005A |  | MIC-009-23 -Fabricate, paint & Install additional X Line to Tunnel supports | 45323 | 45328 | 42159 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 40051.05 | 0.95 | 2107.95 | 0 | 2107.95 | 2002.5525 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 6323.85 | 40051.05 |  |  | 6323.85 |  |  |  | 6323.85 |  | 0 |  | - | 0 | - | 0 | 0 | 2002.5525
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3493 | C | USCSB2402006A |  | CDS pipe labels | 45323 | 45323 | 3502 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 3502 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 3502 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | UMEC | USC21C005 | F21P1 Chemical & WCCS package | 3494 | C | USCSB2402007A |  | CDS TSMC UPW 8-178 Chemical Scope (T&M) | 45323 | 45325 | 7085 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 7085 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 6731 | 0 | 0 |  | 354 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3495 | C | USCSB2402008A |  | CDS Sensor FLS-VM-400 | 45323 | 45327 | 1963.5 | [6 empty] | AutomationDirect.com INC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1785 | 0.90909 | 178.5 | 0 | 178.5 | 0 | 1785 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 176.72 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 3496 | C | USCSB2402009A |  | UMEC overtime for Blackout Testing Sunday Work | 45323 | 45325 | 25009 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 25009 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 23759 | 0 | 0 |  | 0 |  | 1250 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | TMAH | Equipment | USC21C011 | F21 TMAH System | 3497 | C | USCSB2402010A |  | HFC/ Tmah tools | 45323 | 45322 | 629.87 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 629.87 | 1 | 0 | 0 | 0 | 0 | 629.87 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | TMAH | Equipment | USC21C011 | F21 TMAH System | 3498 | C | USCSB2402011A |  | HFC/Tmah sealant tool | 45323 | 45323 | 3097.89 | [6 empty] | Southern Industrial Supply, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3097.89 | 1 | 0 | 0 | 0 | 0 | 3097.89 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3499 | C | USCSB2402012A |  | Mobile helium leak detector for tool hookup team | 45323 | 45345 | 44200 | [6 empty] | INFICON Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 44200 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  | 44200 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 3500 | C | USCSB2402013A |  | UPW-UMEC-TSMC-CO for B side ACM-C expansion | 45323 | 45327 | 70061 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 66558 | 0.95 | 3503 | 0 | 3503 | 0 | [48 empty] | 0 | 0 |  |  | 59552 | 0 | 0 |  | 7006 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 3501 | C | USCSB2402014A |  | WWT Stripper Fan Connection | 45323 | 45323 | 3266 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 3266 | 0 | 3266 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 489.9 |  |  |  | 489.9 |  |  |  | 489.9 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3502 | C | USCSB2402015A |  | WWT B side Geijinsin Lb1/L20 submain | 2024/2/1 2024/9/10 | 2024/2/5 2024/9/16 | 456000 | -24000 | 480000 |  |  |  |  | Gejinsin Enterprise Co., Ltd. | PR Approved | PO Approved | R1: As per PM Jim to Adjust this PR to 95% of the total amount. Jim has informed the Gejinsin. |  | Kuan-Chung Su | [11 empty] | 456000 | 1 | 0 | 0 | 0 | 111666 | [48 empty] | 0 | 150000 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 48000 | 151800 |  |  | 48000 |  |  | 130200 | 48000 |  | 30180 |  | 24000 | 30180 | - | 30180 | 21126 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3503 | C | USCSB2402016A |  | Pallet jack and sweeping compound for James McCormick shared by all HK system | 45323 | 45323 | 1124.9 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1011 | 0.89875 | 113.9 | 0 | 113.9 | 0 | 1011 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3504 | C | USCSB2402017A |  | Clamps for A side 2024.1.31-1 | 45323 | 45324 | 7130.9 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 7130.9 | 1 | 0 | 0 | 0 | 7130.9 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1069.635 |  |  |  | 1069.635 |  |  | 7130.9 | 1069.635 |  | 3565.45 |  | - | 3565.45 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3505 | C | USCSB2402018A |  | Material Request for the label.for 150 tools, tool hookup team | 45323 | 45323 | 659.4 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 376.02 | 0.57025 | 283.38 | 0 | 283.38 | 0 | 376.02 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3506 | C | USCSB2402019A | -01 | Connectors for HK Power trade | 45324 | 2024/2/5 2024/2/13 | 180400 | -30100.5 | 210500.5 | V |  |  |  | Crescent Electric Supply Co | PR Approved | PO Approved | R1: Negotiated from $$210,500.50 to $180,400 |  | Ta Wei Wang | [11 empty] | 180399.99 | 1 | 0.01 | 0 | 0.01 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 180399.99 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3507 | C | USCSB2402020A |  | CDS HPM Punch materials | 45324 | 45324 | 4560.23 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 4560.23 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 4560.23 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3508 | C | USCSB2402021A |  | CDS CDA fittings | 45324 | 45325 | 956.96 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 956.96 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 | 956.96 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3509 | C | USCSB2402022A | -01 | CDS LB2 SS parts | 45324 | 2024/2/2 2024/2/8 | 14128.04 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | PO R1: Change Trade Term: 100% NET 45 -> 100% NET 30 |  | Ta Wei Wang | [11 empty] | 14077.5 | 0.99642 | 50.54 | 0 | 50.54 | 0 | [48 empty] | 0 | 0 |  | 14077.5 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3510 | C | USCSB2402023A |  | CDS cush clamp, screw | 45324 | 45324 | 195.83 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 195.83 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 195.83 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3511 | C | USCSB2402024A |  | WWT A side remaining unistrut 2024.1E1 | 45324 | 45324 | 16456.08 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 16456.08 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 | 16456.08 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3512 | C | USCSB2402025A |  | CDS 1" CPVC and Coupling | 45324 | 45324 | 14238 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 14238 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 14238 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3513 | C | USCSB2402026A |  | WWT Cleaning Material | 45324 | 45324 | 791 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 791 | 1 | 0 | 0 | 0 | 0 | 791 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | TMAH | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3514 | C | USCSB2402027A |  | Tmah Resin filling | 45324 | 45324 | 908.9 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 908.9 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 908.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3515 | C | USCSB2402028A |  | SUS added to A side 02/01 all drop not finish 1st order(SUS WWTSP1E2024-1) | 45324 | 45324 | 3442.64 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3442.64 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 | 3442.64 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C029 | EBO21- Tool interconnection | 3516 | C | USCSB2402029A |  | EBO: ZFP3-1: INSTALL GEX EXHAUST | 45325 | 45331 | 7858 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 7858 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 7858 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3517 | C | USCSB2402030A |  | KCSMA6, KCASA4 Core Hole Sleeve Handoff | 45325 | 45328 | 610.3 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 610.3 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 610.3 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | UMEC | USC21C005 | F21P1 Chemical & WCCS package | 3518 | C | USCSB2402031A |  | CDS TSMC UPW 8-177 NH4 TMAH | 45325 | 45330 | 220941 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 220941 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 209894 | 0 | 0 |  | 11047 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3519 | C | USCSB2402032A |  | filter | 45325 | 45335 | 89971.2 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 89971.2 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 89971.2 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3520 | C | USCSB2402033A |  | Etch 2 CIP installation DAQ - DAQ installation tools | 45325 | 45327 | 319.83 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 283.43 | 0.88619 | 36.4 | 0 | 36.4 | 0 | 283.43 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3521 | C | USCSB2402034A |  | UPG MALE SLEEVE, UPG COUPLING BODY, | 45325 | 45327 | 1510.5 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1510.5 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 319 |  | 0 |  | 1191.5 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3522 | C | USCSB2402035A | -01 | CDS LB2 SS parts | 2024/2/3 2024/2/6 2024/2/27 | 2024/2/9 2024/2/28 | 0 | -7721.5 | 7721.5 |  |  |  | V | Propersys Corp | PR Approved | PO Approved | PR R1:As per TJ to updated the quote (remove item 3、4 and 7 ) PO R1: Duplication Order |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3523 | C | USCSB2402036A |  | Cleanroom paper shared by all hk systems | 45325 | 45327 | 1472.2 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 736.1 | 0.5 | 736.1 | 0 | 736.1 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 736.1 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3524 | C | USCSB2402037A |  | KCASA4 Dividers and AC Cover Modifications | 45325 | 45329 | 3080.34 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 3080.34 | 0 | 3080.34 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3525 | C | USCSB2402038A |  | CDS Lorry FNDP parts | 45325 | 45327 | 1727.5 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1727.5 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 1727.5 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3526 | C | USCSB2402040A |  | MMI Tile alignment T&M (Hank) | 45328 | 45335 | 78000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 78000 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 35319.5 | 0 | 0 |  | 42680.5 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 3527 | C | USCSB2402041A |  | Cleaning Material(ishine floor finish) | 45328 | 45330 | 5610 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 4537.8 | 0.80888 | 1072.2 | 0 | 1072.2 | 862.182 | 4537.8 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 862.182 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3528 | C | USCSB2402042A |  | CDS Conduit Tee | 45328 | 45328 | 2688.58 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2688.58 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 2688.58 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 3529 | C | USCSB2402043A |  | CDS Welder rental for Chemical welding. | 45328 | 45328 | 2800 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 2800 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 2800 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3530 | C | USCSB2402044A |  | ETCH 2 CIP installation - ETCH 2 CIP installation TOOLS. | 45328 | 45328 | 171.89 | [6 empty] | Harbor Freight Tools USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 171.89 | 40824 | -40652.11 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3531 | C | USCSB2402045A |  | CDS 1/2 GROUNDING PIGTAIL | 45328 | 45328 | 27.24 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 27.24 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 27.24 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3532 | C | USCSB2402046A |  | WWT Hardware for punches | 45328 | 45330 | 5203.94 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5203.94 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  | 1653.35 | 80.08 | 3470.51 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3533 | C | USCSB2402047A |  | CDS BT union and gasket | 45328 | 45329 | 1718.93 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1718.93 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 1460.43 | 0 |  | 0 |  |  |  | 258.5 | 257.84 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 3534 | C | USCSB2402048A |  | WWT Leak Detector Accessory-Omron F03-20T | 45328 | 45328 | 1840.39 | [6 empty] | Mouser Electronics | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1840.39 | 1 | 0 | 0 | 0 | 0 | 1840.39 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | VOC | Labor | USC21C008 | F21P1 CCTV & Security | 3535 | C | USCSB2402049A | -01 | VOC Electric CO17&CO28 | 45328 | 2024/2/20 2024/3/15 | 13954 | -23890 | 37844 |  | V |  | V | Spectra Electrical Services, Inc. | PR Approved | PO Approved | Amount applied for includes claims for Davis Bacon Act training, which may if any be reimbursed upon receipt of funds from Chips Act |  | Tiong Sheng Poh | [11 empty] | 13954 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 13954 | [6 empty] | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC22C001 | F21 P1 Office and WH Security and CCTV | 3536 | C | USCSB2402050A |  | VOC Electric CO#7,8,18,19,21,27,29 | 45328 | 45337 | 405423.43 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 405423.43 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 158377.51 |  | 196260.18 | 50785.74 | 0 | 0 |  | 0 | [16 empty] | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 3537 | C | USCSB2402051A |  | VOC Electric CO#5.6.9.10.12.13.14.15.16.20.22.24.26 | 45328 | 45641 | 415467.87 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 415467.87 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 147020.69 | 0 | 134520.83 |  | 0 |  | 133926.35 | [14 empty] | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3538 | C | USCSB2402052A |  | cable lugs for hk power trade | 45328 | 45329 | 148.48 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 148.48 | 1 | 0 | 0 | 0 | 0 | 148.48 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Helix | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3539 | C | USCSB2402053A |  | WWT-Helix-A side 1/15 + 15 in March (partial 1.4M) | 45329 | 45335 | 1400000 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1399921.49 | 0.99994 | 78.51 | 12590 | -12511.49 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 756650.49 |  | 643271 |  |  |  |  | 210000 |  |  |  | 210000 |  |  |  | 210000 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 3540 | C | USCSB2402054A | -01 | WWT-TMAH-LCMSMS-set up chemicals | 45329 | 2024/2/9 2024/5/21 2024/7/12 | 8949.45 | [6 empty] | Agilent Technologies, Inc. | PR Approved | PO Approved | R1: Change per New Quote R2: Change payment term |  | Yi En Wong | [11 empty] | 0 | 0 | 8949.45 | 0 | 8949.45 | 8949.45 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1342.4175 |  |  |  | 1342.4175 |  |  |  | 1342.4175 |  | 4474.725 |  | - | 4474.725 | - | 0 | 0 | 0
Base-Build | VOC | Labor | USC22C013 | F21P1 QR Lab Security & CCTV | 3541 | C | USCSB2402055A |  | VOC Extending General Conditions(CO # 31) | 45329 | 45337 | 229358 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 229358 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 124232.86 |  |  |  | 105125.14 | [10 empty] | - | 0 | - | 0 | 0
Others | Liquid Penetrant | Labor | USC22C035 | CAP_A_90772_F21 Phone call base build and Liquid penetrant testing system | 3542 | C | USCSB2402056A |  | Mask Room Viewtile (T&M) | 45329 | 45328 | 3000 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1568.96 | 0.52299 | 1431.04 | 0 | 1431.04 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 774.76 | [14 empty] | 0 |  | 794.2 | 0 | 813.03 | 0 | 0
Base-Build | Triazole | Labor | USC22C022 | F21P1 Triazole treatment system | 3543 | C | USCSB2402057A |  | WWT-Triazole Electrical | 45329 | 45336 | 275000 | [6 empty] | 2000 GOLD LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 275000 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 275000 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3544 | C | USCSB2402058A |  | CIP ETCH3 - CIP Tools ETCH3 | 45329 | 45331 | 191.79 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 174.13 | 0.90792 | 17.66 | 0 | 17.66 | 0 | 174.13 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3545 | C | USCSB2402059A |  | cable lugs for hk power trade | 2024/2/7 2024/2/10 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:zero out |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 3546 | C | USCSB2402060A |  | CDS Lorry A Add pressure detector piping | 45329 | 45336 | 165474 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 157200.3 | 0.95 | 8273.7 | 0 | 8273.7 | 8273.7 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 132379.2 | 157200.3 | 24821.1 | [8 empty] | 8273.7 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3547 | C | USCSB2402061A |  | materials for all systems, tool hookup team 300 tools | 45329 | 45332 | 1347.9 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1225.4 | 0.90912 | 122.5 | 0 | 122.5 | 0 | 1225.4 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3548 | C | USCSB2402062A |  | Consolidated Electrical Distributors Fiber Optic Material for GWH OSC | 45329 | 45330 | 721 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 721 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 721 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3549 | C | USCSB2402063A |  | Fiberglass Routing S-Hook for 2-3/4" Maximum Bundle Diameter, Yellow | 45329 | 45329 | 3582.69 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3582.69 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 3582.69 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 3550 | C | USCSB2402064A |  | EBO: ZCOAT-1: RIGID UNISTRUT CLAMPS | 45329 | 45364 | 274.97 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 274.97 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 274.97 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3551 | C | USCSB2402065A |  | Cleanroom paper shared by all hk systems | 45330 | 45334 | 2944.4 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2944.4 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 2944.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3552 | C | USCSB2402066A | -01 | Orbit Industrial Services & Maintenance/Weight scales for EUV maintenance. | 45329 | 2/15/2024 3/7/2024 | 6507.2 | [6 empty] | ORBIT industrial service & maintenance LLC | PR Approved | PO Approved | R1: completion date change |  | Yikang Wang | [11 empty] | 6507.2 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 6507.2 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3553 | C | USCSB2402067A |  | WWT material 01.26 (A Side) | 45330 | 45336 | 10075.75 | 10075.75 | [5 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 8936.58 | 0.88694 | 1139.17 | 0 | 1139.17 | 983.0238 | [49 empty] | 0 |  |  | 3358.59 | 0 | 0 |  | 0 |  |  |  | 3683.19 | 503.7875 | 1894.8 |  |  | 1007.575 |  |  |  | 1007.575 |  | 983.0238 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 3554 | C | USCSB2402068A |  | Sinfonia Electrical Technical Support | 45330 | 45336 | 888462 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 444231 | 0.5 | 444231 | 0 | 444231 | 0 | [49 empty] | 0 |  |  | 444231 | 0 | 0 |  | 0 | [16 empty] | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3555 | C | USCSB2402069A |  | Quick-Clamp High-Vacuum Fitting for Stainless Steel Tubing, Straight Reducer for 1-1/2" x 1" Tube | 45330 | 45331 | 2727.44 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2714.8 | 0.99537 | 12.64 | 0 | 12.64 | 0 | [49 empty] | 0 |  |  | 0 | 2714.8 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3556 | C | USCSB2402070A |  | ULINE UTILITY CART, for gas system | 45330 | 45332 | 3625 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 3625 | 1 | 0 | 0 | 0 | 0 | 3625 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 3557 | C | USCSB2402071A |  | EBO: ZMERIT & ZASC5-1: FEMALE CONNECTORS | 45330 | 45330 | 86.56 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 86.56 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  | 86.56 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3558 | C | USCSB2402072A |  | WWT Blind Flange installation | 45330 | 45343 | 20700 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 20700 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 20700 |  |  | 3105 |  |  |  | 3105 |  |  |  | 3105 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3559 | C | USCSB2402073A |  | WWT Add Litho Drain Pipe Supports | 2024/2/8 2024/8/21 | 2024/2/21 2024/8/21 | 40824 | -17496 | 58320 | V |  |  | V | Mirador Construction Service, LLC | PR Approved | PO Approved | PR R1: As per Jim to revise the PO amount to $40,824 for close out. |  | Ta Wei Wang | [11 empty] | 0 | 0 | 40824 | 0 | 40824 | 58320 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8748 |  |  |  | 8748 |  |  |  | 8748 |  | 14580 |  | - | 14580 | - | 14580 | 14580 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3560 | C | USCSB2402074A | -01 | Temporary chemical leak kit 10/45-10 | 45330 | 2024/2/14 2024/4/3 | 6515.1 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | R1: Switch payment method to Credit Card per Angela's request |  | Jen-Ping Tsai | [11 empty] | 6515.1 | 1 | 0 | 0 | 0 | 0 | 6515.1 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 977.265 |  |  |  | 977.265 |  |  |  | 977.265 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 3561 | C | USCSB2402075A | -01 | KCBDA4 Vent Line Retro Fit | 45330 | 2024/2/22 2024/5/4 | 120000 |  |  |  | V |  |  | YAHO System Technology Inc. | PR Approved | PO Approved | R1: Updateing contract scope to align quantity of Tool ID (Removed KCBDA1) |  | Ta Wei Wang | [11 empty] | 36000 | 0.3 | 84000 | 0 | 84000 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 36000 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3562 | C | USCSB2402076A |  | CDS M6 x 1 x 16 (5/8) Screws | 45330 | 45331 | 130 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 130 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 130 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3563 | C | USCSB2402077A |  | CDS M6 x 1 x 16 (5/8) Screws PP | 45330 | 45331 | 875 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 875 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 875 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3564 | C | USCSB2402078A |  | KKSV03, KKDD03, KKDB05 AMAT Terminations | 45330 | 45332 | 4908.24 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1472.47 | 0.3 | 3435.77 | 0 | 3435.77 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 1472.47 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3565 | C | USCSB2402079A |  | WWT SUS Pipes_20240207 (A Side) | 45330 | 45331 | 1635.28 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1635.28 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 1635.28 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Triazole | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3566 | C | USCSB2402081A |  | TRIAZOLE & NH3 stripper pad scopes | 45330 | 45352 | 63146.26 | [6 empty] | Revolution Industrial LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 63146.26 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 63146.26 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3567 | C | USCSB2402082A |  | Change Order KCSMA6 Dividers and AC Cover Modifications | 45330 | 45332 | 2613.84 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2613.84 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 2613.84 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Trident | USC21C014 | F21P1 WH2SO4 | 3568 | C | USCSB2402083A |  | Tunnel Thermal Expansion 2.7.24 | 45330 | 45336 | 12590 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 12590 | 128830.25 | -116240.25 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1888.5 |  |  |  | 1888.5 |  |  |  | 1888.5 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3569 | C | USCSB2402084A |  | KCUVA3 AC Cover Modificatons | 45339 | 45343 | 836.85 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 836.85 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 836.85 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | MMI | USC21C011 | F21 TMAH System | 3570 | C | USCSB2402085A |  | Tmah ACF expansion Rack for MMI. | 45330 | 45336 | 59283 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 49048 | 0.82735 | 10235 | 0 | 10235 | 8338.16 | [49 empty] | 0 |  |  | 0 | 0 | 3950 |  | 0 |  | 34863 |  |  |  | 10235 | [8 empty] | 2452.4 |  | - | 2452.4 | - | 3433.36 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3571 | C | USCSB2402086A |  | CDS HPM Punch materials | 45331 | 45341 | 13068.24 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 13068.24 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 13068.24 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3572 | C | USCSB2402087A |  | CDS HPM Punch materials | 45331 | 45337 | 8108.79 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 8108.79 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 8108.79 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3573 | C | USCSB2402088A |  | HOS90190 "KLAM" hose25' X 1-1/2" w/ male & female ends, for gas 300 tools, tool hookup team | 45331 | 45357 | 19311 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 19311 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 19311 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C029 | EBO21- Tool interconnection | 3574 | C | USCSB2402089A |  | EBO: ZASC5-1: TUBE WELDING & 4% H2/He INSTALL | 45331 | 45335 | 7683 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 7683 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 7683 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3575 | C | USCSB2402091A |  | WWT Hardware for A side punches | 45331 | 45335 | 3892.26 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3892.26 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 3597.9 | 192.8 | 101.56 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3576 | C | USCSB2402092A |  | Nilfisk GM-80 CR Vacuum 10 - Industrial with ULPA (01790150), for Gas 300 tools, tool hook up team | 45331 | 45337 | 14604.4 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 14604.4 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 14604.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3577 | C | USCSB2402093A |  | WWT SUS Pipes_20240208 (A Side) | 45331 | 45335 | 245.76 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 245.76 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  | 245.76 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3578 | C | USCSB2402094A |  | psi high pressure regulators ang N2 cylinder, Tool hook up for gas 300 tools | 45332 | 45332 | 2663.15 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1190.33 | 0.44696 | 1472.82 | 0 | 1472.82 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 1190.33 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3579 | C | USCSB2402095A |  | CDS HPM Punch materials | 45332 | 45337 | 1579.7 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1579.7 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 1579.7 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3580 | C | USCSB2402096A |  | DI polycell wipes, shared for all systems, Tool hookup team | 45332 | 45336 | 14912.29 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 6924.45 | 0.46435 | 7987.84 | 0 | 7987.84 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 6924.45 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3581 | C | USCSB2402097A |  | Lug for HK power trade | 45332 | 45335 | 1120 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 714 | 0.6375 | 406 | 0 | 406 | 0 | 714 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 3582 | C | USCSB2402098A |  | Lit 3: KPAN01-T: Grounding Box and Wiring Installation | 2/10/2024 8/28/2024 | 2/22/2024 8/29/2024 | 0 | -3850 | 3850 |  |  |  |  | Advanced Technical Solutions, LLC | PR Approved | PO Approved | R1: Advanced Technical Solutions did not do the work |  | Yikang Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3583 | C | USCSB2402099A |  | Chemical Team Material | 45332 | 45347 | 491.37 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 446.7 | 0.90909 | 44.67 | 0 | 44.67 | 0 | 446.7 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 3584 | C | USCSB2402100A |  | Lit 3: KPAP01-T: Grounding Box and Wiring Installation | 2/10/2024 8/28/2024 | 2/22/2024 8/29/204 | 0 | -3850 | 3850 |  |  |  |  | Advanced Technical Solutions, LLC | PR Approved | PO Approved | R1: Advanced Technical Solutions did not do the work |  | Yikang Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 3585 | C | USCSB2402101A |  | TMAH MS/HS receptacle | 45332 | 45335 | 54.52 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 54.52 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 54.52 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3586 | C | USCSB2402102A |  | Plastic第五批短期採購_(MICU_T&M), tool hookup team for tsmc | 45332 | 45337 | 11053.44 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 11053.44 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 841.44 | 5045.28 |  | 5166.72 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3587 | C | USCSB2402103A |  | Plastic第五批短期採購, Tool hookup team for tsmc | 45332 | 45337 | 13851 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 13851 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 13851 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3588 | C | USCSB2402105A | -01 | 第五批短期採購需求, tool hookup for tsmc plastic system | 2024/2/10 2024/3/2 2024/7/31 | 2024/2/15 2024/3/2 2024/8/1 | 6270.32 | 496.54 | 5773.78 | V |  |  |  | WW Grainger Inc | PR Approved | PO Approved | R1: Change Delivery Method to Self Pickup per requested R2: Per purchasing team request, this should change to the correct amount. R3: Adding Tax |  | Yikang Wang | [11 empty] | 5697.64 | 0.90867 | 572.68 | 0 | 572.68 | 0 | 5697.64 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3589 | C | USCSB2402106A |  | Vacuum Hose,10 ft. L,Hose 1-1/2" Dia | 45332 | 45335 | 881.69 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 881.69 | 1 | 0 | 0 | 0 | 0 | 881.69 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | UMEC | USC21C006 | F21P1 Slurry package | 3590 | C | USCSB2402107A |  | CDS TSMC 8-181 CUSO4, COSO4, H3PO4 | 45332 | 45344 | 150625 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 150625 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 97906 | 45188 | 0 |  | 7531 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3591 | C | USCSB2402108A |  | lock, chain, and hammer, tool hook up team shared for all systems' | 45333 | 45342 | 1473.34 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1473.34 | 1 | 0 | 0 | 0 | 0 | 1473.34 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3592 | C | USCSB2402110A |  | Chan and Cutter, shared for all system 300 tools | 45333 | 45335 | 571.86 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 518.81 | 0.90723 | 53.05 | 0 | 53.05 | 0 | 518.81 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3593 | C | USCSB2402111A |  | Liquid argon shared by all HK system | 45334 | 45337 | 52138 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 52138 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  | 21445.48 | 0 | 0 | 19170.97 |  | 7025.22 |  |  |  | 3995.84 |  | 500.49 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3594 | C | USCSB2402112A |  | CDS Materials for CRG | 45335 | 45335 | 31582.96 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 19413.05 | 0.61467 | 12169.91 | 0 | 12169.91 | 0 | [49 empty] | 0 |  |  | 0 | 14843.05 | 4570 |  | 0 |  |  |  |  | 12169.91 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 3595 | C | USCSB2402113A |  | EBO: ZMERIT: FEMALE CONNECTORS | 45335 | 45335 | 86.56 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 86.56 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 86.56 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3596 | C | USCSB2402114A |  | CDS caps and gaskets | 45335 | 45335 | 4698.9 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 4698.9 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 4698.9 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC23C054 | UPW Change Order | 3597 | C | USCSB2402115A |  | PCO 79 Price Adjustment for Incentive Weekend OT and Swing Shift | 45335 | 45345 | 1282154.51 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 988872.66 | 0.77126 | 293281.85 | 3036 | 290245.85 | 64107.73 | [49 empty] | 0 |  |  | 0 | 0 | 0 | 178460.28 | 178460.28 |  |  |  |  | 333360.17 | 230846.38 |  |  | 384646.35 | 439885.42 |  |  | 256430.9 | 124643.59 | 64107.73 |  | 15036.99 | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 3598 | C | USCSB2402116A |  | AMHS F21 Side B 8 Additional DP Installation | 45335 | 45338 | 45728.4 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 45728.4 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 45728.4 | [8 empty] | - | 0 | - | 0 | 0
Base-Build | TMAH | Labor | USC21C011 | F21 TMAH System | 3599 | C | USCSB2402117A |  | 2000 Gold T&M-Labor 30days 10ppl | 45335 | 45337 | 300000 | [6 empty] | 2000 GOLD LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 29850 | 0.0995 | 270150 | 0 | 270150 | 26865 | [49 empty] | 0 |  |  | 0 | 18350 | 0 |  | 0 | [5 empty] | 11500 | [8 empty] | 14925 |  | - | 11940 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3600 | C | USCSB2402118A |  | office supplies for tool hookup department | 45335 | 45337 | 187.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 183.14 | 0.97675 | 4.36 | 0 | 4.36 | 0 | 183.14 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 3601 | C | USCSB2402119A |  | Urgent Lorry Tank Repair | 45335 | 45336 | 2965 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 2965 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 2965 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3602 | C | USCSB2402120A |  | Tools for chemical team | 45335 | 45336 | 406.87 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 326.15 | 0.80161 | 80.72 | 0 | 80.72 | 0 | 326.15 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3603 | C | USCSB2402122A |  | stackable bins, broom and dust pan combo for HK Exhaust. Cleanroom tapes shared by all HK system | 45336 | 45336 | 1794 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1794 | 1 | 0 | 0 | 0 | 0 | 1794 | [48 empty] | 0 |  |  | 0 | 0 | 0 | [16 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3604 | C | USCSB2402123A |  | WWT - T&M Proposal to Work Stainless Line in LB2 | 45336 | 45337 | 46091 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 46091 | 0 | 46091 | 46091 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 6913.65 |  |  |  | 6913.65 |  |  |  | 6913.65 |  | 11522.75 |  | - | 11522.75 | 43786.45 | 11522.75 | 11522.75 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3605 | C | USCSB2402124A | -01 | Sulfate Analyser SO4 reagents | 45336 | 2024/2/15 2024/02/26 2024/3/1 | 568.54 | 16 | 552.54 | V |  |  |  | Hach Company | PR Approved | PO Approved | R1: Change payment method to credit card R2: Adding Shippment Fee |  | Ta Wei Wang | [11 empty] | 568.54 | 1 | 0 | 31125.38 | -31125.38 | 0 | 568.54 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 3606 | C | USCSB2402125A |  | Hex Head Bolt for AMAT Change Order completion | 45336 | 45342 | 15.98 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 15.98 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 15.98 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 3607 | C | USCSB2402126A |  | AMHS M165/M187 Additional Module Installation | 45336 | 45337 | 453323.83 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 350283.33 | 0.7727 | 103040.5 | 0 | 103040.5 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 350283.33 | [6 empty] | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3608 | C | USCSB2402127A |  | Cabinet door in TM room | 45336 | 45337 | 152.72 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 152.72 | 0 | 152.72 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 22.908 |  |  |  | 22.908 |  |  |  | 22.908 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3609 | C | USCSB2402128A |  | FIQ Sensor Cable x2 for FIQCWS9034 | 45336 | 45337 | 404.04 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 404.04 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 404.04 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3610 | C | USCSB2402129A |  | CDS plastic clamp | 45336 | 45337 | 296 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 296 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 296 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3611 | C | USCSB2402130A |  | WWT 7 Chemical - 1 | 45336 | 45379 | 3246.65 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3111.84 | 0.95848 | 134.81 | 0 | 134.81 | 124.4736 | [52 empty] | 0 | 0 | 0 |  | 528.67 |  |  |  | 2583.17 | 486.9975 |  |  |  | 486.9975 |  |  |  | 486.9975 |  | 0 |  | - | 0 | - | 0 | 0 | 124.4736
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3612 | C | USCSB2402131A |  | CDS Pipes and fittings, etc | 45336 | 2024/2/19 2024/3/7 | 15421.2 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 15421.2 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 14193.68 | 1227.52 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3613 | C | USCSB2402132A |  | CDS flare nut 1-1/4 | 45336 | 45337 | 437.7 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 437.7 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 437.7 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 3614 | C | USCSB2402133A |  | CDS L20 Monitoring piping and cable engineering | 45336 | 45352 | 1610000 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1529500 | 0.95 | 80500 | 0 | 80500 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 1288000 | 1449000 | 241500 |  |  | 80500 |  |  |  | 80500 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3615 | C | USCSB2402135A |  | WWT UMEC copper tubing to instrument | 45337 | 45338 | 3709 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3709 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 3524 | 0 | 0 |  | 185 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3616 | C | USCSB2402136A |  | WWT FRP coating in WRC&FAB | 45337 | 45344 | 73038 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 73038 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 73038 |  |  |  |  | 10955.7 |  |  |  | 10955.7 |  |  |  | 10955.7 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | AMC THC | NUUO | USC21C013 | F21P1 AMC THC Monitoring System | 3617 | C | USCSB2402137A |  | F21 EBO AMC Engineering | 45337 | 45370 | 194291 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 162451.45 | 0.83612 | 31839.55 | 0 | 31839.55 | 27200.74 | [52 empty] | 0 | 0 | 0 |  | 42884.6 |  | 47789.35 |  |  |  | 39207.5 |  |  | 77717 | 27845 |  |  | 48573 | 4725 | 27200.74 |  | - | 0 | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3618 | C | USCSB2402139A |  | Office supplies for HK PPEP team | 45337 | 45342 | 237.6 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 211.21 | 0.88893 | 26.39 | 0 | 26.39 | 0 | 211.21 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3619 | C | USCSB2402142A |  | ETC Brady M210 Handheld label maker | 45337 | 45350 | 111.54 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 101.4 | 0.90909 | 10.14 | 0 | 10.14 | 0 | 101.4 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C006 | F21P1 Slurry package | 3620 | C | USCSB2402143A |  | CDS HongDong recent construction work by 02/06/24 | 45337 | 45349 | 54626.4 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 54626.4 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 54626.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3621 | C | USCSB2402144A |  | MMI Tile alignment RMF bolts. T&M Hardware for Hank | 45337 | 45350 | 35190 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 35190 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 35190 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3622 | C | USCSB2402145A |  | Banner Industries Durabiti Tube Squaring .75 tall for 301 & 302 | 45337 | 45337 | 560 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 560 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 560 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3623 | C | USCSB2402146A |  | WWT PTFE coating bolt | 2024/2/15 2024/2/21 2024/3/13 | 45369 | 22575.43 | [6 empty] | LIGHTNING BOLT & SUPPLY, INC. | PR Approved | PO Approved | PR R2:As per purchasing team Oneil to revise the freight. PR R1:Revise PR amount after confirmation of shipping charge |  | Kuan-Chung Su | [11 empty] | 22575.43 | 1 | 0 | 0 | 0 | 0 | 22575.43 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3624 | C | USCSB2402147A |  | contractor bags for HK Exhaust team | 2/15/2024 8/8/2024 | 2/20/2024 8/31/2024 | 2245.95 | 175.95 | 2070 | V |  |  |  | U-Line Corporation | PR Approved | PO Approved | R1: Match the actual payment for credit card reconciliation |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2245.95 | 1 | 0 | 0 | 0 | 0 | 2245.95 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3625 | C | USCSB2402148A |  | CDS Sealing Compound Powder, Qty 2 | 45337 | 45337 | 89.62 | [6 empty] | Walmart Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 0 | 0 | 89.62 | 0 | 89.62 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C012 | F21 Barcode RFID System | 3626 | C | USCSB2402149A |  | UPW-UMEC-LB2 A.5/L10 Q.5 Design change | 45337 | 45344 | 94329 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 86577 | 0.91782 | 7752 | 0 | 7752 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 86577 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3627 | C | USCSB2402150A |  | WWT 7 Chemical - 2 | 45337 | 2024/3/5 2024/7/29 | 1510.55 | 387.85 | 1122.7 |  |  |  |  | Midland Scientific, Inc. | PR Approved | PO Approved | R1: Add Freight fee per purchasing team Yikang. |  | Ta Wei Wang | [11 empty] | 1510.55 | 1 | 0 | 0 | 0 | 291.902 | 1510.55 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 291.902 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 3628 | C | USCSB2402151A |  | CDS DHL Platform Extensions | 45337 | 45341 | 12418 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 12418 | 1 | 0 | 0 | 0 | 620.9 | [49 empty] | 0 |  |  | 0 | 0 | 11797.1 |  | 0 | [5 empty] | 620.9 | [8 empty] | 0 |  | - | 0 | - | 0 | 620.9
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3629 | C | USCSB2402152A |  | Nut order for Luis | 45338 | 45338 | 1444 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1444 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 1444 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 3630 | C | USCSB2402153A |  | Torque Wrench, Torque Wrench Set, Tamperproof tape | 45338 | 45342 | 1324.55 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1324.55 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 1324.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3631 | C | USCSB2402154A |  | Electric Scissor Lift skyjack/Packaging & Crating unit/Palletizing tire cover for Skyjack 3219/new sales tax | 2024/2/16 2024/3/21 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Purchasing used orginal PR submitted |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3632 | C | USCSB2402156A |  | office supplies for tool hookup department | 45338 | 45342 | 1478 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1383.33 | 0.93595 | 94.67 | 0 | 94.67 | 0 | 1383.33 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3633 | C | USCSB2402157A |  | Quality Material | 45338 | 45339 | 1035.06 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 963.11 | 0.93049 | 71.95 | 0 | 71.95 | 0 | 963.11 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1035.06 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3634 | C | USCSB2402158A |  | E-OPS Staffing Pricing Worksheet QA Renewal 3/6 months | 45338 | 45343 | 279900.97 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 23346 | 0.083408 | 256554.97 | 0 | 256554.97 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 6552 | 16794 | 0 | 6883.5 | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 3635 | C | USCSB2402159A | -01 | CDS Pressure tests | 45338 | 2/27/2024 3/28/2024 | 6204.96 | -11424.12 | 17629.08 |  |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: Removed Items Per Request |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 6204.96 | 0 | 6204.96 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 6204.96 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3636 | C | USCSB2402160A |  | TCBC105 刀刃 | 45338 | 45342 | 4545 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4545 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 4545 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 3637 | C | USCSB2402161A |  | CED WIRE, KKSS03 Metrology | 45338 | 45342 | 205.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 205.5 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 205.5 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3638 | C | USCSB2402162A |  | Polyethylene Tubing Coil for HK Exhaust | 45339 | 45343 | 1069.28 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 1069.28 | 0 | 1069.28 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3639 | C | USCSB2402163A |  | DRY ETC3: KETRTC, KETRT6, KETRT9: AC CONNECTORS | 45339 | 45343 | 433.65 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 433.65 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 433.65 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 3640 | C | USCSB2402165A |  | SDS HPM L20 H2O2&KOH VMB Control | 45339 | 45344 | 58500 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 35100 | 0.6 | 23400 | 0 | 23400 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 35100 |  |  | 35100 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC23C014 | F21P1 Labor incentive program-MICU | 3641 | C | USCSB2402166A |  | Laydown Material - U Line | 45339 | 45359 | 583.22 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 530.2 | 0.90909 | 53.02 | 0 | 53.02 | 0 | 530.2 | [51 empty] | 0 | 0 | 0 | [16 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3642 | C | USCSB2402167A | -01 | RMF hole penetration repairs | 45339 | 45370 | 17594.31 | -2168.57 | 19762.88 |  |  |  |  | Greenberry Industrial | PR Approved | PO Approved | R1:Lower manhour negotiated |  | Tiong Sheng Poh | [11 empty] | 17594.31 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 17594.31 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Site Expense | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3643 | C | USCSB2402168A |  | ASME IX P8 WPS and Welder Qualification | 45339 | 45374 | 6254 | [6 empty] | Phoenix National Laboratories, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 3330 | 0.53246 | 2924 | 0 | 2924 | 266.4 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 938.1 |  |  |  | 938.1 | 3330 |  |  | 938.1 |  | 0 |  | - | 0 | - | 0 | 0 | 266.4
Base-Build | Chemical | Equipment | USC21C006 | F21P1 Slurry package | 3644 | C | USCSB2402170A |  | CDS Divider_HPM_MIC_EA001_24_AZ03 | 45339 | 45367 | 11057.3 | [6 empty] | JY TECHS INC. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 11057.3 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 11057.3 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3645 | C | USCSB2402171A |  | Milwaukee Fleece Dust Bags (3-Pack), Nashua Tape, Chain, tool hookup team | 45339 | 45351 | 498.73 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 438.88 | 0.88 | 59.85 | 0 | 59.85 | 0 | 438.88 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3646 | C | USCSB2402172A |  | CDS HPM Punch materials etc | 45339 | 45344 | 3200.49 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 3199.13 | 0.99958 | 1.36 | 0 | 1.36 | 0 | [52 empty] | 0 | 0 | 3199.13 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3647 | C | USCSB2402174A |  | Crimper Kit for HK Power trade | 45340 | 45342 | 3900 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3549 | 0.91 | 351 | 0 | 351 | 0 | 3549 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3648 | C | USCSB2402175A | -01 | label, cabinet and magnet, tool hookup team | 2/20/2024 2/29/2024 8/22/2024 | 2/22/2024 3/1/2024 8/28/2024 | 764.2 | -206.21 | 970.41 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: change the quantity as request R2: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 764.2 | 1 | 0 | 0 | 0 | 0 | 764.2 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3649 | C | USCSB2402176A |  | LATERAL FILE CABINET - 36" WIDE, 4 DRAWER, WHITE, cabinet dolly, tool hook up | 45342 | 45343 | 1055.59 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 972 | 0.92081 | 83.59 | 0 | 83.59 | 0 | [52 empty] | 972 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3650 | C | USCSB2402177A |  | Multi-Tap Connector; 10-250 AWG-kcmil; 2-Port; 600 VAC; 3/16 In.for HK Power trade | 45342 | 45343 | 204.7 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 204.7 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 204.7 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3651 | C | USCSB2402178A | -01 | MILWAUKEE Drill for HK Power trade | 45342 | 2/21/2024 2/23/2024 | 728 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | R1: Change Delivery Method to Self Pickup per requested |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 728 | 1 | 0 | 1187018.48 | -1187018.48 | 0 | 728 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3652 | C | USCSB2402179A |  | M18 18V Lithium-Ion Cordless Force Logic 600 MCM Crimper Kit with 600 MCM Copper U-Style Die Kit for HK Power trade | 45342 | 45343 | 7808 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7098 | 0.90907 | 710 | 0 | 710 | 0 | 7098 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | Heating Jacket | Labor | USC23C035 | TSMC F21 Heating Jacket Installation | 3653 | C | USCSB2402180A |  | Kinpo heating jacket project | 45342 | 45350 | 2764724.26 | [6 empty] | Kinpo Co. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1351789.01 | 0.48894 | 1412935.25 | 0 | 1412935.25 | 0 | [52 empty] | 0 | 414708.64 | 0 |  | 0 | [7 empty] | 449793.95 |  | 487286.42 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3654 | C | USCSB2402181A |  | HK Power team tool request | 45342 | 45342 | 3955 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3955 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 3955 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 3655 | C | USCSB2402182A |  | UPW Continuation of Work Phase 1 | 45343 | 45346 | 717845.48 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 717845.48 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | 717845.48 | 717845.48 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3656 | C | USCSB2402183A |  | EUV Crane Project Code Materials | 45342 | 45343 | 806.91 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 806.91 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 353.76 |  | 0 | [9 empty] | 453.15 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3657 | C | USCSB2402184A |  | For PCW and all system, tool hookup team | 45343 | 45343 | 12510.99 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 12510.99 | 1 | 0 | 0 | 0 | 0 | 12510.99 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 3658 | C | USCSB2402185A |  | CDS Welder rental for Chemical welding. | 45343 | 45344 | 650 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 650 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3659 | C | USCSB2402186A |  | CDS Monstair low b2b pc strut | 45343 | 45344 | 932.84 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 932.84 | 0 | 932.84 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 932.84 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 3660 | C | USCSB2402187A |  | CDS Welder rental for Chemical welding.(RENTAL FROM 11-7-23 TO 12-5-23) | 45343 | 45344 | 650 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 650 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3661 | C | USCSB2402188A |  | For gas system stores coupon in L40, tool hookup team | 45343 | 45343 | 1060 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1060 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 1060 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3662 | C | USCSB2402189A |  | CDS coax tube | 45343 | 45344 | 652 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 652 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 652 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC21C005 | F21P1 Chemical & WCCS package | 3663 | C | USCSB2402190A |  | CDS T&M work Jan 2024 | 45343 | 45371 | 1103574.8 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1103574.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 1103574.8 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3664 | C | USCSB2402191A | -01 | (2) Steel Storage cabinets 72" with adjusteable drawers for storing Respitory Equipment and PPE. | 45343 | 2024/2/28 2024/3/22 | 457.11 | 31.41 | 425.7 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: PR amount change to add shipping |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 457.11 | 1 | 0 | 0 | 0 | 0 | 457.11 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3665 | C | USCSB2402193A |  | CDS 1" 90 elbow | 45343 | 45344 | 149.94 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 149.94 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 149.94 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3666 | C | USCSB2402195A |  | CDS CRG Lorry punch | 45343 | 45348 | 13776.86 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 13776.76 | 0.99999 | 0.1 | 0 | 0.1 | 0 | [52 empty] | 0 | 0 | 13776.76 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C010 | tsmc AZ sewer and water pipeline installation | 3667 | C | USCSB2402196A |  | Laydown, Bins & Rack to organize bolts & elbows | 45343 | 45351 | 652.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 592.98 | 0.90906 | 59.32 | 0 | 59.32 | 0 | 592.98 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3668 | C | USCSB2402197A |  | CDS 5/8 Screw sets | 45343 | 45344 | 405 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | B | [7 empty] | 405 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 405 | 405 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3669 | C | USCSB2402198A |  | CDS 1" SS EP tube | 45343 | 45345 | 562 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 562 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 562 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3670 | C | USCSB2402199A |  | general labor for RS Payroll services | 45343 | 45349 | 3600 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 3600 | 0 | 3600 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3671 | C | USCSB2402200A |  | Crimper Kit for HK Power trade | 45343 | 45348 | 10647 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10647 | 1 | 0 | 0 | 0 | 0 | 10647 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3672 | C | USCSB2402201A |  | Stripper packing procurement | 45343 | 45348 | 12365 | [6 empty] | LANTEC PRODUCTS INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 12365 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 12365 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3673 | C | USCSB2402202A | -01 | CDS Air Valves | 45343 | 2024/3/11 2024/4/1 | 10135 |  |  |  | V |  |  | Marketech International Corp. | PR Approved | PO Approved | R1: Combine the item one&two into 'PFA裡襯球閥150#RF(PB12) +單動常關氣缸:2 |  | Ta Wei Wang | [11 empty] | 10135 | 1 | 0 | 0 | 0 | 10135 | [52 empty] | 0 | 0 | 0 |  | 0 | [13 empty] | 10135 | 0 |  | - | 0 | - | 0 | 10135
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3674 | C | USCSB2402203A |  | NUUO Labor | 45343 | 45356 | 656250 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 656250 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 310312.5 |  | 345937.5 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3675 | C | USCSB2402204A |  | NUUO Change Order: add terminations | 45343 | 45370 | 315000 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 315000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 315000 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3676 | C | USCSB2402205A |  | Hot Ground Wire | 45343 | 45350 | 1879.74 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1879.74 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1879.74 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3677 | C | USCSB2402206A | -01 | E-OPS Installers for 3 Months | 2024/2/21 2024/4/18 | 2024/2/28 2024/4/26 | 0 | -189281.69 | 189281.69 |  |  |  |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | R1: Canceled order |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3678 | C | USCSB2402207A |  | Manlift skates and jack for James M. shared by all HK system | 45344 | 45343 | 1097.66 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 997.86 | 0.90908 | 99.8 | 0 | 99.8 | 0 | 997.86 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3679 | C | USCSB2402208A |  | WWT: Fabricate and Install T-1985 Ladder | 45344 | 45348 | 9588 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9588 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1438.2 | 9588 |  |  | 1438.2 |  |  |  | 1438.2 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Rosendin | USC21C005 | F21P1 Chemical & WCCS package | 3680 | C | USCSB2402209A |  | CDS REI CO 70/CO 73/CO 79/CO 86 | 45344 | 45353 | 1249493.14 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 62474.66 | 0.05 | 1187018.48 | 0 | 1187018.48 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 62474.66 | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3681 | C | USCSB2402210A |  | CDS Monstair cleanroom hardware needs | 45344 | 45351 | 5424.32 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5424.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 5424.32 | 5424.32 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3682 | C | USCSB2402211A |  | Cable tie for HK CYH PCW | 45344 | 45348 | 424.18 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 424.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 424.18 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3683 | C | USCSB2402212A |  | CDS 20amp breakers | 45344 | 45344 | 1088.6 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1088.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1088.6 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3684 | C | USCSB2402213A |  | CDS SMC pressure gauges | 45344 | 45344 | 111 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 111 | 0 | 111 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 111 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | NUUO | USC21C005 | F21P1 Chemical & WCCS package | 3685 | C | USCSB2402214A |  | CDS Fire Barrier Sealant materials | 45344 | 45344 | 4864.6 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4864.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 4864.6 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3686 | C | USCSB2402215A |  | CDS 5/8 Hex nut, EG | 45344 | 45344 | 17.82 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 17.82 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 17.82 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3687 | C | USCSB2402216A |  | CDS electrial materials | 2024/2/22 2024/2/27 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:As per Purchasing team, replaced by other order. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3688 | C | USCSB2402217A | -01 | WWT LSR SUS material | 2024/2/22 2024/3/1 | 2024/2/24 2024/3/9 | 0 | -4915.2 | 4915.2 |  |  |  |  | Ferguson Enterprises, LLC | PR Approved | PO Approved | Incorrect order placed |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3689 | C | USCSB2402218A |  | RS PAYROLL SERVICES, TIMECARD PAYMENT FOR ASSOCIATES | 2/22/2024 10/4/2024 | 2/26/2024 10/11/2024 | 9384.53 | -9518.37 | 18902.9 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 9384.53 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 9384.53 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | UMEC | USC21C005 | F21P1 Chemical & WCCS package | 3690 | C | USCSB2402219A |  | CDS TSMC 8-188 M1 Poly 700 | 45344 | 45353 | 57820 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 54929 | 0.95 | 2891 | 0 | 2891 | 2891 | [52 empty] | 0 | 54929 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 2891
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3691 | C | USCSB2402220A | -01 | WWT LSR Small SUS material | 2024/2/22 2024/3/5 | 2024/2/27 2024/3/5 | 0 | -25804 | 25804 |  |  |  |  | Ferguson Enterprises, LLC | PR Approved | PO Approved | R1: As per engineer Cindy Fan to cancel the order and will issue another order in lieu. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 3692 | C | USCSB2402221A |  | TMAH Customized Clear PVC Cover | 45344 | 45344 | 2625 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2625 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2625 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3693 | C | USCSB2402222A |  | WWT Stripper insulation | 45344 | 45351 | 1096382.54 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1096382.54 | 1 | 0 | 0 | 0 | 265365.3384 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 164457.381 | 449771.76 |  |  | 164457.381 |  |  |  | 164457.381 | 646610.78 | 53972.6112 |  | - | 53972.6112 | - | 53972.6112 | 53972.6112 | 49474.8936
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3694 | C | USCSB2402223A |  | Hard Hat Chin Strap with Black Elastic Strap and Chin Cup shared by all hookup system | 45344 | 45348 | 2308.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2056.5 | 0.89084 | 252 | 0 | 252 | 0 | 2056.5 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3695 | C | USCSB2402224A | -01 | WWT E2 missing material 202402 | 45345 | 2024/2/26 2024/2/29 | 15633.2 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Trade Term Changes from DDP to FOB |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 15633.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2158.54 |  | 10274.66 |  | 3200 |  |  | 2344.98 |  |  |  | 2344.98 |  |  |  | 2344.98 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3696 | C | USCSB2402225A |  | WWT E2 missing SUS material | 45345 | 45345 | 348.9 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 348.9 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 348.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3697 | C | USCSB2402226A |  | CDS Cush Clamps | 45345 | 45349 | 25628.6 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 25626.6 | 0.99992 | 2 | 0 | 2 | 0 | [52 empty] | 0 | 0 | 24162.06 |  | 0 |  | 1312.74 |  |  | 154.54 | 93.61 |  |  |  | 58.19 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 3698 | C | USCSB2402227A |  | CDS Welder rental for Chemical welding(RENTAL FROM 1-4-24 TO 2-1-24) | 45345 | 45351 | 650 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 650 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 3699 | C | USCSB2402228A |  | UPW-ORGANO-L10 Q-6.5 Line Design Mod | 45345 | 45349 | 6000 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 6000 | 0 | 6000 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3700 | C | USCSB2402229A | -01 | Portable Handheld VOC Monitor | 45345 | 3/11/2024 3/14/2024 | 36968.83 | [6 empty] | FASTENAL COMPANY | PR Approved | PO Approved | R1: Correct Payment Term |  | Yikang Wang | [11 empty] | 36968.83 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 18478 | 0 | 0 | 0 |  | 0 |  | 18490.83 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC22C009 | F21P1 230kV MTR Oil and Drain Pipe work | 3701 | C | USCSB2402230A |  | UPW-UMEC-COs for ORGANO180, 183 and 186 | 45346 | 45351 | 13236 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12574 | 0.94998 | 662 | 0 | 662 | 0 | [52 empty] | 0 | 11912 | 0 |  | 662 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Labor | USC21C011 | F21 TMAH System | 3702 | C | USCSB2402231A |  | install house keeping pads and Dike wall in Fab LB2/WRC | 45346 | 45350 | 42875 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 41560 | 0.96933 | 1315 | 0 | 1315 | 3158.56 | [52 empty] | 0 | 0 | 39482 |  | 0 | [13 empty] | 2078 | 0 |  | - | 0 | - | 0 | 0 | 3158.56
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3703 | C | USCSB2402233A |  | ELECTRICAL QA (Foreman Level) Proposal (Contract Staffing) | 45346 | 45358 | 107241.75 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 107241.75 | 0 | 107241.75 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3704 | C | USCSB2402234A |  | CDS electrical materials | 45346 | 45350 | 5599.62 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5599.62 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 5599.62 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3705 | C | USCSB2402235A |  | DRY ETC 1,2 AND 3 Hex Washer Drill Point Screw | 45346 | 45350 | 26.79 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 23.93 | 0.89324 | 2.86 | 0 | 2.86 | 0 | 23.93 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3706 | C | USCSB2402236A |  | RS PAYROLL SERVICES, TIMECARD PAYMENT FOR ASSOCIATES | 45346 | 45349 | 284 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 284 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 284 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3707 | C | USCSB2402237A |  | CDS 2" Pipe cush clamps | 45346 | 45349 | 2244 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 44.88 | 0.02 | 2199.12 | 0 | 2199.12 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 44.88 | 2244 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 3708 | C | USCSB2402238A |  | UPW-Harrington-U bolts and tank gaskets | 45346 | 45349 | 597.4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 597.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 597.4 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3709 | C | USCSB2402239A |  | CDS Ring Terminals | 45346 | 45349 | 146.67 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 121.67 | 0.82955 | 25 | 0 | 25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 121.67 |  |  | 24.93 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3710 | C | USCSB2402240A |  | WWT Gasket_20240223 (A Side) | 45346 | 45350 | 1455.6 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1455.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1455.6 |  | 0 |  |  |  |  | 218.34 |  |  |  | 218.34 |  |  |  | 218.34 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | Labor | USC21C008 | F21P1 CCTV & Security | 3711 | C | USCSB2402241A |  | F21 CCTV Engineering (T&M) | 45346 | 45352 | 62593.07 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 62593.07 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 62593.07 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3712 | C | USCSB2402242A |  | cable tray | 45346 | 45370 | 1349.61 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1349.61 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1349.61 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3713 | C | USCSB2402243A |  | M10(1.5) X 12 HEX SC 18-8 SS, T&M project, tool hookup team | 45347 | 45350 | 5625 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5625 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 5625 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3714 | C | USCSB2402244A |  | Clear PVC Y-Strainers with PP Filter(20mesh), tool hookup team | 45347 | 45350 | 8213.4 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8213.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 8213.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3715 | C | USCSB2402245A |  | WWT Narrow flat washer_20240223 (A Side) | 45347 | 45349 | 1016.21 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1016.21 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1016.21 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3716 | C | USCSB2402246A |  | SS stem and nut for CGA 580, TOOL HOOKUP TEAM | 45347 | 45350 | 338.96 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 338.96 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 338.96 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3717 | C | USCSB2402247A |  | WWT Hardware_20240223 (A Side) | 45347 | 45349 | 2042.83 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2042.83 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1447.42 | 0 |  | 0 |  |  |  | 595.41 |  |  |  |  | 102.1415 |  |  |  | 102.1415 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3718 | C | USCSB2402248A |  | Fiberglass Routing S-Hook for 2-3/4" Maximum Bundle Diameter, Yellow, Tool hookup | 45347 | 45349 | 5838.06 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 5384.67 | 0.92234 | 453.39 | 0 | 453.39 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 5384.67 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3719 | C | USCSB2402249A |  | Shared for all system, tool hookup team | 45347 | 45349 | 3073.39 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2244.4 | 0.73027 | 828.99 | 0 | 828.99 | 0 | 2244.4 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3720 | C | USCSB2402250A |  | CDS sealing materials | 45349 | 45348 | 1987.68 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1987.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1987.68 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3721 | C | USCSB2402251A |  | HK Electrical PM Luis Retiz's material request | 45349 | 45353 | 1828.24 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 1828.24 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 648.76 |  | 1179.48 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3722 | C | USCSB2402252A |  | HK Electrical PM Luis Retiz's material request | 45349 | 45353 | 144 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 144 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 144 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3723 | C | USCSB2402253A |  | WWT line leak check T&M work | 45349 | 45356 | 178114 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 178114 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 178114 |  |  |  |  | 26717.1 |  |  |  | 26717.1 |  |  |  | 26717.1 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3724 | C | USCSB2402254A |  | WWT materials-1 | 45349 | 45350 | 1532 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 780 | 0.50914 | 752 | 0 | 752 | 1532 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 229.8 |  |  |  | 229.8 |  |  | 780 | 229.8 |  | 1532 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3725 | C | USCSB2402255A |  | WWT materials-2 | 45349 | 45350 | 9459 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9459 | 1 | 0 | 0 | 0 | 9459 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1418.85 |  |  |  | 1418.85 |  |  | 9459 | 1418.85 |  | 4729.5 |  | - | 4729.5 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3726 | C | USCSB2402256A |  | for UPW system 預置區, tool hookup team | 45349 |  | 8732.06 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 8096 | 0.92716 | 636.06 | 0 | 636.06 | 0 | [52 empty] | 8096 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Site Expense | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3727 | C | USCSB2402257A |  | Grainger Work Table | 45349 | 45350 | 579.06 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 579.06 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 579.06 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3728 | C | USCSB2402258A |  | Foxboro A1U Enclosure Sample | 45349 | 45352 | 144 | [6 empty] | Black Label Services Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 144 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 144 | [10 empty] | 144 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3729 | C | USCSB2402259A | -01 | CDS VCR parts etc | 45350 | 3/1/2024 3/5/2024 | 15490.8 | 1925 | 17415.8 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: Price Change per Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15490.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 12274.8 | 3216 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3730 | C | USCSB2402260A |  | Fork terminal for HK Power trade | 45350 | 45352 | 1350 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 1350 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3731 | C | USCSB2402261A |  | WWT Chemical Area Safety Paint(OPEN PR) | 45350 | 45352 | 50000 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 50000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 7500 | 50000 |  |  | 7500 |  |  |  | 7500 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3732 | C | USCSB2402262A |  | CDS strut and hardware | 45350 | 45351 | 4529.9 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 4529.9 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 4321.4 |  | 0 |  |  |  | 26.65 | 208.5 | 181.85 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3733 | C | USCSB2402264A | -01 | WWT Fitting_20240227 (A Side) | 45350 | 45351 | 10855.74 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Trade Term Changes from DDP to FOB |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 10855.74 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1811.38 | 1132.52 |  | 7911.84 |  |  |  |  | 542.787 |  |  |  | 1085.574 |  |  |  | 1628.36 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3734 | C | USCSB2402265A |  | Trailer related, tool hookup team | 45350 | 45351 | 710 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 613.41 | 0.86396 | 96.59 | 0 | 96.59 | 0 | 613.41 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3735 | C | USCSB2402266A | -01 | WWT Pipes_20240227 (A Side) | 45350 | 45350 | 11932.16 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Trade Term Changes from DDP to FOB |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 11932.16 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 10197.26 | 205.6 |  | 437.6 | [7 empty] | 1091.7 | 357.9648 |  |  |  | 596.608 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | UMEC | USC21C012 | F21 Barcode RFID System | 3736 | C | USCSB2402267A |  | UPW-UMEC-2023-Dec-extend GC-2 | 45350 | 45353 | 121128 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 115072 | 0.95 | 6056 | 0 | 6056 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 115072 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3737 | C | USCSB2402268A |  | UPW-UMEC-2023-Dec-extend GC-1 | 45350 | 45353 | 337815 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 320924 | 0.95 | 16891 | 0 | 16891 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 320924 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3738 | C | USCSB2402269A | -02 | Bags and cleanroom tapes for HK Exhaust and PCW | 2024/2/28 2024/3/1 3/26/2024 | 3/22/2024 3/27/2024 3/28/2024 | 2180.85 | 32.98 | 2147.87 |  |  |  |  | U-Line Corporation | PR Approved | PO Approved | PR R1:tax was not included R1: PR Amendment change tax R2: Change Tax Amount |  | Jen-Ping Tsai Yikang Wang | [11 empty] | 2180.85 | 1 | 0 | 0 | 0 | 0 | 2180.85 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3739 | C | USCSB2402270A |  | WWT - BMWC L15 Ceiling Work CO | 45350 | 45356 | 149419 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 121219.15 | 0.81127 | 28199.85 | 0 | 28199.85 | 23031.6385 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 121219.15 | 22412.85 |  |  |  | 22412.85 |  |  |  | 22412.85 |  | 6060.9575 |  | - | 6060.9575 | - | 6060.9575 | 4848.766 | 0
Hookup | Hookup | Equipment | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 3740 | C | USCSB2402271A | -01 | For Plastic system storage | 2/28/2024 4/2/2024 | 2/29/2024 4/6/2024 | 0 | -10909.18 | 10909.18 |  |  |  |  | U-Line Corporation | PR Approved | PO Approved | R1: per purchasing team request, change to new PR: USCSB2404003 |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3741 | C | USCSB2402272A |  | Davit Arms and Manway Covers | 45350 | 45350 | 10355 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10355 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 10355 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3742 | C | USCSB2402273A |  | Housekeeping and Equipment maintenance(Open PO) | 45351 | 45351 | 106000 | [6 empty] | SEMITEC LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 79539.38 | 0.75037 | 26460.62 | 0 | 26460.62 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6047.5 |  | 31624 |  | 34787.88 |  | 1180 |  | 2360 |  | 2360 |  | 1180 | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3743 | C | USCSB2402274A |  | WWT SUS Weld Pipes_20240227 (A Side) | 45351 |  | 2545.92 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2545.92 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 2545.92 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 3744 | C | USCSB2402275A | -01 | 2rd MMI ASML special barricade | 45351 | 2024/3/14 2024/4/17 | 20713 | -1260 | 21973 |  |  |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | PO R1: Supplier agreed to remove overtime |  | Kuan-Chung Su | [11 empty] | 20713 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 20713 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | MIMO/Rigging | USC21C011 | F21 TMAH System | 3745 | C | USCSB2402276A |  | Un install and re install steel for tank move in | 45351 | 45352 | 13050 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 12397.5 | 0.95 | 652.5 | 0 | 652.5 | 619.875 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 12397.5 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 619.875
Base-Build | UPW and Chemical | UMEC | USC21C005 | F21P1 Chemical & WCCS package | 3746 | C | USCSB2402278A |  | CDS UPW - 8-189 TMAH Interface Modification L10 | 45351 | 45351 | 15659 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 15659 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 14876 | 0 |  | 783 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3747 | C | USCSB2402279A |  | office supply, tool hookup team | 45351 | 45351 | 1073.32 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 994.51 | 0.92657 | 78.81 | 0 | 78.81 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 994.51 | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3748 | C | USCSB2402281A |  | CDS NZMB1-A25-NA breaker | 45351 | 45363 | 1163.64 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1163.64 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1163.64 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3749 | C | USCSB2402282A |  | office supplies for tool hookup department | 45351 | 45351 | 925.53 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 848.77 | 0.91706 | 76.76 | 0 | 76.76 | 0 | 848.77 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3750 | C | USCSB2402283A |  | Plate, box, and outlet for HK power trade | 45351 | 45352 | 6272 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6272 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3839.13 |  | 2432.87 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3751 | C | USCSB2402284A |  | Electrical tapes for HK Power Trade | 45351 | 45352 | 847.68 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 847.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 847.68 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3752 | C | USCSB2402285A |  | Change Order KEPOA1 | 45351 | 45352 | 490.83 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 490.83 | 0 | 490.83 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3753 | C | USCSB2403001A |  | Cable Gland Lokman 20 Pack PG9 Plastic Waterproof Adjustable 4-8mm Cable Glands Joints with Gasket, Black (PG9) for HK Power | 45352 | 45352 | 98.9 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 77 | 0.77856 | 21.9 | 0 | 21.9 | 0 | 77 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3754 | C | USCSB2403002A | -01 | WWT - Marquis CO 1 Media loading for for four hour delay and Specialty PPE to work in TMAH | 45352 | 2024/3/2 2024/3/4 | 6845.83 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved | R1: Changed Remark Contract Scope |  | Ta Wei Wang | [11 empty] | 6845.83 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 6845.83 |  | 0 |  |  |  |  | 1026.8745 |  |  |  | 1026.8745 |  |  |  | 1026.87 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3755 | C | USCSB2403003A |  | HK Electrical PM Conn and Bush INS | 45352 | 45352 | 85.3 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 85.29 | 0.99988 | 0.01 | 0 | 0.01 | 0 | [52 empty] | 0 | 0 | 0 |  | 85.29 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3756 | C | USCSB2403004A |  | WWT Center Ring_20240228 (A Side) | 45352 | 45352 | 3580 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3580 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3580 |  | 0 |  |  |  |  | 537 |  |  |  | 537 |  |  |  | 537 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3757 | C | USCSB2403005A |  | CDS 2" OD cush clamps EG | 45352 | 45356 | 1616.73 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1616.7 | 0.99998 | 0.03 | 0 | 0.03 | 0 | [52 empty] | 0 | 0 | 1616.7 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | EUV Overhead Crane | Material | USC24C002 | [RM]F21 EUV Crane service contract | 3758 | C | USCSB2403006A |  | Certex-Phoenix CX07-0130TT MlB4 EE2 93 93 X Four Leg Nylon bridle sling, SO116-FS20-Us 3/4 Stainless SPA Shackle US Made 6,00 | 45352 | 45357 | 860.5 | [6 empty] | Certex USA LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 860.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 860.5 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3759 | C | USCSB2403007A |  | CDS lcp ms CDA parts | 45352 | 45357 | 2750.08 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2750.08 | 1 | 0 | 24368.21 | -24368.21 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 2750.08 |  |  |  |  | 2750.08 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 3760 | C | USCSB2403008A |  | QR LABS: CHAD LABS: SS CUSHION CLAMPS | 45352 |  | 112.45 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 112.45 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 112.45 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3761 | C | USCSB2403009A |  | WWT LSR SUS material | 45352 | 45356 | 8506.8 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 8506.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 8506.8 |  | 0 |  |  |  |  | 1276.02 |  |  |  | 1276.02 |  |  |  | 1276.02 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3762 | C | USCSB2403010A |  | CDS Mini circuit breaker, QO, 15A, 2 pole, 240VAC, 22kA, bolt on mount | 45352 | 45363 | 515.84 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 515.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 515.84 |  |  |  |  | 515.84 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3763 | C | USCSB2403011A |  | UPW-Ebro valves for train B | 45352 | 45355 | 5426 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5426 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 5426 |  |  | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3764 | C | USCSB2403012A | -01 | Core hole Conduit | 3/1/2024 4/4/2024 | 3/18/2024 4/5/2024 | 8307.1 | 2507.75 | 5799.35 |  |  | V |  | Wesco Distribution, Inc. | PR Approved | PO Approved | PR R1: The quantity adjustment is made in accordance with the subcontractor's request and has been approved by the AMAT PM. |  | Yikang Wang | [11 empty] | 7167.21 | 0.86278 | 1139.89 | 0 | 1139.89 | 0 | [52 empty] | 0 | 7167.21 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3765 | C | USCSB2403013A | -01 | tools for calibration for HK power system | 45352 | 2024/3/13 2024/3/20 | 0 | -2239.66 | 2239.66 |  |  |  |  | Border State Industries, Inc. | PR Approved | PO Approved | PO R1:change to amazon because account is still on hold |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3766 | C | USCSB2403013B |  | tools for calibration for HK power system | 45352 | 2024/3/12 2024/3/19 2024/3/20 | 2239.66 |  |  | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: change to amazon because account is still on hold B: Change to AMAZON |  | Yi En Wong | [11 empty] | 1823.42 | 0.81415 | 416.24 | 0 | 416.24 | 0 | 1823.42 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3767 | C | USCSB2403014A |  | UPW-Tomoe valve for train B | 45352 | 45355 | 8225 | [6 empty] | Tomoe USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 8225 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 8225 |  |  |  |  | 7813.75 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3768 | C | USCSB2403015A |  | UPW-GF valve for train B | 45352 | 45353 | 830.76 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 830.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 830.76 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3769 | C | USCSB2403016A |  | CDS strut end caps | 45352 | 45356 | 2250 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2250 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2100 |  |  |  |  | 150 | 150 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 3770 | C | USCSB2403017A |  | CDS Welder rental for Chemical welding.(RENTAL FROM 2-2-24 TO 3-1-24) | 45352 | 45357 | 650 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 650 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3771 | C | USCSB2403018A |  | WWT Threaded Plug_20240229 (A Side) | 45353 | 45355 | 120.34 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 120.34 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 120.34 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3772 | C | USCSB2403019A |  | Product/DOT 6502PZ PULL LINE DSPNG PAIL,240 FT STEEL FISHTAPE,CADDY CAT32HP 2IN CAT5 CABLE CLIP | 45353 | 45355 | 1391.77 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 103.96 | 0.074696 | 1287.81 | 0 | 1287.81 | 0 | [52 empty] | 0 | 0 | 0 |  | 103.96 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Barcode | Equipment | USC22C019 | AMC monitor 595T0 | 3773 | C | USCSB2403020B |  | F21 Brcode system _ G-Bit | 45353 | 2024/3/5 2024/3/8 2024/3/11 | 1026 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved |  | R1: Correcting the Supplier B: Correcting the Supplier | Yikang Wang | [11 empty] | 1026 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1026 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3774 | C | USCSB2403021A |  | WWT Fitting_20240301 (A Side) | 45353 | 45356 | 4916.22 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4916.22 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2445.61 |  | 2470.61 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3775 | C | USCSB2403022A |  | WWT - Replacement Coupling for P-350 AA/AB | 45353 | 45356 | 1260 | [6 empty] | Phoenix Pumps, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1228.12 | 0.9747 | 31.88 | 0 | 31.88 | 36.8436 | 1228.12 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 36.8436
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3776 | C | USCSB2403023A |  | CDS tools for flare | 45353 | 45357 | 2016 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2016 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2016 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Greenberry | USC23C045 | WWT Change Order (Piping) | 3777 | C | USCSB2403024A |  | WWT Tunnel additional rack on expansion loop | 45353 | 45357 | 59468.46 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 59468.46 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 59468.46 | 8920.269 |  |  |  | 8920.269 |  |  |  | 8920.269 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C006 | F21P1 Slurry package | 3778 | C | USCSB2403025A |  | Chem PVDF Fittings_20240229 | 45353 | 45356 | 207.14 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 207.14 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 207.14 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | NUUO | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3779 | C | USCSB2403026A |  | WWT Lorry CCB Fiber, Power, Control Pull & Termination | 45353 | 45356 | 255000 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 255000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 255000 |  |  |  |  | 38250 |  |  |  | 38250 |  |  |  | 38250 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3780 | C | USCSB2403027A |  | CDS 1/4" ball valve and snoop | 45353 | 45356 | 1189.25 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1189.25 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1189.25 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3781 | C | USCSB2403028A |  | WWT Hardware_20240229 (A Side) | 45356 | 45355 | 2746.88 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2746.88 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 469.1 | 1918.23 |  | 0 |  |  |  | 359.55 | 137.344 |  |  |  | 274.688 |  |  |  | 412.032 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | USC22C014 | F21P1 AMHS Power Panel | 3782 | C | USCSB2403029A |  | General laborer and Housekeeping&Superintendent Service (Open PO) | 45356 | 45358 | 100000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 64821.62 | 0.64822 | 35178.38 | 0 | 35178.38 | 0 | [52 empty] | 0 | 0 | 22195.06 |  | 12832.56 |  |  |  | 29794 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3783 | C | USCSB2403030A | -01 | extension ladder, tie-down straps, and locks for HK PPL | 3/5/2024 3/19/2024 8/22/2024 | 3/5/2024 4/5/2024 8/28/2024 | 416.33 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | R1: Matching the amount with the actual cost R2: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 416.33 | 1 | 0 | 0 | 0 | 0 | 416.33 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3784 | C | USCSB2403031A |  | WWT Center Ring_20240304 (A Side) | 45356 | 45358 | 7311 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7311 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7311 |  |  | 1096.65 |  |  |  | 1096.65 |  |  |  | 1096.65 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3785 | C | USCSB2403032A |  | UPW-train B valves from ORGANO | 45356 | 45358 | 1645 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1645 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1645 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3786 | C | USCSB2403033A |  | WWT - T&M Proposal to Work Stainless Line in LB2 | 45356 | 45359 | 46091 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2861.4 | 0.062082 | 43229.6 | 0 | 43229.6 | 46091 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 6913.65 |  |  |  | 6913.65 |  |  |  | 6913.65 | 2861.4 | 11522.75 |  | - | 11522.75 | - | 11522.75 | 11522.75 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 3787 | C | USCSB2403034A |  | WWT - Replacement Couplings for F21P1 WWT Goulds pumps | 45356 | 45366 | 12518.62 | [6 empty] | Phoenix Pumps, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 12518.62 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 12518.62 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3788 | C | USCSB2403036A | -01 | TSMC Straight Shoe Tee Fitting w/Flange for HK Exhaust trade | 45356 | 2024/3/7 2024/3/11 | 68773.55 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved | R1: Revise ship-to address and delivery instructions |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 44905.34 | 0.65294 | 23868.21 | 0 | 23868.21 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 23347.34 |  | 10830.84 |  | 10727.16 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Labor | USC21C005 | F21P1 Chemical & WCCS package | 3789 | C | USCSB2403037A |  | SDS H2O2 to equipment wiring | 2024/3/5 2024/6/12 | 45457 | 22080 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved | PR R1: After negotiations by Engineer Johnny with the supplier, the PR amount was adjusted. |  | 0 |  |  |  | 0 | [7 empty] | 0 | 0 | 22080 | 0 | 22080 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [12 empty] | 25000 |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Site Expense | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3790 | C | USCSB2403039A |  | United Rentals Branch DK8,30 foot 2wd Articulating Electric Boom Lift | 45356 | 45357 | 1988.38 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1112.7 | 0.5596 | 875.68 | 0 | 875.68 | 0 | [52 empty] | 0 | 0 | 1112.7 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3791 | C | USCSB2403040A | -01 | WWT - Replacement guard for P-350 AB | 45356 | 2024/3/15 2024/3/21 | 601.82 | 85.02 | 516.8 | V |  |  |  | Phoenix Pumps, Inc. | PR Approved | PO Approved | R1: Change PR amount to add freight and credit card fee |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 601.82 | 1 | 0 | 0 | 0 | 0 | 601.82 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 90.273 |  |  |  | 90.273 |  |  |  | 90.273 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC21C011 | F21 TMAH System | 3792 | C | USCSB2403041A | -01 | WWT - LSR(i) Scope | 2024/3/5 2024/4/27 | 2024/3/16 2024/5/7 | 0 | -247423 | 247423 |  |  |  |  | BMWC Constructors, INC. | PR Approved | PO Approved | R1: As per engineer Jim to cancel the PR. |  | Yikang Wang |  |  |  | 0 | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3793 | C | USCSB2403042A |  | Cooper Wiring Devices CS8269 Recp Single 50A 250V 2P3W H/L BK for HK Power trade | 45356 | 45357 | 49.49 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 44.78 | 0.90483 | 4.71 | 0 | 4.71 | 0 | 44.78 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3794 | C | USCSB2403043A |  | Heavy duty Contractor's bags for HK Power trades | 45356 | 45358 | 563.12 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 563.12 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 563.12 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3795 | C | USCSB2403044A |  | QAQC and office supply for trail 14, tool hookup team | 45357 | 45372 | 596.81 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 520.94 | 0.87287 | 75.87 | 0 | 75.87 | 0 | 520.94 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3796 | C | USCSB2403045A |  | Hole Seal; 1/2 In.; Gasketed, Oil Tight; Steel for HK Electrical PM | 45357 | 45362 | 6360 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6360 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3122.76 |  | 3237.24 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C006 | F21P1 Slurry package | 3797 | C | USCSB2403046A |  | Chem Gasket_20240305 | 45357 | 45362 | 75.18 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 75.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 75.18 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 3798 | C | USCSB2403047A |  | Cable Sleeving - Snap Tube, Small Box (KST-70R) for LAM tool KCOXN7 | 45357 | 45363 | 10867.68 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 10867.68 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 10867.68 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | UMEC | USC21C005 | F21P1 Chemical & WCCS package | 3799 | C | USCSB2403048A |  | CDS UPW - 8-195 AOR HFC HFD Chem Drains | 45357 | 45363 | 95913 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 95913 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 91117 | 0 |  | 4796 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Site Expense | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3800 | C | USCSB2403049A |  | United Rentals Branch DK8/Item# 11292094 Boom 45-50' Telescopic 4WD Make :Gene Model: S-45XC | 45357 | 45357 | 4414.44 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4414.44 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 4414.44 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3801 | C | USCSB2403050A |  | WWT SUS SCH40 Pipes_20240305 (A Side) | 45357 | 45358 | 32705.6 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 32705.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 32705.6 |  | 0 |  |  |  |  | 4905.84 |  |  |  | 4905.84 |  |  |  | 4905.84 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3802 | C | USCSB2403052A |  | BandSawBlade, Fiber Disc, Thread Sealant Tape, Tool hookup team | 45357 | 45362 | 451.55 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 451.55 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 451.55 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Site Expense | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3803 | C | USCSB2403053A |  | United Rentals Branch DK8/10 scissor lift operator certificates/Fall Pro Awareness for Equipment | 45357 | 45357 | 2256.7 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2256.7 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2256.7 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3804 | C | USCSB2403054A |  | WWT: Triazole Electrical Panel Anchoring | 45357 | 45356 | 2430 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2430 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2430 |  | 0 |  |  |  |  | 364.5 |  |  |  | 364.5 |  |  |  | 364.5 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Site Expense | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3805 | C | USCSB2403056A |  | United Rentals/Scissor Lift 39-40 Electric 45-48 Wide/ item#297951AH/ Scissor lift 39-40' Electric 45-48" Wide item 199199AH | 45357 | 45358 | 7047.64 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7047.64 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 7047.64 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 3806 | C | USCSB2403057A | -01 | WWT-Ammonia-High concentration standards solution | 45357 | 2024/3/6 2024/3/27 | 170.64 | [6 empty] | Winn Marion Barber, LLC | PR Approved | PO Approved | R1: Remark 10 and 20 discussion with supplier |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 170.64 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 25.596 | 170.64 |  |  | 25.596 |  |  |  | 25.596 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3807 | C | USCSB2403058A |  | Red and blue cable tie for high pressure hose for HK PCW trade | 2024/3/6 2024/8/22 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Close | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3808 | C | USCSB2403059A |  | Security cart for HK power trade | 45357 | 45358 | 3428 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3428 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3428 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3809 | C | USCSB2403060A |  | Wire mesh bin for HK PPL trade | 45357 | 45370 | 2949.69 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2949.69 | 1 | 0 | 0 | 0 | 0 | 2949.69 | [51 empty] | 0 | 0 | 0 | [16 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3810 | C | USCSB2403061A |  | COLLAPSIBLE WIRE CONTAINER WITH CASTERS, for TSMC construction team | 45357 | 45363 | 10542.84 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 10542.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 10542.84 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3811 | C | USCSB2403062A |  | Office supplies for tool hookup ppep trade | 45357 | 45358 | 332.34 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 328.02 | 0.987 | 4.32 | 0 | 4.32 | 0 | 328.02 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3812 | C | USCSB2403063A |  | 4 in. Crimped Wire Wheel for HK PPL trade | 45357 | 45357 | 138 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 121.6 | 0.88116 | 16.4 | 0 | 16.4 | 0 | 121.6 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3813 | C | USCSB2403064A |  | Cable ties for HK PCW trade | 45357 | 45358 | 1560 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1560 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 1560 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3814 | C | USCSB2403065A |  | U-LINE-Bump cap white, Ice Wraparounds-Clear,Uline Safety Glass Wipes | 45357 | 45358 | 175.39 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 175.39 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 175.39 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC22C009 | F21P1 230kV MTR Oil and Drain Pipe work | 3815 | C | USCSB2403066A |  | UPW-Harrington-U-bent for Brine RO tank | 45358 | 45358 | 2455 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2255 | 0.91853 | 200 | 0 | 200 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 2255 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3816 | C | USCSB2403067A |  | Desk mat is required in the laydown area for materials and tools to prevent damage. Shared by all HK system | 45358 | 45363 | 8871.1 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 7818.85 | 0.88138 | 1052.25 | 0 | 1052.25 | 0 | 7818.85 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3817 | C | USCSB2403068A | -01 | CDS NZM1-XTVD DOOR COUPLING ROTARY HDL LOCK | 45358 | 2024/3/9 2024/3/22 | 241.24 | [6 empty] | RS AMERICAS, INC | PR Approved | PO Approved | PO R1:Payment Term Change |  | Yikang Wang |  |  |  | 0 | [7 empty] | 241.24 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 241.24 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 3818 | C | USCSB2403069A |  | CDS Welder rental for Chemical welding.( RENTAL FROM 1-29-24 TO 2-26-24) | 45358 | 45362 | 1400 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 1400 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 1400 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3819 | C | USCSB2403071A |  | RS PAYROLL SERVICES, TIMECARD PAYMENT FOR ASSOCIATES INVOICE#4721 | 45358 | 45358 | 3538.29 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3538.29 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3538.29 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3820 | C | USCSB2403072A |  | desk mats in the laydown area for materials and tools to prevent damage to the floor shared by all HK systen | 2024/3/7 2024/3/13 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: change vendor zero out | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3821 | C | USCSB2403073A |  | RS PAYROLL SERVICES, TIMECARD PAYMENT FOR ASSOCIATES INVOICE#4729 | 45358 | 45362 | 9698.84 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 9698.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 9698.84 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3822 | C | USCSB2403074A |  | Mobile helium leak detector 100 to 230 V (± 10%) 50/60 Hz for HK PPL trade | 45358 | 45362 | 44220 | [6 empty] | INFICON Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 44200 | 0.99955 | 20 | 0 | 20 | 0 | [52 empty] | 44200 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | UMEC | USC21C005 | F21P1 Chemical & WCCS package | 3823 | C | USCSB2403075A |  | CDS UPW - 8-194 Chem UPW Loops | 45358 | 45363 | 24859 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 24859 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 23616 | 0 |  | 1243 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3824 | C | USCSB2403077A |  | Liquidtight Flex Connector for HK Power trade | 45358 | 45363 | 5354.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 5354.12 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 5354.12 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3825 | C | USCSB2403078A |  | TTI Molex battery cable lug for HK Power trade | 45358 | 45364 | 1009.05 | [6 empty] | TTI, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 980 | 0.97121 | 29.05 | 0 | 29.05 | 0 | 980 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3826 | C | USCSB2403079A |  | PG19 Cable gland for HK Power | 2024/3/7 2024/3/12 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:user request | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3827 | C | USCSB2403080A |  | Heavy duty clear trash bags for HK Power trades | 45358 | 45363 | 1207 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1064.2 | 0.88169 | 142.8 | 0 | 142.8 | 0 | 1064.2 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3828 | C | USCSB2403081A |  | P clamp for gas system, tool hookup team | 45358 | 45362 | 953 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 953 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 953 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3829 | C | USCSB2403082A |  | Shared for all system, tool hookup team | 45359 | 45372 | 4150 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 4150 | 0 | 4150 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 4150 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3830 | C | USCSB2403083A |  | WWT Blind Flange_20240307 (A Side) | 45359 | 45363 | 6109.2 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 6109.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 4753.99 |  | 1355.21 |  |  | 916.38 |  |  |  | 916.38 |  |  |  | 916.38 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 3831 | C | USCSB2403084A |  | WWT - T-135AA Repair(MMI will reimburse) | 45359 | 45363 | 14189.19 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 14189.19 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 2128.3785 | 14189.19 |  |  | 2128.3785 |  |  |  | 2128.3785 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3832 | C | USCSB2403085A |  | UPW-ORGANO BSGN valves | 45359 | 45358 | 1730 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1730 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1730 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3833 | C | USCSB2403086A |  | WWT Bolt Sets_Copper State(B side) | 45359 | 45362 | 34789.81 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 34789.81 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 22970.77 |  | 0 |  |  |  | 11819.04 | 5218.4715 |  |  |  | 5218.4715 |  |  |  | 5218.4715 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3834 | C | USCSB2403087A |  | Loto PR for Power Luis Retiz | 45359 | 45389 | 1176.12 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1023.11 | 0.8699 | 153.01 | 0 | 153.01 | 0 | 1023.11 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3835 | C | USCSB2403089A |  | Cable Tray Clamps for HK Power trade | 2024/3/8 2024/3/13 | 45364 | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Change QTY to 10000 | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3836 | C | USCSB2403090A |  | Cable Gland 20 Pack PG19 Waterproof Adjustable 12-16mm Nylon Cable Glands Joints with Gaskets, Black(PG19) for HK Power trade | 45359 | 45362 | 571.6 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 519.6 | 0.90903 | 52 | 0 | 52 | 0 | 519.6 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 3837 | C | USCSB2403091A |  | VOC System K-type wire and temperature controller | 45360 | 45363 | 34098 | [6 empty] | Desiccant Technology Corporation | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 34098 | 1 | 0 | 0 | 0 | 24550.56 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 9648 |  |  | 32394 |  |  |  |  | 24450 | 24550.56 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3838 | C | USCSB2403092A |  | share material for upw system and storage usage | 45360 | 45363 | 1107.8 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1041.8 | 0.94042 | 66 | 0 | 66 | 0 | 1041.8 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 3839 | C | USCSB2403093A |  | CDS Welder rental for Chemical welding.(RENTAL FROM 2-27-24 To 3-8-24) | 45360 | 45363 | 350 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 350 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 350 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3840 | C | USCSB2403094A |  | CDS green screws | 45360 | 45374 | 1120 | [6 empty] | Valqua NGC, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 1120 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1120 |  |  | 1120 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3841 | C | USCSB2403095A |  | WWT Fab LB2 Missing Rack Column 6 | 2024/3/9 2024/3/13 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: As per engineer Manuel to change the vendor and cancel this PR. |  | 0 |  |  |  | 0 | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3842 | C | USCSB2403096A |  | BUR BTCGC1/0SS GROUND CLAMP | 45360 | 45363 | 93500 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 93500 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 93500 | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3843 | C | USCSB2403097A |  | WWT Fittings_20240308 (A Side) | 45360 | 45363 | 6196.14 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 6196.14 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 1143.86 |  | 5052.28 |  |  | 929.421 |  |  |  | 929.421 |  |  |  | 929.421 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3844 | C | USCSB2403098A |  | Night Vison Optical Monocular Camping/Hunting Handheld Telescope Water Proof and Anti-Fog for HK Exhaust trade | 45360 | 45363 | 147.3 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 133.92 | 0.90916 | 13.38 | 0 | 13.38 | 0 | 133.92 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3845 | C | USCSB2403099A |  | WWT Hardware_20240308 (A Side) | 45360 | 45362 | 1928.71 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 1928.71 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 652.66 | 636.45 |  | 0 |  |  |  | 639.6 | 96.4355 |  |  |  | 192.871 |  |  |  | 192.871 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3846 | C | USCSB2403100A |  | WWT PVC & PP Pipes_20240308 (A Side) | 45360 | 45362 | 1264.24 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 1264.24 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1264.24 |  |  | 189.636 |  |  |  | 189.636 |  |  |  | 189.636 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3847 | C | USCSB2403101A |  | Power Cables | 2024/3/9 2024/3/16 | 45379 | 41280.2 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved | PR R1:Adjusting the amount between quotation and the PR. |  | Yikang Wang |  |  |  | 0 | [7 empty] | 41268.93 | 0.99973 | 11.27 | 0 | 11.27 | 0 | [52 empty] | 0 | 6975.57 | 4384.25 |  | 2234.98 | [5 empty] | 27674.13 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3848 | C | USCSB2403102A |  | CDS JJ Healy CO2 90 elbow | 45360 | 45362 | 452.21 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 452.21 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 452.21 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C046 | F21P1 ATS Interconnection | 3849 | C | USCSB2403103A |  | PCA-ATS: DAILY USE TOOL: TELESCOPIC EXTENSION POLE & WERA TOOL-CHECK PLUS TOOL SET | 45360 | 45364 | 352.99 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 320.89 | 0.90906 | 32.1 | 0 | 32.1 | 0 | 320.89 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3850 | C | USCSB2403104A |  | [B side][Manpower-MU] 協益/1month | 45360 | 45364 | 139678 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 0 | 0 | 139678 | 0 | 139678 | 139678 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 20951.7 |  |  |  | 20951.7 |  |  |  | 20951.7 |  | 27935.6 |  | - | 27935.6 | - | 27935.6 | 27935.6 | 27935.6
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3851 | C | USCSB2403105A |  | [B side][Manpower-MU] 元富/宇翔/柯達/3months | 45360 | 45364 | 707171.3 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 0 | 0 | 707171.3 | 0 | 707171.3 | 707171.3 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 106075.695 |  |  |  | 106075.695 |  |  |  | 106075.695 |  | 141434.26 |  | - | 141434.26 | - | 141434.26 | 141434.26 | 141434.26
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 3852 | C | USCSB2403106A |  | PCI AWT-A-01~07 foundations rework | 45362 | 45365 | 38953 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 38952.97 | 1 | 0.03 | 0 | 0.03 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 38952.97 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Triazole | UMEC | USC22C022 | F21P1 Triazole treatment system | 3853 | C | USCSB2403107A |  | 03/10 overtime work to finish triazole | 45362 | 45363 | 12999 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 12999 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 12349 | 0 |  | 0 |  | 650 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 3854 | C | USCSB2403108A |  | 2nd 1000pcs tiles swap | 45363 | 45365 | 26052 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 26052 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 26052 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3855 | C | USCSB2403109A |  | CDS CO2 Swivel Adapter | 2024/3/12 2024/3/19 | 45365 | 0 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved | PR R1: As per Jeremiah Healy and Harvey Pinder to cancel the PR. |  | Tiong Sheng Poh | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3856 | C | USCSB2403110A |  | Marketech calibration request for quote timing and turnaround with CALHUB support and documentation conforming to ISO 9001 | 45363 | 45363 | 565.65 | [6 empty] | National Calibration Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 226.4 | 0.40025 | 339.25 | 0 | 339.25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 226.4 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3857 | C | USCSB2403111A |  | Industrial tapes for HK Power trade | 45363 | 45363 | 106.69 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 106.69 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 106.69 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3858 | C | USCSB2403112A |  | share for all systems, tool hookup team | 45363 | 45364 | 1099.23 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 929.98 | 0.84603 | 169.25 | 0 | 169.25 | 0 | 929.98 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3859 | C | USCSB2403113A |  | 25 INTALLERS | 45363 | 45398 | 389707.5 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | 0 | [11 empty] | 389707.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 389707.5 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3860 | C | USCSB2403114A |  | Warning sign 3-1/2 in. x 5 in. NEC Arc Flash Adhesive for HK power trade | 45363 | 45363 | 649 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 590 | 0.90909 | 59 | 0 | 59 | 0 | 590 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical Lab | Equipment | USC22C021 | F21P1 Chemical Lab setup | 3861 | C | USCSB2403115A |  | 2 Hach Dissolved Oxygen Sensor Repair | 45363 | 45363 | 1900 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1900 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 1900 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3862 | C | USCSB2403116A |  | HK Electrical PM material request | 45363 | 45364 | 115.28 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 103.6 | 0.89868 | 11.68 | 0 | 11.68 | 0 | 103.6 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3863 | C | USCSB2403117A |  | HK Electrical PM material request | 45363 | 45364 | 2500 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2500 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 2500 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3864 | C | USCSB2403118A |  | Support Safety Badges Check | 45363 | 45365 | 16000 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 16000 | 0 | 16000 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC22C022 | F21P1 Triazole treatment system | 3865 | C | USCSB2403119A |  | WWT: Triazole Tank Anchoring and Crossover Platform Modification | 45364 | 45364 | 11968 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 11968 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1795.2 | 11968 |  |  | 1795.2 |  |  |  | 1795.2 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3866 | C | USCSB2403120A |  | WWT 7 Chemical - 3 | 45364 | 45363 | 996.82 | [6 empty] | Midland Scientific, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 949.36 | 0.95239 | 47.46 | 0 | 47.46 | 996.82 | 949.36 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 149.523 |  |  |  | 149.523 |  |  |  | 149.523 |  | 996.82 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3867 | C | USCSB2403121A |  | WWT 5_Blind Flange_20240312 (A Side) | 45364 | 45365 | 603.68 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 603.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 603.68 |  |  |  |  | 90.552 |  |  |  | 90.552 |  |  |  | 90.55 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 3868 | C | USCSB2403122A |  | PCO 82 Contract Pricing Adjustment, Continuation of Work Phase 2, Revision 0(batch 1/2) | 45364 | 45365 | 950000 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 950000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 500000 |  |  |  | 450000 |  |  | 500000 |  |  |  | 450000 |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 3869 | C | USCSB2403123A |  | Fab L10/20 Co2 special permit | 45364 | 45366 | 158496 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 158496 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 158496 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3870 | C | USCSB2403124A | -01 | tape for all systems | 45364 | 2024/3/13 2024/3/15 | 1998.24 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | R1: Change Ship-to Address to Surprise WH |  | Yikang Wang | [11 empty] | 1996.4 | 0.99908 | 1.84 | 0 | 1.84 | 0 | [52 empty] | 0 | 0 | 0 |  | 1996.4 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3871 | C | USCSB2403125A |  | 3199 INSTRUMENTATION MISC 6" 24 hour 150 psi cicular chart recorder paper 60 pcs, tool hookup team | 45364 | 45365 | 379.26 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 379.26 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 379.26 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 3872 | C | USCSB2403126A |  | 3rd MMI tile alignment T&M | 2024/3/13 2024/3/15 |  | 0 | [6 empty] | 0 | PR Approved | PO Approved | PR R1:Change project code | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 3873 | C | USCSB2403127A |  | HK UPW DP Panel Additional request | 45364 | 45370 | 181267.28 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 181267.28 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 156496.84 |  | 24770.44 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3874 | C | USCSB2403128A |  | CDS VCR, etc | 45364 | 45367 | 1182.55 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1182.55 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1182.55 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3875 | C | USCSB2403129A |  | Office supplies for HK PPEP team | 45364 | 45364 | 181.51 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 164.19 | 0.90458 | 17.32 | 0 | 17.32 | 0 | 164.19 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3876 | C | USCSB2403130A |  | Band Saw Blade for HK Exhaust trade | 45364 | 45364 | 2917.2 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2572.44 | 0.88182 | 344.76 | 0 | 344.76 | 0 | 2572.44 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3877 | C | USCSB2403131A |  | Tipped hole cutters for stainless steel mild steel copper for HK Power trade JerYih | 45364 | 45364 | 272.66 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 236.8 | 0.86848 | 35.86 | 0 | 35.86 | 0 | 236.8 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3878 | C | USCSB2403132A |  | Label Roll for Power System | 45364 | 45364 | 5180.2 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5172.54 | 0.99852 | 7.66 | 0 | 7.66 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 4383.56 | [5 empty] | 788.98 |  |  | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3879 | C | USCSB2403133A |  | hose hook up/installation | 45364 | 45377 | 189853.88 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 189853.88 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 189853.88 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3880 | C | USCSB2403134A |  | WWT - GB-PCO 108- Common Rack addition 6/N.5 | 45365 | 45366 | 13654.97 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 12972.22 | 0.95 | 682.75 | 138173.82 | -137491.07 | 648.611 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 2048.2455 |  |  | 12972.22 | 2048.2455 |  |  |  | 2048.2455 |  | 0 |  | - | 0 | - | 0 | 0 | 648.611
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3881 | C | USCSB2403135A |  | 十字吊架 | 45365 | 45364 | 379 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 379 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 379 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC23C054 | UPW Change Order | 3882 | C | USCSB2403137A |  | PCO 82 Contract Pricing Adjustment, Continuation of Work Phase 2, Revision 0(batch 2/2) | 45365 | 45365 | 50000 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 50000 | 1 | 0 | 9200 | -9200 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 50000 | [6 empty] | 50000 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3883 | C | USCSB2403138A |  | WWT - (20) 5" PVC Blind Flanges | 45365 | 45364 | 6036.8 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 6036.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6036.8 |  |  | 905.52 |  |  |  | 905.52 |  |  |  | 905.52 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3884 | C | USCSB2403139A |  | Multi-Voltage Rapid Battery Charger for HK Exhasut system | 45365 | 45366 | 297 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 198 | 0.66667 | 99 | 0 | 99 | 0 | 198 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3885 | C | USCSB2403140A |  | CDS plastic clamp tube OD 1 | 45365 | 45367 | 140 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 140 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 140 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3886 | C | USCSB2403142A |  | Clear 20-Gauge Plastic Sheeting after epoxy shared by all HK system | 45365 | 45370 | 6467.05 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 6466.95 | 0.99998 | 0.1 | 2682.2 | -2682.1 | 0 | 6466.95 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 3887 | C | USCSB2403143A |  | RS Payroll Onsite Manpower General Labor Foundations | 45365 | 45385 | 18760.63 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 18760.63 | 0 | 18760.63 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3888 | C | USCSB2403144A |  | WWT - Field-12 Rental for (120 days) | 45365 | 45369 | 19090.8 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 16227.18 | 0.85 | 2863.62 | 0 | 2863.62 | 4581.792 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 2863.62 | 6522.69 |  | 4931.79 | 2863.62 |  |  | 4772.7 | 2863.62 |  | 2290.896 |  | - | 2290.896 | - | 0 | 0 | 0
Others | AMHS | Labor | USC24C002 | [RM]F21 EUV Crane service contract | 3889 | C | USCSB2403145A |  | Mennens Cleanroom Cranes EUV Crane Support Annual Inspections | 45365 | 45394 | 15624.11 | [6 empty] | Mennens Cleanroom Cranes B.V. | PR Approved | PO Approved | WO amount € 13,582.69 (@1.1501) Pay in Euro, MICU hereby agrees to assume the responsibility of paying in Euro, thereby accepting the associated currency exchange risk. Furthermore, MICU acknowledges and agrees to cover any additional international wire transfer charges or fees that may accrue during the payment process. |  | Yikang Wang | [11 empty] | 13585 | 0.86949 | 2039.11 | 0 | 2039.11 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 13585 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 3890 | C | USCSB2403146A |  | 5 in. x 60 in. Non-insulated Flexible SS-Flex 800 Stainless Steel Hose Silver For KDSRK1 | 2024/3/14 2024/8/12 | 2024/3/14 2024/8/12 | 234.76 | -31.46 | 266.22 | V |  |  |  | The Home Depot, Inc | PR Approved | PO Approved | PR R1: Price Variation of $31.46 which created an excess in the original PO |  | Ta Wei Wang | [11 empty] | 234.76 | 1 | 0 | 0 | 0 | 0 | 234.76 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3891 | C | USCSB2403147A |  | Electrical tape for HK Power trade | 45365 | 45367 | 847.68 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 847.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 811.28 | [9 empty] | 36.4 |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3892 | C | USCSB2403148A |  | Cleanroom paper shared by all hk systems | 45365 | 45366 | 2944.4 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 2944.4 | 0 | 2944.4 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | USC21C005 | F21P1 Chemical & WCCS package | 3893 | C | USCSB2403149A |  | Amazon - MIMO - Move In/Move Out Team | 45365 | 45370 | 3981.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3446.04 | 0.86556 | 535.26 | 0 | 535.26 | 0 | 3446.04 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3894 | C | USCSB2403150A |  | Cable ties for HK Power trade | 45365 | 45366 | 1600 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1600 | 1 | 0 | 1239812.27 | -1239812.27 | 0 | [52 empty] | 0 | 0 | 0 |  | 1600 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C046 | F21P1 ATS Interconnection | 3895 | C | USCSB2403152A | -01 | ATS CHILLER: NO TOOL ID: DAILY USE OF LADDERS, CHAINS, LOCKS, STORAGE CHEST, HEX KEY SET, & CASTER KIT W/ HARDWARE | 2024/3/14 2024/4/1 | 2024/3/21 2024/5/2 | 1927.65 | -51.82 | 1979.47 |  |  |  |  | The Home Depot, Inc | PR Approved | PO Approved | R1: Ridgid storage chest was refunded. Ordered 2nd time with a discount. |  | Yikang Wang | [11 empty] | 1927.65 | 1 | 0 | 0 | 0 | 0 | 1927.65 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3896 | C | USCSB2403153A |  | Connectors for HK Power trade | 45366 | 45370 | 917.81 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 917.81 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 917.81 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC22C014 | F21P1 AMHS Power Panel | 3897 | C | USCSB2403154A |  | Yaho support for chemical(11/06/2023~02/22/2024) | 45366 | 45369 | 613283.87 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 450217.11 | 0.73411 | 163066.76 | 0 | 163066.76 | 0 | [52 empty] | 0 | 0 | 450217.11 |  | 0 | [12 empty] | 163066.76 |  | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | Heating Jacket | Labor | USC22C014 | F21P1 AMHS Power Panel | 3898 | C | USCSB2403155A |  | Yaho support for Heating Jacket(01/26/2024~04/30/2024) | 45366 | 45369 | 36799.98 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 36799.98 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 13799.98 |  | 0 | [5 empty] | 23000 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3899 | C | USCSB2403156A |  | CDS clamps for the T supports | 45366 | 45366 | 1339 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1339 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1339 |  |  | 1339 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3900 | C | USCSB2403157A |  | OSC WELDING SUPPLIES Arizona/Albuquerque V&F Co./Swagelok Southwest Co | 45366 | 45370 | 344.96 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 344.96 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 344.96 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3901 | C | USCSB2403158A |  | RFQ_Struts & Accessories_Copper State_B side_20240306 | 45366 | 45369 | 183635.46 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 183635.46 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 67018.96 |  | 0 |  |  |  | 116564.86 | 27545.319 |  |  |  | 27545.319 | 51.64 |  |  | 27545.319 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | Labor | USC23C059 | F21P1 Foundation T&M | 3902 | C | USCSB2403159A |  | 3rd MMI tile alignment T&M | 2024/3/15 2024/10/11 | 2024/4/17 2024/10/11 | 192088.4 | -107911.6 | 300000 | V |  |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 192088.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 188624.4 |  |  |  | 3464 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC22C021 | F21P1 Chemical Lab setup | 3903 | C | USCSB2403160A |  | UPW-Mezzanine 3 & 4 Epoxy Floor Coating-Degan | 45366 | 45374 | 200050.78 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 200050.78 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 200050.78 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3904 | C | USCSB2403161A |  | ETC3 LAM Conduit Change Order - Material Order for Conduit Installation on 7 LAM Tools 1. KEMEL2 2. KEMEL3 3. KEMEL5 4. KEMEL | 45366 | 45377 | 4266.62 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 4266.62 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 4266.62 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3905 | C | USCSB2403162A |  | cleanroom tapes shared by all hk trades | 45366 | 45369 | 755.16 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 696 | 0.92166 | 59.16 | 0 | 59.16 | 0 | [52 empty] | 0 | 0 | 0 |  | 696 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3906 | C | USCSB2403164A |  | M610 PRINTER - Handheld Label Maker for HK Power system | 45366 | 45370 | 1380.67 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1375.33 | 0.99613 | 5.34 | 0 | 5.34 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 1375.33 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3907 | C | USCSB2403165A |  | 1/2 in. x 250 ft Polyethylene Tubing Coil in Natural Color for HK Exhaust team | 45366 | 45370 | 1069.28 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 972.08 | 0.9091 | 97.2 | 0 | 97.2 | 0 | 972.08 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3908 | C | USCSB2403166A |  | 3-Port and 4-Port connectors for HK Power trade | 45366 | 45370 | 259.1 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 259.1 | 0 | 259.1 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 3909 | C | USCSB2403167A |  | HK UPW hookup material | 45366 | 45409 | 345859.17 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 38954.3 | 0.11263 | 306904.87 | 0 | 306904.87 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 2766.52 |  |  | 0 | 33369.54 | 2818.24 | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 3910 | C | USCSB2403168A |  | HK Chemical PVDF Materials Pipe | 45366 | 45366 | 1688.82 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 1688.82 | 0 | 1688.82 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3911 | C | USCSB2403170A |  | WWT - GB PCO #104 / New Misc. Support Modifications on X/2 | 45367 | 45369 | 9200 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 9200 | 0 | 9200 | 9200 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1380 |  |  |  | 1380 |  |  |  | 1380 |  | 4600 |  | - | 4600 | - | 0 | 0 | 0
Base-Build | WWT | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3912 | C | USCSB2403171A |  | WWT: Hopper Anchor Modifications | 45367 | 45369 | 4852 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 4852 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 4852 |  |  | 727.8 |  |  |  | 727.8 |  |  |  | 727.8 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3913 | C | USCSB2403172A |  | CDS electrical tape and tool | 45367 | 45370 | 108.78 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 107.48 | 0.98805 | 1.3 | 0 | 1.3 | 0 | 107.48 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3914 | C | USCSB2403173A | -01 | CONNECTOR and ADAPTOR | 45367 | 2024/3/18 2024/3/20 | 0 | -137.14 | 137.14 |  |  |  | V | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: The purchase was completed but not complied with the purchasing policy; Engineering team purchased via personal credit card |  | Kuan-Chung Su | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3915 | C | USCSB2403174A |  | Scissor lift for HK department | 45367 | 45369 | 8404.77 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2682.2 | 0.31913 | 5722.57 | 0 | 5722.57 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 2682.2 | - | 0 | 2682.2 | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3916 | C | USCSB2403175A |  | YAHO T&M A side work from 11/2023-05/2024 | 2024/3/16 2024/3/26 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Due to budget issue,so need to change the budget code and cancel this PR. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3917 | C | USCSB2403176A |  | CDS 6awg 5C | 45367 | 45371 | 6817.62 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 6567.62 | 0.96333 | 250 | 0 | 250 | 0 | [52 empty] | 0 | 0 | 0 |  | 6567.62 | [8 empty] | 250 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3918 | C | USCSB2403177A | -01 | WWT Cleaning Material | 45367 | 2024/3/18 2024/3/19 | 898.04 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | R1: Change to Store Pick up per Angela Hsu |  | Ta Wei Wang | [11 empty] | 791.69 | 0.88158 | 106.35 | 0 | 106.35 | 898.04 | 791.69 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 134.706 |  |  |  | 134.706 |  |  |  | 134.706 |  | 898.04 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 3919 | C | USCSB2403178A |  | CDS Box | 45367 | 45371 | 7110 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 7110 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 7110 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 3920 | C | USCSB2403179A |  | U-Line - MIMO - Move In/Move Out Team | 45369 | 45370 | 5544.35 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5110 | 0.92166 | 434.35 | 0 | 434.35 | 0 | [52 empty] | 0 | 0 | 0 |  | 5110 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | USC21C005 | F21P1 Chemical & WCCS package | 3921 | C | USCSB2403180A |  | Zoro - MIMO - Move In/Move Out Team | 2024/3/18 2024/3/28 | 45383 | 3907.96 | [6 empty] | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3407.96 | 0.87206 | 500 | 0 | 500 | 0 | [52 empty] | 0 | 0 | 1988.34 |  | 1419.62 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 3922 | C | USCSB2403181A | -01 | Global Industrial - MIMO - Move In/Move Out Team | 45369 | 2024/3/20 2024/3/28 | 607.09 | [5 empty] | V | Global Equipment Company Inc. | PR Approved | PO Approved | R1: Listing Global Industrial Concerns on the PO |  | Ta Wei Wang | [11 empty] | 551.9 | 0.90909 | 55.19 | 0 | 55.19 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 551.9 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3923 | C | USCSB2403182A | -01 | B side MU FAB/HPM+Drain material | 2024/3/19 2024/3/28 | 2024/3/19 2024/4/1 | 1240156.97 | -1300840.72 | 2540997.69 |  |  |  | V | Mega Union Technology Inc. | PR Approved | PO Approved | R1: Change to seperate labor and material for 30% witholing tax |  | Yi En Wong | [11 empty] | 0 | 0 | 1240156.97 | 56625.5 | 1183531.47 | 1240156.97 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 186023.5455 |  |  |  | 186023.5455 |  |  |  | 186023.5455 |  | 248031.394 |  | - | 248031.394 | - | 248031.394 | 248031.394 | 248031.394
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 3924 | C | USCSB2403183A |  | prep and epoxy housekepping pads in Fab LB1,L10 and L20 37 PADS TOTAL | 45370 | 45372 | 27215.03 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 27215.03 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 27215.03 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3925 | C | USCSB2403184A | -02 | WWT-lab tech-hood sash weight | 45370 | 2024/3/19 2024/3/27 2024/4/12 | 409.68 | 85.23 | 324.45 | V |  |  |  | LabTech Supply Company Inc | PR Approved | PO Approved | R2: The previous amount of $324.45 should sum up with the freight of $85.23, also change payment method R1: Change Total amount to add credit card fee |  | Ta Wei Wang | [11 empty] | 324.45 | 0.79196 | 85.23 | 0 | 85.23 | 409.68 | 324.45 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 61.452 |  |  |  | 61.452 |  |  |  | 61.452 |  | 409.68 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3926 | C | USCSB2403185A |  | RS Payroll Services manpower labor cost from previous work assigned- open invoices | 45370 | 45371 | 2835.63 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 2835.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2835.63 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 3927 | C | USCSB2403186A | -01 | U-Line - MIMO - Move In/Move Out Team | 45370 | 3/21/2024 3/27/2024 | 1804 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | R1: Change payment method |  | Yikang Wang | [11 empty] | 1791.9 | 0.99329 | 12.1 | 0 | 12.1 | 0 | 1791.9 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3928 | C | USCSB2403187A |  | Shared for all system, tool hookup team | 45370 | 45372 | 1065.8 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 785.97 | 0.73745 | 279.83 | 0 | 279.83 | 0 | 785.97 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC22C013 | F21P1 QR Lab Security & CCTV | 3929 | C | USCSB2403188A |  | F21 P1 Gown Office IT Room speed gate | 45370 | 45370 | 18599.9 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 18599.9 | 0 | 18599.9 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 17670 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3930 | C | USCSB2403189A |  | office supplies for tool hookup department | 45370 | 45370 | 376.93 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 338.6 | 0.89831 | 38.33 | 0 | 38.33 | 0 | 338.6 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3931 | C | USCSB2403190A |  | RS Payroll Services manpower labor cost from previous work assigned- open invoices | 3/19/2024 10/4/2024 | 3/21/2024 10/11/2024 | 5191.44 | -3816.5 | 9007.94 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 5191.44 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 5191.44 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3932 | C | USCSB2403191A | -02 | CDS Punch list SS screws | 3/19/2024 3/29/2024 | 2024/3/20 2024/4/2 | 29.69 | 6.92 | 22.77 |  |  |  |  | The Home Depot, Inc | PR Approved | PO Approved | R1: Change Delivery Location |  | Yikang Wang | [11 empty] | 0 | 0 | 29.69 | 0 | 29.69 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 29.69 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3933 | C | USCSB2403193A |  | KEMEA1 iPUP Mechanical Piping Rev1 | 45370 | 45378 | 15000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 15000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 15000 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3934 | C | USCSB2403194A |  | Knockout Tool Kit-New PR for Power system | 45370 | 45370 | 1650 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1499.99 | 0.90908 | 150.01 | 0 | 150.01 | 0 | 1499.99 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3935 | C | USCSB2403195A |  | Blade and band saw, tool hookup team | 45370 | 45370 | 1704.87 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1704.87 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 1704.87 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3936 | C | USCSB2403196A |  | Fuji Recording Chart,愛知 Circular Recording Chart, tool hookup team | 45370 | 45371 | 2287 | [6 empty] | Richwell Instrument Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2287 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 2287 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3937 | C | USCSB2403197A |  | L-gland, nut, gasket | 45370 | 45382 | 4793.49 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 4793.49 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 4793.49 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3938 | C | USCSB2403198A |  | [B side] Welding machine rental from Harrington 12”*1/20”*1 - 2nd rental | 45371 | 45371 | 47858.4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 41143.69 | 0.8597 | 6714.71 | 0 | 6714.71 | 11751.943 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 7178.76 | 16788.49 |  |  | 7178.76 |  |  | 11963.69 | 7178.76 |  | 5875.9715 | 12391.51 | - | 5875.9715 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3939 | C | USCSB2403199A |  | CDS LB1 B side supports materials | 45371 | 45372 | 7266.13 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 7266.13 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7266.13 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Barcode | Rosendin | USC21C012 | F21 Barcode RFID System | 3940 | C | USCSB2403200A |  | PCO 81, Revision 1: Repull One Fiber Optic Cable from CP1 to CP31 | 45371 | 45371 | 42234.76 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 42234.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 42234.76 | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3941 | C | USCSB2403201A |  | Vinyl Mat for Hook-up team All Trades | 45371 | 45378 | 44700 | [6 empty] | Xiang Sheng Hardware Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 44700 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 44700 | - | 0 | - | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | USC21C003 | F21P1 UPW | 3942 | C | USCSB2403202A |  | 8800lb Dolly for MIMO - Move In/Move Out Team | 45371 | 45379 | 1391.96 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1160.08 | 0.83341 | 231.88 | 0 | 231.88 | 0 | 1160.08 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3943 | C | USCSB2403203A |  | WWT WRC laboratory furniture_2 | 45371 | 45376 | 214.5 | [6 empty] | Ramo Trading & Consulting Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 185.25 | 0.86364 | 29.25 | 0 | 29.25 | 0 | 185.25 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 32.175 |  |  |  | 32.175 |  |  |  | 32.175 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3944 | C | USCSB2403204A |  | WWT WRC laboratory furniture_3 | 45371 | 45385 | 129.36 | [6 empty] | Mega Depot, LLC | PR Approved | PO Approved | [14 empty] | 117.6 | 0.90909 | 11.76 | 0 | 11.76 | 10.584 | 117.6 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 19.404 |  |  |  | 19.404 |  |  |  | 19.404 |  | 0 |  | - | 0 | - | 0 | 0 | 10.584
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3945 | C | USCSB2403206A |  | Consolidated Electrical Distributors Inc,Taiwaan Vendor Electricl Upgrade | 45371 | 45377 | 1123.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1123.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 749 | [14 empty] | 0 |  | 374.5 | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3946 | C | USCSB2403207A |  | WWT Caps_20240319 | 45372 | 45376 | 13343.35 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 13343.35 | 1 | 0 | 0 | 0 | 2878.2177 | [52 empty] | 0 | 0 | 4171.33 |  | 0 |  |  |  |  | 2001.5025 |  |  |  | 2001.5025 |  |  | 9172.02 | 2001.5025 |  | 2878.2177 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3947 | C | USCSB2403208A |  | Additional 220 V outlets to complete the electrical requirements | 45372 | 45372 | 1472 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1350 | 0.91712 | 122 | 0 | 122 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1350 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Site Expense | USC21C011 | F21 TMAH System | 3948 | C | USCSB2403209A |  | WWT009_B 區機台租賃_Mega(8 month) | 2024/3/21 2024/4/2 | 45387 | 261357 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 261357 | 0 | 261357 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 39203.55 |  |  |  | 39203.55 |  |  |  | 39203.55 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3949 | C | USCSB2403210A |  | Additional 220 V outlets to complete the electrical requirements materials | 45372 | 45373 | 1761.71 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 1685.64 | 0.95682 | 76.07 | 0 | 76.07 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1529.6 | [9 empty] | 156.04 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3950 | C | USCSB2403211A | -01 | CDS Circuit Lockout Kit | 45372 | 3/30/2024 4/4/2024 | 900 | -96.6 | 996.6 | V |  |  |  | Wesco Distribution, Inc. | PR Approved | PO Approved | R1: Quote Update |  | Yikang Wang | [11 empty] | 900 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 900 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3951 | C | USCSB2403212A |  | 350kcmil 3C+GND Power Cable | 45372 | 45381 | 10065 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 10065 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 10065 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Trident | USC21C014 | F21P1 WH2SO4 | 3952 | C | USCSB2403213A |  | 2023 H2SO4 Labor Incentive Change Order | 45372 | 45377 | 56625.5 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 56625.5 | 13760.39 | 42865.11 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 8493.825 |  |  |  | 8493.825 |  |  |  | 8493.825 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 3953 | C | USCSB2403214A |  | Labor: Torque and Seal AMAT CVD | 45372 | 45380 | 3600 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3600 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 3600 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3954 | C | USCSB2403215A |  | For tailer 15 office supplies, tool hookup team | 45372 | 45372 | 1883.78 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1426.12 | 0.75705 | 457.66 | 0 | 457.66 | 0 | 1426.12 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3955 | C | USCSB2403216A |  | 3 month Brycon Contract | 45372 | 45380 | 224190 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 42942.06 | 0.19154 | 181247.94 | 0 | 181247.94 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 42942.06 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 3956 | C | USCSB2403217A |  | U-Line - Taiwan Installer team | 45372 | 45376 | 13585 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 12350 | 0.90909 | 1235 | 0 | 1235 | 1111.5 | [52 empty] | 0 | 0 | 0 |  | 12350 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 1111.5
Base-Build | WWT | Labor | USC21C011 | F21 TMAH System | 3957 | C | USCSB2403218A |  | WWT009 - GB-PCO 110- Remove and Reinstall main rack LB2 B-side supports (N.5-P/19-19.5) | 45372 | 45377 | 12152.2 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 11544.59 | 0.95 | 607.61 | 0 | 607.61 | 577.2295 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1822.83 |  |  | 11544.59 | 1822.83 |  |  |  | 1822.83 |  | 0 |  | - | 0 | - | 0 | 0 | 577.2295
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3958 | C | USCSB2403219A |  | Home Depot Order for 2 ladders and 4 combo locks for cages | 45372 | 45376 | 569.69 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 515.17 | 0.9043 | 54.52 | 0 | 54.52 | 0 | 515.17 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 3959 | C | USCSB2403220A |  | CVD AMAT Interconnect Oil Piping on KCOLA1 | 45372 | 45376 | 22277 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 22277 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 22277 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3960 | C | USCSB2403221A |  | WWT 009 _B SIDE P clamp | 45372 | 45376 | 68189.46 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 68189.46 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 10228.419 | 68189.46 |  |  | 10228.419 |  |  |  | 10228.419 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3961 | C | USCSB2403222A |  | M6 Printer kit for HK Power trade | 45372 | 45377 | 15424 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 15424 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 15424 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3962 | C | USCSB2403223A |  | Ring Tongue for HK Power trade | 45372 | 45377 | 4352 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 4352 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1644 | [12 empty] | 0 |  | 2708 | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 3963 | C | USCSB2403224A |  | AMAT CVD Bolts, Square Washers, Spring Nuts, & Flat washers | 45373 | 45377 | 773.85 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 773.85 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 773.85 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3964 | C | USCSB2403225A |  | THHN Insulated Metallic Cable | 2024/3/22 2024/4/13 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Pr no longer needed |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3965 | C | USCSB2403226A |  | Electrician tools Power System order form Luis | 45373 | 45376 | 2078.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1883.3 | 0.90617 | 195 | 0 | 195 | 0 | 1883.3 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3966 | C | USCSB2403227A |  | S-11545 Draw ULINE - Cord Bags – 20X24X4 Clear 250/Per Carton | 45373 | 45376 | 199.12 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 197.26 | 0.99066 | 1.86 | 0 | 1.86 | 199.12 | 197.26 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 29.868 |  |  |  | 29.868 |  |  |  | 29.868 |  | 199.12 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3786 | C | USCSB2403230A |  | CGS Global Support Onsite Manpower Tent 1 | 2024/3/22 2024/6/19 | 45491 | 16203.5 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | RPR R1::Updated budget cost. | [13 empty] | 0 | 0 | 16203.5 | 0 | 16203.5 | 16203.5 | [71 empty] | 8101.75 |  | - | 8101.75 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3968 | C | USCSB2403231A |  | 20' & 40' storage containers for HK Power team | 2024/3/22 2024/8/22 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Close | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC22C009 | F21P1 230kV MTR Oil and Drain Pipe work | 3969 | C | USCSB2403232A |  | UPW DC Bank Panel to Panel Termination & Cable Pull | 45373 | 45378 | 30720 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 30720 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 30720 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC22C013 | F21P1 QR Lab Security & CCTV | 3970 | C | USCSB2403233A |  | VOC/ B side + control and power wire. | 45374 | 45378 | 179837.71 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 179837.71 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 28587.03 |  | 151250.68 | [10 empty] | 170846 |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3971 | C | USCSB2403234A |  | Modcule CIP Create ad installed E- Sensors at DAQ Box on 7 tools | 2024/3/23 2024/9/17 | 2024/3/29 2024/9/17 | 0 | -7367.23 | 7367.23 | V |  |  |  | Commercial Comm and Electric Inc | PR Approved | PO Approved | PO R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Tiong Sheng Poh | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 3972 | C | USCSB2403235A |  | Jeoufwu Foundation manufacture M0603 | 45374 | 45383 | 2450 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 2450 | 0 | 2450 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3973 | C | USCSB2403236A |  | battery and Oxygen regulator, tool hookup | 45374 | 45376 | 875.51 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 803.36 | 0.91759 | 72.15 | 0 | 72.15 | 0 | 803.36 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3974 | C | USCSB2403237A |  | Extension Cord, Faceshield Bracket, Flashlight, Screwdriver, TOOL HOOKUP | 45374 | 45376 | 3254.42 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3254.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3254.42 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3975 | C | USCSB2403238A |  | MIC internal Manpower: Labor | 45374 | 45380 | 62172.48 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 27778 | 0.44679 | 34394.48 | 0 | 34394.48 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 27778 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3976 | C | USCSB2403239A | -02 | Arizona/Albuquerque V&F Co./Swagelok Southwest Co,OSC Welding Supplies | 45377 | 2024/4/5 2024/4/8 2024/4/9 | 358.84 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: Change Shipping Address to Glendale R2: Change trade term from DDP to FOB |  | Ta Wei Wang | [11 empty] | 210.71 | 0.5872 | 148.13 | 0 | 148.13 | 0 | [52 empty] | 0 | 0 | 0 |  | 167.43 | [5 empty] | 43.28 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 3977 | C | USCSB2403240A |  | WWT PVC Pipes_20240325 (B Side) | 45377 | 45378 | 81734.33 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 81734.32 | 1 | 0.01 | 0 | 0.01 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 12260.1495 | 81734.32 |  |  | 12260.1495 |  |  |  | 12260.1495 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3978 | C | USCSB2403241A | -01 | CDS CO2 system warning signs | 45377 | 2024/3/27 2024/3/30 | 176.9 | 7.06 | 169.84 | V |  |  |  | Compliance Signs, LLC | PR Approved | PO Approved | R1: Due to the additional shipping fee as per purchasing team David. |  | Ta Wei Wang | [11 empty] | 176.9 | 1 | 0 | 0 | 0 | 0 | 176.9 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 176.9 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 3979 | C | USCSB2403242A |  | CDS Leakage detection tape installation | 45377 | 45393 | 220800 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 220800 | 0 | 220800 | 110400 | [52 empty] | 0 | 0 | 0 |  | 0 | [12 empty] | 110400 |  | 110400 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3980 | C | USCSB2403243A |  | Switchboard Mat for HK power system | 45377 | 45376 | 1000 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 1000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC21C005 | F21P1 Chemical & WCCS package | 3981 | C | USCSB2403244A |  | CDS INSTALL VMB WITH SUPPORTS TSMC-008 | 45377 | 45378 | 98660 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 84899.61 | 0.86053 | 13760.39 | 0 | 13760.39 | 4933 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 93727 | 84899.61 |  |  |  |  | 4933 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3982 | C | USCSB2403245A | -01 | Locks and vacuum filter for HK Exhaust trade | 45377 | 2024/3/27 2024/4/3 | 1381.51 | -2189.62 | 3571.13 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Returning budget per purchasing request |  | Ta Wei Wang | [11 empty] | 1381.51 | 1 | 0 | 0 | 0 | 0 | 1381.51 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3983 | C | USCSB2403246A |  | WWT_Premium White T-Shirt Rags | 45377 | 45379 | 2946.6 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2946.6 | 1 | 0 | 1025537 | -1025537 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2946.6 |  |  | 441.99 |  |  |  | 441.99 |  |  |  | 441.99 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3984 | C | USCSB2403247A |  | plastic wrap and lock and zip lock, tool hookup team | 45377 | 45387 | 3238.5 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3238.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 3238.5 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3985 | C | USCSB2403248A |  | Arc Flash sticker for HK Power system | 45377 | 45384 | 2525 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2525 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2525 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC23C045 | WWT Change Order (Piping) | 3986 | C | USCSB2403249A |  | UPW-UMEC-COs for MA-137, 162, 172 and 182 | 2024/3/26 2024/7/16 | 2024/5/6 2024/7/16 | 87328 | -887 | 88215 |  |  |  |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | Order was subsequently revised to new amount. |  | 0 | [11 empty] | 83804 | 0.95965 | 3524 | 0 | 3524 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 49864 |  |  |  | 27632 |  |  | 0 | 6308 | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3987 | C | USCSB2403250A |  | CUSH TUBE STRUT CLMP CUSH TUBE STRUT CLMP | 45377 | 45378 | 143.58 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 143.58 | 1 | 0 | -1001.15 | 1001.15 | 0 | [52 empty] | 0 | 0 | 143.58 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 3988 | C | USCSB2403251A | -02 | Additional wiring material for Ammonia analyzer_WWT | 45377 | 3/30/2024 4/3/2024 4/5/2024 | 144.77 | -14.48 | 159.25 |  |  |  |  | WW Grainger Inc | PR Approved | PO Approved | R1: Remove Item Buffer R2: Change Payment Method |  | Yikang Wang | [11 empty] | 144.77 | 1 | 0 | 0 | 0 | 144.77 | 144.77 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 21.7155 |  |  |  | 21.7155 |  |  |  | 21.7155 |  | 144.77 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3989 | C | USCSB2403252A |  | Cable ties for HK Power trade | 45378 | 45387 | 220.4 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 220.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 220.4 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3990 | C | USCSB2403253A |  | RYOBI BAND SAW FOR DRY ETC | 45378 | 45378 | 138.82 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 129.61 | 0.93366 | 9.21 | 0 | 9.21 | 0 | 129.61 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | FMCS | Labor | USC22C007 | TSMC F21 FMCS Installation | 3991 | C | USCSB2403254A |  | Overtime for Fiber Cable Pulls & Splicers 3 Weeks | 45378 | 45378 | 57058 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 57058 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 57058 | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3992 | C | USCSB2403255A |  | WWT Hardware_20240320 (A Side) | 45378 | 45378 | 769.85 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 769.85 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 769.85 |  | 0 |  |  |  |  | 115.4775 |  |  |  | 115.4775 |  |  |  | 115.48 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 3993 | C | USCSB2403256A | -01 | WWT-Ammonia standards solution | 45378 | 2024/3/27 2024/3/28 | 493.63 | [5 empty] | V | Winn Marion Barber, LLC | PR Approved | PO Approved | R1: Removing Liquidated Damage per email discussion |  | Ta Wei Wang | [11 empty] | 493.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 74.0445 | 493.63 |  |  | 74.0445 |  |  |  | 74.0445 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | MIMO/Rigging | USC21C005 | F21P1 Chemical & WCCS package | 3994 | C | USCSB2403257A |  | 24-097 CDS Platform 3 Move Quote (cat work move) | 45378 | 45412 | 24635 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 24635 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 24635 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C006 | F21P1 Slurry package | 3995 | C | USCSB2403258A |  | TSMC UPW - 8-201 Remote Cabinet Drains (L20) | 45378 | 45449 | 44754 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 42516 | 0.94999 | 2238 | 0 | 2238 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 42516 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC24C006 | WWT B side Project | 3996 | C | USCSB2403259A |  | WWT: TSMC Approved CO, Design Change to Relocate 18.5 line CuCMP and CWD line | 45378 | 45386 | 41840 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 41840 | 0 | 41840 | 50208 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 6276 |  |  |  | 6276 |  |  |  | 6276 |  | 20920 |  | - | 12552 | - | 12552 | 4184 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 3997 | C | USCSB2403260A |  | WWT-FRP-piping-T780&710 repair (A side) | 45378 | 45380 | 13626.15 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 13626.15 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 13626.15 |  |  | 2043.9225 |  |  |  | 2043.9225 |  |  |  | 2043.9225 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3998 | C | USCSB2403261A | -01 | Cable for HK Power trade | 2024/3/27 2024/4/23 | 2024/4/11 2024/4/23 | 29967.24 |  |  |  | V |  |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Previous item 2 not available |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 29967.24 | 0 | 29967.24 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3999 | C | USCSB2403262A | -01 | WWT WRC laboratory furniture_1 | 45378 | 2024/3/27 2024/04/18 | 966.72 | 179.98 | 1146.7 |  |  | V |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Cancelled purchase for GREATMEET Metal Storage Cabinet |  | Ta Wei Wang | [11 empty] | 862.36 | 0.89205 | 104.36 | 0 | 104.36 | 0 | 862.36 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 145.008 |  |  |  | 145.008 |  |  |  | 145.008 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | USC21C008 | F21P1 CCTV & Security | 4000 | C | USCSB2403263A |  | F21 P1 EBO AMC gas hookup | 45378 | 45383 | 99907.93 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 99907.93 | 1 | 0 | 0 | 0 | 99907.93 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 19982 |  |  |  | 19982 | 99907.93 | 24976.98 |  | - | 24976.98 | - | 44958.57 | $14,987.00 | 4995.4
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4001 | C | USCSB2403264A |  | Locknut, tapes, and ties for HK Power system | 45378 | 45392 | 17575 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 17575 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 20 |  |  | 0 | 7006.83 | 10548.17 | 0 | - | 0 | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4002 | C | USCSB2403265A |  | Jeoufwu Foundation support from 12/1/23~12/31/23 and 2/16/24~5/17/24 | 45378 | 45384 | 130425.45 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 130425.45 | 0 | 130425.45 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 4003 | C | USCSB2403266A |  | WWT: (6) ANSI300 4" Flanges for LSR | 45378 | 45381 | 849.12 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 849.12 | 0 | 849.12 | 849.12 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 127.368 |  |  |  | 127.368 |  |  |  | 127.368 |  | 849.12 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4004 | C | USCSB2403267A |  | 3/8 in PE Tubing Coil for exhaust trade | 45378 | 45385 | 2091.3 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1901.2 | 0.9091 | 190.1 | 0 | 190.1 | 0 | 1901.2 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 4005 | C | USCSB2403268A |  | B side remaining pipe MU can't supply . | 2024/3/28 2024/3/30 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Need to change the budget code, so need to cancel this PR |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | USC23C045 | WWT Change Order (Piping) | 4006 | C | USCSB2403269A |  | welding machine 6300 fix part. | 2024/3/28 2024/4/23 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: As per Jim to cancel the PR. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4007 | C | USCSB2403270A |  | WWT PVC Glue & Primer_20240327 | 45379 | 45379 | 1965 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1965 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 1965 |  |  |  |  | 294.75 |  |  |  | 294.75 |  |  |  | 294.75 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4008 | C | USCSB2403271A |  | Truck Stakebed rental for HK | 45379 | 45401 | 9262.02 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 3663.98 | 0.39559 | 5598.04 | 0 | 5598.04 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 3663.98 | 0 | 3663.98 | 0 | 0
Base-Build | WWT | MMI | USC23C045 | WWT Change Order (Piping) | 4009 | C | USCSB2403272A |  | WWT: HPM L10/L20 Rack Fabrication and Installation | 45379 | 45380 | 34293 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 34293 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 5143.95 | 10478 |  |  | 5143.95 | 23815 |  |  | 5143.95 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4010 | C | USCSB2403273A |  | Grounding Plug and Step Drill Set for exhaust | 45379 | 45385 | 619.2 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 619.2 | 0 | 619.2 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4011 | C | USCSB2403274A | -01 | Office supplies for tool hookup department | 45379 | 45387 | 0 | -905.81 | 905.81 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1:Zero out. go through HR |  | Ta Wei Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4012 | C | USCSB2403275A |  | B side MU FAB/HPM LB2 Main Drain | 45380 | 45387 | 1281921.72 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 1281921.72 | 0 | 1281921.72 | 1281921.72 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 256384.344 |  | - | 256384.344 | - | 256384.344 | 256384.344 | 256384.344
Non-TSMC Interconnection | Interconnection | Material | USC23C016 | F21P1 Mattson Interconnection | 4013 | C | USCSB2403276A |  | MATTSON: KEPRM6-8: GROUND CONDUIT FROM L20-L10 FOR SIGNAL CABLING. | 45380 |  | 903.52 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 903.52 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 903.52 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C016 | F21P1 Mattson Interconnection | 4014 | C | USCSB2403277A |  | MATTSON: KEPRM6-8: PFA CLEAR TUBE FOR SIGNAL CABLE. | 2024/3/29 2024/4/23 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1 :INCORRECT PROJECT CODE, S/B USC24C009 | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C021 | F21P1 KLA Interconnection | 4015 | C | USCSB2403278A |  | ME: KPMI04: CABLE PULL | 45380 | 45383 | 4788 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 4788 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 4788 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4016 | C | USCSB2403279A |  | powercable | 45380 | 45380 | 30817.02 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 30816.97 | 1 | 0.05 | 0 | 0.05 | 0 | [52 empty] | 0 | 0 | 0 |  | 29527.82 |  | 1289.15 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C029 | EBO21- Tool interconnection | 4017 | C | USCSB2403280A |  | EBO: ZFP3-1: GEX EXHAUST REWORK | 45380 | 45383 | 1900 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1900 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1900 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C032 | F21_AZQR_Hookup_ Interconnection | 4018 | C | USCSB2403281A |  | QR: CHAD LABS (KXIM01-07): INSTALL GAS LINES | 45380 | 45383 | 9829 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 9829 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 9829 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Scaffolding | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4019 | C | USCSB2403282A |  | F21 L30 Column S/9.5 Scaffold. | 45380 | 45384 | 5024 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 5024 | 0 | 5024 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4020 | C | USCSB2403283A |  | Apollo Forklift - WWT | 45380 | 45383 | 4176.7 | [6 empty] | Apollo Forklift LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 4176.7 | 0 | 4176.7 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 626.505 |  |  |  | 626.505 |  |  |  | 626.505 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | VOC | MMI | USC21C007 | F21P1 VOC package （Installation ) | 4021 | C | USCSB2403284A |  | VOC Additional Welding - Modifications | 45380 | 45380 | 11912 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 11912 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 11912 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 4022 | C | USCSB2403285A |  | WWT Fittings_20240328 (B Side) | 45380 | 45381 | 11530.68 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 11530.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 11188.38 |  |  | 1729.602 |  |  | 342.3 | 1729.602 |  |  |  | 1729.602 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 4023 | C | USCSB2403286A |  | WWT SUS Fittings & Pipes_20240328 (A Side) | 45380 | 45380 | 9412.45 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 8196.37 | 0.8708 | 1216.08 | 0 | 1216.08 | 1065.5281 | [52 empty] | 0 | 0 | 8196.37 |  | 0 |  |  |  |  | 1411.8675 |  |  |  | 1411.8675 |  |  |  | 1411.8675 |  | 409.8185 |  | - | 655.7096 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4024 | C | USCSB2403288A |  | Amazon - Waste Water Team | 45381 | 45385 | 2587.34 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 2587.34 | 0 | 2587.34 | 2587.34 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 388.101 |  |  |  | 388.101 |  |  |  | 388.101 |  | 1293.67 |  | - | 1293.67 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4025 | C | USCSB2403289A |  | X STRAP Standard Power PIU Work | 45381 | 45383 | 106.7 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 92.15 | 0.86364 | 14.55 | 0 | 14.55 | 0 | 92.15 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 4026 | C | USCSB2403290A |  | Pay the lien outsourcing company | 45381 | 45383 | 910318.51 | [6 empty] | X3 Tradesmen Arizona LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 910318.51 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 563282.6 | 0 | 298215 | 48820.91 | 48820.91 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 4027 | C | USCSB2403291A |  | Pay the lien outsourcing company | 45381 | 45383 | 1150254.2 | [6 empty] | Finish Line Staffing, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1150254.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 698217.4 | 0 | 363285 | 88751.8 | 88751.8 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4028 | C | USCSB2403292A |  | Hydraulic Crimping & Tinned Copper Wire Lugs Kit | 45381 | 45383 | 115.48 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 91.98 | 0.7965 | 23.5 | 52510 | -52486.5 | 0 | 91.98 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4029 | C | USCSB2403293A |  | Nuts and bolts for pipe straps for HK PPL trade | 45381 | 45383 | 591 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 591 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 591 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4030 | C | USCSB2403294A |  | TSMC F21 P1 CDS/SDS B side Support | 45381 | 45385 | 1435672.3 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1435672.3 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 165020.39 |  | 257358.71 |  |  | 941509.59 | 939470.74 |  | 73822.46 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC24C005 | Chemical & WCCS B Side Project | 4031 | C | USCSB2403295A |  | Proposal TSMC-011 @ Chemical Piping_Side B_LB1 CPVC_GN2_PFA_RELAY_VMB_PULL BOX Installations | 45381 | 45394 | 2742000 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1782300 | 0.65 | 959700 | 0 | 959700 | 137100 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1645200 | 1782300 |  |  | 548400 |  |  |  | 411300 |  |  |  | - | 137100 | 959700 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 4032 | C | USCSB2403296A |  | THHN PVC tray cable KCEPA2 & KDGA1 | 45381 | 45395 | 9780.2 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | 0 | [11 empty] | 9780.2 | 1 | 0 | 389400 | -389400 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 9780.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 4033 | C | USCSB2403297A |  | WWT Hardware_20240329 (B Side) | 45381 | 45383 | 4055.18 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 4055.18 | 1 | 0 | 11123.04 | -11123.04 | 0 | [52 empty] | 0 | 0 | 3965.22 |  | 0 |  | 85.75 |  |  | 608.277 |  |  |  | 608.277 | 4.21 |  |  | 608.277 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | USC21C005 | F21P1 Chemical & WCCS package | 4034 | C | USCSB2403298A |  | Amazon - MIMO - Move In/Move Out Team | 45381 | 45383 | 388.25 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 347.3 | 0.89453 | 40.95 | 0 | 40.95 | 0 | 347.3 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 4035 | C | USCSB2403299A |  | WRC L20 Additional Welding | 45381 | 45383 | 1828 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 1828 | 0 | 1828 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 1828 | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 4036 | C | USCSB2403300A |  | LB2 Train-A Anchor Tank Safety Supplies | 45381 | 45393 | 211.75 | [6 empty] | Safety Solutions & Supply | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 211.75 | 32064.57 | -31852.82 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC22C019 | AMC monitor 595T0 | 4037 | C | USCSB2403301A |  | FAB A+B VOC Plumbing and NG Observation | 45381 | 45383 | 5400 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 540 | 0.1 | 4860 | 0 | 4860 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 540 |  |  | 5400 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Site Expense | USC24C006 | WWT B side Project | 4038 | C | USCSB2403302A |  | (B side)WWT Widos Welding Machine_20240329 | 45381 | 45387 | 195000 | [6 empty] | Widos Taiwan Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 195000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 91395 |  | 103605 |  |  |  |  | 29250 |  |  |  | 29250 |  |  |  | 29250 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 4039 | C | USCSB2403303A |  | B side remaining pipe MU can't supply . | 45381 | 45384 | 25945.36 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 25945.36 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 25945.36 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4040 | C | USCSB2403304A |  | Insulating Roll Blanket,Clear,Class 1 for HK Power trade | 45381 | 2024/4/1 2024/7/24 | 1082.49 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | R1: Revising the payment to credit card as it was charged back in April for urgent request |  | Yikang Wang | [11 empty] | 1082.49 | 1 | 0 | 0 | 0 | 0 | 1082.49 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4041 | C | USCSB2403305A | -01 | Electrical insulating gloves for HK Power trade | 45381 | 2024/4/1 2024/4/2 | 94.02 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | R1: Change payment method to US2 Credit Card |  | Ta Wei Wang | [11 empty] | 94.02 | 1 | 0 | 0 | 0 | 0 | 94.02 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC22C022 | F21P1 Triazole treatment system | 4042 | C | USCSB2404001A |  | WWT - Marquis Carbon Media loading #2 | 45383 | 45394 | 119850 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 36675 | 0.30601 | 83175 | 0 | 83175 | 25305.75 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 17977.5 | 36675 |  |  | 17977.5 |  |  |  | 17977.5 |  | 9168.75 |  | - | 9168.75 | - | 6968.25 | 0 | 0
Base-Build | WWT | Equipment | USC24C006 | WWT B side Project | 4043 | C | USCSB2404002A |  | WWT LJ Tools_20240329 | 45384 | 45392 | 64323.97 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 64323.97 | 0 | 64323.97 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 9648.5955 |  |  |  | 9648.5955 |  |  |  | 9648.5955 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 4044 | C | USCSB2404003A |  | Plastic 儲物工具報價(新增), tool hookup team | 45384 | 45384 | 11607.67 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 11607.67 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 11607.67 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 4045 | C | USCSB2404004A |  | Temperature Indicator for Train B | 45384 | 45385 | 1237 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1237 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1237 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC24C006 | WWT B side Project | 4046 | C | USCSB2404005A |  | (A side)YAHO T&M A side work from 11/2023-05/2024 | 45384 | 45385 | 769450 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 757316.67 | 0.98423 | 12133.33 | 0 | 12133.33 | 136953.5 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 595450 |  |  | 115417.5 |  |  |  | 115417.5 |  |  |  | 115417.5 | 161866.67 | 29772.5 |  | - | 29772.5 | - | 29772.5 | 29772.5 | 17863.5
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4047 | C | USCSB2404007A |  | WWT Bside clamp / Copperstate 1st order | 45384 | 45385 | 18932.5 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 18932.5 | 1 | 0 | 1462.11 | -1462.11 | 0 | [52 empty] | 0 | 0 | 1833.05 |  | 0 |  | 3874.3 |  | 9085.15 | 2839.875 | 4140 |  |  | 2839.875 |  |  |  | 2839.875 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4048 | C | USCSB2404008A |  | 18 Tanks Quote for Fab 21 | 45384 | 45387 | 1260000 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1197000 | 0.95 | 63000 | 149200 | -86200 | 63000 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1197000 |  |  | 1008000 | [6 empty] | 63000 | 189000 | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 4049 | C | USCSB2404009A |  | Request for Quote_Please Purchase a Breaker_CED_20240325 | 45384 | 45385 | 125 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 125 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 125 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4050 | C | USCSB2404010A |  | Harness and SRL for WWT x100 | 45384 | 45387 | 44724 | [6 empty] | Palo Verde First Aid-Fire-Safety-Shredding | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 44724 | 0 | 44724 | 53668.8 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 6708.6 |  |  |  | 6708.6 |  |  |  | 6708.6 |  | 22362 |  | - | 13417.2 | - | 13417.2 | 4472.4 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4051 | C | USCSB2404011A |  | WWT SS Fittings_20240401 (B Side) | 45384 | 45387 | 531.44 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 531.44 | 0 | 531.44 | 531.44 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 79.716 |  |  |  | 79.716 |  |  |  | 79.716 |  | 531.44 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 4052 | C | USCSB2404012A |  | NUUO April Labor | 45384 | 45390 | 584370 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 584370 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 111697.5 | [5 empty] | 467197.5 |  | 5475 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4053 | C | USCSB2404013A |  | B-side_WWT_(25) D225 PN10 Ends Caps of Drains | 45384 | 45386 | 5140 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5140 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 771 | 5140 |  |  | 771 |  |  |  | 771 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | MMI | USC21C011 | F21 TMAH System | 4054 | C | USCSB2404014A |  | WWT: Fabricate and Install (2) Ladders for TMAH Expansion | 45384 | 45385 | 15526 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 15526 | 1 | 0 | 331.77 | -331.77 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7763 |  |  | 2328.9 | 7763 |  |  | 2328.9 |  |  |  | 2328.9 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | Material | USC22C001 | F21 P1 Office and WH Security and CCTV | 4055 | C | USCSB2404015A |  | F21 P1 CUP L30 Glass Baffle Railing | 45384 | 45395 | 5576 | [6 empty] | Southwest Metalsmiths, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 5576 | 1 | 0 | 0 | 0 | 5576 | [52 empty] | 0 | 0 | 0 |  | 0 | [12 empty] | 5298 |  | 0 |  | 5576 | 5576 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4056 | C | USCSB2404016A |  | CCE DAQ E-SENSOR(S) INSTALLATION | 2024/4/2 2024/8/29 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Case Closed | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C047 | F21P1 HK Seismic Installation | 4057 | C | USCSB2404017A |  | Hookup seismic installation | 45384 | 45385 | 1222937 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1170427 | 0.95706 | 52510 | 0 | 52510 | 0 | [52 empty] | 0 | 669280 | 0 |  | 0 | [5 empty] | 417576 |  |  |  | 66572 |  |  |  | 7120 | 0 |  | 9879 | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 4058 | C | USCSB2404018A | -01 | Additional Modules M166M188 and 27 STKs PR | 2024/4/2 2024/4/11 | 2024/4/2 2024/4/11 | 24240 | 910 | 23330 | V |  |  |  | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | R1: updated to reflect the newest quote w/ total $24,240 LSW sent us at the end of Feb. The old quote with final price of $23,330 |  | Yi En Wong | [11 empty] | 24240 | 1 | 0 | 82134.66 | -82134.66 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 19420 |  |  |  |  | 0 |  | 4820 | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4059 | C | USCSB2404019A |  | MMI MST M194 Open & Recovery | 45384 | 45385 | 11999 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 11999 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 11999 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 4060 | C | USCSB2404020A |  | Hot box change | 45384 | 45385 | 4317.5 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 4317.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 4317.5 | 4317.5 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4061 | C | USCSB2404021A |  | F21 Bside 耘起(耘程)塑材人力 | 45384 | 45385 | 1037400 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 570900 | 0.55032 | 466500 | 0 | 466500 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 345800 |  |  |  | 345800 | 376200 |  |  | 345800 | 194700 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC21C006 | F21P1 Slurry package | 4062 | C | USCSB2404022A |  | TSMC/ FAB21:A Side Chem Temp Hand Rail Fab and Install | 45384 | 45385 | 11123.04 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 11123.04 | 0 | 11123.04 | 11123.04 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 11123.04 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | CRG | USC24C005 | Chemical & WCCS B Side Project | 4063 | C | USCSB2404023A |  | B-side L30 SDS scope | 45384 | 45395 | 288517 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | 0 | [11 empty] | 288517 | 1 | 0 | 0 | 0 | 14425.85 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 274091.15 |  |  | 288517 |  |  | 14425.85 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 4064 | C | USCSB2404024A |  | Butterfly Valves for Train B | 45385 | 45387 | 765 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 765 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 765 | [6 empty] | 688.5 |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4065 | C | USCSB2404025A |  | Lit 3: KPPTT1, KPPTT2, & KPPTT2 Exhaust Hard Duct CIP Material | 45385 | 45392 | 32064.57 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 32064.57 | 0 | 32064.57 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 4066 | C | USCSB2404026A |  | PP/EPDM PNU 627 DIA VLV 2: FLG | 45385 | 45385 | 1136.74 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1136.74 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1136.74 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4067 | C | USCSB2404027A |  | WWT Center Ring 4x2_20240402 (B Side) | 45385 | 45387 | 1193 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1193 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1193 |  |  | 178.95 |  |  |  | 178.95 |  |  |  | 178.95 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C019 | F21P1 Hitachi Interconnection | 4068 | C | USCSB2404028A |  | ME: KPCD03, KPCD13, KPCD17-19: CABLE PULLS | 45385 | 45387 | 31175 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 31175 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 31175 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4069 | C | USCSB2404029A |  | WWT UIS Manpower_20240329 | 45385 | 45387 | 595712 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 302240.16 | 0.50736 | 293471.84 | 0 | 293471.84 | 148097.6784 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 302240.16 | 89356.8 |  |  |  | 89356.8 |  |  |  | 89356.8 |  | 30224.016 |  | - | 30224.016 | - | 30224.016 | 30224.016 | 27201.6144
Non-TSMC Interconnection | Interconnection |  | USC23C019 | F21P1 Hitachi Interconnection | 4070 | C | USCSB2404030A |  | ME: KPCD10: CABLE PULL | 45385 | 45387 | 11598 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 11598 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 11598 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 4071 | C | USCSB2404031A |  | 帆宣計價單-美國tsmc CPVC 平接 | 45385 | 45393 | 8350 | [6 empty] | JHENGTONG INTERNATIONAL LIMITED | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 8350 | 0 | 8350 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 8350 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Triazole | Material | USC22C022 | F21P1 Triazole treatment system | 4072 | C | USCSB2404032A |  | copper tubing | 45385 |  | 17944 | [7 empty] | PR Approved | PO Processing |  |  | 0 | [11 empty] | 0 | 0 | 17944 | 0 | 17944 | 21532.8 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 8972 |  | - | 5383.2 | - | 5383.2 | 1794.4 | 0
Base-Build | UPW | Rosendin | USC24C008 | UPW B Side Project | 4073 | C | USCSB2404033A |  | REI UPW PCO 083 Contract Pricing Adjustment Phase 3, R0 | 45385 | 45394 | 1000000 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 500000 | [8 empty] | 500000 | 0 | 500000 | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4074 | C | USCSB2404035A |  | SO 151205 PO for HK Power system | 45385 | 45385 | 524.48 | [6 empty] | National Calibration Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 524.48 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 524.48 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Others | CCTV | Labor | USC22C013 | F21P1 QR Lab Security & CCTV | 4075 | C | USCSB2404036A |  | F21 P1 Gown Office IT Room speed gate engineering | 45385 | 45390 | 62180 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 59071 | 0.95 | 3109 | 0 | 3109 | 3109 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 59071 |  |  | 59071 |  | 0 |  | - | 0 | - | 0 | 0 | 3109
Hookup | Foundation |  | USC23C059 | F21P1 Foundation T&M | 4076 | C | USCSB2404037A |  | tools for HK PPL trade | 45385 | 45429 | 17001.18 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | [14 empty] | 17001.18 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 14173.78 |  | 2827.4 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4077 | C | USCSB2404038A | -01 | F21 B side 弘東人力 | 2024/4/3 NA 2024/8/2 | 2024/4/5 2024/4/23 2024/8/7 | 966500 | -10000 | 976500 | V |  |  |  | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved | R1: Detailed scope added in remark (6) R2: As per Johnny Wan to update the price. |  | Yi En Wong | [11 empty] | 679000 | 0.70253 | 287500 | 0 | 287500 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 325500 |  |  |  | 325500 |  |  | 177600 | 325500 | 177600 | 0 | 161900 | 161900 | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 4078 | C | USCSB2404039A |  | F21 P1 WRC Building Flow meters & Temp installation engineering of stack | 2024/4/3 2024/4/5 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Per PM's request to cancel this order as the vendor needs to update the quote. |  | Ta Wei Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C006 | F21P1 Slurry package | 4079 | C | USCSB2404040A |  | Rent 2 IR units for 2 months | 45385 | 45387 | 16768.8 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 15232.05 | 0.90836 | 1536.75 | 0 | 1536.75 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 10900 | 13072.76 | [5 empty] | 0 | 4332.05 | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4080 | C | USCSB2404041A |  | WWT Hardware_20240402 (B Side) | 45385 | 45392 | 9478.26 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 9478.26 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3799.92 |  | 0 |  | 4293.51 |  | 1384.83 | 1421.739 |  |  |  | 1421.739 |  |  |  | 1421.739 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Helix | USC24C006 | WWT B side Project | 4081 | C | USCSB2404042A |  | TSMC WWT Electric BOQ for FAB B side Rev3 | 45386 | 45399 | 7500000 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7072405 | 0.94299 | 427595 | 0 | 427595 | 1003092.16 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 714728 |  | 1850785 | 1125000 | 2280623 |  |  | 1125000 | 1423190 |  |  | 1125000 | 803079 | 188079.78 |  | - | 188079.78 | - | 188079.78 | 250773.04 | 188079.78
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4082 | C | USCSB2404043A |  | WWT PVC Glue & Primer_20240327_B side | 45386 | 45391 | 81064.8 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 81064.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 71840.76 |  | 9224.04 | 12159.72 |  |  |  | 12159.72 |  |  |  | 12159.72 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Trident | USC22C022 | F21P1 Triazole treatment system | 4083 | C | USCSB2404044A |  | Main CO Trident WSR | 45386 | 45394 | 59604.44 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | 0 | [11 empty] | 48711.73 | 0.81725 | 10892.71 | 0 | 10892.71 | 8768.1114 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 48711.73 | [6 empty] | 2435.5865 |  | - | 2435.5865 | - | 3896.9384 | 0 | 0
Base-Build | UPW | Material | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 4084 | C | USCSB2404045A |  | pH Sensor Accessories & Control Net Adapters from Organo | 45386 | 45387 | 410 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 410 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 410 | [6 empty] | 410 |  | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 4085 | C | USCSB2404047A |  | Pay the lien outsourcing company_Hart Land | 45386 | 45387 | 1714688.63 | [6 empty] | Hart Land Resources, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1714688.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 |  | 0 | 537427.29 | 537427.29 |  |  | 400000 | 400000 |  |  |  | 400000 |  |  |  | 377261.34 |  |  |  |  | - | 0 | - |  | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4086 | C | USCSB2404048A |  | WWT_ FAB LB2 / WRC L10_Acid/Chemical Area Safety Paint | 45386 | 45419 | 276676.69 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 276676.69 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 41501.5035 | 276676.69 |  |  | 41501.5035 |  |  |  | 41501.5035 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | USC24C007 | Low Voltage B Side Project | 4087 | C | USCSB2404049A |  | F21-P1_B-SIDE CCTV & ACCESS (not Include L20 HPM) | 45386 | 45392 | 2341425.36 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1888238.75 | 0.80645 | 453186.61 | 0 | 453186.61 | 792847.57 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 600319.78 | 351214 | 443009.3 |  |  | 257557 | 283884 |  |  | 257557 |  | 218033 | 221364.29 | 339661.38 | 218033 | - | 118927.19 | 118927.19 | 118927.19
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4088 | C | USCSB2404050A |  | Impact driver tool for HK exhaust team | 45386 | 45391 | 1834.8 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1143 | 0.62296 | 691.8 | 0 | 691.8 | 0 | 1143 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C013 | F21P1 QR Lab Security & CCTV | 4089 | C | USCSB2404051A |  | F21-P1_B-SIDE CCTV & ACCESS Fiber splicing and panel to panel Inner connection | 45386 | 45391 | 140156 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 136703.2 | 0.97536 | 3452.8 | 0 | 3452.8 | 65873.32 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 70078 | 67363 |  |  | 28032 |  |  |  | 28032 | 69340.2 | 21023.4 |  | - | 19621.84 | - | 18220.28 | 0 | 7007.8
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4090 | C | USCSB2404052A |  | 電料補齊.1 20240403 | 45386 | 45387 | 2119.1 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2119.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2119.1 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C046 | F21P1 ATS Interconnection | 4091 | C | USCSB2404053A |  | ATS: NO TOOL: CLEANROOM TAPE & NOTEBOOKS | 45387 | 45387 | 320.04 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 320.04 | 0 | 320.04 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 4092 | C | USCSB2404054A |  | Bulk Power Cables | 45387 | 45391 | 41554.75 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 41554.75 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 41554.75 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4093 | C | USCSB2404055A |  | WWT Welding machine | 45387 | 45391 | 70580 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 57169.8 | 0.81 | 13410.2 | 0 | 13410.2 | 17637.942 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 10587 | 14116 |  | 21879.8 | 10587 |  |  | 21174 | 10587 |  | 5399.37 |  | - | 5399.37 | - | 6839.202 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 4094 | C | USCSB2404057A |  | 16 remaining tools for AMAT interconnection, per TSMC need to order asap. | 45388 | 45391 | 74928.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 74923.6 | 0.99994 | 4.6 | 0 | 4.6 | 0 | [52 empty] | 0 | 0 | 0 |  | 74923.6 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 4095 | C | USCSB2404059A |  | 10 Sinfonia Manpower for AMHS | 45388 | 45399 | 327267.18 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | WO amount NTD 9,458,589 (@ 0.0346) | [13 empty] | 327267.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 327267.18 | [6 empty] | - |  | - |  | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4096 | C | USCSB2404060A |  | FAB A SDS, CDS, WCCS Pressure Test | 45388 | 45391 | 24562.5 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 18740 | 0.76295 | 5822.5 | 0 | 5822.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6895 |  |  | 6123.11 |  |  | 6935 | 6140.63 |  |  | 4910 | 5403.75 |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4097 | C | USCSB2404061A |  | KEMEA1 & KEPPA2 THHN PVC CABLE TRAYS | 45388 | 45394 | 10181.6 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 10181.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 10181.6 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4098 | C | USCSB2404062A | -01 | Wire for HK power trade | 2024/4/6 2024/4/13 | 2024/4/10 2024/04/23 | 29967.24 |  |  |  | V | V |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Previous item 2 not available and replaced by item 1 |  | Lisa Chan | [11 empty] | 29967.24 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 29967.24 | 0 | - | 0 | 0
Base-Build | TMAH | Equipment | USC21C011 | F21 TMAH System | 4099 | C | USCSB2404063A | -01 | Cast Iron Conduit box for TATUNG MOTOR WH0202FEJ SN14063611 in STRIPPER PAD | 45388 | 2024/4/29 2024/4/30 | 65 | [6 empty] | Tatung Company | PR Approved | PO Approved | R1: Change payment method to prepayment |  | 0 | [11 empty] | 65 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 65 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4100 | C | USCSB2404064A |  | WWT PVC Glue & Primer | 45388 | 45391 | 34257.6 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 34257.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 34257.6 |  |  | 5138.64 |  |  |  | 5138.64 |  |  |  | 5138.64 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4101 | C | USCSB2404065A |  | WWT Ball Valve_20240404(A&B Side) | 45388 | 45391 | 5239.84 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 5239.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 785.976 |  |  |  | 785.976 | 5239.84 |  |  | 785.976 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | USC24C007 | Low Voltage B Side Project | 4102 | C | USCSB2404066A |  | F21 P1 B side CCTV Power system | 45388 | 2024/4/10 2024/8/6 | 329623.97 | -17348.63 | 346972.6 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PO R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Kuan-Chung Su | [11 empty] | 329623.97 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 150204.32 |  |  | 52046 |  |  | 76610.86 | 52046 | 102808.79 |  |  | 34698 |  |  |  | - |  | - |  | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4103 | C | USCSB2404067A |  | For scissorlift safety, so people do not steal our lifts again. The other is for Pressure Testing. | 45388 | 45390 | 108.2 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 108.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 108.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4104 | C | USCSB2404068A | -01 | zip lock bag, tool hookup team | 45388 | 2024/4/9 2024/4/11 | 2418.99 | [5 empty] | V | Thomas Scientific Holdings LLC | PR Approved | PO Approved | R1: Revise ship-to address and instructions |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 2418.99 | 0 | 2418.99 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4105 | C | USCSB2404069A |  | Plug Lockout Box for all sysem, tool hookup team | 45389 | 45390 | 109.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 96.8 | 0.88402 | 12.7 | 0 | 12.7 | 0 | 96.8 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C021 | F21P1 KLA Interconnection | 4106 | C | USCSB2404070A |  | ME: MULTIPLE TOOLS: MANPOWER FOR APRIL 1ST - 26TH 2024 | 45390 | 45422 | 19820 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 6982.5 | 0.3523 | 12837.5 | 0 | 12837.5 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 6982.5 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4107 | C | USCSB2404072A | -01 | M4支援F21專案材料/BOX Open PO | 45391 | 2024/4/9 2024/4/23 | 6200000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | R1: change ship to location to Sky Harbor |  | Yi En Wong | [11 empty] | 233257.79 | 0.037622 | 5966742.21 | 0 | 5966742.21 | 6200000 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 233257.79 | - | 0 | 502175.68 | 0 | 6200000
Base-Build | Chemical | CRG | USC24C005 | Chemical & WCCS B Side Project | 4108 | C | USCSB2404073A |  | Invoice No. MICU-008(1/28/24-2/17/24 T&M) | 45391 | 45406 | 1291338.73 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | 0 | [11 empty] | 1291338.73 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1291338.73 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC24C005 | Chemical & WCCS B Side Project | 4109 | C | USCSB2404074A |  | Invoice No. MICU-009(021824-31624 T&M) | 45391 | 45407 | 2152918.88 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | 0 | [11 empty] | 2152918.88 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | 2152918.88 | 2152918.88 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4110 | C | USCSB2404075A |  | WWT PVC 10_Pipes_20240408 (B Side) | 45391 | 45393 | 12563 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 12563 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 12563 |  |  | 1884.45 |  |  |  | 1884.45 |  |  |  | 1884.45 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4111 | C | USCSB2404076A |  | WWT Fittings for 60604_20240408 (B Side) | 45391 | 45393 | 8076.18 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lisa Chan | [11 empty] | 8076.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 8076.18 |  |  | 1211.427 |  |  |  | 1211.427 |  |  |  | 1211.427 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4112 | C | USCSB2404078A |  | Cable management | 45391 | 45391 | 3042.12 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3042.12 | 1 | 0 | 0 | 0 | 0 | 3042.12 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4113 | C | USCSB2404079A |  | PVDF料補齊.1 20240408 | 45391 | 45392 | 28868.8 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Sian-Ning Pei | [11 empty] | 28868.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 28868.8 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4114 | C | USCSB2404080A |  | Bulk Lugs | 45391 | 45391 | 6289 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6289 | 1 | 0 | 83116.98 | -83116.98 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 5669 | [5 empty] | 620 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4115 | C | USCSB2404082A |  | Misc tools for HK Exhaust trade HL. For 300 tools | 45391 | 45408 | 3035.6 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 2773.1 | 0.91353 | 262.5 | 0 | 262.5 | 0 | 2773.1 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3935 | C | USCSB2404083A |  | WIRE 24WG 4C for MOULE CIP' UNITS | 45392 | 45456 | 1298.85 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1298.85 | 0 | 1298.85 | 0 | [73 empty] | - |  | 1298.85 |  | 0
Base-Build | VOC | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4117 | C | USCSB2404084A |  | Zoro - Clean and equipment maintenance | 45392 | 45391 | 104.16 | [6 empty] | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 94.69 | 0.90908 | 9.47 | 0 | 9.47 | 0 | [52 empty] | 0 | 0 | 0 |  | 94.69 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Housekeeping | USC21C003 | F21P1 UPW | 4118 | C | USCSB2404085A |  | Home Depot - Cleaning and equipment maintenance | 45392 | 45398 | 275.37 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | 0 | [11 empty] | 248.35 | 0.90188 | 27.02 | 0 | 27.02 | 0 | 248.35 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 41.3055 |  |  |  | 41.3055 |  |  |  | 41.3055 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4119 | C | USCSB2404086A |  | Equipment Share GENIE GR-20 for HK | 45392 | 45394 | 2365.7 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 2365.7 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 2365.7 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 4120 | C | USCSB2404088A |  | MICU CGS Manpower | 45392 | 45449 | 15232 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 15232 | 0 | 15232 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 4121 | C | USCSB2404089A |  | MICU RS Payroll Manpower | 45392 | 45397 | 2664 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 2664 | 0 | 2664 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Scaffolding | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3894 | C | USCSB2404090A |  | F21 EUV Bay 2 Scaffold | 45393 | 45427 | 159320 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 159320 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 159320 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 4123 | C | USCSB2404092A |  | Aluminum Clamps for Diffusion Tool ID#KDFAD1 | 45393 | 45397 | 354 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 354 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 354 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 4124 | C | USCSB2404093A |  | CVD1 Tool Interconnection Dividers for KCUVA1, KCUVA2, KCBDA6 | 45393 | 45392 | 3062 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3062 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 3062 | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 4125 | C | USCSB2404094A | -01 | Ball valves KCOLA1 KCOLA2 KCOLA3 | 45393 | 2024/4/11 2024/4/16 | 0 | -2589 | 2589 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | PO R1:PC no longer wants |  | Ta Wei Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4126 | C | USCSB2404095A |  | FAB A WWT and WWTD Observation (Change Order) | 45393 | 45397 | 2526 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 2526 | 0 | 2526 | 2526 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 378.9 |  |  |  | 378.9 |  |  |  | 378.9 |  | 2526 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4127 | C | USCSB2404096A |  | WRC WWT Observation (Change Order) | 45393 | 45395 | 10602 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 10602 | 0 | 10602 | 10602 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1590.3 |  |  |  | 1590.3 |  |  |  | 1590.3 |  | 5301 |  | - | 5301 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4128 | C | USCSB2404097A |  | 鐵管2" 90度彎曲加工 | 45393 | 45409 | 42375 | [6 empty] | Chukar SB&F LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 42375 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 41019 |  | 1356 | 42375 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4129 | C | USCSB2404098A |  | SDS VMB Pneumatic Spare Parts | 45393 | 45397 | 6450 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 6450 | 1 | 0 | 31500 | -31500 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6450 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4130 | C | USCSB2404099A |  | WWT Fittings_20240409 (B Side) | 45393 | 45397 | 4817.18 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 4817.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 4053.34 | 722.577 | 552.4 |  | 211.44 | 722.577 |  |  |  | 722.577 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4131 | C | USCSB2404100A |  | WWT Gasket_20240410 (A Side) | 45393 | 45394 | 838.74 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 838.74 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 838.74 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 4132 | C | USCSB2404101A |  | SUPPLY MATERIAL/ BUILD SHAFT WALL/ APPLY DRYWALL AND SHAFT WALL TO FRAMING/ TAPE AND SAND DRYWALL TO PAINT PREP FINISH/INSTAL | 45393 | 45405 | 68027 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 68027 | 0 | 68027 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C021 | F21P1 KLA Interconnection | 4133 | C | USCSB2404102A |  | ME: KPIN01: INSTALL GEX L20 TO L30 & CABLE PULLS | 45394 | 45412 | 17561.15 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 17561.15 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 17561.15 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 4134 | C | USCSB2404103A |  | CVD Labor | 45413 | 45413 | 9888 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 9888 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 9888 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4135 | C | USCSB2404104A |  | Strectch wrap for HK power trade | 45395 | 45407 | 546.84 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 546.84 | 1 | 0 | 23000 | -23000 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 546.84 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 3923 | C | USCSB2404107A |  | non materila provided by trade | 45395 | 45436 | 55105.01 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 55105.01 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 55105.01 | [6 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4137 | C | USCSB2404108A |  | NUUO Change Order: terminations | 45395 | 45419 | 56430 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 56430 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [7 empty] | 15390 |  | 41040 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4138 | C | USCSB2404109A |  | 2吋SUSBA 3280 ft購買 | 45397 | 45401 | 40737.6 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 40737.6 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 40737.6 |  |  | 40737.6 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4139 | C | USCSB2404110A |  | CPVC 料補齊.1 | 45397 | 45399 | 92838 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 92838 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 76428 |  |  |  | 16410 | 16410 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 4140 | C | USCSB2404111A |  | 6 Sinfonia Manpower for AMHS | 45397 | 45405 | 122015.73 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | This is NTD, not USD | [13 empty] | 122015.73 | 1 | 0 | 115900 | -115900 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 122015.73 | [6 empty] | - |  | - | 0 | 0
Base-Build | WWT | Helix | USC24C006 | WWT B side Project | 4141 | C | USCSB2404112A |  | TSMC WWT Electric BOQ for FAB B side Rev3 - part 2 | 45397 | 45400 | 2050000 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved | [14 empty] | 1176567 | 0.57394 | 873433 | 0 | 873433 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 307500 |  |  |  | 307500 |  |  |  | 307500 | 668108 | 0 |  | 508459 | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC24C006 | WWT B side Project | 4142 | C | USCSB2404113A |  | Megaunion 220V-400V變壓器 | 45397 | 45397 | 1653.08 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1653.08 | 0 | 1653.08 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC24C006 | WWT B side Project | 4143 | C | USCSB2404114A | -01 | MU11304N035-R1-MICU Area B E2 manpower support for electricity personnel | 2024/4/15 2024/5/29 | 2024/4/18 2024/6/3 | 263304.8 | 5500 | 257804.8 | V |  |  |  | Mega Union Technology Inc. | PR Approved | PO Approved | R1: As per engineer to update quote add tools fee. | [13 empty] | 105703.52 | 0.40145 | 157601.28 | 0 | 157601.28 | 263304.8 | [54 empty] | 0 |  | 0 | [13 empty] | 105703.52 | 52660.96 |  | - | 52660.96 | - | 52660.96 | 52660.96 | 52660.96
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4144 | C | USCSB2404115A |  | [PFD] CABLE TRAY FLOOR L10 | 2024/4/15 2024/4/19 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Per request from contractor via 4/17 email and confirmed with Johnny Wan, withdrawing it | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4145 | C | USCSB2404116A |  | F21 B side L30 Tray安裝工程 | 45397 | 45419 | 42220 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 40109 | 0.95 | 2111 | 0 | 2111 | 2111 | [54 empty] | 0 |  | 0 |  |  |  |  | 21110 | 33776 |  |  | 18999 |  |  |  |  | 6333 | 2111 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4146 | C | USCSB2404117A |  | WWT SUS 90Elbow_20240412 (B Side) | 45397 | 45397 | 1216.08 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 1216.08 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 1216.08 | 182.412 |  |  |  | 182.412 |  |  |  | 182.412 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 4147 | C | USCSB2404118A |  | Quality Material | 2024/4/15 2024/4/16 | 45401 | 314.66 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 278.25 | 0.88429 | 36.41 | 2699 | -2662.59 | 0 | 278.25 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 4148 | C | USCSB2404119A |  | E2 Team_CV 三合一施作工具請MIC協助報價/採購 | 2024/4/16 2024/4/23 | 45404 | 1256.94 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | PR R1:zero out first two items | [13 empty] | 1124.22 | 0.89441 | 132.72 | 0 | 132.72 | 0 | 1124.22 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4149 | C | USCSB2404120A |  | Tool for HK PPL trade Tunyi. For 50 tools | 45398 | 45407 | 97.18 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 88.34 | 0.90903 | 8.84 | 0 | 8.84 | 0 | 88.34 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 4150 | C | USCSB2404121A |  | SS Clamps to repair 14" SS Leaks | 45398 | 45401 | 1437.77 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 1437.77 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 1437.77 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4151 | C | USCSB2404122A |  | WWT pipe installation | 45398 | 45399 | 282500 | [6 empty] | Full Money Technology Ltd. | PR Approved | PO Approved | [14 empty] | 148000 | 0.52389 | 134500 | 0 | 134500 | 54760 | [54 empty] | 0 |  | 0 |  |  |  | 37000 | 42375 |  |  | 37000 | 42375 |  |  | 37000 | 42375 |  | 18500 | 37000 | - | 18500 | 30790 | 17760 | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4152 | C | USCSB2404123A |  | A business trip to TSMC in the US | 2024/4/16 2024/5/3 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:wrong requisition, should be UPW's scope under USC21C003, please cancel this and will re-issue | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 3965 | C | USCSB2404124A |  | KEMEL8 NEED TO INSTALL DAQ E-SENSOR AN CABLE ROUTING | 45398 | 45456 | 8372 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8372 | 0 | 8372 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 4154 | C | USCSB2404125A |  | WWT Stripper P-1231AA/AC insulation repair | 45398 | 45399 | 5055.97 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5055.97 | 0 | 5055.97 | 5055.97 | [54 empty] | 0 |  | 0 |  |  |  |  | 758.3955 |  |  |  | 758.3955 |  |  |  | 758.3955 |  | 5055.97 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 4155 | C | USCSB2404126A |  | Reduction Tees | 45398 | 45399 | 1464 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1464 | 8008 | -6544 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 4156 | C | USCSB2404127A |  | REI Change Orders | 45398 | 45401 | 114773.34 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 114773.34 | 0 | 114773.34 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4157 | C | USCSB2404128A |  | TOOL ID: KEPOL6 INSTALLATION OF CIP SENSORS TO DAQ AND TERMINICATIONS | 45398 |  | 731.5 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 731.5 | 0 | 731.5 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4158 | C | USCSB2404130A |  | TW trade 3rd 11 AMAT interconnect expert support from hook up team | 45399 | 45408 | 315000 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 283500 | 0.9 | 31500 | 0 | 31500 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 121500 |  | 162000 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4159 | C | USCSB2404131A |  | DRY ETC 1,2,3 MISC TOOLS ZIP TIES, AIRIC WIRE FERRULE CONNECTORS, MILWAUKEE DEEP CUT BAND SAW,&PVC CLEAR POLYETHYLENE | 2024/4/17 2024/10/3 | 2024/4/26 2024/10/3 | 807.85 | -24.97 | 832.82 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: Match to the actual expense | [13 empty] | 807.85 | 1 | 0 | 0 | 0 | 0 | 807.85 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4160 | C | USCSB2404132A |  | WWT B side Drain label | 45399 | 45400 | 2400.92 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 2376.27 | 0.98973 | 24.65 | 0 | 24.65 | 2400.92 | [54 empty] | 0 |  | 0 |  |  |  |  | 360.138 |  |  |  | 360.138 |  |  | 2376.27 | 360.138 |  | 2400.92 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4161 | C | USCSB2404133A |  | Ground bush for HK Power Luis for 60 tools | 45399 | 45425 | 6587.89 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 6587.89 | 1 | 0 | 1166000 | -1166000 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | 6587.89 | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4162 | C | USCSB2404134A | -01 | CHEM_L30 SDS VMB/ piping supports 240415020001_ (QT04350562-1) | 45399 | 2024/4/17 2024/4/18 | 1206.55 | -1386 | 2592.55 |  |  |  |  | Copper State Bolt & Nut Company | PR Approved | PO Approved | R1: Cancel Item No.2 as the spec cannot fulfill the requirements | [13 empty] | 1206.55 | 1 | 0 | 475000 | -475000 | 0 | [54 empty] | 0 |  | 0 |  | 1206.55 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC24C008 | UPW B Side Project | 4163 | C | USCSB2404135A |  | UPW-UMEC-extend GC for 2024 Jan - Feb | 45399 | 45451 | 889529 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 845053 | 0.95 | 44476 | 0 | 44476 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 845053 |  |  | 444764.5 |  | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | Heating Jacket | Labor | USC23C035 | TSMC F21 Heating Jacket Installation | 4164 | C | USCSB2404136A |  | Heating Jacket Manpower | 45399 | 45401 | 92000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | [14 empty] | 34500 | 0.375 | 57500 | 0 | 57500 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 11500 | [9 empty] | 11500 | 0 | 11500 | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4165 | C | USCSB2404137A |  | CPVC 料補齊.T2 | 45400 | 45400 | 11250 | [6 empty] | ZHENGTONG INTERNATIONAL LIMITED | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11250 | 0 | 11250 | 0 | [54 empty] | 0 |  | 0 | [8 empty] | 11250 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4004 | C | USCSB2404138A |  | CGS Global Support Onsite Manpower | 45400 | 45495 | 2726 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2726 | 0 | 2726 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4167 | C | USCSB2404139A |  | F21 B side電與訊號線購買01 | 45400 | 45419 | 23684.7 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 23684.7 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 23684.7 |  |  | 23684.7 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4168 | C | USCSB2404140A | -01 | WWT - RO Membrane Installation LB2 P1 A side | 2024/4/18 2024/4/26 | 2024/4/19 2024/4/26 | 0 | -13950.95 | 13950.95 |  |  |  | V | Marquis Construction Services LLC | PR Approved | PO Approved | Request to cancel by engineering team | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | CRG | USC24C005 | Chemical & WCCS B Side Project | 4169 | C | USCSB2404141A |  | Proposal TSMC-012 @ Chemical Piping_Side B_L10 CPVC_GN2_PFA_PULL BOX_RELATED SUPPORTS Installations | 45400 | 45405 | 610000 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 494100 | 0.81 | 115900 | 0 | 115900 | 30500 | [54 empty] | 0 |  | 0 | [8 empty] | 366000 |  |  | 494100 | 213500 |  | 30500 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4170 | C | USCSB2404142A |  | F21 B side L20 Tray安裝工程 | 45400 | 45401 | 294000 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 279300 | 0.95 | 14700 | 1960.05 | 12739.95 | 14700 | [54 empty] | 0 |  | 0 |  |  |  |  | 147000 | 235200 |  |  | 132300 |  |  |  |  | 44100 | 0 |  | - | 14700 | - | 0 | 0
Hookup | Barricade | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4171 | C | USCSB2404143A |  | ASML special barricade accessories | 45400 | 45407 | 3180 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3180 | 0 | 3180 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 4172 | C | USCSB2404144A | -01 | M0495 Foundation manufacture | 2024/4/18 2024/5/28 | 2024/4/25 2024/5/29 | 0 | -3733 | 3733 |  |  | V | V | Milling Machinery, Inc. | PR Approved | PO Approved | PR R1: Zero out the PR to release the budget per instructed | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 3942 | C | USCSB2404145A |  | Borrowed San Tan labor 3/11/24 - 4/12/24 | 45400 | 45423 | 30652.8 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 30652.8 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 30652.8 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 4174 | C | USCSB2404146A |  | KCOLA3 Olympia Project | 45401 | 45408 | 25013 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 25013 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 25013 | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4175 | C | USCSB2404147A |  | Amazon - UPW Clean up and equipment maintenance | 45401 | 45405 | 251.9 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 229 | 0.90909 | 22.9 | 0 | 22.9 | 0 | 229 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 4176 | C | USCSB2404148A |  | UPW-UMEC-COs for CE148 and 157 | 45401 | 45405 | 32584 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 28256 | 0.86717 | 4328 | 0 | 4328 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 28256 | 32584 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Housekeeping | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4177 | C | USCSB2404149A |  | Amazon - UPW Clean up and equipment maintenance | 2024/4/19 2024/4/30 | 45427 | 3556.74 | [6 empty] | A&A Materials | PR Approved | PO Approved | rpr r1: Original vendor is out of the rock necessary, found a new vendor information is now updated and entered. | [13 empty] | 3233.4 | 0.90909 | 323.34 | 0 | 323.34 | 0 | 3233.4 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC24C008 | UPW B Side Project | 4178 | C | USCSB2404150A |  | Outstanding Incentive Change Requests | 45401 | 45451 | 305092 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 305092 | 0 | 305092 | 0 | [54 empty] | 0 |  | 0 | [12 empty] | 152546 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 4179 | C | USCSB2404151A |  | PSAT L Bracket | 45401 | 45401 | 353.05 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 353.05 | 1 | 0 | 164823 | -164823 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 353.05 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC22C013 | F21P1 QR Lab Security & CCTV | 3949 | C | USCSB2404152A |  | VOC duct flange insulation | 2024/4/19 2024/7/9 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Replaced by Petrochem USCSB2407020A | [13 empty] | 0 | 1 | 0 | 3050 | -3050 | 0 | [56 empty] | 0 | [12 empty] | 24852 |  |  |  | - |  | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 4181 | C | USCSB2404153A | -01 | F21 P1 WRC Building Flow meters & Temp installation engineering of stack | 45402 | 2024/5/1 2024/5/4 | 35004 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved | R1: Discount applies to Item 005 instead of 002 | [13 empty] | 35004 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [15 empty] | 35004 | - |  | - | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4182 | C | USCSB2404154A | -01 | 垚鋐電力人力-點工人力(15人/3個月) | 45402 | 2024/4/26 2024/5/1 | 615000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | WO R1: Revise the Supplier Chinese Name on Construction Name from 堯宏 to 垚鋐 | [13 empty] | 0 | 0 | 615000 | 0 | 615000 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 183500 |  |  |  | 205000 |  |  |  | 205000 |  | 0 |  | - | 0 | 432869.37 | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4183 | C | USCSB2404155A |  | 信紘人力-點工人力(8人4個月) | 45402 | 45405 | 304000 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 152000 | 0.5 | 152000 | 0 | 152000 | 76000 | [54 empty] | 0 |  | 0 |  |  |  |  | 76000 |  |  |  | 76000 | 76000 |  |  | 76000 | 76000 | 76000 |  | - |  | 152000 | 0 | 0
Base-Build | Chemical | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4184 | C | USCSB2404156A |  | F21 P1B區 Chemical赴美管路工程施工by機具租賃 | 45402 | 45405 | 48048 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 24024 | 0.5 | 24024 | 0 | 24024 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 48048 |  |  |  |  | 8008 |  |  |  | 8008 | 0 |  | 8008 | 0 | 8008 | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4185 | C | USCSB2404157A |  | 捨得人力-點工人力(13人/2個月) | 2024/4/20 2024/4/25 | 2024/5/10 2024/7/9 | 208000 | [6 empty] | AUCAN INC | PR Approved | PO Approved | PR R1: D24N21001非內連線工程，且電力工程人力新增至13位已重新報價(不計入美國工資及費用)且廠商修改為捨得 WO R1: Completion date adjustment based on actual onboarding date | [13 empty] | 208000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 104000 |  |  |  | 104000 |  |  | 208000 |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C063 | F21P1-0423_H_T&M Hardware_MICU | 4186 | C | USCSB2404158A |  | Plastic_CV三合一物料儲存工具 | 2024/4/20 2024/4/25 | 45408 | 14445.8 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | PR R1:Per end user request, add one more item in this order. | [13 empty] | 13843.8 | 0.95833 | 602 | 0 | 602 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 13843.8 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 4187 | C | USCSB2404159A |  | KCBDA2 San Tan Fire Borrow | 45402 | 45405 | 2781 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 2781 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 2781 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 4188 | C | USCSB2404161A |  | WWT blower GIP gasket purchase | 45402 | 45401 | 1639.95 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 1639.95 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 1639.95 | 245.9925 |  |  |  | 245.9925 |  |  |  | 245.9925 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4189 | C | USCSB2404163A |  | Megaunion 元富 B side 8m 1 scope + 210 header +120 all | 45402 | 45408 | 859100 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 859100 | 0 | 859100 | 859100 | [54 empty] | 0 |  | 0 | [14 empty] | 171820 |  | - | 171820 | - | 171820 | 171820 | 171820
Base-Build | Chemical | CRG | USC24C005 | Chemical & WCCS B Side Project | 4190 | C | USCSB2404164A |  | Proposal TSMC-013 @ Chemical Piping_Side B_L30 CPVC_GN2_PFA_PULL BOX_RELATED SUPPORTS Installations | 45405 | 45416 | 2200000 | -100000 | 2300000 | V |  |  |  | CRG International | PR Approved | PO Approved | [14 empty] | 1034000 | 0.47 | 1166000 | 0 | 1166000 | 880000 | [54 empty] | 0 |  | 0 | [8 empty] | 660000 |  |  | 1034000 | 660000 |  | 770000 |  | - | 110000 | - | 0 | 0
Base-Build | Chemical | CRG | USC24C005 | Chemical & WCCS B Side Project | 4191 | C | USCSB2404165A |  | Proposal TSMC-014 @ Chemical Piping_Side B_L20 CPVC_GN2_PFA_PULL BOX_RELATED SUPPORTS Installations | 45405 | 45416 | 9500000 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 9025000 | 0.95 | 475000 | 0 | 475000 | 1900000 | [54 empty] | 0 |  | 0 | [8 empty] | 3800000 |  |  |  | 3800000 | 4940000 | 1425000 |  | 4085000 | 475000 | - | 0 | 0
Base-Build | WWT | Site Expense | USC24C006 | WWT B side Project | 4192 | C | USCSB2404166A |  | WIDOS WELDING MACH. | 45405 | 45407 | 95487 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 95487 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 95487 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3928 | C | USCSB2404167A |  | WIRE SECURITY CAGE/ COLLAPSIBLE WIRE CONTAINER WITH CASTERS | 45405 | 45419 | 12555.53 | [6 empty] | Global Equipment Company Inc. | PR Approved | PO Approved | [14 empty] | 12555.53 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 11059.75 |  | 1495.78 | [10 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC24C009 | F21P1 Nova Interconnection | 4194 | C | USCSB2404168A |  | NOVA: KEPRM6-8: PFA CLEAR TUBE FOR SIGNAL CABLE. | 45405 | 45406 | 1825 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 1825 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 1825 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C059 | F21P1 Foundation T&M | 4195 | C | USCSB2404170A |  | 3 in 1 project for HK Power system | 45405 | 45406 | 31192.78 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 31192.78 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 765.8 |  |  | 0 |  | 30426.98 | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 4196 | C | USCSB2404171A |  | Chemical for commissioning flush | 45405 | 45405 | 1737.6 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved | [14 empty] | 1737.6 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 1737.6 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4197 | C | USCSB2404172A |  | WWT blower GIP&SUS material | 45405 | 45406 | 38491.25 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 38476.62 | 0.99962 | 14.63 | 0 | 14.63 | 8637.4926 | [54 empty] | 0 |  | 0 |  |  |  |  | 5773.6875 | 25404.39 |  |  | 5773.6875 |  |  | 13072.23 | 5773.6875 |  | 5080.878 |  | - | 3556.6146 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 4198 | C | USCSB2404173A |  | CMP: KMOPA5: ROUTE PFA LINE TO CPVC DOUBLE CONTAINMENT PIPE. ROUTE TO DIO3 GENERATOR. | 45405 | 45412 | 8816 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 8816 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [7 empty] | 8816 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4199 | C | USCSB2404174A |  | CHEM_Waste System Fab L20 PVDF PIPE USED | 45405 | 45405 | 1960.05 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1960.05 | 0 | 1960.05 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 1960.05 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C032 | F21_AZQR_Hookup_ Interconnection | 4200 | C | USCSB2404175A |  | QR LAB: KXPTR1 & KXPTR2: C/O TUBING REWORK FOR GAS INSTALL | 45405 | 45412 | 36481.28 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 36481.28 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 36481.28 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 4201 | C | USCSB2404176A |  | WWT-A side EOR CA service for WRC and FAB | 45405 | 45413 | 254073 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 254073 | 0 | 254073 | 254073 | [54 empty] | 0 |  | 0 |  |  |  |  | 38110.95 |  |  |  | 38110.95 |  |  |  | 38110.95 |  | 50814.6 |  | - | 50814.6 | - | 50814.6 | 50814.6 | 50814.6
Base-Build | UPW | Labor | USC23C054 | UPW Change Order | 4202 | C | USCSB2404177A | -01 | UPW-B side CA/observation service | 45405 | 2024/5/22 2024/6/10 | 112800 | [6 empty] | M Consultants, LLC BDA M-Engineering | PR Approved | PO Approved | R1: Change terms based on the consensus MICU and the vendor have | [13 empty] | 65708 | 0.58252 | 47092 | 0 | 47092 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 49604 | 0 | 16104 | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4203 | C | USCSB2404178A |  | Safety Filter for LSR ACF | 45406 | 45405 | 856.8 | [6 empty] | ServAPure Company | PR Approved | PO Approved | [14 empty] | 856.8 | 1 | 0 | 29861.78 | -29861.78 | 856.8 | 856.8 | [53 empty] | 0 |  | 0 | [14 empty] | 856.8 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4204 | C | USCSB2404179A |  | WWT Fittings for 60606_20240423 (A Side) | 45406 | 45411 | 20160.61 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 20160.61 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 20160.61 | 3024.0915 |  |  |  | 3024.0915 |  |  |  | 3024.0915 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4205 | C | USCSB2404180A |  | Amazon - Chemical Team | 45406 | 45406 | 2428.27 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 2230.99 | 0.91876 | 197.28 | 0 | 197.28 | 0 | 2230.99 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C021 | F21P1 KLA Interconnection | 4206 | C | USCSB2404181A |  | ME: KKDB02: 10" EXHAUST DUCTING INSTALLATION | 45406 | 45411 | 20797.71 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 20797.71 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 20797.71 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4207 | C | USCSB2404182A |  | L30 HPM Y line divider fixed (A side) | 45406 | 45407 | 89754 | [6 empty] | JY TECHS INC. | PR Approved | PO Approved | [14 empty] | 89754 | 1 | 0 | 0 | 0 | 89754 | [54 empty] | 0 |  | 0 | [9 empty] | 89754 |  |  |  |  | 89754 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4208 | C | USCSB2404183A |  | Chemical FAB A and Lorry CA and Observation | 45406 | 45419 | 272520 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 272520 | 92648 | 179872 | 272520 | [54 empty] | 0 |  | 0 | [14 empty] | 272520 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4209 | C | USCSB2404184A |  | FAB B Chemical Electrical Permit + CA | 45406 | 45408 | 85680 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 56380 | 0.65803 | 29300 | 0 | 29300 | 85680 | [54 empty] | 0 |  | 0 | [5 empty] | 20790 | [5 empty] | 35590 |  |  | 85680 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 4210 | C | USCSB2404185A |  | FAB A UPW Observation (LB1 to L30) | 45407 | 45413 | 19800 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 19800 | 0 | 19800 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 5900 | 0 | 0
Base-Build | Chemical | Rosendin | USC24C005 | Chemical & WCCS B Side Project | 4211 | C | USCSB2404187A |  | REI Proposed Change order | 45407 | 45408 | 2495333.54 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 2495333.54 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 2495333.54 | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C046 | F21P1 ATS Interconnection | 4212 | C | USCSB2404188A |  | ATS: NO TOOL: CLEANROOM NOTEBOOKS | 45407 | 45411 | 154.8 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 154.8 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 154.8 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC24C006 | WWT B side Project | 4213 | C | USCSB2404189A |  | WWT - Install (166) Embedded Pipe on B-Side for Litho Drains | 45407 | 45412 | 198642 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 188709.9 | 0.95 | 9932.1 | 0 | 9932.1 | 27910.2685 | [54 empty] | 0 |  | 0 |  |  |  |  | 29796.3 |  |  |  | 29796.3 | 164178.05 |  |  | 29796.3 | 24531.85 | 8208.9025 |  | - | 8208.9025 | - | 11492.4635 | 0 | 0
Base-Build | WWT | Labor | USC24C006 | WWT B side Project | 4214 | C | USCSB2404190A |  | WWT - B-Side CS Tank FRP Flange Coating and Spool Interconnections | 45407 | 45419 | 234118.03 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 233935.16 | 0.99922 | 182.87 | 0 | 182.87 | 2316.6969 | [54 empty] | 0 |  | 0 |  |  |  |  | 35117.7045 | 46651.04 |  |  | 35117.7045 | 185018.65 |  |  | 35117.7045 | 2265.47 | 0 |  | - | 0 | - | 0 | 0 | 2316.6969
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4215 | C | USCSB2404191A |  | Tray canle wire cut for HK Power system. Tool id KPE604-S | 45407 | 45407 | 2000 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1750 | 0.875 | 250 | 0 | 250 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 500 |  |  | 0 |  | 1250 | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C006 | F21P1 Slurry package | 4216 | C | USCSB2404193A |  | Trailer 40 Access Control System Installation | 45407 |  | 0 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved | PR R1: As Per Eric to cancel this PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C006 | F21P1 Slurry package | 4217 | C | USCSB2404194A |  | Trailer 40 Electrified Lock Work | 45407 |  | 0 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved | PR R1: As Per Eric to cancel this PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4218 | C | USCSB2404195A |  | WWT 1-2 Bolts_20240424 (A&B Side) | 45407 | 45407 | 1115.18 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1115.18 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 1012.59 |  |  | 167.277 |  |  |  | 167.277 | 102.59 |  |  | 167.277 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4219 | C | USCSB2404196A |  | WWT PVC_PVDF FittingsPipes (B Side)_20240424 | 45408 | 45416 | 137159.87 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 137159.87 | 1 | 0 | 0 | 0 | 2678.7814 | [54 empty] | 0 |  | 0 |  |  |  |  | 20573.9805 | 123302.26 |  | 10636.81 | 20573.9805 |  |  | 3220.8 | 20573.9805 |  | 0 |  | - | 0 | - | 0 | 0 | 2678.7814
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4220 | C | USCSB2404197A |  | WWT Fittings (A Side)_Ryan Herco_20240424 | 45408 | 45412 | 9099.81 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 9099.81 | 1 | 0 | 3658 | -3658 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 1364.9715 |  |  |  | 1364.9715 | 9099.81 |  |  | 1364.9715 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC24C008 | UPW B Side Project | 4221 | C | USCSB2404198A | -02 | Materials for Train 2 from Taiwan Supplier | 45408 | 2024/4/30 2024/5/6 2024/5/14 | 104387.04 | -42.46 | 104429.5 |  | V |  |  | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | R1: Items 8, 9, 10 out of stock R2: Item 006 is out of stock | [13 empty] | 104387.04 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 104387.04 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C060 | F21 CT Local Scrubber Interconnection | 3957 | C | USCSB2404199A |  | PCA-CT: KCASA1, KCSCN2, KCOXA1, KCOXN8, KCOXN1-2, KCOXN5-6, KCSMA3, KCSCN3-4: WIRES | 45408 | 45413 | 1250 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1250 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 1250 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 4223 | C | USCSB2404200A | -01 | WWT-ammonia 1000 ppm standards solution for stripper | 45408 | 2024/4/26 2024/5/17 | 0 | -147.3 | 147.3 |  |  |  |  | Midland Scientific, Inc. | PR Approved | PO Approved | R1: Change supplier | [13 empty] | 136.02 | 1 | -136.02 | 0 | -136.02 | 0 | 136.02 | [53 empty] | 0 |  | 0 | [12 empty] | 22.1 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 4018 | C | USCSB2404200B |  | WWT-ammonia 1000 ppm standards solution for stripper | 45408 | 45433 | 78.5 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 58.5 | 0.74522 | 20 | 0 | 20 | 14.625 | [62 empty] | 58.5 | [8 empty] | 14.625 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | UMEC | USC24C006 | WWT B side Project | 4225 | C | USCSB2404201A |  | WWT - LSR(I)(A side) | 45408 | 45415 | 245895 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 233600 | 0.95 | 12295 | 0 | 12295 | 11680 | [54 empty] | 0 |  | 0 |  |  |  |  | 36884.25 |  |  |  | 36884.25 | 233600 |  |  | 36884.25 |  | 0 |  | - | 0 | - | 0 | 0 | 11680
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4226 | C | USCSB2404203A |  | DRY ETC MATERIAL ORDER FOR ETC 1,2,3 from Amazon | 2024/4/26 2024/9/26 | 2024/4/29 2024/9/26 | 893.05 | -101.2 | 994.25 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: Match to the actual expense (See packing slip) | [13 empty] | 893.05 | 1 | 0 | 9001.2 | -9001.2 | 0 | 893.05 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4227 | C | USCSB2404204A |  | WWT DS & LCB (B side material) | 45408 | 45411 | 24411 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 24411 | 0 | 24411 | 29293.2 | [54 empty] | 0 |  | 0 |  |  |  |  | 3661.65 |  |  |  | 3661.65 |  |  |  | 3661.65 |  | 12205.5 |  | - | 7323.3 | - | 7323.3 | 2441.1 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3962 | C | USCSB2404205A | -01 | WWT PP PN10 D140 Pipes_20240425 (B Side) | 2024/4/27 2024/5/15 | 2024/4/30 2024/5/15 | 0 | -21853.2 | 21853.2 | V |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Items: As per engineer Cindy to cancel this PR | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4023 | C | USCSB2404206A |  | May mid may- mid June Labor | 45409 | 45459 | 231840 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 231840 | 1 | 0 | 58327.5 | -58327.5 | 0 | [66 empty] | 197430 |  |  |  | 34410 |  |  | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3963 | C | USCSB2404212A |  | WWT PVC Glue & Primer_20240429 | 45411 | 45412 | 30690 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 30690 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 2788.25 |  | 27901.75 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3964 | C | USCSB2404213A |  | WWT Fittings_ZeWei_20240426 (B Side) | 45412 |  | 1564.04 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 1395.26 | 0.89209 | 168.78 | 0 | 168.78 | 153.4786 | [54 empty] | 0 |  | 0 | [5 empty] | 1395.26 | [8 empty] | 153.4786 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | MIMO/Rigging | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 3965 | C | USCSB2404214A |  | CGS move in labor support | 45412 | 45414 | 100000 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 56954.87 | 0.56955 | 43045.13 | 8663.34 | 34381.79 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 37579.54 | 0 | 19375.33 | - | 0 | 12191.55 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3966 | C | USCSB2404215A |  | WWT the Drain Remaining Pipes_20240426 (B Side) | 45412 | 45414 | 131920.9 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 131920.9 | 1 | 0 | 26549.6 | -26549.6 | 3834.543 | [54 empty] | 0 |  | 0 | [5 empty] | 127818.1 | [5 empty] | 4102.8 |  |  | 0 |  | - | 0 | - | 0 | 0 | 3834.543
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3967 | C | USCSB2404216A |  | WWT Ball Valve&Cap_20240426 (B Side) | 45412 | 45413 | 24493.17 | [6 empty] | Supertung Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 24493.17 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 12246 | [5 empty] | 12247.17 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 3968 | C | USCSB2404217A |  | CMP: KMOPA5: 3/8" FITTINGS | 45412 | 45412 | 10.43 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 10.43 | 1 | 0 | 46468.8 | -46468.8 | 0 | [54 empty] | 0 |  | 0 |  | 10.43 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C019 | F21P1 Hitachi Interconnection | 3969 | C | USCSB2404218A |  | ME: KPCD15: CABLE PULLS | 45412 | 45413 | 9847 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 9847 | 1 | 0 | 8821.67 | -8821.67 | 0 | [54 empty] | 0 |  | 0 | [7 empty] | 9847 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 3970 | C | USCSB2404219A |  | F21 AMAT PVD DI MAX *37 SET | 45412 | 45427 | 92648 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 92648 | 18856.6 | 73791.4 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 3971 | C | USCSB2404220A |  | WWT Clamps_20240429 (A Side) | 45412 | 45412 | 1433.95 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 1433.95 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 1433.95 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3972 | C | USCSB2404221A |  | Cord connector for HK Power system for 10 tools | 45412 | 45422 | 12427.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 6414.95 | 0.51619 | 6012.55 | 0 | 6012.55 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 808.94 |  |  | 0 |  | 5606.01 | 0 | 6012.55 | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 3973 | C | USCSB2404222A |  | CHEM_WCCS SUS project_hardware 240415020003_ (01-00166939) | 45412 | 45412 | 12824.48 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved | [14 empty] | 12824.48 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 12824.48 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4024 | C | USCSB2404223A |  | Ferrules crimps for HK Power Luis | 45412 | 45426 | 2270.99 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 2270.99 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [16 empty] | 2270.99 |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3974 | C | USCSB2404224A |  | WWT Fittings for Remaining Fittings for Drain_20240429 (B Side) | 45412 | 45413 | 9339.11 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 9339.11 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 6667.13 |  | 1432.92 |  | 1239.06 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3975 | C | USCSB2404225A |  | WWT Fittings for O3_20240429 (B Side) | 45412 | 45413 | 25213.35 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 25213.35 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 6737.48 |  | 18475.87 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 3976 | C | USCSB2404226A | -01 | P1B區Chemical SP2人力支援SP1施工 (SUS 12人/3月，CPVC 11人/1.5月) | 2024/4/30 2024/6/13 | 2024/5/8 2024/6/13 | 0 | -375221 | 375221 |  |  |  | V | Trusval Technology CO., LTD. | PR Approved | PO Approved | R1: As per PM Johnny to cancel this PR ,due to 2次配人力仍由TSMC所調配，相關費用會由TSMC直接與MIC對接，不需要透過信紘. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 150088.4 |  |  |  | 112566.3 |  |  |  | 112566.3 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3977 | C | USCSB2405001A |  | WWT Diaphragm_20240430 (B Side) | 45413 | 45413 | 3173.32 | [6 empty] | Hwa Chi Technology Co., Ltd | PR Approved | PO Approved | [14 empty] | 3173.32 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 3173.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3978 | C | USCSB2405002A |  | WWT 2-1/2" & 4-5/8" Clamps (B Side)_20240429 | 45413 | 45413 | 1292.9 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1292.9 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 1292.9 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 3979 | C | USCSB2405003A |  | BIM and Valves for MAU Bypass | 45413 | 45413 | 1314.25 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 1314.25 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 1314.25 | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 3980 | C | USCSB2405004A |  | KCOLA3 Olympia Project Material | 45413 | 45416 | 3106 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 3106 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 3106 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC24C008 | UPW B Side Project | 3981 | C | USCSB2405005A |  | FAB LB2 MAU Bypass | 45413 | 45416 | 73158 | 5062 | 78220 | V |  |  |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 65842 | 0.9 | 7316 | 0 | 7316 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 65842 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3982 | C | USCSB2405006A |  | WWT 4-5/8" Clamps_20240429 (B Side) | 45413 | 45415 | 7605 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 7605 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 7605 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 4018 | C | USCSB2405007A |  | CMP: KMRPE4: CAP 3/4" SWG | 45414 | 45419 | 25.2 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 25.2 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 25.2 | [10 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C019 | F21P1 Hitachi Interconnection | 4019 | C | USCSB2405008A |  | ME: KPCD15: RMF MODIFICATIONS. | 45414 | 45420 | 1942 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 1942 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 1942 | [6 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 3983 | C | USCSB2405009A |  | WWT Center Ring 3x1.5_20240501 (B Side) | 45414 | 45419 | 3978 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | [14 empty] | 3978 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 3978 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 3984 | C | USCSB2405010A |  | Washer nut and bolt for HK Power trade for 200 tools | 45415 | 45415 | 740 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 740 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 740 |  |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4022 | C | USCSB2405011A |  | Cable connector and outlet plate for HK Power Trade | 45415 | 45447 | 15084.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 2000.46 | 0.13262 | 13083.74 | 0 | 13083.74 | 0 | [56 empty] | 0 | [16 empty] | 2000.46 |  | 4082.54 |  | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 3985 | C | USCSB2405012A |  | WWT-UMEC-2023Veteran's day_Overtime | 45415 | 45425 | 10654 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 10121 | 0.94997 | 533 | 0 | 533 | 506.05 | [54 empty] | 0 |  | 0 |  |  |  | 10121 | [10 empty] | 0 |  | - | 0 | - | 0 | 0 | 506.05
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 4024 | C | USCSB2405013A |  | Kaoten Foxboro Calibration A Side | 45415 | 45433 | 11135 | [6 empty] | Kaoten Scientific Co., Ltd | PR Approved | PO Approved | [14 empty] | 11135 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 11135 |  |  |  |  | - |  | - |  | 0
Base-Build | CCTV | NUUO | USC21C013 | F21P1 AMC THC Monitoring System | 3986 | C | USCSB2405014A |  | F21 P1 parking gates installation-(1/11 ) | 45415 | 45427 | 58327.5 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 58327.5 | 0 | 58327.5 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C019 | AMC monitor 595T0 | 3987 | C | USCSB2405015A |  | F21 P1 parking gates installation-(2/11) | 45415 | 45427 | 2803.5 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2803.5 | 0 | 2803.5 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC21C008 | F21P1 CCTV & Security | 3988 | C | USCSB2405016A |  | F21 P1 parking gates installation-(3/11) | 45415 | 2024/5/15 2024/8/6 | 60187.83 | -1136.87 | 61324.7 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PO R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. | [13 empty] | 58676.94 | 0.9749 | 1510.89 | 0 | 1510.89 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 58676.94 | [6 empty] | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C001 | F21 P1 Office and WH Security and CCTV | 3989 | C | USCSB2405017A |  | F21 P1 parking gates installation-(4/11) | 45415 | 45427 | 8663.34 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8663.34 | 0 | 8663.34 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC21C012 | F21 Barcode RFID System | 3990 | C | USCSB2405018A |  | F21 P1 parking gates installation-(5/11) | 45415 | 45427 | 26549.6 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 26549.6 | 0 | 26549.6 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C009 | F21P1 230kV MTR Oil and Drain Pipe work | 3991 | C | USCSB2405019A |  | F21 P1 parking gates installation-(6/11) | 45415 | 45427 | 2996.7 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2996.7 | 0 | 2996.7 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3992 | C | USCSB2405020A |  | F21 P1 parking gates installation-(7/11) | 45415 | 45427 | 46468.8 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 46468.8 | 0 | 46468.8 | 44145.36 | [54 empty] | 0 |  | 0 | [14 empty] | 44145.36 |  | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C035 | CAP_A_90772_F21 Phone call base build and Liquid penetrant testing system | 3993 | C | USCSB2405021A |  | F21 P1 parking gates installation-(8/11) | 45415 | 45427 | 10686.2 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10686.2 | 0 | 10686.2 | 10151.89 | [54 empty] | 0 |  | 0 | [14 empty] | 10151.89 |  | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC21C007 | F21P1 VOC package （Installation ) | 3994 | C | USCSB2405022A |  | F21 P1 parking gates installation-(9/11) | 45415 | 45427 | 18856.6 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 18856.6 | 0 | 18856.6 | 17913.77 | [54 empty] | 0 |  | 0 | [14 empty] | 17913.77 |  | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 3995 | C | USCSB2405023A |  | F21 P1 parking gates installation-(10/11) | 45415 | 45427 | 74783.1 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 74783.1 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 74783.1 | [6 empty] | - |  | - | 0 | 0
Base-Build | CCTV | NUUO | USC22C013 | F21P1 QR Lab Security & CCTV | 3996 | C | USCSB2405024A |  | F21 P1 parking gates installation-(11/11) | 45415 | 45427 | 63539.96 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 63539.96 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 63539.96 | [6 empty] | - |  | - | 0 | 0
Hookup | Foundation | Material | USC23C059 | F21P1 Foundation T&M | 4036 | C | USCSB2405025A |  | 3 in 1 project Orbum 1CPDH WP 1GPLSTC HORZ DEV CVR | 45416 | 45421 | 1476.81 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1476.81 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [16 empty] | 1476.81 |  | - |  | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4037 | C | USCSB2405027A |  | P1A additional foundations installation for KMVX81 and KMVIE1 | 45416 | 45426 | 43646.6 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 43646.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 43646.6 | [8 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 4038 | C | USCSB2405028A |  | DI-max greenberry KSANA1&KSRHA1 | 45416 | 45441 | 6752 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6752 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 6752 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C032 | F21_AZQR_Hookup_ Interconnection | 4068 | C | USCSB2405029A |  | QR: KXNP01: CABLE TRAY INSTALL | 45418 | 45446 | 5308 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 5308 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 5308 | [8 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4039 | C | USCSB2405030A |  | WWT 5_8 Bolt_20240506 (B Side) | 45419 | 45419 | 1105.2 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1105.2 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 |  | 1105.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC24C008 | UPW B Side Project | 4040 | C | USCSB2405031A |  | UPW Foxboro A2U | 45419 | 45426 | 183582 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved | [14 empty] | 36716.4 | 0.2 | 146865.6 | 0 | 146865.6 | 0 | [56 empty] | 36716.4 | [16 empty] | - |  | - |  | 0
Base-Build | Chemical | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4041 | C | USCSB2405032A |  | SDS L3 CES5003-2.5 Drain revise (Urgent) | 45419 | 45425 | 12000 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved | [14 empty] | 10800 | 0.9 | 1200 | 0 | 1200 | 12000 | [56 empty] | 0 | [5 empty] | 10800 | [8 empty] | 12000 |  | - |  | - |  | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4042 | C | USCSB2405033A |  | Forklift for HK item 11329770 | 45419 | 45420 | 402.81 | [6 empty] | United Rentals | PR Approved | PO Approved | [14 empty] | 402.81 | 1 | 0 | 94059 | -94059 | 0 | [56 empty] | 0 | [11 empty] | 402.81 |  |  |  |  | - |  | - |  | 0
Base-Build | Chemical | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4043 | C | USCSB2405034A |  | SDS L3 Add one VMB | 45419 | 45426 | 60000 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved | [14 empty] | 54000 | 0.9 | 6000 | 0 | 6000 | 60000 | [56 empty] | 0 | [9 empty] | 54000 |  |  |  |  | 60000 |  | - |  | - |  | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4044 | C | USCSB2405035A |  | Temporary chemical leak kit_20/45-10 | 45419 | 45423 | 7194.11 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7194.11 | 0 | 7194.11 | 7194.11 | [56 empty] | 0 | [14 empty] | 7194.11 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Triazole | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4045 | C | USCSB2405036A |  | Triazole Change Order | 45419 | 45428 | 109566.81 | [6 empty] | 2000 GOLD LLC | PR Approved | PO Approved | [14 empty] | 109566.81 | 1 | 0 | 333350 | -333350 | 0 | [56 empty] | 0 |  |  |  | 109566.81 | [10 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4046 | C | USCSB2405037A |  | CHEM_ panel design_20240506_ (12004) | 45419 | 45419 | 1980 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | [14 empty] | 1980 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 1980 | 1980 | [7 empty] | - |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4047 | C | USCSB2405038A |  | CHEM_WCCS WLS CDA/ GN2 _HF1000-10PC2FSM CV=29.0*2ea | 45419 | 45419 | 3054.12 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 3054.12 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 3054.12 |  |  | 3054.12 | [7 empty] | - |  | - |  | 0
Base-Build | Chemical | Labor | USC21C006 | F21P1 Slurry package | 4048 | C | USCSB2405039A |  | CDS B side move in Night shift | 45420 | 45430 | 16900 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 8450 | 0.5 | 8450 | 0 | 8450 | 0 | [56 empty] | 0 | [8 empty] | 16900 | 8450 | [6 empty] | - |  | - |  | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 4049 | C | USCSB2405040A |  | Materials for Train 2 from Taiwan Supplier | 45420 | 45422 | 3653.67 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 3653.67 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 3653.67 | [10 empty] | - |  | - |  | 0
Base-Build | Chemical | Labor | USC24C005 | Chemical & WCCS B Side Project | 4050 | C | USCSB2405041A |  | F21 B side L20/L10 UPW 工程發包_MornstAir | 45420 | 45425 | 700000 | [6 empty] | MornstAir Inc. | PR Approved | PO Approved | [14 empty] | 665000 | 0.95 | 35000 | 0 | 35000 | 35000 | [56 empty] | 0 | [8 empty] | 350000 |  |  |  | 315000 |  |  | 497600 | 167400 | 35000 | - |  | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4051 | C | USCSB2405043A |  | lock up the Scissorlift, Tool hookup team for 500 tools | 45420 | 45420 | 642.05 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 642.05 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 642.05 | [6 empty] | - |  | - |  | 0
Base-Build | UPW | Material | USC24C008 | UPW B Side Project | 4068 | C | USCSB2405044A |  | Sticker | 45420 | 45427 | 2278.51 | [6 empty] | StickerYou Inc. | PR Approved | PO Approved | [14 empty] | 2141.99 | 0.94008 | 136.52 | 0 | 136.52 | 0 | 2141.99 | [55 empty] | 0 | [16 empty] | - |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4052 | C | USCSB2405045A |  | CHEM_WCCS _hardware for standing by materials (TCELC) | 45420 | 45422 | 8360 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved | [14 empty] | 8360 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 4560 |  |  | 8360 | 3800 | [6 empty] | - |  | - |  | 0
Others | AMHS | Material | USC23C015 | F21P1 AMHS Wiring Work Outline | 4053 | C | USCSB2405046A |  | 12,000 Feet 1 AWG 1/C PSP Cable | 45420 | 45422 | 36050.08 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 36050.08 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [16 empty] | 36050.08 |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4054 | C | USCSB2405047A |  | WWT: OPEN PO II | 45420 | 45428 | 70000 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 69485.71 | 0.99265 | 514.29 | 0 | 514.29 | 712.8 | [56 empty] | 0 | [9 empty] | 720 |  | 54271.88 |  | 11017.49 | 712.8 | 3476.34 | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4055 | C | USCSB2405048A |  | HK Scaffold services | 45420 | 45428 | 209376.5 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 127720 | 0.61 | 81656.5 | 0 | 81656.5 | 0 | [56 empty] | 0 | [7 empty] | 127720 | [8 empty] | - |  | - |  | 0
Others | 光阻櫃 | Equipment | USC24C007 | Low Voltage B Side Project | 4056 | C | USCSB2405049A |  | F21-P1_B-Side mask room exhaust hookup | 45420 | 45425 | 107719.82 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 107719.82 | 0 | 107719.82 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 4057 | C | USCSB2405050A |  | Ball valves KCOLA1 KCOLA2 KCOLA3 | 45420 | 45421 | 2589 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 2589 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 2589 | [10 empty] | - |  | - |  | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4058 | C | USCSB2405052A |  | V-Belt K-30 for HK Exhaust trade for 20 tools | 45420 | 45429 | 2094.51 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1771.33 | 0.8457 | 323.18 | 0 | 323.18 | 0 | 1771.33 | [55 empty] | 0 | [16 empty] | - |  | - |  | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 4059 | C | USCSB2405053A |  | 5191-8121 vials and 5191-8151 caps for LS_MS/MS TMAH room device | 2024/5/8 2024/9/10 2024/10/4 | 2024/5/9 2024/9/10 2024/10/4 | 0 | -177.55 | 177.55 | V |  |  |  | Agilent Technologies, Inc. | PR Approved | PO Approved | po r1:quote number changed | [13 empty] | 0 | 1 | 0 | 0 | 0 | 177.55 | [56 empty] | 0 | [14 empty] | 177.55 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4061 | C | USCSB2405056A |  | CHEM_WCCS _Consumable hardware A_QT04357379-1 | 45421 | 45422 | 36379 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 36379 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [8 empty] | 36379 | 36379 | [6 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4062 | C | USCSB2405057A |  | WWT 1-2 Bolts_20240508 (B Side) | 45421 | 45425 | 1057.43 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1057.43 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 |  |  |  | 1057.43 | [10 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4063 | C | USCSB2405058A |  | WWT Drain PP_20240508 (B Side) | 45421 | 45434 | 299445.93 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 299445.93 | 0 | 299445.93 | 299445.93 | [56 empty] | 0 | [14 empty] | 59889.186 |  | - | 59889.186 | - | 59889.186 | 59889.186 | 59889.186
Non-TSMC Interconnection | Interconnection |  | USC24C009 | F21P1 Nova Interconnection | 4094 | C | USCSB2405059A |  | PCA: NOVA: KUECN4: CuDD SLIP STREAM CONNECTION FLOW. | 45421 | 45447 | 8715 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 8715 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 8715 | [6 empty] | - |  | - |  | 0
Base-Build | UPW | Material | USC24C008 | UPW B Side Project | 4064 | C | USCSB2405060A |  | Train 2 Materials from ORGANO | 45421 | 45422 | 36569.82 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 36569.82 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 36569.82 | [8 empty] | - |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4065 | C | USCSB2405061A |  | CHEM_WCCS _Consumable hardware B_USA_ 01-00167344_ 0508 | 2024/5/9 2024/5/17 | 45433 | 156440 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | PR R1:As per purchasing team Nicole to compare prices with Copper State, which offers a 22.2% lower cost than Carson . | [13 empty] | 156440 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 156440 |  |  | 156440 | [7 empty] | - |  | - |  | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4082 | C | USCSB2405062A |  | Storage box for HK PPL trade for 100 tools | 45422 | 45425 | 1193.5 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 1193.5 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 1193.5 | [10 empty] | - |  | - |  | 0
Others | AMHS | Labor | USC22C006 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 4066 | C | USCSB2405063A |  | Area A EUV Cranes Bay 1 and 2 | 45422 | 45454 | 245785 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 245785 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 245785 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4067 | C | USCSB2405064A |  | WWT Fittings_20240509 (A Side) | 45422 | 45425 | 5491.18 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 5491.18 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 2617.33 |  | 2873.85 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Helix | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4085 | C | USCSB2405065A |  | WWT A-Side Sand Blast Room Cable Pulling Requirement_20240509 | 45423 | 45425 | 44126 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved | [14 empty] | 44126 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 44126 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4086 | C | USCSB2405066A |  | 6181 TSMC UPW - 8-203 TR-2 Chem Drains CO | 45423 | 45441 | 281782 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 173634 | 0.6162 | 108148 | 480000 | -371852 | 19711.85 | [56 empty] | 0 | [11 empty] | 133790 | 374525.15 |  |  | 39844 | - |  | - |  | 19711.85
Hookup | Hookup | Material | USC23C059 | F21P1 Foundation T&M | 4087 | C | USCSB2405067A |  | additional 3 in 1 project material HK Power system | 45423 | 45429 | 1454.42 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1454.42 | 1 | 0 | 497000 | -497000 | 0 | [56 empty] | 0 | [16 empty] | 1454.42 |  | - |  | 0
Base-Build | WWT | Equipment | USC24C006 | WWT B side Project | 4088 | C | USCSB2405068A |  | WWT B Side Instrument Batch 1 | 45423 | 45505 | 87147.49 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 87147.49 | 0 | 87147.49 | 0 | [56 empty] | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS | Equipment | USC23C015 | F21P1 AMHS Wiring Work Outline | 4089 | C | USCSB2405069A |  | AUcan for AMHS extra 8 DP panel installation | 45423 | 45427 | 352000 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 352000 | 0 | 352000 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4090 | C | USCSB2405070A |  | WWT Blind Flange 4&6_20240510 (A Side) | 45423 | 45425 | 2125.4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2125.4 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 2125.4 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW |  | USC21C003 | F21P1 UPW | 4091 | C | USCSB2405071A |  | Fall Protection System | 45423 | 45446 | 5175 | [6 empty] | Safe Keeper Safety Products LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5175 | 6205 | -1030 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4092 | C | USCSB2405072A |  | Mechanical iPUP | 45423 | 45447 | 15000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 15000 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 15000 | [6 empty] | - |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4093 | C | USCSB2405073A |  | CHEM_WCCS _Consumable hardware C_Cush A clamp_USA_ 01-00167404_ 0510 | 45423 | 45432 | 71965 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 71965 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 39352.26 | 71965 |  |  |  |  | 32612.74 |  |  | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 4094 | C | USCSB2405074A |  | Borrowed Delta Wye People | 45423 | 45446 | 11115 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 11115 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 11115 | [8 empty] | - |  | - |  | 0
Base-Build | Chemical | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4095 | C | USCSB2405075A |  | CHEM_WCCS SUS project_LINDE_ ARGON, REFRIGERATED LIQUID*30pcs | 45423 | 45427 | 15686.9 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 15536.12 | 0.99039 | 150.78 | 0 | 150.78 | 0 | [56 empty] | 0 | [5 empty] | 9847.96 |  | 2538.39 | 15686.9 | 3149.77 | [6 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection | Equipment | USC23C036 | F21P1 AMAT Interconnection | 4096 | C | USCSB2405076A |  | Voltage Testing Pen | 5/11/2024 9/25/2024 | 5/15/2024 9/26/2024 | 117.3 | -14.52 | 131.82 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Match to the actual expense (See packing slip) | [13 empty] | 117.3 | 1 | 0 | 0 | 0 | 0 | 117.3 | [55 empty] | 0 | [16 empty] | - |  | - |  | 0
Base-Build | WWT | Equipment | USC24C006 | WWT B side Project | 4097 | C | USCSB2405077A |  | WWT Welding Rod_20240510 (B Side) | 45423 | 45427 | 3482 | [6 empty] | Supertung Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 3482 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 3482 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4098 | C | USCSB2405078A |  | Replenish wire lugs used to complete P1A project | 45423 | 45433 | 1179 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1179 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 1179 | [10 empty] | - |  | - |  | 0
Base-Build | UPW | Material | USC24C008 | UPW B Side Project | 4099 | C | USCSB2405079A |  | ICPMS LAB Train 2 CO To ORGANO | 45425 | 45427 | 8760 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8760 | 0 | 8760 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Base-Build | UPW | UMEC | USC24C008 | UPW B Side Project | 4100 | C | USCSB2405080A |  | Train 2 ICPMS CO To UMEC | 45426 | 45427 | 86810 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 65159 | 0.75059 | 21651 | 0 | 21651 | 0 | [56 empty] | 0 |  |  |  | 65159 | [12 empty] | - |  | 17310 |  | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4101 | C | USCSB2405081A |  | HK Electrical PM material request | 45426 | 45427 | 3264.45 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 2752.4 | 0.84314 | 512.05 | 0 | 512.05 | 0 | 2752.4 | [55 empty] | 0 | [16 empty] | - |  | - |  | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4102 | C | USCSB2405082A |  | HK Electrical PM Luis Retiz's material request | 45426 | 45428 | 1695.75 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 1695.75 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 1695.75 | [8 empty] | - |  | - |  | 0
Base-Build | 光阻櫃 | Labor | USC24C007 | Low Voltage B Side Project | 4103 | C | USCSB2405083A |  | F21-P1_B-Side mask room exhaust hookup designs | 45426 | 45426 | 5946.48 | [6 empty] | MornstAir Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5946.48 | 0 | 5946.48 | 0 | [56 empty] | 0 | [12 empty] | 5947 |  |  |  | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4104 | C | USCSB2405084A |  | Brycon April usage | 45426 | 45447 | 749607.1 | [6 empty] | Brycon Corporation | PR Approved | PO Approved | [14 empty] | 732191.1 | 0.97677 | 17416 | 0 | 17416 | 0 | [56 empty] | 0 | [9 empty] | 582390.54 |  |  |  | 139552.4 |  | 10248.16 | - |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4105 | C | USCSB2405085A | -01 | CHEM_ Ryan Herco Flow Solutions_ PVDV+CPVC+PP | 5/14/2024 5/31/2024 | 2024/5/17 2024/6/5 | 0 | -108633.48 | 108633.48 |  |  |  |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | R1: Due to quote revised item context and quote number ,so as per engineer Janie to cancel the PR,and create new PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [8 empty] | 54316.74 |  |  |  | 54316.74 |  |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4106 | C | USCSB2405086A |  | CHEM_CDS SDS project for valve_ SemiTorr Group_Qte1526621 | 45427 | 45447 | 62133.4 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 62133.4 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [8 empty] | 64308.6 |  |  | 62133.4 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4107 | C | USCSB2405087A |  | WWT B side Drain label - batch 2 | 45427 | 45427 | 1664.55 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1664.55 | 0 | 1664.55 | 1664.55 | [56 empty] | 0 | [14 empty] | 1664.55 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4108 | C | USCSB2405088A |  | Duralable for tool hookup team | 45427 | 45448 | 2456.68 | [6 empty] | Graphic Products, Inc. | PR Approved | PO Approved | [14 empty] | 2451.78 | 0.99801 | 4.9 | 0 | 4.9 | 0 | [56 empty] | 0 | [9 empty] | 2451.78 | [6 empty] | - |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4109 | C | USCSB2405089A |  | CHEM_WCCS _Unistrut | 45427 | 45427 | 33975 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 33975 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [8 empty] | 33975 |  |  | 33975 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4110 | C | USCSB2405090A |  | WWT-Enzyme for TSMC urgent request on 5/13 | 45427 | 45429 | 55281.6 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved | [14 empty] | 55281.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 |  |  |  | 55281.6 | [10 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4111 | C | USCSB2405091A |  | The electrical pipe installation for power and control of WSR. | 45427 | 45427 | 244.89 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 244.89 | 1 | 0 | 0 | 0 | 244.89 | [56 empty] | 0 | [14 empty] | 244.89 |  | 244.89 | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4112 | C | USCSB2405092A |  | CHEM_ HANSEN_ Chemical label | 45428 | 45428 | 14175 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 14175 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 14175 |  |  | 14175 | [7 empty] | - |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4113 | C | USCSB2405093A |  | CHEM_ puch list for A side_John | 45428 | 45428 | 132.02 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 132.02 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 132.02 |  |  | 132.02 | [7 empty] | - |  | - |  | 0
Base-Build | WWT | Helix | USC24C006 | WWT B side Project | 4114 | C | USCSB2405094A |  | WWT B Side Battery Panel Rigging and Installation | 45428 | 45433 | 38923 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved | [14 empty] | 38923 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [14 empty] | 0 |  | 38923 | 0 | - | 0 | 0 | 0
Base-Build | Chemical | CRG | USC24C005 | Chemical & WCCS B Side Project | 4115 | C | USCSB2405095A |  | l20 model [PROPOSAL STATUS FOR L20 AND L30] | 45428 | 45433 | 480000 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 480000 | 0 | 480000 | 240000 | [56 empty] | 0 | [12 empty] | 240000 |  | 216000 |  | - | 24000 | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4116 | C | USCSB2405096A |  | DFK Tech F21P1- POWER-B Machine panel power connection Bid No. Item Content Material Designated Vendor Model/Specific-Urgent | 45428 | 45458 | 1420000 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 710000 | 0.5 | 710000 | 0 | 710000 | 450000 | [56 empty] | 0 | [8 empty] | 300000 |  |  |  | 750000 | 710000 | 375000 |  | - |  | - | 75000 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4128 | C | USCSB2405097A |  | Scaffolding | 45428 | 45448 | 42082 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 42082 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 28850 |  | 13232 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4117 | C | USCSB2405098A |  | Lit 3: KPPTT1, KPPTT2, and KPPTT3: Material: Flex Exhaust for Blower Box | 45428 | 45441 | 690.84 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 690.84 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 690.84 | [10 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4118 | C | USCSB2405099A |  | WWT 2" Backing Ring_20240515 (A&B Side) | 45428 | 45429 | 2225 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2225 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 2225 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4119 | C | USCSB2405100A |  | FAB A and Lorry Chemical Electrical Special Observations | 45428 | 45433 | 19650 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 7962.5 | 0.40522 | 11687.5 | 0 | 11687.5 | 0 | [56 empty] | 0 | [5 empty] | 2197.5 |  |  | 19650 |  |  | 4472.5 |  |  |  | 1292.5 | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4120 | C | USCSB2405101A |  | tsmc support Chemical (55gal/KuritaK0800/Catalase2xConcentrated) | 45429 | 45433 | 365512.5 | [6 empty] | Kurita America Inc | PR Approved | PO Approved | [14 empty] | 307030.5 | 0.84 | 58482 | 0 | 58482 | 49124.88 | [56 empty] | 0 | [9 empty] | 307030.5 |  |  |  |  | 15351.525 |  | - | 15351.525 | - | 18421.83 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4133 | C | USCSB2405102A |  | Chem. Adjustable chain Sling | 45429 | 45434 | 430.99 | [6 empty] | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved | [14 empty] | 430.99 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 430.99 | [10 empty] | - |  | - |  | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4121 | C | USCSB2405103A |  | WWT A side Heat Exchanger Insulation | 45429 | 45433 | 35730.22 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved | [14 empty] | 35730.22 | 1 | 0 | 0 | 0 | 42876.264 | [56 empty] | 0 | [14 empty] | 17865.11 | 35730.22 | - | 10719.066 | - | 10719.066 | 3573.022 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4135 | C | USCSB2405104A | -01 | Cleanroom order for HK EHS | 2024/5/17 2024/5/25 | 45435 | 231.64 | -182.04 | 413.68 |  |  |  |  | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 231.64 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 231.64 | [10 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4122 | C | USCSB2405105A |  | WWT LC/MS/MS Acrylic Dust Cover | 45429 | 45430 | 3040 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | [14 empty] | 3040 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 3040 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4137 | C | USCSB2405106A |  | CHEM_B side FB1-F20 VMB construction | 45430 | 45432 | 8449.1 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 8449.1 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 8449.1 |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4138 | C | USCSB2405107A |  | Lock for tool box | 45430 | 45434 | 109.9 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 74.9 | 0.68153 | 35 | 30255.26 | -30220.26 | 0 | 74.9 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4158 | C | USCSB2405108A |  | Mobile Storage Container Combo Office for HK | 45430 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Zero out. Change vendor | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT | Labor | USC21C003 | F21P1 UPW | 4139 | C | USCSB2405109A | -01 | WWT B Side Battery Recharge 2 | 5/18/2024 6/4/2024 | 2024/5/21 2024/6/5 | 0 | -9800 | 9800 |  |  |  | V | Gruber Industries | PR Approved | PO Approved | R1: As per engineer Chihhao to revise the quote, so cancel this PR, and add new PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4140 | C | USCSB2405110A |  | Mateiral Storage | 45430 | 45443 | 201.76 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 187.97 | 0.93165 | 13.79 | 0 | 13.79 | 0 | 187.97 | [72 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4141 | C | USCSB2405111A |  | CDS L brackets requested by Alonso in 2023 | 45433 | 2024/5/22 2024/5/28 | 2177 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2177 | 0 | 2177 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4142 | C | USCSB2405112A |  | Action Scaffolding | 45433 | 45442 | 2064 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2064 | 0 | 2064 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4143 | C | USCSB2405114A |  | Knaack jobsite box for HK PPL trade | 45433 | 45433 | 3515.4 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 3515.4 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 3515.4 | [10 empty] | - |  | - |  | 0
Base-Build | Chemical | CRG | USC24C005 | Chemical & WCCS B Side Project | 4144 | C | USCSB2405115A |  | CHEM_B side L20/ L30_R-TEE _GN2 | 45433 | 45435 | 28236.06 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 28236.06 | 0 | 28236.06 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4145 | C | USCSB2405116A | -01 | WWT - Material Modify Chemical Tanks Level Guage to Flange Connection | 2024/5/21 2024/6/10 | 2024/5/22 2024/6/13 | 11297 | 3887 | 7410 | V |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | PR R1: Due to Harrington made a mistake when pricing the flanges. | [13 empty] | 11297 | 1 | 0 | 0 | 0 | 11297 | [70 empty] | 11297 | 5648.5 |  | - | 5648.5 | - | 0 | 0 | 0
Hookup | Foundation |  | USC23C047 | F21P1 HK Seismic Installation | 4146 | C | USCSB2405118A |  | 3rd work order for Hookup seismic work | 45433 | 45448 | 352125 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 77253.8 | 0.21939 | 274871.2 | 0 | 274871.2 | 0 | [66 empty] | 18367 |  |  |  | 22336 |  |  | 36550.8 |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4147 | C | USCSB2405119A |  | WWT 6X4 Reducing Tee_20240520 (B Side) | 45434 | 45435 | 2793.9 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2793.9 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 2793.9 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4148 | C | USCSB2405120A |  | WWT - T-665AA Tank Repair | 45434 | 45436 | 10841.82 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 10841.82 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 10841.82 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4149 | C | USCSB2405121A |  | WWT Ball Valve_20240521 (B Side) | 45434 | 45436 | 10318.9 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 10318.9 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 9531.55 |  | 787.35 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV |  | USC24C007 | Low Voltage B Side Project | 4150 | C | USCSB2405122A |  | F21P1 Gown Office Security PFA area Security & CCTV | 45434 | 45436 | 27500 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 24750 | 0.9 | 2750 | 0 | 2750 | 26125 | [70 empty] | 24750 | 13750 |  | - | 12375 | - |  | 0
Base-Build | Barcode |  | USC22C001 | F21 P1 Office and WH Security and CCTV | 4151 | C | USCSB2405123A |  | F21 Barcode system _G-Bit | 45434 | 45435 | 256.5 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved | [14 empty] | 256.5 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 256.5 | [6 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4152 | C | USCSB2405124A |  | A side Scaffolding building-Waste PVDF Submain add support | 45434 | 45435 | 19560 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 19560 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 19560 |  |  | - |  | - |  | 0
Base-Build | VOC |  | USC24C007 | Low Voltage B Side Project | 4153 | C | USCSB2405125A |  | F21 P1 VOC system extension GC (JAN.FEB.MAR.APR/2024) | 45434 | 45451 | 120057 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 120057 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 101228.03 |  |  |  | 18828.97 | [6 empty] | - |  | - |  | 0
Base-Build | VOC |  | USC24C007 | Low Voltage B Side Project | 4154 | C | USCSB2405126A |  | F21 P1 VOC system extension GC (MAY/2024) | 45434 | 45451 | 87354 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 87354 | 1 | 0 | 476270.88 | -476270.88 | 0 | [66 empty] | 87354 | [6 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4155 | C | USCSB2405127A |  | WWT Fittings_20240521 (B Side) | 45434 | 45436 | 45566.81 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 45566.81 | 1 | 0 | 0 | 0 | 11331.745 | [64 empty] | 11283.91 |  | 11379.58 |  | 22903.32 |  |  | 5665.8725 |  | - | 5665.8725 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4156 | C | USCSB2405128A |  | Quote of 100 argon cylinders for HK shared by all system | 45434 | 45437 | 53373 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 53373 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 1514.69 |  | 13194.25 |  | 9425.85 |  | 14849.81 |  | 11964.24 |  | 2424.16 | - |  | - |  | 0
Base-Build | WWT | MIMO/Rigging | USC24C006 | WWT B side Project | 4157 | C | USCSB2405129A |  | WWT T-780BABB Header rigging | 45434 | 45443 | 23750 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 23750 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 23750 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4158 | C | USCSB2405130A |  | WWT RT&Bushing_20240521 (B Side) | 45434 | 45435 | 2408.7 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2408.7 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2408.7 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4159 | C | USCSB2405131A |  | F21P1A L30 Slurry VMB 訊號及氣源管拉設 | 45435 | 45451 | 20590 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 20590 | 0 | 20590 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4160 | C | USCSB2405132A |  | F21P1A L10 Pump area WLS Aegis panel 工程 | 45435 | 45451 | 90000 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 90000 | 0 | 90000 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4161 | C | USCSB2405133A |  | (MA0240028A)TSMC F21P1_B HPM 20 UPW 配管(SDS) | 2024/5/23 2024/6/22 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:As per Johnny wan return this PR,and find alternative supplier. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4162 | C | USCSB2405134A |  | 2" SUS Pipe Bending Reuqest--400R | 45435 | 45444 | 14662.5 | [6 empty] | Chukar SB&F LLC | PR Approved | PO Approved | [14 empty] | 14662.5 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 14662.5 | [8 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C021 | F21P1 KLA Interconnection | 4168 | C | USCSB2405138A |  | ME: NO TOOL ID: MANPOWER (UBALDO FERREYRA JR) FOR JUNE 2024 | 2024/5/23 2024/9/18 | 2024/6/11 2024/9/18 | 11656.5 | 2536.5 | 9120 | V |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | PR R1 :This is to include the OT HRS WE 06/09 for $256.50 & REG HRS WE 07/04 for $2,280.00. See 2nd page. | [13 empty] | 11656.5 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 11656.5 |  | - |  | 0
Base-Build | WWT | Labor | USC24C006 | WWT B side Project | 4163 | C | USCSB2405139A |  | F21 FAB B MU management engineer quotation | 2024/5/23 2024/7/1 |  | 2759355 | [7 empty] | PR Approved | PO Processing | PR R1:Modify the QTY and price of airline tickets according to purchasing team Oneil. | [13 empty] | 0 | 0 | 2759355 | 0 | 2759355 | 2759355 | [71 empty] | 551871 |  | - | 551871 | - | 551871 | 551871 | 551871
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4164 | C | USCSB2405140A | -01 | 氨氮標準液 | 45435 | 2024/5/28 2024/5/29 | 320.67 | [6 empty] | Winn Marion Barber, LLC | PR Approved | PO Approved | R1: Modify Liquidation Damage to NA | [13 empty] | 320.67 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 320.67 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | Organo |  | USC24C013 | Organo USA - UPW Electrical | 4165 | C | USCSB2405141A |  | CIP Motor Change | 45436 | 45462 | 60510.53 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 30255.27 | 0.5 | 30255.26 | 0 | 30255.26 | 0 | [73 empty] | 30255.27 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4166 | C | USCSB2405142A |  | Lorry A/B缺失工程 | 45436 | 45443 | 60000 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved | [14 empty] | 54000 | 0.9 | 6000 | 0 | 6000 | 0 | [73 empty] | 54000 |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4167 | C | USCSB2405143A |  | WWT - Supply (4) 18inch FRP Flanges to Complete T-740BA-BB-BC Interconnection | 45436 | 45448 | 2753.64 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2753.64 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 2753.64 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4168 | C | USCSB2405144A |  | CHEM_WCCS_Ladder + EXT cord for F21 project use | 45436 | 45440 | 2767.52 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 2767.52 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 2767.52 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 4169 | C | USCSB2405145A |  | DIFF 1& 2 no tool ID#, monthly rental rate for Nitrogen ACCT68520233 09/20/2023-06/20/2024 | 2024/5/24 2024/5/30 | 45448 | 511.49 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | PR R1:We had adjusted off the safety & environmental fee for Oct thru Dec 2023 as we did for the other accounts. When we added the | [13 empty] | 188.31 | 0.36816 | 323.18 | 0 | 323.18 | 0 | [62 empty] | 188.31 | [10 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4170 | C | USCSB2405146A |  | WWT Fittings_20240523 (B Side) | 45436 | 45441 | 18097.34 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 18097.34 | 1 | 0 | 0 | 0 | 1522.612 | [66 empty] | 1673.2 |  | 16424.14 |  |  | 1522.612 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4171 | C | USCSB2405147A |  | WWT Hardware_20240523 (B Side) | 45436 | 45440 | 6610.11 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 6610.11 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2639.01 |  | 3971.1 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4178 | C | USCSB2405149A |  | WWT materials (B side)_WIDOS INSERTS | 45436 | 45440 | 25818.75 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 25818.75 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 25818.75 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4179 | C | USCSB2405150A |  | WRC A side platform recover (material) | 45437 | 45442 | 10857.7 | [6 empty] | Fibergrate Composite Structures Inc | PR Approved | PO Approved | [14 empty] | 10857.7 | 1 | 0 | 5695.78 | -5695.78 | 10857.7 | [70 empty] | 10857.7 | 5428.85 |  | - | 5428.85 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC24C005 | Chemical & WCCS B Side Project | 4180 | C | USCSB2405151A |  | TSMC F21 B SIDE SDS ATRS Regulator | 45440 | 45442 | 6773.75 | [6 empty] | Flodraulic Group | PR Approved | PO Approved | [14 empty] | 6773.75 | 1 | 0 | 37302 | -37302 | 0 | [62 empty] | 6657.15 |  | 116.6 | [8 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4181 | C | USCSB2405152A |  | These cables will be installed for control system of WSR. | 45441 | 45442 | 1973.12 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1973.12 | 1 | 0 | 114079 | -114079 | 0 | [64 empty] | 1973.12 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4182 | C | USCSB2405153A |  | Hex bolt and nut for HK PPL trade. New PR to replace USCSB2312151 | 45441 | 45442 | 281.49 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved | [14 empty] | 281.49 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 281.49 | [10 empty] | - |  | - |  | 0
Base-Build | WWT | Equipment | USC24C006 | WWT B side Project | 4183 | C | USCSB2405154A |  | WWT WRC laboratory furniture_Sensor | 45441 | 45441 | 105.86 | [6 empty] | Mega Depot, LLC | PR Approved | PO Approved | [14 empty] | 105.28 | 0.99452 | 0.58 | 0 | 0.58 | 0 | 105.28 | [70 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C021 | F21P1 KLA Interconnection | 4245 | C | USCSB2405155A |  | ME: KKDB02: CO FOR EXHAUST DUCT REROUTING | 45441 | 45498 | 13500 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 13500 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 13500 |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4184 | C | USCSB2405156A |  | WWT Container Covers_20240524 (B Side) | 45441 | 45441 | 1899.49 | [6 empty] | Global Equipment Company Inc. | PR Approved | PO Approved | [14 empty] | 1899.49 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 1899.49 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4185 | C | USCSB2405157A |  | open po for invoice past due, tool hookup team | 45441 | 45443 | 7538.91 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 6617.61 | 0.87779 | 921.3 | 0 | 921.3 | 0 | [60 empty] | 6617.61 | [12 empty] | - |  | - |  | 0
Non-TSMC | Organo |  | USC24C013 | Organo USA - UPW Electrical | 4186 | C | USCSB2405158A |  | CIP Pump Change Scaffold | 45441 | 45443 | 44049 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 44049 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 26429 | [7 empty] | 17620 | - |  | - |  | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 4187 | C | USCSB2405159A |  | TSMC Hookup UPW P1B materials_non panels | 45441 | 45446 | 1476607.74 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 682780.26 | 0.4624 | 793827.48 | 5948.94 | 787878.54 | 0 | [66 empty] | 298795.29 |  | 100776.38 |  |  |  | 269619.48 | 13589.11 |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4188 | C | USCSB2405160A |  | WWT PP軟管及接頭_20240528 (B Side) | 45441 | 45446 | 5502 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5502 | 0 | 5502 | 5502 | [71 empty] | 5502 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4189 | C | USCSB2405161A |  | WWT Center Rings_20240528 (B Side) | 45441 | 45450 | 5770 | [6 empty] | HSIUNG CHANG Enterprise Co., Ltd. | PR Approved | PO Approved | [14 empty] | 5770 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 5770 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation |  | USC23C059 | F21P1 Foundation T&M | 4190 | C | USCSB2405162A |  | 3rd waffle covers from MMI | 45441 | 45446 | 129420 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 129420 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 129420 |  |  | - |  | - |  | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4191 | C | USCSB2405163A |  | Hilti bolts for foundation works in P1B. | 45441 | 45446 | 29510 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29510 | 0 | 29510 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4192 | C | USCSB2405164A |  | Swagelok pressure-reducing redgulators and compressionto npt adaptors | 45441 | 45442 | 61556.2 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 61556.2 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 4701.4 | [7 empty] | 28427.4 |  | 28427.4 | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4193 | C | USCSB2405165A |  | Linde previous unpaid | 45441 | 45446 | 70000 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 70000 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 46542.97 |  | 16235 |  | 7222.03 | [8 empty] | - |  | - |  | 0
Base-Build | W-H2SO4 |  | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4194 | C | USCSB2405166A |  | WSR 廢硫酸缺料接點 | 45441 | 45446 | 98303 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 98303 | 0 | 98303 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4195 | C | USCSB2405167A |  | 200 2/0 AWG | 45441 | 45443 | 1124 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1124 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 1124 | [8 empty] | - |  | - |  | 0
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4196 | C | USCSB2405168A |  | Horiba Calibration Service | 45442 | 2024/6/26 2024/7/4 | 55484 | [6 empty] | HORIBA Instruments Incorporated | PR Approved | PO Approved | R1: Add Billing Address per request | [13 empty] | 0 | 0 | 55484 | 0 | 55484 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4197 | C | USCSB2405169A |  | Additional P1A B6-1 foundation, KEPSLD, KEPSLE for MMI | 45442 | 45450 | 67725 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 27291 | 0.40297 | 40434 | 0 | 40434 | 0 | [70 empty] | 27291 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4198 | C | USCSB2405170A |  | Grainer One Hiole Lug compression connectors: 8 / 6 AWG | 45442 | 45449 | 7742.98 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 2848.1 | 0.36783 | 4894.88 | 0 | 4894.88 | 0 | [66 empty] | 2848.1 | [6 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4199 | C | USCSB2405171A |  | Extremely Urgent_RFQ_MICU Chemical Team Request Material_05232024-1 | 45442 | 45446 | 222472.89 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 221641.52 | 0.99626 | 831.37 | 8385 | -7553.63 | 0 | [62 empty] | 39869.28 |  | 32579.79 |  | 99531.32 |  | 8111.95 |  | 39771 |  | 1778.18 | - |  | 829.82 |  | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4200 | C | USCSB2405172A |  | 3/8" HEAT SHRINK TUBING 3:1 RATIO and HEAT- ALL SHRINNK TUBING HWT-0025 | 45442 | 45448 | 279.27 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 253.82 | 0.90887 | 25.45 | 0 | 25.45 | 0 | 253.82 | [72 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4201 | C | USCSB2405173A |  | Extremely Urgent_RFQ_MICU Chemical Team Request Material_05232024_Semitorr | 45442 | 45446 | 63239.02 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 63228.63 | 0.99984 | 10.39 | 0 | 10.39 | 0 | [68 empty] | 63228.63 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4202 | C | USCSB2405174A |  | WWT PVC PP Unions_20240529 (B Side) | 45442 | 45447 | 216 | [6 empty] | Delpha Plastics Co., Ltd. | PR Approved | PO Approved | [14 empty] | 216 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 216 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | W-H2SO4 |  | USC21C014 | F21P1 WH2SO4 | 4203 | C | USCSB2405175A |  | WSR tool | 2024/5/30 2024/7/4 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:As per engineer Jim to cancel the PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4204 | C | USCSB2405176A |  | WWT Ball Valves Purchase(A & B side) | 45442 | 45449 | 30281.9 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 30281.9 | 0 | 30281.9 | 36338.28 | [71 empty] | 15140.95 |  | - | 9084.57 | - | 9084.57 | 3028.19 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4205 | C | USCSB2405177A |  | 珠光不上膜空白綠色圓標-20mm | 45443 | 45443 | 150 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 150 | 0 | 150 | 0 | [73 empty] | - |  | 150 |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4206 | C | USCSB2405178A |  | PIPE P/E CLR PVC SCH40, FOR CHEMICAL tool hookup team | 45443 | 45443 | 332 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 332 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 332 | [8 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4207 | C | USCSB2405179A |  | CHEM_ Ryan Herco Flow Solutions_ CDS/ SDS/ WCCS_ L10/L20_ PVDV+CPVC+PP | 45443 | 45447 | 132742.51 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 125622.62 | 0.94636 | 7119.89 | 72.24 | 7047.65 | 0 | [66 empty] | 82810.62 |  |  |  | 33981.09 |  |  | 8830.91 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4208 | C | USCSB2405180A |  | [上禾] MICU E2 支援報價單(8人*4 month) | 45443 | 45448 | 176000 | [6 empty] | SHANG-HE project company | PR Approved | PO Approved | [14 empty] | 11000 | 0.0625 | 165000 | 0 | 165000 | 0 | [73 empty] | 11000 |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4209 | C | USCSB2405181A |  | WWT - (166) L20 Litho B Side Embedded Pipe Sealing | 45443 | 45461 | 114079 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 114079 | 0 | 114079 | 114079 | [71 empty] | 22815.8 |  | - | 22815.8 | - | 22815.8 | 22815.8 | 22815.8
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4210 | C | USCSB2405182A |  | WWT Hardware_20240529 (B Side) | 45443 | 45446 | 4724.96 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 4724.96 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 1332 |  | 3392.96 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4211 | C | USCSB2405183A |  | WWT Fittings_20240530 (B Side) | 45443 | 45447 | 12603.4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 6798.02 | 0.53938 | 5805.38 | 0 | 5805.38 | 3147.7032 | [66 empty] | 5829.08 |  | 968.94 |  |  | 3147.7032 |  | - | 0 | 5805.38 | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4212 | C | USCSB2405184A |  | 3 house keeping pads 128"x48" PAD PREP, EPOXY AND YELLOW PERIMETOR PAINT | 45443 | 45448 | 2432.19 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 2432.19 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 2432.19 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4213 | C | USCSB2405185A |  | F21P1 B side Electrical Materials Purchasing | 45443 | 45447 | 170226.91 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 170226.91 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 66636.3 |  | 103231.2 |  | 359.41 |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4229 | C | USCSB2405186A |  | Ryan Herco CPVC/PP/PVDF 0530 | 45443 | 45446 | 10494.72 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 10494.72 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 269.36 |  | 3430.94 | [6 empty] | 6794.42 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4230 | C | USCSB2405187A | -01 | (MA0240031A)TSMC F21P1_B HPM Material quotation | 45443 | 2024/6/4 2024/6/18 | 0 | -437475.16 | 437475.16 | V |  |  |  | MornstAir Inc. | PR Approved | PO Approved | R1: As per purchasing team David to revise the vendor to Chern shuo,so close this PR and add new PR for this order. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4231 | C | USCSB2406002A |  | CED 五金料件0531-1 | 45444 | 45447 | 62544.05 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 41584.84 | 0.66489 | 20959.21 | 0 | 20959.21 | 0 | [73 empty] | 41584.84 |  | 15116.6 |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4232 | C | USCSB2406003A |  | CED Wire 0531-1 | 45444 | 45446 | 10566 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 10566 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 10566 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4233 | C | USCSB2406004A |  | 彰京SUS-0531 | 45444 | 45447 | 288643.18 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 288643.18 | 0 | 288643.18 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4234 | C | USCSB2406005A |  | F21P1 WCCS PVDF ADPT | 45444 | 45446 | 407.4 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 407.4 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 407.4 | [8 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4235 | C | USCSB2406009A |  | (Chemical Borrowed)澤維實業PVDF 料件0531 | 45444 | 45447 | 589183.95 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 150907.82 | 0.25613 | 438276.13 | 0 | 438276.13 | 589183.95 | [71 empty] | 117836.79 | 150907.82 | - | 117836.79 | 438276.13 | 117836.79 | 117836.79 | 117836.79
Base-Build | Slurry |  | USC21C006 | F21P1 Slurry package | 4236 | C | USCSB2406010A |  | F21P1 IES- Cable Tray B side | 45444 | 45449 | 172999.41 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 158001.38 | 0.91331 | 14998.03 | 5929.46 | 9068.57 | 0 | [70 empty] | 31659.51 |  | 68792.35 | 57549.52 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4237 | C | USCSB2406011A |  | F21P1 CED Y-Conduit | 45444 | 45447 | 27214.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 8592.1 | 0.31572 | 18622.4 | 0 | 18622.4 | 0 | [73 empty] | 8592.1 |  | 18622.4 |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4238 | C | USCSB2406012A |  | F21P1 SUS B-Flange | 45444 | 45446 | 4648 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 4648 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 4648 | [8 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4239 | C | USCSB2406013A |  | F21P1 - Electric conduit | 45444 | 45446 | 3749.82 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 3749.82 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 3749.82 | [10 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4240 | C | USCSB2406014A |  | Hardware for Chemical System | 45444 | 45446 | 4541.8 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 4541.8 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2105.8 | [5 empty] | 2436 |  |  | - |  | - |  | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 4241 | C | USCSB2406015A |  | T140 discharge panel modification | 45444 | 45472 | 67302.18 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved | [14 empty] | 67302.18 | 1 | 0 | 0 | 0 | 80762.616 | [70 empty] | 67302.18 | 33651.09 |  | - | 20190.654 | - | 20190.654 | 6730.218 | 0
Base-Build | WWT | Labor | USC21C003 | F21P1 UPW | 4242 | C | USCSB2406016A |  | WWT B Side Battery Recharge 2_R2 | 45446 | 45448 | 17250 | [6 empty] | Gruber Industries | PR Approved | PO Approved | [14 empty] | 17250 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 17250 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Slurry |  | USC21C006 | F21P1 Slurry package | 4243 | C | USCSB2406017A |  | FAB A SDS Permit Revision | 45447 | 45449 | 8385 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8385 | 0 | 8385 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC | Organo |  | USC24C013 | Organo USA - UPW Electrical | 4244 | C | USCSB2406018A |  | WRC UPW Pump Revision - Observation | 45447 | 45449 | 5100 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5100 | 0 | 5100 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Base-Build | Housekeeping | USC23C056 | Fab LB2 Trench Cleaning | 4245 | C | USCSB2406019A |  | B side housekeeping(Open PO) | 45447 |  | 122000 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 122000 | 0 | 122000 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4246 | C | USCSB2406020A |  | WWT Beam Clamps & Base_20240603 (B Side) | 45447 | 45447 | 3610.78 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3610.78 | 0 | 3610.78 | 3610.78 | [71 empty] | 1805.39 |  | - | 1805.39 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4247 | C | USCSB2406021A |  | pad prep/epoxy and yellow safety paint of 1 pad in Fab L10 HPM Bside Bed 457*113(inch) | 45447 | 45450 | 6813.78 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 6813.78 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 6813.78 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4248 | C | USCSB2406022A |  | 1-1/2 SS 304L 法蘭洗孔 | 45447 | 45448 | 85.43 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 85.43 | 1 | 0 | 93450 | -93450 | 0 | [66 empty] | 85.43 | [6 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4249 | C | USCSB2406023A |  | TCELC-F21P1 CDS support 追加 quotation | 45447 | 45449 | 27420 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 27420 | 0 | 27420 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4250 | C | USCSB2406024A |  | multi conductor tray cable | 45448 | 45449 | 6069 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6069 | 0 | 6069 | 0 | [73 empty] | - |  | 6034 |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4251 | C | USCSB2406025A | -01 | 4-40' Rental Containers for HK shared by all system | 2024/6/5 2024/6/20 | 2024/6/6 2024/6/20 | 3416.23 | 2100 | 1316.23 |  |  | V |  | Allied Storage Containers | PR Approved | PO Approved | Additional amount is for extension of rental from 1 to 6 months. | [13 empty] | 2612.35 | 0.76469 | 803.88 | 10455 | -9651.12 | 0 | [66 empty] | 1736.23 |  |  |  | 456.12 |  | 420 | - |  | 420 |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4252 | C | USCSB2406026A |  | F21P1 B Side material RH- PVDF 1/2"x3/4" ADPT | 45448 | 45448 | 2794.2 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 2794.2 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2794.2 | [8 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4253 | C | USCSB2406027A |  | Cleanroom tape for HK shared by all system | 45448 | 45448 | 644.49 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 644.49 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 644.49 | [10 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4254 | C | USCSB2406028A |  | F21P1 B Side material CED - Eletrical/Signal | 45448 | 45448 | 18603.07 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 13207.27 | 0.70995 | 5395.8 | 0 | 5395.8 | 0 | [73 empty] | 13207.27 |  | 5155.98 |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4255 | C | USCSB2406029A |  | F21P1 B Side EES Porder Coating Cable Tray | 45448 | 45448 | 71600 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 71600 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 71600 | [10 empty] | - |  | - |  | 0
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4256 | C | USCSB2406030A |  | 40,000 Feet 1 AWG 3/C Cable | 45448 | 45451 | 356800 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 65116 | 0.1825 | 291684 | 0 | 291684 | 0 | [73 empty] | 65116 |  | 291684 |  | 0
Base-Build | Chemical |  | USC21C006 | F21P1 Slurry package | 4257 | C | USCSB2406031A |  | F21P1 B Side material Harrington - CPVC fitting | 45448 | 45454 | 199098.22 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 199098.22 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 179421.62 |  |  |  | 19676.6 |  |  |  |  | - |  | - |  | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4258 | C | USCSB2406032A |  | Two consultants order from 5/18/2024~12/19/2024 | 45448 | 45454 | 173449.64 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 173449.64 | 0 | 173449.64 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4259 | C | USCSB2406033A |  | F21P1 B Side material - PVDF /Ele | 45449 | 45454 | 402666.49 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 383107.09 | 0.95143 | 19559.4 | 0 | 19559.4 | 0 | [66 empty] | 249554.75 |  | 133552.34 |  |  |  |  | - |  | - |  | 0
Hookup | Foundation |  | USC23C047 | F21P1 HK Seismic Installation | 4260 | C | USCSB2406034A |  | QR, EBO seismic installation. Replacement of PR USCSB2308029 | 45449 | 45454 | 89813.46 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 89813.46 | 2024.1 | 87789.36 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4261 | C | USCSB2406035A |  | P1A KDMRA1(ADI-C-11) foundation installation | 45449 | 45451 | 15360.4 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 15360 | 0.99997 | 0.4 | 0 | 0.4 | 0 | [66 empty] | 15360 | [6 empty] | - |  | - |  | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4262 | C | USCSB2406036A |  | 3rd 1000pcs tile swap | 45449 | 45451 | 26052 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 26052 | 0 | 26052 | 0 | [73 empty] | - |  | 26052 |  | 0
Non-TSMC | Organo |  | USC24C013 | Organo USA - UPW Electrical | 4263 | C | USCSB2406037A |  | WRC UPW Pump Revision - Permit | 45449 | 45450 | 2150 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2150 | 151835 | -149685 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | UPW |  | USC21C003 | F21P1 UPW | 4264 | C | USCSB2406038A |  | CGS Global Manpower Labor for painting of housekeeping pads | 45449 | 45465 | 2856 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 1303.06 | 0.45625 | 1552.94 | 0 | 1552.94 | 0 | [73 empty] | 1303.06 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4265 | C | USCSB2406039A |  | CHEM_CDS/ SDS/ WCCS_ SUS project_LINDE_ ARGON, REFRIGERATED LIQUID*200pcs | 45449 | 45455 | 103121 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 15342.46 | 0.14878 | 87778.54 | 0 | 87778.54 | 0 | [66 empty] | 3377.61 |  | 1957.92 |  | 5948.03 |  | 4058.9 | - |  | 3475.25 |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4266 | C | USCSB2406040A |  | F21P1 B Side material Mcmaster-carr - SUS Y-Strainers | 45449 | 45449 | 300.12 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 300.12 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 300.12 | [10 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4267 | C | USCSB2406041A |  | F21P1 B Side material Harrington - PVC Conduit fitting for PP | 45449 | 45449 | 423.5 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 423.5 | 1 | 0 | 50775.04 | -50775.04 | 0 | [66 empty] | 142 |  | 281.5 |  |  |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4268 | C | USCSB2406042A | -01 | F21P1 B Side material Amz - RS-232 Connector | 45449 | 2024/6/6 2024/6/18 | 389.9 | 0.9 | 389 |  | V |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Align with the actual purchase amount | [13 empty] | 389.9 | 1 | 0 | 0 | 0 | 0 | 389.9 | [72 empty] | - |  | - |  | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4269 | C | USCSB2406043A |  | CGS Global Manpower Labor for painting of housekeeping pads | 45449 | 45465 | 2856 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 2856 | 1 | 0 | 0 | 0 | 2856 | [71 empty] | 1428 |  | 2856 | 1428 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4270 | C | USCSB2406044A |  | WWT CDA B SUS material | 45449 | 45454 | 3586.55 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 3586.55 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 3586.55 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4271 | C | USCSB2406045A |  | CGS Global Manpower Labor for painting of housekeeping pads | 45449 | 45450 | 3427.2 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 3427.2 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 1713.6 | [6 empty] | 1713.6 |  | - |  | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4272 | C | USCSB2406046A |  | Delta Wye | 45449 | 45456 | 14440 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 14440 | 1 | 0 | 104319.9 | -104319.9 | 0 | [68 empty] | 14440 |  |  |  |  | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4273 | C | USCSB2406047A |  | Rework KSSWA1 | 45449 | 45454 | 3500 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 3500 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3500 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4281 | C | USCSB2406048A |  | DRY ETC 3 | 45450 | 45455 | 1104 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1104 | 0 | 1104 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4274 | C | USCSB2406049A |  | WWT-GB PCO #112_Cut and extend 2 supports on X/2 | 45450 | 45454 | 4350 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4350 | 0 | 4350 | 4350 | [71 empty] | 2175 |  | - | 2175 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC24C006 | WWT B side Project | 4275 | C | USCSB2406050A |  | FAB B WWT Observation and CA Service | 45450 | 45456 | 309480 | [6 empty] | M Consultants, LLC BDA M-Engineering | PR Approved | PO Approved | [14 empty] | 109836 | 0.35491 | 199644 | 144450 | 55194 | 309480 | [70 empty] | 70328 | 61896 | 39508 | - | 61896 | - | 61896 | 61896 | 61896
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4276 | C | USCSB2406051A |  | FAB A CDS-WCCS Permit Revision | 45450 | 45454 | 93450 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 93450 | 0 | 93450 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C053 | AMAT Interconnection (TSMC) | 4277 | C | USCSB2406052A |  | scaffolding assembly/dismantling KCENA3 ,KEARA1 , KEMEA2, | 45450 | 45454 | 5022 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 5022 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 5022 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4286 | C | USCSB2406053A |  | Delta Wye Manpower to install and label DAQ cables | 45450 | 45456 | 38592 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 38592 | 1 | 0 | 48728 | -48728 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 38592 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4287 | C | USCSB2406054A |  | FAB A WCCS Observation | 45450 | 45455 | 50410 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 14697.5 | 0.29156 | 35712.5 | 3545.35 | 32167.15 | 0 | [68 empty] | 11437.5 |  |  |  | 3260 | - |  | - |  | 0
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4288 | C | USCSB2406055A |  | Materials from ORGANO | 45451 | 45454 | 10699.88 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 10699.88 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 10699.88 |  |  |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4289 | C | USCSB2406056A |  | F21P1 Marketech QUO8338 WCCS.SDS B-Side Labels | 45451 | 45454 | 28986.5 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 28986.5 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 28986.5 | [6 empty] | - |  | - |  | 0
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4290 | C | USCSB2406057A |  | Ashcroft PIA KM31 | 45454 | 45454 | 839.13 | [6 empty] | Ashcroft Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 839.13 | 1215 | -375.87 | 0 | [73 empty] | - |  | 286.84 |  | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 4291 | C | USCSB2406058A |  | (A side)YAHO T&M A side work from 05/2024-07/2024 | 45454 | 45455 | 467500 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | [14 empty] | 430583.33 | 0.92103 | 36916.67 | 0 | 36916.67 | 467500 | [70 empty] | 430583.33 | 93500 |  | - | 93500 | - | 93500 | 93500 | 93500
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4292 | C | USCSB2406059A |  | WWT Fittings & Pipes_20240607 (B Side) | 45454 | 45455 | 5792.42 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 5792.42 | 1 | 0 | 0 | 0 | 5792.42 | [68 empty] | 5489.17 |  | 303.25 | 2896.21 |  | - | 2896.21 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4293 | C | USCSB2406060A |  | F21P1 B Side Lorry to CDU & DHL to CDU CPVC installation | 45454 | 45454 | 15500 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved | [14 empty] | 15500 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 15500 |  | - |  | 0
Base-Build | Chemical | Material | USC24C005 | Chemical & WCCS B Side Project | 4294 | C | USCSB2406061A |  | CHEM_R325 bent_ SUS 316L BA tube | 45454 | 45455 | 5249.5 | [6 empty] | Chukar SB&F LLC | PR Approved | PO Approved | [14 empty] | 5249.5 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 5249.5 | [8 empty] | - |  | - |  | 0
Base-Build | WWT | Equipment | USC21C011 | F21 TMAH System | 4295 | C | USCSB2406062A |  | F21 WWT industrial media converter | 45454 | 45454 | 755.28 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved | [14 empty] | 755.28 | 1 | 0 | 151340 | -151340 | 0 | [70 empty] | 755.28 | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C011 | F21 TMAH System | 4296 | C | USCSB2406063A |  | WWT - Harrington Fusion Machine Rental TMAH EXP | 45454 | 45462 | 13168.2 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 10754.03 | 0.81667 | 2414.17 | 0 | 2414.17 | 0 | [68 empty] | 3950.46 |  |  | 0 | 6803.57 | - | 0 | - | 0 | 0 | 0
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4297 | C | USCSB2406064A |  | AMHS Power Tools for Panel Install | 45454 | 45454 | 973 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 875.35 | 0.89964 | 97.65 | 0 | 97.65 | 0 | 875.35 | [72 empty] | - |  | - |  | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 4298 | C | USCSB2406066A |  | Pipe support _Hua Yi close PR_ batch 1/2 | 45455 | 45462 | 83260 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 83260 | 55213.6 | 28046.4 | 99912 | [71 empty] | 41630 |  | - | 24978 | - | 24978 | 8326 | 0
Base-Build | WWT | Labor | USC24C006 | WWT B side Project | 4299 | C | USCSB2406067A |  | (A side) Support _Hua Yi close PR_ batch 2/2 | 45455 | 45462 | 151835 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 151835 | 0 | 151835 | 151835 | [71 empty] | 30367 |  | - | 30367 | - | 30367 | 30367 | 30367
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4300 | C | USCSB2406068A |  | install MIC supplied Door hardware on fire doors at mezzanines 1 and 2, (5 sets of doors total) | 2024/6/12 2024/7/02 | 2024/6/25 2024/7/02 | 4091 | [5 empty] | V | ISEC Incorporated | PR Approved | PO Approved | PR R1: Per ISEC's request- revised the terms and completion dates | [13 empty] | 4091 | 1 | 0 | 78800 | -78800 | 4091 | [70 empty] | 4091 | 2045.5 |  | - | 2045.5 | - | 0 | 0 | 0
Base-Build | CCTV |  | USC22C013 | F21P1 QR Lab Security & CCTV | 4301 | C | USCSB2406069A |  | F21 Chemical system control cable | 45455 | 45460 | 61428 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 61428 | 0 | 61428 | 0 | [73 empty] | - |  | 61428 |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4302 | C | USCSB2406070A |  | breakers for TSMC Grant Chen for P1B tools | 45456 | 45459 | 6550 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6550 | 5490 | 1060 | 0 | [73 empty] | - |  | 6550 |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4303 | C | USCSB2406071A |  | Chemical Team Urgent Materials Wire First Priority (化學系統控制線材0611第一優先級購買) | 45456 | 45460 | 225468.02 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 101962.42 | 0.45223 | 123505.6 | 0 | 123505.6 | 0 | [73 empty] | 101962.42 |  | 72730.56 |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4304 | C | USCSB2406072A |  | P1B power tool request for Third, tool base is 50 tools | 45456 | 45459 | 1867.42 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1514.25 | 0.81088 | 353.17 | 0 | 353.17 | 0 | 1514.25 | [72 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4305 | C | USCSB2406073A |  | FAB A CO2 System Inspection(The 70% remaining) | 45456 | 45461 | 369824 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved | [14 empty] | 129438 | 0.35 | 240386 | 9775 | 230611 | 0 | [70 empty] | 129438 |  |  | - |  | 240386 |  | 0
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4306 | C | USCSB2406074A |  | AMHS DP Breakers due to TSMC Design Change | 45457 | 45471 | 7950 | [6 empty] | THIRD ENTERPRISE CO., LTD | PR Approved | PO Approved | [14 empty] | 7950 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 7950 | - |  | - |  | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 4307 | C | USCSB2406075A |  | M0495 Foundation manufacture_2 | 45457 | 45474 | 5372 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 5372 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 5372 |  | - |  | 0
Base-Build | CCTV |  | USC24C007 | Low Voltage B Side Project | 4308 | C | USCSB2406076A |  | F21-P1_B-SIDE CCTV & ACCESS (L20 HPM) | 45457 | 45460 | 300779 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 300779 | 0 | 300779 | 285740.05 | [71 empty] | 150389.5 |  | - | 135350.55 | 148379.28 |  | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4309 | C | USCSB2406077A |  | One additional tile for KDSET1_ AIB-C-06 | 45457 | 45461 | 4533 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 4533 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 4533 |  |  | - |  | - |  | 0
Base-Build | CCTV |  | USC22C013 | F21P1 QR Lab Security & CCTV | 4310 | C | USCSB2406078A |  | F21-P1_B-SIDE Photoresist cabinet exhaust hookup | 45457 | 45457 | 288.96 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 288.96 | 0 | 288.96 | 0 | [73 empty] | - |  | 288.96 |  | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4311 | C | USCSB2406080A |  | FAB CO2 System Permit and Inspection | 45457 | 45463 | 274320 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved | [14 empty] | 0 | 0 | 274320 | 0 | 274320 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4312 | C | USCSB2406081A |  | F21 A side CPVC 未完成工作0613 | 45457 | 45463 | 288900 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved | [14 empty] | 57780 | 0.2 | 231120 | 0 | 231120 | 0 | [73 empty] | 57780 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4319 | C | USCSB2406082A |  | FAB Chemical Observation - LSW | 45457 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Change the budget code. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4325 | C | USCSB2406083A |  | Twist drill bits for HK PPL Trade | 45457 | 45469 | 40.23 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 33.28 | 0.82724 | 6.95 | 0 | 6.95 | 0 | 33.28 | [72 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4320 | C | USCSB2406084A |  | 化學系統控制線材0613 for priority 3 | 45457 | 45461 | 73400 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 73400 | 0 | 73400 | 0 | [73 empty] | - |  | 24672 |  | 0
Base-Build | WWT |  | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4321 | C | USCSB2406085A |  | Mess remaining painting Jeff | 45458 | 45464 | 70906.95 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 67361.6 | 0.95 | 3545.35 | 0 | 3545.35 | 0 | [70 empty] | 67361.6 | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4322 | C | USCSB2406086A |  | WWT Ball Valve_20240613 (B Side) | 45458 | 45463 | 23942.3 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23942.3 | 0 | 23942.3 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4339 | C | USCSB2406087A |  | KCENA4 Heat Shrinks | 45458 | 45483 | 33.74 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 33.74 | 1 | 0 | 971.3 | -971.3 | 0 | 33.74 | [72 empty] | - |  | - |  | 0
Base-Build | Slurry |  | USC21C005 | F21P1 Chemical & WCCS package | 4323 | C | USCSB2406088A |  | FAB A SDS Observation | 45458 | 45463 | 59110 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 2015 | 0.034089 | 57095 | 0 | 57095 | 0 | [72 empty] | 2015 | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4324 | C | USCSB2406089A |  | WWT B Side Instrument Batch 2 | 45458 | 45463 | 35680.03 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 35680.03 | 452415.728 | -416735.698 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4325 | C | USCSB2406090A |  | PR Harrington WWT - WRC Material Line Rework Chem Lines 203, 204, 103, 104(A side) | 45461 | 45464 | 42178.61 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 42178.61 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 40765.51 |  | 1413.1 | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | Micron - Material |  | USC24C001 | Micron - Chemical SOLBLE RN3000 | 4326 | C | USCSB2406091A |  | SOLBLE RN3000 250kg x 4 drums for Micron Manassas facility, Virginia | 45461 | 45467 | 79600 | [6 empty] | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved | [14 empty] | 79600 | 1 | 0 | 35969.78 | -35969.78 | 0 | [70 empty] | 79600 |  |  | - |  | - |  | 0
Base-Build | TMAH |  | USC21C011 | F21 TMAH System | 4327 | C | USCSB2406092A |  | PR Harrington WWT - TMAH Expansion Material (PP) | 45461 | 45464 | 56795.35 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 56795.35 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 55584.91 |  | 167.31 | 0 |  | 1043.13 | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4328 | C | USCSB2406093A |  | FAB Chemical Observation - LSW | 45462 | 45463 | 542050 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 59080 | 0.10899 | 482970 | 0 | 482970 | 0 | [72 empty] | 59080 | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4330 | C | USCSB2406095A |  | F21P1 B Side Pillar - PFA | 45462 | 45464 | 374081.95 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | [14 empty] | 363567.55 | 0.97189 | 10514.4 | 0 | 10514.4 | 0 | [70 empty] | 363567.55 |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4331 | C | USCSB2406096A |  | F21P1 B side 彰京 - PFA | 45462 | 45467 | 160828 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 160828 | 0 | 160828 | 0 | [73 empty] | - |  | - |  | 0
Others | AMHS |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4332 | C | USCSB2406097A |  | HPM Panel Protection | 45462 | 45489 | 169888 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 169888 | 0 | 169888 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4333 | C | USCSB2406098A |  | UPW B Side Panel Materials | 45462 | 45467 | 2350 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 2350 | 1 | 0 | 282887.278 | -282887.278 | 0 | [68 empty] | 2350 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4334 | C | USCSB2406099A |  | B side/A side punch fix team (Yi Sheng) | 2024/6/19 2024/8/12 | 2024/7/8 2024/8/12 | 166400 | 27200 | 193600 | V |  |  |  | YI-SHENG engineering Co.,Ltd | PR Approved | PO Approved | PR R1: Revise the PR amount after purchasing team negotiation per David Wang. | [13 empty] | 0 | 0 | 166400 | 269677 | -103277 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4335 | C | USCSB2406100A |  | AMHS 25K Feet Channel Tray CO | 45463 | 45468 | 1180902.8 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 1180902.8 | 1 | 0 | 251593.05 | -251593.05 | 0 | [64 empty] | 1180902.8 | [8 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC24C009 | F21P1 Nova Interconnection | 4371 | C | USCSB2406101A |  | PCA: NOVA: KUECN4-7: CO PRESSURE TESTING | 45463 | 45498 | 5490 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5490 | 142512.8 | -137022.8 | 0 | [73 empty] | - |  | - |  | 0
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4337 | C | USCSB2406102A |  | AMHS DP Meggar Testing CO | 45463 | 45468 | 74880 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 74880 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 74880 | [8 empty] | - |  | - |  | 0
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4338 | C | USCSB2406103A |  | AMHS PSP Additional 1 AWG 3/C Wire CO | 45463 | 45467 | 512375.38 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 512375.38 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 512375.38 | [8 empty] | - |  | - |  | 0
Base-Build | Chemical | CRG | USC24C005 | Chemical & WCCS B Side Project | 4339 | C | USCSB2406104A |  | TSMC / FAB21: BEND 85 EACH 90 DEGREE ELBOWS WITH A 16" RADIUS WITH 2" DIAMETER .065 WALL 316 SS. | 45463 | 45471 | 9775 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9775 | 15.12 | 9759.88 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4340 | C | USCSB2406105A |  | Hand tools shared by all HK trades | 45463 | 45464 | 5939.07 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 4877.15 | 0.8212 | 1061.92 | 0 | 1061.92 | 0 | 4877.15 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4341 | C | USCSB2406106A |  | HK 6 Scissor lifts rental for 4 week | 45464 | 45464 | 5395.25 | [6 empty] | United Rentals | PR Approved | PO Approved | [14 empty] | 1581.49 | 0.29313 | 3813.76 | 0 | 3813.76 | 0 | [72 empty] | 1581.49 | - |  | 670.55 |  | 0
Base-Build | VOC |  | USC22C013 | F21P1 QR Lab Security & CCTV | 4342 | C | USCSB2406107A |  | B side VOC duct modification | 45464 | 45465 | 12000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 8687.62 | 0.72397 | 3312.38 | 71864 | -68551.62 | 12000 | [70 empty] | 8687.62 |  |  | - | 12000 | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4343 | C | USCSB2406108A |  | CVD Brycon Material | 45464 | 45484 | 1839.08 | [6 empty] | Brycon Corporation | PR Approved | PO Approved | [14 empty] | 1839.08 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1839.08 |  |  | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4349 | C | USCSB2406109A |  | Per purchasing team request. initiate a new PR to write off this invoice. | 45464 | 45471 | 2184.47 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 2184.47 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 2184.47 | [10 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4350 | C | USCSB2406110A |  | LSR MU 元富 scope lump sump | 45465 | 45475 | 500500 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 500500 | 0 | 500500 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4351 | C | USCSB2406111A |  | WWT Cleaning Material | 45465 | 45467 | 339.4 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 329 | 0.96936 | 10.4 | 0 | 10.4 | 0 | 329 | [70 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4352 | C | USCSB2406112A |  | WWT - PR Brahma A-Side FRP T-740AA-AB-AC Tank Interconnection Spools(A side) | 45465 | 45471 | 68309.09 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 68042.31 | 0.99609 | 266.78 | 951.91 | -685.13 | 0 | [70 empty] | 68042.31 | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4353 | C | USCSB2406113A |  | WWT: CCR Scope Initial Funding to Start Work | 45465 | 45475 | 50000 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 50000 | 0 | 50000 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4354 | C | USCSB2406114A |  | WWT: CCR System Scope | 45465 | 45475 | 449679 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 342119.7 | 0.76081 | 107559.3 | 500 | 107059.3 | 0 | [70 empty] | 52216.75 | 0 |  | 289902.95 | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4355 | C | USCSB2406115A |  | F21P1 HPM L10B CDU/DHL CDA/GN2 | 45465 | 45469 | 91105.48 |  | 65 |  |  |  |  | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 75213.52 | 0.82557 | 15891.96 | 0 | 15891.96 | 0 | [66 empty] | 15344.62 |  | 29433.62 |  | 13950.3 |  |  | 16484.98 |  | 15891.96 |  | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4356 | C | USCSB2406116A |  | lay down box | 45467 | 45468 | 769.85 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 769.85 | 0 | 769.85 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4357 | C | USCSB2406117A |  | CED-訊號電力材料_20240621 (Signal Wire Material) | 45467 | 45468 | 5444.44 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5444.44 | 0 | 5444.44 | 0 | [73 empty] | - |  | 423.15 |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4358 | C | USCSB2406118A |  | F21 AMAT PVD last 4 machine | 45468 | 45469 | 80000 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 80000 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 80000 |  |  |  |  | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4359 | C | USCSB2406120A |  | AMAT TW trade P1B 2nd 33 machine material | 45468 | 45471 | 565519.66 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 565519.66 | 13230 | 552289.66 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4360 | C | USCSB2406121A |  | [Pure] SS box door | 45468 | 45474 | 21551.14 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | [14 empty] | 15085.8 | 0.7 | 6465.34 | 540 | 5925.34 | 0 | [72 empty] | 15085.8 | - |  | 6465.34 |  | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 4361 | C | USCSB2406122A |  | TSMC UPW P1B materials_panels | 45468 | 45474 | 2361781.26 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 317940.25 | 0.13462 | 2043841.01 | 0 | 2043841.01 | 0 | [72 empty] | 88457.94 | 229482.31 |  | - |  | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4362 | C | USCSB2406123A |  | Cleanroom tapes for foundation | 45468 | 45468 | 720 | [6 empty] | Xiang Sheng Hardware Enterprise Co., Ltd. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 720 | 0 | 720 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4363 | C | USCSB2406124A |  | F21 A Side Lorry Expansion Joint | 45468 | 45474 | 29353.4 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29353.4 | 0 | 29353.4 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4364 | C | USCSB2406125A |  | A區系統區閥件追加_球閥及接頭部分 | 45468 | 45476 | 20109.6 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 20109.6 | 23784.63 | -3675.03 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | VOC |  | USC24C007 | Low Voltage B Side Project | 4365 | C | USCSB2406126A |  | F21-P1_B-Side mask room gas piping hookup_batch 1/2 | 45468 | 2024/7/3 2024/7/8 | 196000 | -19235.7 | 215235.7 |  |  |  |  | Welmade Technology Corporation | PR Approved | PO Approved | R1: Per supplier request to split the amount to align with quote item# for USCSB2406126A & 127A - Total stays the same | [13 empty] | 0 | 0 | 196000 | 0 | 196000 | 196000 | [73 empty] | - | 29400 | - | 39200 | 117600 | 9800
Base-Build | VOC |  | USC22C013 | F21P1 QR Lab Security & CCTV | 4366 | C | USCSB2406127A |  | F21-P1_B-Side mask room gas piping hookup_batch 2/2 | 45468 | 2024/7/3 2024/7/8 | 85711.22 | 19235.7 | 66475.52 |  |  |  |  | Welmade Technology Corporation | PR Approved | PO Approved | R1: Per supplier request to split the amount to align with quote item# for USCSB2406126A & 127A - Total stays the same | [13 empty] | 0 | 0 | 85711.22 | 0 | 85711.22 | 85711.22 | [73 empty] | - | 12856.68 | - | 17142.24 | 51426.74 | 4285.56
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4367 | C | USCSB2406128A |  | AMAT TW trade P1B 1st 24 machine material | 45468 | 45471 | 282887.28 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 282887.28 | 0 | 282887.28 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4368 | C | USCSB2406129A |  | 捨得人力-點工人力(13人 6-8月) | 2024/6/25 2024/6/28 | 45482 | 269677 | [6 empty] | AUCAN INC | PR Approved | PO Approved | PR R1:Due to vendor update the quote. | [13 empty] | 0 | 0 | 269677 | 0 | 269677 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4369 | C | USCSB2406130A |  | AMAT TW trade P1B 3th 33 machine material | 45469 | 45471 | 251593.05 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 251593.05 | 0 | 251593.05 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical | CRG | USC21C005 | F21P1 Chemical & WCCS package | 4370 | C | USCSB2406131A |  | TSMC / FAB21: SIDE A H202 ROOM ADDITIONAL SUPPORTS | 45469 | 45470 | 142512.8 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 142512.8 | 0 | 142512.8 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4371 | C | USCSB2406132A |  | 0613 缺料明細材料報價 | 45469 | 45475 | 14641.06 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14641.06 | 0 | 14641.06 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4372 | C | USCSB2406133A |  | Amazon Loto PR for Power Luis Retiz for 100 LOTO for 7 tools | 45469 | 45469 | 1370.06 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1218.51 | 0.88938 | 151.55 | 0 | 151.55 | 0 | 1218.51 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4373 | C | USCSB2406134A |  | Grainger Loto PR for Power Luis Retiz for 100 LOTO for 7 tools | 45469 | 45470 | 211.7 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 211.7 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 211.7 | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4374 | C | USCSB2406135A |  | Hex Panel Nut and Shims/ for 5 tools/ tool hookup team | 2024/6/26 2024/6/28 | 45472 | 63.38 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | PR R1:change shipping cost to usd $10. | [13 empty] | 63.36 | 0.99968 | 0.02 | 0 | 0.02 | 0 | [68 empty] | 63.36 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT |  | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4375 | C | USCSB2406136A |  | sand,prep,expoxy and yellow safety paint at one house keeping pad. | 45470 | 45472 | 1604 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 1604 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 1604 |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4376 | C | USCSB2406137A |  | WRC SS Bypass(UPW SUS fix bypass only) | 45470 | 2024/8/1 2024/9/5 | 132224 | -11999 | 144223 |  |  |  | V | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | PO R1: Scope Change to Not Include QA/QC | [13 empty] | 0 | 0 | 132224 | 6482.99 | 125741.01 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4377 | C | USCSB2406138A |  | HK PCW tool request for 100 tools | 45470 | 45471 | 353.76 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 279.4 | 0.7898 | 74.36 | 0 | 74.36 | 0 | 279.4 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4378 | C | USCSB2406139A |  | Anchor Strut Fasteners for Fall Protection Working at Heights per TSMC Requirements | 45470 | 2024/6/27 2024/6/29 | 418.92 | -41.89 | 460.81 |  |  |  |  | NEFCO Construction Supply LLC | PR Approved | PO Approved | PO R1:Removed unnecessary buffer | [13 empty] | 418.92 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 418.92 |  | - |  | 0
Base-Build | UPW | Material | USC24C008 | UPW B Side Project | 4379 | C | USCSB2406141A |  | Ladder Safety System Materials | 45471 | 45474 | 5310 | [6 empty] | Diversified Products USA | PR Approved | PO Approved | [14 empty] | 5310 | 1 | 0 | 522.36 | -522.36 | 0 | [70 empty] | 5310 |  |  | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4380 | C | USCSB2406142A |  | HK P1B NFPA 70E Electrical Hazards Training required for people working with or around electricity. | 45471 | 45476 | 8300 | [6 empty] | LC LIND, LLC | PR Approved | PO Approved | [14 empty] | 8300 | 1 | 0 | 265.5 | -265.5 | 0 | [68 empty] | 8300 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4381 | C | USCSB2406143A |  | WWT Contain-it double pipe | 45471 | 45471 | 3098.6 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2432.4 | 0.785 | 666.2 | 0 | 666.2 | 0 | [68 empty] | 1908.7 |  |  | 0 | 523.7 | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4382 | C | USCSB2406144A |  | WWT- Brahma T-740Bs FRP Interconnection, T-110Bs Additional Flange Coating | 45471 | 45476 | 44781.12 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 43754.24 | 0.97707 | 1026.88 | 5363 | -4336.12 | 0 | [70 empty] | 43754.24 | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4383 | C | USCSB2406145A |  | CED Wire cut charge for HK Power trade for 1 tool | 45471 | 45472 | 2500 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2500 | 2768.76 | -268.76 | 0 | [73 empty] | - |  | 2000 |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4384 | C | USCSB2406146A |  | WWT - Brahma T-140AC-AC Carboline Flange Coating | 45471 | 45476 | 53131.05 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 38618.12 | 0.72685 | 14512.93 | 0 | 14512.93 | 0 | [70 empty] | 38618.12 | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | Micron - Material |  | USC24C001 | Micron - Chemical SOLBLE RN3000 | 4385 | C | USCSB2406147A |  | SOLBLE RN3000 250kg x 10 drums for Micron Manassas facility, Virginia | 45471 | 2024/7/16 2024/7/19 | 194050 | 2700 | 191350 |  |  |  |  | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved | [14 empty] | 194050 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 194050 | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4396 | C | USCSB2406148A |  | 儀表採樣箱收缺失之材料 | 45471 | 45476 | 5985 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5985 | 0 | 5985 | 5985 | [71 empty] | 2992.5 |  | - | 2992.5 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 4397 | C | USCSB2406149A |  | QA/QC for Gas Piping System in Furnace for Diffusion for tool ID#KDTNK2 | 45471 | 45478 | 12400 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | [14 empty] | 12400 | 1 | 0 | 44.09 | -44.09 | 0 | [73 empty] | 12400 |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4398 | C | USCSB2406151A |  | CED 化學系統電力訊號線0627 (CED Cat 6 Plenum Rated Cable) | 45472 | 45474 | 13230 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13230 | 659.84 | 12570.16 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4399 | C | USCSB2406152A |  | Y terminals for HK Power P1B 40 tools | 45472 | 45475 | 540 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 540 | 0 | 540 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4400 | C | USCSB2406153A |  | These will be for P1B signoff documents and for staff to carry extra copies with them. | 45472 | 45475 | 94.13 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 49.47 | 0.52555 | 44.66 | 0 | 44.66 | 0 | 49.47 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4401 | C | USCSB2406154A |  | For GAS and Plastic system, 100 tools | 2024/6/30 2024/9/26 | 2024/7/1 2024/9/26 | 625.95 | -161.46 | 787.41 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: Per purchaning team request, amend to the final amount. | [13 empty] | 625.95 | 1 | 0 | 0 | 0 | 0 | 625.95 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4402 | C | USCSB2406155A |  | Ryan Herco: Rental fee cover April and May. | 45473 | 45475 | 20279.1 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 20279.1 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 20279.1 | [8 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4403 | C | USCSB2407001A |  | CED 化學系統電力訊號五金0627 (CED Chem Signal Cable Hardware) | 45474 | 45474 | 23743.52 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23743.52 | 0 | 23743.52 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4404 | C | USCSB2407002A |  | CED 化學系統線0627 | 2024/7/1 2024/7/4 | 45475 | 0 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1:As per engineer Johnny Wan to cancel the PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4405 | C | USCSB2407003A |  | EES 防爆接線盒0627 (Made-to-Order Explosion Proof Box) | 45474 | 45476 | 7106 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 7106 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 7106 |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4406 | C | USCSB2407004A |  | 泉太 MICU E2 支援報價單(2個月) | 45474 | 45478 | 52000 | [6 empty] | CHEN-TAI-ENTERPRISE CO.,LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 52000 | 0 | 52000 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4407 | C | USCSB2407005A |  | F21P1 Fab LB2 WWT Tank H2SO4 Header | 45474 | 45474 | 2100 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | [14 empty] | 2100 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 2100 |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4408 | C | USCSB2407006A |  | F21P1 Fab HMP Mixing box | 45474 | 45475 | 992 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | [14 empty] | 992 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 992 |  |  | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4409 | C | USCSB2407007A |  | WWT Inventory Management System_2 year | 2024/7/1 2024/7/18 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Due to it can use the company's system,so as per purchasing team to cancel the PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4410 | C | USCSB2407009A |  | A+B side sump pump L10(labor + material) | 2024/7/2 2024/7/9 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: AS per engineer Jim to cancel this order, WWT decide to have another vendor working on it. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4411 | C | USCSB2407010A |  | WWT Hardware #1 | 45475 | 45476 | 1875.15 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1875.15 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 1875.15 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4412 | C | USCSB2407011A |  | B side gasket 補料 | 45475 | 45477 | 5553 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5553 | 34977.25 | -29424.25 | 5553 | [71 empty] | 2776.5 |  | - | 2776.5 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4413 | C | USCSB2407012A |  | These instruments will be installed for control system of B site. | 45475 | 45475 | 3598 | [6 empty] | Process Technology, Inc | PR Approved | PO Approved | [14 empty] | 3598 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3598 | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4414 | C | USCSB2407013A |  | F21P1 HPM CDU/DHL CDA/GN2 | 45475 | 45479 | 28521 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 28521 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 28521 | [6 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4415 | C | USCSB2407014A |  | Wires for chemical tank area | 45475 | 45478 | 6482.99 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6482.99 | 0 | 6482.99 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4416 | C | USCSB2407015A |  | 珠光不上膜白底黑字圓 | 45475 | 45475 | 260 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | [14 empty] | 260 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 260 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT |  | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4417 | C | USCSB2407016A |  | WWT - SCS Lorry to tunnel confined space rescue | 45475 | 45482 | 1950 | [6 empty] | Safety Compliance Services, Inc | PR Approved | PO Approved | [14 empty] | 1950 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 | 1950 | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4418 | C | USCSB2407017A |  | Mobile Storage Container Combo Office for HK | 2024/7/2 2024/7/4 | 45479 | 5302 | [6 empty] | Allied Storage Containers | PR Approved | PO Approved | PR R1:Revise to 6 months | [13 empty] | 3960.7 | 0.74702 | 1341.3 | 0 | 1341.3 | 0 | [66 empty] | 2052 |  |  |  | 993.7 |  | 495 | 420 |  | 275 |  | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4419 | C | USCSB2407018A |  | 8 AWG Max Wire Size | 45475 | 45485 | 265.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 265.5 | 0 | 265.5 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4420 | C | USCSB2407019A |  | HK Power Luis escape strap request | 45475 | 45491 | 3486.7 | [6 empty] | Paramount Corp DBA Oberon | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3486.7 | 0 | 3486.7 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | VOC |  | USC22C013 | F21P1 QR Lab Security & CCTV | 4421 | C | USCSB2407020A |  | F21 P1 VOC duct insulation | 45475 | 45479 | 58950 | [6 empty] | Petrochem Insulation, Inc | PR Approved | PO Approved | [14 empty] | 53587 | 0.90902 | 5363 | 0 | 5363 | 43580 | [72 empty] | 15370 | 38217 | 43580 | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4422 | C | USCSB2407021A |  | Mast Lift 25ft for HK shared by all systems | 45476 | 45482 | 25668.15 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 9653.54 | 0.37609 | 16014.61 | 2982.85 | 13031.76 | 0 | [73 empty] | 9653.54 |  | 692.19 |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4452 | C | USCSB2407023A |  | Materials for gasket on Fab B side | 2024/7/3 2024/7/4 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Duplicate one, return to cancel per engineer Jim. | [13 empty] | 0 | 1 | 0 | 6178.61 | -6178.61 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4423 | C | USCSB2407024A |  | Storage containers for tools and materials for Fab A side | 45476 | 45476 | 799 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 799 | 0 | 799 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4424 | C | USCSB2407025A |  | F21P1 B Side PFA - Nylon Line | 2024/7/3 2024/7/9 | 45484 | 1238.15 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | PR R1:Add shipping & handling&10% buffer | [13 empty] | 1125.59 | 0.90909 | 112.56 | 0 | 112.56 | 0 | 1125.59 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4425 | C | USCSB2407026A |  | Fresh water tank for 6 months for HK shared by all system | 45476 | 45479 | 3413.95 | [6 empty] | United Rentals | PR Approved | PO Approved | [14 empty] | 838.17 | 0.24551 | 2575.78 | 0 | 2575.78 | 0 | [68 empty] | 749.99 |  |  |  | 44.09 | 44.09 |  | - |  | 0
Base-Build | WWT |  | USC23C045 | WWT Change Order (Piping) | 4426 | C | USCSB2407027A |  | A site LB2 VFD power cable re-pull | 45477 | 45476 | 659.84 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 659.84 | 0 | 659.84 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4427 | C | USCSB2407028A |  | Modify 6 Beams on Cable Tray Rack LB2 B side | 45477 | 45483 | 13684.48 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13684.48 | 0 | 13684.48 | 0 | [71 empty] | 0 |  | - | 0 | 13684.48 | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4428 | C | USCSB2407029A |  | Pressure washer, hose, and sump pump for HK MIMO | 45477 | 45478 | 217.31 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 217.31 | 0 | 217.31 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4429 | C | USCSB2407030A |  | Generators rentals for HK MIMO for 6 months | 45477 | 2024/7/9 2024/7/11 | 11027.53 | -1818.97 | 12846.5 |  |  |  |  | Herc Rentals Inc. | PR Approved | PO Approved | PO R1: James McCormick got a lower price revised quotation from Herc | [13 empty] | 3964.12 | 0.35947 | 7063.41 | 0 | 7063.41 | 0 | [72 empty] | 1982.06 | 1982.06 |  | 1982.06 |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4430 | C | USCSB2407031A |  | Tools for HK PCW for 100 tools | 45477 | 45477 | 1489.62 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1261.9 | 0.84713 | 227.72 | 0 | 227.72 | 0 | 1261.9 | [72 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4431 | C | USCSB2407032A |  | Materials for B side LB 1 Drain | 45479 | 45481 | 1958.08 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 1958.08 | 1 | 0 | 80641.31 | -80641.31 | 0 | [68 empty] | 1958.08 |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4432 | C | USCSB2407033A |  | Opening 10 B Side STKs | 45482 | 45486 | 34286.4 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 34286 | 0.99999 | 0.4 | 0 | 0.4 | 0 | [70 empty] | 34286 |  |  | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4433 | C | USCSB2407034A |  | B Side EEW PPE for HK Power for 100 tools | 2024/7/9 2024/7/13 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:change project code | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT | Material | USC24C006 | WWT B side Project | 4434 | C | USCSB2407035A |  | Sticker | 45482 | 45484 | 1079.74 | [6 empty] | StickerYou Inc. | PR Approved | PO Approved | [14 empty] | 1050.79 | 0.97319 | 28.95 | 0 | 28.95 | 1079.74 | 1050.79 | [70 empty] | 1079.74 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4435 | C | USCSB2407036A |  | B Side ELECTRICAL RUBBER GLOVE INFLATION TOOL for HK Power for 100 tools | 45482 | 45502 | 97.5 | [6 empty] | JM Test Systems, LLC | PR Approved | PO Approved | [14 empty] | 82.5 | 0.84615 | 15 | 0 | 15 | 0 | 82.5 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4436 | C | USCSB2407037A |  | B Side Power tower for HK Power for 100 tools | 45482 | 45483 | 1245 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1245 | 1 | 0 | 0 | 0 | 0 | 1245 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4437 | C | USCSB2407038A |  | B Side Insulating Roll Blanket for HK Power for 100 tools | 45482 | 45490 | 600.99 | -589.75 | 1190.74 |  |  |  |  | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved | [14 empty] | 0 | 0 | 600.99 | 0 | 600.99 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | UPW | Material | USC24C008 | UPW B Side Project | 4438 | C | USCSB2407039A |  | Valve Handles for B Area | 45482 | 45482 | 1313 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved | [14 empty] | 1313 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1313 |  |  | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4439 | C | USCSB2407040A |  | P1B Self Adhesive Cable Zip Tie for HK Power fot 300 tools | 45482 | 45483 | 30.79 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 26.99 | 0.87658 | 3.8 | 0 | 3.8 | 0 | 26.99 | [72 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4440 | C | USCSB2407041A |  | A site punch | 45482 | 2024/7/12 2024/7/15 | 34977.25 | -734.4 | 35711.65 |  |  |  |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Supplier offer better price after negotiation | [13 empty] | 0 | 0 | 34977.25 | 0 | 34977.25 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4441 | C | USCSB2407042A |  | EES 防爆接線盒0708 | 45482 | 45483 | 16608.23 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 16608.23 | 1 | 0 | 18235 | -18235 | 0 | [70 empty] | 16608.23 |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4442 | C | USCSB2407043A |  | CHEM_WCCS SUS project_ for CDS/ SDS VMB supports | 45482 | 45483 | 26940 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved | [14 empty] | 26940 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 26940 |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4443 | C | USCSB2407044A |  | WWT- threaded machine | 2024/7/10 2024/7/11 | 45483 | 3750 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | PR R1:No need buffer as we found out can be purchased from Ferguson | [13 empty] | 3750 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3750 | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | Organo |  | USC24C013 | Organo USA - UPW Electrical | 4444 | C | USCSB2407045A |  | MCP Fan Cover | 45483 | 45484 | 200 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 200 | 0 | 200 | 0 | [73 empty] | - |  | 200 |  | 0
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4445 | C | USCSB2407046A |  | A Side AC Panel Relocation | 45483 | 45485 | 49800 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 47310 | 0.95 | 2490 | 11135 | -8645 | 0 | [73 empty] | 47310 |  | - |  | 0
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4446 | C | USCSB2407047A |  | 5 Yisin AMHS Engineers support Muratec | 45483 | 45489 | 12500 | [6 empty] | Yi Sin Mechanical LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 12500 | 0 | 12500 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4447 | C | USCSB2407048A |  | Shelf for Plastic system, extension cord for welding machine | 2024/7/10 2024/9/26 | 2024/7/11 2024/9/26 | 1328.43 | -145 | 1473.43 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: Per purchasing team request, this should change to the final amount. | [13 empty] | 1328.43 | 1 | 0 | 0 | 0 | 0 | 1328.43 | [72 empty] | - |  | - |  | 0
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4448 | C | USCSB2407049A |  | 9 YCF AMHS Engineers support Muratec from 12/13/23~3/27/24 | 45483 | 45511 | 13719.85 | [6 empty] | YUNG CHENG FENG ENGINEERING CO.,LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13719.85 | 2315 | 11404.85 | 0 | [73 empty] | - |  | - |  | 0
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4449 | C | USCSB2407050A |  | 7 YCF AMHS Engineers support Muratec from 6/10/24~12/10/24 | 2024/7/10 2024/9/27 | 2024/7/27 2024/9/30 | 34292.54 | 15392.54 | 18900 | V |  |  |  | YUNG CHENG FENG ENGINEERING CO.,LTD. | PR Approved | PO Approved | R1: Adjust price and terms due to DBA compliance requirements | [13 empty] | 0 | 0 | 34292.54 | 142933.44 | -108640.9 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4450 | C | USCSB2407051A |  | Painting mess CO | 45483 | 45489 | 59656.95 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 56674.1 | 0.95 | 2982.85 | 0 | 2982.85 | 0 | [71 empty] | 0 |  | 56674.1 | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4451 | C | USCSB2407052A |  | Onsite Trailers | 45483 | 45485 | 6178.61 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6178.61 | 0 | 6178.61 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 4452 | C | USCSB2407053A |  | Material for P1B to bulk order Tubing | 2024/7/10 2024/7/24 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:order canceled Steven wants a different vendor | [13 empty] | 0 | 1 | 0 | 39080.38 | -39080.38 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4453 | C | USCSB2407054A |  | To supplement the damage and missing leak sensor cable for site A and site B. | 45483 | 45486 | 3800 | [6 empty] | Autotronic Enterprise Co., Ltd | PR Approved | PO Approved | [14 empty] | 3800 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 3800 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4454 | C | USCSB2407056A |  | P1B EEW PPE for HK Power for 100 tools | 45484 | 45498 | 18642.08 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 10029.42 | 0.538 | 8612.66 | 0 | 8612.66 | 0 | 3240 | [67 empty] | 6789.42 |  |  |  |  | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4485 | C | USCSB2407056B |  | P1B EEW PPE for HK Power for 100 tools | 45484 | 45499 | 7995.67 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7995.67 | 113646 | -105650.33 | 0 | [73 empty] | - |  | 7995.67 |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4475 | C | USCSB2407057A |  | ATF-C/ KCUVA7 QC work, KCUVA1/ KCUVA2 Tube Work, KCUVA1/ KCUVA2 QC Work | 45484 | 45510 | 41930 | [6 empty] | CT-TECH USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 41930 | 0 | 41930 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 4455 | C | USCSB2407058A |  | PVD CIP DI-max | 45484 | 45485 | 5600 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 5600 | 1 | 0 | 13355.75 | -13355.75 | 0 | [70 empty] | 5600 |  |  | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4456 | C | USCSB2407059A |  | P1B EEW PPE 3/8" Drive SAE Insulated Hex Head Sockets - Extra Long for 100 tools | 2024/7/11 2024/7/23 | 45498 | 462.95 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | pr r1:change vendor | [13 empty] | 462.1 | 0.99816 | 0.85 | 0 | 0.85 | 0 | [68 empty] | 462.1 |  |  |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4457 | C | USCSB2407060A |  | CHEM_CDS project_Ladder and EXT code | 45484 | 45484 | 619.03 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 619.03 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 619.03 |  |  | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4458 | C | USCSB2407061A |  | CED 化學系統線0710 | 45484 | 45488 | 80641.31 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 80641.31 | 0 | 80641.31 | 0 | [73 empty] | - |  | - |  | 0
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4459 | C | USCSB2407062A |  | AMHS - Cleanroom Supplies | 45484 | 45488 | 1917.44 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 1917.44 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1917.44 |  |  | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4460 | C | USCSB2407063A |  | WWT FAB Chemical dump centralizer | 45484 | 45488 | 3536 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | [14 empty] | 3536 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3536 | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4461 | C | USCSB2407064A |  | WWT: OPEN PO III | 45484 | 2024/7/16 2024/7/24 | 100000 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | PO R1: Change Contract Out Name | [13 empty] | 93016.68 | 0.93017 | 6983.32 | 0 | 6983.32 | 0 | [71 empty] | 0 |  | 93016.68 | 0 | 263.77 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4483 | C | USCSB2407065A |  | U- Bolts and Hex Nut Zinc for P1B Material | 45484 | 45496 | 558.11 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 558.11 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 29.61 |  | 528.5 | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4484 | C | USCSB2407066A |  | Chemical dump ( 1 month) | 2024/7/11 2024/7/24 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Cancelled per PM Andy confirmation | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C029 | EBO21- Tool interconnection | 4485 | C | USCSB2407067A |  | EBO: ZKT-6 ENVIRONMENTAL ENCLOSURE | 45485 | 45490 | 6951.97 | [6 empty] | Brycon Corporation | PR Approved | PO Approved | [14 empty] | 6951.97 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 6951.97 | - |  | - |  | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 4462 | C | USCSB2407068A |  | Ryan Herco USCSB2204014A extension PO | 45485 | 45489 | 63489.56 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 63489.56 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 63489.56 | [8 empty] | - |  | - |  | 0
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4487 | C | USCSB2407069A |  | UMEC GC for 2024 March & April | 45486 | 45492 | 856637 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 813805 | 0.95 | 42832 | 0 | 42832 | 0 | [68 empty] | 813805 |  |  |  |  | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4488 | C | USCSB2407070A |  | M200 calibration service | 45486 | 45489 | 3600 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Processing | 因機台為MICU對下包以租賃形式，所有維修、校正皆不須由MICU負擔，故取消此單 | [13 empty] | 0 | 0 | 3600 | 0 | 3600 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4489 | C | USCSB2407072A |  | LB-1 Sump Pump Piping - Train A/Train B_WWT UMEC scope | 45486 | 45500 | 182350 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 126551 | 0.694 | 55799 | 0 | 55799 | 0 | [70 empty] | 99198 | 0 | 27353 | - | 0 | 28447 | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4490 | C | USCSB2407073A |  | WWT CrPVC pipes for dump | 45486 | 45488 | 18936 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 18936 | 1 | 0 | 327359.1 | -327359.1 | 0 | [71 empty] | 0 | 18936 | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4491 | C | USCSB2407075A |  | Mfr. No.XC5585-CB Cleanbuild Construction Cleanroom Notebook, 5.5x8.5, College Rule Shared by all HK system | 45486 | 45488 | 234.9 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 154.8 | 0.659 | 80.1 | 340.5 | -260.4 | 0 | [73 empty] | 154.8 |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4492 | C | USCSB2407076A |  | 美國WWT-P1A WRC PVC配管工程(2024/07/01~2024/09/30) | 2024/7/13 2024/7/23 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: As per Engineer Jim to cancel this PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | Organo |  | USC24C013 | Organo USA - UPW Electrical | 4493 | C | USCSB2407077A |  | Foxboro B Side Calibration | 45486 | 45491 | 11135 | [6 empty] | Kaoten Scientific Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11135 | 1984 | 9151 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4494 | C | USCSB2407078A |  | For UPW system pe-fab area | 2024/7/14 2024/10/3 | 2024/7/15 2024/10/3 | 211.84 | -21.1 | 232.94 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: Per purchaning team request, amend to the final amount. | [13 empty] | 211.84 | 1 | 0 | 0 | 0 | 0 | 211.84 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4495 | C | USCSB2407079A |  | For welding machine extension cord, and office supplies, tool hookup team | 2024/7/14 2024/10/3 | 2024/7/15 2024/10/3 | 1552.09 | -198.14 | 1750.23 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: Per purchaning team request, amend to the final amount. | [13 empty] | 1552.09 | 1 | 0 | 55504 | -55504 | 0 | 1552.09 | [72 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4496 | C | USCSB2407080A |  | Label for Gas/Plastic/UPW system | 45487 | 45500 | 2315 | [6 empty] | KANTEK TECHNOLOGY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2315 | 0 | 2315 | 0 | [73 empty] | - |  | - |  | 0
Others | AMHS |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4497 | C | USCSB2407081A |  | MMI B Side Seismic Project | 45488 | 45495 | 1016740.97 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 299875.03 | 0.29494 | 716865.94 | 0 | 716865.94 | 0 | [73 empty] | 299875.03 |  | - |  | 0
Others | AMHS |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4498 | C | USCSB2407082A |  | Top Chain B Side Seismic Project | 45488 | 45496 | 610000 | [6 empty] | Top Chain Construction Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 610000 | 0 | 610000 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4499 | C | USCSB2407083A |  | Sticker | 45489 | 45492 | 390.96 | [6 empty] | StickerYou Inc. | PR Approved | PO Approved | [14 empty] | 356 | 0.91058 | 34.96 | 0 | 34.96 | 0 | 356 | [70 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4500 | C | USCSB2407084A |  | LB2 B 24 Added supports for punch_WWT | 45489 | 45505 | 39080.38 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 39080.38 | 48564 | -9483.62 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4501 | C | USCSB2407085A |  | For Gas trade TCBC105 刀刃 | 45489 | 45488 | 1515 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved | [14 empty] | 1515 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 1515 | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4502 | C | USCSB2407086A |  | F21P1 B side 電力訊號貼紙_Chemical | 45489 | 45489 | 3355 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3355 | 0 | 3355 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4503 | C | USCSB2407087A |  | LB2 GIP Blower System_WWT | 45489 | 45492 | 568229 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 278432 | 0.49 | 289797 | 0 | 289797 | 0 | [68 empty] | 119328 |  |  | 0 | 159104 | - | 0 | 119328 | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4504 | C | USCSB2407088A |  | CGS Global Support Onsite Manpower | 45489 | 45503 | 37436.5 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 37436.5 | 0 | 37436.5 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4505 | C | USCSB2407089A |  | T-780BA/BB handrail fabrication and installation_WWT | 45489 | 45499 | 13355.75 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13355.75 | 0 | 13355.75 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4506 | C | USCSB2407090A |  | Chemical Scope | 45489 | 45489 | 27.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 19.99 | 0.72691 | 7.51 | 120885.59 | -120878.08 | 0 | 19.99 | [72 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4507 | C | USCSB2407091A | -01 | CED 化學系統L10 Breaker | 45489 | 2024/7/17 2024/7/22 | 0 | -28545 | 28545 |  |  | V |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | WO R1: Confirmed by Mars the items have already been ordered in USCSB2407061A, so this order needs to be cancelled | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4508 | C | USCSB2407092A |  | WWT CCR system SUS material | 45489 | 45490 | 9806.9 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 9806.9 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 9806.9 | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | FMCS |  | USC22C007 | TSMC F21 FMCS Installation | 4509 | C | USCSB2407093A |  | LB PULL BACK & CUP POWER CABLES | 45489 | 45498 | 24007 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved | [14 empty] | 0 | 0 | 24007 | 0 | 24007 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4510 | C | USCSB2407094A |  | Welding Inspection Tool Set | 2024/7/16 2024/8/7 | 2024/8/2 2024/8/7 | 1020.25 | -122.5 | 1142.75 | V |  |  |  | G.A.L Gage, CO. | PR Approved | PO Approved | PR R1: Supplier offered discounts | [13 empty] | 1020.25 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 1020.25 | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4522 | C | USCSB2407095A |  | YAHO_KEVILE_KEMEL2 | 45489 |  | 52000 | [6 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 52000 | 56800.04 | -4800.04 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4511 | C | USCSB2407096A |  | Anion Tower Materials_UPW | 45490 | 45491 | 774 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 774 | 90936.22 | -90162.22 | 0 | [73 empty] | - |  | 774 |  | 0
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4512 | C | USCSB2407097A |  | 4th 1000pcs tile swap | 45490 | 45496 | 26052 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 26052 | 534.67 | 25517.33 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4513 | C | USCSB2407098A |  | Overtime Overage for NUUO | 45490 | 45497 | 213300 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 213300 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 213300 |  |  | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4514 | C | USCSB2407099A |  | P1B Extension Ladder Request for HK PPL Trade for 100 tools | 45490 | 45491 | 427.9 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 389 | 0.90909 | 38.9 | 0 | 38.9 | 0 | 389 | [72 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C001 | TEL Main Tool Interconnection | 4515 | C | USCSB2407100A |  | Tools for all Dry ETC Tools | 2024/7/17 2024/9/23 | 2024/7/23 2024/9/23 | 32.5 | -5.86 | 38.36 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: Match to the actual expense (See packing slip) | [13 empty] | 32.5 | 1 | 0 | 0 | 0 | 0 | 32.5 | [72 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4516 | C | USCSB2407101A |  | LB2 B 12 Added supports for punch and WRC lab | 45490 | 45493 | 44712.14 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 44712.14 | 0 | 44712.14 | 0 | [71 empty] | 0 |  | - | 0 | 44712.14 | 0 | 0 | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4517 | C | USCSB2407102A |  | P1B Extension Ladder Request for HK Power Trade for 100 tools | 45490 | 45491 | 1283.7 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1167 | 0.90909 | 116.7 | 346.5 | -229.8 | 0 | 1167 | [72 empty] | - |  | - |  | 0
Non-TSMC | Organo |  | USC24C013 | Organo USA - UPW Electrical | 4518 | C | USCSB2407103A |  | UPW Additional PIA & Spare | 45490 | 45497 | 363732.33 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 363732.33 | 0 | 363732.33 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4519 | C | USCSB2407104A |  | P1B Material | 45490 | 45503 | 56996.67 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 54128.5 | 0.94968 | 2868.17 | 0 | 2868.17 | 0 | [72 empty] | 732.57 | 53395.93 |  | 978.11 |  | 0
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4520 | C | USCSB2407105A |  | CGS Global Support Onsite Manpower | 45490 | 45499 | 6384 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6384 | 0 | 6384 | 0 | [73 empty] | - |  | - |  | 0
Others | AMHS |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4521 | C | USCSB2407106A |  | L10 H.5-14 and A.5-14 Scaffolds | 45491 | 45491 | 4960 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 2976 | 0.6 | 1984 | 0 | 1984 | 0 | [73 empty] | 2976 |  | - |  | 0
Others | AMHS |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4522 | C | USCSB2407107A |  | LB1 Planking Scaffold | 45491 | 45493 | 5270 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5270 | 0 | 5270 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4523 | C | USCSB2407108A |  | WWT 3rd Party QAQC Services | 45491 | 45492 | 262000 | [6 empty] | Independent QA/QC Services Inc. | PR Approved | PO Approved | [14 empty] | 101788 | 0.3885 | 160212 | 1096 | 159116 | 0 | [70 empty] | 64170 | 0 |  | 37618 | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4524 | C | USCSB2407109A |  | WWT_Drain pipeline construction under MU_3weeks | 45491 | 45511 | 110000 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 110000 | 0 | 110000 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C010 | tsmc AZ sewer and water pipeline installation | 4525 | C | USCSB2407110A |  | CGS Global Support Onsite Manpower | 45491 | 45499 | 13158 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13158 | 0 | 13158 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4526 | C | USCSB2407111A |  | Installation of Drip Pan (PVC Bag) 追加工程 | 45492 | 45513 | 89625.85 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved | [14 empty] | 0 | 0 | 89625.85 | 29740.47 | 59885.38 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4527 | C | USCSB2407112A |  | WWT stainless steel material for CDA B | 45492 | 45492 | 9954.41 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 9219.67 | 0.92619 | 734.74 | 39806 | -39071.26 | 0 | [70 empty] | 9219.67 | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4528 | C | USCSB2407113A |  | independent QAQC services to MIC | 45492 | 45498 | 99000 | [6 empty] | Independent QA/QC Services Inc. | PR Approved | PO Approved | [14 empty] | 17568 | 0.17745 | 81432 | 0 | 81432 | 0 | [73 empty] | 17568 |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4529 | C | USCSB2407114A |  | sump pump rubber bushing and welding rod_WWT | 45492 | 45496 | 2602 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2602 | 76365.24 | -73763.24 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4530 | C | USCSB2407115A |  | WWT B區工程缺料 | 45492 | 45496 | 13977.68 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 150.36 | 0.010757 | 13827.32 | 0 | 13827.32 | 0 | [71 empty] | 0 |  | 150.36 | 0 | 3808.32 | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4531 | C | USCSB2407116A |  | F21P1 Bside WCCS-SUS Spare & Combine Valve | 45492 | 45507 | 34994.9 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 34994.9 | 0 | 34994.9 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4532 | C | USCSB2407117A |  | FAB A CDS-WCCS Permit Revision Change Order | 45492 |  | 20000 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 20000 | 0 | 20000 | 0 | [73 empty] | - |  | - |  | 0
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4533 | C | USCSB2407118A |  | NUUO 6 DP System Installation | 45492 | 2024/7/22 2024/7/31 | 313616.15 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | R1: Changing remark to align with template | [13 empty] | 313616.15 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 313616.15 |  | - |  | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 4546 | C | USCSB2407119A |  | TSMC UPW P1B additional materials_2nd | 45492 | 45509 | 4233266.03 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 152080.19 | 0.035925 | 4081185.84 | 378705.6 | 3702480.24 | #N/A | [72 empty] | 83848.49 | 68231.7 |  | 243503.93 |  | #N/A
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4534 | C | USCSB2407120A |  | L20 Loop 3 Pipe Adjustment_UPW | 45492 | 45499 | 8548 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8548 | 0 | 8548 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4535 | C | USCSB2407121A |  | CDA System Hardware_WWT | 45493 | 45497 | 3277.69 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 564.93 | 0.17236 | 2712.76 | 0 | 2712.76 | 0 | [70 empty] | 564.93 | 0 |  | - | 0 | 2272.39 | 0 | 0 | 0
Others | AMHS |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4536 | C | USCSB2407122A |  | AMHS B Side HPM Tray Relocation Installation | 45493 | 45502 | 290250 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 121275 | 0.41783 | 168975 | 0 | 168975 | 0 | [70 empty] | 121275 |  |  | - |  | 154462.5 |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4537 | C | USCSB2407123A |  | welding label shared for all system, tool hookup team | 45493 | 45495 | 1290 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1290 | 519585 | -518295 | 0 | [73 empty] | - |  | 1290 |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4538 | C | USCSB2407124A |  | 8 HK MIMO team members renewal for 3 months | 45493 | 45499 | 255779.7 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | [14 empty] | 58137.05 | 0.22729 | 197642.65 | 0 | 197642.65 | 0 | [72 empty] | 5144.03 | 52993.02 |  | 12508.33 |  | 0
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4539 | C | USCSB2407125A |  | HPM Area Tray Relocation Material | 45493 | 45497 | 90936.22 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 90936.22 | 7061 | 83875.22 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4540 | C | USCSB2407126A |  | MAST LIFT 25FT DRIVABLE LCS BATT for HK | 45493 | 45499 | 42780.26 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 5352.09 | 0.12511 | 37428.17 | 0 | 37428.17 | 0 | [72 empty] | 1030.75 | 4321.34 |  | 2593.2 |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4541 | C | USCSB2407127A |  | MIC/BMWC/Okland B side缺料_WWT | 45493 | 45496 | 8588.7 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 8588.7 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1360.77 | 0 | 7227.93 | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4542 | C | USCSB2407128A |  | 儀表管路需求 Mateials for pipeline_WWT | 45493 | 45498 | 13446.8 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 1450.43 | 0.10786 | 11996.37 | 0 | 11996.37 | 0 | [70 empty] | 285.51 | 0 | 1164.92 | - | 0 | - | 0 | 0 | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4543 | C | USCSB2407129A |  | Double sided tape for HK exhaust team | 45493 | 45496 | 593.67 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 405 | 0.6822 | 188.67 | 0 | 188.67 | 0 | 405 | [72 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4544 | C | USCSB2407130A |  | WWT Termination Fitting for chem lines and missing material for SL2 | 45496 | 45497 | 27627.47 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 27627.47 | 0 | 27627.47 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4545 | C | USCSB2407132A |  | CED 350 BUNDY One-Hole Log Compression Connector: 6 AWG MAX Hole Size | 45496 | 45498 | 346.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 346.5 | 21130 | -20783.5 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4546 | C | USCSB2407133A |  | WWT - A-420AA Support Extensions | 45496 | 45497 | 9365 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 9365 | 1 | 0 | 411200.16 | -411200.16 | 0 | [71 empty] | 0 |  | 9365 | 0 | - | 0 | 0 | 0
Base-Build | VOC |  | USC22C013 | F21P1 QR Lab Security & CCTV | 4547 | C | USCSB2407134A |  | F21 P1 VOC duct Label | 45496 | 45496 | 700 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 700 | 1 | 0 | 0 | 0 | 700 | [68 empty] | 700 |  |  |  |  | - | 700 | - |  | 0
Base-Build | VOC |  | USC22C013 | F21P1 QR Lab Security & CCTV | 4548 | C | USCSB2407135A |  | F21 P1 VOC duct material | 45496 | 45502 | 38874 | [6 empty] | Ducts, Inc. | PR Approved | PO Approved | [14 empty] | 38874 | 1 | 0 | 0 | 0 | 38874 | [70 empty] | 13000 |  | 25874 | - | 38874 | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4549 | C | USCSB2407136A |  | WWT_B Side Hardware | 45496 | 45498 | 4042.61 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 4042.61 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3780.11 | 0 | 262.5 | - | 0 | - | 0 | 0 | 0
Non-TSMC | EDG |  | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 4550 | C | USCSB2407137A |  | TSMC Diesel Pump Power Circuit Relocate | 45497 | 45498 | 32647 | [6 empty] | D.P. Electric, Inc. | PR Approved | PO Approved | [14 empty] | 32647 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 32647 | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4551 | C | USCSB2407138A |  | Duct seal for HK Power trade Third for 150 tools | 45497 | 45498 | 1096 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1096 | 0 | 1096 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4565 | C | USCSB2407139A |  | FLOW/REG 356-AR/HE-580 DUAL for Gas trade | 45497 | 45506 | 349 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 349 | 1 | 0 | 0 | 0 | #N/A | [72 empty] | 349 | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4552 | C | USCSB2407140A |  | WWT Tent 9 WMS Service Order(12 month) | 45497 | 45504 | 3345 | [6 empty] | 3PL Central LLC dba Extensiv | PR Approved | PO Approved | [14 empty] | 1371.55 | 0.41003 | 1973.45 | 0 | 1973.45 | 0 | [70 empty] | 535.3 | 0 | 836.25 | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4553 | C | USCSB2407142A |  | CHEM_Addition project for B side DHL's walking path | 45497 | 45500 | 29740.47 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29740.47 | 0 | 29740.47 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4554 | C | USCSB2407143A |  | Cord grip for HK power trade for 80 tools | 45497 | 45499 | 39806 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 39806 | 0 | 39806 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4555 | C | USCSB2407144A |  | Cord grip for HK power trade for 80 tools | 45497 | 45499 | 21364 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1442.07 | 0.0675 | 19921.93 | 0 | 19921.93 | 0 | [72 empty] | 1442.07 | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4570 | C | USCSB2407145A |  | Wires & Terminals for AMAT 36 machines | 45497 | 45506 | 76644.45 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 76644.45 | 0 | 76644.45 | 0 | [73 empty] | - |  | - |  | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4556 | C | USCSB2407146A |  | Chemical Team Cleanroom supplies | 45498 | 45499 | 532.55 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 532.55 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 532.55 | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4557 | C | USCSB2407147A |  | FLOW/REG 356-AR/HE-580 DUAL for Gas trade | 45498 | 45499 | 110.79 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 102.36 | 0.92391 | 8.43 | 4350 | -4341.57 | 0 | [68 empty] | 102.36 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4558 | C | USCSB2407148A |  | WWT AWD(O3) system - Okland | 45498 | 45519 | 451746.57 | [6 empty] | Okland Construction Company, Inc. | PR Approved | PO Processing | [14 empty] | 0 | 0 | 451746.57 | 0 | 451746.57 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4559 | C | USCSB2407149A |  | MA 200 Pipe Adjustment_UPW | 45498 | 45499 | 13675 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13675 | 0 | 13675 | 0 | [73 empty] | - |  | - |  | 0
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4560 | C | USCSB2407150A |  | 9500 FT 350 kcmil Feeders_AMHS | 45498 | 45502 | 406980 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 406980 | 0 | 406980 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC22C037 | F21P1 Screen Main tool interconnection | 4576 | C | USCSB2407151A |  | WET_ETC: SEE LIST OF TOOLS: BULK MATERIALS FOR P1B (HMT) | 45499 | 45511 | 265272 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 265272 | 0 | 265272 | #N/A | [73 empty] | - |  | 265272 |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4561 | C | USCSB2407152A |  | Gloves for HK PCW trade CYH for 200 tools | 45499 | 45499 | 142.89 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 124.7 | 0.8727 | 18.19 | 0 | 18.19 | 0 | 124.7 | [72 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4562 | C | USCSB2407153A |  | Tool: KETRTE Scaffolding requested by Trey Pubins | 45499 | 45504 | 702 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 702 | 1 | 0 | 3799.21 | -3799.21 | 0 | [68 empty] | 702 |  |  |  |  | - |  | - |  | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4563 | C | USCSB2407154A |  | LB2 WWT 60608 & 60110 | 45499 | 45505 | 546932 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 546932 | 4720 | 542212 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4564 | C | USCSB2407155A |  | LB2 VS1380 steel pipes_WWT | 45499 | 45511 | 71497 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 71497 | 0 | 71497 | 0 | [71 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4581 | C | USCSB2407156A |  | Chem Team Fitting KS23 to Replace KS17 (CED 化學訊號fitting換料0725) | 45499 | 45503 | 7061 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7061 | 0 | 7061 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4582 | C | USCSB2407157A |  | T&M to have GJX involve in A+B side punch fixed(2024/07/01~2024/09/30) | 2024/7/27 2024/8/6 | 45505 | 0 | [7 empty] | PR Approved | PO Approved | PR R1:As per Jim& Serena to cancel this PR USCSB2407157 for Gejinsin and create a new PR : USCSB2408020 for Daxin(達鑫). | [13 empty] | 0 | 1 | 0 | 0 | 0 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4583 | C | USCSB2407158A |  | FLOW/REG 356-AR/HE-580 DUAL for Gas trade | 45500 | 45502 | 3909.6 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 3909.6 | 1 | 0 | 0 | 0 | #N/A | [70 empty] | 3909.6 |  |  | - |  | - |  | #N/A
Hookup | Foundation |  | USC23C047 | F21P1 HK Seismic Installation | 4584 | C | USCSB2407160A |  | Hillman 12-mm x 1.75 Zinc-plated Steel Hex Nut (2-Count) | 45500 | 45503 | 308.25 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 308.25 | 0 | 308.25 | #N/A | [73 empty] | - |  | 308.25 |  | #N/A
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 4585 | C | USCSB2407162A |  | For use on the CVD/LAM tools - Heat shrink tubing needed for use on cables that MIC provides for the tools. | 2024/7/27 2024/8/9 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Duplicate PR, use USCSB2408021 instead of this one | [13 empty] | 0 | 1 | 0 | 0 | 0 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4586 | C | USCSB2407163A |  | CO from tsmc for Enzyme to improve, we take the B side to fill A side need first | 45501 | 45506 | 77222.59 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 77222.59 | 302966.4 | -225743.81 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4587 | C | USCSB2407164A |  | Wire TCXH for HK Power Trade | 45502 | 45503 | 21130 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21130 | 0 | 21130 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4588 | C | USCSB2407165A |  | WWT - Brahma A-Side Carboline Flange Coating | 45503 | 45506 | 587428.8 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 587428.8 | 32998.74 | 554430.06 | #N/A | [73 empty] | - |  | - |  | #N/A
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 4589 | C | USCSB2407166A |  | CVD KCSCN2 Erect?scaffold to install pipe. Gather and transport materials from laydown yard to the loading deck. | 45503 | 45507 | 1550 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 1550 | 1 | 0 | 52.41 | -52.41 | #N/A | [70 empty] | 1550 |  |  | - |  | - |  | #N/A
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4590 | C | USCSB2407167A |  | rework KCENA6 & KCENA4, CO KCEPA3 | 45503 | 45510 | 60338 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 60338 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 60338 |  | - |  | 0
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4591 | C | USCSB2407168A |  | CIP Pump Replacement_UPW | 45503 | 45506 | 6825 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6825 | 0 | 6825 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Foundation |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4592 | C | USCSB2407169A |  | Mobile shelving for foundation | 45503 | 45505 | 1547.55 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 1546.13 | 0.99908 | 1.42 | 0 | 1.42 | #N/A | [70 empty] | 1546.13 |  |  | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4593 | C | USCSB2407170A |  | PPE for UPW system, tool hookup team | 45503 | 45506 | 480.23 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 479.79 | 0.99908 | 0.44 | 0 | 0.44 | #N/A | [70 empty] | 479.79 |  |  | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4594 | C | USCSB2407171A |  | LB2 VS1380 steel pipes material_WWT | 45504 | 45506 | 11605.69 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 11605.69 | 1 | 0 | 0 | 0 | #N/A | [72 empty] | 11605.69 | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4595 | C | USCSB2407172A |  | WWT - P-780 AB blockage fix | 45504 | 45517 | 1540 | [6 empty] | Phoenix Pumps, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1540 | 43003.56 | -41463.56 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4596 | C | USCSB2407173A |  | Scissor lift for HK department start 05/02 | 45504 | 45503 | 496.08 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 496.08 | 0 | 496.08 | #N/A | [73 empty] | - |  | - |  | #N/A
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4597 | C | USCSB2407174A |  | MISUMI | 45504 | 45507 | 24452.28 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 24452.28 | 0 | 24452.28 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4598 | C | USCSB2407175A |  | WWT shortage of fitting materials on the B side | 45504 | 45506 | 54289.81 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 33067.63 | 0.60909 | 21222.18 | 0 | 21222.18 | #N/A | [72 empty] | 25624.54 | 7443.09 |  | 21222.18 |  | #N/A
Non-TSMC Interconnection | Interconnection |  | USC23C053 | AMAT Interconnection (TSMC) | 4599 | C | USCSB2407176A |  | scaffolding assembly/dismantling | 45504 | 45517 | 21152 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 19383 | 0.91637 | 1769 | 0 | 1769 | #N/A | [68 empty] | 13232 |  | 6151 |  |  | - |  | - |  | #N/A
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 4600 | C | USCSB2408001A |  | O3 Double Containment | 45505 | 45513 | 36254 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | [14 empty] | 36254 | 1 | 0 | 0 | 0 | #N/A | [73 empty] | 36254 |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4601 | C | USCSB2408002A |  | Extension cord for welding machine, Tool hookup team | 45506 | 45506 | 4350 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4350 | 0 | 4350 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4602 | C | USCSB2408003A |  | WWT shortage of Stainless materials on the B side | 45506 | 45513 | 10731.44 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 7799 | 0.72674 | 2932.44 | 14816.7 | -11884.26 | #N/A | [73 empty] | 7799 |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4603 | C | USCSB2408005A |  | Wire Brush for HK PPL Prefab | 45506 | 45506 | 210.94 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 153.12 | 0.72589 | 57.82 | 0 | 57.82 | #N/A | 153.12 | [72 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4604 | C | USCSB2408006A |  | WWT: (400 Total) Centralizer for H2SO2 and NaOH Rework | 45506 | 45512 | 3319 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | [14 empty] | 3319 | 1 | 0 | 0 | 0 | #N/A | [72 empty] | 3319 | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4605 | C | USCSB2408008A |  | office supply and materials, tool hookup team | 2024/8/2 2024/9/25 | 2024/8/7 2024/9/25 | 499.12 | -230.57 | 729.69 | V | V |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: CHAIN PASS 2/0 ZNC125'CHAIN PASS 2/0 ZNC125' not receive and purchasing request to amend 154.93 refund. | [13 empty] | 499.12 | 1 | 0 | 13892.59 | -13892.59 | #N/A | 499.12 | [72 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4606 | C | USCSB2408009A |  | Hardware for P1-B project, Gas and Chemical system | 45507 | 45513 | 23652.95 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23652.95 | 0 | 23652.95 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4607 | C | USCSB2408010A |  | HPM Beam removal_WWT | 45507 | 45511 | 3799.21 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3799.21 | 0 | 3799.21 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4608 | C | USCSB2408011A |  | Wire Thnn for HK Power trade Third for 12 tools | 45507 | 45510 | 4720 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4720 | 95255 | -90535 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 4609 | C | USCSB2408012A |  | PCO 89, Foxboro RIAs, Revision 0 | 45507 | 45512 | 3102.4 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 3102.4 | 1 | 0 | 0 | 0 | #N/A | [73 empty] | 3102.4 |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4635 | C | USCSB2408013A |  | P1-B Hardware for Plastic system, Tool hookup team | 45507 | 45523 | 25989.5 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 25989.5 | 43000 | -17010.5 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4610 | C | USCSB2408014A |  | Cleaning services for HK 3-plex | 45507 | 45517 | 1350 | [6 empty] | Viking Facility Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1350 | 0 | 1350 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4611 | C | USCSB2408015A |  | RE: 8 CTI Stripper Pad duct flange sealing with Vinyl | 45507 | 45532 | 19907.14 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 19907.14 | 0 | 19907.14 | #N/A | [73 empty] | - |  | 18911.79 |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4612 | C | USCSB2408016A |  | Ryan Herco: Rental fee cover June | 45507 | 45514 | 12153.69 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 12153.69 | 1 | 0 | 0 | 0 | #N/A | [68 empty] | 12153.69 |  |  |  |  | - |  | - |  | #N/A
Non-TSMC Interconnection | Interconnection |  | USC22C037 | F21P1 Screen Main tool interconnection | 4613 | C | USCSB2408017A |  | WET-SEE TOOL LIST-P1B BULK MATERIALS | 45507 | 45516 | 2891 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2891 | 1 | 0 | 0 | 0 | #N/A | [73 empty] | 2891 |  | - |  | #N/A
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4614 | C | USCSB2408018A |  | NUUO for AMAT P1B 17 machines | 45507 | 45521 | 761216 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 761216 | 0 | 761216 | 0 | [73 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C053 | AMAT Interconnection (TSMC) | 4615 | C | USCSB2408019A |  | DIFF - P1B MATERIALS - 1" conduit mounting clamps | 45509 | 45513 | 154.35 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 154.35 | 1 | 0 | 2682.2 | -2682.2 | #N/A | [73 empty] | 154.35 |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4616 | C | USCSB2408020A |  | T&M to have (達鑫)Daxin involve in A+B side punch fixed(2024/07/01~2024/12/31)(management fee and profit、Miscellaneous expenses | 2024/8/6 2024/8/21 | 2024/8/22 2024/9/12 | 283251.53 | -102700 | 385951.53 | V |  |  | V | Daxin Energy Engineering Co., Ltd. | PR Approved | PO Approved | PR R1:As per purchasing team David to update the price. WO R1: To remove rental, housing, plane ticket, and add Remark 6.10 | [13 empty] | 0 | 0 | 283251.53 | 0 | 283251.53 | #N/A | [73 empty] | - |  | - |  | #N/A
Interconnection | Interconnection |  | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 4617 | C | USCSB2408021A |  | Polyolefin heat shrink Fittings needed for cables that MIC provides for tool KCANN4,KCANN5,KCANN6,KCANN7 for CVD/LAM | 45510 | 45516 | 550 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 550 | 1 | 0 | 0 | 0 | #N/A | [73 empty] | 550 |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4619 | C | USCSB2408024A |  | WWT: Farnsworth assist EOR with Design Change Review and Revisions | 45511 | 45524 | 49200 | [6 empty] | Farnsworth Group, Inc | PR Approved | PO Approved | [14 empty] | 49200 | 1 | 0 | 47136 | -47136 | #N/A | [73 empty] | 49200 |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4620 | C | USCSB2408025A |  | Receptacle tester and power extension for HK Power 3-in-1 QA/QCfor 300 tools | 45511 | 45511 | 75.81 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 65.68 | 0.86638 | 10.13 | 0 | 10.13 | #N/A | 65.68 | [72 empty] | - |  | - |  | #N/A
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4621 | C | USCSB2408026A |  | MICU B Side Mezz#3 & #4 Partition Wall | 45511 | 45539 | 385531 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 385531 | 11837 | 373694 | #N/A | [73 empty] | - |  | - |  | #N/A
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4622 | C | USCSB2408027A |  | L30 Ladder Tray to 3in Conduit Replacement | 45511 | 45517 | 227175.6 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 227175.6 | 1 | 0 | 20671 | -20671 | #N/A | [73 empty] | 227175.6 |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4623 | C | USCSB2408028A |  | Water seal pot and pump cable box_WWT | 45511 | 45511 | 9483.94 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9483.94 | 0 | 9483.94 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4624 | C | USCSB2408029A |  | Additional support for punch and emergency pumps_WWT | 45511 | 45541 | 43003.56 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 43003.56 | 0 | 43003.56 | #N/A | [73 empty] | - |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4625 | C | USCSB2408030A |  | WWT_ Copper Tube request for B side. | 45512 | 45512 | 16465.8 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 16423.9 | 0.99746 | 41.9 | 0 | 41.9 | #N/A | [70 empty] | 13294.8 |  | 3129.1 | - |  | - |  | #N/A
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4626 | C | USCSB2408031A |  | CDA/GN2 Particle testing Equipment Calibration (設備校正0806) | 45512 | 45512 | 2100 | [6 empty] | Particle Measuring Systems, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2100 | 4536 | -2436 | #N/A | [73 empty] | - |  | - |  | #N/A
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4627 | C | USCSB2408032A |  | Sinfonia Manpower Support to MML (first batch)(6/17/2024- 11/22/2024) | 45512 | 45554 | 568811.52 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | NTD 16,779,101 (@0.0339) | [13 empty] | 0 | 0 | 568811.52 | 0 | 568811.52 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4628 | C | USCSB2408033A |  | USCSB2402019A issue over shipped amount | 45512 | 45513 | 509.58 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 509.58 | 1 | 0 | 21911.91 | -21911.91 | #N/A | [68 empty] | 509.58 |  |  |  |  | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4654 | C | USCSB2408034A | -01 | Label kit shared for UPW and PCW system, item 3, tool hookup team | 45512 | 8/13/2024 8/14/2024 | 1696.33 | -117.68 | 1814.01 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Some items quantity changed between PO approved and Amazon order placed | [13 empty] | 1696.33 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1150.42 |  | 310.55 | 235.36 |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4655 | C | USCSB2408035A |  | Hardware for P1-B project, Plastic and Gas system | 45512 | 45518 | 4718.91 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 4129.28 | 0.87505 | 589.63 | 3449 | -2859.37 | 0 | 4129.28 | [72 empty] | - |  | -
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4629 | C | USCSB2408037A |  | L30 3in Conduit and Strut Order_Materials | 45512 | 45516 | 14816.7 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14816.7 | 0 | 14816.7 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4630 | C | USCSB2408038A |  | Pallet Truck for HK MIMO | 2024/8/9 2024/8/10 | 45516 | 1524.75 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | PR R1:To inclide Shipping & handling | [13 empty] | 0 | 0 | 1524.75 | 84115.95 | -82591.2 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4631 | C | USCSB2408040A |  | Struct clamp for HK PPL trade for 100 tools | 45513 | 45513 | 2664.83 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved | [14 empty] | 2664.83 | 1 | 0 | 35123.62 | -35123.62 | #N/A | [72 empty] | 2664.83 | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4632 | C | USCSB2408041A |  | Straight tee fittings w/ flanges for Exhaust HL for 50 tools | 45513 | 45518 | 23911.99 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23911.99 | 5097 | 18814.99 | #N/A | [73 empty] | - |  | - |  | #N/A
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4633 | C | USCSB2408042A |  | 30,000 FT #8/3C Wire_AMHS | 45513 | 45517 | 56700 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 56700 | 1 | 0 | 0 | 0 | #N/A | [73 empty] | 56700 |  | - |  | #N/A
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4634 | C | USCSB2408043A |  | VT Network Cable Wiring_AMHS | 45513 | 45518 | 524805.7 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 255580.38 | 0.487 | 269225.32 | 0 | 269225.32 | #N/A | [73 empty] | 255580.38 |  | - |  | #N/A
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4635 | C | USCSB2408044A |  | LB2 GIP Blower material supplement_WWT | 45513 | 45525 | 100268 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 100268 | 0 | 100268 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4636 | C | USCSB2408045A |  | Stainless steel materials for L30 clean room area, P1-B construction, Tool hookup team | 45513 | 45513 | 11424 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11424 | 5881 | 5543 | #N/A | [73 empty] | - |  | - |  | #N/A
Non-TSMC Interconnection | Interconnection |  | USC24C016 | AMAT Mozart New Scope | 4637 | C | USCSB2408046A |  | AMAT Mozart New Scope | 45513 | 45520 | 43000 | [6 empty] | AUCAN INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 43000 | 0 | 43000 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4665 | C | USCSB2408047A |  | Liquid Argon for Gas, PCW, and PPL | 45514 | 45516 | 5272.3 | [6 empty] | Linde Gas & Equipment Inc. | PR Approved | PO Approved | [14 empty] | 4583.36 | 0.86933 | 688.94 | 0 | 688.94 | 0 | [72 empty] | 4583.36 | - |  | 391.25
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4666 | C | USCSB2408048A |  | pipe threading oil and cutting blade saw for HK PCW trade | 45514 | 45516 | 1227.78 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1078.16 | 0.87814 | 149.62 | 0 | 149.62 | 0 | 1078.16 | [72 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4667 | C | USCSB2408049A |  | Circular Saw Blade for HK PCW tools for 50 tools | 45514 | 45519 | 672 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 672 | 1 | 0 | 419583.97 | -419583.97 | 0 | [70 empty] | 672 |  |  | - |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4668 | C | USCSB2408050A |  | Lit 2: KPE603.S, KPE604.S, KPE605.S, KPE606.S, KPE607.S: EUV RF Cable Tray Cover Installation | 45514 | 45519 | 11667 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11667 | 0 | 11667 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4669 | C | USCSB2408051A |  | Label kit for BBP 37, Gas and chemical system | 45514 | 45516 | 1912.35 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 1912.35 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1912.35 |  |  | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4670 | C | USCSB2408052A |  | Equipment 2331025 Scissor lifts rentals 08/12-12/02 | 45517 | 45518 | 9648.03 | [6 empty] | United Rentals | PR Approved | PO Approved | [14 empty] | 2521.15 | 0.26131 | 7126.88 | 0 | 7126.88 | 0 | [72 empty] | 2521.15 | - |  | 2354.43
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4671 | C | USCSB2408053A |  | Lit 2: KPE601-S, KPE602-S, KPE603-S, KPE604-S, KPE605-S, KPE606-S, KPE607-S: GMS Fittings Fabrications | 45517 | 45520 | 6962 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6962 | 0 | 6962 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4672 | C | USCSB2408054A |  | Lit 2: KPE604-S: BTS Base Block Relocation | 45517 | 45519 | 4133 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 4133 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 4133 |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4673 | C | USCSB2408055A |  | Lit 3: KPAP02-T: Rework | 45517 | 45519 | 47136 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 47136 | 3374.8 | 43761.2 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4674 | C | USCSB2408056A |  | Lit 3: KPAP02-T: BB Rework | 45517 | 45520 | 21493 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 21493 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 21493 |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4675 | C | USCSB2408057A |  | Lit 3: KPD802-T: PFA BB Rework | 45517 | 45519 | 11837 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11837 | 0 | 11837 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4676 | C | USCSB2408058A |  | Lit 3: KPE601-T: PFA Rework | 45517 | 45519 | 20671 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 20671 | 0 | 20671 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4677 | C | USCSB2408060A |  | Label printer for printing location ID and Tool ID | 45517 | 45518 | 2931.65 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 2931.65 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 2931.65 |  |  | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4678 | C | USCSB2408061A |  | WWT shortage of fitting materials on the B side Sump Pump | 45517 | 45519 | 7407.77 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 5842.97 | 0.78876 | 1564.8 | 17475 | -15910.2 | 0 | [73 empty] | 5842.97 |  | 1564.8
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4679 | C | USCSB2408062A |  | IR 63 welding machine calibration | 45518 | 45520 | 6321.5 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6321.5 | 0 | 6321.5 | 0 | [73 empty] | - |  | -
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 4680 | C | USCSB2408064A |  | TSMC UPW P1B additional materials_2nd_4 materials | 45518 | 45520 | 42590 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 38054 | 0.8935 | 4536 | 0 | 4536 | 0 | [72 empty] | 35149 | 2905 |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4681 | C | USCSB2408065A |  | Extension ladder for HK exhaust trade for 300 tools | 45518 | 45530 | 5879.09 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 1941.93 | 0.33031 | 3937.16 | 0 | 3937.16 | 0 | [73 empty] | 1941.93 |  | 3937.16
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4682 | C | USCSB2408066A |  | WWT LSR system - Okland | 45519 | 45524 | 21911.91 | [6 empty] | Okland Construction Company, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21911.91 | 0 | 21911.91 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4683 | C | USCSB2408067A |  | WWT_ Copper Tube request for B side_茂迅 | 45519 | 45520 | 17493.45 | [6 empty] | SWIFT ENGINEERING CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 17493.45 | 0 | 17493.45 | 0 | [73 empty] | - |  | 17493.45
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4684 | C | USCSB2408068A |  | Lit 3: KPE605-T: Cable Tray Modifications | 45519 | 45520 | 3449 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3449 | 0 | 3449 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4685 | C | USCSB2408069A |  | WWT Tent 9 WMS Barcode Paper Label | 45519 | 45519 | 85.74 | [6 empty] | Barcodes LLC | PR Approved | PO Approved | [14 empty] | 85.74 | 1 | 0 | 271779.06 | -271779.06 | 0 | [73 empty] | 85.74 |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4686 | C | USCSB2408070A |  | WWT CDA system branch - CRG | 45519 | 45520 | 84115.95 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 84115.95 | 883.32 | 83232.63 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4687 | C | USCSB2408071A |  | WWT - WRC Agitator Support Extensions | 45519 | 45541 | 51123.62 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 51123.62 | 0 | 51123.62 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4688 | C | USCSB2408072A |  | Lit 3: KPE605-T: BB Rework | 45519 | 45524 | 5097 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5097 | 0 | 5097 | 0 | [73 empty] | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4689 | C | USCSB2408073A |  | INT--AMAT--CGS(Mar.&Apr.) | 45519 | 45523 | 16231.48 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 16231.48 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 16231.48 |  |  | - |  | -
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4690 | C | USCSB2408074A |  | Shipment Cost for Backup DP Parts | 45520 | 45524 | 4725 | [6 empty] | THIRD ENTERPRISE CO., LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4725 | 0 | 4725 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4691 | C | USCSB2408075A |  | Handtools for HK Exhaust trade for 200 tools | 45520 | 45523 | 706.49 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 609.89 | 0.86327 | 96.6 | 0 | 96.6 | 0 | 609.89 | [72 empty] | - |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4692 | C | USCSB2408076A |  | Lit 3: KPOCT2: Exhaust Rework | 45520 | 45523 | 5881 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5881 | 33292.33 | -27411.33 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4693 | C | USCSB2408077A |  | WWT - FRP membrane atpads- dike walls around Tmah expansion LB2 N.5 | 45520 | 45534 | 97275 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 97275 | 2278.5 | 94996.5 | 0 | [73 empty] | - |  | 77820
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4694 | C | USCSB2408078A |  | WWT - Lower Level Guage Assembly Tee's | 45520 | 45525 | 15472 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15472 | 0 | 15472 | 0 | [73 empty] | - |  | 14698.4
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4695 | C | USCSB2408079A |  | Hex nut, bolt, and washer for HK power trade for 200 tools | 45520 | 45523 | 352.76 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 302.98 | 0.85888 | 49.78 | 128900 | -128850.22 | 0 | [72 empty] | 291.02 | 11.96 |  | -
Others | AMHS |  | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 4696 | C | USCSB2408080A |  | AMHS TSMC Labor 9 Distribution Panels | 45520 | 45527 | 952044.09 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 952044.09 | 0 | 952044.09 | 0 | [73 empty] | - |  | 532460.12
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4697 | C | USCSB2408081A |  | office supplies for tool hookup department shared by all systems | 45520 | 45523 | 1125.21 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 948.19 | 0.84268 | 177.02 | 0 | 177.02 | 0 | 948.19 | [72 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4698 | C | USCSB2408082A |  | Hand tools for HK power trader JY for 200 tools | 45520 | 45527 | 8853.54 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 8486.94 | 0.95859 | 366.6 | 0 | 366.6 | 0 | [73 empty] | 8486.94 |  | 366.6
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4699 | C | USCSB2408083A |  | Lit 3: No Tool ID: Material to Help Install Storage Cabinet | 45520 | 45532 | 1059.85 | [6 empty] | Cutting Edge Mfg LLC | PR Approved | PO Approved | [14 empty] | 1059.85 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 1059.85 | - |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4700 | C | USCSB2408084A |  | Lit 2: KPE604-S, KPE606-S, and KPE607-S: Install Dry Laser Anchor | 45521 | 45525 | 10960 | [6 empty] | Top Chain Construction Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10960 | 0 | 10960 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4701 | C | USCSB2408085A |  | Yaho 12 Manpower Support due to TSMC schedule change | 45524 |  | 163000 | [6 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 163000 | 5976.68 | 157023.32 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4702 | C | USCSB2408087A |  | Flat flange for HK Exhaust trade for 52 tools | 45525 | 45527 | 21013 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21013 | 0 | 21013 | 0 | [73 empty] | - |  | -
Non-TSMC | EDG |  | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 4703 | C | USCSB2408088A |  | Cup Fiber termination, installation and testing report project | 45525 | 45526 | 5300 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 5035 | 0.95 | 265 | 0 | 265 | 0 | [73 empty] | 5035 |  | -
Hookup | Foundation |  | USC23C059 | F21P1 Foundation T&M | 4704 | C | USCSB2408089A |  | M10*80mm Socket Countersunk for Foundation | 45525 | 45527 | 2923.2 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2923.2 | 0 | 2923.2 | 0 | [73 empty] | - |  | 2328.48
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4709 | C | USCSB2408090A |  | office supplies | 45525 | 45535 | 408.52 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 329.49 | 0.80655 | 79.03 | 0 | 79.03 | 0 | [73 empty] | 329.49 |  | -
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4705 | C | USCSB2408091A |  | Salary Delta of Sinfonia Engineers from 2/28/24 to 5/31/24 | 45525 | 45532 | 55339.39 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | [14 empty] | 49744.07 | 0.89889 | 5595.32 | 0 | 5595.32 | 0 | [70 empty] | 49744.07 |  |  | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4706 | C | USCSB2408092A |  | Liquid Argon for Gas, Chemical, PCW, and PPL for HK | 45526 | 45532 | 49910 | [6 empty] | Linde Gas & Equipment Inc. | PR Approved | PO Approved | [14 empty] | 18153.56 | 0.36373 | 31756.44 | 0 | 31756.44 | 0 | [72 empty] | 18153.56 | - |  | 14635
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4707 | C | USCSB2408094A |  | AMAT interconnect manager fee for 22 machines | 45526 |  | 956570.48 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 956570.48 | 0 | 956570.48 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4713 | C | USCSB2408097A |  | Hand tool for GAS system, Tool HK team | 45526 | 45539 | 174.95 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 156.91 | 0.89688 | 18.04 | 0 | 18.04 | 0 | 156.91 | [72 empty] | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4708 | C | USCSB2408098A |  | AMAT_P1A_T&M_LABOR_Brycon_KCUVA1_KCUVA2_May_Jun | 45526 | 45533 | 222207.51 | [6 empty] | Brycon Corporation | PR Approved | PO Approved | [14 empty] | 222207.51 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 222207.51 |  | -
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4715 | C | USCSB2408099A |  | AMAZON | 45526 | 45539 | 93.47 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 84.98 | 0.90917 | 8.49 | 38000 | -37991.51 | 0 | 84.98 | [72 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4716 | C | USCSB2408100A |  | Parts of Tube Facing Tool, Hardware for tool hookup team | 45526 | 45532 | 1100 | [6 empty] | Potex Technologies Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1100 | 0 | 1100 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4709 | C | USCSB2408101A |  | Pressure washer, hose, and sump pump for HK MIMO | 45526 | 45531 | 219.75 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 209.69 | 0.95422 | 10.06 | 0 | 10.06 | 0 | [72 empty] | 209.69 | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4710 | C | USCSB2408102A |  | AMAT_DIF_NUUO_Cable pulls and terminator power cable for DIF 11 machine_KIHITA_KDPNA2_KDCBA2_KIHIT9_KIHIT8_KIHITB_KDDAA2_KIHI | 45527 | 45540 | 416723 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 416723 | 14700 | 402023 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4711 | C | USCSB2408103A |  | Cleanroom paper shared by all hk systems | 45527 | 45531 | 883.32 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 883.32 | 0 | 883.32 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4712 | C | USCSB2408104A |  | QAQC OFFICE RELATED SUPPLIES | 8/23/2024 8/29/2024 | 8/27/2024 8/29/2024 9/18/2024 | 677.85 | 8.08 | 669.77 |  |  | V | V | Amazon.com, Inc. | PR Approved | PO Approved | R1: BUSINESS PRICE R2: match with the actual spending | [13 empty] | 677.85 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 677.85 | - |  | -
Interconnection | Interconnection |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 4755 | C | USCSB2408105A |  | P1B_CVD1_CIP_GAS_LINE_CT_CT-202407160001_CT-202407160002 | 45527 |  | 72618 | [6 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 72618 | 40963.96 | 31654.04 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4722 | C | USCSB2408107A |  | Amazon.com Order for DRY ETC | 45528 | 45539 | 110.78 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 53.35 | 0.48159 | 57.43 | 55800 | -55742.57 | 0 | 53.35 | [72 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4723 | C | USCSB2408109A |  | safety equipment for tool hookup team | 45528 | 45532 | 527.2 | [6 empty] | Palo Verde First Aid-Fire-Safety-Shredding | PR Approved | PO Approved | [14 empty] | 0 | 0 | 527.2 | 0 | 527.2 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4724 | C | USCSB2408110A |  | Consumables Hardware for HK Power trade Third | 45528 | 8/31/2024 9/5/2024 | 1141.31 | -24.47 | 1165.78 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: Change Payment Method to Credit Card as Shipping Date is too late. | [13 empty] | 1141.31 | 1 | 0 | 0 | 0 | 0 | 1141.31 | [72 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4725 | C | USCSB2408111A |  | Hand tools for HK Power trade Third for 297 tools | 45528 | 45538 | 33292.33 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | [14 empty] | 0 | 0 | 33292.33 | 0 | 33292.33 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4726 | C | USCSB2408112A |  | Mobile Storage Cabinet for HK Power trade | 45528 | 45531 | 2278.5 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2278.5 | 0 | 2278.5 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4727 | C | USCSB2408113A |  | Cordless impact driver and strap wrench for HK Power trade Third for 297 tools | 45528 | 45531 | 1163.8 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 943.68 | 0.81086 | 220.12 | 0 | 220.12 | 0 | [72 empty] | 943.68 | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4728 | C | USCSB2408115A |  | Wire TCXH for HK Power Trade for 200 tools | 45528 | 45547 | 3313060 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3313060 | 0 | 3313060 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4729 | C | USCSB2408116A |  | Label for GAS system, P1-B hookup team | 45531 | 45533 | 714.9 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 597.93 | 0.83638 | 116.97 | 0 | 116.97 | 0 | [72 empty] | 597.93 | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC23C021 | F21P1 KLA Interconnection | 4730 | C | USCSB2408117A |  | ME: KPSP07, KPSP04, KPCD05, KPCD02, KKSV04, KKDB03, KKDB01-03: INSTALL SIGNAL/POWER CABLES & MOVE CHILLER HOSES. | 45531 | 45534 | 12385.5 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 12385.5 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 12385.5 | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC23C019 | F21P1 Hitachi Interconnection | 4731 | C | USCSB2408120A |  | ME: KPCD07: CABLE PULL | 45531 | 45534 | 4416 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 4416 | 1 | 0 | 226226.26 | -226226.26 | 0 | [72 empty] | 4416 | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC24C003 | F21P1 Lasertec Interconnection | 4732 | C | USCSB2408121A |  | ME: KPMI03: CABLE PULL | 45531 | 45534 | 2518.5 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 2518.5 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 2518.5 | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC23C017 | F21P1 ASML Interconnection | 4733 | C | USCSB2408122A |  | ME: KKSS02: CABLE PULL | 45531 | 45534 | 3346.5 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 3346.5 | 1 | 0 | 158181.57 | -158181.57 | 0 | [72 empty] | 3346.5 | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4734 | C | USCSB2408123A |  | welding training/ certification materials | 45531 | 45538 | 5977.02 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5977.02 | 105977.64 | -100000.62 | 0 | [73 empty] | - |  | -
Non-TSMC | Micron - Material |  | USC24C001 | Micron - Chemical SOLBLE RN3000 | 4735 | C | USCSB2408124A |  | SOLBLE RN3000 20kg x 7 drums | 45531 | 45533 | 11200 | [6 empty] | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11200 | 1181.96 | 10018.04 | 0 | [73 empty] | - |  | 11200
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4736 | C | USCSB2408125A |  | keep PPE for the TOOL HOOK UP EHS Department. | 45532 | 45533 | 487.92 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 419.42 | 0.85961 | 68.5 | 274022.36 | -273953.86 | 0 | [72 empty] | 419.42 | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4737 | C | USCSB2408126A |  | Waterproof tarp for HK | 45532 | 45533 | 125.38 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 97.98 | 0.78146 | 27.4 | 634.55 | -607.15 | 0 | [72 empty] | 97.98 | - |  | -
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4738 | C | USCSB2408127A |  | Lit 3: KPAN03-T: E4B, E6B Flex Replacement (Live Tool) | 45532 | 45541 | 6348 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6348 | 0 | 6348 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4739 | C | USCSB2408128A |  | Generators rentals for HK for 8 months | 45532 | 45534 | 14645.71 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14645.71 | 0 | 14645.71 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4740 | C | USCSB2408129A |  | 10 Scissor Lifts rentals for HK for 8 months | 2024/8/29 2024/9/13 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Previous PO can cover till a later time | [13 empty] | 0 | 1 | 0 | 41530.89 | -41530.89 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4741 | C | USCSB2408130A |  | 6 Scissor Lifts rentals for HK for 8 months | 2024/8/29 2024/9/13 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Previous PO can cover till a later time | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4742 | C | USCSB2408131A |  | Truck STKBD rentals for HK for 8 months | 2024/8/29 2024/9/13 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Previous PO can cover till a later time | [13 empty] | 0 | 1 | 0 | 350 | -350 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4765 | C | USCSB2408132A |  | 8'x8'x40' Mobile Storage Container for HK for 8 months | 45533 | 45552 | 10790.5 | [6 empty] | Allied Storage Containers | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10790.5 | 0 | 10790.5 | 0 | [73 empty] | - |  | -
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4743 | C | USCSB2408133A |  | F21 P1B區Chemical赴美管路工程施工by人月 For 2 month | 45533 | 45555 | 76000 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 76000 | 0 | 76000 | 0 | [73 empty] | - |  | -
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4744 | C | USCSB2408134A |  | 支援F21帆宣電力工程-點工(不含機具) for 1 month | 45533 |  | 48000 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 48000 | 0 | 48000 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4768 | C | USCSB2408135A |  | 20' Office for HK for 8 months | 2024/8/29 2024/9/13 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Previous PO can cover till a later time | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4745 | C | USCSB2408136A |  | WWT B Side Electrical DS Stand | 45533 | 45541 | 14700 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14700 | 0 | 14700 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 4746 | C | USCSB2408137A |  | Scaffold for HK | 45533 | 45540 | 396266.5 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 396266.5 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 396266.5 | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4747 | C | USCSB2408138A |  | WWT Flange repair - Belzona | 2024/8/29 2024/9/20 | 2024/9/13 2024/9/20 | 44000 | [5 empty] | V | DCP Coatings, LLC | PR Approved | PO Approved | PO R1: Revised completion date and term 9 to non-warranty per vendor's request and confirmation with Thomas and Eugene. | [13 empty] | 0 | 0 | 44000 | 0 | 44000 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4748 | C | USCSB2408139A |  | KIL CGB For HK Power trade for 200 tools | 45533 | 45544 | 380015.85 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 380015.85 | 0 | 380015.85 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4749 | C | USCSB2408140A |  | WWT A+B side punch which is paid by tsmc_水泥基座填塞 | 45533 | 45553 | 62000 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 62000 | 0 | 62000 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4750 | C | USCSB2408141A |  | WWT shortage materials on the B side LSR, CCR, and ACF-1928 | 45533 | 45534 | 3608.9 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3608.9 | 0 | 3608.9 | 0 | [73 empty] | - |  | 3608.9
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4751 | C | USCSB2408143A |  | PR BMWC WWT - CCR CO-1 | 45534 | 45542 | 36475 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 36475 | 274.48 | 36200.52 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4752 | C | USCSB2408144A |  | WWT Tent 9 materials container | 45534 | 45545 | 4982 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4982 | 0 | 4982 | 0 | [73 empty] | - |  | 4707
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4753 | C | USCSB2408145A |  | Calibration | 45534 | 45535 | 466 | [6 empty] | Ceet Industries Inc DBA Trident Calibration Labs | PR Approved | PO Approved | [14 empty] | 0 | 0 | 466 | 0 | 466 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 4754 | C | USCSB2408146A |  | DIFF1-2: KDPOT3, KDAPK5, KDSRK1, KDTNK2, KDRIM2, KIMIS1: INSTALL SIGNAL & POWER CABLES | 45534 | 45539 | 47541 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 47541 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 47541 | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4763 | C | USCSB2408147A |  | Label for GAS, CHEMICAL and PPL | 45534 | 9/5/2024 9/12/2024 | 1955 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | PO R1: Revise responsible engineer and update the completion date | [13 empty] | 0 | 0 | 1955 | 0 | 1955 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4764 | C | USCSB2408149A |  | Struct anchor for HK Safety | 45534 | 45551 | 6482 | [6 empty] | Diversified Products USA | PR Approved | PO Approved | [14 empty] | 6482 | 1 | 0 | 1068676.52 | -1068676.52 | 0 | [73 empty] | 6482 |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4765 | C | USCSB2408150A |  | Extension Cords Request for HK PCW, PPL, Power, EXH | 45534 | 45540 | 1488 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1488 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 1488 |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4766 | C | USCSB2408151A |  | Hardware for HK Power for 200 tools | 45534 | 45545 | 454485.56 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 454485.56 | 13782 | 440703.56 | 0 | [73 empty] | - |  | -
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4767 | C | USCSB2408161A |  | Damaged Valves on A Side, Replacement order through UMEC, TSMC issued PO | 45535 | 45540 | 930 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 930 | 0 | 930 | 0 | [73 empty] | - |  | 930
Base-Build | Chemical |  | USC21C005 | F21P1 Chemical & WCCS package | 4768 | C | USCSB2408162A |  | REVISED VARTEAGA Invoice No. MICU-010 @ T^0M WORK_CDS L10_L20_L30 Cleanroom CPVC_SS_PFA Chemical System Tubes_ Batch 1/3 | 45535 | 45546 | 158181.57 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 158181.57 | 624778.25 | -466596.68 | 0 | [73 empty] | - |  | -
|  |  | USC23C012 | F21P1 Hot DI Machine Hookup | 4769 | C | USCSB2408164A |  | Proposal TSMC-015 @ ICP_MASS_Side B_ Total Boxes_CPVC_SUS_PFA_Support Installations_Side A. Paint_(Rev.1)_Batch 2/2 | 45535 | 45546 | 105977.64 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 105977.64 | 0 | 105977.64 | 0 | [73 empty] | - |  | -
|  |  | USC23C042 | F21P1 Chemical Safety Cabinet Installation | 4770 | C | USCSB2408165A |  | REVISED VARTEAGA Invoice No. MICU-010 @ T^0M WORK_CDS L10_L20_L30 Cleanroom CPVC_SS_PFA Chemical System Tubes_ Batch 3/3 | 45535 | 45546 | 1181.96 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1181.96 | 0 | 1181.96 | 0 | [73 empty] | - |  | -
Base-Build | Chemical |  | USC24C005 | Chemical & WCCS B Side Project | 4787 | C | USCSB2408166A |  | Proposal TSMC-015 @ ICP_MASS_Side B_ Total Boxes_CPVC_SUS_PFA_Support Installations_Side A. Paint_(Rev.1)_Batch 1/2 | 45535 | 45546 | 274022.36 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 274022.36 | 0 | 274022.36 | 0 | [73 empty] | - |  | -
Base-Build | UPW |  | USC21C003 | F21P1 UPW | 4771 | C | USCSB2409001A |  | CIA Sensor | 45539 | 45540 | 634.55 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 634.55 | 0 | 634.55 | 0 | [73 empty] | - |  | -
Base-Build | UPW |  | USC21C003 | F21P1 UPW | 4772 | C | USCSB2409002A |  | PIA KM31-584_Broken PIA instrument replacement | 45539 | 45540 | 355.94 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 355.94 | 0 | 355.94 | 0 | [73 empty] | - |  | 355.94
Base-Build | UPW |  | USC21C003 | F21P1 UPW | 4773 | C | USCSB2409003A |  | Horiba SILA Buffer Tank and PFA Tube | 45539 | 45540 | 788.6 | [6 empty] | HORIBA Instruments Incorporated | PR Approved | PO Approved | [14 empty] | 0 | 0 | 788.6 | 0 | 788.6 | 0 | [73 empty] | - |  | -
|  |  | USC23C012 | F21P1 Hot DI Machine Hookup | 4774 | C | USCSB2409004A |  | REVISED VARTEAGA Invoice No. MICU-010 @ T^0M WORK_CDS L10_L20_L30 Cleanroom CPVC_SS_PFA Chemical System Tubes_ Batch 2/3 | 45539 | 45546 | 41530.89 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 41530.89 | 0 | 41530.89 | 0 | [73 empty] | - |  | -
Base-Build | VOC |  | USC24C007 | Low Voltage B Side Project | 4775 | C | USCSB2409005A |  | F21 P1 VOC Electricity Change Order _CO#32,CO#33,CO#34,CO#36,CO#40 | 45539 | 45542 | 24728 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 24728 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 24728 |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4776 | C | USCSB2409006A |  | M200 Calibration | 45539 | 45539 | 350 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 350 | 0 | 350 | 0 | [73 empty] | - |  | -
Base-Build | CCTV |  | USC21C008 | F21P1 CCTV & Security | 4777 | C | USCSB2409007A |  | F21 P1 VOC Electricity Change Order _CO#35 | 45539 | 45542 | 11099 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 11099 | 1 | 0 | 926 | -926 | 0 | [73 empty] | 11099 |  | -
Base-Build | CCTV |  | USC22C013 | F21P1 QR Lab Security & CCTV | 4778 | C | USCSB2409008A |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 1/6 | 45539 | 45542 | 118515.2 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 118515.2 | 1 | 0 | 911.4 | -911.4 | 0 | [73 empty] | 118515.2 |  | -
Base-Build | VOC |  | USC21C007 | F21P1 VOC package （Installation ) | 4779 | C | USCSB2409009A |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 2/6 | 45539 | 45542 | 16567.6 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 16567.6 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 16567.6 |  | -
Base-Build | CCTV |  | USC22C001 | F21 P1 Office and WH Security and CCTV | 4780 | C | USCSB2409010A |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 3/6 | 45539 | 45542 | 25656.57 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 25656.57 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 25656.57 |  | -
Base-Build | CCTV |  | USC21C008 | F21P1 CCTV & Security | 4781 | C | USCSB2409011A |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 4/6 | 45539 | 45542 | 1037.99 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 1037.99 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 1037.99 |  | -
Base-Build | VOC |  | USC21C013 | F21P1 AMC THC Monitoring System | 4782 | C | USCSB2409012A |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 5/6 | 45539 | 45542 | 12271.61 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 12271.61 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 12271.61 |  | -
Base-Build | VOC |  | USC24C007 | Low Voltage B Side Project | 4783 | C | USCSB2409013A |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 6/6 | 45539 | 45545 | 648.03 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 648.03 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 648.03 |  | -
Base-Build | VOC |  | USC21C013 | F21P1 AMC THC Monitoring System | 4784 | C | USCSB2409014A |  | F21 P1 VOC Electricity Change Order _CO#30_Batch 1/2 | 45539 | 9/7/2024 9/12/2024 | 128026.61 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | PO R1: Revise Payment Term in Remark | [13 empty] | 82077.61 | 0.6411 | 45949 | 0 | 45949 | 0 | [73 empty] | 82077.61 |  | -
Base-Build | VOC |  | USC22C019 | AMC monitor 595T0 | 4785 | C | USCSB2409015A |  | F21 P1 VOC Electricity Change Order _CO#30_Batch 2/2 | 45539 | 9/7/2024 9/12/2024 | 17971.39 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | PO R1: Revise Payment Term in Remark | [13 empty] | 17971.39 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 17971.39 |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4803 | C | USCSB2409016A |  | Argon regulator for yaho, gas system | 45539 | 45551 | 349 | [6 empty] | Linde Gas & Equipment Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 349 | 0 | 349 | 0 | [73 empty] | - |  | 349
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4786 | C | USCSB2409017A |  | AMAT_Purchase 4 sets of D-ring, Sliding beam clamp, D-ring anchor for Tool ID:KSWGA2,KDIGA8,KSCPA2,KSSBAH | 45539 | 45541 | 301.93 | [6 empty] | WW Grainger Inc (DBA Grainger) | PR Approved | PO Approved | [14 empty] | 0 | 0 | 301.93 | 2649.96 | -2348.03 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4787 | C | USCSB2409018A |  | Extension Cords Request for HK PCW, PPL, Power, EXH | 45540 | 45539 | 1362.59 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1176.56 | 0.86347 | 186.03 | 0 | 186.03 | 0 | 1176.56 | [72 empty] | - |  | -
Hookup | Foundation |  | USC23C047 | F21P1 HK Seismic Installation | 4788 | C | USCSB2409019A |  | M12 Hex Nut*500, 1/2" nuts*2500 | 45540 | 45541 | 258.9 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 258.9 | 66660.77 | -66401.87 | 0 | [73 empty] | - |  | 258.9
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4789 | C | USCSB2409020A |  | Payment for HuaYi's Lien | 2024/9/5 2024/9/18 | 45545 | 0 | [6 empty] | Sullins, Johnston, Rohrbach & Magers | PR Approved | PO Approved | PR R1: Go this PR to APN per Debby. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4837 | C | USCSB2409021A |  | safety | 45540 | 2024/9/23 2024/10/14 | 37.88 | -8.3 | 46.18 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 37.88 | 0 | 37.88 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 4790 | C | USCSB2409022A |  | AMHS TSMC Infrastructure Main Tray | 45540 | 45548 | 1187418.35 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1187418.35 | 0 | 1187418.35 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4791 | C | USCSB2409023A |  | MU E2 manpower support for 6 people_B 區suction + A side NaOH 管路 | 45540 |  | 131065 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 131065 | 0 | 131065 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4792 | C | USCSB2409024A |  | cord grips kit 2'' for HK Power | 45540 | 45546 | 13782 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13782 | 32975.97 | -19193.97 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4793 | C | USCSB2409025A |  | Y terminals_Panduit_PV10-8F-D for HK Power for 297 tools | 45540 | 45545 | 5400 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5400 | 0 | 5400 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 4794 | C | USCSB2409026A |  | AMHS TSMC Labor Next 6 Distribution Panels | 45540 | 45554 | 842251.77 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 842251.77 | 0 | 842251.77 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4795 | C | USCSB2409027A |  | EEW PPE Torque Wrench for 200 tools | 45540 | 45544 | 2749.95 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 2499.95 | 0.90909 | 250 | 246.2 | 3.8 | 0 | 2499.95 | [72 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4814 | C | USCSB2409028A |  | Glove Guard Cable Safe Hook Extreme, Yellow, 12 Inch Hook (25 Pack) | 45540 | 45551 | 6862.12 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 6862.12 | 1 | 0 | 0 | 0 | 0 | 6862.12 | [72 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4796 | C | USCSB2409029A |  | 500 Thick Waffle Covers for HK safety | 2024/9/6 2024/9/17 | 2024/9/16 2024/9/17 | 35765.5 | [5 empty] | V | Milling Machinery, Inc. | PR Approved | PO Approved | PO R1: Incorrect ship-to address | [13 empty] | 0 | 0 | 35765.5 | 0 | 35765.5 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4797 | C | USCSB2409030A |  | HK Exhaust hardware Request for 200 Tools | 45541 | 45545 | 1029.48 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved | [14 empty] | 2.38 | 0.0023118 | 1027.1 | 0 | 1027.1 | 0 | [73 empty] | 2.38 |  | 414.81
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4798 | C | USCSB2409031A |  | Cutting Band Saw Blade for HK Power Team for 200 tools | 45541 | 45545 | 1978.35 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1708.5 | 0.8636 | 269.85 | 468 | -198.15 | 0 | 1708.5 | [72 empty] | - |  | -
Base-Build | WWT |  | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 4799 | C | USCSB2409032A |  | WWT - Brahma A-Side Carboline Flange Coating CO-1 | 45541 | 45547 | 27906.25 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 27906.25 | 0 | 27906.25 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4800 | C | USCSB2409033A |  | AMHS Hole Framing 2 | 45541 | 45555 | 57081.62 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 57081.62 | 11494.43 | 45587.19 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4820 | C | USCSB2409034A |  | P-760AB Removal and Transportation | 45541 | 45545 | 4320 | [6 empty] | Phoenix Pumps, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4320 | 0 | 4320 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4821 | C | USCSB2409035A |  | WWT shortage of hardware materials on the B side and WRC | 45542 | 45545 | 624.97 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 624.97 | 491.62 | 133.35 | 0 | [73 empty] | - |  | 624.97
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4822 | C | USCSB2409037A |  | Terminal Lugs for HK Power for 200 Tools | 45542 | 45545 | 4454 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4454 | 11865.5 | -7411.5 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4823 | C | USCSB2409038A |  | WWT shortage of fitting materials for B Side, Fab Exhaust, LSR Non-Oxidant Biocide, P-810 | 45542 | 45545 | 3936.91 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3936.91 | 0 | 3936.91 | 0 | [73 empty] | - |  | 3025.51
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4824 | C | USCSB2409039A |  | Label for gas and plastic system, p1-b tool hookup team | 45542 | 45545 | 740 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 740 | 0 | 740 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4825 | C | USCSB2409040A |  | WWT - WRC Platform Flashing | 45542 | 45547 | 73316.13 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 73316.13 | 0 | 73316.13 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4826 | C | USCSB2409041A |  | WWT - WRC Clarifier Platform Compliance Modification | 45545 | 45546 | 38654.87 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 38654.87 | 70080 | -31425.13 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4827 | C | USCSB2409042A |  | QAQC WELDER CERTIFICATION | 45545 | 45568 | 6700 | [6 empty] | Independent QA/QC Services Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6700 | 0 | 6700 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | =ROW(G4834)-9 | C | USCSB2409043A |  | HK Power trade hardware requested_Metal Wall plate | 45545 | 45545 | 179.9 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 179.9 | 1 | 0 | 15400 | -15400 | 0 | [73 empty] | 179.9 |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4829 | C | USCSB2409044A |  | WWT: SCS PR - Confined Space Safety Tank T-140AB | 45545 | 45547 | 1000 | [6 empty] | Safety Compliance Services, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1000 | 0 | 1000 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4830 | C | USCSB2409045A |  | 4) 26' clean room ready, 2-man scissor lifts | 45546 | 45551 | 3278.1 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3278.1 | 774.69 | 2503.41 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4831 | C | USCSB2409046A |  | VOC Detector Shipping & Handling | 45547 | 45549 | 9239 | [6 empty] | FASTENAL | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9239 | 0 | 9239 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4844 | C | USCSB2409047A |  | Cleanroom paper shared by all hk systems | 45547 | 45551 | 2649.96 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2649.96 | 0 | 2649.96 | 0 | [73 empty] | - |  | -
Base-Build | UPW |  | USC21C003 | F21P1 UPW | 4832 | C | USCSB2409048A |  | Foxboro Instrument Swap A Side T&M | 45547 | 45548 | 3237.92 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3237.92 | 1925.7 | 1312.22 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4833 | C | USCSB2409049A |  | 25,000 FT #6/3C Wire_AMHS | 45547 | 45551 | 66675 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 66675 | 0 | 66675 | 0 | [73 empty] | - |  | -
Base-Build | UPW |  | USC24C008 | UPW B Side Project | 4834 | C | USCSB2409050A |  | T&M WRC L20 Rack Welding | 45548 | 45548 | 3891 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3891 | 0 | 3891 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4835 | C | USCSB2409051A |  | Trash bag for tool hookup team | 45548 | 45551 | 415.9 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 366.5 | 0.88122 | 49.4 | 521.73 | -472.33 | 0 | 366.5 | [72 empty] | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4849 | C | USCSB2409053A |  | P1A_AMAT_KCEPA3_CABLE WORK_Delta Wye | 45549 | 45561 | 300 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 300 | 30153.96 | -29853.96 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4850 | C | USCSB2409054A |  | WWT shortage of hardware materials on the B side and WRC | 45549 | 45551 | 510.04 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 510.04 | 0 | 510.04 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4851 | C | USCSB2409055A |  | TSMC Added Cables for 3 DPs_AMHS | 45549 | 45553 | 32975.97 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 32975.97 | 0 | 32975.97 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC22C014 | F21P1 AMHS Power Panel | 4852 | C | USCSB2409056A |  | Urgent AMHS Material for NUUO | 45552 |  | 82865.99 | [6 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 82865.99 | 196480 | -113614.01 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4853 | C | USCSB2409057A |  | Ladder for P1-B project, tool hookup team | 45552 | 45555 | 19737.03 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 19737.03 | 24774.35 | -5037.32 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4854 | C | USCSB2409058A |  | WWT shortage materials on the B side NaOH | 45552 | 45552 | 246.2 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 246.2 | 31138.21 | -30892.01 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4855 | C | USCSB2409059A |  | WWT shortage materials on the B side NaOH | 45552 | 45552 | 257.5 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 257.5 | 62983 | -62725.5 | 0 | [73 empty] | - |  | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4884 | C | USCSB2409060A |  | Hand tool, Tower Manufacturing 30396501-08 Manual-Reset 20 AMP Inline GFCI Triple Tap Cord, Yellow/Black, tool hookup team | 45552 | 45566 | 2401.72 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2401.72 | 0 | 2401.72 | 0 | [75 empty] | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4856 | C | USCSB2409061A |  | HK PCW hand tool-consumable request_ Battery Pack for 100 tools | 45553 | 45553 | 98.98 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 89.98 | 0.90907 | 9 | 2978.44 | -2969.44 | 0 | 89.98 | [72 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4857 | C | USCSB2409062A |  | Y terminals_Panduit_PV10-8F-D for HK Power for 20 tools | 45553 | 45553 | 442 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 442 | 984.08 | -542.08 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4858 | C | USCSB2409063A |  | 6-Tier Commercial Grade Heavy Duty Steel Wire Shelving | 2024/9/18 2024/10/10 | 2024/9/19 2024/10/11 | 0 | -288 | 288 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4932 | C | USCSB2409063B |  | 6-Tier Commercial Grade Heavy Duty Steel Wire Shelving | 45576 | 45577 | 229.98 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 229.98 | 2045.57 | -1815.59 | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4859 | C | USCSB2409064A |  | MIC HK power team hardwareBrady ribbon and label for 200 tools | 45553 | 45554 | 15825.25 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15825.25 | 0 | 15825.25 | 0 | [73 empty] | - |  | 4508.91
Hookup | Hookup |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4860 | C | USCSB2409065A |  | Ryan Herco: Rental fee cover August | 45553 | 45554 | 12295.2 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 0 | 0 | 12295.2 | 141.81 | 12153.39 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4861 | C | USCSB2409066A |  | CLEANROOM TAPE - 1" X 36 YDS, CLEAR | 45553 | 45555 | 491.62 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 491.62 | 0 | 491.62 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4862 | C | USCSB2409067A |  | BBP 37 label ribbon for PORT label | 45553 | 45554 | 11754.9 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11754.9 | 0 | 11754.9 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4863 | C | USCSB2409068A |  | Exhaust hand tool-consumables Requested for 200 tools | 45554 | 45555 | 4295.94 | [6 empty] | WW Grainger Inc (DBA Grainger) | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4295.94 | 14144 | -9848.06 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4882 | C | USCSB2409069A |  | Cleanroom notebooks shared by all hk systems | 45554 | 45559 | 216.72 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 216.72 | 0 | 216.72 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4864 | C | USCSB2409071A |  | P1B_Dry Etch_Module CIP(Pumping Line)_KEMEA9 | 45554 | 45555 | 15400 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15400 | 0 | 15400 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4865 | C | USCSB2409072A |  | Iron plate installation and positioning | 45554 | 45576 | 70080 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 70080 | 0 | 70080 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4866 | C | USCSB2409073A |  | Office Supples for HK shared by Hank's 4 systems | 45554 | 2024/9/23 2024/9/30 | 224.15 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | R1: Revise to change Payment Term to NET 30 | [13 empty] | 0 | 0 | 224.15 | 0 | 224.15 | 0 | [73 empty] | - |  | 192.46
Interconnection | Interconnection |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 4867 | C | USCSB2409074A |  | P1B_Dry Etch_Module CIP(Pumping Line)_KESDA6 | 45554 | 45565 | 15400 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15400 | 0 | 15400 | 0 | [73 empty] | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4868 | C | USCSB2409075A |  | RS Payroll AMAT #5113 6/13/2024 | 45554 | 45561 | 7635.62 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 7635.62 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 7635.62 |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4869 | C | USCSB2409076A |  | UNIVERSAL SORBENT PADS for upw system | 45554 | 45558 | 775.4 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 775.4 | 147460.3 | -146684.9 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC23C053 | AMAT Interconnection (TSMC) | 4889 | C | USCSB2409077A |  | CEMQ-PCA: NO TOOL ID: 4 MONTHS OF SCISSOR LIFTS | 45554 | 45559 | 2893.65 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2893.65 | 680408.73 | -677515.08 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4870 | C | USCSB2409078A |  | Sinfonia Manpower Support to MML (second batch)_8/5~12/20 | 45555 | 45559 | 426253.94 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | NTD12,319,478(@0.0346) | [13 empty] | 0 | 0 | 426253.94 | 0 | 426253.94 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4871 | C | USCSB2409079A |  | WWT shortage materials on the B side ACF-720BA~BD | 45555 | 45558 | 1849.8 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1849.8 | 2437.66 | -587.86 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4872 | C | USCSB2409080A |  | WWT change order (Galvanized Bar-Grate) from TSMC in the Fab | 45555 | 45561 | 14474.5 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14474.5 | 0 | 14474.5 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC23C011 | F21P1 AMHS MML Power Design - Muratech | 4873 | C | USCSB2409081A |  | 150 3-Pole DP Fillers_AMHS | 45555 | 45560 | 3585 | [6 empty] | HD Supply, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3585 | 0 | 3585 | 0 | [73 empty] | - |  | -
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 4894 | C | USCSB2409082A |  | P1B_AMAT_MATERIAL_CED | 45555 | 45560 | 521.73 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 521.73 | 4025.36 | -3503.63 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4895 | C | USCSB2409083A |  | Flexible Conduit for HK power tool base 45 | 45556 | 45558 | 30153.96 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 30153.96 | 0 | 30153.96 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4896 | C | USCSB2409084A |  | 250MCM 4C+G cable for Power 28 tools | 45556 |  | 188511.12 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 188511.12 | 0 | 188511.12 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4897 | C | USCSB2409085A |  | WWT shortage of hardware materials on the B side sump pump at TIMA | 45556 | 45561 | 25.63 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 25.63 | 0 | 25.63 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4898 | C | USCSB2409086A |  | 250MCM 4C+G cable for Power 40 tools | 45556 | 45560 | 196480 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 196480 | 85864.03 | 110615.97 | 0 | [73 empty] | - |  | 196480
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4899 | C | USCSB2409087A |  | Safety PPE, Tool hookup team | 45556 | 45560 | 34418 | [6 empty] | Diversified Products USA | PR Approved | PO Approved | [14 empty] | 0 | 0 | 34418 | 0 | 34418 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4900 | C | USCSB2409088A |  | Safety PPE, Tool hookup team | 45556 | 45560 | 28805 | [6 empty] | Diversified Products USA | PR Approved | PO Approved | [14 empty] | 0 | 0 | 28805 | 0 | 28805 | 0 | [73 empty] | - |  | -
Others | AMHS |  | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 4901 | C | USCSB2409089A |  | 12in Ladder Tray and Wire_AMHS | 2024/9/23 2024/9/26 | 45562 | 130675 | [6 empty] | Sonepar Mountain Holdings LLC dba QED | PR Approved | PO Approved | PR R1:As per purchasing team David to change the vendor. | [13 empty] | 0 | 0 | 130675 | 0 | 130675 | 0 | [73 empty] | - |  | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4913 | C | USCSB2409091A |  | label shared for all systems, P1-B Tool hook up team | 45560 | 45566 | 3915.15 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3915.15 | 0 | 3915.15 | 0 | [75 empty] | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4902 | C | USCSB2409092A |  | BLANK PLASTIC TAGS for tube share for gas and plastic system, P1-B tool hookup team | 45560 | 45562 | 2950 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2950 | 0 | 2950 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4903 | C | USCSB2409093A |  | Hand tool for upw system, tool hookup team | 45560 | 45562 | 979.57 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 979.57 | 317723.42 | -316743.85 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4904 | C | USCSB2409094A |  | Hand tool for upw system, tool hookup team | 45560 | 45562 | 546.19 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 546.19 | 266314.09 | -265767.9 | 0 | [73 empty] | - |  | 220.99
Base-Build | WWT |  | USC24C006 | WWT B side Project | 4905 | C | USCSB2409095A |  | WWT shortage materials on the B side NaOH H2SO4, AWD O3 | 45560 | 45561 | 1979.59 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1979.59 | 0 | 1979.59 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4906 | C | USCSB2409096A |  | Steel Padlock for HK MIMO | 45560 | 45565 | 37.39 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 37.39 | 2102 | -2064.61 | 0 | [73 empty] | - |  | 32.99
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4907 | C | USCSB2409099A |  | MIC power team hardware request RED WASH for 200 tools | 45561 | 45562 | 269.44 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 269.44 | 0 | 269.44 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4908 | C | USCSB2409100A |  | HK Power trade Hand tool_consumable Request 9/23 for 200 tools | 45561 | 45562 | 4655.16 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4655.16 | 0 | 4655.16 | 0 | [73 empty] | - |  | 36.42
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4909 | C | USCSB2409101A |  | HK Power trade Hardware_Request 9/18 for 200 tools | 45561 | 45562 | 93.97 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 93.97 | 0 | 93.97 | 0 | [73 empty] | - |  | 85.43
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4910 | C | USCSB2409102A |  | Power hardware request_ Cable tie 9/23 for 100 tools | 45561 | 45562 | 14105 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14105 | 0 | 14105 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4911 | C | USCSB2409103A |  | MIC power team hand tool padlock and chain request for 200 tools | 45561 | 45562 | 222.13 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 222.13 | 0 | 222.13 | 0 | [73 empty] | - |  | 192.68
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4912 | C | USCSB2409104A |  | Hardware 軟外塞增加 1000個 | 45561 | 45561 | 250 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved | [14 empty] | 250 | 1 | 0 | 12874 | -12874 | 0 | [73 empty] | 250 |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4913 | C | USCSB2409105A |  | MICU Spotter Quote | 45561 | 45569 | 8694 | [6 empty] | Foresight Technologies, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8694 | 0 | 8694 | 0 | [73 empty] | - |  | -
|  |  | USC23C036 | F21P1 AMAT Interconnection | 4926 | C | USCSB2409107A |  | AMAT_DIF_KDIGA5 KDIGA6 KDIGA7 KDIGA9_Eletrical materials | 45561 | 45566 | 2310.68 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2310.68 | 0 | 2310.68 | 0 | [75 empty] | -
Others | AMHS |  | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 4914 | C | USCSB2409108A |  | AMHS_Oct-Nov 9 Distribution Panels_Batch 1/2 | 45562 | 45565 | 393757.74 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 393757.74 | 0 | 393757.74 | 0 | [73 empty] | - |  | -
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4915 | C | USCSB2409109A |  | PCW hand tool consumable for 297 tools | 45562 | 45563 | 2211.32 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2211.32 | 0 | 2211.32 | 0 | [73 empty] | - |  | 442.49
Others | AMHS |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4916 | C | USCSB2409110A |  | P1AB Retrofit Work_AMHS | 45562 | 45566 | 147460.3 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 147460.3 | 0 | 147460.3 | 0 | [73 empty] | - |  | -
|  |  | USC22C025 | Tool Hookup Material (UPW&Chemical) | 4930 | C | USCSB2409111A |  | AMHS TSMC First 23 DPs CCE Scope | 45562 | 45576 | 1030141.91 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1030141.91 | 0 | 1030141.91 | 0 | [75 empty] | -
|  |  | USC22C025 | Tool Hookup Material (UPW&Chemical) | 4931 | C | USCSB2409112A |  | AMHS_Oct-Nov 9 Distribution Panels_Batch 2/2 | 45562 | 45565 | 586242.26 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 586242.26 | 0 | 586242.26 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4932 | C | USCSB2409113A |  | label kit for BBP 37 and white circle label for QC, tool hookup team | 45562 | 45565 | 2402.58 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2402.58 | 0 | 2402.58 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4933 | C | USCSB2409115A |  | MIC power team hand tool-consumable stretch wrap request for 200 tools | 45562 | 45566 | 378.84 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 378.84 | 0 | 378.84 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4934 | C | USCSB2409116A |  | MIC power team hardware request 4 AWG ?’’ terminal for 200 tools | 45562 | 45565 | 203.19 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 203.19 | 0 | 203.19 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 4935 | C | USCSB2409117A |  | WWT shortage materials on the B side L10, LB1, L20 Drain exhaust | 45562 | 45562 | 4025.36 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4025.36 | 0 | 4025.36 | 0 | [75 empty] | -
|  |  | USC23C059 | F21P1 Foundation T&M | 4936 | C | USCSB2409118A |  | 4th waffle covers from MMI | 45563 | 45567 | 70660 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 70660 | 0 | 70660 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4937 | C | USCSB2409119A |  | M18 FUEL 18V Lithium-Ion Brushless Cordless Deep Cut Band Saw with Two 5.0Ah Batteries, Charger, Hard Case, tool hookup tea, | 45563 | 45567 | 549 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 549 | 0 | 549 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4938 | C | USCSB2409120A |  | Glove Guard Extreme Cable Safe Hook, Yellow, 9 Inch HookGlove Guard Extreme Cable Safe Hook, Yellow, 9 Inch Hook | 45563 | 45566 | 2080.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2080.5 | 0 | 2080.5 | 0 | [75 empty] | -
|  |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4939 | C | USCSB2409121A |  | 27 Future Stockers_AMHS | 45563 | 45566 | 156116.42 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 156116.42 | 0 | 156116.42 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4940 | C | USCSB2409122A |  | Label printer shared for all system | 45563 | 45567 | 231.49 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 231.49 | 0 | 231.49 | 0 | [75 empty] | -
|  |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4941 | C | USCSB2409123A |  | 3 person YCF Engineers support to Muratec(20240930~20241230) | 45563 | 45562 | 10646.8 | [6 empty] | YUNG CHENG FENG ENGINEERING CO.,LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10646.8 | 0 | 10646.8 | 0 | [75 empty] | -
|  |  | USC22C025 | Tool Hookup Material (UPW&Chemical) | 4942 | C | USCSB2409124A |  | AC box relocation _AMHS | 45563 | 45566 | 50855.5 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 50855.5 | 54187.06 | -3331.56 | 0 | [75 empty] | -
|  |  | USC22C025 | Tool Hookup Material (UPW&Chemical) | 4943 | C | USCSB2409125A |  | AMHS Zip Stocker Removal | 45563 | 45566 | 22770 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 22770 | 68762.44 | -45992.44 | 0 | [75 empty] | -
|  |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4944 | C | USCSB2409126A |  | M166/M188 Future Modules_AMHS | 45563 | 45570 | 453145.33 | [7 empty] | PR Approved | PO Approving | [14 empty] | 0 | 0 | 453145.33 | 0 | 453145.33 | 0 | [75 empty] | -
|  |  | USC22C025 | Tool Hookup Material (UPW&Chemical) | 4945 | C | USCSB2409127A |  | AMHS_P1B 14 DPs CCE Scope_ Batch 1/2 | 45563 | 45575 | 562342.33 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 562342.33 | 0 | 562342.33 | 0 | [75 empty] | -
|  |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4946 | C | USCSB2409128A |  | AMHS_P1B 14 DPs CCE Scope_ Batch 2/2 | 45563 | 45575 | 488291.33 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 488291.33 | 0 | 488291.33 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4947 | C | USCSB2409129A |  | MIMO Team PO Renewal Proposal (Professional Services) - 2 Months | 45565 | 45576 | 173016.68 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | [14 empty] | 0 | 0 | 173016.68 | 0 | 173016.68 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4948 | C | USCSB2410001A |  | Electrical Insulation tape Quotation request for HK Power for 200 tools | 45566 | 45566 | 2102 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2102 | 0 | 2102 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4949 | C | USCSB2410002A |  | Cleanroom tape for HK Power for 200 tools | 45566 | 45567 | 24300 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 24300 | 0 | 24300 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4950 | C | USCSB2410003A |  | 60/40 Tin Lead Solder Wire for HK Power for 40 tools | 45566 | 45566 | 263.91 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 263.91 | 0 | 263.91 | 0 | [75 empty] | -
|  |  | USC22C034 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/ N2/APK/UPK/ASRS | 4951 | C | USCSB2410004A |  | 10/3 wire for AMHS Scope | 45566 | 45570 | 3604.35 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3604.35 | 0 | 3604.35 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 4952 | C | USCSB2410005A |  | BMWC WWT - CCR CO-2(Piping rerouting and equipment tags changes to match the design) | 45566 | 45567 | 2383 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2383 | 0 | 2383 | 0 | [75 empty] | -
| UPW |  | USC24C008 | UPW B Side Project | 4953 | C | USCSB2410006A |  | Limit Switch for SB-P Valve_UPW | 45566 | 45566 | 60.57 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 0 | 0 | 60.57 | 0 | 60.57 | 0 | [75 empty] | -
|  |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 4954 | C | USCSB2410007A |  | Lit 2: KPE604-S: GMS Box Rework | 45566 | 45569 | 12874 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 12874 | 0 | 12874 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 4955 | C | USCSB2410009A |  | WWT shortage of hardware materials on the B side | 45566 | 45567 | 320 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 320 | 0 | 320 | 0 | [75 empty] | -
|  |  | USC24C008 | UPW B Side Project | 4956 | C | USCSB2410011A |  | UPW Mezz 3 & 4 Painting | 45566 |  | 99255.87 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 99255.87 | 0 | 99255.87 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4957 | C | USCSB2410012A |  | Safety PPE, Tool hookup team | 45566 | 45570 | 1118.4 | [6 empty] | Palo Verde First Aid-Fire-Safety-Shredding | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1118.4 | 0 | 1118.4 | 0 | [75 empty] | -
|  |  | USC23C035 | TSMC F21 Heating Jacket Installation | 4958 | C | USCSB2410014A |  | 400 CGB's for distribution panels. 8 addtional panels not part of orginal scope And DP changes _AMHS | 45567 |  | 18491.95 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 18491.95 | 0 | 18491.95 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 4959 | C | USCSB2410015A |  | WWT - Brahma A-Side Carboline Flange Coating CO-2 | 45567 |  | 125505.35 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 125505.35 | 0 | 125505.35 | 0 | [75 empty] | -
|  |  | USC22C027 | CAP_E_F21P1 Autoshelf Installation 4 set | 4960 | C | USCSB2410016A |  | Additional Material needs for P1B AMHS 1/3,6/3,8/3,10/3 wire_ 1/3 batch | 45567 |  | 28552.26 | [6 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 28552.26 | 0 | 28552.26 | 0 | [75 empty] | -
|  |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 4961 | C | USCSB2410017A |  | LAM CVD Module CIP gas line modification for Tools: KCANN5/KCAPN2/KCOXNM/KCOCN2/KCOXNB/KCOXNA/KCOXNH/KCOXND/KCOXNN/KCANN4/KCT | 45567 | 45574 | 61189 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 61189 | 0 | 61189 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4962 | C | USCSB2410019A |  | Safety PPE, Tool hookup team | 45567 | 45570 | 235 | [6 empty] | Palo Verde First Aid-Fire-Safety-Shredding | PR Approved | PO Approved | [14 empty] | 0 | 0 | 235 | 0 | 235 | 0 | [75 empty] | -
|  |  | USC22C025 | Tool Hookup Material (UPW&Chemical) | 4963 | C | USCSB2410020A |  | Additional Material needs for P1B AMHS 1/3,6/3,8/3,10/3 wire_2/3 batch | 45567 |  | 50072.4 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 50072.4 | 0 | 50072.4 | 0 | [75 empty] | -
|  |  | USC22C028 | CAP_E_F21P1 Autoshelf Foundation | 4964 | C | USCSB2410021A |  | Additional Material needs for P1B AMHS 1/3,6/3,8/3,10/3 wire_3/3 batch | 45567 |  | 20147.79 | [6 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 20147.79 | 0 | 20147.79 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4965 | C | USCSB2410022A |  | Hand tool-consumable for HK power | 45568 | 45570 | 3794.53 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3794.53 | 0 | 3794.53 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 4966 | C | USCSB2410023A |  | This is Tsmc clean trench project which issue a PO to us to have MICU pay their vendor first. | 45568 | 45581 | 285092.78 | [6 empty] | Clean Harbors Environmental Services Inc | PR Approved | PO Approving | [14 empty] | 0 | 0 | 285092.78 | 0 | 285092.78 | 0 | [75 empty] | -
|  |  | USC23C035 | TSMC F21 Heating Jacket Installation | 4967 | C | USCSB2410024A |  | DP Design Change_AMHS_1/7 batch | 45568 | 45576 | 8608.27 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8608.27 | 0 | 8608.27 | 0 | [75 empty] | -
|  |  | USC22C027 | CAP_E_F21P1 Autoshelf Installation 4 set | 4968 | C | USCSB2410025A |  | DP Design Change_AMHS_2/7 batch | 45568 | 45576 | 947.74 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 947.74 | 2170.65 | -1222.91 | 0 | [75 empty] | -
|  |  | USC22C014 | F21P1 AMHS Power Panel | 4969 | C | USCSB2410026A |  | DP Design Change_AMHS_3/7 batch | 45568 | 45576 | 47762.44 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 47762.44 | 181.85 | 47580.59 | 0 | [75 empty] | -
|  |  | USC22C034 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/ N2/APK/UPK/ASRS | 4970 | C | USCSB2410027A |  | DP Design Change_AMHS_4/7 batch | 45568 | 45576 | 8225.65 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8225.65 | 0 | 8225.65 | 0 | [75 empty] | -
|  |  | USC22C028 | CAP_E_F21P1 Autoshelf Foundation | 4971 | C | USCSB2410028A |  | DP Design Change_AMHS_5/7 batch | 45568 | 45576 | 4714.21 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4714.21 | 0 | 4714.21 | 0 | [75 empty] | -
|  |  | USC22C025 | Tool Hookup Material (UPW&Chemical) | 4972 | C | USCSB2410029A |  | DP Design Change_AMHS_6/7 batch | 45568 | 45576 | 299045.58 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 299045.58 | 0 | 299045.58 | 0 | [75 empty] | -
|  |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 4973 | C | USCSB2410030A |  | DP Design Change_AMHS_7/7 batch | 45568 | 45576 | 379483.64 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 379483.64 | 0 | 379483.64 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 4974 | C | USCSB2410031A |  | WWT LSR Heat Exchanger insulation | 45568 | 45573 | 34392 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 0 | 0 | 34392 | 0 | 34392 | 0 | [75 empty] | -
|  |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 4975 | C | USCSB2410032A |  | 5th 1000pcs tile swap | 45568 | 45569 | 26052 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 26052 | 0 | 26052 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4976 | C | USCSB2410033A |  | HK YAHO Equipment rental End date 08/31/2024 | 45568 | 45572 | 1448000 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1448000 | 0 | 1448000 | 0 | [75 empty] | -
|  |  | USC22C025 | Tool Hookup Material (UPW&Chemical) | 4977 | C | USCSB2410034A |  | Urgent 7 DP Fillers_AMHS | 45568 | 45570 | 443.87 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 443.87 | 0 | 443.87 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4978 | C | USCSB2410035A |  | HK Chuan Ta Technology Corp Equipment rental End date 08/31/2024 | 45568 | 45573 | 56000 | [6 empty] | Chuan Ta Technology Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 56000 | 0 | 56000 | 0 | [75 empty] | -
|  |  | USC22C025 | Tool Hookup Material (UPW&Chemical) | 4979 | C | USCSB2410036A |  | Urgent 23 DP Fillers_AMHS | 45568 | 45570 | 1371.03 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1371.03 | 0 | 1371.03 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4980 | C | USCSB2410037A |  | Laien Parts Technology Co.， Ltd Equipment rental End date 08/31/2024 | 45568 | 45573 | 54400 | [6 empty] | Laien Parts Technology Co., Ltd. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 54400 | 0 | 54400 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4981 | C | USCSB2410038A |  | HK GENII IDEAS Co.， Ltd Equipment rental End date 08/31/2024 | 45568 | 45573 | 260400 | [6 empty] | GENII IDEAS Co., Ltd. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 260400 | 0 | 260400 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4982 | C | USCSB2410039A |  | HK Li Jie Industrial Co.，Ltd Equipment rental End date 08/31/2024 | 45568 | 45574 | 463284 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 463284 | 0 | 463284 | 0 | [75 empty] | -
|  |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4983 | C | USCSB2410040A |  | HK_Wholetech_Equipment Rental_1st PO_End date 12/31/2024 | 45568 |  | 96500 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 96500 | 0 | 96500 | 0 | [75 empty] | -
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 4984 | C | USCSB2410041A |  | HK_HuengLuei Equipment Rental_1st PO_End date 12/31/2023 | 45568 | 45575 | 38660 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 38660 | 0 | 38660 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4985 | C | USCSB2410042A |  | HK_Tunyi_Equipment Rental_2nd PO_End date 8/31/2024 | 45568 | 45582 | 434661.05 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approving | [14 empty] | 0 | 0 | 434661.05 | 0 | 434661.05 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4986 | C | USCSB2410043A |  | HK_Third_Equipment Rental_2nd PO_End date 8/31/2024 | 45568 | 45575 | 80000 | [6 empty] | DA YI CHENG Technology Co., Ltd. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 80000 | 0 | 80000 | 0 | [75 empty] | -
Hookup | Hookup |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4987 | C | USCSB2410044A |  | HK_Hueng Luei_Equipment Rental_2nd PO_End date 8/31/2024 | 45568 | 45582 | 83040 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 83040 | 0 | 83040 | 0 | [75 empty] | -
|  |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4988 | C | USCSB2410045A |  | Additional Material needs for P1B AMHS 1/3,6/3,8/3,10/3 wire_the last DP materials. | 45568 |  | 155479.92 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 155479.92 | 0 | 155479.92 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4989 | C | USCSB2410046A |  | HK_Wholetech_Equipment Rental_2nd PO_End date 8/31/2024 | 45569 |  | 538000 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 538000 | 0 | 538000 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5005 | C | USCSB2410047A |  | extension cord for Plastic system, tool hook up team | 45569 | 45572 | 1250 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1250 | 0 | 1250 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4990 | C | USCSB2410048A |  | 3-plex cleaning services | 45569 | 45575 | 2700 | [6 empty] | Viking Facility Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2700 | 0 | 2700 | 0 | [75 empty] | -
|  |  | USC24C013 | Organo USA - UPW Electrical | 4991 | C | USCSB2410049A |  | Door frame & door for Mezz#3 | 45569 | 2024/10/7 2024/10/11 | 3780 | 280 | 3500 |  |  |  |  | Suncoast Glass & Glazing,LLC dba Mirror Works dba Horn Doors | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3780 | 0 | 3780 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4992 | C | USCSB2410050A |  | HK_Chi Yi Hsin_Equipment Rental_2nd PO_End date 8/31/2024 | 45569 | 45575 | 648000 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 648000 | 0 | 648000 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4993 | C | USCSB2410051A |  | HK_Youngchi_Equipment Rental_1st PO_End date 8/31/2024 | 45569 |  | 151000 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 151000 | 0 | 151000 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 4994 | C | USCSB2410052A |  | HK_JerYih_Equipment Rental_1st PO_End date 8/31/2024 | 45569 | 45576 | 120996.5 | [6 empty] | Jer-Yih Electrical Engineering Ltd. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 120996.5 | 0 | 120996.5 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5011 | C | USCSB2410053A |  | extension cord for all system, tool hook up team | 45569 | 45572 | 2276.85 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2276.85 | 0 | 2276.85 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 4995 | C | USCSB2410055A |  | PCW CYH Hand tool Purchase request 10/2 for 200 tools | 45569 | 45569 | 5022.9 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5022.9 | 0 | 5022.9 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 4996 | C | USCSB2410056A |  | WWT Stripper system label | 45569 | 45569 | 2145.65 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2145.65 | 0 | 2145.65 | 0 | [75 empty] | -
Base-Build |  |  | USC21C011 | F21 TMAH System | 4997 | C | USCSB2410057A |  | 5191-8121 vials and 5191-8151 caps for LS_MS/MS TMAH room device | 45569 | 45569 | 181.85 | [6 empty] | VWR International, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 181.85 | 0 | 181.85 | 0 | [75 empty] | -
|  |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 5015 | C | USCSB2410058A |  | ALPS Manpower Support to MML(14週) | 45569 | 45573 | 17836 | [6 empty] | ALPSGIKEN TAIWAN CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 17836 | 0 | 17836 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5016 | C | USCSB2410059A |  | Third Party Inspection Services 4 CWI Inspectors for 17 weeks | 45570 | 45575 | 222360 | [6 empty] | Independent QA/QC Services Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 222360 | 0 | 222360 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5017 | C | USCSB2410060A |  | container for water storage, upw system Tool HK team | 45570 | 45576 | 48.09 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 48.09 | 0 | 48.09 | 0 | [75 empty] | -
|  |  | USC24C020 | F21P1 CCTV_New Request | 5018 | C | USCSB2410061A |  | F21-P1B CCTV new requirement for fence area | 45570 | 45576 | 28866.6 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 28866.6 | 0 | 28866.6 | 0 | [75 empty] | -
|  |  | USC24C020 | F21P1 CCTV_New Request | 5019 | C | USCSB2410062A |  | F21-P1 CCTV and ACS for HPM(A&B) & pump room | 45570 | 45576 | 36163.8 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 36163.8 | 0 | 36163.8 | 0 | [75 empty] | -
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 5020 | C | USCSB2410071A |  | HK Trusval Technology CO.， LTD Equipment rental End date 08/31/2024 | 45571 |  | 792950 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 792950 | 0 | 792950 | 0 | [75 empty] | -
|  |  | USC23C003 | F21P1 Module Tool Interconnection CVD | 5021 | C | USCSB2410072A |  | P1B AMAT CVD1 -- GreenBerry | 45572 | 45580 | 227000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 227000 | 0 | 227000 | 0 | [75 empty] | -
|  |  | USC23C036 | F21P1 AMAT Interconnection | 5052 | C | USCSB2410073A |  | P1B_AMAT_EPI_KCEPA4_MATERIAL_Crescent | 45572 | 45581 | 14896 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14896 | 0 | 14896 | 0
|  |  | USC24C006 | WWT B side Project | 5022 | C | USCSB2410074A |  | Additional support for LSR&CCR system | 45573 | 45576 | 41653.6 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 41653.6 | 0 | 41653.6 | 0 | [75 empty] | -
|  |  | USC23C059 | F21P1 Foundation T&M | 5023 | C | USCSB2410075A |  | MMI foundation/seismic related T&M. | 45573 | 45575 | 100000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 100000 | 0 | 100000 | 0 | [75 empty] | -
|  |  | USC23C047 | F21P1 HK Seismic Installation | 5024 | C | USCSB2410076A |  | P1B seismic order | 45573 |  | 2629200 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 2629200 | 0 | 2629200 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 5025 | C | USCSB2410077A |  | WWT - EOR Services for CWR Stripper and Enzyme Cabinet Additions | 45573 |  | 27160 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 27160 | 0 | 27160 | 0 | [75 empty] | -
|  |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 5026 | C | USCSB2410078A |  | KDSTSH_AIB-F-18 Modification | 45573 | 45576 | 14490.59 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14490.59 | 0 | 14490.59 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 5027 | C | USCSB2410080A |  | F21P1 Temporary Tent Area Secruity & CCTV System equipment | 45574 |  | 239911 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 239911 | 0 | 239911 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 5028 | C | USCSB2410081A |  | UPW Mezz 3 & 4 Painting | 45574 | 45576 | 96229.05 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 96229.05 | 0 | 96229.05 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5029 | C | USCSB2410082A |  | Office Related request shared by all HK System | 45574 | 45576 | 169.43 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 169.43 | 0 | 169.43 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 5030 | C | USCSB2410083A |  | Move in and Installation of 20 speed gates_5 ACS Panels_54 CAT6 Cables_6 Power Cords | 45574 |  | 234145.3 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 234145.3 | 0 | 234145.3 | 0 | [75 empty] | -
|  |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 5031 | C | USCSB2410086A |  | Lit 1: KPAN03-S: CIP UPW Line | 45574 | 45582 | 6789 | [7 empty] | PR Approved | PO Approving | [14 empty] | 0 | 0 | 6789 | 0 | 6789 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 5032 | C | USCSB2410087A |  | Clean materials for WWT | 45574 | 45582 | 289.3 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approving | [14 empty] | 0 | 0 | 289.3 | 0 | 289.3 | 0 | [75 empty] | -
|  |  | USC24C008 | UPW B Side Project | 5033 | C | USCSB2410088A |  | UMEC EXTEND GC MAY 2024 | 45574 |  | 419041 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 419041 | 0 | 419041 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5035 | C | USCSB2410090A |  | Pressure washer for HK MIMO | 45575 | 45580 | 398.16 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 398.16 | 0 | 398.16 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5036 | C | USCSB2410091A |  | Pad locks for EEW | 45575 | 45580 | 1381.71 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1381.71 | 0 | 1381.71 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5037 | C | USCSB2410092A |  | Hand tools request for HK power for 200 tools | 45575 | 45581 | 13590.24 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approving | [14 empty] | 0 | 0 | 13590.24 | 0 | 13590.24 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5038 | C | USCSB2410093A |  | 100 Liquid Argon for Gas, Chemical, PCW, and PPL for HK | 45575 |  | 49910 | [6 empty] | Linde Gas & Equipment Inc. | PR Approved | PO Processing | [14 empty] | 0 | 0 | 49910 | 0 | 49910 | 0 | [75 empty] | -
|  |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 5069 | C | USCSB2410094A |  | M197 PSP-3A and 3B Relocation | 45576 |  | 18031.08 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 18031.08 | 0 | 18031.08 | 0
|  |  | USC23C054 | UPW Change Order | 5039 | C | USCSB2410095A |  | Valves for Added POU Scope | 45576 |  | 796 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 796 | 0 | 796 | 0 | [75 empty] | -
|  |  | USC24C006 | WWT B side Project | 5071 | C | USCSB2410096A |  | Mezzanine 3 Floor/ Pad Epoxy Coating Phase 2 | 45576 |  | 199960.14 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 199960.14 | 0 | 199960.14 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5072 | C | USCSB2410098A |  | PCW_CYH Hand tools consumable Request 10/7 for 200 tools | 45576 | 45581 | 163.37 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approving | [14 empty] | 0 | 0 | 163.37 | 0 | 163.37 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5073 | C | USCSB2410099A |  | CYH Hand tools Request 10/10 for 200 tools | 45576 | 45581 | 1115.09 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approving | [14 empty] | 0 | 0 | 1115.09 | 0 | 1115.09 | 0
|  |  | USC23C036 | F21P1 AMAT Interconnection | 5074 | C | USCSB2410100A |  | ITC AMAT KSSBAC KSAPA2 MATERIALS NEED 2 CRIMPER AND 2 STRIPPER | 45576 | 45581 | 670.91 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 670.91 | 0 | 670.91 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5075 | C | USCSB2410103A |  | Crimping Tools 10-8AWG for HK Power for 297 tools | 45577 |  | 1422.94 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1422.94 | 0 | 1422.94 | 0
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 5076 | C | USCSB2410104A |  | Ryan Herco: Rental fee cover September | 45577 |  | 7582.6 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 7582.6 | 0 | 7582.6 | 0
|  |  | USC21C003 | F21P1 UPW | 5077 | C | USCSB2410105A |  | Added POU Scope in LB1, L20 & L30 | 45577 |  | 687063 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 687063 | 0 | 687063 | 0
|  |  | USC24C018 | Tool Hook Up E2 Trade Equipment Rental | 5078 | C | USCSB2410106A |  | HK Chuan Ta Technology Corp Equipment rental End date 08/31/2024 | 45577 |  | 77000 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 77000 | 0 | 77000 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5079 | C | USCSB2410107A |  | QA OFFICE SUPPLIES | 45580 | 45580 | 239.35 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approving | [14 empty] | 0 | 0 | 239.35 | 0 | 239.35 | 0
|  |  | USC24C005 | Chemical & WCCS B Side Project | 5080 | C | USCSB2410108A |  | Greenberry engineering requirements F21 B side pressure test engineering | 45580 |  | 570000 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 570000 | 0 | 570000 | 0
|  |  | USC21C003 | F21P1 UPW | 5081 | C | USCSB2410109A |  | POU Added Scopes in LB1, L20 & L30 | 45580 |  | 22074.27 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 22074.27 | 0 | 22074.27 | 0
|  |  | USC24C006 | WWT B side Project | 5082 | C | USCSB2410110A |  | WWT shortage materials on Drain PT Sampling Port & RO CCR Punch List | 45580 |  | 1804 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1804 | 0 | 1804 | 0
|  |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 5083 | C | USCSB2410111A |  | PCI foundation area exceeded scope | 45580 |  | 600000 | [6 empty] | 0 | PR Approving | PR Applying | [14 empty] | 0 | 0 | 600000 | 0 | 600000 | 0
|  |  | USC23C053 | AMAT Interconnection (TSMC) | 5084 | C | USCSB2410112A |  | P1B, ICT, PCA SOW, NEC | 45581 | 45581 | 3826.47 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approving | [14 empty] | 0 | 0 | 3826.47 | 0 | 3826.47 | 0
|  |  | USC23C036 | F21P1 AMAT Interconnection | 5085 | C | USCSB2410113A |  | P1B AMAT CVD/PVD/EPI/DIF ELETRICAL - AUCAN 79 TOOLS | 45581 |  | 3344328 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 3344328 | 0 | 3344328 | 0
|  |  | USC24C005 | Chemical & WCCS B Side Project | 5086 | C | USCSB2410114A |  | MICU-010 @ T&M Work - CDS L10 L20 L30 - Cleanroom CPVC-SS-PFA Chem. System Tubes W.O. No. PENDING | 45581 |  | 1078272.58 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 1078272.58 | 0 | 1078272.58 | 0
|  |  | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 2476 | C | USCSB2410115A |  | P1B_Dry Etch_Module CIP(Pumping Line)_KEMEA6,7,8 | 45581 |  | 46200 | [6 empty] | 0 | PR Approving | PR Applying | [14 empty] | 0 | 0 | 46200 | 0 | 46200 | 0
|  |  | USC24C006 | WWT B side Project | 5088 | C | USCSB2410116A |  | P-760AB Removal and Transportation - CO | 45581 |  | 2700 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 2700 | 0 | 2700 | 0
|  |  | USC24C005 | Chemical & WCCS B Side Project | 5089 | C | USCSB2410117A |  | TSMC-030 @ Side A & B Lorry / HPM20 Solvent Room / L15 Bridge Pressure Tests and PFA Pulls / Terminations | 45581 |  | 350000 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 350000 | 0 | 350000 | 0
|  |  | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 5090 | C | USCSB2410118A |  | Additional Material needs for P1B AMHS 1/3,6/3,8/3,10/3 wire_the last DP materials. | 45582 |  | 118555 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 118555 | 0 | 118555 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 5091 | C | USCSB2410119A |  | Laminating sheet for HK shared by all systems | 45582 |  | 142.93 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 142.93 | 0 | 142.93 | 0
|  |  | USC23C015 | F21P1 AMHS Wiring Work Outline | 5092 | C | USCSB2410121A |  | Kai Yang Manpower Support to MML | 45582 |  | 19110 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 19110 | 0 | 19110 | 0
|  |  | USC24C006 | WWT B side Project | 5093 | C | USCSB2410122A |  | A site, B site and WRC New Manpower Requirement | 45582 |  | 441650 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 441650 | 0 | 441650 | 0
|  |  | USC24C006 | WWT B side Project | 5094 | C | USCSB2410123A |  | Blower for UMEC not included in original scope | 45582 |  | 177419 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 177419 | 0 | 177419 | 0
|  |  | USC24C013 | Organo USA - UPW Electrical | 5095 | C | USCSB2410124A |  | UMEC EXTEND GC AUGUST 2024 | 45582 |  | 198172.7 | [7 empty] | PR Approved | PO Approved | [14 empty] | 0 | 0 | 198172.7 | 0 | 198172.7 | 0
|  |  | USC24C005 | Chemical & WCCS B Side Project | 5096 | C | USCSB2410125A |  | D24O21023-支援F21 帆宣電力工程-點工(不含電機具)04到8/31_內連線5個人 | 45583 |  | 74710 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 74710 | 0 | 74710 | 0
|  |  | USC24C005 | Chemical & WCCS B Side Project | 5097 | C | USCSB2410126A |  | [Urgent RFQ No. 290] Chemical Team Power Materials Needed | 45583 |  | 37844 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 37844 | 0 | 37844 | 0
|  |  | USC24C005 | Chemical & WCCS B Side Project | 5098 | C | USCSB2410127A |  | F21 A.B side CO2_ Pressure head Brass Fitting Adaptor | 45583 |  | 3180 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 3180 | 0 | 3180 | 0
|  |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 5099 | C | USCSB2410128A |  | Lit 1: KPAN03-S: Cable Rework | 45583 |  | 3496 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 3496 | 0 | 3496 | 0
Non-TSMC | MIC - Material | Material | USC22C016 | Asahi Valve and Positioner from Harrington |  | C | USCSB2210011A |  | Asahi Valve and Positioner from Harrington | 44841 | 44843 | 54894.23 | [23 empty] | 54894.23 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 54371.57 | 522.66 | [5 empty] | 0 | [11 empty] | 0 |  | 0 | 0 | 0
Non-TSMC | MIC - Material | Material | USC22C016 | Asahi Valve and Positioner from Harrington |  | C | USCSB2212036A |  | Asahi valve from Harrington | 44915 | 44917 | 2833.95 | [23 empty] | 2833.95 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 986.9 |  |  | 0 |  |  | 1847.05 | [8 empty] | 0 |  | 0 | 0 | 0
Non-TSMC | MIC - Material | Material | USC22C016 | Asahi Valve and Positioner from Harrington |  | C | USCSB2301015A |  | Asahi valve from Harrington | 44936 | 44936 | 761.76 | [23 empty] | 761.76 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 761.76 | [8 empty] | 0 |  | 0 | 0 | 0
Non-TSMC | MIC - Material | Equipment | USC23C010 | Holon-Mitsubishi Breaker |  | C | USCSB2301028A |  | Mitsubishi Breaker | 44973 | 44974 | 0 | [23 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0
Non-TSMC | MIC - Material | Material | USC22C016 | Asahi Valve and Positioner from Harrington |  | C | USCSB2301057A |  | Gasket from Harrington | 44954 | 44957 | 1586.56 | [23 empty] | 1586.56 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 1586.56 | [11 empty] | 0 |  | 0 | 0 | 0
Non-TSMC | MIC - Material | Material | USC22C016 | Asahi Valve and Positioner from Harrington |  | C | USCSB2310159A |  | Gasket from Harrington for M5 | 45223 | 45225 | 1142.44 | [23 empty] | 1142.44 | 1 | 0 | 0 | 0 | 0 | [46 empty] | 1142.44
Non-TSMC | MIC - Material | Material | USC22C016 | Asahi Valve and Positioner from Harrington |  |  | USCSB2312125A |  | Gasket from Harrington_1207 request |  |  | 6081.02 | [23 empty] | 6081.02 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 6081.02

## Stack_dummy
TSMC 新工 | Type | Type2 | Main/CO/DCR | Actual Pertain | PM Type | Category | Scope | Project Number | PO # | Amount | Project Name | Item | Type22 | Rev | PO Description | PR Date | PO Date | Change Order | Original | Price Change --Reason for change 1 價格異動 2 項目異動 3 數量異動 4業主變更 | Item Change | Quantity Change | Client Request | Vendor/Subcontractor | PR 狀況備註 | PO 狀況備註 | Remark M2 | Remark Elaine | Payment Term | Incoterms | Warranty | 請購人 | 採購人 | OCIP Enrollment | PO Signed Back | PM | Budget Item | GMP | Form 5000 or 5005 | Lien Filed | Accumulated AP (Paid) | AP % | Balance Before Open Invoice | Open Invoice | Balance | Total Plan | Debit and Credit Card/ Previous | 102021 Real | 112021 Real | 122021 Real | 012022 Real | 022022 Real Urgent Payment | 022022 Real Regular | 032022 | 042022 | 052022 20th payment | 052022 5th payment | 062022 20th payment | 062022 5th payment | 072022 20th payment | 072022 5th payment | 082022 20th payment | 082022 5th payment | 092022 20th payment | 092022 5th payment | 102022 20th payment | 102022 5th payment | 112022 20th payment | 112022 5th payment | 122022 20th payment | 122022 5th payment | 012023 20th payment | 012023 5th payment | 022023 20th payment | 022023 5th payment | 032023 20th payment | 032023 5th payment | 042023 20th payment | 042023 5th payment | 052023 20th payment | 052023 5th payment | 062023 20th payment | 062023 5th payment | 072023 20th payment | 072023 5th payment | 082023 20th payment | 082023 5th payment | 092023 20th payment | 092023 5th payment | 102023 20th payment | 102023 5th payment | 112023 20th payment | 112023 5th payment | 122023 20th payment | 122023 5th payment | 012024 20th Payment | 012024 5th Payment | 022024 20th Payment | 022024 5th Payment | 032024 20th Payment | 032024 5th Payment | 042024 20th Plan | 042024 20th Payment | 042024 5th Plan | 042024 5th Paymen | 052024 20th Plan | 052024 20th Payment | 052024 5th Plan | 052024 5th Payment | 062024 20th Plan | 062024 20th Payment | 062024 5th Plan | 062024 5th Payment | 072024 20th Plan | 072024 20th Payment | 072024 5th Plan | 072024 5th Payment | 082024 Plan | 082024 20th Payment | 082024 5th Payment | 092024 Plan | 092024 20th Payment | 102024 Plan | 112024 Plan | 122024 Plan
Base-Build | Chemical | Harder | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2201007A | 94143616.47 | F21P1 Chemical & WCCS package | 1368 | C | -04 | Chemical Mechanical Work #1 & #2 | 2022/1/20 2024/1/12 2024/2/6 2024/6/13 | 2022/1/25 2023/1/8 2024/1/15 2024/2/13 2024/6/13 | -1578248.72 | 95721865.19 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R4: As per engineer Johnny to cancel all Harder orders. R3: As per Johnny Wan,Due to Harder will leave this month on 2/23.So we need to remove the amount from Harder's project. R2: As per Engineer Johhny Wan to change the scope for Harder, but do not release until all contract is finalized | According to contract 95% by progress-T/T 30 days-after acceptance; 5% as-built drawing & punch list-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | CHEM |  |  |  |  | 5005 |  | 94143616.47 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 2094129 | 2704016.22 | 4040544.33 |  | 417465.07 | 0 | 1781642.51 |  | 4216462.61 |  | 3064264.82 |  | 3572903.14 |  | 5786891.65 |  | 8297322.7 |  | 11850710.2 |  | 4008521.26 |  | 1601905.82 |  | 4809804.55 |  | 6771650.72 | 0 | 3721362.34 |  | 2554883.36 |  | 3727093.67 |  | 3847670.9 | 0 | 0 | 0 |  | 301793 | 2844224.5 | 2000000 | 4206602.82 | 0 | 2220598.35 |  | 0 | 2535701.9 | 423796 |  | 741655.03 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2108001A | 86000000 | F21P1 UPW | 1317 | C |  | Mechanical works for UPW package | 44427 | 44435 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | UPW | 44461 | Matt |  | Y | 5005 |  | 85961575 | 0.99955 | 38425 | 0 | 38425 | 0 |  | 2466924 | 982645 | 3906729 | 2943825 |  | 2276834 | 4461100 | 450026 | 6877712 |  | 5267057 |  | 2091083 |  | 2215396.33 |  |  | 2511386 | 6073662 |  | 4453731 |  | 4081416 |  | 8156020.16 |  | 4183951.51 | 0 | 2540935 |  | 4203592 |  | 0 | 2367969 | 3457032 |  | 1526847 |  | 2971422 | 0 | 1217312 | 0 | 2315152 |  | 0 | 1635302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 364939 | [6 empty] | 326514 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | LPS | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C009 | USCSB2109003A | 24675557.76 | F21P1 WWT package (Installation and 2 batch tanks) | 1321 | C | -03 | Mechanical/Installation w/Engineering Support | 44443 | 44462 | -3324442.24 | 28000000 |  | V |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | 2/2 contract terminate 7/11 change order (remove equipment rigging scope) 9/2 scope reduction | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Rui Ma | Cherry Chang | WWT | 44515 | Henry |  | Y | 5005 |  | 24675557.76 | 1 | 0 | 0 | 0 | 0 |  |  | 905030 | 521272.65 |  | 276903.42 | 921068.63 | 4146903.13 | 603353.33 |  | 1036753.1 |  |  |  | 1050957.87 | 1402278.28 |  | 1611859.33 | 1847484.66 |  | 102100 | 1675184.02 | 2017484.57 | 6556924.77 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0

## pc_overview_dummy
TSMC 新工 | Type | Type2 | Project Number | Project Name | Item | Type22 | PO # | Rev | PO Description | PR Date | PO Date | Amount | Change Order | Original | Price Change --Reason for change 1 價格異動 2 項目異動 3 數量異動 4業主變更 | Item Change | Quantity Change | Client Request | Vendor/Subcontractor | PR 狀況備註 | PO 狀況備註 | Remark M2 | Remark Elaine | Payment Term | Incoterms | Warranty | 請購人 | 採購人 | OCIP Enrollment | PO Signed Back | PM | Budget Item | GMP | Form 5000 or 5005 | Lien Filed | Accumulated AP (Paid) | AP % | Balance Before Open Invoice | Open Invoice | Balance | Total Plan | Debit and Credit Card/ Previous | 102021 Real | 112021 Real | 122021 Real | 012022 Real | 022022 Real Urgent Payment | 022022 Real Regular | 032022 | 042022 | 052022 20th payment | 052022 5th payment | 062022 20th payment | 062022 5th payment | 072022 20th payment | 072022 5th payment | 082022 20th payment | 082022 5th payment | 092022 20th payment | 092022 5th payment | 102022 20th payment | 102022 5th payment | 112022 20th payment | 112022 5th payment | 122022 20th payment | 122022 5th payment | 012023 20th payment | 012023 5th payment | 022023 20th payment | 022023 5th payment | 032023 20th payment | 032023 5th payment | 042023 20th payment | 042023 5th payment | 052023 20th payment | 052023 5th payment | 062023 20th payment | 062023 5th payment | 072023 20th payment | 072023 5th payment | 082023 20th payment | 082023 5th payment | 092023 20th payment | 092023 5th payment | 102023 20th payment | 102023 5th payment | 112023 20th payment | 112023 5th payment | 122023 20th payment | 122023 5th payment | 012024 20th Payment | 012024 5th Payment | 022024 20th Payment | 022024 5th Payment | 032024 20th Payment | 032024 5th Payment | 042024 20th Plan | 042024 20th Payment | 042024 5th Plan | 042024 5th Paymen | 052024 20th Plan | 052024 20th Payment | 052024 5th Plan | 052024 5th Payment | 062024 20th Plan | 062024 20th Payment | 062024 5th Plan | 062024 5th Payment | 072024 20th Plan | 072024 20th Payment | 072024 5th Plan | 072024 5th Payment | 082024 Plan | 082024 20th Payment | 082024 5th Payment | 092024 Plan | 092024 20th Payment | 102024 Plan | 112024 Plan | 122024 Plan
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 1368 | C | USCSB2201007A | -04 | Chemical Mechanical Work #1 & #2 | 2022/1/20 2024/1/12 2024/2/6 2024/6/13 | 2022/1/25 2023/1/8 2024/1/15 2024/2/13 2024/6/13 | 94143616.47 | -1578248.72 | 95721865.19 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R4: As per engineer Johnny to cancel all Harder orders. R3: As per Johnny Wan,Due to Harder will leave this month on 2/23.So we need to remove the amount from Harder's project. R2: As per Engineer Johhny Wan to change the scope for Harder, but do not release until all contract is finalized | According to contract 95% by progress-T/T 30 days-after acceptance; 5% as-built drawing & punch list-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | CHEM |  |  |  |  | 5005 |  | 94143616.47 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 2094129 | 2704016.22 | 4040544.33 |  | 417465.07 | 0 | 1781642.51 |  | 4216462.61 |  | 3064264.82 |  | 3572903.14 |  | 5786891.65 |  | 8297322.7 |  | 11850710.2 |  | 4008521.26 |  | 1601905.82 |  | 4809804.55 |  | 6771650.72 | 0 | 3721362.34 |  | 2554883.36 |  | 3727093.67 |  | 3847670.9 | 0 | 0 | 0 |  | 301793 | 2844224.5 | 2000000 | 4206602.82 | 0 | 2220598.35 |  | 0 | 2535701.9 | 423796 |  | 741655.03 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 1369 | C | USCSB2201008A |  | tsmc F21P1 VOC 雜項工程 | 44587 | 44589 | 100000 | [6 empty] | Desiccant Technology Corporation | PR Approved | PO Approved |  | 100% upon receipt- T/T 30 days (after acceptance) | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y |  |  |  |  | NA |  | 100000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 100000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Material | USC21C008 | F21P1 CCTV & Security | 1370 | C | USCSB2201009A | -01 | Access Control/Wifi/CCTV in new Office/Warehouse | 44589 | 44602 | 92382.74 | 3946.98 | 88435.76 | V | V |  |  | Galaxy3 LLC | PR Approved | PO Approved | Some material/work was not necessary/changed, so the price has been reduced | According to Contract 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | N | [6 empty] | 92382.74 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 92382.74 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0