## Stack
TSMC 新工 | Type | Type2 | Main/CO/DCR | Actual Pertain | PM Type | Category | Scope | Project Number | PO # | Amount | Project Name | Item | Type22 | Rev | PO Description | PR Date | PO Date | Change Order | Original | Price Change --Reason for change 1 價格異動 2 項目異動 3 數量異動 4業主變更 | Item Change | Quantity Change | Client Request | Vendor/Subcontractor | PR 狀況備註 | PO 狀況備註 | Remark M2 | Remark Elaine | Payment Term | Incoterms | Warranty | 請購人 | 採購人 | OCIP Enrollment | PO Signed Back | PM | Budget Item | GMP | Form 5000 or 5005 | Lien Filed | Accumulated AP (Paid) | AP % | Balance Before Open Invoice | Open Invoice | Balance | Total Plan | Debit and Credit Card/ Previous | 102021 Real | 112021 Real | 122021 Real | 012022 Real | 022022 Real Urgent Payment | 022022 Real Regular | 032022 | 042022 | 052022 20th payment | 052022 5th payment | 062022 20th payment | 062022 5th payment | 072022 20th payment | 072022 5th payment | 082022 20th payment | 082022 5th payment | 092022 20th payment | 092022 5th payment | 102022 20th payment | 102022 5th payment | 112022 20th payment | 112022 5th payment | 122022 20th payment | 122022 5th payment | 012023 20th payment | 012023 5th payment | 022023 20th payment | 022023 5th payment | 032023 20th payment | 032023 5th payment | 042023 20th payment | 042023 5th payment | 052023 20th payment | 052023 5th payment | 062023 20th payment | 062023 5th payment | 072023 20th payment | 072023 5th payment | 082023 20th payment | 082023 5th payment | 092023 20th payment | 092023 5th payment | 102023 20th payment | 102023 5th payment | 112023 20th payment | 112023 5th payment | 122023 20th payment | 122023 5th payment | 012024 20th Payment | 012024 5th Payment | 022024 20th Payment | 022024 5th Payment | 032024 20th Payment | 032024 5th Payment | 042024 20th Plan | 042024 20th Payment | 042024 5th Plan | 042024 5th Paymen | 052024 20th Plan | 052024 20th Payment | 052024 5th Plan | 052024 5th Payment | 062024 20th Plan | 062024 20th Payment | 062024 5th Plan | 062024 5th Payment | 072024 20th Plan | 072024 20th Payment | 072024 5th Plan | 072024 5th Payment | 082024 Plan | 082024 20th Payment | 082024 5th Payment | 092024 Plan | 102024 Plan | 112024 Plan | 122024 Plan
Base-Build | Chemical | Harder | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2201007A | 94143616.47 | F21P1 Chemical & WCCS package | 1324 | C | -04 | Chemical Mechanical Work #1 & #2 | 2022/1/20 2024/1/12 2024/2/6 2024/6/13 | 2022/1/25 2023/1/8 2024/1/15 2024/2/13 2024/6/13 | -1578248.72 | 95721865.19 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R4: As per engineer Johnny to cancel all Harder orders. R3: As per Johnny Wan,Due to Harder will leave this month on 2/23.So we need to remove the amount from Harder's project. R2: As per Engineer Johhny Wan to change the scope for Harder, but do not release until all contract is finalized | According to contract 95% by progress-T/T 30 days-after acceptance; 5% as-built drawing & punch list-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | CHEM |  |  |  |  | 5005 |  | 94143616.47 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 2094129 | 2704016.22 | 4040544.33 |  | 417465.07 | 0 | 1781642.51 |  | 4216462.61 |  | 3064264.82 |  | 3572903.14 |  | 5786891.65 |  | 8297322.7 |  | 11850710.2 |  | 4008521.26 |  | 1601905.82 |  | 4809804.55 |  | 6771650.72 | 0 | 3721362.34 |  | 2554883.36 |  | 3727093.67 |  | 3847670.9 | 0 | 0 | 0 |  | 301793 | 2844224.5 | 2000000 | 4206602.82 | 0 | 2220598.35 |  | 0 | 2535701.9 | 423796 |  | 741655.03 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2108001A | 86000000 | F21P1 UPW | 1273 | C |  | Mechanical works for UPW package | 44427 | 44435 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | UPW | 44461 | Matt |  | Y | 5005 |  | 85961575 | 0.99955 | 38425 | 0 | 38425 | 0 |  | 2466924 | 982645 | 3906729 | 2943825 |  | 2276834 | 4461100 | 450026 | 6877712 |  | 5267057 |  | 2091083 |  | 2215396.33 |  |  | 2511386 | 6073662 |  | 4453731 |  | 4081416 |  | 8156020.16 |  | 4183951.51 | 0 | 2540935 |  | 4203592 |  | 0 | 2367969 | 3457032 |  | 1526847 |  | 2971422 | 0 | 1217312 | 0 | 2315152 |  | 0 | 1635302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 364939 | [6 empty] | 326514 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | LPS | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C009 | USCSB2109003A | 24675557.76 | F21P1 WWT package (Installation and 2 batch tanks) | 1277 | C | -03 | Mechanical/Installation w/Engineering Support | 44443 | 44462 | -3324442.24 | 28000000 |  | V |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | 2/2 contract terminate 7/11 change order (remove equipment rigging scope) 9/2 scope reduction | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Rui Ma | Cherry Chang | WWT | 44515 | Henry |  | Y | 5005 |  | 24675557.76 | 1 | 0 | 0 | 0 | 0 |  |  | 905030 | 521272.65 |  | 276903.42 | 921068.63 | 4146903.13 | 603353.33 |  | 1036753.1 |  |  |  | 1050957.87 | 1402278.28 |  | 1611859.33 | 1847484.66 |  | 102100 | 1675184.02 | 2017484.57 | 6556924.77 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Rosendin | Main Contract Scope | CDS | Chemical | Electrical | M+L | USC21C005 | USCSB2109015A | 17593400.53 | F21P1 Chemical & WCCS package | 1289 | C |  | CDS & WCCS Electrical | 44463 | 44469 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days | York Yeh |  |  | Yi-Hsin Lee | York Yeh | CHEM |  | Henry |  | Y | 5005 |  | 17414347.5 | 0.98982 | 179053.03 | 0 | 179053.03 | 0 | [8 empty] | 149405.43 |  | 683579.07 |  | 683579.07 |  | 683579.07 |  | 138108.51 |  | 285535.39 |  | 683467.33 |  | 784663.64 |  |  | 652556.18 |  |  | 0 | 1035342.01 |  | 1004716.07 |  | 823696.8 | 1286168.86 | 173493.75 |  |  | 1918232.22 |  | 1595328.69 | 0 | 1254380.34 | 0 |  | 0 | 1409135.26 | 0 | 154611.25 | 600482.93 | 197726.22 |  | 354477.45 | 862081.96 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2111007A | 16493658 | F21P1 UPW | 1311 | C | -01 | UPW Electrical work | 2021/11/30 2021/12/17 | 2021/12/2 2021/12/21 | -78210.4 | 16571868.4 | V |  |  |  | Rosendin Electric, Inc. | PR Approved | PO Approved | Price Discount | 95%by progress, net 30days; 5%after final acceptance, net 30days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | UPW | 44568 | Matt |  | Y | 5005 |  | 16493657.94 | 1 | 0.06 | 0 | 0.06 | 210372.96 | [7 empty] | 175540 | 244362 |  | 814522.15 |  | 581188.84 |  | 523223.98 |  | 573781.57 |  | 1221976.93 |  | 1387027.55 |  |  |  | 1016428.81 | 1474307.02 | 1490175.67 |  | 1300288.28 |  | 1067689.7 |  | 585665.41 | 0 | 562607.38 |  | 700988.73 |  | 204131.48 |  | 388556.82 | 0 | 430638.74 | 0 |  | 281851.06 | 0 | 0 | 423015.33 | 0 |  |  | 0 | 158870.07 | 280400.29 |  | 125798.18 |  | 417870.24 |  |  | 300000 | 62751.71 |  |  | 250000 |  |  |  | 100000 |  | 105186.48 |  | - | 0 | 105186.48 | 0
Base-Build | WWT | CCE | Main Contract Scope | WWT | WWT | Electrical | M+L | USC21C009 | USCSB2202002A | 15871093.37 | F21P1 WWT package (Installation and 2 batch tanks) | 1329 | C |  | WWT electrical work | 44599 | 44602 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT (Y) |  |  |  | Y | 5005 |  | 15734929.07 | 0.99142 | 136164.3 | 0 | 136164.3 | 0 | [7 empty] | 1509883 | 993313 |  | 795344 |  | 1704977 |  | 1025087 |  | 1042971 |  | 290381.16 |  | 360140 |  | 2055066.93 |  | 382982 |  | 293847.84 |  | 616577.75 |  | 549609.84 |  | 630151 | 0 |  |  | 1773188.26 |  | 381176 |  | 273929.94 | 0 | 337714.85 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 718588.5 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2303078A | 15748423.99 | F21P1 AMHS Wiring Work Outline | 1815 | C | -01 | AMHS Project Labor - Muratec | 2023/3/21 2024/3/29 | 2023/3/28 2024/4/2 | -3775261.34 | 19523685.33 |  |  |  | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | R1: As per BD team Debby, MICU will decrease the amount of lien, $3,775,261.34, from AMHS Murata labor PO and pay the lien . |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8764942.66 | 0.55656 | 6983481.33 | 1015037.26 | 5968444.07 | 1181131.8 | [28 empty] | 0 |  |  |  |  | 0 |  | 403134.6 | 659384.8 |  | 974866.6 |  | 0 | 1321505.64 | 0 | 0 | 1202146.64 | 0 | 1199144.06 | 1148633.1 | 1483876.4 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 204729.5 |  |  |  | 944905 |  |  |  | 944905.4 | 5947.5 |  |  | 366303.32 |  |  | 1181131.8
Base-Build | Chemical | Southland | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2109009A | 15735376.61 | F21P1 Chemical & WCCS package | 1283 | C | -02 | WCCS Mechanical Work | 2021/9/4 2021/9/24 2022/1/13 | 2021/9/14 2021/9/30 2022/1/18 | 4773066.55 | 10962310.06 | V | V | V |  | Southland Industries | PR Approved | PO Approved | Rev02-Scope change after clarification Rev01-Raw material price increase of Mechanical work | 95% by progress, 5% after acceptance, T/T 30 days | York Yeh |  |  | Yi-Hsin Lee | York Yeh | CHEM | 44482 | Henry |  | Y | 5005 |  | 15735376.61 | 1 | 0 | 0 | 0 | 0 |  |  | 219248 |  |  | 303687.4 |  | 315820 | 176363.06 |  | 38550 |  |  |  | 330017 |  | 76014 |  |  |  | 1151755 |  | 297435 |  | 1238784 |  | 1594990 |  | 1598093 |  |  |  |  | 0 | 1344047 |  | 886899 | 537594 | 2559300 |  | 0 | 1628857.64 | 0 | 0 | 1086956.64 | 0 | 0 | 0 | 251604.22 | 0 |  |  | 0 | 0 | 99361.65 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Southland | Main Contract Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2109005A | 15420592.14 | F21P1 Slurry package | 1279 | C | -01 | Slurry Mechanical Work | 2021/9/4 2022/1/7 | 2021/9/16 2022/1/7 | 702235.1 | 14718357.04 | V | V | V |  | Southland Industries | PR Approved | PO Approved | 標單需求澄清後，報價調整 please provide final quotation. | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang | DDP | 1 year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | Cherry Chang | Slurry | 44482 | Henry | Mechanical Work | Y | 5005 |  | 15420592.14 | 1 | 0 | 0 | 0 | 0 |  |  | 295000 | 98325.7 |  | 166911 |  |  | 356242.29 | [5 empty] | 237492 |  | 44441 |  | 247418 |  | 1056003.31 |  |  |  | 2869640 |  | 995571 |  | 1544044 |  |  |  |  | 0 | 2103594 |  | 504716 | 1256712 | 1370141 |  | 1008145.59 | 0 | 0 | 0 |  | 0 | 0 | 457460.42 | 0 | 210200.32 |  |  | 270090 | 328444.51 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2209004A | 12000000 | F21P1 WWT package (Installation and 2 batch tanks) | 1457 | C |  | PSS-WWT mechanic work scope cut from LPS – Part#1 | 44812 | 44816 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Replace LPS USCSB2109003A-02 deducted Scope | 95% by progress-Net 45 days-after acceptance; 5% after final acceptance-Net 45 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 12000000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 2916925.18 |  | 3179605.05 |  | 4765534.89 |  | 1137934.88 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC | AMHS | Material |  |  | AMHS |  |  | USC23C015 | USCSB2303079A | 10291428.24 | F21P1 AMHS Wiring Work Outline | 1816 | C |  | AMHS Project Material - MURATA BRANCH CIRCUITS | 45006 | 45006 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 10291428.24 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 3878836.8 |  |  |  | 6412591.44 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC24C005 | USCSB2404165A | 9500000 | Chemical & WCCS B Side Project | 4147 | C |  | Proposal TSMC-014 @ Chemical Piping_Side B_L20 CPVC_GN2_PFA_PULL BOX_RELATED SUPPORTS Installations | 45405 | 45416 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 9025000 | 0.95 | 475000 | 4085000 | -3610000 | 1900000 | [54 empty] | 0 |  | 0 | [8 empty] | 3800000 |  |  |  | 3800000 | 4940000 | 1425000 |  | 4085000 | 475000 | 0 | 0
Base-Build | WWT | LPS | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C009 | USCSB2112003A | 8912174.27 | F21P1 WWT package (Installation and 2 batch tanks) | 1315 | C | -02 | WWT Mechanical #2 | 2021/12/10 2022/11/9 | 2021/12/15 2022/11/15 2023/02/02 | -455398.34 | 9367572.61 | v |  |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | 2/2 contract terminate 11/15 sope transfer to PSS | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | WWT |  | Henry |  | Y | 5005 |  | 7748947.02 | 0.86948 | 0 | 0 | 0 | 0 | [5 empty] | 88892.31 | 520927.25 | 431799.72 | 569982.36 |  | 133266.67 |  | 0 |  | 133266.67 | 1543872.33 |  | 776196.52 | 774924.81 |  |  | 2556036.71 | 219781.67 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2301036A | 8858760.4 | F21P1 WWT package (Installation and 2 batch tanks) | 1657 | C |  | PSS - Drain system and piping work #2 | 44944 | 44965 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8858760.4 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 1167159.59 |  | 4907230.06 | 549357.89 | 0 | 2235012.86 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC | EDG | Equipment |  |  | Others |  |  | USC22C003 | USCSB2209014A | 8800000 | TSMC Fab21 Project Phase 1 EDG Package | 1466 | C |  | SUNDT-Generator Fuel and Exhaust Piping | 44819 | 44847 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 95% by progress, 5% after final acceptance, T/T 35 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 8358244.99 | 0.9498 | 441755.01 | 441755.01 | 0 | 0 | [22 empty] | 1271769.47 |  | 1887512.99 |  |  |  | 0 | 1388654.35 |  |  | 2798825.22 | 0 | 711001.5 | [5 empty] | 300481.46 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Southland | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2109008A | 8497604.48 | F21P1 VOC package （Installation ) | 1282 | C | -01 | VOC Mechanical Work | 2021/9/4 2021/9/24 | 2021/9/14 2021/9/30 | 523677.36 | 7973927.12 | V |  |  |  | Southland Industries | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | VOC | 44482 | Martin |  | Y | 5005 |  | 8497604.22 | 1 | 0.26 | 0 | 0.26 | 0 |  |  | 169260 | [11 empty] | 815419 |  |  |  | 216808 |  | 1355044.9 |  | 1638388 |  | 864412 |  | 984866 |  | 271272 |  |  | 1067861 |  | 0 |  |  | 129885 | 343592 | 570874 |  | 69922.32 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | - |  |  | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C025 | USCSB2210047A | 8057264.13 | AMHS TSMC Instrustructure and Branch Circuits | 1529 | C |  | AMHS electric project | 2022/10/26 2023/03/21 | 2022/11/17 2023/03/21 | -10291428.52 | 18348692.65 |  |  |  | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | Separate scope for TSMC and MURATECH; this is for TSMC |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 8057264.13 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 3669738.53 |  | 0 |  | 2704632.5 |  | 425348.38 | 0 | 1257544.72 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C025 | USCSB2304058A | 8052087.54 | AMHS TSMC Instrustructure and Branch Circuits | 1897 | C |  | AMHS Project Labor - TSMC | 2023/4/20 2024/8/8 | 2023/4/24 2024/8/8 | -3790638.71 | 11842726.25 |  |  |  | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | R1: Adjusting the PR amount to close out this PO per David Short. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7924848.54 | 0.9842 | 127239 | 0 | 127239 | 592136.31 | [33 empty] | 277997.7 |  | 871704.6 | 1711059 |  | 1536686.85 |  | 543152.7 | 0 | 980759.6 | 0 |  | 0 | 647971.6 | 301163.86 | 0 | 0 |  |  | 0 | 0 | 0 |  | 127239 |  |  |  |  | 592136.31 | 927113.63 | [6 empty] | 473709.05 |  |  |  | - |  |  | 592136.31
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2304081A | 7997860 | F21P1-0404_H_Hallway plate install_MICU | 1919 | C |  | MMI foundation installation | 45044 | 45048 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5524411.6 | 0.69074 | 2473448.4 | 0 | 2473448.4 | 0 | [32 empty] | 1060892 | 0 | 538680 |  | 1199818 |  | 738364 |  | 654718 | 0 | 347879.6 | 0 |  | 0 | 143520 | 0 | 114940 | 0 |  | 19000 | 26500 | 0 | 0 |  | 0 | [9 empty] | 354250 |  |  |  | 325850 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Greenberry | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2207007A | 7994980 | F21P1 WWT package (Installation and 2 batch tanks) | 1422 | C |  | WWT & TMAH pipe rack | 44748 | 44753 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  | 95% by progress-net 30 days-after acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 7814921.78 | 0.97748 | 180058.22 | 0 | 180058.22 | 156298.4356 | [26 empty] | 402071.73 | 1656165.87 | 2536539.27 |  | 1575043.82 |  |  | 0 | 83847.66 |  | 477611.92 |  | 158546.5 |  | 0 | 0 | 0 | 0 |  | 796552.81 | 0 | 0 | 0 | 0 |  |  | 0 | 128542.2 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 156298.4356
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2311119A | 7800000 | WWT Change Order (Piping) | 2970 | C |  | PSS SW-23-DEC Final prepay | 45258 | 45259 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7800000 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 7800000 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2305003A | 7782795 | F21P1-0404_H_Hallway plate install_MICU | 1927 | C |  | Greenberry Foundation Installation | 45048 | 45050 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4735129.56 | 0.60841 | 3047665.44 | 1096718.63 | 1950946.81 | 0 | [33 empty] | 0 | 532343.19 | [5 empty] | 576705.1 | 1926995.07 | 391389.99 | 0 |  | 0 | 0 | 0 | 3795.91 | 468696.91 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 245021.72 |  |  |  |  | 0 | 314785.73 | 275395.94 | 0 | 0 | 0
Base-Build | WWT | Helix | Main Contract Scope | WWT | WWT | Electrical | M+L | USC24C006 | USCSB2404042A | 7500000 | WWT B side Project | 4037 | C |  | TSMC WWT Electric BOQ for FAB B side Rev3 | 45386 | 45399 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7072405 | 0.94299 | 427595 | 0 | 427595 | 1003092.16 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 714728 |  | 1850785 | 1125000 | 2280623 |  |  | 1125000 | 1423190 |  |  | 1125000 | 803079 | 188079.78 |  | - | 188079.78 | 188079.78 | 250773.04 | 188079.78
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2304066A | 6831432.84 | F21P1-0404_H_Hallway plate install_MICU | 1905 | C |  | PCI Foundation Installation | 45038 | 45051 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3658062.26 | 0.53548 | 3173370.58 | 632010.93 | 2541359.65 | 0 | [33 empty] | 0 |  |  |  | 187742 | 245860.45 |  | 0 | 0 | 0 | 0 | 386468 | 516258 | 0 | 715153 | 221114.15 | 0 |  | 169653.35 | 0 | 0 | 230270.61 |  | 0 |  |  |  | 349498.51 |  | 161796.67 |  |  |  | 52889.1 |  |  |  | 421358.42 | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404072A | 6200000 | Chemical & WCCS B Side Project | 4063 | C | -01 | M4支援F21專案材料/BOX Open PO | 45391 | 2024/4/9 2024/4/23 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | R1: change ship to location to Sky Harbor |  | Yi En Wong | [11 empty] | 233257.79 | 0.037622 | 5966742.21 | 0 | 5966742.21 | 6200000 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 233257.79 | - | 0 | 0 | 6200000
Base-Build | Chemical | MIMO/Rigging | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2202001A | 6153000 | F21P1 Chemical & WCCS package | 1328 | C |  | Rigging for UPW & Chemical Package | 44594 | 44609 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y |  |  |  |  | 5005 |  | 5845350 | 0.95 | 307650 | 0 | 307650 | 0 | [8 empty] | 360800 |  | 295200 |  | 105600 |  |  |  | 194400 |  |  |  | 1505200 |  | 1845900 |  |  |  | 615300 |  | 746825 |  | 176125 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 307650 |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C037 | USCSB2301019A | 6080000 | F21P1 Screen Main tool interconnection | 1641 | C |  | WET Tool Interconnect | 44935 | 44935 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6080000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 6080000 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | 5G | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C010 | USCSB2206022A | 5913533 | F21 P1 LSC CMS and DPM 5G System | 1411 | C |  | F21 P1 LSC CMS and DPM 5G System | 44735 | 44743 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 5913533 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 2736927 |  |  | 0 | [5 empty] | 3176606 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Pipeline | MMI |  |  | Water Line | Mechanical | M+L | USC21C010 | USCSB2110008A | 5655525.57 | tsmc AZ sewer and water pipeline installation | 1297 | C |  | TSMC Frontage Water Main | 44477 | 44490 | 300000 | 5355525.57 |  | V |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | 10/13 專案告知因scope增加故請購異動增加300,000(未成立PO前異動) | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | Cherry Chang |  |  | Rui Ma | Cherry Chang | Y |  | Martin |  | N | 5005 |  | 5655525.57 | 1 | 0 | 0 | 0 | 0 |  |  |  | 1335745.69 | 1354538.74 |  | 1005317.72 | 1215860 | 297604.21 |  | 63682.93 | [9 empty] | 382776.28 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC | EDG | Equipment |  |  | Others |  |  | USC22C003 | USCSB2207016A | 5400000 | TSMC Fab21 Project Phase 1 EDG Package | 1431 | C |  | F21 Electrical Generator installation | 44757 | 44761 | [6 empty] | Delta Diversified Enterprises, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [5 empty] | 5005 |  | 5105559.55 | 0.94547 | 294440.45 | 294440.45 | 0 | 0 | [18 empty] | 327278 |  | 508107 |  | 719764 |  | 462251 |  | 686917.45 |  | 0 | 1100327.05 |  | 604485.95 | 696429.1 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409039A | 5053720 | Tool Interconnection Project (Main Tool & Other Vendors) | 1240 | P |  | KPAE02-S Full Scope | 45554 | 45556 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5053720 | 0 | 5053720 | 0 | [73 empty] | -
Base-Build | WWT | Helix | Main Contract Scope | WWT | WWT | Electrical | Labor | USC23C045 | USCSB2311041A | 4935846 | WWT Change Order (Piping) | 2896 | C |  | F21 P1 FAB A WWT Electrical Engineering (T&M) | 45239 | 45240 | [6 empty] | Okland Construction Company, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4911102.69 | 0.99499 | 24743.31 | 0 | 24743.31 | 49111.0269 | [43 empty] | 0 |  | 0 | 2202659.59 | 0 | 0 | 0 |  |  | 0 | 2217332.83 | 0 |  | 0 |  | 491110.27 |  |  | 246792.3 | [9 empty] | 0 |  | - | 0 | 0 | 0 | 49111.0269
Hookup | Hookup | Material |  |  | Others |  |  | USC22C026 | USCSB2211020A | 4766818.83 | F21P1-0423_H_Unistrut Support Frame_MICU | 1554 | C |  | MISC BOM-3 CLAMPS | 44882 | 44895 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Replace USCSB2210029A |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 4766661.4 | 0.99997 | 157.43 | 0 | 157.43 | 0 | [23 empty] | 176648.56 |  | 1181514.54 | 109093.39 |  | 0 |  | 1596119.92 |  | 1359670.44 | 0 |  |  |  |  | 236118.9 |  | 0 | 0 | 107495.65 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2312175A | 4500000 | F21P1 WWT package (Installation and 2 batch tanks) | 3162 | C | -01 | PSS Dec payment request | 45283 | 2023/12/24 2023/12/25 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | R1: Change Payment Terms to 100% Prepayment by 12/28/2023 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4500000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 4500000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USC2109014A | 4470815 | F21P1 WWT package (Installation and 2 batch tanks) | 16 | P |  | FIRST 22 CS TANKS | 44463 | 44477 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved | 追加WO:USCSB2202007(CS Tank changed order work) | 25 % upon submittal approval, 20% upon material purchase, 50% upon ready to ship, and 5% after delivered 60 days (NET-30 days). | Cherry Chang |  |  | Rui Ma | Cherry Chang | Y | 44482 | Henry |  | N | 5000 |  | 4470815 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 300151.72 | 232324.8 | 232828.66 |  | 313396.54 |  |  | 416886.5 | 739882.6 |  | 548302.62 |  | 826752 |  | 289892.87 |  | 341815.88 |  |  |  | 228580.81 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401135A | 4238904.2 | F21P1-0404_H_labor for 50 tools_MICU | 3320 | C |  | Wire for HK Power trade next 100 tools | 45309 | 45318 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4238222.86 | 0.99984 | 681.34 | 0 | 681.34 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 929060 |  | 679888.8 |  | 477850.4 |  | 655357 |  | 462823.66 |  | 453223 | 0 | 580020 | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2407119A | 4233266.03 | Tool Hookup Material (UPW&Chemical) | 4546 | C |  | TSMC UPW P1B additional materials_2nd | 45492 | 45509 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 152080.19 | 0.035925 | 4081185.84 | 392907.75 | 3688278.09 | [73 empty] | 83848.49 | 68231.7
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USC2109003A | 4120988.48 | F21P1 WWT package (Installation and 2 batch tanks) | 13 | P | -01 | Tank | 2021/9/4 2021/9/17 | 2021/9/13 2021/9/28 | 43208.01 | 4077780.47 | V |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | 44474 | Henry |  | N | 5000 |  | 4120988.4786 | 1 | 0.0014 | 0 | 0.0014 | 0 | [6 empty] | 305045.36 |  | 237956.17 |  | 437432.646 |  | 377511.99 |  | 458362.76 |  |  |  | 789001.51 |  | 320081.8436 |  |  |  | 524527.049 |  |  |  | 330555.71 |  |  |  |  | 0 | 255584.11 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 84929.33 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | VOC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Electrical | M+L | USC21C007 | USCSB2109010A | 4099969.21 | F21P1 VOC package （Installation ) | 1284 | C |  | VOC Electrical & Controls | 44460 | 44490 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | Cherry Chang |  |  | Yi-Hsin Lee | Cherry Chang | VOC | 44494 | Martin |  | Y | 5005 | Y | 4099969.21 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 23400.08 |  | 675199.77 | 536571.24 | 27265.04 |  | 19396.52 |  | 19396.52 |  |  |  |  | 19396.52 | 39468.12 |  | 19396.52 |  | 129064.89 |  | 194482.17 |  | 263346.54 |  | 0 | 210688.68 |  |  | 368774.47 | 0 | 215564.41 |  | 258018.11 |  | 311614.45 |  | 271232.22 | 0 | 170536.5 | 0 |  | 160544.35 | 105931.05 | 29310.45 | 0 | 31370.59 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2309035A | 4038170.94 | WWT Change Order (Piping) | 2512 | C |  | PSS WWT scope for invoice SW-23-0107 and SW-23-0134 | 45177 | 45176 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4038170.94 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 4038170.94 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USC2110005A | 4000000 | F21P1 UPW | 19 | P |  | UPW FRP Tank | 44481 | 44484 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | 取代USC210800A (Augusta Fiberglass Coating,Inc.) | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days) | Cherry Chang | EX-WORK/工廠價 | 1year after the acceptance is completed and transferred to the owner | Chia-Yi Chang | Cherry Chang | N | 44491 | Matt |  | N | 5000 |  | 3999999.9135 | 1 | 0.0865 | 0 | 0.0865 | 0 |  |  |  |  | 412671.45 |  | 232597 |  | 668190.35 |  | 384435.0585 |  | 556676.42 |  | 260321.426 |  |  |  | 567506.31 |  | 79695.219 |  |  |  | 507793.08 |  |  |  | 0 | 258517.22 |  |  |  | 0 | 71596.38 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2310080A | 4000000 | WWT Change Order (Piping) | 2740 | C |  | PSS Per Diem | 45211 | 45211 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3700000 | 0.925 | 0 | 0 | 0 | 0 | [40 empty] | 3700000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 120000 | [9 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Southland | DCR Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2401070A | 4000000 | F21P1 Chemical & WCCS package | 3259 | C |  | MIC and Southland reach agreement to modify contract for F21 A side Southland Scope. | 45303 | 45309 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4000000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 1212933.74 | 1076265.19 | 1710801.07 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2305015A | 4000000 | F21P1 WWT package (Installation and 2 batch tanks) | 1940 | C |  | PSS 11M CO 4/4 batch | 45049 | 45054 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | WWT Package 3 A side: 4.01, 4.16, 4.17 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 4000000 |  |  | 0 | [7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C011 | USCSB2305014A | 4000000 | F21 TMAH System | 1939 | C |  | PSS 11M CO 3/4 batch | 45049 | 45054 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | WWT Package 3 A side-4.02, 4.03, 4.04, 4.06, 4.07, 4.09, 4.10, 4.12, 4.13, 4.15 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 3000000 |  |  | 0 | [6 empty] | 1000000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2205001A | 3804475 | F21P1 UPW | 1365 | C |  | TSMC UPW Common Supports for Area B of FAB Building | 44684 | 44685 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y | [6 empty] | 3690340.75 | 0.97 | 114134.25 | 0 | 114134.25 | 0 | [10 empty] | 45000 |  | 15000 |  | 10000 |  | 192000 |  | 446481 |  |  |  | 1630382.25 |  | 65275 |  | 206790 |  | 295950 |  | 253400 |  | 25975 | 0 |  |  | 333971.75 |  |  |  | 32272.5 | 0 | 52000 | 0 |  | 9453.76 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 76389.49 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2306039A | 3730153.88 | WWT Change Order (Piping) | 2073 | C |  | PSS WWT Project. For invoice SW-23-0065 Final | 45087 | 45090 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3730153.88 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 3730153.88 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC23C054 | USCSB2308003A | 3678899.78 | UPW Change Order | 2307 | C |  | UMEC UPW Change Order #1 | 45139 | 45150 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3062664 | 0.83249 | 616235.78 | 0 | 616235.78 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1231982 |  | 0 | 1830682 | 0 |  | 0 | [8 empty] | 616235.78 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2201005A | 3530956 | F21P1 WWT package (Installation and 2 batch tanks) | 1322 | C | -01 | WWT Platform | 2022/1/18 2022/2/2 | 2022/1/27 2022/2/8 | 689364 | 2841592 | V | V |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | Scope increase with tanks setup and freight | 95% by progress-T/T 30 Days-after acceptance; 5% by final acceptance-T/T 30 Days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y |  |  |  | N | 5005 | Y | 3354408.2 | 0.95 | 176547.8 | 0 | 176547.8 | 167720.41 | [6 empty] | 35000 |  | 35000 |  | 35000 | [11 empty] | 50000 |  | 250000 |  | 310900.4 |  | 895630 |  | 808623.07 |  | 542255.23 | 0 | 391999.5 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 167720.41
Hookup | Hookup | Material |  |  | Others |  |  | USC22C026 | USCSB2210027A | 3521842.92 | F21P1-0423_H_Unistrut Support Frame_MICU | 1510 | C | -01 | MISC BOM-1 STRUCTURE | 44853 | 44858 | -415763.5 | 3937606.42 |  | V |  |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Cannot revise description and cannot add new item, so we can only cancel this PO and get a new one, which is super redundant and a waste of time |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 3521362.18 | 0.99986 | 480.74 | 0 | 480.74 | 0 | [23 empty] | 967990.42 |  | 583071.47 | 843709.61 |  | 0 | 422610.08 | 693994.15 |  |  | 0 | [6 empty] | 0 | 0 | 9986.45 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C008 | USCSB2109016A | 3465068.83 | F21P1 CCTV & Security | 1290 | C | -01 | CCTV Electrical Field Work | 2021/9/25 2023/6/16 | 2021/9/30 2023/6/19 | -1250000 | 4715068.83 |  |  |  |  | BPG Technologies, LLC | PR Approved | PO Approved | Adjusting this PR amount based on PM's request. BPG will be expel from the work recently. | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | CCTV |  | Martin |  | Y | *5005 |  | 3465068.83 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 46952 |  | 15651 |  |  |  | 290381 |  | 127431 |  | 236976 |  |  |  | 321867 |  |  |  | 312234 |  | 712582 |  | 466621 |  | 198124 |  |  | 0 |  |  |  | 736249.83 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408115A | 3313060 | TSMC Fab 21 P1B Tool Hook Up | 4728 | C |  | Wire TCXH for HK Power Trade for 200 tools | 45528 | 45547 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3313060 | 0 | 3313060 | 0 | [73 empty] | -
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2210038A | 3243647.71 | F21P1 WWT package (Installation and 2 batch tanks) | 1520 | C |  | Lab Drainpipe installation | 44854 | 44960 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 3058089.79 | 0.94279 | 185557.92 | 0 | 185557.92 | 0 | [28 empty] | 324364.77 | 2468779.31 |  |  |  | 0 | [6 empty] | 264945.71 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC23C054 | USCSB2308088A | 3202670 | UPW Change Order | 2385 | C |  | UMEC UPW Change Order #2 | 45154 | 45184 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3034614 | 0.94753 | 168056 | 0 | 168056 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1943918 | 0 |  |  | 0 | 0 | 1090696 |  | 0 |  |  |  |  | 168056 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Greenberry | CO Scope (adding/additional scope) | WWT | WWT | Steel | M+L | USC21C009 | USCSB2205022A | 3200000 | F21P1 WWT package (Installation and 2 batch tanks) | 1384 | C | -01 | Tunnel Common Supports | 2022/5/18 2022/6/25 | 2022/5/24 2022/6/27 | 1600000 | 1600000 | V | V | V |  | Greenberry Industrial | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y |  |  |  |  | 5005 |  | 3040000 | 0.95 | 160000 | 0 | 160000 | 152000 | [20 empty] | 2163771.28 |  |  | 876228.72 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 152000
[5 empty] | Others |  |  | USC24C017 | US2SB2410001A | 3150000 | MIC Glendale Warehouse Management | 4 | C |  | Transpak Operational expense Aug-Dec 2024 | 45569 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 3150000 | 0 | 3150000 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2204014A | 3024944.33 | Tool Hookup Material (UPW&Chemical) | 1363 | C | -02 | Tool Hook up Material (UPW & Chemical) | 2022/4/28 2022/6/14 2022/6/28 | 2022/5/2 2022/6/16 2022/7/2 | -148256.15 | 3173200.48 | V | V |  |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | Rev02-6 UPW Part No. Changed Rev01-12 UPW Items changed 原開單專案編號USC21C009 | 100% Arrival(delivery) after shipping-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 3024944.33 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 71135.03 |  | 251959.52 |  | 151600.16 | 307483.19 | 558308.8 | 460127.35 | 52.56 |  | 83940.3 |  | 1687.55 | 428643.66 |  |  | 307970.77 | 40789.6 | 0 | 0 | 0 | 15042.3 | 0 | 224734.52 | 0 | 31713.22 | 0 |  |  | 24252.39 | 0 | 0 |  | 0 | [7 empty] | 65503.41 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Steel | M+L | USC21C003 | USCSB2108004A | 3000000 | F21P1 UPW | 1275 | C |  | tsmc Basement Equipment Mezzanines | 44439 | 44445 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% Progress payment T/T-30Days (After Acceptance); 5% Final payment T/T-30 Days(After Acceptance) | York Yeh |  |  | Yi-Hsin Lee | York Yeh | N |  | Matt |  | N | 5005 |  | 2850000 | 0.95 | 150000 | 0 | 150000 | 0 |  | 50000 | 300000 | 300000 | 300000 |  | 100000 |  | 144186 |  | 144333 |  | 219711 |  | 491417 |  |  |  | 247297 |  | 283000 |  | 221265 | [5 empty] | 48791 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2306031A | 2880222.72 | WWT Change Order (Piping) | 2066 | C |  | PSS WWT Project for invoice SW-23-0086 Final | 45086 | 45090 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2880222.72 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 2880222.72 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C047 | USCSB2306115A | 2834400 | F21P1 HK Seismic Installation | 2148 | C |  | Additional Items for foundation project_MMI | 45101 | 45132 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2204886 | 0.7779 | 629514 | 0 | 629514 | 0 | [33 empty] | 0 | [6 empty] | 0 | 499583 | 0 | 0 |  | 0 | 0 | 1052163 | 376739 | 0 |  |  | 0 | 0 | 276401 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC24C017 | US2SB2409001A | 2793603.82 | MIC Glendale Warehouse Management | 1 | C |  | Transpak Operational Invoice March-July | 45560 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 2793603.82 | 0 | 2793603.82 | 0 | [73 empty] | -
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2111006A | 2780000 | F21P1 Chemical & WCCS package | 1310 | C |  | Cold Storage | 2021/11/19 2023/12/1 | 44524 | [6 empty] | UHO TECHNIQUE & ENGINEERING CO., LTD. | PR Approved | PO Approved | PR R1: Adjusting the PR amount to align with the actual PO; to release the budget for the project per request. 待專案確認FOB港口 | 90% by progress, net 30 days (20% equipment purchased, 20% delivery F.O.B, 50% by site progress) 10% after acceptance, net 30 days | York Yeh | FOB Keelung port | 1year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | York Yeh | CHEM (Y) | 44533 | Henry |  | Y |  |  | 2780000 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 556000 | [13 empty] | 834000 |  | 417000 |  |  |  | 417000 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 278000 | 278000 |  | 278000 | 278000 |  | 0 |  | - | 0 | 0 | 0
Non-TSMC | Heating Jacket | Labor |  |  | Others |  |  | USC23C035 | USCSB2402180A | 2764724.26 | TSMC F21 Heating Jacket Installation | 3609 | C |  | Kinpo heating jacket project | 45342 | 45350 | [6 empty] | Kinpo Co. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1351789.01 | 0.48894 | 1412935.25 | 0 | 1412935.25 | 0 | [52 empty] | 0 | 414708.64 | 0 |  | 0 | [7 empty] | 449793.95 |  | 487286.42 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC24C006 | USCSB2405139A | 2759355 | WWT B side Project | 4163 | C |  | F21 FAB B MU management engineer quotation | 2024/5/23 2024/7/1 | [8 empty] | PR Approved | PO Processing | PR R1:Modify the QTY and price of airline tickets according to purchasing team Oneil. | [13 empty] | 0 | 0 | 2759355 | 0 | 2759355 | 2759355 | [71 empty] | 551871 |  | - | 551871 | 551871 | 551871 | 551871
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC24C005 | USCSB2403295A | 2742000 | Chemical & WCCS B Side Project | 3987 | C |  | Proposal TSMC-011 @ Chemical Piping_Side B_LB1 CPVC_GN2_PFA_RELAY_VMB_PULL BOX Installations | 45381 | 45394 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1782300 | 0.65 | 959700 | 959700 | 0 | 137100 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1645200 | 1782300 |  |  | 548400 |  |  |  | 411300 |  |  |  | - | 137100 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USC2110015A | 2724480 | F21P1 UPW | 20 | P | -01 | UPW FRP PP Lining Tanks | 2021/10/19 2021/11/18 | 2021/10/26 2021/11/22 | 160200 | 2564280 |  | V |  |  | An-Cor Industrial Plastics, Inc. | PR Approved | PO Approved | 新增附屬安全設備 11/22 收到異動會辦(防墜落系統&EXPORY施工) | Based on T&C | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | N | 44529 | Matt |  | N | 5000 |  | 2724480 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 885456 |  | 340560 |  |  | 296759 |  |  |  |  | 170879.5 |  |  |  | 230879.5 |  |  | 70439.75 |  |  |  |  | 0 |  | 295131.75 |  |  | 85439.75 | 170879.5 |  |  | 178055.25 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C006 | USCSB2306032A | 2720533 | F21P1 Slurry package | 2067 | C |  | Liberty scaffolding | 45086 | 45090 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2720533 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 2300000 |  | 420533 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Material | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Material | USC21C013 | USCSB2110004A | 2668000 | F21P1 AMC THC Monitoring System | 1293 | C |  | AMC THC Monitoring System Package Rack & Accessories | 44477 | 44487 | [6 empty] | Weltall Technology Corporation | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Martin |  | ? |  |  | 2401200 | 0.9 | 266800 | 0 | 266800 | 266800 |  |  |  |  | 400200 | [13 empty] | 2001000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 |  | 0 | 266800
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2301037A | 2632901 | F21P1 WWT package (Installation and 2 batch tanks) | 1658 | C |  | F21P1 PSS WWT system #1 | 44944 | 44959 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2632901 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 2632901 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2206017A | 2592117 | Tool Hookup Material (UPW&Chemical) | 1406 | C |  | F21 Hook up PFA 管材 | 44726 | 44736 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  | 100% by progress-T/T 30 Dyas-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 0 | 0 | 2592117 | 0 | 2592117 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2301020A | 2520000 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1642 | C |  | ASML Tool Interconnection | 44935 | 44935 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1040401 | 0.41286 | 1479599 | 0 | 1479599 | 0 | [28 empty] | 0 |  | 1040401 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2303093A | 2500000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1830 | C |  | Glendale Warehouse Office TI | 45010 | 45034 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1742807.08 | 0.69712 | 757192.92 | 0 | 757192.92 | 0 | [33 empty] | 0 | 416473.69 |  | 234316.93 |  | 215063.16 |  | 397639.82 | 0 | 0 | 0 |  | 146315.4 | 3049 | 0 | 215133.54 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 114815.54 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EUV Overhead Crane | Labor |  |  | Others |  |  | USC22C006 | USCSB2205017A | 2500000 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1380 | C |  | TSMC EUV OVERHEAD CRANES in Area A of FAB Building | 44694 | 44697 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 2500000 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 404000 | [5 empty] | 276560 |  | 122250 |  | 134387.5 |  | 153525 |  | 61250 |  | 230080 |  | 381577.5 |  | 420935 |  | 65435 | 0 | 125000 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 125000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Rosendin | DCR Scope | CDS | Chemical | Electrical | M+L | USC24C005 | USCSB2404187A | 2495333.54 | Chemical & WCCS B Side Project | 4167 | C |  | REI Proposed Change order | 45407 | 45408 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 2495333.54 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 2495333.54 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2309036A | 2366258 | WWT Change Order (Piping) | 2513 | C |  | 8-129 WWT LSR FAB-LB2 | 45177 | 45191 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2253922 | 0.95253 | 112336 | 0 | 112336 | 112696.1 | [40 empty] | 0 | 0 | 0 | 0 | 449589 | 0 | 0 | 0 | 1064164 | 442371 |  |  | 78963 | 48000 | 0 |  | 0 |  | 170835 |  |  | 70987.74 |  |  |  | 70987.74 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 112696.1
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2406122A | 2361781.26 | Tool Hookup Material (UPW&Chemical) | 4361 | C |  | TSMC UPW P1B materials_panels | 45468 | 45474 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 317940.25 | 0.13462 | 2043841.01 | 265452.09 | 1778388.92 | 0 | [72 empty] | 88457.94 | 229482.31 |  |  | 0
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC24C007 | USCSB2404049A | 2341425.36 | Low Voltage B Side Project | 4043 | C |  | F21-P1_B-SIDE CCTV & ACCESS (not Include L20 HPM) | 45386 | 45392 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1888238.75 | 0.80645 | 453186.61 | 339661.38 | 113525.23 | 792847.57 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 600319.78 | 351214 | 443009.3 |  |  | 257557 | 283884 |  |  | 257557 |  | 218033 | 221364.29 | 339661.38 | 218033 | 118927.19 | 118927.19 | 118927.19
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C008 | USCSB2110013A | 2272119 | F21P1 CCTV & Security | 1302 | C |  | F21P1 FAB Secruity& CCTV System | 44483 | 44491 | [6 empty] | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Martin |  | ? | 5000 |  | 2021968 | 0.8899 | 250151 | 0 | 250151 | 0 |  |  |  |  | 340818 |  | 77252 | 36354 |  | 454423 |  |  | 454425 |  | 181769 |  | 90884 | [5 empty] | 68183 |  |  |  | 47958 |  | 0 | 86748 |  |  |  | 0 | [5 empty] | 32792 | 0 | 0 | 0 | 0 |  | 0 | 0 | 122303 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 28059 | [6 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC22C025 | USCSB2302016A | 2253000 | AMHS TSMC Instrustructure and Branch Circuits | 1697 | C |  | AMHS Power Panel Construction | 44965 | 44965 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved | To replace Main Electric USCSB2208008A (should be canceled) |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2019000 | 0.89614 | 234000 | 0 | 234000 | 0 | [28 empty] | 0 |  | 606000 |  |  | 0 |  |  | 393470 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 1019530 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Exterior Pad | Material | Main Contract Scope | WWT | WWT | Civil | M+L | USC22C011 | USCSB2207015A | 2223500 | WRC Exterior Pads - NH3 and Diesel System | 1430 | C |  | WRC Exterior Pads - NH3 and Diesel System | 44755 | 44761 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 2112178 | 0.94993 | 111322 | 0 | 111322 | 0 | [22 empty] | 79500 |  | 2032678 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409021A | 2210375.61 | Tool Interconnection Project (Main Tool & Other Vendors) | 1224 | P |  | KIHIB2: EXHAUST, SIGNAL & POWER CABLE INSTALL | 45546 | 45551 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2210375.61 | 0 | 2210375.61 | 0 | [73 empty] | -
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2311092A | 2200000 | WWT Change Order (Piping) | 2943 | C |  | PSS SW-23-NOV Final prepay | 45248 | 45249 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2200000 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 2200000 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC24C005 | USCSB2404164A | 2200000 | Chemical & WCCS B Side Project | 4146 | C |  | Proposal TSMC-013 @ Chemical Piping_Side B_L30 CPVC_GN2_PFA_PULL BOX_RELATED SUPPORTS Installations | 45405 | 45416 | -100000 | 2300000 | V |  |  |  | CRG International | PR Approved | PO Approved | [14 empty] | 1034000 | 0.47 | 1166000 | 0 | 1166000 | 880000 | [54 empty] | 0 |  | 0 | [8 empty] | 660000 |  |  | 1034000 | 660000 |  | 770000 |  | - | 110000 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC24C005 | USCSB2404074A | 2152918.88 | Chemical & WCCS B Side Project | 4065 | C |  | Invoice No. MICU-009(021824-31624 T&M) | 45391 | 45407 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | 0 | [11 empty] | 2152918.88 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | 2152918.88 | 2152918.88 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USC2210016A | 2150304 | F21P1 WWT package (Installation and 2 batch tanks) | 258 | P |  | WRC Chem Room Epoxy/Installation of FRP Membrane | 44854 | 44855 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 2150304 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 645091.2 |  |  |  | 884205.13 |  |  |  | 114059.18 |  | 506948.49 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Helix | Main Contract Scope | WWT | WWT | Electrical | M+L | USC24C006 | USCSB2404112A | 2050000 | WWT B side Project | 4097 | C |  | TSMC WWT Electric BOQ for FAB B side Rev3 - part 2 | 45397 | 45400 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved | [14 empty] | 1176567 | 0.57394 | 873433 | 508459 | 364974 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 307500 |  |  |  | 307500 |  |  |  | 307500 | 668108 | 0 |  | 508459 | 0 | 0 | 0 | 0
Base-Build | WWT | LPS | Main Contract Scope | WWT | WWT | Steel | Material | USC21C009 | USCSB2111003A | 2000000 | F21P1 WWT package (Installation and 2 batch tanks) | 1307 | C | -01 | WWT Pipe Rack | 2021/11/9 2022/5/21 | 2021/11/15 2022/5/24 | -6500000 | 8500000 | V |  |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | 更換廠商(因LPS下包無法出工) | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | 44524 | Henry |  | N | 5005 |  | 2000000 | 1 | 0 | 0 | 0 | 0 |  |  |  | 1700000 |  |  |  |  | 0 |  |  |  |  | 300000 | [14 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | M+L | USC21C005 | USC2208005A | 2000000 | F21P1 Chemical & WCCS package | 206 | P |  | Scaffold | 44779 | 44783 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved | USCSB2205005A Extension order | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 2000000 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 2000000 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | MMI | The budget execution does not pertain to this project | Pipeline | WWT | Civil | M+L | USC21C003 | USCSB2109001A | 2000000 | F21P1 UPW | 1276 | C |  | tsmc 43rd Ave Sewer Line Extension | 44440 | 44445 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | UPW(N) |  | Matt |  | Y | 5005 |  | 2000000 | 1 | 0 | 0 | 0 | 0 |  | 300000 | 1315157.69 | 384842.31 | [24 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C006 | USCSB2305013A | 2000000 | F21P1 Slurry package | 1938 | C |  | PSS 11M CO 2/4 batch | 45049 | 45054 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Package 3 A side-4.08, 4.11, 4.14 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 2000000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2205005A | 2000000 | F21P1 UPW | 1369 | C |  | Scaffold for F21 MEP Scaffold work | 44686 | 44691 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 1999976 | 0.99999 | 24 | 0 | 24 | 0 | [13 empty] | 285972 |  | 1384578 | 85380 |  | 244046 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Barcode | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C012 | USCSB2307096A | 1950462 | F21 Barcode RFID System | 2262 | C |  | F21 P1 Barcode system Engineering | 45128 | 45138 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1576220.76 | 0.80813 | 374241.24 | 0 | 374241.24 | 273064.67 | [38 empty] | 116113.76 |  | 1040099 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 420008 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 97523.1 | 97523.1 | 78018.47
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2201010A | 1950339.22 | F21P1 WWT package (Installation and 2 batch tanks) | 1327 | C |  | WWT Housekeeping Pad | 44592 | 44601 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N | 5005 |  | 1950339.22 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 682618.73 | [6 empty] | 156027.14 |  |  |  | 103367.98 | 865622.23 |  |  | 26819.63 |  | 18144 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 97739.51 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2310146A | 1917083 | WWT Change Order (Piping) | 2802 | C |  | WWT-LSRi-uncompleted lines | 45223 | 45225 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1734669 | 0.90485 | 182414 | 0 | 182414 | 173466.9 | [42 empty] | 0 | 0 |  | 0 | 0 | 443041 | 453152 | 254062 |  |  | 268826 | 162319 | 0 |  | 0 |  | 28057 |  | 125212 | 95854.15 |  |  |  | 95854.15 |  |  |  | 57512.49 |  | 0 |  | - | 0 | 0 | 0 | 173466.9
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C045 | USCSB2401067A | 1914858 | WWT Change Order (Piping) | 3256 | C |  | J.T. Thorpe Aug invoice | 45302 | 45307 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1914858 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 1914858 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2206019A | 1909676.1 | F21P1 WWT package (Installation and 2 batch tanks) | 1408 | C |  | PP materials d225 and d180 | 44728 | 44733 | 329504.4 | 1580171.7 | V |  |  |  | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved | 實際需求數量變更, 貿易條件從EXW改FCA | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1909676.1 | 1 | 0 | 0 | 0 | 0 | [15 empty] | 1909676.1 | [12 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | MIMO/Rigging | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2207017A | 1890000 | F21P1 WWT package (Installation and 2 batch tanks) | 1432 | C |  | WWT rigging and equipment move in | 44758 | 44761 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 1890000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 378000 |  | 378000 |  | 378000 |  | 378000 |  | 283500 |  | 94500 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C006 | USCSB2307115A | 1876313.76 | F21P1 Slurry package | 2279 | C |  | Liberty March invoice and April invoice | 45133 | 45134 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | Will be covered in the GC of TSMC's PO |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1876313.76 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 1876313.76 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | M+L | USC23C045 | USCSB2309168A | 1839196.6 | WWT Change Order (Piping) | 2637 | C |  | F21 P1 A site Access Control, ACS Panel interconnection | 45197 | 45203 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1745473.34 | 0.94904 | 93723.26 | 0 | 93723.26 | 175765.81 | [40 empty] | 0 | 0 | 251160 | 0 |  | 0 | 0 | 1064932.07 | 347338.72 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 18392 | [9 empty] | 0 |  | 82042.55 | 36783.93 | 36783.93 | 10238.12 | 91959.83
Base-Build | Triazole | Material | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC22C022 | USCSB2210043A | 1794999.84 | F21P1 Triazole treatment system | 1525 | C |  | MU-Triazole System | 44859 | 44861 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | MICU joint project with MU Taiwan, TSMC bargained the project altogether directly with both parties |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 784435.72 | 0.43701 | 1010564.12 | 0 | 1010564.12 | 439284.0032 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 455035.72 |  |  |  | 329400 | [6 empty] | 94132.2864 |  | - | 94132.2864 | 94132.2864 | 78443.572 | 78443.572
Base-Build | WWT | LPS | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2206016A | 1756177.47 | F21P1 WWT package (Installation and 2 batch tanks) | 1405 | C |  | WWT add BOM on March | 44725 | 44727 | [6 empty] | Lasco Process Systems, LLC. | PR Approved | PO Approved | USCSB2109003A Change order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [5 empty] | 5005 |  | 1352739.95 | 0.77028 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 351235.49 |  | 306760.62 |  | 688372.16 | 6371.68 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USC2109002A | 1733380.86 | F21P1 WWT package （USA EQ-FRP tank) | 12 | P |  | tank,FRP | 44441 | 44449 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | 44491 | Henry |  | N | 5000 |  | 1733380.512 | 1 | 0.348 | 0 | 0.348 | 0 |  |  |  |  | 185254.72 |  | 18468.9 |  | 258067.11 |  | 189095.6655 |  | 215557.25 |  | 35447.54 |  |  |  | 442551.84 |  | 137921.28 |  |  |  | 55868.3865 |  |  |  | 0 | 156894.82 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 38253 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2404047A | 1714688.63 | F21P1 AMHS Wiring Work Outline | 4041 | C |  | Pay the lien outsourcing company_Hart Land | 45386 | 45387 | [6 empty] | Hart Land Resources, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1714688.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 |  | 0 | 537427.29 | 537427.29 |  |  | 400000 | 400000 |  |  |  | 400000 |  |  |  | 377261.34 |  |  |  |  | - | 0 |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312098A | 1696396.84 | F21P1-0404_H_labor for 50 tools_MICU | 3089 | C |  | urgent wire request for Third top 100 tools. USCSB2311090 Replacement | 45275 | 45278 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1696396.84 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 173654.65 | 345091.74 |  | 499534.28 | 31017.5 | 380800.48 | 266298.19 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C001 | USCSB2205008A | 1670175 | F21 P1 Office and WH Security and CCTV | 1372 | C | -02 | CCTV Office Design and equipment | 2022/5/10 2023/8/15 | 2022/5/11 2023/8/15 2023/9/ 9 | -730573 | 2400748 | V |  |  | V | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved | Swap the balance to Aegis USA because of 30% withholding tax issue | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N | [6 empty] | 1670175 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 480150 |  | 144045 |  | 144045 |  | 72023 |  | 120036 |  |  |  | 504140 |  |  |  | 108912 |  | 0 | 96824 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2306112A | 1660117 | F21P1 UPW | 2145 | C |  | UMEC-2022 week 60 hour rate difference | 45100 | 45131 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1256301 | 0.75675 | 403816 | 0 | 403816 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 1256301 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Rosendin | DCR Scope | CDS | Chemical | Electrical | M+L | USC21C006 | USCSB2401227A | 1658637 | F21P1 Slurry package | 3409 | C |  | REI CDS CO | 45317 | 45331 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1658637 | 1 | 0 | 1658637 | -1658637 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 1658637 | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2308089A | 1649670.58 | WWT Change Order (Piping) | 2386 | C |  | PSS WWT Project. For invoice SW-23-0131 Final | 45154 | 45154 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1649670.58 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 1000000 | 649670.58 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2205024A | 1633000 | F21P1 WWT package (Installation and 2 batch tanks) | 1386 | C | -01 | WWT FRP tanks | 2022/5/19 2022/6/15 | 2022/5/23 2022/6/16 | -437000 | 2070000 |  |  |  |  | Shanghai Mega Union Environmental Technology Co., LTD | PR Approved | PO Approved | 取消7個桶槽 | 25% Prepayment-T/T 30 days; 70% by shipment-after acceptance-t/t 30 days; 5% after final acceptance-t/t 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1551350 | 0.95 | 81650 | 0 | 81650 | 77567.5 | [9 empty] | 408250 | [6 empty] | 387021 |  |  | 756079 | [8 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 77567.5
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC21C005 | USCSB2402133A | 1610000 | F21P1 Chemical & WCCS package | 3570 | C |  | CDS L20 Monitoring piping and cable engineering | 45336 | 45352 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1529500 | 0.95 | 80500 | 0 | 80500 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 1288000 | 1449000 | 241500 |  |  | 80500 |  |  |  | 80500 |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409052A | 1600000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1254 | P |  | KEPSL7 INTERNAL CONNECT HOOK UP | 45560 | 45561 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1600000 | 0 | 1600000 | 0 | [73 empty] | -
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C045 | USCSB2312108A | 1590281.5 | WWT Change Order (Piping) | 3098 | C |  | JT Thorpe Sep Invoice | 45276 | 45279 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1590281.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 1590281.5 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC23C054 | USCSB2312092A | 1554463 | UPW Change Order | 3083 | C |  | UPW-UMEC-extend GC 2023-Sep to Nov | 45274 | 45282 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1476470 | 0.94983 | 77993 | 0 | 77993 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 1476470 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Barcode | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C012 | USCSB2110012A | 1550000 | F21 Barcode RFID System | 1301 | C |  | F21P1 Barcode & RFID System | 44482 | 44491 | [6 empty] | Ying Pao Technology Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | N | 44502 | Martin |  | ? |  |  | 1017474.56 | 0.65644 | 532525.44 | 0 | 532525.44 | 155000 | [8 empty] | 109781.26 | [9 empty] | 555701.81 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 109130.1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 238700 | 242861.39 | [10 empty] | - |  |  | 77500 | 77500
Base-Build | Base-Build | Scaffolding |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC22C024 | USCSB2210018A | 1500000 | UIS Scaffolding | 1501 | C |  | Liberty Industrial Group Scaffold | 44845 | 44851 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | Open PO | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 1490921.08 | 0.99395 | 9078.92 | 0 | 9078.92 | 0 | [26 empty] | 1490921.08 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2301021A | 1500000 | F21P1 Chemical & WCCS package | 1643 | C |  | PDP panel | 44936 | 44945 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1500000 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 686057 | 0 |  |  |  | 813943 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Civil | M+L | USC21C003 | USCSB2111008A | 1495365.57 | F21P1 UPW | 1312 | C | -01 | UPW civil work (Housekeeping Pad) | 2021/11/30 2021/12/21 | 2021/12/15 2021/12/29 | -224391.43 | 1719757 | V |  |  |  | Degan Construction LLC | PR Approved | PO Approved | 批量議價 | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | York Yeh |  |  | Yi-Hsin Lee | York Yeh | N |  | Matt / Martin |  | N | 5005 |  | 1493744.85 | 0.99892 | 1620.72 | 0 | 1620.72 | 0 |  |  |  |  | 299073.11 |  |  | 299073.11 | [6 empty] | 312531.4 |  |  |  | 235077.29 | 347989.94 | [8 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2301012A | 1492567.83 | F21P1 Chemical & WCCS package | 1635 | C |  | TW Supporting Piping Materials | 44932 | 44960 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 1492567.83 | 0 | 1492567.83 | 1492567.83 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 1492567.83
Base-Build | General Condition | Other Scope |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C010 | USC2408011A | 1484981.27 | General Conditions B Side Project | 1177 | P |  | 15-HPM L30 V Line 及FAB L10 L LINE配合氣化課拆庫板 (MICU) | 45513 | 45524 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved | [14 empty] | 1484981.27 | 1 | 0 | 484981.27 | -484981.27 | [71 empty] | 1000000 |  |  | 484981.27
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2405159A | 1476607.74 | Tool Hookup Material (UPW&Chemical) | 4187 | C |  | TSMC Hookup UPW P1B materials_non panels | 45441 | 45446 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 682780.26 | 0.4624 | 793827.48 | 312914.29 | 480913.19 | 0 | [66 empty] | 298795.29 |  | 100776.38 |  |  |  | 269619.48 | 13589.11 |  |  | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410033A | 1448000 | Tool Hook Up E2 Trade Equipment Rental | 4976 | C |  | HK YAHO Equipment rental End date 08/31/2024 | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1448000 | 0 | 1448000 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2205023A | 1442704.28 | F21P1 Chemical & WCCS package | 1385 | C |  | CDS T-box | 44699 | 44704 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  | 20% upon received material and approved submittal-Net 45 days; 60% due on delivery with evidence-net 45 days; 20% by received and after acceptance-net 45 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 1442704.28 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 288540.86 |  |  |  | 66179.35 |  | 181354.29 |  | 182599.74 |  | 157941.7 |  | 153670.67 |  | 147796.07 |  | 0 |  |  |  |  | 0 | [5 empty] | 61871.76 | 0 | 0 | 202749.84 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC24C005 | USCSB2403294A | 1435672.3 | Chemical & WCCS B Side Project | 3986 | C |  | TSMC F21 P1 CDS/SDS B side Support | 45381 | 45385 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1435672.3 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 165020.39 |  | 257358.71 |  |  | 941509.59 | 939470.74 |  | 73822.46 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Helix | Main Contract Scope | WWT | WWT | Electrical | Labor | USC23C045 | USCSB2309165A | 1427459.08 | WWT Change Order (Piping) | 2634 | C |  | WWT Support_HELIX | 45196 | 45217 | [6 empty] | Okland Construction Company, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1398534.33 | 0.97974 | 28924.75 | 0 | 28924.75 | 27970.6866 | [40 empty] | 0 | 0 | 0 | 0 |  | 1398534.33 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 27970.6866
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | M+L | USC24C005 | USCSB2405096A | 1420000 | Chemical & WCCS B Side Project | 4116 | C |  | DFK Tech F21P1- POWER-B Machine panel power connection Bid No. Item Content Material Designated Vendor Model/Specific-Urgent | 45428 | 45458 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 710000 | 0.5 | 710000 | 0 | 710000 | 450000 | [56 empty] | 0 | [8 empty] | 300000 |  |  |  | 750000 | 710000 | 375000 |  | - |  | 75000 | 0
Base-Build | UPW | MIMO/Rigging | Main Contract Scope | UPW | UPW | Mechanical | Labor | USC21C005 | USCSB2304016A | 1400000 | F21P1 Chemical & WCCS package | 1857 | C |  | Additional Rigging work in the Phase A for UPW scope | 45023 | 45030 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | This change order is corresponding to USCSB2202001A |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1400000 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 1000000 | 0 | 400000 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Helix | Main Contract Scope | WWT | WWT | Electrical | Labor | USC21C009 | USCSB2402053A | 1400000 | F21P1 WWT package (Installation and 2 batch tanks) | 3495 | C |  | WWT-Helix-A side 1/15 + 15 in March (partial 1.4M) | 45329 | 45335 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1399921.49 | 0.99994 | 78.51 | 0 | 78.51 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 756650.49 |  | 643271 |  |  |  |  | 210000 |  |  |  | 210000 |  |  |  | 210000 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | W-H2SO4 | Trident | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C014 | USCSB2207020A | 1375375 | F21P1 WH2SO4 | 1435 | C | -01 | W-H2SO4 Mechanical Work | 2022/7/23 2022/11/4 | 2022/7/26 2022/11/9 | -44703 | 1420078 |  | V |  |  | Trident Mechanical Services | PR Approved | PO Approved | Trident cannot catch up PFA lead time, so we use our own-purchased PFA (we prepruchase more in M4 order) and cancelled PFA in Trident's double containment | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong | [11 empty] | 1375375 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 167139 | [9 empty] | 587927 |  | 227074 |  | 225416 |  | 153511 |  |  | 14308 | [12 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | CCTV | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C001 | USCSB2203001A | 1367378.8 | F21 P1 Office and WH Security and CCTV | 1336 | C | -01 | Office Building Security & CCTV Electrical Work | 2022/3/1 2023/12/27 | 2022/3/3 2023/12/29 | -1422569.88 | 2789948.68 |  |  |  | V | Norstan Communications, Inc.dba Black Box Network Services | PR Approved | PO Approved | R1: As per Paul:the vendor has exited, and the account is settled. | 95% by progress-after acceptance-net 40 days; 5% after final acceptance-net 40 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [5 empty] | 5005 |  | 1367378.8 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 811269.29 |  |  |  | 556109.51 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207003A | 1359840 | F21P1 UPW | 183 | P |  | ESD Jumpsuit With Hood, Sticky Mat, Nitrile Disposable Glove & Face Mask, ESD Safety Shoe… | 44764 | 44768 | [6 empty] | Super Starnix SDN BHD | PR Approved | PO Approved |  | 15% Prepayment; 85% after cargo received-Net 30 days-After acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 1359840 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 203976 | [11 empty] | 214965 |  | 59500 | 12876.65 |  |  |  | 437099.75 | 18600 |  | 177272.6 |  |  |  | 0 | 209525 | 0 | 26025 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | LPS | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2205021A | 1337939.49 | F21P1 WWT package (Installation and 2 batch tanks) | 1383 | C |  | Simona PVDF material for WWT | 44698 | 44706 | [6 empty] | Lasco Process Systems, LLC. | PR Approved | PO Approved | USCSB2109003A change order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1321837.89 | 0.98797 | 16101.6 | 0 | 16101.6 | 0 | [12 empty] | 267587.9 |  |  |  |  | 869338.1 | 177296.59 |  |  | 7615.3 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C045 | USCSB2310180A | 1317346 | WWT Change Order (Piping) | 2832 | C |  | Liberty July invoice | 45227 | 45233 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1317346 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 1317346 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C045 | USCSB2309173A | 1316565.5 | WWT Change Order (Piping) | 2642 | C |  | Liberty June Invoice | 45197 | 45203 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1316565.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1316565.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2211027A | 1305645.46 | F21 TMAH System | 1560 | C |  | F21P1 TMAH | 44884 | 44886 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 580012.96 | 0.44423 | 725632.5 | 0 | 725632.5 | 324807.2576 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 119512.96 |  | 150000 | [7 empty] | 310500 |  |  |  |  | 69601.5552 |  | - | 69601.5552 | 69601.5552 | 58001.296 | 58001.296
Hookup | Warehouse | Outsourcing |  |  | Others |  |  | USC22C008 | USCSB2303047A | 1300000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1789 | C |  | Tool Hookup staffing needs | 44999 | 45000 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1092823.97 | 0.84063 | 207176.03 | 0 | 207176.03 | 0 | [28 empty] | 0 |  |  |  | 13031.89 | 47105.98 | 24314.19 | 147319.76 | 184293.85 |  | 147186.03 |  | 0 | 0 | 0 | 0 |  | 529572.27 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | 0 | 0 | Chemical | Electrical | Labor | USC22C010 | USCSB2304077A | 1299998.2 | F21 P1 LSC CMS and DPM 5G System | 1915 | C | -01 | F21P1 Slurry A Electrical/Controls | 2023/4/27 2024/5/14 | 2023/6/5 2024/5/14 | -1.8 | 1300000 | V |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | Finalized and closing order |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1299998.2 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 500032.12 | 0 |  |  | 294000 |  | 357504.98 |  | 0 | 0 | 148461.1 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC24C005 | USCSB2404073A | 1291338.73 | Chemical & WCCS B Side Project | 4064 | C |  | Invoice No. MICU-008(1/28/24-2/17/24 T&M) | 45391 | 45406 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | 0 | [11 empty] | 1291338.73 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1291338.73 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Southland | The budget execution does not pertain to this project | VOC | Low Voltage | Mechanical | M+L | USC23C054 | USCSB2308075A | 1290937.49 | UPW Change Order | 2373 | C | -01 | F21 P1 VOC Extended General Conditions | 2023/8/15 2023/11/6 | 2023/9/13 2023/11/6 | 110904.49 | 1180033 |  |  |  |  | Southland Industries | PR Approved | PO Approved | R1: Adjusting the amount for extended GC according to PM's request. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1290937.49 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 865303 | 0 | 104910 | 104910 | 0 | 104910 |  |  | 110904.49 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C008 | USCSB2306140A | 1288488.34 | F21P1 CCTV & Security | 2173 | C |  | F21 P1 CCTV FAB Camera, Conduit, Cabling and Panel Installation | 45107 | 45117 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1288488.34 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 216945.1 | 72644 |  | 998899.24 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC23C054 | USCSB2402115A | 1282154.51 | UPW Change Order | 3553 | C |  | PCO 79 Price Adjustment for Incentive Weekend OT and Swing Shift | 45335 | 45345 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 988872.66 | 0.77126 | 293281.85 | 15036.99 | 278244.86 | 64107.73 | [49 empty] | 0 |  |  | 0 | 0 | 0 | 178460.28 | 178460.28 |  |  |  |  | 333360.17 | 230846.38 |  |  | 384646.35 | 439885.42 |  |  | 256430.9 | 124643.59 | 64107.73 |  | 15036.99 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2403275A | 1281921.72 | WWT B side Project | 3968 | C |  | B side MU FAB/HPM LB2 Main Drain | 45380 | 45387 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 1281921.72 | 1025537 | 256384.72 | 1281921.72 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 256384.344 |  | - | 256384.344 | 256384.344 | 256384.344 | 256384.344
Hookup | Hookup | Material |  |  | Others |  |  | USC22C026 | USCSB2309187A | 1272328.2 | F21P1-0423_H_Unistrut Support Frame_MICU | 2655 | C |  | New batch of rack use | 45198 | 45212 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1272229.2 | 0.99992 | 99 | 198 | -99 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 84639.2 | 0 |  | 74993.95 | 780040 | 326616.05 | 0 |  | 5940 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC24C005 | USCSB2404008A | 1260000 | Chemical & WCCS B Side Project | 4004 | C |  | 18 Tanks Quote for Fab 21 | 45384 | 45387 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1197000 | 0.95 | 63000 | 0 | 63000 | 63000 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1197000 |  |  | 1008000 | [6 empty] | 63000 | 189000 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USC2111063A | 1251211.84 | F21P1 WWT package (Installation and 2 batch tanks) | 64 | P | -01 | Supply Tank | 44525 | 44531 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved | remark修改 | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days) | York Yeh |  |  | Rui Ma | York Yeh | N | 44553 | Henry |  | N | 5000 |  | 1242913.35 | 0.99337 | 8298.49 | 0 | 8298.49 | 12429.1335 | [18 empty] | 558632.7 |  | 223233.27 |  |  | 360135.6 |  |  |  |  | 76669.03 |  |  | 24242.75 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 12429.1335
Base-Build | Chemical | Rosendin | DCR Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2402209A | 1249493.14 | F21P1 Chemical & WCCS package | 3636 | C |  | CDS REI CO 70/CO 73/CO 79/CO 86 | 45344 | 45353 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 62474.66 | 0.05 | 1187018.48 | 1187018.48 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 62474.66 | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2205004A | 1247244.64 | F21P1 Slurry package | 1368 | C |  | 台積電(美國)F21P1防火填塞工程 | 44686 | 44692 | [6 empty] | Kinpo Co. | PR Approved | PO Approved |  | 30% Prepayment-Net 30 days; 28% by progress to Kinpo Taiwan-after acceptance-net 30 days; 42% by progress to Kinpo USA-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y | [6 empty] | 374173 | 0.3 | 873071.64 | 0 | 873071.64 | 62362.23 | [11 empty] | 374173 | [16 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 374173.39 |  |  |  | 436535.62 |  | 0 |  | - | 0 | 0 | 62362.23
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403182A | 1240156.97 | F21P1 WWT package (Installation and 2 batch tanks) | 3879 | C | -01 | B side MU FAB/HPM+Drain material | 2024/3/19 2024/3/28 | 2024/3/19 2024/4/1 | -1300840.72 | 2540997.69 |  |  |  | V | Mega Union Technology Inc. | PR Approved | PO Approved | R1: Change to seperate labor and material for 30% witholing tax |  | Yi En Wong | [11 empty] | 0 | 0 | 1240156.97 | 0 | 1240156.97 | 1240156.97 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 186023.5455 |  |  |  | 186023.5455 |  |  |  | 186023.5455 |  | 248031.394 |  | - | 248031.394 | 248031.394 | 248031.394 | 248031.394
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C047 | USCSB2404017A | 1222937 | F21P1 HK Seismic Installation | 4013 | C |  | Hookup seismic installation | 45384 | 45385 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1170427 | 0.95706 | 52510 | 9879 | 42631 | 0 | [52 empty] | 0 | 669280 | 0 |  | 0 | [5 empty] | 417576 |  |  |  | 66572 |  |  |  | 7120 | 0 |  | 9879 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409015A | 1220000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1219 | P |  | Dry Etch P1B Delta Wye Lump Sum Contract | 45542 | 45548 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1220000 | 22652.2 | 1197347.8 | 0 | [73 empty] | -
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2303046A | 1192357 | F21P1 UPW | 1788 | C |  | GF material raise | 44996 | 45029 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1072152 | 0.89919 | 120205 | 0 | 120205 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 1072152 | [6 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409042A | 1191034.88 | Tool Interconnection Project (Main Tool & Other Vendors) | 1245 | P |  | P1B_KCANN4_CVD2_N/20.5_LAM | 45555 | 45559 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1191034.88 | 0 | 1191034.88 | 0 | [73 empty] | -
Others | AMHS |  |  |  | AMHS |  |  | USC22C025 | USCSB2409022A | 1187418.35 | AMHS TSMC Instrustructure and Branch Circuits | 4790 | C |  | AMHS TSMC Infrastructure Main Tray | 45540 | 45548 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1187418.35 | 1187418.35 | 0 | 0 | [73 empty] | -
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2406100A | 1180902.8 | F21P1 AMHS Power Panel | 4335 | C |  | AMHS 25K Feet Channel Tray CO | 45463 | 45468 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 1180902.8 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 1180902.8 | [8 empty] | - |  |  | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2312037A | 1178171.5 | WWT Change Order (Piping) | 3030 | C |  | WWT_Manpower support _MEGA | 45267 | 45273 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 588647.14 | 0.49963 | 589524.36 | 0 | 589524.36 | 1178171.5 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 176725.725 |  |  |  | 176725.725 |  |  | 588647.14 | 176725.725 |  | 235634.3 |  | - | 235634.3 | 235634.3 | 235634.3 | 235634.3
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401142A | 1169995.9 | F21P1-0404_H_labor for 50 tools_MICU | 3327 | C |  | Steel core material Flex for HK Power trade | 45310 | 45315 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1169995.9 | 1 | 0 | 11409.85 | -11409.85 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 526430.82 |  | 290940.33 |  | 159870.66 |  | 134971.38 | [5 empty] | 46372.9 |  |  |  |  | 0 |  | 11409.81 | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2403291A | 1150254.2 | F21P1 AMHS Wiring Work Outline | 3983 | C |  | Pay the lien outsourcing company | 45381 | 45383 | [6 empty] | Finish Line Staffing, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1150254.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 698217.4 | 0 | 363285 | 88751.8 | 88751.8 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | GF Agru Material | Material |  |  | WWT | Mechanical | Material | USC22C023 | USCSB2210025A | 1129032.26 | AZ GF Agru Material | 1508 | C |  | GF PP&PVDF Material Li Jie | 44848 | 44851 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved |  | 100% by shipping-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1129032.26 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 1129032.26 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2212029A | 1104701 | F21P1 WWT package (Installation and 2 batch tanks) | 1602 | C |  | Clamps Lorry – L10-20-30 | 44911 | 44916 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 899102.27 | 0.81389 | 0 | 0 | 0 | 0 | [26 empty] | 843029.89 |  | 56072.38 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 55235.05 |  |  |  | 55235.05 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2402190A | 1103574.8 | F21P1 Chemical & WCCS package | 3619 | C |  | CDS T&M work Jan 2024 | 45343 | 45371 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1103574.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 1103574.8 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2402222A | 1096382.54 | WWT Change Order (Piping) | 3649 | C |  | WWT Stripper insulation | 45344 | 45351 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1096382.54 | 1 | 0 | 0 | 0 | 265365.3384 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 164457.381 | 449771.76 |  |  | 164457.381 |  |  |  | 164457.381 | 646610.78 | 53972.6112 |  | - | 53972.6112 | 53972.6112 | 53972.6112 | 49474.8936
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2205011A | 1089600 | F21P1 WWT package (Installation and 2 batch tanks) | 1375 | C |  | Outsourcing Foreman | 44692 | 44692 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1089600 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 28971.72 | 57454.65 |  | 157433.05 | 85602.27 | 24722.38 | 2912 | 138322.64 |  | 26247.22 | 103463 |  |  |  | 294956.76 |  | 169514.31 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Steel | M+L | USC21C003 | USCSB2110016A | 1085250 | F21P1 UPW | 1305 | C |  | UPW common Rack | 44488 | 44495 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y | 44501 | Matt / Martin |  | N | 5005 |  | 1085250 | 1 | 0 | 0 | 0 | 0 |  |  |  | 40000 | 150000 |  | 100000 |  | 30000 |  | 66800 | [5 empty] | 45500 |  | 368771 |  |  |  | 80259 |  | 100335 |  |  |  | 49322.5 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 54262.5 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2109012A | 1060000 | F21P1 Chemical & WCCS package | 1286 | C |  | Chemical Storage Design, PE Stamp and onsite Work | 44460 | 44463 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by Progress-T/T 30 days, 5% after final acceptance - T/T 30 days | Cherry Chang |  |  | Rui Ma | Cherry Chang | Y | 44468 | Henry |  | N | 5005 |  | 1060000 | 1 | 0 | 0 | 0 | 0 |  | 30000 |  | 30000 | 30000 |  | 30000 |  | 135000 | [7 empty] | 72500 |  | 265834 |  | 240819 |  | 120829 | [5 empty] | 0 |  |  |  | 50233 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 54785 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Frontage Line Hydrant | Material |  |  | Water Line | Civil | M+L | USC22C018 | USCSB2209026A | 1045000 | US Fab Frontage line hydrants | 1478 | C |  | TSMC Hydrant Proposal | 44827 | 44836 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-After acceptance; 5% after final completion-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1045000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 88267.12 | [5 empty] | 474750 |  | 81600 |  | 61850 |  |  |  |  | 0 | 338532.88 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC23C045 | USCSB2312128A | 1037689.53 | WWT Change Order (Piping) | 3118 | C |  | CGS outsourcing manpower | 45277 | 45278 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1037689.53 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 1037689.53 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC24C005 | USCSB2404021A | 1037400 | Chemical & WCCS B Side Project | 4017 | C |  | F21 Bside 耘起(耘程)塑材人力 | 45384 | 45385 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 570900 | 0.55032 | 466500 | 194700 | 271800 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 345800 |  |  |  | 345800 | 376200 |  |  | 345800 | 194700 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2312063A | 1036853 | WWT Change Order (Piping) | 3055 | C |  | WWT - Install L30 Drains | 2023/12/9 2024/3/6 | 2024/1/3 2024/3/6 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | Amount revised to settle actual work completed and release excess budget |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 985010.35 | 0.95 | 51842.65 | 0 | 51842.65 | 194539.575 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 98475.1 |  | 0 | 0 | 305273.95 |  | 265883.15 |  | 39575.1 |  |  | 155527.95 |  |  |  | 155527.95 | 68951 |  |  | 155527.95 |  | 38907.915 | 206852.05 | - | 38907.915 | 38907.915 | 38907.915 | 38907.915
[5 empty] | Others |  |  | USC22C025 | USCSB2409111A | 1030141.91 | Tool Hookup Material (UPW&Chemical) | 4930 | C |  | AMHS TSMC First 23 DPs CCE Scope | 45562 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1030141.91 | 0 | 1030141.91 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2312001A | 1017869.91 | Tool Hookup Material (UPW&Chemical) | 2996 | C | -01 | HK Chemical PVDF and PP Materials_aditional request | 45261 | 2023/12/6 2023/12/15 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | PO R1:remark revised based on Supplier feedback and confirm with Legal |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1016451.49 | 0.99861 | 1418.42 | 0 | 1418.42 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 34310.72 | 478990.91 | 0 |  | 42132.52 |  | 64472.16 |  | 3448.97 |  |  |  | 226776.16 |  | 154998.96 |  |  |  |  | 0 | 11321.09 | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C031 | USCSB2407081A | 1016740.97 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4497 | C |  | MMI B Side Seismic Project | 45488 | 45495 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 299875.03 | 0.29494 | 716865.94 | 299875.03 | 416990.91 | 0 | [73 empty] | 299875.03 |  |  | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2310028A | 1012845 | WWT Change Order (Piping) | 2691 | C |  | WWT -LB2-Lab drain | 45204 | 45212 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 962923 | 0.95071 | 49922 | 0 | 49922 | 48146.15 | [40 empty] | 0 | 0 | 0 | 0 | 324110 | 0 | 0 | 0 | 520838 | 66599 |  |  | 51376 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 48146.15
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C013 | USCSB2401149A | 1000982.17 | F21P1 QR Lab Security & CCTV | 3334 | C |  | F21 AUX and FAB CCTV, Access control and ACS system | 45310 | 45316 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 950933.06 | 0.95 | 50049.11 | 82042.55 | -31993.44 | 50049.11 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 872868.31 | 0 |  | 0 | [13 empty] | 78064.75 | 15014.73 |  | - | 15014.73 | 15014.73 | 5004.92
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C004 | USCSB2305012A | 1000000 | F21P1 WWT package （USA EQ-FRP tank) | 1937 | C |  | PSS 11M CO 1/4 batch | 45049 | 45054 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Lorry Support Installation (14.1) & Lorry Pipe Material+Installation (14.2) & Mobilization (18.2) & RFI additional material (18.3) |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 1000000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USC2201005A | 1000000 | F21P1 Slurry package | 99 | P |  | Sleeve,PFA,1"(PFA tube, Pipe Label) | 44575 | 44588 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | tsmc F21P1 MIC 設備費用 | 100% by progress, T/T 45 days, after acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | N | [6 empty] | 0 | 0 | 1000000 | 0 | 1000000 | 1000000 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 1000000
Base-Build | Base-Build | Scaffolding | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | M+L | USC21C005 | USC2303002A | 1000000 | F21P1 Chemical & WCCS package | 268 | P |  | Scaffolding | 44993 | 44999 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 1000000 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | MIMO/Rigging | Main Contract Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2304017A | 1000000 | F21P1 Slurry package | 1858 | C |  | Additional Rigging work in the Phase A for Chemical scope | 45023 | 45030 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | This change order is corresponding to USCSB2202001A |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 1000000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USC2402117A | 1000000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 827 | P |  | TransPak February partial operation fee | 45351 | 45352 | [6 empty] | Transpak, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [50 empty] | 1000000 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2306002A | 1000000 | F21P1 AMAT Interconnection | 2037 | C |  | AMAT Interconnect Labor | 45079 | 45090 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 27565.48 |  | 66715.84 | 0 | 48837.72 | 0 | 57263.36 | 0 | 0 | 137864.49 | 0 | 107659.6 | 63752.78 |  | 0 | 0 | 197357.59 |  | 292983.14 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Material | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Material | USC21C013 | USCSB2110005A | 1000000 | F21P1 AMC THC Monitoring System | 1294 | C | -01 | AMC THC Monitoring System Package Host Equipment | 44477 | 2021/10/18 2021/10/20 | [6 empty] | Weltall Technology Corporation | PR Approved | PO Approved | 修正貿易條款，原CIF to LAX修改為DDP on site. | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Martin |  | ? |  |  | 900000 | 0.9 | 100000 | 0 | 100000 | 100000 |  |  |  |  | 150000 | [13 empty] | 750000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 |  | 0 | 100000
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Labor | USC24C008 | USCSB2404033A | 1000000 | UPW B Side Project | 4029 | C |  | REI UPW PCO 083 Contract Pricing Adjustment Phase 3, R0 | 45385 | 45394 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 500000 | [8 empty] | 500000 | 0 | 500000 | - | 0 | 0 | 0
Base-Build | WWT | Helix | Main Contract Scope | WWT | WWT | Electrical | Labor | USC21C009 | USCSB2401146A | 1000000 | F21P1 WWT package (Installation and 2 batch tanks) | 3331 | C |  | WWT-Helix-A side 1/15 + 15 in March (partial 1M) | 45310 | 45310 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 975025 | 0 | 24975 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USC2210013A | 1000000 | F21P1 WWT package (Installation and 2 batch tanks) | 256 | P |  | CM Services | 44841 | 44845 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 518549.47 | 0.51855 | 481450.53 | 0 | 481450.53 | 0 | [18 empty] | 244960.27 |  | 52417 |  |  |  | 51594 |  | 64422 |  | 0 |  |  |  | 11058 | 0 |  |  | 8242 | 17767.4 | 8242 |  | 9438 | 0 | 16484 | 0 |  | 0 | 8481.2 | 0 | 9737 | 9737 |  | 5969.6 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2308016A | 991453.5 | F21P1-0404_H_labor for 50 tools_MICU | 2318 | C |  | CED cable for Hand Tool | 45141 | 45174 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 991453.48 | 1 | 0.02 | 0 | 0.02 | 0 | [38 empty] | 436214.59 |  | 0 | 237260.87 | 0 | 0 |  | 0 | 253153.09 | 0 | 0 | 0 |  |  | 0 | 64824.93 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C003 | USCSB2204003A | 987756 | F21P1 UPW | 1353 | C |  | Activated Carbon | 44655 | 44662 | [6 empty] | Calgon Carbon Corporation | PR Approved | PO Approved |  | 90% by shipment-net 60 days-after acceptance; 10% final acceptance-net 60 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 987756 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 661340.68 | [6 empty] | 239279.04 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 87136.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | CCE | DCR Scope | WWT | WWT | Electrical | M+L | USC23C054 | USCSB2308124A | 986866.74 | UPW Change Order | 2421 | C |  | F21 P1 WWT Electric Engineering-CCE | 45160 | 45168 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 986866.74 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 986866.74 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC21C006 | USCSB2401219A | 972000 | F21P1 Slurry package | 3401 | C |  | CDS Lorry A 18 Tank | 45317 | 45320 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 923400 | 0.95 | 48600 | 0 | 48600 | 48600 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 777600 |  | 0 |  |  |  |  | 145800 | 145800 | [8 empty] | 48600 |  | - | 0 | 0 | 0
Non-TSMC | FMCS | Material |  |  | Others |  |  | USC22C007 | USCSB2205028A | 970000 | TSMC F21 FMCS Installation | 1390 | C |  | TSMC F21 FMCS Installation | 44707 | 44708 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  | 90% by progress-after acceptance-net 30 days; 10% after final acceptance-net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [5 empty] | 5005 |  | 952462.29 | 0.98192 | 17537.71 | 0 | 17537.71 | 0 | [19 empty] | 137016.94 |  |  |  | 55484.1 | 62126.6 |  | 81800.85 |  | 0 |  |  |  | 293817.5 | 0 | 107801.4 |  |  |  | 88836 |  | 0 | 0 | 39369.8 | 0 |  | 0 | 0 | 0 | 0 | 0 | 32363.1 |  | 0 | 0 | 27826 |  | 0 |  | 26020 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC24C005 | USCSB2404038A | 966500 | Chemical & WCCS B Side Project | 4033 | C | -01 | F21 B side 弘東人力 | 2024/4/3 NA 2024/8/2 | 2024/4/5 2024/4/23 2024/8/7 | -10000 | 976500 | V |  |  |  | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved | R1: Detailed scope added in remark (6) R2: As per Johnny Wan to update the price. |  | Yi En Wong | [11 empty] | 679000 | 0.70253 | 287500 | 161900 | 125600 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 325500 |  |  |  | 325500 |  |  | 177600 | 325500 | 177600 | 0 | 161900 | 161900 | 0 | 0 | 0
Base-Build | WWT | Greenberry | DCR Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2402004A | 962482 | F21P1 WWT package (Installation and 2 batch tanks) | 3447 | C |  | MIC-004-22 X1-Line Cable Tray Supports | 45323 | 45337 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 962482 | 1 | 0 | 0 | 0 | 962482 | [48 empty] | 0 | 0 |  |  | 0 |  | 0 |  | 0 |  |  |  |  | 48124.1 |  |  |  | 144372.3 |  |  | 962482 | 144372.3 |  | 192496.4 |  | - | 192496.4 | 192496.4 | 192496.4 | 192496.4
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C004 | USCSB2205020A | 960814.29 | F21P1 WWT package （USA EQ-FRP tank) | 1382 | C |  | WWT Hopper and Piping Header | 44697 | 44700 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  | 95% by shipment-Net 30 days-after acceptance, 5% after function tested-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 960814.29 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 713320 | [12 empty] | 24000 | 0 | 59994.29 |  |  | 163500 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2408094A | 956570.48 | F21P1 AMAT Interconnection | 4707 | C |  | AMAT interconnect manager fee for 22 machines | 45526 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 956570.48 | 0 | 956570.48 | 0 | [73 empty] | -
Others | AMHS |  |  |  | AMHS |  |  | USC22C025 | USCSB2408080A | 952044.09 | AMHS TSMC Instrustructure and Branch Circuits | 4696 | C |  | AMHS TSMC Labor 9 Distribution Panels | 45520 | 45527 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 952044.09 | 952044.09 | 0 | 0 | [73 empty] | -
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2403122A | 950000 | F21P1 UPW | 3824 | C |  | PCO 82 Contract Pricing Adjustment, Continuation of Work Phase 2, Revision 0(batch 1/2) | 45364 | 45365 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 950000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 500000 |  |  |  | 450000 |  |  | 500000 |  |  |  | 450000 |  | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2306098A | 931858 | F21P1 UPW | 2131 | C |  | UMEC-2022 Sep to Dec incentive | 45098 | 45107 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 931858 | 0 | 931858 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C001 | USCSB2303073A | 927440.77 | F21 P1 Office and WH Security and CCTV | 1811 | C |  | Security & CCTV Electrical Work | 45002 | 45009 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | Replace Galaxy3 USCSB2202003A |  | Yi En Wong |  |  |  | Yi En Wong | Y | [6 empty] | 927440.77 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 110620 | 349396.94 |  | 425210 | 0 |  | 42213.83 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | CCE | DCR Scope | WWT | WWT | Electrical | Material | USC21C009 | USCSB2211012A | 916925 | F21P1 WWT package (Installation and 2 batch tanks) | 1547 | C |  | CCE Redesign Change Order | 44874 | 44875 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | USCSB2202002A Change Order |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 916925 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 183385 |  | 687693.75 |  | 45846.25 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2403290A | 910318.51 | F21P1 AMHS Wiring Work Outline | 3982 | C |  | Pay the lien outsourcing company | 45381 | 45383 | [6 empty] | X3 Tradesmen Arizona LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 910318.51 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 563282.6 | 0 | 298215 | 48820.91 | 48820.91 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | CCE | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | M+L | USC21C008 | USCSB2301035A | 900000 | F21P1 CCTV & Security | 1656 | C |  | F21P1 Office Secruity CCTV System | 44944 | 44948 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 715880 | 0.79542 | 184120 | 0 | 184120 | 0 | [26 empty] | 540000 |  | 0 |  | 175880 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C005 | USCSB2307079A | 900000 | F21P1 Chemical & WCCS package | 2245 | C |  | Tool Hookup Design/Base Build Design/System/Safety | 45126 | 45132 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 900000 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 840331.81 |  |  | 59668.19 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Rosendin | DCR Scope | CDS | Chemical | Electrical | M+L | USC21C006 | USCSB2308094A | 898441.26 | F21P1 Slurry package | 2391 | C |  | CDS 2” Conduit in Lorry change order | 45155 | 45168 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 898441.26 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 898441.26 | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C005 | USC2301005A | 896185 | F21P1 Chemical & WCCS package | 264 | P |  | Kelly Outsourcing | 44943 | 44958 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 882540.55 | 0.98477 | 13644.45 | 0 | 13644.45 | 0 | [28 empty] | 286159.06 |  | 472960.48 |  | 123421.01 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USC2301004A | 896185 | F21P1 WWT package (Installation and 2 batch tanks) | 263 | P |  | Kelly Outsourcing | 44943 | 44958 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 896185 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 462989.74 |  | 304510.25 |  | 128685.01 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Labor | Main Contract Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2109007A | 892286.55 | F21P1 Slurry package | 1281 | C | -05 | Slurry Electrical | 2021/9/4 2021/12/14 2022/6/15 2023/5/17 2023/4/19 | 2021/9/14 2021/12/20 2022/6/17 2023/4/26 2023/5/19 2023/11/23 | -210232.36 | 1102518.91 |  | V |  | V | Climatec, LLC | PR Approved | PO Approved | PO R5:According to PM indication:Closing out Climatec from the project per request. Scope Changed after reviewing rev02-6/17 scope changed (material raised up ) from 2467383 to 2485140.6 rev03-4/26 cancelling climatatec rev04-5/19 adjust PR amount to issue the same work scope to Hua Yi | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Slurry (Y) |  | Henry |  | Y | 5005 |  | 892286.55 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 892286.55 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC24C008 | USCSB2404135A | 889529 | UPW B Side Project | 4119 | C |  | UPW-UMEC-extend GC for 2024 Jan - Feb | 45399 | 45451 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 845053 | 0.95 | 44476 | 0 | 44476 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 845053 |  |  | 444764.5 |  | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2402068A | 888462 | F21P1 AMHS Wiring Work Outline | 3510 | C |  | Sinfonia Electrical Technical Support | 45330 | 45336 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 444231 | 0.5 | 444231 | 0 | 444231 | 0 | [49 empty] | 0 |  |  | 444231 | 0 | 0 |  | 0 | [16 empty] | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2203007A | 880212 | F21P1 WWT package (Installation and 2 batch tanks) | 1342 | C |  | Tanks freight | 44625 | 44631 | 103498 | 776714 | V |  | V |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Vendor recounts tank amounts for delivery | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N |  |  | 880212 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 845517 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 34695 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | AMC THC | CCE | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C013 | USCSB2204004A | 867959.59 | F21P1 AMC THC Monitoring System | 1354 | C | -01 | AMC/THC electric and low voltage | 2022/4/6 2023/6/20 | 2022/4/25 2023/6/26 | -900000 | 1767959.59 |  |  |  | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | Per user's instruction to cancel CCE's AMC/THC scope | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [5 empty] | 5005 | Y | 853014.89 | 0.98278 | 14944.7 | 0 | 14944.7 | 0 | [10 empty] | 137809 |  | 128830.61 | [5 empty] | 193245.91 | [5 empty] | 91192.7 |  |  |  | 0 |  | 176144.15 |  |  | 0 | [6 empty] | 125792.52 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2302032A | 867838.53 | Tool Hookup Material (UPW&Chemical) | 1713 | C |  | Tool Hookup Material (UPW 20k) | 44971 | 44979 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 867838.53 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 82927.31 | 5775.33 | 29251.83 | 247721.9 |  | 45116.28 |  | 160759.44 |  |  | 226750.52 | 0 | 1819.57 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 67716.35 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2207010A | 860400 | F21P1 Slurry package | 1425 | C |  | Engineering Design Assistance and Engineer of Record Services | 44749 | 44750 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 848120 | 0.98573 | 12280 | 0 | 12280 | 0 | [14 empty] | 129060 |  | 250000 |  | 200000 |  | 229060 |  | 40000 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC24C006 | USCSB2404163A | 859100 | WWT B side Project | 4145 | C |  | Megaunion 元富 B side 8m 1 scope + 210 header +120 all | 45402 | 45408 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 859100 | 0 | 859100 | 859100 | [54 empty] | 0 |  | 0 | [14 empty] | 171820 |  | - | 171820 | 171820 | 171820 | 171820
Base-Build | UPW |  |  |  | UPW | Mechanical | M+L | USC24C008 | USCSB2407069A | 856637 | UPW B Side Project | 4487 | C |  | UMEC GC for 2024 March & April | 45486 | 45492 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 813805 | 0.95 | 42832 | 0 | 42832 | 0 | [68 empty] | 813805 |  |  |  |  | - |  |  | 0
Base-Build | Base-Build | Scaffolding |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC22C024 | USCSB2308140A | 851774.5 | UIS Scaffolding | 2435 | C |  | Liberty May 04 | 45161 | 45163 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 851774.5 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 851774.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC24C017 | US2SB2409002A | 850000 | MIC Glendale Warehouse Management | 2 | C |  | Transpak Intrastate Transportation from August to December 2024 | 45562 | 45657 | [6 empty] | Transpak, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 850000 | 0 | 850000 | 0 | [73 empty] | -
Base-Build | Base-Build | Housekeeping | Main Contract Scope | CDS | Chemical | Mechanical | Housekeeping | USC21C005 | USCSB2306043A | 850000 | F21P1 Chemical & WCCS package | 2077 | C |  | Supervisor, safety, and housekeeping manpower | 45090 | 45098 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 850000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 719303.93 |  |  | 127128.9 |  |  | 0 | 0 | 3567.17 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | 5G | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C010 | USCSB2312135A | 848096 | F21 P1 LSC CMS and DPM 5G System | 3124 | C |  | F21 CMS & DPM IMP Engineering | 45279 | 45280 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 356100.65 | 0.41988 | 491995.35 | 48785.29 | 443210.06 | 424048 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 95890.36 | 53906 | 0 |  | 0 |  | 110350.9 |  |  | 169620 | 47168.1 |  |  | 42405 | [5 empty] | 84809.6 |  | 48785.29 | 84809.6 | 84809.6 | 84809.6 | 84809.6
Others | AMHS |  |  |  | AMHS |  |  | USC22C025 | USCSB2409026A | 842251.77 | AMHS TSMC Instrustructure and Branch Circuits | 4794 | C |  | AMHS TSMC Labor Next 6 Distribution Panels | 45540 | 45554 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 842251.77 | 0 | 842251.77 | 0 | [73 empty] | -
Base-Build | Base-Build | Equipment | Main Contract Scope | CDS | Chemical | Civil | Housekeeping | USC21C005 | USCSB2205003A | 842152.03 | F21P1 Chemical & WCCS package | 1367 | C |  | CDS/WCCS/SDS/WWT/UPW/VOC/THC/Cold storage housekeeping pad & Dike | 44686 | 44706 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 842152.03 | 1 | 0 | 0 | 0 | 0 | [19 empty] | 100078.6 |  |  | 292963.56 |  | 70353.34 |  | 44291.42 |  | 0 |  | 103859.68 |  | 33165.82 | 0 |  |  |  | 197439.61 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2206021A | 831105 | F21P1 UPW | 1410 | C |  | F21P1 Laboratory scope | 44731 | 44733 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 0 | 0 | 831105 | 0 | 831105 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USCSB2312144A | 830000 | F21P1 Slurry package | 3133 | C |  | CDS MICU Equipment-1 | 45279 | 45280 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 830000 | 0 | 830000 | 830000 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 830000
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309178A | 825000 | WWT Change Order (Piping) | 2647 | C |  | WWT -MU Train A rest material | 45198 | 45202 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 825000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 53997.2 | 36417.6 | 0 | 0 | 116698.7 | 0 |  | 249072.5 | 368814 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2206018A | 818469.26 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1407 | C |  | Pallet Storage System | 44727 | 44729 | [6 empty] | Toyotalift of Arizona, Inc. | PR Approved | PO Approved |  | 30% upfront on material cost; Remaining 40% by shipment-Net 30 days-after acceptance; Remaining balance due-net 30 days-after final acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [5 empty] | 5005 |  | 803346.37 | 0.98152 | 15122.89 | 0 | 15122.89 | 0 | [10 empty] | 211524.98 | [5 empty] | 327387.6 | 264433.79 | [10 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MIMO/Rigging | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2304018A | 800000 | F21 TMAH System | 1859 | C |  | Additional Rigging work in the Phase A for WWT scope | 45023 | 45030 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | This change order is corresponding to USCSB2202001A |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 800000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 200000 |  | 600000 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | GF Agru Material | Material |  |  | WWT | Mechanical | Material | USC22C023 | USCSB2211015A | 774105 | AZ GF Agru Material | 1549 | C |  | AZ GF Material Summary Table | 44876 | 44881 | [6 empty] | SWIFT ENGINEERING CO., LTD. | PR Approved | PO Approved | TSMC Nego already |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 774105 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 774105 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Steel | M+L | USC21C003 | USCSB2112005A | 769545 | F21P1 UPW | 1317 | C |  | UPW A-G pipe rack | 2021/12/15 2021/12/22 | 44558 | 374850 | 394695 |  | V |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | added scope | 95% by Progress, T/T30 days 5%after final acceptance,T/T 30 days | Cherry Chang |  |  | Yi-Hsin Lee | Cherry Chang | N | 44573 | Matt / Martin |  | N | 5005 |  | 769545 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 50000 |  | 30000 |  | 25000 |  | 116000 |  | 115793 |  | 401667 | [5 empty] | 31085 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC24C006 | USCSB2404005A | 769450 | WWT B side Project | 4002 | C |  | (A side)YAHO T&M A side work from 11/2023-05/2024 | 45384 | 45385 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 757316.67 | 0.98423 | 12133.33 | 0 | 12133.33 | 136953.5 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 595450 |  |  | 115417.5 |  |  |  | 115417.5 |  |  |  | 115417.5 | 161866.67 | 29772.5 |  | - | 29772.5 | 29772.5 | 29772.5 | 17863.5
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2408018A | 761216 | F21P1 AMAT Interconnection | 4614 | C |  | NUUO for AMAT P1B 17 machines | 45507 | 45521 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 761216 | 0 | 761216 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | MIMO/Rigging | Main Contract Scope | WWT | WWT | Electrical | Labor | USC21C009 | USCSB2210026A | 761100 | F21P1 WWT package (Installation and 2 batch tanks) | 1509 | C |  | WWT-Panel Move-In and installation | 44848 | 44852 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [6 empty] | Y | 641145 | 0.84239 | 119955 | 0 | 119955 | 102583.2 | [20 empty] | 188800 |  | 41300 |  | 7945 |  | 120980 |  | 0 |  |  |  |  | 0 |  |  | 64900 |  |  |  | 143232.5 | 0 | 0 | 0 | 73987.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 38055 |  |  |  | 22833 |  |  |  | 22833 |  | 32057.25 |  | - | 32057.25 | 19234.35 | 19234.35 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2405084A | 749607.1 | F21P1 AMAT Interconnection | 4104 | C |  | Brycon April usage | 45426 | 45447 | [6 empty] | Brycon Corporation | PR Approved | PO Approved | [14 empty] | 732191.1 | 0.97677 | 17416 | 10248.16 | 7167.84 | 0 | [56 empty] | 0 | [9 empty] | 582390.54 |  |  |  | 139552.4 |  | 10248.16 | - |  |  | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Steel | M+L | USC21C003 | USCSB2201002A | 744188 | F21P1 UPW | 1319 | C |  | UPW blue, purple ,yellow area pipe rack | 44574 | 44578 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days | Yi En Wong | DDP | 1 year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | Yi En Wong | Y | 44581 | Martin | Steel Work | N | 5005 |  | 744188 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 30000 |  | 90000 |  | 192000 |  | 112720 |  |  |  | 88381.04 |  | 80033.86 |  | 104866.6 |  | 8977.1 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 37209.4 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | M+L | USC21C005 | USCSB2306078A | 735000 | F21P1 Chemical & WCCS package | 2111 | C | -01 | Mezzanines Fireproof Coating #1 & #2 | 45094 | 2023/7/3 2023/7/22 | [6 empty] | Alpha Insulation and Waterproofing, Inc | PR Approved | PO Approved | R1:contract name change |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 735000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 403676.42 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 294573.58 |  | 0 | 0 | 0 |  | 0 |  |  |  | 36750 |  |  |  |  | 36750 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | CO Scope (adding/additional scope) | WWT | WWT | Civil | M+L | USC21C009 | USCSB2312115A | 735000 | F21P1 WWT package (Installation and 2 batch tanks) | 3105 | C |  | INTUMESCENT FIREPROOFING mezz 1 and 2 Fab LB2 (release of second half) | 45276 | 45279 | [6 empty] | Alpha Insulation and Waterproofing, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 661500.04 | 0.9 | 73499.96 | 0 | 73499.96 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 283664.97 | 0 | 0 | 0 |  | 0 |  |  |  | 148722.26 | [7 empty] | 163652 |  |  | 0 | 65460.81 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2309156A | 732452.27 | WWT Change Order (Piping) | 2627 | C |  | WWT-settle cost for AIG | 45195 | 45197 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 732452.27 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 732452.27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C001 | USCSB2308125A | 730573 | F21 P1 Office and WH Security and CCTV | 2422 | C |  | F21P1 OFFICE Security and CCTV System | 45160 | 45163 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved | Change order for USCSB2205008A because of withholding tax |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 304794 | 0.4172 | 425779 | 0 | 425779 | 0 | [39 empty] | 244171 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 60623 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2206002A | 721645 | F21P1 UPW | 1394 | C |  | TOC Analyzer and portable | 44714 | 44719 | [6 empty] | Veolia WTS Analytical Instruments, Inc. | PR Approved | PO Approved |  | 100% by shipment-net 30 days-after accpetance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | Y | [6 empty] | 707497.95 | 0.9804 | 14147.05 | 0 | 14147.05 | 0 | [16 empty] | 294406.35 |  |  |  | 377349.6 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 13844 | 0 | 14986 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 6912 | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2402182A | 717845.48 | F21P1 UPW | 3611 | C |  | UPW Continuation of Work Phase 1 | 45343 | 45346 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 717845.48 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | 717845.48 | 717845.48 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C001 | USCSB2401152A | 709832.25 | F21 P1 Office and WH Security and CCTV | 3337 | C |  | F21 AUX and FAB CCTV, Access control and ACS system 1st portion | 45310 | 2024/1/25 2024/8/6 | -290194.42 | 1000026.67 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PO R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 709832.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 632333.61 |  | 0 |  |  |  |  | 90803 | 77498.64 |  |  | 50002 |  |  |  | 50002 |  |  |  | - |  |  | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2403105A | 707171.3 | F21P1 WWT package (Installation and 2 batch tanks) | 3807 | C |  | [B side][Manpower-MU] 元富/宇翔/柯達/3months | 45360 | 45364 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 0 | 0 | 707171.3 | 0 | 707171.3 | 707171.3 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 106075.695 |  |  |  | 106075.695 |  |  |  | 106075.695 |  | 141434.26 |  | - | 141434.26 | 141434.26 | 141434.26 | 141434.26
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Labor | USC23C054 | USCSB2308077A | 705000 | UPW Change Order | 2374 | C | -01 | F21 P1 UPW/CDS Change Order | 45153 | 2023/8/30 2024/2/23 | -295000 | 1000000 |  |  |  |  | Rosendin Electric, Inc. | PR Approved | PO Approved | PO R1 :As per PM:Kate Wu,adjusting the PR amount to align with the actual PO; to release the budget for the project per request. |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards | [7 empty] | 705000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 705000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Trailer | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2108003A | 700000 | F21P1 UPW | 1274 | C |  | Modular Site Office | 44433 | 44441 | [6 empty] | Design Modulars Inc. | PR Approved | PO Approved |  | 80% upon delivery and completion of DMI’s scope of work.Net 30 days 20% upon final occupancy and inspection final.Net 30 days | Cherry Chang |  |  | Yi-Hsin Lee | Cherry Chang | N | 44456 | Matt |  | N | 5005 |  | 700000 | 1 | 0 | 0 | 0 | 0 | [5 empty] | 560000 |  | 140000 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC24C005 | USCSB2405041A | 700000 | Chemical & WCCS B Side Project | 4050 | C |  | F21 B side L20/L10 UPW 工程發包_MornstAir | 45420 | 45425 | [6 empty] | MornstAir Inc. | PR Approved | PO Approved | [14 empty] | 665000 | 0.95 | 35000 | 167400 | -132400 | 35000 | [56 empty] | 0 | [8 empty] | 350000 |  |  |  | 315000 |  |  | 497600 | 167400 | 35000 |  | 0
Base-Build | Triazole | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC22C022 | USCSB2306096A | 686619 | F21P1 Triazole treatment system | 2129 | C |  | WWT Triazole | 45098 | 45108 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 686619 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 102993 |  | 137324 | 0 | 68662 | 0 | 0 |  | 0 | 82394 | 0 | 0 | 0 |  |  | 89260 | 171655 | 0 |  | 0 |  | 34331 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | General Condition | Outsourcing |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC23C022 | USCSB2311122A | 676020 | F21P1_H_2D/3D drawing | 2973 | C |  | Kelly Outsourcing manpower | 45259 | 45266 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 676020 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 | 676020 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | M+L | USC23C054 | USCSB2308087A | 670874.78 | UPW Change Order | 2384 | C |  | F21 Warehouse CCTV over time and CO | 45154 | 45163 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 660865.38 | 0.98508 | 10009.4 | 0 | 10009.4 | 6708.75 | [38 empty] | 26262 |  | 0 | 0 | 477987.13 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 156616.25 |  | 0 | [14 empty] | 0 |  | - |  | 0 | 0 | 6708.75
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2207011A | 670653 | F21P1 WWT package (Installation and 2 batch tanks) | 1426 | C |  | d225 drain pipe materials | 44750 | 44753 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 670653 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 670653 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2212025A | 665277.46 | F21P1 WWT package (Installation and 2 batch tanks) | 1598 | C |  | WWT Lab drain pipe materials | 44909 | 44916 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 665277.46 | 664482.58 | 794.88 | 665277.46 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 99791.619 |  |  |  | 99791.619 |  |  |  | 99791.619 |  | 133055.492 |  | - | 133055.492 | 133055.492 | 133055.492 | 133055.492
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2306116A | 661015 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2149 | C |  | AMHS Grating Floor Opening | 45101 | 45135 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 661015 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 382020 |  |  | 131790 | 0 | 33310 | 0 |  | 89990 | 23905 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | Main Contract Scope | CDS | Chemical | Mechanical | Housekeeping | USC21C005 | USCSB2306029A | 661000 | F21P1 Chemical & WCCS package | 2064 | C |  | Housekeeping for WRC, Lorry A & B | 45086 | 45090 | [6 empty] | Handy Technology Corp. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 594065.02 | 0.89874 | 66934.98 | 0 | 66934.98 | 0 | [33 empty] | 0 |  | 169920 | 248601.07 | 2718.21 |  | 172825.74 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2207009A | 660920 | F21P1 WWT package (Installation and 2 batch tanks) | 1424 | C |  | Kelly outsourcing engineering | 44749 | 44750 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 659932.88 | 0.99851 | 987.12 | 0 | 987.12 | 0 | [14 empty] | 53797.82 |  | 90770.69 |  | 145762.52 |  | 202214.57 |  |  | 167387.28 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2308100A | 658791.27 | WWT Change Order (Piping) | 2397 | C |  | RFQ – MIC – Stripper System Piping, Pumps, Outside Tanks - Insulation | 45155 | 45205 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 658791.27 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 284591.39 | 0 | 24904.87 |  | 0 | 129031.91 | 220263.1 |  | 0 | [8 empty] | 32939.5635 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2402203A | 656250 | F21P1 AMAT Interconnection | 3630 | C |  | NUUO Labor | 45343 | 45356 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 656250 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 310312.5 |  | 345937.5 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C013 | USCSB2306126A | 653553.4 | F21P1 AMC THC Monitoring System | 2159 | C |  | THC electric and low voltage engineering | 45105 | 2023/7/10 2024/8/6 | -123326.6 | 776880 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PO R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 653553.4 | 1 | 0 | 58818.75 | -58818.75 | 0 | [33 empty] | 0 | [6 empty] | 49475 | 0 | 0 | 0 |  | 202258.4 | 401820 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 62151 |  |  |  | 22297 |  | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Labor | USC23C014 | USCSB2304001A | 651855 | F21P1 Labor incentive program-MICU | 1842 | C |  | 2022 holiday incentive (Nov, Dec) | 45017 | 45022 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 632823 | 0.9708 | 19032 | 0 | 19032 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 632823 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401087A | 650310 | F21P1-0404_H_labor for 50 tools_MICU | 3276 | C |  | MICU HK Power Hardware quote for Third next 100 tools | 45304 | 45309 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 30240 | 0.046501 | 620070 | 131964 | 488106 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 30240 | [6 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2307061A | 650000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2228 | C |  | CGS Global Support | 45121 | 45128 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 650000 | 0 | 650000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410050A | 648000 | Tool Hook Up E2 Trade Equipment Rental | 4992 | C |  | HK_Chi Yi Hsin_Equipment Rental_2nd PO_End date 8/31/2024 | 45569 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 648000 | 0 | 648000 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409036A | 644335 | Tool Interconnection Project (Main Tool & Other Vendors) | 1238 | P |  | SINGLE-LAYER TUBING / CONSTRUCTION LABOR (5PPL2DAYS) | 45553 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 644335 | 0 | 644335 | 0 | [73 empty] | -
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2310099A | 644264 | WWT Change Order (Piping) | 2761 | C | -01 | WWT-Suction pipes for train A | 2023/10/17 2023/12/8 | 2023/10/19 2024/1/4 | 123508 | 520756 |  |  | V |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | PR R1Renew quotation |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 612083 | 0.95005 | 32181 | 0 | 32181 | 30604.15 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 187472 | 113557 | 37474 |  |  | 69786 | 103234 | 0 |  | 51617 |  |  |  | 48943 | 32213.2 |  |  |  | 32213.2 |  |  |  | 32213.2 |  | 0 |  | - | 0 | 0 | 0 | 30604.15
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2303075A | 642756.2 | F21P1-0404_H_Hallway plate install_MICU | 1813 | C |  | QR/EBO foundation | 45003 | 45013 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 338859.97 | 0.5272 | 303896.23 | 0 | 303896.23 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 30530.92 |  | 189291.63 |  |  |  | 42743.36 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 8021.9 |  | 0 | 0 | 0 |  | 0 |  | 34136.08 | [5 empty] | 34136.08 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC23C045 | USCSB2312111A | 638265.04 | WWT Change Order (Piping) | 3101 | C |  | Kelly outsourcing | 45276 | 45279 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 638265.04 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 638265.04 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2203006A | 630878 | F21P1 UPW | 1341 | C |  | Tanks freight | 44625 | 44629 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 100% by progress-Net 30 Days-After Acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N |  |  |  | N |  |  | 630878 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 630878 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401101A | 623987 | F21P1-0404_H_labor for 50 tools_MICU | 3288 | C |  | HK Exhaust material for next 100 tools. Special specifications only available in Taiwan. | 45304 | 45313 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 623987 | 0 | 623987 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2401179A | 619121.32 | F21P1 Slurry package | 3364 | C |  | CDS T&M work Nov | 2024/1/23 2024/1/26 | 45315 | [6 empty] | CRG International | PR Approved | PO Approved | PR R1:As per Purchasing team's David Wang,due to update the price and quote. |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 619121.32 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  | 619121.32 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312045A | 618000 | Tool Interconnection Project (Main Tool & Module) | 591 | P | -01 | KPE604-S Build ASML EUV Water Line & QC | 2023/12/12 2024/1/9 | 2023/12/15 2024/1/9 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | Revision of Trade term from DDP to ExW |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 196240.24 | 0.31754 | 421759.76 | 0 | 421759.76 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 182532.16 | [5 empty] | 13708.08 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC24C005 | USCSB2404154A | 615000 | Chemical & WCCS B Side Project | 4138 | C | -01 | 垚鋐電力人力-點工人力(15人/3個月) | 45402 | 2024/4/26 2024/5/1 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | WO R1: Revise the Supplier Chinese Name on Construction Name from 堯宏 to 垚鋐 | [13 empty] | 0 | 0 | 615000 | 432869.37 | 182130.63 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 183500 |  |  |  | 205000 |  |  |  | 205000 |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | 0 | 0 | Chemical | Mechanical | Labor | USC22C014 | USCSB2403154A | 613283.87 | F21P1 AMHS Power Panel | 3853 | C |  | Yaho support for chemical(11/06/2023~02/22/2024) | 45366 | 45369 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 450217.11 | 0.73411 | 163066.76 | 0 | 163066.76 | 0 | [52 empty] | 0 | 0 | 450217.11 |  | 0 | [12 empty] | 163066.76 |  | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C031 | USCSB2407082A | 610000 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4498 | C |  | Top Chain B Side Seismic Project | 45488 | 45496 | [6 empty] | Top Chain Construction Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 610000 | 0 | 610000 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC24C005 | USCSB2404141A | 610000 | Chemical & WCCS B Side Project | 4125 | C |  | Proposal TSMC-012 @ Chemical Piping_Side B_L10 CPVC_GN2_PFA_PULL BOX_RELATED SUPPORTS Installations | 45400 | 45405 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 494100 | 0.81 | 115900 | 0 | 115900 | 30500 | [54 empty] | 0 |  | 0 | [8 empty] | 366000 |  |  | 494100 | 213500 |  | 30500 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401020A | 601000 | F21P1-0404_H_labor for 50 tools_MICU | 3211 | C |  | HK YAHO Equipment Rental for 3 months | 45296 | 45317 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 601000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 601000 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Material | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC22C019 | USCSB2210015A | 600000 | AMC monitor 595T0 | 1498 | C |  | MICU-TSMC F21P1 Litho AMC 64CH online monitoring system | 44841 | 44848 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  | 95% by shipping-Net 30 days-After acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 600000 | 1 | 0 | 0 | 0 | 30000 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 104264.5 | 378222.5 | 0 | 0 |  |  | 87513 | 0 | 0 |  | 0 | [14 empty] | 0 | 30000 | - | 0 | 0 | 0 | 30000
Base-Build | Chemical | Housekeeping | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C005 | USCSB2305094A | 600000 | F21P1 Chemical & WCCS package | 2015 | C |  | Detail Clean | 45066 | 45289 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 477767.25 | 0.79628 | 122232.75 | 46880 | 75352.75 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 131437.5 | 0 | 0 |  |  | 63156.25 | 0 | 87343.75 |  | 0 |  | 63281.25 | [11 empty] | 85668.5 | 0 |  | 46880 | 0 | 0 | 0
Base-Build | WWT | LPS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2109004A | 599155.6 | F21P1 WWT package (Installation and 2 batch tanks) | 1278 | C | -01 | Front-End Engineering Support Service | 44443 | 44462 | -844.4 | 600000 |  |  |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | Rev01-According to PM indication:Terminating LPS from the project | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Rui Ma | Cherry Chang | WWT |  | Henry |  | Y | 5005 |  | 599155.6 | 1 | 0 | 0 | 0 | 0 |  |  | 100000 | 150000 |  |  |  |  | 0 |  | 100000 |  | 0 |  |  |  |  | 129536 | 119619.6 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306032A | 596273 | Tool Interconnection Project (Main Tool & Module) | 316 | P |  | KPE602-S TRIDENT MECHANICAL - LABOR | 45087 | 45139 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 596273 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 498221 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 98052 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | DCR Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2404029A | 595712 | F21P1 WWT package (Installation and 2 batch tanks) | 4025 | C |  | WWT UIS Manpower_20240329 | 45385 | 45387 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 302240.16 | 0.50736 | 293471.84 | 0 | 293471.84 | 148097.6784 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 302240.16 | 89356.8 |  |  |  | 89356.8 |  |  |  | 89356.8 |  | 30224.016 |  | - | 30224.016 | 30224.016 | 30224.016 | 27201.6144
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C003 | USCSB2302044A | 595649.07 | F21P1 UPW | 1725 | C |  | LPS RH materials #2 | 44980 | 44986 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 595649.07 | 1 | 0 | 0 | 0 | 11615.4726 | [28 empty] | 0 |  |  | 59660.15 |  | 0 |  | 188422.24 |  | 79808.76 |  |  | 0 | 0 | 0 | 0 |  | 252882.48 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 14875.44 |  |  | 0 |  | - | 0 | 0 | 0 | 11615.4726
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405050A | 594870.95 | Tool Interconnection Project (Main Tool & Other Vendors) | 1092 | P |  | KRWRS5 / KRWRS4 / KRWRS2 / KDHBS1 / KRWRS7 / KDBCS1 / KRWRS6 / KCSCSB / KRWRS3 / KDSNS1 / KDCRS1 / KDCCS2 / KCSCSA / KRWRS1 / KDSTSA / KDCRS4 / KDCCS3 / KCSCS7 / KDCCS1 / KCSCS9 / KEPSS1 / KEPST4- DNS SCREEN INTERCONNECTS-Line Labeling | 45426 | 45428 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 594870.95 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 594870.95 | [8 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2312047A | 591435 | WWT Change Order (Piping) | 3040 | C |  | WWT_LB2 LSR Scope_BMWC | 45268 | 45294 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 561863.25 | 0.95 | 29571.75 | 0 | 29571.75 | 28093.1625 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 365211.11 | 50567.79 |  | 0 |  | 146084.35 |  |  | 29571.75 |  |  |  | 59143.5 |  |  |  | 59143.5 |  | 0 |  | - | 0 | 0 | 0 | 28093.1625
Base-Build | Chemical | Rosendin | DCR Scope | CDS | Chemical | Electrical | M+L | USC21C006 | USCSB2305080A | 590648 | F21P1 Slurry package | 2001 | C |  | CDS Solvent Room Conduit & Updated Cable Tray/Supports Constructible BIM Model | 45063 | 45079 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 590648 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 389547.79 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 201100.21 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2308118A | 590060 | WWT Change Order (Piping) | 2416 | C |  | WWT -BMWC Tunnel Trestle r2 | 45157 | 45162 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 590060 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 89888.05 | 0 |  | 415522.21 | 55146.76 | 0 | 0 | 0 |  |  | 29502.98 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2406009A | 589183.95 | WWT B side Project | 4235 | C |  | (Chemical Borrowed)澤維實業PVDF 料件0531 | 45444 | 45447 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 150907.82 | 0.25613 | 438276.13 | 0 | 438276.13 | 589183.95 | [71 empty] | 117836.79 | 150907.82 | - | 117836.79 | 117836.79 | 117836.79 | 117836.79
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2407165A | 587428.8 | WWT B side Project | 4588 | C |  | WWT - Brahma A-Side Carboline Flange Coating | 45503 | 45506 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 587428.8 | 411200.16 | 176228.64 | [74 empty] | -
[5 empty] | Others |  |  | USC22C025 | USCSB2409112A | 586242.26 | Tool Hookup Material (UPW&Chemical) | 4931 | C |  | AMHS_Oct-Nov 9 Distribution Panels_Batch 2/2 | 45562 | 45565 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 586242.26 | 0 | 586242.26 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2404012A | 584370 | F21P1 AMAT Interconnection | 4008 | C |  | NUUO April Labor | 45384 | 45390 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 584370 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 111697.5 | [5 empty] | 467197.5 |  | 5475 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2401180A | 582103.64 | F21P1 Slurry package | 3365 | C |  | CDS T&M work Dec | 2024/1/23 2024/1/26 | 45315 | [6 empty] | CRG International | PR Approved | PO Approved | PR R1:As per Purchasing team's David Wang,due to update the price and quote. |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 582103.64 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 582103.64 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C005 | USCSB2204007A | 581700 | F21P1 Chemical & WCCS package | 1356 | C |  | Lorry building engineering services | 44669 | 44679 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  | 100% Progress Payment-Net 30 days-After acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 581700 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 232680 |  |  |  | 122000 | [5 empty] | 164706 |  | 25000 |  |  |  | 18657 |  | 0 |  |  |  |  | 0 |  |  | 8000 |  | 9500 |  | 0 | 0 | 1157 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C005 | USCSB2307135A | 581400 | F21P1 Chemical & WCCS package | 2297 | C |  | TSMC FAB, Lorry, and WRC Field Observation | 45135 | 45139 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 416179 | 0.71582 | 165221 | 0 | 165221 | 0 | [39 empty] | 24500 | 38424 | 0 | 0 | 0 |  | 118430 | 0 | 84775 | 0 | 150050 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C003 | USCSB2206009A | 571949.64 | F21P1 UPW | 1400 | C |  | Commissioning Chemicals | 44720 | 44727 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | Y | [6 empty] | 571786.07 | 0.99971 | 163.57 | 0 | 163.57 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 7284.8 |  |  | 5309.2 | 5595.2 | 0 | 11065.6 | 0 | 5210.4 | 53158.25 | 5733 | 60838.09 | 103206.08 | 0 | 116016.46 |  | 22129.28 | 33109.9 | 89273.84 |  | 13804.7 |  | 17765.04 |  | 8700 | [5 empty] | 10425.6 |  | 3160.63 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Southland | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2210005A | 569074 | F21P1 VOC package （Installation ) | 1489 | C |  | VOC project Added insulation per Bill of Materials | 44835 | 44841 | [6 empty] | Southland Industries | PR Approved | PO Approved | USCSB2109008A-1 change order (TSMC will pay) | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 569074 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 54574 | [7 empty] | 0 |  |  |  | 42315 | 0 |  |  |  | 177364 |  |  | 84630 | 0 | 0 | 0 |  | 0 | 50778 | 79129 | 0 | 0 | 80284 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2408032A | 568811.52 | F21P1 AMHS Wiring Work Outline | 4627 | C |  | Sinfonia Manpower Support to MML (first batch)(6/17/2024- 11/22/2024) | 45512 | 45554 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | NTD 16,779,101 (@0.0339) | [13 empty] | 0 | 0 | 568811.52 | 0 | 568811.52 | [74 empty] | -
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2407087A | 568229 | WWT B side Project | 4503 | C |  | LB2 GIP Blower System_WWT | 45489 | 45492 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 278432 | 0.49 | 289797 | 147740 | 142057 | 0 | [68 empty] | 119328 |  |  | 0 | 159104 | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2406120A | 565519.66 | F21P1 AMAT Interconnection | 4359 | C |  | AMAT TW trade P1B 2nd 33 machine material | 45468 | 45471 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 565519.66 | 452415.728 | 113103.932 | 0 | [73 empty] | - |  |  | 0
[5 empty] | Others |  |  | USC22C025 | USCSB2409127A | 562342.33 | Tool Hookup Material (UPW&Chemical) | 4945 | C |  | AMHS_P1B 14 DPs CCE Scope_ Batch 1/2 | 45563 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 562342.33 | 0 | 562342.33 | 0
Base-Build | Base-Build | Outsourcing |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC23C002 | USCSB2309008A | 559797.76 | F21P1-0404_H_Hallway plate install_MICU | 2486 | C |  | Project manpower supply for safety, project management and house keeping | 45170 | 45174 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 559797.76 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 559797.76 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C005 | USCSB2207006A | 557900 | F21P1 Chemical & WCCS package | 1421 | C |  | Engineering Design Assistance and Engineer of Record Services | 44748 | 44750 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 557900 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 200000 |  | 150000 |  |  |  | 139475 |  | 25000 |  | 25000 |  | 6300 |  | 0 |  |  |  |  | 0 | [5 empty] | 12125 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2305062A | 550898.8 | F21P1-0404_H_Hallway plate install_MICU | 1984 | C |  | 3rd, 4th X-B3-EUV and DUV foundation installation | 45059 | 45064 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 217179.5 | 0.39423 | 333719.3 | 26914.26 | 306805.04 | 0 | [33 empty] | 0 | [6 empty] | 217179.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Southland | The budget execution does not pertain to this project | AMC THC | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2203012A | 547240 | F21P1 VOC package （Installation ) | 1347 | C |  | AMC THC mechanic work | 44638 | 44641 | [6 empty] | Southland Industries | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 Days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | VOC? | [6 empty] | 536295.54 | 0.98 | 10944.46 | 0 | 10944.46 | 10944.8 | [16 empty] | 9546 | [7 empty] | 7201 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 112991 | 0 | 0 | 0 | 24155 | 0 | 0 | 91331 | 47532 | 0 | 85867.3 |  | 89065.92 | 0 | 0 |  | 0 | [9 empty] | 68606.32 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 10944.8
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2407154A | 546932 | WWT B side Project | 4563 | C |  | LB2 WWT 60608 & 60110 | 45499 | 45505 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 546932 | 0 | 546932 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical |  | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2406093A | 542050 | F21P1 Chemical & WCCS package | 4328 | C |  | FAB Chemical Observation - LSW | 45462 | 45463 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 59080 | 0.10899 | 482970 | 68565 | 414405 | 0 | [72 empty] | 59080 | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306049A | 539509.11 | Tool Interconnection Project (Main Tool & Module) | 333 | P |  | KPE601-S TRIDENT MECHANICAL SERVICES LABOR PAY | 45105 | 45171 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 539509.11 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 345890.11 | 0 | 0 | 0 | 0 |  | 0 | 99008.73 | 0 | 0 | 0 |  |  | 76198 | 0 | 0 |  | 0 | [7 empty] | 18412.27 | [6 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410046A | 538000 | Tool Hook Up E2 Trade Equipment Rental | 4989 | C |  | HK_Wholetech_Equipment Rental_2nd PO_End date 8/31/2024 | 45569 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 538000 | 0 | 538000 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2408043A | 524805.7 | F21P1 AMHS Power Panel | 4634 | C |  | VT Network Cable Wiring_AMHS | 45513 | 45518 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 255580.38 | 0.487 | 269225.32 | 255580.38 | 13644.94 | [74 empty] | 255580.38
Base-Build | Chemical | Southland | DCR Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2310068A | 517921.17 | F21P1 Chemical & WCCS package | 2729 | C |  | Southland Co for Chemical team | 45210 | 45212 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 517921.17 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 517921.17 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2406103A | 512375.38 | F21P1 AMHS Power Panel | 4338 | C |  | AMHS PSP Additional 1 AWG 3/C Wire CO | 45463 | 45467 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 512375.38 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 512375.38 | [8 empty] | - |  |  | 0
Base-Build | AMC THC | Material | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C013 | USCSB2306079A | 508710 | F21P1 AMC THC Monitoring System | 2112 | C |  | F21P1 EBO AMC+TVOC 16CH online monitoring system | 45094 | 45105 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 313284 | 0.61584 | 195426 | 175588.5 | 19837.5 | 195426 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 83942 |  | 229342 |  |  |  |  | 76307 |  |  |  | 93705 |  | 76306.5 |  | - | 66132.3 | 25435.5 | 25435.5 | 2116.2
Base-Build | UPW | CCE | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2303015A | 502320 | F21P1 UPW | 1757 | C |  | UPW system panels installation and linking | 44987 | 45014 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 408480 | 0.81319 | 93840 | 0 | 93840 | 0 | [28 empty] | 0 | 257600 | 84640 |  |  | 0 | 5520 | [5 empty] | 12880 | 0 | 47840 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Labor | USC24C006 | USCSB2406110A | 500500 | WWT B side Project | 4350 | C |  | LSR MU 元富 scope lump sump | 45465 | 45475 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 500500 | 0 | 500500 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2110010A | 500000 | F21P1 WWT package (Installation and 2 batch tanks) | 1299 | C |  | Site 3rd Party QC Service | 44482 | 44484 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | 44488 | Paul |  | N |  |  | 500000 | 1 | 0 | 0 | 0 | 0 |  |  |  | 8011.58 |  |  | 14956.14 | 23951.01 | 26369.79 |  | 35869.2 |  |  |  | 77159.16 |  |  | 23071.19 | 45497.18 |  | 50831.94 |  | 41878.65 |  | 46076.51 | 36415.05 | 47188.39 |  | 22724.21 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | Base-Build | Labor |  |  | Base-Build |  |  | USC22C025 | USC2303003A | 500000 | AMHS TSMC Instrustructure and Branch Circuits | 269 | P |  | General Laborer and Housekeeping Services /Superintendent Services | 44999 | 45000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 469122.5 | 0.93824 | 30877.5 | 0 | 30877.5 | 0 | [28 empty] | 0 |  |  |  | 260757.5 | 94647.5 | 113217.5 | 500 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USC2301008A | 500000 | F21P1 Slurry package | 266 | P |  | General Laborer and Housekeeping Services/Superintendent Services | 44953 | 44959 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 489760 | 0.97952 | 10240 | 0 | 10240 | 0 | [25 empty] | 168622.5 | 65322.5 | 148015 | 67055 | 40745 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC23C002 | USCSB2309111A | 500000 | F21P1-0404_H_Hallway plate install_MICU | 2583 | C |  | Tool Hookup Design/Base Build Design/System/Safety | 45188 | 45188 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 421156.11 | 0.84231 | 78843.89 | 0 | 78843.89 | 0 | [39 empty] | 36567.56 | 91774.55 | 195712.22 | 96221.77 | 0 | 880.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | M+L | USC22C010 | USCSB2308106A | 500000 | F21 P1 LSC CMS and DPM 5G System | 2403 | C |  | BPG termination | 45156 | 45157 | [6 empty] | BPG Technologies, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 500000 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 500000 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C008 | USCSB2210020A | 500000 | F21P1 CCTV & Security | 1503 | C |  | Sunrise Phoenix housekeeping services | 44845 | 44846 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 457477.5 | 0.91495 | 42522.5 | 0 | 42522.5 | 0 | [18 empty] | 21525 | 99892.5 | 71137.5 | 36357.5 | 69712.5 | 113525 | 45327.5 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC23C045 | USCSB2309181A | 500000 | WWT Change Order (Piping) | 2650 | C |  | Sunrise Phoenix housekeeping services | 45198 | 45203 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 488382.87 | 0.97677 | 11617.13 | 0 | 11617.13 | 0 | [40 empty] | 63400.2 | 77352.14 | 77714.67 | 0 |  | 87045.67 | 28918.02 | 87710.52 | 25882.31 | 16621.84 | 9027 | 9306.5 | 5404 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | MIMO/Rigging |  |  | Others |  |  | USC23C002 | USCSB2306054A | 500000 | F21P1-0404_H_Hallway plate install_MICU | 2088 | C |  | Foundation accessory move-in labor | 45091 | 45135 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 395220 | 0.79044 | 104780 | 0 | 104780 | 0 | [33 empty] | 0 | [6 empty] | 0 | 112960 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 282260 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C005 | USCSB2306077A | 500000 | F21P1 Chemical & WCCS package | 2110 | C |  | Sunrise Phoenix housekeeping services | 45094 | 45103 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 500000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 84410 | 208180 | 126220 | 81190 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | Main Contract Scope | CDS | Chemical | Mechanical | Housekeeping | USC21C005 | USCSB2307120A | 500000 | F21P1 Chemical & WCCS package | 2284 | C |  | Sunrise Phoenix housekeeping service | 45134 | 45139 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 499370.23 | 0.99874 | 629.77 | 0 | 629.77 | 0 | [37 empty] | 144815 | 225345.38 | 39313.25 | 51848.37 | 0 | 38048.23 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | Main Contract Scope | CDS | Chemical | Mechanical | Project Outsourcing (專案管理外包人力) | USC21C005 | USCSB2307121A | 500000 | F21P1 Chemical & WCCS package | 2285 | C | -01 | General labor and Housekeeping Service/Superintendent Service | 2023/7/27 2023/9/11 | 2023/8/1 2023/9/12 | -100000 | 600000 |  |  |  |  | Handy Technology Corp. | PR Approved | PO Approved | Adjusting the amount due to Handy Tech been expelled from TSMC site/The workload will be adding to CGS in the future. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 490308.75 | 0.98062 | 9691.25 | 0 | 9691.25 | 0 | [38 empty] | 95459.4 | 394849.35 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C011 | USCSB2211011A | 496063.78 | F21 TMAH System | 1546 | C |  | LC/MS/MS System for TSMC Project | 44873 | 44886 | [6 empty] | Agilent Technologies, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 496063.78 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 496063.78 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | 光阻櫃 | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC22C012 | USCSB2306067A | 494371.72 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 2100 | C |  | A Side Photoresist Cabinet Exhaust Hookup engineering | 45093 | 45142 | [6 empty] | MornstAir Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 469653.13 | 0.95 | 24718.59 | 0 | 24718.59 | 0 | [33 empty] | 0 | [6 empty] | 469653.13 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410042A | 494352.29 | Tool Hook Up E2 Trade Equipment Rental | 4985 | C |  | HK_Tunyi_Equipment Rental_2nd PO_End date 8/31/2024 | 45568 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 494352.29 | 0 | 494352.29 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C005 | USCSB2305067A | 490292.57 | F21P1 Chemical & WCCS package | 1989 | C |  | Stripper Platform and F21P1 FRP Works | 45062 | 45083 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 490292.57 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 235372.57 | 73543.8855 |  |  | 254920 | 73543.8855 |  |  |  | 73543.8855 |  | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C031 | USCSB2409128A | 488291.33 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4946 | C |  | AMHS_P1B 14 DPs CCE Scope_ Batch 2/2 | 45563 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 488291.33 | 0 | 488291.33 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2302007A | 485560.79 | Tool Hookup Material (UPW&Chemical) | 1688 | C | -01 | Tool Hookup Material (UPW 23k) | 2023/2/3 2023/3/2 | 2023/2/8 2023/3/3 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | Price change |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 485560.79 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 950.3 | 15474.95 | 2956.03 | 43783.97 | 82105.25 |  | 12978.52 | 14840.5 | 97084.75 |  |  | 97738.94 | 0 | 2983.44 | 0 |  | 55766.9 | 40526.9 | 0 | 10063.66 | 0 |  |  | 0 | 0 | 8306.68 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2401173A | 480826 | WWT Change Order (Piping) | 3358 | C |  | WWT-Install L20 HPM Drains | 45314 | 45315 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 433945.75 | 0.9025 | 46880.25 | 0 | 46880.25 | 43394.575 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 45678.85 | 0 |  | 0 |  | 246663.7 |  |  | 72123.9 | 95924.35 |  |  | 72123.9 | 45678.85 |  |  | 72123.9 |  | 0 |  | - | 0 | 0 | 0 | 43394.575
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405095A | 480000 | Chemical & WCCS B Side Project | 4115 | C |  | l20 model [PROPOSAL STATUS FOR L20 AND L30] | 45428 | 45433 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 480000 | 0 | 480000 | 240000 | [56 empty] | 0 | [12 empty] | 240000 |  | 216000 |  | - | 24000 |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2310011A | 479503.83 | Tool Hookup Material (UPW&Chemical) | 2674 | C |  | HK UPW DP Panel additional request | 45202 | 45210 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 479503.83 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 45555.6 | 284470.61 |  |  | 0 | 82311.54 | 0 |  | 0 |  |  |  | 67166.08 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2303001A | 479076.14 | F21P1 UPW | 267 | P |  | Liberty Scaffolding | 44993 | 44999 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 479076.14 | 0 | 479076.14 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2307022A | 476835.84 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2194 | C |  | OSC Contracted Labor Force – 6 months | 45113 | 45119 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 476835.84 | 1 | 0 | 0 | 0 | 0 | [35 empty] | 70638.68 | 26484.38 |  | 75827.17 |  | 0 | 96116.72 | 0 | 0 |  | 0 | 42223.99 | 10711.5 | 22450.14 | 23876.68 | 20372.63 | 29491.4 | 0 | 0 | 0 |  | 51029.65 |  | 7612.9 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2302046A | 476190 | F21P1-0404_H_Hallway plate install_MICU | 1727 | C |  | TSMC F21 Stainless steel plate | 2023/2/23 2023/6/14 | 45001 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | Adjusting this PR to align with already issued PO. (PR 509,699.00) |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 476190 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 476190 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG | Labor |  |  | Others |  |  | USC22C003 | USCSB2204013A | 473540 | TSMC Fab21 Project Phase 1 EDG Package | 1362 | C |  | TSMC Fab21 Project Phase 1 EDG Package | 44679 | 44680 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 473540 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 355933.5 |  |  | 14944 |  |  | 21623.5 |  |  |  | 37681.5 |  |  |  | 12821 |  | 6721 |  |  |  | 0 |  | 5515.5 |  | 9460.5 | 0 | 8839.5 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2305049A | 470099.35 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1974 | C |  | KPE601 S LIT 2 TRIDENT- TIME AND MATERIAL | 45057 | 45069 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 470099.35 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 369338.46 | 0 |  |  | 100760.89 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C012 | USCSB2304059A | 468465 | F21 Barcode RFID System | 1898 | C | -01 | General labor and Housekeeping Service/Superintendent Service | 2023/4/20 2023/12/28 | 2023/4/25 2023/12/28 | -31535 | 500000 | V |  |  |  | Handy Technology Corp. | PR Approved | PO Approved | Scope was completed for final total of $468,465. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 468465 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 268670 | 0 | 199795 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2406058A | 467500 | WWT Change Order (Piping) | 4291 | C |  | (A side)YAHO T&M A side work from 05/2024-07/2024 | 45454 | 45455 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | [14 empty] | 430583.33 | 0.92103 | 36916.67 | 0 | 36916.67 | 467500 | [70 empty] | 430583.33 | 93500 |  | - | 93500 | 93500 | 93500 | 93500
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C009 | USCSB2304035A | 466583.7 | F21P1 WWT package (Installation and 2 batch tanks) | 1875 | C |  | WWT Activated carbon | 45031 | 45050 | [6 empty] | Calgon Carbon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 355635.5 | 0.76221 | 110948.2 | 126407 | -15458.8 | 116227.265 | [33 empty] | 0 |  |  | 208991.75 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 28206.75 | 0 | 0 |  | 0 |  |  |  |  | 46658.37 |  |  |  | 46658.37 |  |  |  | 46658.37 |  | 23719.85 |  | 118437 | 23719.85 | 23719.85 | 23719.85 | 21347.865
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2402106A | 464666.96 | Tool Interconnection Project (Main Tool & Other Vendors) | 818 | P |  | Interconnection cable pull for KDSET1, KDCRS5, KDMRS3, KDCRS1, KDHBS1, KDMRS2, KDSNS1, KDMRS1, KDMRS4, KCSCS3, KEPSL5, KEPSL3 KEPSL1, KDCCS1, KEPSL4, KDCRS4, KDCCS2, KDCCS3, KCSCSA, KEBCT3, KRWRS7, KCSCS9 KCSCS7, KEPSL6, KEPSS1, KCSCSB, KCSCSC KEPST4, KCSCS6, KEPSL2 | 45349 | 45357 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 432000.56 | 0.9297 | 32666.4 | 0 | 32666.4 | 0 | [52 empty] | 0 | 0 | 54666.96 |  | 0 | [5 empty] | 377333.6 | [8 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410039A | 463284 | Tool Hook Up E2 Trade Equipment Rental | 4982 | C |  | HK Li Jie Industrial Co.，Ltd Equipment rental End date 08/31/2024 | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 463284 | 0 | 463284 | 0
Hookup | 5G | Material | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC22C010 | USCSB2209028A | 461201.41 | F21 P1 LSC CMS and DPM 5G System | 1480 | C | -01 | GLA CMS project | 2022/9/27 2023/11/23 | 2022/10/3 2023/11/27 | -1209566.59 | 1670768 |  |  |  | V | GLA Arizona, LLC | PR Approved | PO Approved | PO R1:Cutting off GLA from the project per request by PM./ The rest of work will goes to Hua Yi in the future. | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 461201.41 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 112933.4 | [5 empty] | 0 |  |  |  |  | 0 | 236136.24 |  |  |  | 112131.77 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2401200A | 456146.57 | F21P1 AMAT Interconnection | 3385 | C |  | Brycon 6 mnths Electrical work for AMAT Team | 45316 | 45356 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 456146.57 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 456146.57 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2402015A | 456000 | WWT Change Order (Piping) | 3458 | C |  | WWT B side Geijinsin Lb1/L20 submain | 2024/2/1 2024/9/10 | 2024/2/5 2024/9/16 | -24000 | 480000 |  |  |  |  | Gejinsin Enterprise Co., Ltd. | PR Approved | PO Approved | R1: As per PM Jim to Adjust this PR to 95% of the total amount. Jim has informed the Gejinsin. |  | Kuan-Chung Su | [11 empty] | 456000 | 1 | 0 | 24000 | -24000 | 111666 | [48 empty] | 0 | 150000 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 48000 | 151800 |  |  | 48000 |  |  | 130200 | 48000 |  | 30180 |  | 24000 | 30180 | 30180 | 21126 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408151A | 454485.56 | TSMC Fab 21 P1B Tool Hook Up | 4766 | C |  | Hardware for HK Power for 200 tools | 45534 | 45545 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 454485.56 | 0 | 454485.56 | 0 | [73 empty] | -
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2207008A | 454451 | F21P1 Chemical & WCCS package | 1423 | C |  | Lorry Common Rack | 44748 | 44762 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | Y | [6 empty] | 454451 | 1 | 0 | 0 | 0 | 22722.55 | [16 empty] | 23500 |  | 46725.5 |  | 159725.5 |  | 201774.45 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 22725.55 |  |  |  |  | 0 |  | - | 0 | 0 | 22722.55
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2402126A | 453323.83 | F21P1 AMHS Wiring Work Outline | 3563 | C |  | AMHS M165/M187 Additional Module Installation | 45336 | 45337 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 350283.33 | 0.7727 | 103040.5 | 0 | 103040.5 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 350283.33 | [6 empty] | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C015 | USCSB2409126A | 453145.33 | F21P1 AMHS Wiring Work Outline | 4944 | C |  | M166/M188 Future Modules_AMHS | 45563 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 453145.33 | 0 | 453145.33 | 0
Base-Build | CCTV | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C001 | USCSB2307105A | 451916.72 | F21 P1 Office and WH Security and CCTV | 2270 | C |  | F21 P1 CCTV Power Engineering | 45129 | 45139 | [6 empty] | JB Group of LA, LLC dba Infrastructure Solutions Group | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 451916.72 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 451916.72 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2407148A | 451746.57 | WWT B side Project | 4558 | C |  | WWT AWD(O3) system - Okland | 45498 | 45519 | [6 empty] | Okland Construction Company, Inc. | PR Approved | PO Processing | [14 empty] | 0 | 0 | 451746.57 | 0 | 451746.57 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309180A | 451150.2 | F21P1-0404_H_labor for 50 tools_MICU | 2649 | C |  | Hardware for Swift(MAO HSUN) 5b | 45197 | 45223 | [6 empty] | SWIFT ENGINEERING CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 451150.2 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 160110 | 0 |  |  | 0 | 0 | 73835 |  | 132551.2 |  | 84654 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2406114A | 449679 | WWT B side Project | 4354 | C |  | WWT: CCR System Scope | 45465 | 45475 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 342119.7 | 0.76081 | 107559.3 | 289902.95 | -182343.65 | 0 | [70 empty] | 52216.75 | 0 |  | 289902.95 | 0 | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2308023A | 440215 | WWT Change Order (Piping) | 2324 | C |  | 8-120 WRC NaOH and H2SO4 WWT Chemical Lines | 45142 | 45152 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 250923 | 0.57 | 189292 | 0 | 189292 | 20073.84 | [40 empty] | 0 | 61630 | 0 | 66032 |  | 44022 | 0 | 0 | 0 | 0 |  | 79239 | 0 | 0 | 0 |  | 0 |  |  |  |  | 44021.5 |  |  |  | 44021.5 |  |  |  | 44021.5 |  | 0 |  | - | 0 | 0 | 0 | 20073.84
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2304011A | 437346.32 | F21P1-0404_H_Hallway plate install_MICU | 1852 | C |  | EUV foundation Installation | 45022 | 45033 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 437346.32 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 114180.3 |  |  |  | 258621.82 |  | 0 | 0 | 64544.2 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2212044A | 434494 | F21P1 Chemical & WCCS package | 1615 | C |  | UB Box | 44918 | 44924 | [6 empty] | Collabratech Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 434494 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 103941 |  | 250721 |  | 32872 | 0 | 46960 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Instrument | USC21C005 | USCSB2205007A | 434113 | F21P1 Chemical & WCCS package | 1371 | C | -01 | Interior Building Scan and Model | 2022/5/9 2022/5/20 | 2022/5/11 2022/5/24 | 76560 | 357553 | V | V |  |  | Zelus USA, LLC | PR Approved | PO Approved |  | 20% upfront; 80% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 434113 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 151939.55 | 72038.2 | [9 empty] | 78800.63 |  |  |  | 78801 | 26267 | 26266.62 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409037A | 432705.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1239 | P |  | KDZRTA: TOOLS BLAST CONDUIT INSTALLATION | 45553 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 432705.6 | 0 | 432705.6 | 0 | [73 empty] | -
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309152A | 430380 | F21P1-0404_H_labor for 50 tools_MICU | 2623 | C |  | Hardware for CYH (PCW) | 45195 | 45198 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 384608.4 | 0.89365 | 45771.6 | 0 | 45771.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 384608.4 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2308091A | 426380 | F21P1 AMHS Wiring Work Outline | 2388 | C |  | tsmc Fab21 - AMHS Technical Service | 45154 | 45167 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 426380 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 426380 | [6 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2409078A | 426253.94 | F21P1 AMHS Wiring Work Outline | 4870 | C |  | Sinfonia Manpower Support to MML (second batch)_8/5~12/20 | 45555 | 45559 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | NTD12,319,478(@0.0346) | [13 empty] | 0 | 0 | 426253.94 | 0 | 426253.94 | 0 | [73 empty] | -
Hookup | Base-Build | Outsourcing |  |  | Base-Build |  |  | USC23C002 | USCSB2309191A | 425080 | F21P1-0404_H_Hallway plate install_MICU | 2659 | C |  | Project manpower supply for safety, project management and house keeping | 45198 | 45201 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 424149.23 | 0.99781 | 930.77 | 0 | 930.77 | 0 | [40 empty] | 423039.23 | 0 | 1110 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C008 | USCSB2306117A | 423140.27 | F21P1 CCTV & Security | 2150 | C |  | F21 P1 CCTV & Fiber Engineering | 45104 | 45113 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 401820.86 | 0.94962 | 21319.41 | 0 | 21319.41 | 0 | [33 empty] | 0 | [6 empty] | 256104.17 | 0 | 0 | 0 | 42910.69 | 0 | 0 | 102806 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C026 | USCSB2301008A | 421832.3 | F21P1-0423_H_Unistrut Support Frame_MICU | 1631 | C |  | UPDATED BOM-1 10.26 | 44931 | 44935 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | USCSB2210027A change order |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 421827.84 | 0.99999 | 4.46 | 0 | 4.46 | 0 | [28 empty] | 0 |  | 413063.79 |  |  | 0 | [6 empty] | 0 | 0 | 8764.05 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2307056A | 420929 | WWT Change Order (Piping) | 2224 | C |  | TSMC UPW – 8-111 WWT WRC L20 Sludge Press System Piping | 45120 | 45121 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 420928 | 1 | 1 | 0 | 1 | 0 | [39 empty] | 84186 | 0 | 58930 | 0 | 0 | 193627 | 21046 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 63139 | [6 empty] | 12627.87 |  |  |  | 12627.87 |  | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410038A | 420000 | Tool Hook Up E2 Trade Equipment Rental | 4981 | C |  | HK GENII IDEAS Co.， Ltd Equipment rental End date 08/31/2024 | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 420000 | 0 | 420000 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304046A | 418692.97 | F21P1 WWT package (Installation and 2 batch tanks) | 1886 | C |  | Small pipe reinforcement | 45035 | 45049 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 418372.23 | 0.99923 | 320.74 | 0 | 320.74 | 0 | [33 empty] | 0 | 268083.3 |  | 17184.06 |  | 73334.68 |  | 0 | 0 | 574.5 | 0 |  | 1376.32 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 57819.37 |  | 0 | [8 empty] | 12560.7891 |  |  |  | 12560.7891 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | PSS | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2302011A | 417086.58 | F21P1 UPW | 1692 | C |  | WRC media loading | 44964 | 44980 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 417086.58 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 417086.58 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2408102A | 416723 | F21P1 AMAT Interconnection | 4710 | C |  | AMAT_DIF_NUUO_Cable pulls and terminator power cable for DIF 11 machine_KIHITA_KDPNA2_KDCBA2_KIHIT9_KIHIT8_KIHITB_KDDAA2_KIHI | 45527 | 45540 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 416723 | 0 | 416723 | 0 | [73 empty] | -
Base-Build | VOC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Electrical | M+L | USC22C010 | USCSB2402051A | 415467.87 | F21 P1 LSC CMS and DPM 5G System | 3493 | C |  | VOC Electric CO#5.6.9.10.12.13.14.15.16.20.22.24.26 | 45328 | 45641 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 415467.87 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 147020.69 | 0 | 134520.83 |  | 0 |  | 133926.35 | [14 empty] | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2310148A | 414578 | WWT Change Order (Piping) | 2804 | C |  | WWT-BMWC-Litho drain pipe-Train B | 45223 | 45248 | -29699 | 444277 | V |  |  | V | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 414578 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 101724.1 | 0 | 77900 | 0 |  |  | 116850 | 66215 | 0 |  | 0 |  | 31160 |  | 20728.9 | [10 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC23C052 | USCSB2307073A | 407782 | F21 P1A AMHS PSP & DP Power source breakers | 2240 | C |  | F21 P1A AMHS PSP & DP Power source breakers | 45125 | 45128 | [6 empty] | LayerZero Power Systems, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 407782 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 407782 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | CCE | DCR Scope | WWT | WWT | Electrical | M+L | USC23C045 | USCSB2309169A | 407681.85 | WWT Change Order (Piping) | 2638 | C |  | F21 P1 WWT Electric Engineering-CCE | 45197 | 45209 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 407681.85 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 407681.85 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2407150A | 406980 | F21P1 AMHS Wiring Work Outline | 4560 | C |  | 9500 FT 350 kcmil Feeders_AMHS | 45498 | 45502 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 406980 | 378705.6 | 28274.4 | 0 | [73 empty] | - |  |  | 0
Base-Build | VOC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Electrical | M+L | USC22C001 | USCSB2402050A | 405423.43 | F21 P1 Office and WH Security and CCTV | 3492 | C |  | VOC Electric CO#7,8,18,19,21,27,29 | 45328 | 45337 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 405423.43 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 158377.51 |  | 196260.18 | 50785.74 | 0 | 0 |  | 0 | [16 empty] | - | 0 | 0 | 0
Base-Build | VOC | Material | DCR Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C007 | USCSB2308042A | 402952.8 | F21P1 VOC package （Installation ) | 2340 | C |  | 250 MULTI CONDUCTOR (F21 P1 VOC2 and 7 wire order) | 45146 | 45148 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 402952.8 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 402952.8 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Southland | DCR Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2212051A | 402922.04 | F21P1 Chemical & WCCS package | 1622 | C |  | PTFE Lined Pipe - change order | 44924 | 44932 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 402922 | 1 | 0.04 | 0 | 0.04 | 0 | [26 empty] | 317597 |  | 0 |  |  |  |  | 0 |  |  |  |  | 85325 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406033A | 402666.49 | Chemical & WCCS B Side Project | 4259 | C |  | F21P1 B Side material - PVDF /Ele | 45449 | 45454 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 383107.09 | 0.95143 | 19559.4 | 0 | 19559.4 | 0 | [66 empty] | 249554.75 |  | 133552.34 |  |  |  |  | - |  |  | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2212028A | 401347.41 | F21P1 WWT package (Installation and 2 batch tanks) | 1601 | C |  | 2nd Set of Clamps | 44911 | 44916 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 362097.67 | 0.90221 | 0 | 0 | 0 | 0 | [26 empty] | 354621.53 |  | 7476.14 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8026.9482 |  |  |  | 12040.4223 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2305011A | 400656 | F21P1 AMAT Interconnection | 1936 | C |  | AMAT Interconnect Electrical | 45049 | 45051 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 400656 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 6428.72 |  | 19189.36 | 0 | 8782.95 | 0 | 7538.05 | 0 | 0 | 45452.84 | 29147.14 | 0 | 22935.81 |  | 0 | 0 | 132563.97 |  | 128617.16 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Hookup | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2210019A | 398400 | F21P1 WWT package (Installation and 2 batch tanks) | 1502 | C |  | Material Coordinator/Superintendent(Tool Hookup Focus/Tool Hookup Focus Track/Tool Hookup Focus DUV) | 44845 | 44846 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 398400 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 44398.98 |  | 66400 |  | 61371.86 |  | 76063.76 |  | 66926.36 |  | 67313.52 |  | 15925.52 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C008 | USCSB2303049A | 398270.74 | F21P1 CCTV & Security | 1791 | C |  | Sunrise Phoenix housekeeping services | 44999 | 45000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 368432.5 | 0.92508 | 29838.24 | 0 | 29838.24 | 0 | [28 empty] | 0 | 131365 | 78875 | 158192.5 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | NUUO | The budget execution does not pertain to this project | AMC THC | Low Voltage | Electrical | M+L | USC22C019 | USCSB2312199A | 396434 | AMC monitor 595T0 | 3186 | C |  | F21 AMC B side Engineering Construction | 45290 | 45357 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 343287.3 | 0.86594 | 53146.7 | 12268.5 | 40878.2 | 65415.2 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 75597.5 |  | 0 | [8 empty] | 122895 | 153066.7 |  |  | 79287 | 102354.6 | 6541.52 |  | 12268.5 | 13083.04 | 13083.04 | 27750.38 | 4957.22
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2408137A | 396266.5 | F21P1 Module Tool Interconnection DIF1-2 | 4746 | C |  | Scaffold for HK | 45533 | 45540 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 396266.5 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 396266.5 | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401143A | 394884.5 | F21P1-0404_H_labor for 50 tools_MICU | 3328 | C |  | HK PCW 2nd 100 order | 1/19/2024 8/23/2024 | 1/31/2024 8/29/2024 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Yikang Wang (Ta Wei Wang) |  |  |  | Yikang Wang (by David Wang) | [7 empty] | 0 | 0 | 394884.5 | 0 | 394884.5 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C025 | USCSB2409108A | 393757.74 | AMHS TSMC Instrustructure and Branch Circuits | 4914 | C |  | AMHS_Oct-Nov 9 Distribution Panels_Batch 1/2 | 45562 | 45565 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 393757.74 | 0 | 393757.74 | 0 | [73 empty] | -
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2403113A | 389707.5 | F21P1 AMAT Interconnection | 3815 | C |  | 25 INTALLERS | 45363 | 45398 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | 0 | [11 empty] | 389707.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 389707.5 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  |  |  | UPW | Civil | M+L | USC24C008 | USCSB2408026A | 385531 | UPW B Side Project | 4621 | C |  | MICU B Side Mezz#3 & #4 Partition Wall | 45511 | 45539 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 385531 | 0 | 385531 | [74 empty] | -
Base-Build | W-H2SO4 | Material | Main Contract Scope | WWT | WWT | Electrical | M+L | USC21C014 | USCSB2308119A | 384750 | F21P1 WH2SO4 | 2417 | C |  | W-H2SO4 Electrical Work | 8/19/2023 8/17/2024 | 9/21/2023 8/24/2024 | -65250 | 450000 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: As per Jim to closeout the PO. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 384750 | 1 | 0 | 0 | 0 | 53865 | [40 empty] | 384750 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 22500 |  |  |  | 22500 | [5 empty] | 19237.5 |  | - | 19237.5 | 15390 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2306030A | 383185 | F21P1 Chemical & WCCS package | 2065 | C |  | TSMC Offload | 45086 | 45091 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 383185 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 383185 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2301033A | 380441.05 | F21P1 UPW | 1654 | C |  | Tank Painting | 44943 | 44948 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 359334.87 | 0.94452 | 21106.18 | 0 | 21106.18 | 0 | [24 empty] | 189671.16 |  |  |  | 71566.65 |  |  |  |  | 0 |  |  | 74153.19 |  | 23943.87 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408139A | 380015.85 | TSMC Fab 21 P1B Tool Hook Up | 4748 | C |  | KIL CGB For HK Power trade for 200 tools | 45533 | 45544 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 380015.85 | 0 | 380015.85 | 0 | [73 empty] | -
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USC2109012A | 379521.12 | F21P1 Slurry package | 15 | P | -01 | Diaphragm Valve | 2021/9/14 2021/11/13 | 2021/9/17 2021/11/13 | -113568.82 | 493089.94 |  |  | V |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | Design change 11/22 收到採購會辦,業主變更設計(隔膜閥數量變少364>264) | 90% After Received-T/T 30days, 10% T/T 30 days (60days after acceptance) | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | N |  | Henry |  | N | 5000 |  | 379521.12 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 251576.5 |  |  |  |  | 53190.46 | [10 empty] | 74754.16 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C015 | USCSB2410030A | 379483.64 | F21P1 AMHS Wiring Work Outline | 4973 | C |  | DP Design Change_AMHS_7/7 batch | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 379483.64 | 0 | 379483.64 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Material | USC21C005 | USCSB2303082A | 375154.38 | F21P1 Chemical & WCCS package | 1819 | C |  | UPW Panel design change (FUSE AND BREAKER) | 45007 | 45014 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 103710.44 | 0.27645 | 271443.94 | 0 | 271443.94 | 0 | [28 empty] | 0 |  | 4801.56 |  |  | 0 | 98908.88 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2303020A | 375113.92 | F21P1-0404_H_Hallway plate install_MICU | 1762 | C |  | 2nd EUV foundation | 44988 | 44995 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 280369.56 | 0.74743 | 94744.36 | 0 | 94744.36 | 0 | [28 empty] | 0 |  |  |  | 252332.6 | 0 | 28036.96 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2302035A | 375113.92 | F21P1-0404_H_Hallway plate install_MICU | 1716 | C |  | Hookup EUV Foundation installation | 44973 | 44974 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 280369.67 | 0.74743 | 94744.25 | 0 | 94744.25 | 0 | [28 empty] | 0 |  | 203286 |  | 49047.61 | 0 | 28036.06 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406095A | 374081.95 | Chemical & WCCS B Side Project | 4330 | C |  | F21P1 B Side Pillar - PFA | 45462 | 45464 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | [14 empty] | 363567.55 | 0.97189 | 10514.4 | 0 | 10514.4 | 0 | [70 empty] | 363567.55 |  |  | - |  |  | 0
Base-Build | Chemical | PSS | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2301045A | 373750 | F21P1 Chemical & WCCS package | 1662 | C | -01 | PVDFxPVC & PPxPVC Double Contained Drain Scope Per BOQ 82 | 2023/1/20 2023/3/7 | 2023/1/25 2024/3/8 | -201250 | 575000 |  |  |  |  | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Amount is adjusted for work completed and final settlement of scope. Scope to be continued by University Mechanical Engineers (UMEC) | 100% by progress-Net 30 days-After acceptance | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 373750 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 86250 | 0 | 143750 |  | 57500 |  |  |  | 86250 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2304060A | 371116.2 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1899 | C |  | Cable pulls for interconnection - KPE601-S | 45037 | 45054 | [6 empty] | Corbins, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 263946.93 | 0.71122 | 107169.27 | 0 | 107169.27 | 0 | [33 empty] | 0 | [6 empty] | 263946.93 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC21C005 | USCSB2312166A | 370000 | F21P1 Chemical & WCCS package | 3154 | C |  | CDS Chemical Electrical Power Distribution Engineering Technical Supervision Service | 45282 | 45308 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 351500 | 0.95 | 18500 | 0 | 18500 | 18500 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 185000 | 0 | 0 |  | 0 |  |  |  |  | 166500 | 166500 | [8 empty] | 18500 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | CO Scope (adding/additional scope) | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2406073A | 369824 | F21P1 Chemical & WCCS package | 4305 | C |  | FAB A CO2 System Inspection(The 70% remaining) | 45456 | 45461 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved | [14 empty] | 129438 | 0.35 | 240386 | 240386 | 0 | 0 | [70 empty] | 129438 |  |  | - |  |  | 0
Base-Build | Base-Build | Scaffolding |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC22C024 | USCSB2301055A | 367625.5 | UIS Scaffolding | 1672 | C |  | Action scaffolding | 44954 | 44957 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 367625.5 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 367625.5 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC23C045 | USCSB2309023A | 367375.96 | WWT Change Order (Piping) | 2500 | C |  | Installation of FRP Membrane (LB2 A side) | 45177 | 45198 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 367375.96 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 367375.96 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | Tiger Team | Site Expense |  |  | Others |  |  | USC23C043 | USCSB2305114A | 366651 | TSMC F21 Electric Tiger Team Fisk Support & Temp Power | 2030 | C |  | Tiger Team-Wilson Electric | 45073 | 45100 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 366651 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 366651 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2310161A | 366409.31 | F21P1-0404_H_labor for 50 tools_MICU | 2815 | C |  | MATERIAL HANDLERS (5) (Contract Staffing) | 45224 | 45237 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 364303.22 | 0.99425 | 2106.09 | 0 | 2106.09 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 2946.88 | 13952.88 | 27393.5 |  | 0 | 0 | 34517.34 |  | 47355.41 |  | 46653.49 |  |  |  | 52324.7 |  |  |  | 47037.24 |  |  |  | 57542.97 | 0 | 34578.81 | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC24C006 | USCSB2405101A | 365512.5 | WWT B side Project | 4120 | C |  | tsmc support Chemical (55gal/KuritaK0800/Catalase2xConcentrated) | 45429 | 45433 | [6 empty] | Kurita America Inc | PR Approved | PO Approved | [14 empty] | 307030.5 | 0.84 | 58482 | 0 | 58482 | 49124.88 | [56 empty] | 0 | [9 empty] | 307030.5 |  |  |  |  | 15351.525 |  | - | 15351.525 | 18421.83 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2212017A | 364908.17 | F21P1 UPW | 1590 | C |  | UPW 4C Wire & Disconnect Switch | 44906 | 44916 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A-01 Change order (4C cable+disconnect switch) |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 364908.16 | 1 | 0.01 | 0 | 0.01 | 0 | [26 empty] | 114946.07 |  | 114946.07 |  | 135016.02 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Organo |  |  |  | Others |  |  | USC24C013 | USCSB2407103A | 363732.33 | Organo USA - UPW Electrical | 4518 | C |  | UPW Additional PIA & Spare | 45490 | 45497 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 363732.33 | 0 | 363732.33 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | MIMO/Rigging | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2207018A | 360000 | F21P1 WWT package （USA EQ-FRP tank) | 1433 | C |  | WWT rigging and equipment move in | 44761 | 44762 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | Related to USCSB2207017A (Seperated into these 2 POs) | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | N | [6 empty] | 360000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 72000 |  | 72000 |  | 72000 |  | 72000 |  | 54000 |  | 18000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309179A | 358306.67 | WWT Change Order (Piping) | 2648 | C |  | WWT -Train A-PP/PVDF on hand | 45198 | 45204 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 358306.2 | 1 | 0.47 | 0 | 0.47 | 0 | [40 empty] | 0 | 0 | 0 | 43767.6 |  | 32065.85 | 196103.55 | 0 | 48870.75 | 0 |  |  | 37498.45 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2406030A | 356800 | F21P1 AMHS Wiring Work Outline | 4256 | C |  | 40,000 Feet 1 AWG 3/C Cable | 45448 | 45451 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 65116 | 0.1825 | 291684 | 356800 | -65116 | 0 | [73 empty] | 65116 |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311099A | 356731.48 | F21P1-0404_H_labor for 50 tools_MICU | 2950 | C | -01 | 100 tools Terminal demand | 45278 | 2023/12/18 2023/12/20 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Change Completion Date from 12/31/2023 to 02/29/2024 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 356731.48 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 88640.17 | 9698.03 | 46508.74 |  | 130519.41 | 0 | 81365.13 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2210012A | 355000 | F21P1 WWT package (Installation and 2 batch tanks) | 1495 | C |  | F21P1 – WSR-S H2S04 Steel supports | 44840 | 44846 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 355000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 6500 | [5 empty] | 87965.5 |  | 163873.5 |  |  |  | 16436.5 | 0 |  |  | 41809.5 |  |  |  | 20644 | 0 | 17771 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | GF Agru Material | Material |  |  | WWT | Mechanical | Material | USC22C023 | USCSB2210024A | 353593.12 | AZ GF Agru Material | 1507 | C |  | GF PP&PVDF Material Mega union | 44847 | 44851 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  | 100% by shipping-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 353593.12 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 117840 |  | 13533.33 | 0 |  | 111561.19 |  |  | 0 | 110658.6 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401064A | 352148.48 | Tool Interconnection Project (Main Tool & Other Vendors) | 684 | P |  | A crew of 4 with a supervisor budget estimate working 10 hr shifts 4 days to complete triple containment hookups, pipe supports, and pressure testing per (1) Tool on T & M (approx. 16 tools total) & Materials (Tool Trailer, Tool Pick-up, Pipe Bender) | 45316 | 45328 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 76037.27 | 0.21592 | 276111.21 | 0 | 276111.21 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 40567.38 | 0 | 0 |  | 0 |  |  |  | 35469.89 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C047 | USCSB2405118A | 352125 | F21P1 HK Seismic Installation | 4146 | C |  | 3rd work order for Hookup seismic work | 45433 | 45448 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 77253.8 | 0.21939 | 274871.2 | 36550.8 | 238320.4 | 0 | [66 empty] | 18367 |  |  |  | 22336 |  |  | 36550.8 |  |  | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC23C015 | USCSB2405069A | 352000 | F21P1 AMHS Wiring Work Outline | 4089 | C |  | AUcan for AMHS extra 8 DP panel installation | 45423 | 45427 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 352000 | 174675 | 177325 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2305058A | 349263.68 | F21P1 UPW | 1980 | C |  | FAB Grounding | 45059 | 45091 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 331800.5 | 0.95 | 17463.18 | 0 | 17463.18 | 174631.84 | [33 empty] | 0 |  |  | 174631.84 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 87315.92 | 157168.66 | 87315.92 |  | - | 0 | 87315.92 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311050A | 349012.76 | F21P1-0404_H_labor for 50 tools_MICU | 2905 |  |  | HK welding handle and tools | 45240 | 45249 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 349012.76 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 172746.74 |  |  | 176266.02 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2306081A | 348526.86 | F21P1 Chemical & WCCS package | 2114 | C |  | Painting work from PHP T&M work scope (December 2022 to May 2023) | 45097 | 45105 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 348526.86 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 348526.86 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2403167A | 345859.17 | Tool Hookup Material (UPW&Chemical) | 3865 | C |  | HK UPW hookup material | 45366 | 45409 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 38954.3 | 0.11263 | 306904.87 | 69914.48 | 236990.39 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 2766.52 |  |  | 0 | 33369.54 | 2818.24 | 0 | 0 | 0
Base-Build | CCTV | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C001 | USCSB2202003A | 344373.73 | F21 P1 Office and WH Security and CCTV | 1330 | C | -01 | CCTV Warehouse Building | 44600 | 44602 | -655626.27 | 1000000 |  |  |  | V | Galaxy3 LLC | PR Approved | PO Approved | Adjusting the amount due to the termination with Galaxy3. | 95% by progress-after acceptance-net 40 days; 5% after final acceptance-net 40 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 344373.73 | 1 | 0 | 0 | 0 | 0 | [13 empty] | 104196.09 | [14 empty] | 0 | 240177.64 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401100A | 343913.5 | F21P1-0404_H_labor for 50 tools_MICU | 3287 | C |  | HK Exhaust material for next 100 tools. Special specification | 45304 | 45313 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 343913.5 | 0 | 343913.5 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2212040A | 341555.2 | F21P1 UPW | 1611 | C |  | Network & Com | 44915 | 2022/12/26 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A(Rev01) change order (Network & Communication) |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 317646.34 | 0.93 | 23908.86 | 0 | 23908.86 | 47817.72 | [26 empty] | 107589.89 |  | 34155.52 |  | 68311.04 |  | 107589.89 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 23908.86 | 0 | 23908.86
Base-Build | AMC THC | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C019 | USCSB2310175A | 341453.75 | AMC monitor 595T0 | 2828 | C |  | F21 LITHO AMC Engineering | 45226 | 2023/10/31 2024/8/5 | -17971.25 | 359425 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | R1: Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 341453.75 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 274634.8 |  | 0 | 0 | 0 |  | 0 |  | 66818.95 |  |  | 66818 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Hookup | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2211003A | 337906.32 | F21P1 WWT package (Installation and 2 batch tanks) | 1538 | C |  | Tool Team PVD/CVD Project Coordinator/ Superintendent | 2022/11/2 2022/11/8 | 44874 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 324180.38 | 0.95938 | 13725.94 | 0 | 13725.94 | 0 | [19 empty] | 13875.36 | 19230.96 |  |  | 16600 | 44267.22 |  | 50655 |  | 49339.9 |  | 49748.9 |  | 48396.82 | 0 | 32066.22 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC22C012 | USCSB2402268A | 337815 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3693 | C |  | UPW-UMEC-2023-Dec-extend GC-1 | 45350 | 45353 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 320924 | 0.95 | 16891 | 0 | 16891 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 320924 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | NUUO | DCR Scope | SDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2303096A | 336392.16 | F21P1 Slurry package | 1833 | C |  | F21P1 Slurry Instrument air | 45013 | 45019 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 320757.55 | 0.95352 | 15634.61 | 0 | 15634.61 | 0 | [33 empty] | 0 |  |  |  |  | 108705.6 |  | 0 | 0 | 0 | 0 |  | 212051.95 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 15642.24 |  | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C013 | USCSB2401036A | 329646 | F21P1 QR Lab Security & CCTV | 3227 | C |  | F21 CCTV Over Time and Interconnection | 45297 | 45301 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 329646 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 329646 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC24C007 | USCSB2404066A | 329623.97 | Low Voltage B Side Project | 4058 | C |  | F21 P1 B side CCTV Power system | 45388 | 2024/4/10 2024/8/6 | -17348.63 | 346972.6 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PO R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Kuan-Chung Su | [11 empty] | 329623.97 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 150204.32 |  |  | 52046 |  |  | 76610.86 | 52046 | 102808.79 |  |  | 34698 |  |  |  | - |  |  | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2404059A | 327267.18 | F21P1 AMHS Wiring Work Outline | 4051 | C |  | 10 Sinfonia Manpower for AMHS | 45388 | 45399 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | WO amount NTD 9,458,589 (@ 0.0346) | [13 empty] | 327267.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 327267.18 | [6 empty] | - |  |  | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Labor | USC23C014 | USCSB2306040A | 326375 | F21P1 Labor incentive program-MICU | 2074 | C |  | UMEC-2022 labor and Veterans holiday | 45087 | 45090 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 326375 | 0 | 326375 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 326375 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | CO Scope (adding/additional scope) | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2212039A | 325446.02 | F21P1 UPW | 1610 | C |  | X1_Y Line Changes | 44915 | 44916 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A(Rev01) change order (X1-Y Line) |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 325436.01 | 0.99997 | 10.01 | 0 | 10.01 | 0 | [26 empty] | 118263.61 |  | 78641.21 |  | 128531.19 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC22C013 | USCSB2311110A | 325000 | F21P1 QR Lab Security & CCTV | 2961 | C |  | F21 CCTV Engineering | 45253 | 45267 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 325000 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 325000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401021A | 324000 | F21P1-0404_H_labor for 50 tools_MICU | 3212 | C |  | HK CYH Equipment Rental for 3 months | 45296 | 45310 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 324000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 324000 |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401125A | 323660 | F21P1-0404_H_labor for 50 tools_MICU | 3312 | C | -01 | Gas 五金三百台補充第一批不足部分,Tool hookup team | 45309 | 2024/1/23 2024/2/1 |  |  |  |  | V |  | Jinsheng Industrial Co | PR Approved | PO Approved | R1: item 10: 鍍鋅型鋼變向L片(E616) : 數量從50 改 500, ITEM 37: ST?十字丸頭螺絲?(OG0220100004) M4*12: 單價從0.6735改成 0.03 |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 323660 | 1 | 0 | 19680 | -19680 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 153190 | [8 empty] | 0 | 151040 | 19430 | 0 | 0 | 0
Base-Build | AMC THC | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C013 | USCSB2310174A | 322460.69 | F21P1 AMC THC Monitoring System | 2827 | C |  | F21 THC PTFE Engineering | 2023/10/27 2024/8/1 | 2023/11/2 2024/8/7 | -16971.61 | 339432.3 | V |  |  |  | NUUO US Inc. | PR Approved | PO Approved | R1: Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 230830.47 | 0.71584 | 91630.22 | 0 | 91630.22 | 122535.06 | [42 empty] | 0 | 0 |  | 0 | 212764.94 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 67887 |  |  | 18065.53 | 41819 |  | 29021.46 |  | - | 29021.46 | 32246.07 | 32246.07
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309028A | 322290 | Tool Interconnection Project (Main Tool & Module) | 417 | P |  | labor for cable pull | 45191 | 45201 | [6 empty] | Corbins, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 322290 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 322290 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C059 | USCSB2310073A | 320000 | F21P1 Foundation T&M | 2734 | C |  | Tile Alignment | 45211 | 45232 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 320000 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 50030 | 122869.28 | 101251 | 0 |  | 42298 | 3551.72 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407025A | 316773.25 | Tool Interconnection Project (Main Tool & Other Vendors) | 1161 | P |  | C406-010: 1" 90 ELBOW S CLR PVC SCH40 | 45493 | 45499 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 99557.09 | 0.31429 | 217216.16 | 228926.21 | -11710.05 | 0 | [70 empty] | 89726.19 |  |  | 9830.9 |  |  | 0
Base-Build | WWT | CCE | DCR Scope | WWT | WWT | Electrical | M+L | USC23C045 | USCSB2311014A | 315713.89 | WWT Change Order (Piping) | 2869 | C |  | WWT CCE Change Orders | 45233 | 45237 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 299928 | 0.95 | 15785.89 | 0 | 15785.89 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 299928 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2402204A | 315000 | F21P1 AMAT Interconnection | 3631 | C |  | NUUO Change Order: add terminations | 45343 | 45370 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 315000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 315000 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2404130A | 315000 | F21P1 AMAT Interconnection | 4114 | C |  | TW trade 3rd 11 AMAT interconnect expert support from hook up team | 45399 | 45408 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 283500 | 0.9 | 31500 | 0 | 31500 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 121500 |  | 162000 |  |  | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2310037A | 314000 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2700 | C |  | Cutting in Place for Tile and Partitions | 45204 | 45243 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 299120 | 0.95261 | 14880 | 320 | 14560 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 199365 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 18775 |  | 0 |  | 16480 |  |  |  | 17720 |  |  |  | 22120 |  |  |  | 24340 | 0 |  | 320 | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2407118A | 313616.15 | F21P1 AMHS Power Panel | 4533 | C |  | NUUO 6 DP System Installation | 45492 | 2024/7/22 2024/7/31 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | R1: Changing remark to align with template | [13 empty] | 313616.15 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 313616.15 |  |  | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2307018A | 311030 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2190 | C |  | Consolidated Electrical Distributors | 45113 | 45133 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 311030 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 199122.5 |  | 111907.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311017A | 310000 | Tool Interconnection Project (Main Tool & Module) | 490 | P |  | labor for install cabinet anchor | 45237 | 45245 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 310000 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 62000 | 0 |  | 0 |  |  |  | 148800 |  |  |  | 12400 | [5 empty] | 86800 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC24C006 | USCSB2406050A | 309480 | WWT B side Project | 4275 | C |  | FAB B WWT Observation and CA Service | 45450 | 45456 | [6 empty] | M Consultants, LLC BDA M-Engineering | PR Approved | PO Approved | [14 empty] | 109836 | 0.35491 | 199644 | 0 | 199644 | 309480 | [70 empty] | 70328 | 61896 | 39508 | - | 61896 | 61896 | 61896 | 61896
Base-Build | VOC | Southland | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | Housekeeping | USC21C007 | USCSB2304053A | 308247.04 | F21P1 VOC package （Installation ) | 1892 | C |  | LOW NOX VOC Burner Change Out & Clean Harbor | 45036 | 45061 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 308247.04 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 54415 |  | 102998 | 0 | 0 | 0 |  | 0 | 78818 | 9337.14 | 0 | 0 | 3501.41 |  | 0 | 0 | 0 |  | 0 |  | 59177.49 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312055A | 308225.43 | Tool Interconnection Project (Main Tool & Module) | 601 | P |  | KPE603-S T&M Installation for pipes (SS, PVC, PVDF, PP) Ball Valves, Pipe insulation, Cut Beam | 45274 | 45279 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 308225.43 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 308225.43 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2209033A | 308016.58 | F21P1 Chemical & WCCS package | 1485 | C |  | Manifold Boxes | 44834 | 44852 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  | 20% upon received material and approved submittal-Net 30 days-after acceptance; 60% on delivery with evidence-Net 30 days-after acceptance; 20% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 305637.1 | 0.99227 | 2379.48 | 0 | 2379.48 | 0 | [26 empty] | 305637.1 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 2379.48 |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309137A | 307526.42 | F21P1-0404_H_labor for 50 tools_MICU | 2608 | C |  | TW E2 Hookup GF Welding Machine_6 purchase | 45190 | 45195 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 307526.42 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 307526.42 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USC2109015A | 305828 | F21P1 UPW | 17 | P | -01 | tank,FRP | 2021/9/26 2021/11/5 | 2021/10/1 2021/11/16 | 49948 | 255880 | V | V |  |  | HORIBA Instruments Incorporated | PR Approved | PO Approved | 11/10專案回覆待確認運費是否MICU負擔 11/16PO異動簽核中 | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | Cherry Chang | DDP | 24 months warranty after received. | Chia-Yi Chang | Cherry Chang | N |  | Matt |  | N | 5000 |  | 305828 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 305828 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | 5G | CCE | The budget execution does not pertain to this project | LV PDS | Low Voltage | Electrical | M+L | USC22C010 | USCSB2208016A | 305397.2 | F21 P1 LSC CMS and DPM 5G System | 1453 | C |  | F21P1 PDS Cabling and equipment installation | 44800 | 44816 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 95% progress payment-Net 30 days-after acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Mirielli Terres | Yi En Wong | [6 empty] | Y | 304827.48 | 0.99813 | 569.72 | 0 | 569.72 | 0 | [18 empty] | 76349.3 |  | 114069.02 |  | 45809.58 |  | 32649.72 |  | 35949.86 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | -
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Labor | USC24C008 | USCSB2404150A | 305092 | UPW B Side Project | 4134 | C |  | Outstanding Incentive Change Requests | 45401 | 45451 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 305092 | 0 | 305092 | 0 | [54 empty] | 0 |  | 0 | [12 empty] | 152546 |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC24C005 | USCSB2404155A | 304000 | Chemical & WCCS B Side Project | 4139 | C |  | 信紘人力-點工人力(8人4個月) | 45402 | 45405 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 152000 | 0.5 | 152000 | 152000 | 0 | 76000 | [54 empty] | 0 |  | 0 |  |  |  |  | 76000 |  |  |  | 76000 | 76000 |  |  | 76000 | 76000 | 76000 |  | - |  | 0 | 0
Others | Leak Panel | Material |  |  | Others |  |  | USC23C013 | USCSB2303025A | 304000 | Hookup Leak Panel for AZQR&EBO | 1767 | C |  | EBO Leak Panel | 44989 | 45034 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 60800 | 0.2 | 243200 | 0 | 243200 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 60800 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403110A | 303822 | Tool Interconnection Project (Main Tool & Other Vendors) | 926 | P |  | KPE607-S CW and Gas Piping Labor | 45377 | 45392 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 303822 | 0 | 303822 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403108A | 303822 | Tool Interconnection Project (Main Tool & Other Vendors) | 924 | P |  | KPE604-S CW and Gas Piping Labor | 45377 | 45392 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 303822 | 303822 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403109A | 303822 | Tool Interconnection Project (Main Tool & Other Vendors) | 925 | P |  | KPE606-S CW and Gas Piping Installation | 45377 | 45392 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 303822 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [13 empty] | 303822 | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2308129A | 303100 | F21P1-0404_H_labor for 50 tools_MICU | 2426 | C |  | TangCheng Hardware | 45160 | 45169 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 300100 | 0.9901 | 3000 | 0 | 3000 | 0 | [40 empty] | 0 | 0 | 300100 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2306089A | 303006.77 | F21 TMAH System | 2122 | C |  | WWT-PSS-TrainA material | 45098 | 45125 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 303006.77 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 240098.46 |  | 0 | 9495.82 | 6599.9 | 2234.4 |  | 0 | 0 | 0 | 0 | 0 |  | 44578.19 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | CCTV |  | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC24C007 | USCSB2406076A | 300779 | Low Voltage B Side Project | 4308 | C |  | F21-P1_B-SIDE CCTV & ACCESS (L20 HPM) | 45457 | 45460 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 300779 | 148379.28 | 152399.72 | 285740.05 | [71 empty] | 150389.5 |  | - | 135350.55 |  | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2310081A | 300000 | WWT Change Order (Piping) | 2741 | C |  | Taiwan experienced wrokers-help on WWT pipng fixed in FAB A site. | 45211 | 45223 | [6 empty] | Gejinsin Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 300000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 300000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | TMAH | Labor | Main Contract Scope | WWT | WWT | Electrical | Labor | USC21C011 | USCSB2402117A | 300000 | F21 TMAH System | 3555 | C |  | 2000 Gold T&M-Labor 30days 10ppl | 45335 | 45337 | [6 empty] | 2000 GOLD LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 29850 | 0.0995 | 270150 | 0 | 270150 | 26865 | [49 empty] | 0 |  |  | 0 | 18350 | 0 |  | 0 | [5 empty] | 11500 | [8 empty] | 14925 |  | - | 11940 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310027A | 300000 | F21P1-0404_H_labor for 50 tools_MICU | 2690 | C |  | Hueng Luei Galvanized Dust (Air ship) | 45203 | 45219 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 300000 | 0 | 300000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C006 | USCSB2211009A | 300000 | F21P1 Slurry package | 1544 | C |  | F21 General Labor and Housekeeping Service | 44873 | 44875 | [6 empty] | BHTC Arizona, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 300000 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 2340 | 29967.5 | 27462.5 |  | 75527.5 | 81917.5 | 54698.75 |  | 28086.25 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC22C001 | USCSB2310107A | 300000 | F21 P1 Office and WH Security and CCTV | 2769 | C |  | F21 CCTV Engineering | 45216 | 45224 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 300000 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 223563.07 | 3700 | 0 | 72736.93 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C059 | USCSB2403159A | 300000 | F21P1 Foundation T&M | 3858 | C |  | 3rd MMI tile alignment T&M | 45366 | 45399 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 192088.4 | 0.64029 | 107911.6 | 0 | 107911.6 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 188624.4 |  |  |  | 3464 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2307050A | 300000 | F21P1 AMAT Interconnection | 2219 | C |  | AMAT Interconnect- GREENBERRY INDUSTRICAL – MECHANICAL LABOR | 45119 | 45128 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 263755.23 | 0.87918 | 36244.77 | 0 | 36244.77 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 69298.81 | 0 | 0 | 0 |  |  | 0 | 0 | 194456.42 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C003 | USCSB2205012A | 300000 | F21P1 UPW | 1376 | C |  | General Laborer and Housekeeping Service | 44692 | 44697 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y | [6 empty] | 255464 | 0.85155 | 44536 | 0 | 44536 | 0 | [8 empty] | 1800 | 1755 |  | 24915 | 25455 | 24832.5 | 52050 | 27419 | 29130 | 68107.5 | [10 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C011 | USCSB2304045A | 300000 | F21 TMAH System | 1885 | C |  | F21 General Labor and Housekeeping Service | 45034 | 45037 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 300000 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 292800 |  | 0 |  | 7200 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405058A | 299445.93 | WWT B side Project | 4063 | C |  | WWT Drain PP_20240508 (B Side) | 45421 | 45434 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 299445.93 | 0 | 299445.93 | 299445.93 | [56 empty] | 0 | [14 empty] | 59889.186 |  | - | 59889.186 | 59889.186 | 59889.186 | 59889.186
[5 empty] | Others |  |  | USC22C025 | USCSB2410029A | 299045.58 | Tool Hookup Material (UPW&Chemical) | 4972 | C |  | DP Design Change_AMHS_6/7 batch | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 299045.58 | 0 | 299045.58 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2304078A | 298813.47 | F21P1 WWT package （USA EQ-FRP tank) | 1916 | C |  | WWT Triazole tanks | 45043 | 45054 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 298813.47 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 298813.47 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2306004A | 298800 | Tool Interconnection Project (Main Tool & Module) | 289 | P |  | Joseph Turley-Project Coordinator, Clayton Thurber-Superintendent , Marco Galvan Jr-Project Coordinator (6 month) | 45079 | 45084 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 276801.08 | 0.92638 | 21998.92 | 0 | 21998.92 | 0 | [33 empty] | 0 | 66852.76 |  | 51489.88 |  | 42823.36 |  | 33296 | 0 | 31625 | 0 |  | 0 | 20583.8 | 0 | 30130.28 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2303013A | 295810 | F21P1 WWT package （USA EQ-FRP tank) | 1755 | C |  | CO for Alliance | 44987 | 45001 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 295810 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 295810 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC21C005 | USCSB2311140A | 295688.64 | F21P1 Chemical & WCCS package | 2990 | C |  | CDS F21 Lorry A Solvent room Aegis/Co2 installation and inspection | 45260 | 45276 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 280904.21 | 0.95 | 14784.43 | 0 | 14784.43 | 14784.43 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 236550.91 | 0 |  | 0 |  |  |  |  | 44353.3 | 44353.3 | [8 empty] | 14784.43 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2308101A | 294133 | WWT Change Order (Piping) | 2398 | C |  | TSMC UPW-8-127 WWT LB2 Chemical Piping-Group 2 | 45156 | 45169 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 252955 | 0.86 | 41178 | 0 | 41178 | 35413.7 | [40 empty] | 0 | 0 | 0 | 0 | 73533 | 0 | 0 | 111771 | 0 | 0 |  |  | 0 | 0 | 26472 |  | 0 |  |  |  |  | 14706.65 |  |  | 41179 | 29413.3 |  |  |  | 29413.3 |  | 12647.75 |  | - | 12647.75 | 10118.2 | 0 | 0
Base-Build | Base-Build | MMI | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C045 | USCSB2310169A | 294064 | WWT Change Order (Piping) | 2823 | C |  | Material receiving, off-loading, laydown labor | 45225 | 45233 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 294064 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 | 294064 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC24C005 | USCSB2404142A | 294000 | Chemical & WCCS B Side Project | 4126 | C |  | F21 B side L20 Tray安裝工程 | 45400 | 45401 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 279300 | 0.95 | 14700 | 0 | 14700 | 14700 | [54 empty] | 0 |  | 0 |  |  |  |  | 147000 | 235200 |  |  | 132300 |  |  |  |  | 44100 | 0 |  | - | 14700 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2305013A | 293968.24 | Tool Interconnection Project (Main Tool & Module) | 280 | P |  | ZIP TIE | 45073 | 45084 | [6 empty] | KunShan Doodle Electromechanical Science Technology Co.,Ltd. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 293968.24 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 44095.24 |  |  | 102888.88 |  |  | 0 | 146984.12 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC22C036 | USC2301003A | 292800 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 262 | P |  | Superintendent (Tool Hook Up) | 44943 | 44952 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 292800 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 66971.06 |  | 70052 |  | 35941.12 |  | 72095.43 |  | 47740.39 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Triazole | MIMO/Rigging | Main Contract Scope | WWT | WWT | Steel | M+L | USC22C022 | USCSB2306101A | 292297 | F21P1 Triazole treatment system | 2134 | C |  | WWT Triazole steels and move-in | 45098 | 45126 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 292297 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 87689.1 |  | 87689 | 0 | 58549 | 0 |  | 0 | 0 | 0 | 43754 | 0 |  |  | 14615.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C013 | USCSB2312193A | 292071.62 | F21P1 QR Lab Security & CCTV | 3180 | C |  | F21 CCD Room Security CCTV Engineering | 2023/12/29 2024/8/12 | 2024/3/6 2024/8/12 | -91076.06 | 383147.68 | V |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PR R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Ta Wei Wang | [11 empty] | 292071.62 | 1 | 0 | 0 | 0 | 72798.05 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 210378.79 |  |  |  |  | 30652 | 81692.83 |  |  | 30652 |  |  |  | 38315 |  | 19157.38 |  | - | 19157.38 | 19157.38 | 15325.91
Others | AMHS |  |  |  | AMHS |  |  | USC22C031 | USCSB2407122A | 290250 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4536 | C |  | AMHS B Side HPM Tray Relocation Installation | 45493 | 45502 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 121275 | 0.41783 | 168975 | 154462.5 | 14512.5 | 0 | [70 empty] | 121275 |  |  | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C026 | USCSB2210028A | 290183.5 | F21P1-0423_H_Unistrut Support Frame_MICU | 1511 | C |  | MISC UNDERFLOOR/RAISED UNDERFLOOR PREFAB | 44853 | 44858 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 290183.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 290183.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC21C005 | USCSB2406081A | 288900 | F21P1 Chemical & WCCS package | 4312 | C |  | F21 A side CPVC 未完成工作0613 | 45457 | 45463 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved | [14 empty] | 57780 | 0.2 | 231120 | 57780 | 173340 | 0 | [73 empty] | 57780 |  |  | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406004A | 288643.18 | Chemical & WCCS B Side Project | 4233 | C |  | 彰京SUS-0531 | 45444 | 45447 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 288643.18 | 0 | 288643.18 | 0 | [73 empty] | - |  |  | 0
Base-Build | Slurry | CRG | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC24C005 | USCSB2404023A | 288517 | Chemical & WCCS B Side Project | 4019 | C |  | B-side L30 SDS scope | 45384 | 45395 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | 0 | [11 empty] | 288517 | 1 | 0 | 0 | 0 | 14425.85 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 274091.15 |  |  | 288517 |  |  | 14425.85 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310089A | 288348.47 | F21P1-0404_H_labor for 50 tools_MICU | 2750 | C |  | wire cable 3/4 WG for Third Industry | 45213 | 45234 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 81011.79 | 0.28095 | 207336.68 | 0 | 207336.68 | 0 | [42 empty] | 0 | 0 |  | 41392.1 | 0 | 0 | 18017.25 | 0 | 21602.44 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | DCR Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2303054A | 287100 | F21P1 Slurry package | 1794 | C |  | Slurry L10 Model Change | 44999 | 45011 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 279960 | 0.97513 | 7140 | 0 | 7140 | 0 | [28 empty] | 0 | 47850 | 38280 |  |  | 0 |  |  |  |  | 133980 |  | 59850 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C006 | USCSB2410023A | 285092.78 | WWT B side Project | 4966 | C |  | This is Tsmc clean trench project which issue a PO to us to have MICU pay their vendor first. | 45568 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 285092.78 | 0 | 285092.78 | 0
Base-Build | Slurry | Labor | 0 | 0 | Chemical | Steel | Labor | USC21C009 | USCSB2312113A | 283945.4 | F21P1 WWT package (Installation and 2 batch tanks) | 3103 | C |  | USC21C006 SLURRY B SIDE L30 bridge support | 45276 | 45281 | [6 empty] | SDB, Inc. dba SDB Contracting Services | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 283945.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 227156.32 |  |  |  | 42591.81 |  |  | 56789.08 | 14197.27 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Labor | USC24C006 | USCSB2408020A | 283251.53 | WWT B side Project | 4616 | C |  | T&M to have (達鑫)Daxin involve in A+B side punch fixed(2024/07/01~2024/12/31)(management fee and profit、Miscellaneous expenses | 2024/8/6 2024/8/21 | 2024/8/22 2024/9/12 | -102700 | 385951.53 | V |  |  | V | Daxin Energy Engineering Co., Ltd. | PR Approved | PO Approved | PR R1:As per purchasing team David to update the price. WO R1: To remove rental, housing, plane ticket, and add Remark 6.10 | [13 empty] | 0 | 0 | 283251.53 | 0 | 283251.53 | [74 empty] | -
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2406128A | 282887.28 | F21P1 AMAT Interconnection | 4367 | C |  | AMAT TW trade P1B 1st 24 machine material | 45468 | 45471 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 282887.28 | 254598.55 | 28288.73 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | E2 | USC21C009 | USCSB2404122A | 282500 | F21P1 WWT package (Installation and 2 batch tanks) | 4107 | C |  | WWT pipe installation | 45398 | 45399 | [6 empty] | Full Money Technology Ltd. | PR Approved | PO Approved | [14 empty] | 148000 | 0.52389 | 134500 | 0 | 134500 | 54760 | [54 empty] | 0 |  | 0 |  |  |  | 37000 | 42375 |  |  | 37000 | 42375 |  |  | 37000 | 42375 |  | 18500 | 37000 | - | 18500 | 17760 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC24C005 | USCSB2405066A | 281782 | Chemical & WCCS B Side Project | 4086 | C |  | 6181 TSMC UPW - 8-203 TR-2 Chem Drains CO | 45423 | 45441 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 173634 | 0.6162 | 108148 | 94059 | 14089 | 19711.85 | [56 empty] | 0 | [11 empty] | 133790 | 374525.15 |  |  | 39844 | - |  |  | 19711.85
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2303057A | 280793 | F21P1 UPW | 1797 | C |  | Skid repair & membrane installtion | 45000 | 45035 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 280793 | 0 | 280793 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 280793 |  |  |  | 280793 | [5 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402158A | 279900.97 | F21P1-0404_H_labor for 50 tools_MICU | 3590 | C |  | E-OPS Staffing Pricing Worksheet QA Renewal 3/6 months | 45338 | 45343 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 23346 | 0.083408 | 256554.97 | 23677.5 | 232877.47 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 6552 | 16794 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404011A | 278408 | Tool Interconnection Project (Main Tool & Other Vendors) | 966 | P |  | KPE604-S Inventory Labor | 45385 | 45393 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 278408 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 278408 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404015A | 278408 | Tool Interconnection Project (Main Tool & Other Vendors) | 970 | P |  | KPE607-S Inventory Labor | 45385 | 45393 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 278408 | 0 | 278408 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | 光阻櫃 | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC22C012 | USCSB2210010A | 278064.52 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1494 | C |  | Rich - Stainless steel mask bank room shelf and cart | 44839 | 44844 | [6 empty] | RUI QI STAINLESS STEEL FIRM | PR Approved | PO Approved |  | 100% by received-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 278064.52 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 278064.52 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USC2111049A | 277255.58 | F21P1 Chemical & WCCS package | 50 | P |  | Valves for WCCS | 44523 | 44532 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | 專案回覆待確認中(CF)，trade term 修改DAP 12/3 採購單成立 | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh | DAP | 1 year from ship date | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 277255.58 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 232839.32 | [19 empty] | 0 |  |  |  |  | 0 | 2115.06 | 23265.66 | 19035.54 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2404048A | 276676.69 | F21P1 WWT package (Installation and 2 batch tanks) | 4042 | C |  | WWT_ FAB LB2 / WRC L10_Acid/Chemical Area Safety Paint | 45386 | 45419 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 276676.69 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 41501.5035 | 276676.69 |  |  | 41501.5035 |  |  |  | 41501.5035 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Triazole | Labor | Main Contract Scope | WWT | WWT | Electrical | M+L | USC22C022 | USCSB2402057A | 275000 | F21P1 Triazole treatment system | 3499 | C |  | WWT-Triazole Electrical | 45329 | 45336 | [6 empty] | 2000 GOLD LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 275000 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 275000 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2303018A | 274752 | F21P1-0404_H_Hallway plate install_MICU | 1760 | C |  | Protection material management | 44988 | 45034 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 274752 | 0 | 274752 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | CO Scope (adding/additional scope) | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2406080A | 274320 | F21P1 Chemical & WCCS package | 4311 | C |  | FAB CO2 System Permit and Inspection | 45457 | 45463 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved | [14 empty] | 0 | 0 | 274320 | 0 | 274320 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Harder | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2109014A | 274050 | F21P1 Chemical & WCCS package | 1288 | C |  | CDS Mechancial Work Pre-constru Indirect Labor | 44462 | 44468 | [6 empty] | Harder Mechanical Contractors, Inc | PR Approved | PO Approved |  | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | CHEM |  | Henry |  | Y | 5005 |  | 274050 | 1 | 0 | 0 | 0 | 0 |  | 61335 | 67920.9 | 101908.9 | 42885.2 | [23 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Labor | USC24C005 | USCSB2408166A | 274022.36 | Chemical & WCCS B Side Project | 4787 | C |  | Proposal TSMC-015 @ ICP_MASS_Side B_ Total Boxes_CPVC_SUS_PFA_Support Installations_Side A. Paint_(Rev.1)_Batch 1/2 | 45535 | 45546 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 274022.36 | 274022.36 | 0 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311103A | 273885.6 | F21P1-0404_H_labor for 50 tools_MICU | 2954 | C | -02 | Industries pipe label, shared material | 2023/11/22 2024/1/17 | 2023/12/12 2023/12/16 2024/1/24 | -2133.4 | 276019 |  |  |  |  | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved | R1: Remark Information Correction: Quotation No., Completion Date, Trade Term. R2: The price of this order has been decreased due to actual quantity changes. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 273885.6 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 273885.6 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC24C005 | USCSB2404183A | 272520 | Chemical & WCCS B Side Project | 4164 | C |  | Chemical FAB A and Lorry CA and Observation | 45406 | 45419 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 272520 | 131522 | 140998 | 272520 | [54 empty] | 0 |  | 0 | [14 empty] | 272520 |  | - | 0 | 0 | 0
Base-Build | VOC | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C007 | USCSB2305064A | 271432.4 | F21P1 VOC package （Installation ) | 1986 | C |  | F21 VOC Low nox Electrical Work | 2023/5/13 2024/8/1 | 2023/5/23 2024/8/1 | -16567.6 | 288000 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | R1: Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 271432.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 173036 | 87861.4 |  |  | 0 | 0 | 0 | 0 | 10535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 2160 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Labor | USC21C005 | USCSB2406129A | 269677 | F21P1 Chemical & WCCS package | 4368 | C |  | 捨得人力-點工人力(13人 6-8月) | 2024/6/25 2024/6/28 | 45482 | [6 empty] | AUCAN INC | PR Approved | PO Approved | PR R1:Due to vendor update the quote. | [13 empty] | 0 | 0 | 269677 | 269677 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Steel | Material | USC21C005 | USCSB2303088A | 269367 | F21P1 Chemical & WCCS package | 1825 | C |  | L20 Unistruts Rack | 45009 | 45016 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 269367 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 248037 | 0 | 21330 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2302026A | 269319.5 | F21P1-0404_H_Hallway plate install_MICU | 1707 | C |  | Barricade material | 44967 | 44972 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 269319.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 201989.62 | 0 | [6 empty] | 67329.88 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC23C045 | USCSB2311069A | 269240 | WWT Change Order (Piping) | 2923 | C | -01 | WWT-HYC air testing manpower | 2023/11/16 2024/4/30 | 2023/11/27 2024/5/1 | -129520 | 398760 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: As per Sam talked with Hua Yi:Shulan to descope PR USCSB2311069,其餘工程分其他下包，不得再請款 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 269240 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 269240 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 13462 |  |  |  | 13462 |  |  |  | 19938 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C006 | USCSB2312123A | 266747.64 | F21P1 Slurry package | 3114 | C |  | Urgent: CDS CED MIC A side 1 of 2 per Paul | 45276 | 45282 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 266747.64 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 266620.65 | 126.99 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC22C037 | USCSB2407151A | 265272 | F21P1 Screen Main tool interconnection | 4576 | C |  | WET_ETC: SEE LIST OF TOOLS: BULK MATERIALS FOR P1B (HMT) | 45499 | 45511 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 265272 | 265272 | 0 | [74 empty] | -
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Electrical | Labor | USC24C006 | USCSB2404114A | 263304.8 | WWT B side Project | 4099 | C | -01 | MU11304N035-R1-MICU Area B E2 manpower support for electricity personnel | 2024/4/15 2024/5/29 | 2024/4/18 2024/6/3 | 5500 | 257804.8 | V |  |  |  | Mega Union Technology Inc. | PR Approved | PO Approved | R1: As per engineer to update quote add tools fee. | [13 empty] | 105703.52 | 0.40145 | 157601.28 | 0 | 157601.28 | 263304.8 | [54 empty] | 0 |  | 0 | [13 empty] | 105703.52 | 52660.96 |  | - | 52660.96 | 52660.96 | 52660.96 | 52660.96
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC24C006 | USCSB2407108A | 262000 | WWT B side Project | 4523 | C |  | WWT 3rd Party QAQC Services | 45491 | 45492 | [6 empty] | Independent QA/QC Services Inc. | PR Approved | PO Approved | [14 empty] | 101788 | 0.3885 | 160212 | 37618 | 122594 | 0 | [70 empty] | 64170 | 0 |  | 37618 | 0 | 0 | 0 | 0
Base-Build | WWT | Site Expense | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2403209A | 261357 | F21 TMAH System | 3904 | C |  | WWT009_B 區機台租賃_Mega(8 month) | 2024/3/21 2024/4/2 | 45387 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 261357 | 0 | 261357 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 39203.55 |  |  |  | 39203.55 |  |  |  | 39203.55 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | VOC | Southland | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2308060A | 257361 | F21P1 VOC package （Installation ) | 2358 | C |  | F21 P1 VOC Engineering | 45148 | 45184 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 257361 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 257361 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401014A | 257124.72 | F21P1-0404_H_labor for 50 tools_MICU | 3205 | C |  | HK TUN YI Equipment Rental for 3 months | 45295 | 45310 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 257124.72 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 64281.18 |  |  |  | 192843.54 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407124A | 255779.7 | TSMC Fab 21 P1B Tool Hook Up | 4538 | C |  | 8 HK MIMO team members renewal for 3 months | 45493 | 45499 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | [14 empty] | 58137.05 | 0.22729 | 197642.65 | 65501.35 | 132141.3 | 0 | [72 empty] | 5144.03 | 52993.02 |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2310157A | 255034.54 | Tool Hookup Material (UPW&Chemical) | 2812 | C |  | HK UPW PVDF PP Materials | 45223 | 45227 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 255034.54 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 5906.73 | 76765.6 |  |  | 19374.32 | 76746.82 | 35137.49 |  | 38557.08 |  | 2525.38 |  | 21.12 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | NUUO | Main Contract Scope | WWT | WWT | Electrical | Labor | USC21C009 | USCSB2403026A | 255000 | F21P1 WWT package (Installation and 2 batch tanks) | 3735 | C |  | WWT Lorry CCB Fiber, Power, Control Pull & Termination | 45353 | 45356 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 255000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 255000 |  |  |  |  | 38250 |  |  |  | 38250 |  |  |  | 38250 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2210050A | 254247.61 | F21P1 Slurry package | 1532 | C |  | L30 Raised Floor Pipe Channel | 44862 | 44867 | [6 empty] | SDB, Inc. dba SDB Contracting Services | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [5 empty] | 5005 | Y | 254247.61 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 79800 |  | 161735.23 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 12712.38 |  | 0 | [8 empty] | 228822.85 |  |  |  | 12712.38 |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC23C045 | USCSB2404176A | 254073 | WWT Change Order (Piping) | 4157 | C |  | WWT-A side EOR CA service for WRC and FAB | 45405 | 45413 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 254073 | 0 | 254073 | 254073 | [54 empty] | 0 |  | 0 |  |  |  |  | 38110.95 |  |  |  | 38110.95 |  |  |  | 38110.95 |  | 50814.6 |  | - | 50814.6 | 50814.6 | 50814.6 | 50814.6
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2210030A | 252900.42 | Tool Hookup Material (UPW&Chemical) | 1513 | C |  | Harrington-Chemical PVC | 44853 | 44855 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 252900.42 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 252900.42 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2406130A | 251593.05 | F21P1 AMAT Interconnection | 4369 | C |  | AMAT TW trade P1B 3th 33 machine material | 45469 | 45471 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 251593.05 | 251593.05 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Civil | Material | USC21C003 | USCSB2310106A | 250000 | F21P1 UPW | 2768 | C | -03 | construction of shaft wall on Mezzanine 1and 2 | 45216 | 2023/10/31 2023/11/6 2024/01/04 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved | Change of remark: remove original no. (15) and Liquidated damage - Add time & material R3: Indemnity Change |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 117163.87 | 0.46866 | 132836.13 | 0 | 132836.13 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 117163.87 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C059 | USCSB2310153A | 250000 | F21P1 Foundation T&M | 2809 | C |  | Foundation T&M for Greenberry | 45223 | 45238 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 199620.64 | 0.79848 | 50379.36 | 16786.5 | 33592.86 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 4061.25 |  |  |  | 126066.9 |  | 46253.12 | [5 empty] | 23239.37 | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Other Scope | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207021A | 250000 | F21P1 UPW | 201 | P |  | Painting | 44772 | 44776 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | Y | [6 empty] | 250000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 39932.73 |  | 210067.27 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2306052A | 250000 | F21P1 Module Tool Interconnection DIF1-2 | 2086 | C |  | DIFF: ELECTRICAL TRADE - ALL TOOLS SEE ATTACHED | 45091 | 45134 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 248046.38 | 0.99219 | 1953.62 | 0 | 1953.62 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 24081 | 0 |  | 0 | [9 empty] | 32154 |  | 6399.75 |  | 185411.63 | 0 |  | - | 0 | 0 | 0
Base-Build | Penetration Pipe | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC22C020 | USCSB2210014A | 249618 | F21P1 Penetration Pipe | 1497 | C |  | FAB L10, L20 HPM Drain Piping Penetration | 44841 | 44909 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-After acceptance; 5% after final completion-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 249618 | 0 | 249618 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USC2111027A | 249454.5 | F21P1 UPW | 41 | P |  | dissolved oxygen analyzers, Silica Analyzers | 44513 | 44519 | [6 empty] | Hach Company | PR Approved | PO Approved |  | 90% Received, 10% 60 days after acceptance, net 30 days | York Yeh | DDP Office | 2 year limited warranty | Chia-Yi Chang | York Yeh | N | 44540 | Matt |  | N | 5000 |  | 249454.5 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 124727.25 | [12 empty] | 119433.33 |  |  |  |  | 5293.92 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410052A | 248733.5 | Tool Hook Up E2 Trade Equipment Rental | 4994 | C |  | HK_JerYih_Equipment Rental_1st PO_End date 8/31/2024 | 45569 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 248733.5 | 0 | 248733.5 | 0
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C001 | USCSB2401075A | 248169.53 | F21 P1 Office and WH Security and CCTV | 3264 | C |  | F21 CCTV Engineering | 45303 | 45356 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 208731.91 | 0.84109 | 39437.62 | 0 | 39437.62 | 27298.66 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 235762 | 208731.91 | [8 empty] | 7445.09 |  | - | 7445.09 | 7445.09 | 0 | 4963.39
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403120A | 247415.57 | Tool Interconnection Project (Main Tool & Other Vendors) | 935 | P |  | KDSTSA DNS SCREEN INTERCONNECTS 2/12-3/21/2024 | 45378 | 45380 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 247415.57 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 247415.57 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | CO Scope (adding/additional scope) | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2309098A | 247266 | F21P1 UPW | 2571 | C |  | TSMC Fab 21 Phase Construction Administration Services | 45185 | 45191 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 222694 | 0.90063 | 24572 | 0 | 24572 | 0 | [40 empty] | 0 | 0 | 0 | 49453.2 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 89077.6 |  | 0 |  | 84163.2 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403021A | 246302.33 | Tool Interconnection Project (Main Tool & Other Vendors) | 847 | P | -01 | 5401010 l” PIPE P/E HP PVDF 230PSI 16.4’ LGTH SOLD IN BAGS OF 3 | 2024/3/7 2024/4/21 | 2024/3/13 2024/5/2 | 1367.94 | 244934.39 |  |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Updated quantity amount (original amnt 300) by 21 for line 3. Extra were shipped and PM decided to keep the extra 21 pieces. |  | Yikang Wang |  |  |  | 0 | [7 empty] | 246302.33 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 75640.95 |  | 170661.38 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC24C006 | USCSB2404201A | 245895 | WWT B side Project | 4181 | C |  | WWT - LSR(I)(A side) | 45408 | 45415 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 233600 | 0.95 | 12295 | 0 | 12295 | 11680 | [54 empty] | 0 |  | 0 |  |  |  |  | 36884.25 |  |  |  | 36884.25 | 233600 |  |  | 36884.25 |  | 0 |  | - | 0 | 0 | 0 | 11680
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C006 | USCSB2405063A | 245785 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 4066 | C |  | Area A EUV Cranes Bay 1 and 2 | 45422 | 45454 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 245785 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 245785 |  |  |  |  | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2205006A | 242719 | F21P1 WWT package (Installation and 2 batch tanks) | 1370 | C |  | SUNDT ICW Tank Piping | 44688 | 44693 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [5 empty] | 5005 |  | 242719 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 181634 |  |  |  | 0 |  |  |  |  | 0 | 48932.66 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 12152.34 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | The budget execution does not pertain to this project | Pipeline | WWT | Civil | M+L | USC21C003 | USCSB2203015A | 239659.84 | F21P1 UPW | 1350 | C |  | TSMC Water Frontage Main & 43rd Avenue Sewer Line Extension | 2022/3/28 2022/4/9 | 44657 | -37517 | 277176.84 |  | V |  |  | Degan Construction LLC | PR Approved | PO Approved | Rev01-removed item 1-Bond Payment. Bond is paid by AP note. 廠商修改報價單 | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 239659.84 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 239659.84 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2301047A | 238910 | CAP_E_F21P1 AMHS MML Seismic Foundation | 1664 | C |  | Seismic installation labor service | 44951 | 44966 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 73425 | 0.30733 | 165485 | 0 | 165485 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 23891 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3634 | 12725 |  | 0 |  |  |  | 8825 |  | 16150 |  |  |  | 4900 |  |  |  |  | 0 | 3300 | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306022A | 237806.89 | Tool Interconnection Project (Main Tool & Module) | 307 | P |  | KPAP01 S UMEC- LABOR | 45085 | 45100 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 237806.89 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 108894.37 | 80451.19 |  |  |  | 0 | 0 | 0 | 0 |  | 48461.33 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC22C014 | USCSB2208008A | 237481 | F21P1 AMHS Power Panel | 1445 | C | -01 | AMHS Typical Panel | 44786 | 44816 | -1345729 | 1583210 |  |  |  | V | Main Electric Supply Co, LLC | PR Approved | PO Approved | cancelled the PO because of lead time issue | 15% Prepayment; 85% by progress-Net 45 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 237481 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 237481 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2202007A | 236820.52 | F21P1 WWT package (Installation and 2 batch tanks) | 1332 | C |  | CS Tank changed order work | 44607 | 44615 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved | 原PO:USC2109014A追加(CS Tank changed order work) | 5% upon submittal IFA's-Net 30 Days; 5% upon submittal IFC's-Net 30 Days; 35% upon submittal detail drawings approved by the client-Net 30 Days; 50% upon ready to ship status-Net 30 Days; 5% after delivered and acceptance-Net 30 Days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N |  |  | 189638.7 | 0.80077 | 47181.82 | 0 | 47181.82 | 37927.74 | [6 empty] | 133758.7 | [9 empty] | 55880 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 11841.026 |  |  |  | 11841.026 |  |  |  | 11841.026 |  | 9481.935 |  | - | 9481.935 | 9481.935 | 9481.935 | 0
Base-Build | Chemical | MMI | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2307129A | 234226 | F21P1 Chemical & WCCS package | 2291 | C | -01 | Fall Protection System at Lorry | 2023/7/28 2023/8/30 | 2023/8/3 2023/8/30 | -3280 | 237506 | V |  |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | Price Reduced to Honor Previous Discussion |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 234226 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 166644 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 58986.7 | 0 | 8595.3 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2404190A | 234118.03 | WWT B side Project | 4170 | C |  | WWT - B-Side CS Tank FRP Flange Coating and Spool Interconnections | 45407 | 45419 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 233935.16 | 0.99922 | 182.87 | 0 | 182.87 | 2316.6969 | [54 empty] | 0 |  | 0 |  |  |  |  | 35117.7045 | 46651.04 |  |  | 35117.7045 | 185018.65 |  |  | 35117.7045 | 2265.47 | 0 |  | - | 0 | 0 | 0 | 2316.6969
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2212018A | 232780 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1591 | C |  | Security Services | 44908 | 44917 | [6 empty] | Allied Universal Security Services | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 215248.56 | 0.92469 | 17531.44 | 0 | 17531.44 | 0 | [23 empty] | 1389.48 |  | 17827.12 |  |  | 17431.68 | 22288.6 |  |  |  | 0 | 35861.36 |  | 22158.9 |  |  |  | 22288.6 | 17930.68 | 0 | 0 | 17852.86 | 0 | 0 | 22288.6 | 17930.68 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2404206A | 231840 | F21P1 AMAT Interconnection | 4023 | C |  | May mid may- mid June Labor | 45409 | 45459 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 231840 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 197430 |  |  |  | 34410 |  |  | - |  |  | 0
Base-Build | UPW | CCE | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2211025A | 230320 | F21P1 UPW | 1559 | C |  | X line Temp Power RFQ 11_16 | 44883 | 44924 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 230320 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 218804 |  | 0 |  | 11516 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309005A | 230001.2 | F21P1-0404_H_labor for 50 tools_MICU | 2483 | C |  | TW E2 Hookup Gas hardware YAHO | 45170 | 45180 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 230001.12 | 1 | 0.08 | 0 | 0.08 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 144605.52 | 0 | 0 | 50865.6 | 0 | 0 |  | 34530 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | MIMO/Rigging |  |  | Others |  |  | USC23C002 | USCSB2301048A | 230000 | F21P1-0404_H_Hallway plate install_MICU | 1665 | C |  | 600pcs hallway iron plates for move-in | 44951 | 44967 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 230000 | 0 | 230000 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Material | USC21C013 | USCSB2110007A | 230000 | F21P1 AMC THC Monitoring System | 1296 | C |  | 帆宣_tsmc F21P1 轉輪中THC建置六點 | 44477 | 44487 | [6 empty] | Weltall Technology Corporation | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Martin |  | ? |  |  | 207000 | 0.9 | 23000 | 0 | 23000 | 23000 |  |  |  |  | 34500 | [13 empty] | 172500 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 |  | 0 | 23000
Base-Build | VOC | Labor | The budget execution does not pertain to this project | VOC | Low Voltage | Electrical | M+L | USC22C013 | USCSB2402055A | 229358 | F21P1 QR Lab Security & CCTV | 3497 | C |  | VOC Extending General Conditions(CO # 31) | 45329 | 45337 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 229358 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 124232.86 |  |  |  | 105125.14 | [10 empty] | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407017A | 229088 | Tool Interconnection Project (Main Tool & Other Vendors) | 1154 | P |  | KPAN05-S PVC Piping Labor | 45489 | 45492 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 229088 | 0 | 229088 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407019A | 229088 | Tool Interconnection Project (Main Tool & Other Vendors) | 1156 | P |  | KPAN06-S PVC Piping Labor | 45489 | 45492 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 229088 | 0 | 229088 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2306012A | 227783.78 | F21P1 Chemical & WCCS package | 2046 | C |  | Flame arresters | 45080 | 45090 | [6 empty] | Caltrol Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 227783.78 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 227783.78 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | MA-TEK | Labor |  |  | Others |  |  | USC23C037 | USCSB2305050A | 227190 | MA-TEK AZ Lab Project | 1975 | C |  | Design Build for MA-TEK | 45058 | 45063 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 199494 | 0.87809 | 27696 | 0 | 27696 | 0 | [33 empty] | 0 | 53688 |  | 53688 |  | 84249 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 7869 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2408027A | 227175.6 | F21P1 AMHS Wiring Work Outline | 4622 | C |  | L30 Ladder Tray to 3in Conduit Replacement | 45511 | 45517 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 227175.6 | 1 | 0 | 227175.6 | -227175.6 | [74 empty] | 227175.6
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2307091A | 226927 | WWT Change Order (Piping) | 2257 | C |  | 8-115 WWT & Reclaim System Chemical Scope | 45127 | 45139 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 197428 | 0.87001 | 29499 | 0 | 29499 | 25665.64 | [39 empty] | 38626 | 0 | 49876 | 0 | 0 |  | 29501 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 52193 |  | 4539 |  |  |  |  | 22692.7 |  |  | 22693 | 22692.7 |  |  |  | 22692.7 |  | 9871.4 |  | - | 9871.4 | 5922.84 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304065A | 226738.04 | F21P1 WWT package (Installation and 2 batch tanks) | 1904 | C |  | WWT Lab Drain design-MU | 45038 | 45055 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 226738.04 | 0 | 226738.04 | 226738.04 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 34010.706 |  |  |  | 34010.706 |  |  |  | 34010.706 |  | 45347.608 |  | - | 45347.608 | 45347.608 | 45347.608 | 45347.608
Base-Build | VOC | Southland | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2308157A | 225843 | F21P1 VOC package （Installation ) | 2451 | C | -01 | F21 P1 VOC Change Order (southland)_1 | 2023/8/26 2023/9/21 | 2023/9/15 2023/9/21 | -6580 | 232423 | V | V | V |  | Southland Industries | PR Approved | PO Approved | R1:Request from responsible engineer to omit line 1 |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 225843 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 11292 | 0 | 214551 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2312170A | 225633 | F21P1 WWT package (Installation and 2 batch tanks) | 3158 | C |  | WWT-Train B FRP | 45282 | 45286 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 135379.8 | 0.6 | 90253.2 | 0 | 90253.2 | 54151.92 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 135379.8 |  | 0 |  |  |  |  | 33844.95 |  |  |  | 33844.95 |  |  |  | 33844.95 |  | 13537.98 |  | - | 13537.98 | 13537.98 | 13537.98 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2406071A | 225468.02 | Chemical & WCCS B Side Project | 4303 | C |  | Chemical Team Urgent Materials Wire First Priority (化學系統控制線材0611第一優先級購買) | 45456 | 45460 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 101962.42 | 0.45223 | 123505.6 | 225468.02 | -101962.42 | 0 | [73 empty] | 101962.42 |  |  | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC23C002 | USCSB2308009A | 225400 | F21P1-0404_H_Hallway plate install_MICU | 2312 | C | -01 | tsmc Fab21 - AMHS Technical Service | 2023/8/2 2023/8/14 | 2023/8/16 2023/8/18 | -96600 | 322000 |  |  |  |  | Marketech International Corp. | PR Approved | PO Approved | R1:Remove Tax Item in WO |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 225400 | 0 | 225400 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C009 | USCSB2303055A | 224570 | F21P1 WWT package (Installation and 2 batch tanks) | 1795 | C |  | CCB DCR piping | 44999 | 45015 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 213342 | 0.95 | 11228 | 0 | 11228 | 10667.1 | [28 empty] | 0 |  |  | 67371 |  | 0 |  | 101057 |  | 44914 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 10667.1
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2403216A | 224190 | F21P1 Module Tool Interconnection ETC1-3 | 3911 | C |  | 3 month Brycon Contract | 45372 | 45380 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 42942.06 | 0.19154 | 181247.94 | 0 | 181247.94 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 42942.06 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2311051A | 224158 | F21P1 Chemical & WCCS package | 2906 | C |  | CDS B side support Racks LB2/L30 | 45240 | 45266 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 224158 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 106475.04 | 72094.33 | 0 | 45588.63 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | PSS | The budget execution does not pertain to this project | Penetration Pipe | WWT | Civil | M+L | USC21C003 | USCSB2211021A | 223915 | F21P1 UPW | 1555 | C |  | Litho Embedded Pipes installation | 44882 | 44896 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 210793.75 | 0.9414 | 13121.25 | 0 | 13121.25 | 0 | [26 empty] | 22391.5 |  | 44782.99 |  |  |  |  | 0 | 33648.58 |  | 106946.36 |  |  |  | 0 | 0 | 3024.32 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC22C014 | USCSB2401088A | 223600 | F21P1 AMHS Power Panel | 3277 | C |  | AMHS B SIDE extra 8 DP Panels | 45304 | 45320 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 223600 | 0 | 223600 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2312044A | 223520 | F21P1 Slurry package | 3037 | C |  | CDS CO2 System, Lorry A, certify design and test. | 45267 | 45273 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 201168 | 0.9 | 22352 | 0 | 22352 | 0 | [45 empty] | 0 | 67056 | 0 | 0 | 0 | 134112 |  | 0 | 0 | 0 |  | 0 | [8 empty] | 22352 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Oil drain pipe work | Labor | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC22C009 | USCSB2206015A | 223292 | F21P1 230kV MTR Oil and Drain Pipe work | 1404 | C |  | F21P1 230kV MTR waste oil drain pipe | 44723 | 44725 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 100% by progress-t/t 30 days-after acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 212039.37 | 0.94961 | 11252.63 | 0 | 11252.63 | 10601.9685 | [24 empty] | 85942 |  |  |  | 47210.37 |  |  |  |  | 0 | [6 empty] | 78887 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 10601.9685
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Civil | M+L | USC21C003 | USCSB2209019A | 222645 | F21P1 UPW | 1471 | C | -01 | CWS-TSMC AZ Phase 1 | 44821 | 2022/9/20 2023/10/27 | -350000 | 572645 |  |  |  | V | Commercial Wallboard Systems, Inc | PR Approved | PO Approved | CWS cannot satisfy the workers' training for level 3 and 4./The rest of the work will goes to PCI. | 95% by progress-Net 30 days-After acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [5 empty] | Y | 166473.9 | 0.74771 | 56171.1 | 0 | 56171.1 | 0 | [28 empty] | 19076.4 |  | 58036.5 |  |  | 0 | 89361 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405171A | 222472.89 | Chemical & WCCS B Side Project | 4199 | C |  | Extremely Urgent_RFQ_MICU Chemical Team Request Material_05232024-1 | 45442 | 45446 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 221641.52 | 0.99626 | 831.37 | 1481.82 | -650.45 | 0 | [62 empty] | 39869.28 |  | 32579.79 |  | 99531.32 |  | 8111.95 |  | 39771 |  | 1778.18 | - |  |  | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2408098A | 222207.51 | F21P1 AMAT Interconnection | 4708 | C |  | AMAT_P1A_T&M_LABOR_Brycon_KCUVA1_KCUVA2_May_Jun | 45526 | 45533 | [6 empty] | Brycon Corporation | PR Approved | PO Approved | [14 empty] | 222207.51 | 1 | 0 | 222207.51 | -222207.51 | 0 | [73 empty] | 222207.51
Base-Build | Chemical | UMEC | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2402031A | 220941 | F21P1 Chemical & WCCS package | 3474 | C |  | CDS TSMC UPW 8-177 NH4 TMAH | 45325 | 45330 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 220941 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 209894 | 0 | 0 |  | 11047 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC21C005 | USCSB2403242A | 220800 | F21P1 Chemical & WCCS package | 3935 | C |  | CDS Leakage detection tape installation | 45377 | 45393 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 220800 | 0 | 220800 | 110400 | [52 empty] | 0 | 0 | 0 |  | 0 | [12 empty] | 110400 |  | 110400 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2205029A | 220448.25 | F21P1 UPW | 1391 | C | -01 | Hard support for electrical scope | 2022/5/27 2022/6/4 | 2022/5/31 2022/6/13 | -319320.99 | 539769.24 | V |  | V |  | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A-1的Change Order; 數量從555減少到225 | 95% by progress-net 30 days-after acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 220447.85 | 1 | 0.4 | 0 | 0.4 | 0 | [14 empty] | 19595 |  | 22534.71 |  | 19595.4 |  | 85239.99 |  |  |  | 24494.25 |  |  |  | 0 |  | 24494.25 |  |  | 0 | [6 empty] | 0 | 0 | 12737.01 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 11757.24 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C009 | USCSB2303059A | 220244 | F21P1 WWT package (Installation and 2 batch tanks) | 1798 | C |  | IA copper tubing | 45000 | 45013 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 209230 | 0.94999 | 11014 | 0 | 11014 | 10461.5 | [28 empty] | 0 |  |  |  |  | 0 |  | 88097 |  |  |  | 46251 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 30834 | 0 |  |  | 0 | 0 | 0 |  | 22024 |  |  |  |  | 11012.2 |  |  | 22024 | 11012.2 |  |  |  | 11012.2 |  | 0 |  | - | 0 | 0 | 0 | 10461.5
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C009 | USCSB2206011A | 220000 | F21P1 WWT package (Installation and 2 batch tanks) | 1401 | C |  | Safety Coordinators and Site Cleanup | 44721 | 44725 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 219648.49 | 0.9984 | 351.51 | 0 | 351.51 | 0 | [12 empty] | 66197.89 | 14554.85 | 24156.02 | 4816 | 5474 | 6048 | 7196 | [9 empty] | 0 |  | 83397.4 |  |  | 0 | [6 empty] | 0 | 0 | 7808.33 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409040A | 217997.65 | Tool Interconnection Project (Main Tool & Other Vendors) | 1241 | P |  | Interconnection RS Payroll from Feb 2024 to Jun 2024 | 45554 | 45562 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 217997.65 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 217997.65
Non-TSMC | EDG | Equipment |  |  | Others |  |  | USC22C003 | USCSB2307066A | 215440 | TSMC Fab21 Project Phase 1 EDG Package | 2233 | C |  | Additional crane cost&mobilization&re-direct unloading&reloading&storage cost for Bragg | 45122 | 45125 | [6 empty] | Delta Diversified Enterprises, Inc. | PR Approved | PO Approved | Will charge back to Fu Energy with 15% mgmt fee |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 204668 | 0.95 | 10772 | 10770.35 | 1.65 | 0 | [38 empty] | 204668 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG | Equipment |  |  | Others |  |  | USC22C003 | USCSB2306070A | 214766.65 | TSMC Fab21 Project Phase 1 EDG Package | 2103 | C |  | TSMC F21P1(AZ) MICU-DDE Change Orderx7 | 45093 | 45096 | [6 empty] | Delta Diversified Enterprises, Inc. | PR Approved | PO Approved | Back Charge to Customer Fu Energy with 10% Mark-up |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 204026.75 | 0.94999 | 10739.9 | 10739.9 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 204026.75 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2407098A | 213300 | F21P1 AMAT Interconnection | 4513 | C |  | Overtime Overage for NUUO | 45490 | 45497 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 213300 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 213300 |  |  | - |  |  | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2211007A | 211094.27 | F21P1 WWT package (Installation and 2 batch tanks) | 1542 | C |  | Lorry Bridge brackets Fabrication | 44869 | 44902 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 211094.27 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 211094.27 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303009A | 210133 | F21P1 Module Tool Interconnection DIF1-2 | 1751 | C |  | F21P1 DIF1 3 layer containmnet pipe and gas line pipe | 44987 | 45005 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 210133 | 0 | 210133 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405048A | 209376.5 | F21P1-0404_H_labor for 50 tools_MICU | 4055 | C |  | HK Scaffold services | 45420 | 45428 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 127720 | 0.61 | 81656.5 | 0 | 81656.5 | 0 | [56 empty] | 0 | [7 empty] | 127720 | [8 empty] | - |  |  | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Electrical | E2 | USC24C005 | USCSB2404157A | 208000 | Chemical & WCCS B Side Project | 4141 | C |  | 捨得人力-點工人力(13人/2個月) | 2024/4/20 2024/4/25 | 2024/5/10 2024/7/9 | [6 empty] | AUCAN INC | PR Approved | PO Approved | PR R1: D24N21001非內連線工程，且電力工程人力新增至13位已重新報價(不計入美國工資及費用)且廠商修改為捨得 WO R1: Completion date adjustment based on actual onboarding date | [13 empty] | 208000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 104000 |  |  |  | 104000 |  |  | 208000 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C001 | USCSB2205015A | 207173 | F21 P1 Office and WH Security and CCTV | 1378 | C |  | F21 Warehouse CCTV equipment | 44694 | 44697 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [5 empty] | 5000 |  | 189878 | 0.91652 | 17295 | 0 | 17295 | 0 | [14 empty] | 68368 |  |  |  | 55935 |  |  |  | 31077 | [5 empty] | 0 |  | 18784 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 15714 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C009 | USCSB2211004A | 203447.19 | F21P1 WWT package (Installation and 2 batch tanks) | 1539 | C |  | WWT Discharge box adding | 44868 | 44870 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | TSMC has reviewed MU costs directly, so MICU just adds up margin |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 203447.19 | 0 | 203447.19 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 30517.0785 |  |  |  | 30517.0785 |  |  |  | 30517.0785 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2305059A | 200218.1 | F21P1 UPW | 1981 | C |  | WRC Grounding | 45059 | 45091 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 200218.1 | 1 | 0 | 0 | 0 | 20021.8 | [33 empty] | 0 |  |  | 190207.2 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 10010.9 | [8 empty] | 0 |  | - | 10010.9 | 0 | 10010.9
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407031A | 200161.88 | Tool Interconnection Project (Main Tool & Other Vendors) | 1164 | P |  | 17: M-TIC-16L-TU-015: 1/2"*0.49" 304LSMLS Tube AP 4M/PC | 45496 | 45510 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 200161.88 | 200161.88 | 0 | [74 empty] | -
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Civil | M+L | USC22C021 | USCSB2403160A | 200050.78 | F21P1 Chemical Lab setup | 3859 | C |  | UPW-Mezzanine 3 & 4 Epoxy Floor Coating-Degan | 45366 | 45374 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 200050.78 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 200050.78 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2306047A | 200000 | F21P1 AMAT Interconnection | 2081 | C |  | AMAT Interconnect- Greenberry Mechanical Labor | 45090 | 45097 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 164308.2 | 0.82154 | 35691.8 | 0 | 35691.8 | 0 | [33 empty] | 0 |  |  |  |  | 53930.55 |  | 110377.65 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2204009A | 200000 | F21P1 UPW | 1358 | C |  | TSMC F21 AZ Structure Design and PE Stamp | 44677 | 44679 | [6 empty] | SYNERGY Engineering Consultants | PR Approved | PO Approved | Project Code changed from USC21C003 to USC22C006 (WO USCSB2205018A) | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y | [6 empty] | 95880 | 0.4794 | 104120 | 87600 | 16520 | 0 | [28 empty] | 0 |  | 95880 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing |  | UPW | Base-Build | Steel | Project Outsourcing (專案管理外包人力) | USC22C006 | USCSB2205018A | 200000 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1381 | C |  | TSMC F21 AZ Structure Design and PE Stamp | 44695 | 44696 | [6 empty] | SYNERGY Engineering Consultants | PR Approved | PO Approved | Project Code changed from USC21C003 to USC22C006 (Original WO USCSB2204009A) | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | N | [6 empty] | 154000 | 0.77 | 46000 | 0 | 46000 | 0 | [8 empty] | 104000 | [7 empty] | 50000 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC21C011 | USCSB2310069A | 200000 | F21 TMAH System | 2730 | C |  | F21 P1 CCTV Engineering | 45210 | 45224 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 200000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 200000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC21C008 | USCSB2308115A | 200000 | F21P1 CCTV & Security | 2412 | C |  | F21 P1 CCTV Engineering | 45157 | 45175 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 200000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 199875 | 0 | 0 | 0 |  | 0 | 0 | 0 | 125 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2309016A | 200000 | F21P1-0404_H_labor for 50 tools_MICU | 2493 | C | -02 | Chemical Hookup Material | 45175 | 2023/9/18 2023/9/21 2023/9/25 | -48073.72 | 248073.72 |  |  |  |  | Trusval Technology CO., LTD. | PR Approved | PO Approved | Ship-to Location Change; Price Discount due to other service related WO |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 200000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 200000 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2208001A | 200000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1440 | C |  | Transpak Offsite warehouse (storage & handling) | 44776 | 44782 | [6 empty] | Transpak, Inc. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 0 | 0 | 200000 | 0 | 200000 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC21C007 | USCSB2110002A | 199950 | F21P1 VOC package （Installation ) | 1292 | C |  | Pre-construction | 44471 | 44475 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  | 100% by progress, T/T 30 days. | York Yeh |  |  | Rui Ma | York Yeh | VOC | 44490 | Martin |  | Y | 5005 |  | 199950 | 1 | 0 | 0 | 0 | 0 |  | 66650 | 66650 | 66650 | [24 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | CCE | DCR Scope | WWT | WWT | Electrical | M+L | USC21C009 | USCSB2307133A | 199820.95 | F21P1 WWT package (Installation and 2 batch tanks) | 2295 | C |  | F21 P1 WWT Electric Engineering | 45135 | 45139 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 199820.95 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 199820.95 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | NUUO | 0 | 0 | Chemical | Electrical | Material | USC21C009 | USCSB2312192A | 199528.6 | F21P1 WWT package (Installation and 2 batch tanks) | 3179 | C |  | CDS chemical electric materials | 45289 | 45300 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 199528.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 199528.6 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2306002A | 199200 | Tool Interconnection Project (Main Tool & Module) | 287 | P |  | Daniel Gregoire-Superintendent (6 month), Tyler Smith-Project Coordinator (6 month) | 45079 | 45083 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 179572.47 | 0.90147 | 19627.53 | 0 | 19627.53 | 0 | [33 empty] | 0 | 30927.28 |  | 33332.45 |  | 31185 |  | 36424.25 | 0 | 15097.77 | 0 |  | 0 | 11855.72 | 0 | 20750 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C006 | USCSB2406031A | 199098.22 | F21P1 Slurry package | 4257 | C |  | F21P1 B Side material Harrington - CPVC fitting | 45448 | 45454 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 199098.22 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 179421.62 |  |  |  | 19676.6 |  |  |  |  | - |  |  | 0
Base-Build | Barcode | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C012 | USC2111010A | 198808.09 | F21 Barcode RFID System | 29 | P |  | Barcode 系統網路設備 | 44509 | 44517 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Hsiang Cheng Lee | York Yeh | N | 44520 | Martin |  | ? | 5000 |  | 198808.09 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 198808.09 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC24C006 | USCSB2404189A | 198642 | WWT B side Project | 4169 | C |  | WWT - Install (166) Embedded Pipe on B-Side for Litho Drains | 45407 | 45412 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 188709.9 | 0.95 | 9932.1 | 0 | 9932.1 | 27910.2685 | [54 empty] | 0 |  | 0 |  |  |  |  | 29796.3 |  |  |  | 29796.3 | 164178.05 |  |  | 29796.3 | 24531.85 | 8208.9025 |  | - | 8208.9025 | 11492.4635 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2308085A | 197483 | F21P1-0404_H_Hallway plate install_MICU | 2382 | C |  | Swap 1000 pcs tiles from PCI | 45154 | 45168 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 160554 | 0.813 | 36929 | 0 | 36929 | 0 | [40 empty] | 0 | 0 | 160554 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409086A | 196480 | TSMC Fab 21 P1B Tool Hook Up | 4898 | C |  | 250MCM 4C+G cable for Power 40 tools | 45556 | 45560 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 196480 | 0 | 196480 | 0 | [73 empty] | -
Base-Build | VOC |  |  |  | Low Voltage | Mechanical | Labor | USC24C007 | USCSB2406126A | 196000 | Low Voltage B Side Project | 4365 | C |  | F21-P1_B-Side mask room gas piping hookup_batch 1/2 | 45468 | 2024/7/3 2024/7/8 | -19235.7 | 215235.7 |  |  |  |  | Welmade Technology Corporation | PR Approved | PO Approved | R1: Per supplier request to split the amount to align with quote item# for USCSB2406126A & 127A - Total stays the same | [13 empty] | 0 | 0 | 196000 | 0 | 196000 | 196000 | [73 empty] | - | 29400 | 39200 | 117600 | 9800
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307014A | 195711.79 | Tool Interconnection Project (Main Tool & Module) | 349 | P |  | KPAN01-S UMEC LABOR PAY | 45136 | 45152 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 195711.79 | 0 | 195711.79 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306019A | 195711.79 | Tool Interconnection Project (Main Tool & Module) | 304 | P |  | KPAE01-S UMEC-LABOR | 45085 | 45100 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 195711.79 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 20957.86 | 40893.01 |  |  |  | 0 | 0 | 0 | 0 |  | 133860.92 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306023A | 195711.79 | Tool Interconnection Project (Main Tool & Module) | 308 | P |  | KPAN01-S UMEC LABOR | 45085 | 45100 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 195711.79 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2225.53 | 18432.02 |  |  |  | 0 | 0 | 0 | 0 |  | 175054.24 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Site Expense | Main Contract Scope | WWT | WWT | Mechanical | Site Expense | USC24C006 | USCSB2403302A | 195000 | WWT B side Project | 3994 | C |  | (B side)WWT Widos Welding Machine_20240329 | 45381 | 45387 | [6 empty] | Widos Taiwan Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 195000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 91395 |  | 103605 |  |  |  |  | 29250 |  |  |  | 29250 |  |  |  | 29250 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | AMC THC | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C013 | USCSB2402137A | 194291 | F21P1 AMC THC Monitoring System | 3573 | C |  | F21 EBO AMC Engineering | 45337 | 45370 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 162451.45 | 0.83612 | 31839.55 | 0 | 31839.55 | 27200.74 | [52 empty] | 0 | 0 | 0 |  | 42884.6 |  | 47789.35 |  |  |  | 39207.5 |  |  | 77717 | 27845 |  |  | 48573 | 4725 | 27200.74 |  | - | 0 |  | 0
Non-TSMC | Micron - Material |  |  |  | Others |  |  | USC24C001 | USCSB2406147A | 194050 | Micron - Chemical SOLBLE RN3000 | 4385 | C |  | SOLBLE RN3000 250kg x 10 drums for Micron Manassas facility, Virginia | 45471 | 2024/7/16 2024/7/19 | 2700 | 191350 |  |  |  |  | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved | [14 empty] | 194050 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 194050 | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401157A | 193530 | F21P1-0404_H_labor for 50 tools_MICU | 3342 | C |  | Wire MC AL Bare Ground for HK Power trade | 45311 | 45315 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 193530 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 193530 | 0 |  | - | 0 | 0 | 0
Others | AMHS | Outsourcing |  |  | AMHS |  |  | USC22C025 | USCSB2308056A | 193200 | AMHS TSMC Instrustructure and Branch Circuits | 2354 | C |  | Superintendent staffing | 45147 | 45156 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 193200 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 61274.94 |  | 30246.78 | 32813 | 31612.5 | 0 |  | 0 | 24592.39 | 0 | 12660.39 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC21C006 | USCSB2401233A | 192691.19 | F21P1 Slurry package | 3415 | C |  | CDS OE electrical work | 45317 | 45323 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 192691.19 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 192691.19 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2205025A | 192000 | F21P1 WWT package (Installation and 2 batch tanks) | 1387 | C |  | Outsourcing (area superintendent) | 44701 | 44704 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 192000 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 14879.91 |  | 28190.4 |  | 31200 |  | 28482.97 |  | 34956.8 |  | 38395.2 |  |  | 15894.72 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2208015A | 190627.32 | F21P1 UPW | 1452 | C | -02 | UPW 500 MCM Cable | 2022/8/26 2022/12/09 2022/12/20 | 2022/8/31 2022/12/14 2022/12/21 | -3038.52 | 193665.84 |  |  | V |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Quantities change/need to be added 100 pcs per first three items | 100% by shipment-after acceptance-net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 190626.69 | 1 | 0.63 | 0 | 0.63 | 0 | [23 empty] | 190626.69 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2403133A | 189853.88 | F21P1 AMAT Interconnection | 3835 | C |  | hose hook up/installation | 45364 | 45377 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 189853.88 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 189853.88 | [6 empty] | 0 |  | - | 0 | 0 | 0
Others | EUV Steel Plate | Labor |  |  | Others |  |  | USC23C058 | USCSB2309140A | 188859 | F21 EUV Steel Plates | 2611 | C |  | EUV Crane electrical disconnect panel and cable tray. | 45191 | 45203 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 188859 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 188859 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2308113A | 188856 | F21P1 WWT package (Installation and 2 batch tanks) | 2410 | C |  | Field Observation for WRC WWT | 45157 | 45180 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 56656.8 | 0.3 | 132199.2 | 0 | 132199.2 | 39659.76 | [40 empty] | 0 | 0 | 0 | 56656.8 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 18885.6 |  |  |  | 18885.6 |  |  |  | 18885.6 |  | 11331.36 |  | - | 11331.36 | 11331.36 | 5665.68 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409084A | 188511.12 | TSMC Fab 21 P1B Tool Hook Up | 4896 | C |  | 250MCM 4C+G cable for Power 28 tools | 45556 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 188511.12 | 0 | 188511.12 | 0 | [73 empty] | -
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2310182A | 188000 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2834 | C |  | AMHS Floor Recovery | 45227 | 45253 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 188000 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 71440 | 0 |  |  | 35720 | 0 | 35720 |  | 0 | [13 empty] | 45120 | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310036A | 187928.47 | F21P1-0404_H_labor for 50 tools_MICU | 2699 | C |  | Wire THNN | 45204 | 45212 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 187928.46 | 1 | 0.01 | 0 | 0.01 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 27410.98 | 75693.85 | 0 |  |  | 0 | 84823.63 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C025 | USCSB2301049A | 187223.56 | AMHS TSMC Instrustructure and Branch Circuits | 1666 | C |  | Tubing and fittings materials for AMHS GEX | 44956 | 44958 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 187223.56 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 163073.63 | 22802.9 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1347.03 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2211008A | 187120.14 | F21P1 WWT package (Installation and 2 batch tanks) | 1543 | C |  | 4 Trips Plainview, TX | 2022/11/4 2022/12/2 | 44902 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 187120.14 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 187120.14 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2311124A | 186600.65 | F21P1-0404_H_labor for 50 tools_MICU | 2975 | C |  | Tool Hook Up Electrical labor | 45259 | 45267 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 186148.63 | 0.99758 | 452.02 | 0 | 452.02 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 12054.38 |  | 0 | 0 | 57386.26 |  | 25347.38 |  |  |  | 28252.5 |  | 20151.2 |  |  |  | 23333.72 |  |  |  | 16510.69 | 0 | 3112.5 | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2207004A | 184930.38 | Tool Hookup Material (UPW&Chemical) | 1419 | C |  | Tool HK Chemical Material PFA Fitting (Pillar) | 44748 | 44748 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  | 100% after final acceptance-Net 60 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 184930.38 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 73699.14 | 81308.04 |  |  | 0 | [5 empty] | 29923.2 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310051A | 184633.63 | F21P1-0404_H_labor for 50 tools_MICU | 2711 | C |  | Hardware for Tun Yi Pumping Line | 45209 | 45216 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved | Wooden Crate fee can only be charged based on actual usage |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 135476.83 | 0.73376 | 49156.8 | 0 | 49156.8 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 86435.89 | 0 | 0 | 49040.94 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403158A | 183635.46 | F21P1 WWT package (Installation and 2 batch tanks) | 3857 | C |  | RFQ_Struts & Accessories_Copper State_B side_20240306 | 45366 | 45369 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 183635.46 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 67018.96 |  | 0 |  |  |  | 116564.86 | 27545.319 |  |  |  | 27545.319 | 51.64 |  |  | 27545.319 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC24C008 | USCSB2405031A | 183582 | UPW B Side Project | 4040 | C |  | UPW Foxboro A2U | 45419 | 45426 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved | [14 empty] | 36716.4 | 0.2 | 146865.6 | 0 | 146865.6 | 0 | [56 empty] | 36716.4 | [16 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403039A | 183566.91 | Tool Interconnection Project (Main Tool & Other Vendors) | 865 | P |  | KDSTS8 IC- DNS SCREEN INTERCONNECTS - 2/6-3/2/2024 | 45360 | 45363 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 183566.91 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 183566.91 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Hookup | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2209020A | 182400 | F21P1 WWT package (Installation and 2 batch tanks) | 1472 | C |  | Logistics coordinator/superintendent(took Hookup focus) | 44821 | 44824 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 182395.11 | 0.99997 | 4.89 | 0 | 4.89 | 0 | [16 empty] | 6599.16 |  | 28810.54 |  | 31803.42 |  | 29775 |  | 29413.64 |  |  |  | 21596.24 |  |  |  | 34397.11 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2407072A | 182350 | WWT B side Project | 4489 | C |  | LB-1 Sump Pump Piping - Train A/Train B_WWT UMEC scope | 45486 | 45500 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 126551 | 0.694 | 55799 | 46682 | 9117 | 0 | [70 empty] | 99198 | 0 | 27353 | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2403127A | 181267.28 | Tool Hookup Material (UPW&Chemical) | 3829 | C |  | HK UPW DP Panel Additional request | 45364 | 45370 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 181267.28 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 156496.84 |  | 24770.44 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402019A | 180400 | F21P1-0404_H_labor for 50 tools_MICU | 3462 | C | -01 | Connectors for HK Power trade | 45324 | 2024/2/5 2024/2/13 | -30100.5 | 210500.5 | V |  |  |  | Crescent Electric Supply Co | PR Approved | PO Approved | R1: Negotiated from $$210,500.50 to $180,400 |  | Ta Wei Wang | [11 empty] | 180399.99 | 1 | 0.01 | 0 | 0.01 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 180399.99 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C009 | USCSB2210033A | 180187.87 | F21P1 WWT package (Installation and 2 batch tanks) | 1516 | C |  | commissioning chemical purchase | 44853 | 44858 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 176384.38 | 0.97889 | 3803.49 | 0 | 3803.49 | 3527.6876 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 11583.25 | 7720.65 |  | 8288 | 9891.37 | 0 | 0 | 0 | 5345.34 | 56038.11 | 0 | 7794.86 | 16364.66 | 0 |  |  | 15597.12 | 0 | 0 |  | 26199.12 |  |  |  |  | 9009.3935 |  |  | 11561.9 | 9009.3935 |  |  |  | 9009.3935 |  | 0 |  | - | 0 | 0 | 0 | 3527.6876
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309002A | 180180 | Tool Interconnection Project (Main Tool & Module) | 397 | P |  | KPE603-S MANPOWER LABOR PAY | 45170 | 45244 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 153153 | 0.85 | 27027 | 0 | 27027 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 153153 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401096A | 180000 | Tool Interconnection Project (Main Tool & Other Vendors) | 713 | P |  | KPE606-S Labor | 45321 | 45325 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 180000 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 180000 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Electrical | Material | USC21C006 | USCSB2210016A | 179999.59 | F21P1 Slurry package | 1499 | C | -01 | CED Wire | 44841 | 44847 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Qty and Price adjustment according to the quote (incorrect UOM) | 100% by shipment-After Acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 179999.59 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 179999.59 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2310129A | 179876.5 | WWT Change Order (Piping) | 2788 | C | -01 | WWT FAB/WWT Valves | 45219 | 2023/10/25 2023/11/1 | 29348.8 | 150527.7 |  |  |  |  | Mega Union Technology Inc. | PR Approved | PO Approved | R1:As per requester need to renew the quotation price. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 157439.9 | 0.87527 | 22436.6 | 0 | 22436.6 | 18892.788 | [41 empty] | 0 | 0 | 0 |  | 17824.9 | 139615 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 5396.295 |  |  |  | 5396.295 |  |  |  | 3597.53 |  | 7871.995 |  | - | 7871.995 | 3148.798 | 0 | 0
Base-Build | VOC | Material | The budget execution does not pertain to this project | VOC | Low Voltage | Electrical | Material | USC22C013 | USCSB2403233A | 179837.71 | F21P1 QR Lab Security & CCTV | 3926 | C |  | VOC/ B side + control and power wire. | 45374 | 45378 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 179837.71 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 28587.03 |  | 151250.68 | [10 empty] | 170846 |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309092A | 179759.08 | WWT Change Order (Piping) | 2565 | C |  | WWT 20% Fab materials for FAB A side | 45185 | 45195 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 179736.08 | 0.99987 | 23 | 0 | 23 | 0 | [40 empty] | 0 | 0 | 0 | 27554.91 |  | 101341.97 | 2963.47 | 0 | 47181.81 | 0 | 693.92 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310136B | 178286 | F21P1-0404_H_labor for 50 tools_MICU | 2794 | C |  | Yaho Hex nut, square nute, washer | 45219 | 45240 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 178286 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 178286 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2212049A | 178255 | F21P1 Chemical & WCCS package | 1620 | C |  | F21P1 MIC CDS Plastic Box | 44924 | 44931 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 178255 | 0 | 178255 | 178255 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 178255
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC23C045 | USCSB2402253A | 178114 | WWT Change Order (Piping) | 3679 | C |  | WWT line leak check T&M work | 45349 | 45356 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 178114 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 178114 |  |  |  |  | 26717.1 |  |  |  | 26717.1 |  |  |  | 26717.1 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC22C022 | USCSB2312161A | 176243 | F21P1 Triazole treatment system | 3149 | C |  | Chem Pkg 3 WWT Estimate | 45281 | 45293 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 167432 | 0.95001 | 8811 | 0 | 8811 | 8371.6 | [45 empty] | 0 | 0 | 0 | 0 | 114558 |  |  | 31724 | 7050 | 0 |  | 14100 |  |  |  |  | 5287.29 |  |  |  | 8812.15 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 8371.6
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USC2404066B | 176000 | F21P1 AMAT Interconnection | 1012 | P | -01 | tw trade manager fee for company | 2024/4/16 2024/5/22 2024/8/23 | 2024/5/9 2024/6/27 2024/8/30 | -407 | 176407 |  |  |  |  | AUCAN INC | PR Approved | PO Approved | PR R1: Adjusting the PR amount per request from purchaser to align with the latest quotation. PR R2: Adjusting the PR amount to meet the actual final payment amount. | [13 empty] | 0 | 0 | 176000 | 176000 | 0 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC24C005 | USCSB2405180A | 176000 | Chemical & WCCS B Side Project | 4208 | C |  | [上禾] MICU E2 支援報價單(8人*4 month) | 45443 | 45448 | [6 empty] | SHANG-HE project company | PR Approved | PO Approved | [14 empty] | 11000 | 0.0625 | 165000 | 26302 | 138698 | 0 | [73 empty] | 11000 |  |  | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2305061A | 174742 | F21P1-0404_H_Hallway plate install_MICU | 1983 | C |  | 2nd batch Waffle covers | 45059 | 45069 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 174742 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 174742 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2304006A | 174330.18 | Tool Hookup Material (UPW&Chemical) | 1847 | C |  | HK Chemical PFA Reducer | 45022 | 45033 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 174330.18 | 0 | 174330.18 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2406032A | 173449.64 | F21P1-0404_H_Hallway plate install_MICU | 4258 | C |  | Two consultants order from 5/18/2024~12/19/2024 | 45448 | 45454 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 173449.64 | 0 | 173449.64 | 0 | [73 empty] | - |  |  | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2409129A | 173016.68 | TSMC Fab 21 P1B Tool Hook Up | 4947 | C |  | MIMO Team PO Renewal Proposal (Professional Services) - 2 Months | 45565 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 173016.68 | 0 | 173016.68 | 0
Base-Build | Slurry |  | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USCSB2406010A | 172999.41 | F21P1 Slurry package | 4236 | C |  | F21P1 IES- Cable Tray B side | 45444 | 45449 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 158001.38 | 0.91331 | 14998.03 | 57549.52 | -42551.49 | 0 | [70 empty] | 31659.51 |  | 68792.35 | 57549.52 |  |  | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2307112A | 172800 | F21P1 Chemical & WCCS package | 2276 | C |  | TSMC Offload July | 45133 | 45149 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 172800 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 172800 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2308059A | 172111.26 | F21P1 UPW | 2357 | C |  | 500 MCM B Side | 45147 | 45154 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 172111.26 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 172111.26 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Scaffolding |  |  | AMHS |  |  | USC22C031 | USCSB2401028A | 172043 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3219 | C |  | Proposal for Fab L30 EUV crane scaffolding | 45296 | 45321 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 172043 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 172043 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2308054A | 171508.88 | F21P1-0404_H_labor for 50 tools_MICU | 2352 | C |  | Power Hardware | 45147 | 45154 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 171508.88 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 8513.06 | 0 | 0 |  | 0 | 0 | 0 | 162995.82 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | Main Contract Scope | UPW | UPW | Civil | M+L | USC21C003 | USCSB2211010A | 171436.4 | F21P1 UPW | 1545 | C |  | WRC control room raised floor | 2022/11/8 2022/11/23 | 44900 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 171436.4 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 26961.8 |  | 0 |  |  |  | 101615.5 | 0 |  | 42859.1 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | LPS | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2112002A | 171351.52 | F21 TMAH System | 1314 | C | -01 | TMAH Mechanical | 2021/12/9 2023/4/5 | 2021/12/27 2023/4/7 | -1401707.98 | 1573059.5 | V |  |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | 4/7 Adjusting the amount due to the termination with LPS | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Yi-Hsin Lee | Cherry Chang | TMAH | 44564 | Henry |  | Y | 5005 |  | 171351.52 | 1 | 0 | 0 | 0 | 0 | [21 empty] | 171351.52 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Slurry | NUUO | Main Contract Scope | SDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2401114A | 171181.6 | F21P1 Chemical & WCCS package | 3301 | C |  | SDS slurry electrical labor and materials | 45308 | 45355 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 162122.52 | 0.94708 | 9059.08 | 0 | 9059.08 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 162122.52 | [6 empty] | 8559.08 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2212001A | 170580.48 | F21P1 UPW | 1574 | C |  | UPW BIM Modeling of Conduit | 44896 | 44897 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A(Rev01) change order |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 170580.48 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 107465.7 |  |  |  | 0 |  | 20469.66 |  | 6823.22 | 0 |  |  | 10234.83 |  | 3411.61 |  | 13646.44 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 8529.02 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2405185A | 170226.91 | Chemical & WCCS B Side Project | 4213 | C |  | F21P1 B side Electrical Materials Purchasing | 45443 | 45447 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 170226.91 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 66636.3 |  | 103231.2 |  | 359.41 |  |  | - |  |  | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310001A | 170000 | F21P1-0404_H_labor for 50 tools_MICU | 2664 | C |  | HARDWARE FOR LI JIE | 2023/10/3 2023/10/12 | 45211 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 170000 | 0 | 170000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C031 | USCSB2406097A | 169888 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4332 | C |  | HPM Panel Protection | 45462 | 45489 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 169888 | 0 | 169888 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2203003A | 169587.62 | F21P1 Chemical & WCCS package | 1338 | C | -01 | VMB rack | 2022/3/1 2022/4/12 | 2022/3/17 2022/4/12 | 16287.07 | 153300.55 |  |  |  |  | Pure Plastics, LLC | PR Approved | PO Approved | Rev01-Add additional material/ Labor | 20% upon received material and approved submittal-Net 45 days; 60% due on delivery with evidence-Net 45 days; 20% by received and after acceptance-Net 45 days | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | N | [6 empty] | 169587.61 | 1 | 0.01 | 0 | 0.01 | 0 | [7 empty] | 33917.52 |  |  | 101752.57 |  | 33917.52 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Civil | M+L | USC21C003 | USCSB2208009A | 169260 | F21P1 UPW | 1446 | C |  | Drill and Epoxy Rebar Hooks for Curb Based on Detail Provided | 44790 | 44795 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved | USCSB2111008A-01 change order | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 130732.31 | 0.77238 | 38527.69 | 0 | 38527.69 | 0 | [19 empty] | 15840 |  |  | 114892.31 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407022A | 169083.9 | Tool Interconnection Project (Main Tool & Other Vendors) | 1158 | P |  | WET ETC 451 PFA #106 (TUBE SIZE) 1X7/8X200M | 45491 | 45496 | [6 empty] | PILLAR America, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 169083.9 | 0 | 169083.9 | 0 | [73 empty] | - |  |  | 0
AMHS | AMHS |  |  |  | AMHS |  |  | USC22C027 | USCSB2210041A | 168000 | CAP_E_F21P1 Autoshelf Installation 4 set | 1387 | C |  | Autoshelf installation | 44859 | 44860 | [6 empty] | GLA Arizona, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 168000 | 0 | 168000 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2310140A | 167400 | WWT Change Order (Piping) | 2798 | C | -01 | MU/Hand welding machines for WWT | 2023/10/21 2023/12/15 | 2023/11/4 2023/12/30 | -17619.4 | 185019.4 |  | V |  |  | Mega Union Technology Inc. | PR Approved | PO Approved | Reduction in amount is due to split of order as requested by Responsible Engineer |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 167400 | 0 | 167400 | 167400 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 25110 |  |  |  | 25110 |  |  |  | 25110 |  | 33480 |  | - | 33480 | 33480 | 33480 | 33480
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2309138A | 166473 | F21P1 UPW | 2609 | C |  | UPW-CO-trade damage repair | 45191 | 45209 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 166473 | 0 | 166473 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 158149.35 |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC24C006 | USCSB2406099A | 166400 | WWT B side Project | 4334 | C |  | B side/A side punch fix team (Yi Sheng) | 2024/6/19 2024/8/12 | 2024/7/8 2024/8/12 | 27200 | 193600 | V |  |  |  | YI-SHENG engineering Co.,Ltd | PR Approved | PO Approved | PR R1: Revise the PR amount after purchasing team negotiation per David Wang. | [13 empty] | 0 | 0 | 166400 | 39400 | 127000 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2307007A | 165672 | F21 TMAH System | 2180 | C |  | WWT-weld machine rental for PSS | 45108 | 45114 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 159385.82 | 0.96206 | 6286.18 | 0 | 6286.18 | 6375.4328 | [36 empty] | 94807.66 | 20918.17 | 23010 |  | 0 | 0 | 0 | 0 |  | 0 | 20649.99 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 6375.4328
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC21C005 | USCSB2402060A | 165474 | F21P1 Chemical & WCCS package | 3502 | C |  | CDS Lorry A Add pressure detector piping | 45329 | 45336 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 157200.3 | 0.95 | 8273.7 | 0 | 8273.7 | 8273.7 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 132379.2 | 157200.3 | 24821.1 | [8 empty] | 8273.7 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2311106A | 164620 | F21P1 UPW | 2957 | C |  | FAB B UPW Electrical Permit and CA service | 45253 | 45259 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 118684 | 0.72096 | 45936 | 4665.6 | 41270.4 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 96318 | 0 |  | 0 |  | 15367.6 |  |  |  | 2332.8 | [5 empty] | 2332.8 |  |  | 0 |  | 2332.8 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2302037A | 164269.99 | F21P1 Module Tool Interconnection CVD | 1718 | C |  | Lam interconnect cable material | 44973 | 45013 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 164269.98 | 1 | 0.01 | 0 | 0.01 | 0 | [28 empty] | 0 |  |  |  | 150991.17 | 13278.81 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2408085A | 163000 | F21P1 AMHS Wiring Work Outline | 4701 | C |  | Yaho 12 Manpower Support due to TSMC schedule change | 45524 | [7 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 163000 | 0 | 163000 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403063A | 162207.42 | Tool Interconnection Project (Main Tool & Other Vendors) | 886 | P |  | KDSTS3 - DNS SCREEN INTERCONNECTS - 2/1-3/6/2024 | 45366 | 45369 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 162207.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 162207.42 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2305070A | 161517.16 | F21P1 Chemical & WCCS package | 1992 | C |  | TSMC F21 Solvent room vent | 45062 | 45097 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 112072.33 | 0.69387 | 49444.83 | 0 | 49444.83 | 161517.16 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 112072.33 | - | 0 | 0 | 161517.16
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303099A | 161360.62 | F21P1 WWT package (Installation and 2 batch tanks) | 1836 | C |  | 20% bulk order - rush order | 45015 | 45026 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 158411.19 | 0.98172 | 2949.43 | 0 | 2949.43 | 3168.2238 | [31 empty] | 53429.32 |  | 0 |  |  | 212.96 | 2011.62 |  |  | 2750.2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 100007.09 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 3168.2238
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406096A | 160828 | Chemical & WCCS B Side Project | 4331 | C |  | F21P1 B side 彰京 - PFA | 45462 | 45467 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 160828 | 0 | 160828 | 0 | [73 empty] | - |  |  | 0
Base-Build | AMC THC | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C013 | USCSB2311144A | 160060 | F21P1 AMC THC Monitoring System | 2994 | C |  | F21 THC B side Equipment | 45260 | 45273 | -55260 | 215320 |  |  |  |  | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 160060 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 20640 | 73680 |  | 0 |  | 65740 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing |  | UPW | Base-Build | Steel | Project Outsourcing (專案管理外包人力) | USC22C006 | USCSB2209018A | 160000 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1470 | C | -01 | TSMC AZ F21P2 EUV crane structural calculation/design/PE stamp | 2022/9/17 2024/5/7 | 2022/9/21 2024/5/7 | -90000 | 250000 | V |  |  |  | SYNERGY Engineering Consultants | PR Approved | PO Approved | R1: As per SYNERGY:Ting Sheng Wang to closed out the PR.(see the email) | 100% after design documents handover-T/T 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 160000 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 118000 |  |  |  | 0 |  | 42000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2401037A | 159887.7 | F21P1 AMAT Interconnection | 3228 | C |  | Interconnect Installer 6 months installers | 45297 | 45302 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 92088.14 | 0.57596 | 67799.56 | 0 | 67799.56 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 6765.04 |  | 31044.72 |  | 54278.38 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | The budget execution does not pertain to this project | Chemical | Chemical | Mechanical | Material | USC21C006 | USC2204011A | 159571.38 | F21P1 Slurry package | 158 | P |  | Diaphragm Valve | 44678 | 44679 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | USC2109012A-1的Change order，因交期長達1年，再次數量異動增加111pcs成原廠商為我們保留的量(375 pcs) | 90% After received-T/T 30days-after acceptance; 10% after final acceptance-T/T 30days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 159571.38 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 159571.38 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Scaffolding |  |  | AMHS |  |  | USC22C031 | USCSB2404090A | 159320 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3894 | C |  | F21 EUV Bay 2 Scaffold | 45393 | 45427 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 159320 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 159320 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C046 | USCSB2308063A | 159023 | F21P1 ATS Interconnection | 2361 | C |  | ATS Chillers for Dry ETC tools | 45148 | 45161 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 159023 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 159023 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409045A | 158784 | Tool Interconnection Project (Main Tool & Other Vendors) | 1248 | P |  | KPCD (14, 24, 25, 27-333) TOOLS: INSTALL/ROUTE CABLES | 45556 | 45566 | [7 empty] | PR Approved | PO Approving | [14 empty] | 0 | 0 | 158784 | 0 | 158784 | 0 | [73 empty] | -
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2403123A | 158496 | F21P1-0404_H_Hallway plate install_MICU | 3825 | C |  | Fab L10/20 Co2 special permit | 45364 | 45366 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 158496 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 158496 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2302034A | 158453 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1715 | C |  | Office Interiors and Fabrication Clean Room Tenant Improvement | 44971 | 44960 | [6 empty] | M. Arthur Gensler Jr. & Associates, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 158453 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 84551 |  | 0 |  | 26480.5 |  | 16895 | 0 |  |  | 23988.17 |  |  |  | 2200 | 0 | 0 | 0 | 4338.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG | Site Expense |  |  | Others |  |  | USC22C003 | USCSB2401132A | 158300 | TSMC Fab21 Project Phase 1 EDG Package | 3318 | C |  | Generator upgrade | 45309 | 45335 | [6 empty] | D.P. Electric, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 158300 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 15830 |  | 15830 | [7 empty] | 31660 |  | 94980 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Labor | USC21C005 | USCSB2408162A | 158181.57 | F21P1 Chemical & WCCS package | 4768 | C |  | REVISED VARTEAGA Invoice No. MICU-010 @ T^0M WORK_CDS L10_L20_L30 Cleanroom CPVC_SS_PFA Chemical System Tubes_ Batch 1/3 | 45535 | 45546 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 158181.57 | 158181.57 | 0 | 0 | [73 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405061A | 156440 | Chemical & WCCS B Side Project | 4065 | C |  | CHEM_WCCS _Consumable hardware B_USA_ 01-00167344_ 0508 | 2024/5/9 2024/5/17 | 45433 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | PR R1:As per purchasing team Nicole to compare prices with Copper State, which offers a 22.2% lower cost than Carson . | [13 empty] | 156440 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 156440 |  |  | 156440 | [7 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403086A | 156124.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 903 | P |  | 1" PVDF 90° Elbow | 45371 | 45377 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 156124.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 156124.5 |  |  |  |  | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C015 | USCSB2409121A | 156116.42 | F21P1 AMHS Wiring Work Outline | 4939 | C |  | 27 Future Stockers_AMHS | 45563 | 45566 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 156116.42 | 0 | 156116.42 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2206014A | 155528.35 | F21P1 UPW | 1403 | C |  | UPW tray model | 44723 | 44739 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 155528.35 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 49146.96 |  | 49146.96 |  | 49146.96 |  | 8087.47 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C031 | USCSB2410045A | 155479.92 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4988 | C |  | Additional Material needs for P1B AMHS 1/3,6/3,8/3,10/3 wire_the last DP materials. | 45568 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 155479.92 | 0 | 155479.92 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C017 | USCSB2209029A | 154685 | AMHS MML Power Design | 1481 | C |  | AMHS Power Panel Design | 44831 | 44832 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 154685 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 109553 |  | 22769 |  |  |  | 18423.5 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 3939.5 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409014A | 154683.25 | Tool Interconnection Project (Main Tool & Other Vendors) | 1218 | P |  | DRY_ETCH_P1A WORK_LABOR_DEC 2023 TO JUN 2024_DELTA WYE | 45542 | 45546 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 154683.25 | 154683.25 | 0 | 0 | [73 empty] | -
Base-Build | VOC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Electrical | M+L | USC21C007 | USCSB2204012A | 154671 | F21P1 VOC package （Installation ) | 1361 | C |  | Change Order (for VOC Cable Tray) | 44679 | 44680 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | USCSB2109010A的Change order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 154671 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 146937.45 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 7733.55 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309036A | 154500 | Tool Interconnection Project (Main Tool & Module) | 424 | P | -01 | Build water line, insulation jacket and QC test | 45192 | 2023/10/3 2023/11/7 | -132000 | 286500 |  |  |  |  | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | PO R1: Negotiated lower contract sum |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 154500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 154500 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2308142A | 154070 | F21P1 Chemical & WCCS package | 2437 | C |  | chemical storage platform handrail rework | 45161 | 45163 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 154070 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 46221 | 0 |  | 53924.5 | 0 | 0 | 24012 | 0 | 22209 |  | 0 | 0 | 0 |  | 0 | [12 empty] | 7703.5 |  | 0 | 7703.5 | - | 0 | 0 | 0
Base-Build | UPW | Site Expense | CO Scope (adding/additional scope) | UPW | UPW | Electrical | M+L | USC22C010 | USCSB2303080A | 153140 | F21 P1 LSC CMS and DPM 5G System | 1817 | C |  | UPW Temporary Power | 45006 | 45008 | [6 empty] | MMR Constructors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 69046.08 | 0.45087 | 84093.92 | 3634 | 80459.92 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 29293.34 | [5 empty] | 39752.74 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407038A | 152632 | Tool Interconnection Project (Main Tool & Other Vendors) | 1168 | P |  | KPI402-S PVC Piping Labor | 45499 | 45503 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 152632 | 0 | 152632 | 0 | [73 empty] | - |  |  | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2312088A | 152382.62 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3080 | C |  | RS Payroll Services contracted labor/staffing of material handlers, general laborers & various skill sets | 45274 | 45279 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 152135.96 | 0.99838 | 246.66 | 0 | 246.66 | 0 | [45 empty] | 0 | 0 | 91085.07 | 0 | 61050.89 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2306048A | 151960 | F21P1 Module Tool Interconnection DIF1-2 | 2082 | C |  | DIF2: WIRE AF825001 & WIRE AF34/003 FOR POWER TRANSFORMER CONNECTION | 45090 | 45124 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 151960 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 151960 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Steel | Labor | USC24C006 | USCSB2406067A | 151835 | WWT B side Project | 4299 | C |  | (A side) Support _Hua Yi close PR_ batch 2/2 | 45455 | 45462 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 151835 | 151835 | 0 | 151835 | [71 empty] | 30367 |  | - | 30367 | 30367 | 30367 | 30367
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USC2112014A | 151360 | F21P1 Slurry package | 81 | P |  | VMBs for slurry, Valve housing | 44538 | 44581 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | 10/4/2022 close this account for USCSB2209032A, we only paid $45,408 NO VENDOR SHEET | 30%, 30%, 30%, 10% progress payment after acceptance net 30 days. | York Yeh |  |  | Stephon Dean | York Yeh | N |  | Henry |  | N |  |  | 67813.84 | 0.44803 | 83546.16 | 0 | 83546.16 | 0 | [6 empty] | 45408 | [21 empty] | 0 |  |  |  | 22405.84 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404026A | 151273.59 | Tool Interconnection Project (Main Tool & Other Vendors) | 981 | P |  | KDCRS1-DNS SCREEN INTERCONNECTS 3/7-3/28/2024 | 45386 | 45387 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 151273.59 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 151273.59 | [10 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410051A | 151000 | Tool Hook Up E2 Trade Equipment Rental | 4993 | C |  | HK_Youngchi_Equipment Rental_1st PO_End date 8/31/2024 | 45569 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 151000 | 0 | 151000 | 0
Base-Build | Chemical | UMEC | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2402107A | 150625 | F21P1 Slurry package | 3546 | C |  | CDS TSMC 8-181 CUSO4, COSO4, H3PO4 | 45332 | 45344 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 150625 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 97906 | 45188 | 0 |  | 7531 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402034A | 150616.48 | Tool Interconnection Project (Main Tool & Other Vendors) | 758 | P |  | WET cable pull brycone manpower support for one month T&M KDCRS5 KDHBS1, KDMRS2, KDSNS1, KDMRS1, KDMRS4, KCSCS3, KEPSL5, KEPSL3, KEPSL1, KDCCS1 KEPSL4, KDCRS4, KDCCS2, KDCCS3, KCSCSA, KEBCL1, KEBCT3 | 45328 | 45337 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 95549.21 | 0.63439 | 55067.27 | 0 | 55067.27 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 95549.21 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C008 | USCSB2302008A | 149904.15 | F21P1 Module Tool Interconnection LIT2-3 | 1689 | C |  | stand alone track blower air duct | 44964 | 44978 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 149904.03 | 1 | 0.12 | 0 | 0.12 | 0 | [28 empty] | 0 |  |  |  | 89171 | 0 | 45742.63 |  |  |  |  | 14990.4 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407015A | 149656 | Tool Interconnection Project (Main Tool & Other Vendors) | 1153 | P |  | KPD803-S PVC Piping Labor | 45486 | 45492 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 149656 | 0 | 149656 | 0 | [73 empty] | - |  |  | 0
Others | 光阻櫃 | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC22C012 | USCSB2306123A | 149446.89 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 2156 | C |  | Mask Room A Side Utility | 45105 | 45132 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 149446.89 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 24952 | 0 | 0 | 0 |  | 0 | 0 | 118412 | 6082.89 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2402270A | 149419 | WWT Change Order (Piping) | 3695 | C |  | WWT - BMWC L15 Ceiling Work CO | 45350 | 45356 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 121219.15 | 0.81127 | 28199.85 | 0 | 28199.85 | 23031.6385 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 121219.15 | 22412.85 |  |  |  | 22412.85 |  |  |  | 22412.85 |  | 6060.9575 |  | - | 6060.9575 | 6060.9575 | 4848.766 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405053A | 148095.51 | Tool Interconnection Project (Main Tool & Other Vendors) | 1095 | P |  | DNS SCREEN INTERCONNECTS 3/28-4/9/2024 | 45426 | 45434 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 148095.51 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 148095.51 | [10 empty] | - |  |  | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2409110A | 147460.3 | F21P1 AMHS Wiring Work Outline | 4916 | C |  | P1AB Retrofit Work_AMHS | 45562 | 45566 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 147460.3 | 0 | 147460.3 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403064A | 147328.47 | Tool Interconnection Project (Main Tool & Other Vendors) | 887 | P |  | KDCRS5 - DNS SCREEN INTERCONNECTS - 2/13-3/7/2024 | 45366 | 45370 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 147328.47 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 147328.47 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409023A | 147000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1226 | P |  | Labor multiple tool 3/6/2024-5/6/2024 Mechanical Interconnect - Labor KCSCS3, KEPSL5, KEPSL3, KEPSL1, KDCCS1,KEPSL4, KDCRS4, KDCCS2, KDCCS3, KCSCSA, KEBCL1, KRWRS7, KCSCS9, KCSCS7, KEPSL6, KEPSS1, KCSCSB, KCSCSC, KCSCS6, KEPSL2 | 45547 | 45552 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 147000 | 1 | 0 | 191100 | -191100 | 0 | [73 empty] | 147000
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2303016A | 146984.87 | F21P1-0404_H_Hallway plate install_MICU | 1758 | C |  | Two type waffle slabs | 44988 | 45007 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 146984.87 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 146984.87 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Civil | Labor | USC23C045 | USCSB2310048A | 146485 | WWT Change Order (Piping) | 2708 | C |  | Core Drill In Various Areas | 45206 | 45216 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 146485 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 146485 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403042A | 146354.59 | Tool Interconnection Project (Main Tool & Other Vendors) | 868 | P |  | KDCRS2 - DNS SCREEN INTERCONNECTS - 1/26-3/5/2024 | 45363 | 45363 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 146194.22 | 0.9989 | 160.37 | 0 | 160.37 | 0 | [52 empty] | 0 | 0 | 146194.22 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309153A | 145575.68 | F21P1-0404_H_labor for 50 tools_MICU | 2624 | C |  | Hardware for CYH (AIR) | 45195 | 45198 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 145575.68 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 145575.68 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401155A | 144590.09 | F21P1-0404_H_labor for 50 tools_MICU | 3340 | C |  | IR Welding Machine for UPW system for 20 tools | 45310 | 45315 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 144590.09 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 144590.09 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Southland | DCR Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2302040A | 144491 | F21P1 Slurry package | 1721 | C |  | Slurry L10 Model Change | 44975 | 44993 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 144491 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 144491 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2302024A | 143565 | F21P1-0404_H_Hallway plate install_MICU | 1705 | C |  | 1500Kits ABglue for foundation | 44967 | 44974 | [6 empty] | White Cap, LP | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 143565 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 54076.15 |  |  | 89488.85 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | CRG |  |  | Chemical | Steel | Labor | USC21C005 | USCSB2406131A | 142512.8 | F21P1 Chemical & WCCS package | 4370 | C |  | TSMC / FAB21: SIDE A H202 ROOM ADDITIONAL SUPPORTS | 45469 | 45470 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 142512.8 | 0 | 142512.8 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C011 | USCSB2306109A | 141500 | F21 TMAH System | 2142 | C |  | WWT-chemical enclosure | 45100 | 45142 | [6 empty] | Scenic Industries, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 127350 | 0.9 | 14150 | 0 | 14150 | 141500 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 21225 |  |  |  | 21225 |  |  |  | 21225 |  | 28300 | 127350 | - | 28300 | 28300 | 28300 | 28300
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308008A | 141128.35 | Tool Interconnection Project (Main Tool & Module) | 358 | P |  | KPD801-S UMEC UNIVESITY MECHICAL ENGINEERING CONTRACTORS LABOR PAY | 45141 | 45218 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 141128.35 | 0 | 141128.35 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306021A | 141128.35 | Tool Interconnection Project (Main Tool & Module) | 306 | P |  | KPD901-S UMEC- LABOR | 45085 | 45100 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 141128.35 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2225.53 |  |  |  |  | 0 | 0 | 0 | 0 |  | 138902.82 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | Tiger Team | Material |  |  | Others |  |  | USC23C041 | USCSB2307063A | 141120 | TSMC F21 HK Tiger Team | 2230 | C |  | HK Tiger team Cable tray and AC Box | 45121 | 45134 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 141120 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 141120 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | M+L | USC22C013 | USCSB2404051A | 140156 | F21P1 QR Lab Security & CCTV | 4045 | C |  | F21-P1_B-SIDE CCTV & ACCESS Fiber splicing and panel to panel Inner connection | 45386 | 45391 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 136703.2 | 0.97536 | 3452.8 | 0 | 3452.8 | 65873.32 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 70078 | 67363 |  |  | 28032 |  |  |  | 28032 | 69340.2 | 21023.4 |  | - | 19621.84 | 18220.28 | 0 | 7007.8
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2403104A | 139678 | F21P1 WWT package (Installation and 2 batch tanks) | 3806 | C |  | [B side][Manpower-MU] 協益/1month | 45360 | 45364 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 0 | 0 | 139678 | 0 | 139678 | 139678 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 20951.7 |  |  |  | 20951.7 |  |  |  | 20951.7 |  | 27935.6 |  | - | 27935.6 | 27935.6 | 27935.6 | 27935.6
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309192A | 139605 | F21P1-0404_H_labor for 50 tools_MICU | 2660 | C |  | Hardware for CYH (sea) | 2023/9/29 2023/10/9 | 45209 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | PR R1:Adjusting item 041 amount per purchaser's request. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 139605 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 139605 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Civil | M+L | USC21C003 | USCSB2302012A | 138900 | F21P1 UPW | 1693 | C |  | Chemical enclosures installation | 44964 | 44999 | [6 empty] | Scenic Industries, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 138900 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 118065 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 20835 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2303062A | 138326 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1801 | C |  | One-Line Power REV 1 | 45000 | 45015 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 136095 | 0.98387 | 2231 | 0 | 2231 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 122485.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 13609.5 | [6 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409028A | 138255 | Tool Interconnection Project (Main Tool & Other Vendors) | 1231 | P |  | Low Voltage Electrician (8)Hrs per day=total of (105)working days X(2) headcount (1680) totalt man Hrs. | 2024/9/14 2024/9/17 | 45561 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | PR R1:Updated "Description Title" on New Quote. New Upload | [13 empty] | 0 | 0 | 138255 | 0 | 138255 | 0 | [73 empty] | -
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2212004A | 137912 | F21P1 WWT package (Installation and 2 batch tanks) | 1577 | C |  | Alliance - trucking cost | 44896 | 44900 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 137912 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 137912 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | General Condition | Housekeeping |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC24C010 | USC2408016A | 137766.06 | General Conditions B Side Project | 1186 | P |  | Base build-CGS 3&4 opening invoices | 45518 | 45524 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 137766.06 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 137766.06 |  |  | -
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2312075A | 137659.41 | F21P1 AMAT Interconnection | 3067 | C |  | E-OPS Installers for 3 Months | 45273 | 45274 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 132907.78 | 0.96548 | 4751.63 | 0 | 4751.63 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 11852.51 |  | 0 | 0 | 87075.42 |  | 33979.85 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Commissioning | USC21C009 | USCSB2212037A | 137212 | F21P1 WWT package (Installation and 2 batch tanks) | 1608 | C |  | WWT- Na2SO3-Formaldehyde | 44915 | 44916 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 137212 | 1 | 0 | 77434 | -77434 | 33475.68 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 20581.8 |  |  | 59778 | 20581.8 |  |  |  | 20581.8 |  | 11955.6 |  | 77434 | 11955.6 | 9564.48 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404196A | 137159.87 | WWT B side Project | 4175 | C |  | WWT PVC_PVDF FittingsPipes (B Side)_20240424 | 45408 | 45416 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 137159.87 | 1 | 0 | 0 | 0 | 2678.7814 | [54 empty] | 0 |  | 0 |  |  |  |  | 20573.9805 | 123302.26 |  | 10636.81 | 20573.9805 |  |  | 3220.8 | 20573.9805 |  | 0 |  | - | 0 | 0 | 0 | 2678.7814
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2307108A | 135395.49 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2273 | C | -01 | Forward Tilt | 45129 | 2023/8/1 2023/8/7 | [6 empty] | Forward Tilt, LLC | PR Approved | PO Approved | R1:Payment Terms Improved |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 125455.45 | 0.92659 | 9940.04 | 0 | 9940.04 | 0 | [36 empty] | 67697.75 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 57757.7 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC22C001 | USCSB2305071A | 135180 | F21 P1 Office and WH Security and CCTV | 1993 | C |  | TSMC F21P1 Site Security Electronics Permit Assistance | 45062 | 45065 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 135180 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 5260 |  |  |  | 118382.5 |  | 0 | 0 | 7975 | 3562.5 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USC2111038A | 133903.8 | F21P1 UPW | 47 | P | -01 | electromagnetic flowmeter,pressure transmitter | 2021/11/19 2021/12/11 | 2021/11/24 2021/12/14 | -159.6 | 134063.4 |  |  | V |  | Azbil North America, Inc. | PR Approved | PO Approved |  | 90% Received, 10% 60 days after acceptance, net 30 days | York Yeh | DDP Office | 2 year limited warranty | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | 5000 |  | 133903.8 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 133903.8 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409032A | 133287 | Tool Interconnection Project (Main Tool & Other Vendors) | 1234 | P |  | F21 Dif. ADD O3 LOCAL DETECTOR *10set: 機型-1台1EA偵測器 - 共10台 | 45553 | 45555 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 133287 | 0 | 133287 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403019A | 133199.33 | Tool Interconnection Project (Main Tool & Other Vendors) | 846 | P |  | DNS SCREEN IC KDSTS6-KDSTS6 INTERCONNECT WET-labor is completed 1/20-2/12/2024 | 45358 | 45362 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 133199.33 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 133199.33 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312028A | 133012.8 | Tool Interconnection Project (Main Tool & Module) | 577 | P |  | LABOR & MATERIAL FOR GALVANIZED DUCT/ELBOWS FOR BLOWER BOX IN LB1. INSTALLATION OF H-BAR IN L10. | 45266 | 45268 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 113911.63 | 0.8564 | 19101.17 | 0 | 19101.17 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 4064.28 | 3694.8 | 21605.34 | 0 |  | 0 |  | 43182.99 |  | 41364.22 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405179A | 132742.51 | Chemical & WCCS B Side Project | 4207 | C |  | CHEM_ Ryan Herco Flow Solutions_ CDS/ SDS/ WCCS_ L10/L20_ PVDV+CPVC+PP | 45443 | 45447 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 125622.62 | 0.94636 | 7119.89 | 8830.91 | -1711.02 | 0 | [66 empty] | 82810.62 |  |  |  | 33981.09 |  |  | 8830.91 |  |  | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2406137A | 132224 | WWT B side Project | 4376 | C |  | WRC SS Bypass(UPW SUS fix bypass only) | 45470 | 2024/8/1 2024/9/5 | -11999 | 144223 |  |  |  | V | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | PO R1: Scope Change to Not Include QA/QC | [13 empty] | 0 | 0 | 132224 | 0 | 132224 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311112A | 132067.3 | F21P1-0404_H_labor for 50 tools_MICU | 2963 | C |  | F21 Hookup保壓材料, KEMEL7, KSSBA1 | 45253 | 45264 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 132067.3 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 132067.3 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404215A | 131920.9 | WWT B side Project | 3966 | C |  | WWT the Drain Remaining Pipes_20240426 (B Side) | 45412 | 45414 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 131920.9 | 1 | 0 | 0 | 0 | 3834.543 | [54 empty] | 0 |  | 0 | [5 empty] | 127818.1 | [5 empty] | 4102.8 |  |  | 0 |  | - | 0 | 0 | 0 | 3834.543
Base-Build | TMAH | MMI | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C011 | USCSB2307051A | 131687 | F21 TMAH System | 2220 | C |  | Lamella Installation | 45120 | 45126 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 131687 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 131687 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403043A | 131555.19 | Tool Interconnection Project (Main Tool & Other Vendors) | 869 | P |  | KDCRS3 - DNS SCREEN INTERCONNECTS - 1/18-3/5/2024 | 45363 | 45363 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 131555.19 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 131555.19 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2305103A | 131403 | F21P1 UPW | 2024 | C |  | UPW CO-Distribution | 45070 | 45076 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 131403 | 0 | 131403 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 131403 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT |  |  | USC24C006 | USCSB2409023A | 131065 | WWT B side Project | 4791 | C |  | MU E2 manpower support for 6 people_B 區suction + A side NaOH 管路 | 45540 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 131065 | 0 | 131065 | 0 | [73 empty] | -
Others | AMHS |  |  |  | AMHS |  |  | USC22C025 | USCSB2409089A | 130675 | AMHS TSMC Instrustructure and Branch Circuits | 4901 | C |  | 12in Ladder Tray and Wire_AMHS | 2024/9/23 2024/9/26 | 45562 | [6 empty] | Sonepar Mountain Holdings LLC dba QED | PR Approved | PO Approved | PR R1:As per purchasing team David to change the vendor. | [13 empty] | 0 | 0 | 130675 | 0 | 130675 | 0 | [73 empty] | -
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2403265A | 130425.45 | F21P1-0404_H_Hallway plate install_MICU | 3958 | C |  | Jeoufwu Foundation support from 12/1/23~12/31/23 and 2/16/24~5/17/24 | 45378 | 45384 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 130425.45 | 0 | 130425.45 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | LPS | Main Contract Scope | WWT | WWT | Steel | Labor | USC21C009 | USCSB2206025A | 130410.27 | F21P1 WWT package (Installation and 2 batch tanks) | 1414 | C |  | WWT Pipe Rack | 44742 | 44743 | [6 empty] | Lasco Process Systems, LLC. | PR Approved | PO Approved | USCSB2111003A-Rev01 Change order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 130410.27 | 1 | 0 | 0 | 0 | 0 | [15 empty] | 130410.27 | [12 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | VOC | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC21C007 | USCSB2209009A | 130000 | F21P1 VOC package （Installation ) | 1462 | C |  | MIC-TSMC-F21P1- VOC DCS SCADA | 44814 | 44818 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved |  | 15% Prepayment; 35% by progress-Net 30 days-after acceptance (FAT); 40% by progress-Net 30 days-after acceptance (SAT); 10% After final acceptance-Net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 117000 | 0.9 | 13000 | 0 | 13000 | 52000 | [20 empty] | 19500 | [7 empty] | 0 |  |  |  |  | 0 |  |  | 45500 |  |  |  | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 13000 |  | 39000 | 39000 | - |  |  | 0 | 13000
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2204010A | 129799.8 | F21P1 UPW | 1359 | C |  | Project Management Software | 44677 | 44683 | [6 empty] | Procore Technologies, Inc. | PR Approved | PO Approved |  | 100% due upon receipt-After acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 129799.8 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 129799.8 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2305066A | 129675.6 | F21P1-0404_H_Hallway plate install_MICU | 1988 | C |  | 9 type B foundations from MMI to Greenberry | 45062 | 45076 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 123191.82 | 0.95 | 6483.78 | 0 | 6483.78 | 0 | [33 empty] | 0 | [6 empty] | 123191.82 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C059 | USCSB2405162A | 129420 | F21P1 Foundation T&M | 4190 | C |  | 3rd waffle covers from MMI | 45441 | 45446 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 129420 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 129420 |  |  | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310156A | 129032.71 | F21P1-0404_H_labor for 50 tools_MICU | 2811 | C |  | Wire THNN | 45223 | 45229 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 129032.71 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 129032.71 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical Lab | UMEC | The budget execution does not pertain to this project | Chemical Lab | Chemical | Mechanical | M+L | USC22C021 | USCSB2307006A | 128754 | F21P1 Chemical Lab setup | 2179 | C |  | 8-66 FAB Gas Chem Lab Hook-Up(GC Lab Piping) | 45108 | 45133 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 122317 | 0.95001 | 6437 | 0 | 6437 | 6437 | [40 empty] | 0 | 103003 | 0 | 0 |  | 0 | 0 | 0 | 12876 | 0 | 6438 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 6437
Base-Build | VOC |  |  |  | Low Voltage | Electrical | M+L | USC21C013 | USCSB2409014A | 128026.61 | F21P1 AMC THC Monitoring System | 4784 | C |  | F21 P1 VOC Electricity Change Order _CO#30_Batch 1/2 | 45539 | 9/7/2024 9/12/2024 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | PO R1: Revise Payment Term in Remark | [13 empty] | 82077.61 | 0.6411 | 45949 | 82077.61 | -36128.61 | 0 | [73 empty] | 82077.61
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311072A | 127719 | Tool Interconnection Project (Main Tool & Module) | 540 | P |  | PVC Piping | 45258 | 45272 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 127719 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 127719 | [6 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Scaffolding |  |  | Others |  |  | USC23C055 | USCSB2312183A | 127383 | F21P1-0404_H_labor for 50 tools_MICU | 3170 | C |  | scaffold services labor, material, and equipment for hook up shared by all system | 45287 | 45296 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 127383 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 127383 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306045A | 127257.61 | Tool Interconnection Project (Main Tool & Module) | 329 | P | -01 | VIEGA FITTING INTERCONNECT MATERIALS | 45094 | 2023/7/17 2023/07/26 | [6 empty] | Hajoca Corporation DBA Hughes Supply Deer Valley | PR Approved | PO Approved | WO R1:Adjust delivery date |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 127257.58 | 1 | 0.03 | 0 | 0.03 | 0 | [33 empty] | 0 | [5 empty] | 127053.03 | 204.55 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | CCE | DCR Scope | WWT | WWT | Electrical | M+L | USC21C009 | USCSB2312062A | 126710.89 | F21P1 WWT package (Installation and 2 batch tanks) | 3054 | C |  | WWT_CCE CO58 stripper disconnect switch and CO35 RIO Conduit. | 45269 | 45273 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 120375.33 | 0.95 | 6335.56 | 0 | 6335.56 | 0 | [45 empty] | 0 | 0 | 0 | 120375.33 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403131A | 126684.25 | Tool Interconnection Project (Main Tool & Other Vendors) | 946 | P |  | KDHBS1-DNS SCREEN INTERCONNECTS, 2/23-3/19/2024 | 45379 | 45384 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 126684.25 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 126684.25 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310017A | 126419.7 | F21P1-0404_H_labor for 50 tools_MICU | 2680 | C |  | Galvanized Tool | 45203 | 45209 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 126419.7 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 126419.7 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C003 | USCSB2308155A | 126010 | F21P1 UPW | 2449 | C |  | WWT Testing support | 45163 | 45166 | [6 empty] | Jettech System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 126010 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 126010 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C006 | USCSB2410015A | 125505.35 | WWT B side Project | 4959 | C |  | WWT - Brahma A-Side Carboline Flange Coating CO-2 | 45567 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 125505.35 | 0 | 125505.35 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404028A | 125117.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 983 | P |  | KDCCS1-DNS SCREEN INTERCONNECTS 3/7-3/28-2024 | 45386 | 45387 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 125117.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 125117.32 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC23C002 | USC2309041A | 124800 | F21P1-0404_H_Hallway plate install_MICU | 429 | P |  | Manpower Pay for General Labor for Elsa Nieto | 45196 | 45215 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 124800 | 1 | 0 | 3395.67 | -3395.67 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 124800 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC23C011 | USCSB2303090A | 124115 | F21P1 AMHS MML Power Design - Muratech | 1827 | C |  | LSW Design for Murata | 45009 | 45016 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 113755 | 0.91653 | 10360 | 4160 | 6200 | 0 | [28 empty] | 0 |  | 32106.5 |  |  | 0 |  |  |  |  | 3772.5 |  | 0 | 0 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 3699 |  |  | 2867 | 0 | 0 |  | 17006 |  | 12785 |  |  |  | 13869 |  |  |  | 11455 |  | 9168 |  |  | 0 |  | 4160 | 0 | 0 | 0
Interconnection | interconnection | Equipment |  |  | Others |  |  | USC23C005 | USCSB2312013A | 124000 | F21P1 Module Tool Interconnection DIF1-2 | 3007 | C | -01 | YAHO System Technology | 2023/12/2 2024/6/20 | 2023/12/16 2024/6/21 | 12400 | 111600 |  |  | V |  | YAHO System Technology Co., Ltd. | PR Approved | PO Approved | Amount change is to add 1 additional tool. Change supplier's US-based company i.e. YAHO System Technology Inc. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 124000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 24800 |  | 0 | 0 | 12400 |  | 49600 | [13 empty] | 24800 | 0 | 12400 | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2207023A | 122849.71 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1438 | C |  | Internet for Glendale warehouse | 44769 | 44777 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 109255.42 | 0.88934 | 13594.29 | 0 | 13594.29 | 0 | [16 empty] | 71102.52 |  |  |  | 38152.9 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2404111A | 122015.73 | F21P1 AMHS Wiring Work Outline | 4096 | C |  | 6 Sinfonia Manpower for AMHS | 45397 | 45405 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | This is NTD, not USD | [13 empty] | 122015.73 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 122015.73 | [6 empty] | - |  | 0 | 0
Base-Build | Base-Build | Housekeeping |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC23C056 | USCSB2406019A | 122000 | Fab LB2 Trench Cleaning | 4245 | C |  | B side housekeeping(Open PO) | 45447 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 122000 | 0 | 122000 | 0 | [73 empty] | - |  |  | 0
Hookup | 5G | Material | The budget execution does not pertain to this project | 0 | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC22C010 | USCSB2212030A | 121950 | F21 P1 LSC CMS and DPM 5G System | 1603 | C |  | TSMC New FAB Building - KINEMETRICS earthquake instruments | 44911 | 45006 | [6 empty] | Kinemetrics, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 66265 | 0.54338 | 55685 | 0 | 55685 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 66265 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2308071A | 121640.6 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2369 | C |  | Big Ass Fans Glendale Warehouse Industrial Fans | 45153 | 45163 | [6 empty] | Delta T, LLC dba Big Ass Fans | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 121640.6 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 78659 | 0 | 0 | 0 | 0 |  | 32896 | 0 | 0 | 0 | 10085.6 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404006A | 121499.59 | Tool Interconnection Project (Main Tool & Other Vendors) | 961 | P |  | KDCCS2-DNS SCREEN INTERCONNECTS 3/6-3/26/2024 | 45384 | 45387 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 121499.59 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 121499.59 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2301011A | 121205 | F21P1 WWT package (Installation and 2 batch tanks) | 1634 | C |  | Minor Works CCB-MU | 44932 | 44937 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 68285.93 | 0.56339 | 52919.07 | 0 | 52919.07 | 30045.8092 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 18180.75 |  |  | 68285.93 | 18180.75 |  |  |  | 18180.75 |  | 10242.8895 |  | - | 10242.8895 | 9560.0302 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Labor | USC21C012 | USCSB2402267A | 121128 | F21 Barcode RFID System | 3692 | C |  | UPW-UMEC-2023-Dec-extend GC-2 | 45350 | 45353 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 115072 | 0.95 | 6056 | 0 | 6056 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 115072 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2311111A | 120982.1 | F21P1 QR Lab Security & CCTV | 2962 | C |  | F21 CCD room CCTV & Security Equipment | 45253 | 45279 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 101562 | 0.83948 | 19420.1 | 0 | 19420.1 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 28210 | 0 |  | 0 | [9 empty] | 73352 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307003A | 120960 | Tool Interconnection Project (Main Tool & Module) | 339 | P |  | Mechanical labor cost and materials KDSTS2, KDCRS3 | 45118 | 45138 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 111649.32 | 0.92303 | 9310.68 | 0 | 9310.68 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 9529.97 | 0 | 0 | 0 |  |  | 0 | 102119.35 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403038A | 120204.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 864 | P |  | KDSNB2 IC-SHIB INTERCONNECTS 1/31-3/2/2024 | 45360 | 45363 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 120204.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 120204.4 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC |  | The budget execution does not pertain to this project | VOC | Low Voltage | Electrical | Labor | USC24C007 | USCSB2405125A | 120057 | Low Voltage B Side Project | 4153 | C |  | F21 P1 VOC system extension GC (JAN.FEB.MAR.APR/2024) | 45434 | 45451 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 120057 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 101228.03 |  |  |  | 18828.97 | [6 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2401046A | 120000 | F21P1 AMAT Interconnection | 3236 | C |  | Day & Night shift Laborers | 45300 | 45306 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 120000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 69525 | 0 | 0 | 0 |  | 50475 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2402075A | 120000 | F21P1 Module Tool Interconnection CVD | 3517 | C | -01 | KCBDA4 Vent Line Retro Fit | 45330 | 2024/2/22 2024/5/4 |  |  |  | V |  |  | YAHO System Technology Inc. | PR Approved | PO Approved | R1: Updateing contract scope to align quantity of Tool ID (Removed KCBDA1) |  | Ta Wei Wang | [11 empty] | 36000 | 0.3 | 84000 | 0 | 84000 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 36000 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC22C022 | USCSB2404001A | 119850 | F21P1 Triazole treatment system | 3998 | C |  | WWT - Marquis Carbon Media loading #2 | 45383 | 45394 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 36675 | 0.30601 | 83175 | 0 | 83175 | 25305.75 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 17977.5 | 36675 |  |  | 17977.5 |  |  |  | 17977.5 |  | 9168.75 |  | - | 9168.75 | 6968.25 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403119A | 119641.38 | Tool Interconnection Project (Main Tool & Other Vendors) | 934 | P |  | KDBCS1 DNS CREEN INTERCONNECTS 2/17-3/23/2024 | 45378 | 45380 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 119641.38 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 119641.38 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | 0 | Chemical | Electrical | Material | USC22C013 | USCSB2312003A | 119370.32 | F21P1 QR Lab Security & CCTV | 2998 | C |  | CDS CED DFK Lorry HPM materials | 45261 | 45264 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 119370.32 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 57254.36 | 0 | 62115.96 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC23C058 | USCSB2312056A | 119203 | F21 EUV Steel Plates | 3049 | C |  | Provide generator rental for temporary power staged outside of Fab building on West side. | 45268 | 45271 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 119203 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 119203 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV |  |  |  | Low Voltage | Electrical | M+L | USC22C013 | USCSB2409008A | 118515.2 | F21P1 QR Lab Security & CCTV | 4778 | C |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 1/6 | 45539 | 45542 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 118515.2 | 1 | 0 | 118515.2 | -118515.2 | 0 | [73 empty] | 118515.2
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403050A | 118335 | Tool Interconnection Project (Main Tool & Other Vendors) | 874 | P |  | KPPTT1 VEX, Power, and Mechanical Labor | 45363 | 45364 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 118335 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 118335 | [10 empty] | 0 |  | - | 0 | 0 | 0
Others | Tiger Team | Material |  |  | Others |  |  | USC23C051 | USCSB2307062A | 117700 | F21P1 Cable tray installation-tiger team | 2229 | C |  | F21P1 Cable tray installation-tiger team | 45121 | 45134 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 117700 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 117700 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | 2D/3D drawing | Labor |  |  | Others |  |  | USC23C022 | USCSB2308039A | 117660 | F21P1_H_2D/3D drawing | 2337 | C |  | 3D Drawing Support | 45145 | 45166 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 117660 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 117660 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2202009A | 117484 | F21P1 UPW | 1334 | C |  | FRP Tank Changed Order Work | 44607 | 44615 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 25% upon all submittals approved-Net 30 Days; 20% upon receipt of materials-Net 30 Days; 50% upon ready to ship status-Net 30 Days; 5% upon commissioning and acceptance-within 60 days cap from shipping date or the product commission date, whichever is earlier-Net 30 Days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N |  |  |  | N |  |  | 0 | 0 | 117484 | 0 | 117484 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404002A | 117344.42 | Tool Interconnection Project (Main Tool & Other Vendors) | 957 | P |  | KDCRS4-DNS SCREEN INTERCONNECTS 3/19-3/20/2024 | 45384 | 45388 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 117344.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 117344.42 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C003 | USCSB2302043A | 117147.53 | F21P1 UPW | 1724 | C |  | LPS RH materials #1 | 44980 | 44986 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 117147.53 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 115074.15 |  | 0 |  |  |  | 2001.38 |  | 72 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C006 | USCSB2308137A | 116678.45 | F21P1 Slurry package | 2432 | C |  | Liberty May 01 | 45161 | 45163 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 116678.45 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 116678.45 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406001A | 116237 | Tool Interconnection Project (Main Tool & Other Vendors) | 1121 | P |  | KPE604-T VEX, Signal, Power, and Mechanical Installation Labor | 45450 | 45455 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 116237 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 116237 |  |  | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2207003A | 115889.9 | Tool Hookup Material (UPW&Chemical) | 1418 | C |  | Tool HK Chemical Material PFA Fitting (Semitorr) | 44744 | 44748 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  | 100% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 115517.9 | 0.99679 | 372 | 1124 | -752 | 0 | [25 empty] | 12089.25 |  |  | 0 |  | 72144.35 |  | 11471.65 | 0 |  | 104.85 | 19707.8 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309176A | 115575.35 | WWT Change Order (Piping) | 2645 | C |  | WWT -Train A-PVC materials | 45197 | 45204 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 115575.35 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 115186.55 |  | 388.8 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C007 | USCSB2308138A | 115322.66 | F21P1 VOC package （Installation ) | 2433 | C |  | Liberty May 02 | 45161 | 45163 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 115322.66 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 115322.66 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC23C040 | USCSB2305101A | 115269.06 | TSMC F21 Clean Room Suit | 2022 | C | -01 | Open PO for Clean Room Suits | 2023/5/23 2023/8/2 | 2023/5/24 2023/8/9 | -184730.94 | 300000 |  |  |  | V | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved | Open PO for disposable cleanroom jumsuits; 10500 pcs every other week and additional requests |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 115269.06 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 11954.6 | 83282.01 | 20032.45 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2404127A | 114773.34 | F21P1 AMAT Interconnection | 4112 | C |  | REI Change Orders | 45398 | 45401 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 114773.34 | 0 | 114773.34 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309126A | 114768.28 | WWT Change Order (Piping) | 2597 | C |  | TW W1 material 2nd Order | 45190 | 45197 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 114768.28 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 37605.84 | 46869.58 |  | 483.16 | 29809.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC24C006 | USCSB2405181A | 114079 | WWT B side Project | 4209 | C |  | WWT - (166) L20 Litho B Side Embedded Pipe Sealing | 45443 | 45461 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 114079 | 114079 | 0 | 114079 | [71 empty] | 22815.8 |  | - | 22815.8 | 22815.8 | 22815.8 | 22815.8
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408045A | 113968 | Tool Interconnection Project (Main Tool & Other Vendors) | 1194 | P |  | KPAN05-T Exhaust Labor | 45524 | 45528 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 113968 | 0 | 113968 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408048A | 113968 | Tool Interconnection Project (Main Tool & Other Vendors) | 1196 | P |  | KPAN06-T Exhaust Labor | 45524 | 45531 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 113968 | 0 | 113968 | 0 | [73 empty] | -
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2210008A | 113273.07 | F21P1 UPW | 1492 | C |  | UPW A Side Disconnect Switch Change Order | 44839 | 44852 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A-01 Change Order (Disconnect Switch) | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 113273.07 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 35681.02 |  | 35681.02 |  | 22654.61 |  | 19256.42 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2303005A | 113266.1 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1747 | C |  | 2 Clean Room | 44986 | 44988 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 113266.1 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 35326.28 | 26961.8 | 0 |  | 39651.41 |  |  | 11326.61 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC23C054 | USCSB2404177A | 112800 | UPW Change Order | 4158 | C | -01 | UPW-B side CA/observation service | 45405 | 2024/5/22 2024/6/10 | [6 empty] | M Consultants, LLC BDA M-Engineering | PR Approved | PO Approved | R1: Change terms based on the consensus MICU and the vendor have | [13 empty] | 65708 | 0.58252 | 47092 | 0 | 47092 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 49604 | 0 | 16104 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C009 | USC2112019A | 112714.39 | F21P1 WWT package (Installation and 2 batch tanks) | 86 | P | -01 | Copper, free chlorine, and turbidity analyzers. | 2021/12/14 2022/2/1 | 2021/12/28 2022/2/9 | 3456.84 | 109257.55 | V |  |  |  | Hach Company | PR Approved | PO Approved | 12% price increase | 90% by received, Net 30days; 10% by acceptance, Net 30days(after acceptance in 60days). | York Yeh | DDP | 2 year limited warranty | Rui Ma | York Yeh | N |  | Henry |  | N | 5000 |  | 103659.72 | 0.91967 | 9054.67 | 0 | 9054.67 | 8292.7776 | [7 empty] | 56357 | [17 empty] | 47302.72 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 4508.5756 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 8292.7776
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403051A | 112574 | Tool Interconnection Project (Main Tool & Other Vendors) | 875 | P |  | KPE605-T Vex Signal, Power, and Mechanical Install | 45363 | 45364 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 112574 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 112574 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405136A | 112574 | Tool Interconnection Project (Main Tool & Other Vendors) | 1112 | P |  | KPE606-T VEX Signal, Power, and Mechanical Installation Labor | 45435 | 45455 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 112574 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 112574 | [6 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2312005A | 112500 | WWT Change Order (Piping) | 3000 | C |  | WWT -Stripper-2"packing -Harrington | 45261 | 45269 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 112500 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 112500 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2303010A | 112194 | F21P1 Module Tool Interconnection CVD | 1752 | C |  | F21P1 CVD1 gas line pipe | 44987 | 45005 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 112194 | 0 | 112194 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2301032A | 112011 | F21P1 UPW | 1653 | C |  | LB2-Area A-ACF media loading | 44939 | 44949 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 112011 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 112011 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | CCE | CO Scope (adding/additional scope) | WWT | WWT | Electrical | Site Expense | USC21C009 | USCSB2209017A | 112010.28 | F21P1 WWT package (Installation and 2 batch tanks) | 1469 | C |  | site Temp power from UIS panel to sub work area | 44821 | 44824 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 95% progress payment-Net 30 days-after acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 112010.28 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 112010.28 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC23C054 | USCSB2401176A | 110074 | UPW Change Order | 3361 | C |  | UPW-UMEC-T&M tickets | 45314 | 45316 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 110074 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 104570 | 0 | 0 |  | 5504 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Labor | USC24C006 | USCSB2407109A | 110000 | WWT B side Project | 4524 | C |  | WWT_Drain pipeline construction under MU_3weeks | 45491 | 45511 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 110000 | 0 | 110000 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USC2111003A | 109847.32 | F21P1 UPW | 26 | P | -01 | Conductivity Meter | 44504 | 2021/12/2 2022/10/14 | -171227.2 | 281074.52 |  | v |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | 10/14 change quantity because of late delivery Will be changed and replaced partially by USCSB2209011A, USCSB2210006A, USCSB2210007A 12/3 採購單成立 11/9專案回覆待確認中(CF & Supplier's sheet) | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | 44539 | Matt |  | N | 5000 |  | 100398.95 | 0.91399 | 9448.37 | 0 | 9448.37 | 0 | [28 empty] | 0 |  |  |  |  | 28448.4 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 57834.71 | 0 | 0 |  | 5058.87 |  | 625.52 | [12 empty] | 0 | 8431.45 | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C009 | USCSB2301025A | 109698 | F21P1 WWT package (Installation and 2 batch tanks) | 1647 | C |  | CO Sticker Installation | 44937 | 44960 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 85788.6 | 0.78204 | 0 | 0 | 0 | 0 | [28 empty] | 85788.6 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3290.94 |  |  |  | 5484.9 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Triazole | Labor | Main Contract Scope | WWT | WWT | Electrical | M+L | USC21C009 | USCSB2405036A | 109566.81 | F21P1 WWT package (Installation and 2 batch tanks) | 4045 | C |  | Triazole Change Order | 45419 | 45428 | [6 empty] | 2000 GOLD LLC | PR Approved | PO Approved | [14 empty] | 109566.81 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 |  |  |  | 109566.81 | [10 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | Tiger Team | Labor |  |  | Others |  |  | USC23C041 | USCSB2306009A | 108960 | TSMC F21 HK Tiger Team | 2043 | C |  | HK Tiger Team NETcom | 45080 | 45104 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 108960 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 108960 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401032A | 108729 | Tool Interconnection Project (Main Tool & Other Vendors) | 655 | P |  | KPD802-T Labor | 45308 | 45311 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 108729 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 108729 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USC2201006A | 108438.09 | F21P1 Slurry package | 100 | P | -01 | Ball Valve, pressure regulating, Diaphragm Valve | 2022/1/18 2022/2/8 2022/3/31 | 2022/2/10 2022/3/31 | 20599.84 | 87838.25 | V |  |  |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | Rev01:PVDF價格上漲，3個物件漲30%; Original:廠商報價時效性過，因此於請購異動增加價格 | Arrival (delivery) 100.00% NET 30days after shipping | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | N |  |  |  |  | 5000 |  | 108437.73 | 1 | 0.36 | 0 | 0.36 | 0 | [14 empty] | 13484.44 | [9 empty] | 35850.03 | 59103.26 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Civil | M+L | USC23C045 | USCSB2308005A | 108141 | WWT Change Order (Piping) | 2309 | C |  | Mezzanine Epoxy Coatings (WWT -mezz 4 epoxy) | 45139 | 45146 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 108141 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 102733.95 | 0 | 0 | 5407.05 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403041A | 107845.96 | Tool Interconnection Project (Main Tool & Other Vendors) | 867 | P |  | KDSTS9 IC - DNS SCREEN INTERCONNECTS - 2/13-3/4/2024. | 45360 | 45364 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 107845.96 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 107845.96 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | 光阻櫃 | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC24C007 | USCSB2405049A | 107719.82 | Low Voltage B Side Project | 4056 | C |  | F21-P1_B-Side mask room exhaust hookup | 45420 | 45425 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 107719.82 | 0 | 107719.82 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Base-Build | VOC | Southland | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | M+L | USC22C010 | USCSB2308158A | 107443 | F21 P1 LSC CMS and DPM 5G System | 2452 | C |  | F21 P1 VOC Change Order(southland)_2 | 45164 | 45184 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 107443 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 5372 | 102071 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309001A | 107408.38 | Tool Interconnection Project (Main Tool & Module) | 396 | P |  | KPE602-S TRIDENT MATERIAL PAY | 45170 | 45178 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 107408.38 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 107408.38 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | M+L | USC23C045 | USCSB2309058A | 107400 | WWT Change Order (Piping) | 2534 | C |  | Epoxy Pump Pads and Vibration Pads(FAB LB2 and WRC L10) | 45182 | 45216 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 107400 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 107400 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402233A | 107241.75 | F21P1-0404_H_labor for 50 tools_MICU | 3659 | C |  | ELECTRICAL QA (Foreman Level) Proposal (Contract Staffing) | 45346 | 45358 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 107241.75 | 0 | 107241.75 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2309142A | 106561.5 | F21P1 Chemical & WCCS package | 2613 | C | -01 | Chemical VMB boxes for Fab B Side of the CDS system. | 45191 | 2023/10/5 2023/11/17 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | PO R1:Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 106561.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 100075.45 | 0 |  |  | 0 | 0 | 6486.05 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC21C005 | USCSB2308173A | 106454.16 | F21P1 Chemical & WCCS package | 2467 | C |  | CHU-WEI welding equipment | 45167 | 45174 | [6 empty] | JUWEI ENGINEERING CO LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 104852 | 0.98495 | 1602.16 | 0 | 1602.16 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 104852 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1602.16 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401031A | 106205 | Tool Interconnection Project (Main Tool & Other Vendors) | 654 | P |  | KPOCS2-S | 45308 | 45309 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 106205 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 106205 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2306016A | 106082.4 | F21P1 WWT package (Installation and 2 batch tanks) | 2050 | C |  | TIG 3rd party inspections | 45083 | 45089 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 106082.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 106082.4 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC22C031 | USCSB2402273A | 106000 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3698 | C |  | Housekeeping and Equipment maintenance(Open PO) | 45351 | 45351 | [6 empty] | SEMITEC LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 79539.38 | 0.75037 | 26460.62 | 0 | 26460.62 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6047.5 |  | 31624 |  | 34787.88 |  | 1180 |  | 2360 |  | 2360 |  | 1180 | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C012 | USCSB2408164A | 105977.64 | F21P1 Hot DI Machine Hookup | 4769 | C |  | Proposal TSMC-015 @ ICP_MASS_Side B_ Total Boxes_CPVC_SUS_PFA_Support Installations_Side A. Paint_(Rev.1)_Batch 2/2 | 45535 | 45546 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 105977.64 | 105977.64 | 0 | 0 | [73 empty] | -
Base-Build | Chemical | Material | DCR Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2301026A | 105938.22 | F21P1 Chemical & WCCS package | 1648 | C |  | Upsizing conductors | 44937 | 44944 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 105938.22 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 105938.22 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310086A | 105542.89 | F21P1-0404_H_labor for 50 tools_MICU | 2747 | C |  | LABEL | 10/13/2023 8/23/2024 | 2/13/2024 8/29/2024 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Jen-Ping Tsai | [11 empty] | 105480.67 | 0.99941 | 62.22 | 0 | 62.22 | 0 | [49 empty] | 104606.89 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 873.78 | - | 0 | 0 | 0
Others | Liquid Penetrant | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C035 | USCSB2212013A | 105516.7 | CAP_A_90772_F21 Phone call base build and Liquid penetrant testing system | 1586 | C |  | F21 Phone call base build and Liquid penetrant testing system | 44902 | 44909 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 105516.7 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 105516.7 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312072A | 105000 | Tool Interconnection Project (Main Tool & Module) | 616 | P |  | KPAP02-T Interconnect Labor | 45281 | 45288 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 105000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 105000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306024A | 104862.83 | Tool Interconnection Project (Main Tool & Module) | 309 | P |  | KPI401-T UMEC - LABOR | 45085 | 45100 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 104862.83 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2225.53 |  |  |  |  | 0 | 0 | 0 | 0 |  | 102637.3 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308004A | 104862.83 | Tool Interconnection Project (Main Tool & Module) | 354 | P |  | KPI401-S University Medical Engineering Contractor Labor Pay | 45140 | 45199 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 104862.83 | 0 | 104862.83 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2310007A | 104813.23 | F21P1-0404_H_labor for 50 tools_MICU | 2670 | C |  | Galv. st Duct | 2023/10/3 2023/10/17 | 45217 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 104813.23 | 0 | 104813.23 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311071A | 104729 | Tool Interconnection Project (Main Tool & Module) | 539 | P |  | PVC Piping | 45257 | 45268 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 104729 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 104729 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C009 | USCSB2401252A | 104396.2 | F21P1 WWT package (Installation and 2 batch tanks) | 3433 | C |  | WWT commissioning chemical | 45322 | 45328 | [6 empty] | Kurita America Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 81863.88 | 0.78417 | 22532.32 | 0 | 22532.32 | 18010.0536 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 15659.43 | 81863.88 |  |  | 15659.43 |  |  |  | 15659.43 |  | 4093.194 |  | - | 4093.194 | 4093.194 | 5730.4716 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC24C008 | USCSB2404198A | 104387.04 | UPW B Side Project | 4177 | C | -02 | Materials for Train 2 from Taiwan Supplier | 45408 | 2024/4/30 2024/5/6 2024/5/14 | -42.46 | 104429.5 |  | V |  |  | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | R1: Items 8, 9, 10 out of stock R2: Item 006 is out of stock | [13 empty] | 104387.04 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 104387.04 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403040A | 104305.57 | Tool Interconnection Project (Main Tool & Other Vendors) | 866 | P |  | KDSTS5 IC - DNS SCREEN INTERCONNECTS - 2/2-3/4/2024. | 45360 | 45363 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 104305.57 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 104305.57 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C031 | USCSB2211033A | 104295 | CAP_E_F21P1 AMHS MML Seismic Foundation | 1566 | C |  | AMHS APK&UPK iron plate | 44889 | 44895 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 104295 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 12605.5 |  | 29781 |  | 37667 |  |  | 0 | 19026.75 | [5 empty] | 0 | 0 | 0 | 0 |  | 5214.75 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405047A | 104094.82 | Tool Interconnection Project (Main Tool & Other Vendors) | 1089 | P |  | KDCRS4 - DNS SCREEN INTERCONNECT | 45426 | 45429 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 104094.82 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 104094.82 | [10 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C004 | USCSB2211022A | 104000 | F21P1 WWT package （USA EQ-FRP tank) | 1556 | C |  | WWT welding machines rentals from Megaunion | 44883 | 44886 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 104000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 104000 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406039A | 103121 | Chemical & WCCS B Side Project | 4265 | C |  | CHEM_CDS/ SDS/ WCCS_ SUS project_LINDE_ ARGON, REFRIGERATED LIQUID*200pcs | 45449 | 45455 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 15342.46 | 0.14878 | 87778.54 | 3570 | 84208.54 | 0 | [66 empty] | 3377.61 |  | 1957.92 |  | 5948.03 |  | 4058.9 | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401017A | 102986 | Tool Interconnection Project (Main Tool & Other Vendors) | 641 | P |  | KPE603-T Labor | 45302 | 45309 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 102986 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 102986 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2305027A | 102810.49 | Tool Hookup Material (UPW&Chemical) | 1950 | C | -01 | QR Lab UPW DP Material | 2023/5/6 2023/5/17 | 2023/5/15 2023/5/19 | -90282.21 | 193092.7 |  |  | V |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | There was a decrease in the quantity required by TSMC |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 102810.49 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 91386.79 |  |  | 1925.6 | 0 | 0 | 0 |  | 0 | 9498.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2209023A | 102627.93 | F21P1 QR Lab Security & CCTV | 1475 | C |  | F21P1 MFG_Security&CCTV Package | 44824 | 44830 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 83421 | 0.81285 | 19206.93 | 0 | 19206.93 | 0 | [28 empty] | 0 |  |  |  | 83421 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2310039A | 102000 | Tool Interconnection Project (Main Tool & Module) | 459 | P |  | Labor - Cable pull and chemical sus line install | 45217 | 45237 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 102000 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 102000 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401070A | 101870.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 690 | P |  | Labor and materials for KDSNB1 | 45316 | 45317 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 96947.38 | 0.95168 | 4922.82 | 0 | 4922.82 | 0 | [47 empty] | 0 | 0 | 0 | 92169.02 |  | 0 | 4778.36 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312061A | 101870.2 | Tool Interconnection Project (Main Tool & Module) | 607 | P |  | Manpower Pay for KDSTS1 with BRAHMA GROUP | 2023/12/16 2023/12/20 | 45314 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | PR R1: because we are anticipating them working OT so we took the day |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 92114.55 | 0.90423 | 9755.65 | 0 | 9755.65 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 62984.26 |  | 29130.29 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312063A | 101870.02 | Tool Interconnection Project (Main Tool & Module) | 609 | P | -01 | Manpower Pay for KDSTS4 with BRAHMA GROUP | 45276 | 2023/12/18 2024/2/27 | 91683 | 10187.02 | V |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | PR R1: 10x Price change in scope. Subcontractor agreed in 18 cents different |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 93705.81 | 0.91986 | 8164.21 | 0 | 8164.21 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 49318.76 | 0 | 44387.05 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C008 | USCSB2303048A | 101729.26 | F21P1 CCTV & Security | 1790 | C |  | Sunrise Phoenix housekeeping services | 44999 | 45000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 101415 | 0.99691 | 314.26 | 0 | 314.26 | 0 | [28 empty] | 0 | 24240 | 77175 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | CO Scope (adding/additional scope) | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2212038A | 101342.71 | F21P1 UPW | 1609 | C |  | LB2 Wall Redesign Cable Tray Changes | 44915 | 44916 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A(Rev01) change order (Wall Redesign LB2 Cable Tray Change) |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 101342.71 | 1 | 0 | 0 | 0 | 10134.28 | [26 empty] | 32964.24 |  | 3896.57 |  | 55919.77 |  |  | 0 |  |  | 3494.99 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 5067.14 | 0 |  | - | 5067.14 | 0 | 5067.14
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2401113A | 101316 | F21P1 Chemical & WCCS package | 3300 | C |  | CDS B side support LB1 | 45308 | 45328 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 5500 | 0.054286 | 95816 | 0 | 95816 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 5500 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2203009A | 100800 | F21P1 WWT package (Installation and 2 batch tanks) | 1344 | C |  | Outsourcing Service Superintendent Lead | 44635 | 44641 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-after acceptance-T/T 30 days (paid as salary based on agreement) | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y |  |  |  | Y |  |  | 100800 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 9495.36 | 16800 |  | 16800 |  | 16800 |  | 16800 |  | 16800 |  | 7304.64 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | Main Contract Scope | CDS | Chemical | Mechanical | Project Outsourcing (專案管理外包人力) | USC21C005 | USCSB2208007A | 100800 | F21P1 Chemical & WCCS package | 1444 | C |  | Chemical Superintendent Outsourcing | 44784 | 44785 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | Y | [6 empty] | 70047.84 | 0.69492 | 30752.16 | 0 | 30752.16 | 0 | [16 empty] | 8033.76 |  | 16126.56 |  | 17808 |  | 15960 |  | 12119.52 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410044A | 100480 | Tool Hook Up E2 Trade Equipment Rental | 4987 | C |  | HK_Hueng Luei_Equipment Rental_2nd PO_End date 8/31/2024 | 45568 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 100480 | 0 | 100480 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2306120A | 100429 | F21P1 Chemical & WCCS package | 2153 | C |  | MIC / CDS Tank Relocation | 45105 | 45135 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 100429 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 100429 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2310147A | 100297 | WWT Change Order (Piping) | 2803 | C |  | WWT-Chad lab drain-6.5 line | 45223 | 45225 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 95282 | 0.95 | 5015 | 0 | 5015 | 4764.1 | [42 empty] | 0 | 0 |  | 0 | 95282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 4764.1
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2408044A | 100268 | WWT B side Project | 4635 | C |  | LB2 GIP Blower material supplement_WWT | 45513 | 45525 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 100268 | 0 | 100268 | [74 empty] | -
Base-Build | Base-Build | Outsourcing |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC22C006 | USCSB2211006A | 100000 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1541 | C |  | TSMC F21 AZ On-site Construction Coordination | 44869 | 44873 | [6 empty] | SYNERGY Engineering Consultants | PR Approved | PO Approved | extension order for USCSB2205027A |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 100000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | MIMO/Rigging |  |  | Others |  |  | USC23C002 | USCSB2404214A | 100000 | F21P1-0404_H_Hallway plate install_MICU | 3965 | C |  | CGS move in labor support | 45412 | 45414 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 56954.87 | 0.56955 | 43045.13 | 23874.38 | 19170.75 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 37579.54 | 0 | 19375.33 | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407064A | 100000 | WWT B side Project | 4461 | C |  | WWT: OPEN PO III | 45484 | 2024/7/16 2024/7/24 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | PO R1: Change Contract Out Name | [13 empty] | 93016.68 | 0.93017 | 6983.32 | 93280.45 | -86297.13 | 0 | [71 empty] | 0 |  | 93016.68 | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310133A | 100000 | F21P1-0404_H_labor for 50 tools_MICU | 2790 | C |  | Shared material. labels and label makers. Open PO October to November | 45219 | 45233 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 93842.83 | 0.93843 | 6157.17 | 0 | 6157.17 | 0 | [42 empty] | 0 | 0 | 15948 | 0 | 0 | 9778.85 | 36248.54 | 0 | 2473.4 |  | 0 | 0 | 0 |  | 0 | [9 empty] | 6430.84 |  |  |  | 22963.2 | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2201008A | 100000 | F21P1 VOC package （Installation ) | 1325 | C |  | tsmc F21P1 VOC 雜項工程 | 44587 | 44589 | [6 empty] | Desiccant Technology Corporation | PR Approved | PO Approved |  | 100% upon receipt- T/T 30 days (after acceptance) | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y | [6 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 100000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | MIMO/Rigging |  |  | Others |  |  | USC22C008 | USCSB2207002A | 100000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1417 | C |  | Rigging at new Warehouse | 44744 | 44750 | [6 empty] | MEI Rigging & Crating, LLC | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 41132.5 | 0.41132 | 58867.5 | 0 | 58867.5 | 0 | [14 empty] | 15040 |  | 22560 |  | 3532.5 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC22C014 | USCSB2403029A | 100000 | F21P1 AMHS Power Panel | 3738 | C |  | General laborer and Housekeeping&Superintendent Service (Open PO) | 45356 | 45358 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 64821.62 | 0.64822 | 35178.38 | 0 | 35178.38 | 0 | [52 empty] | 0 | 0 | 22195.06 |  | 12832.56 |  |  |  | 29794 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C003 | USCSB2303065A | 100000 | F21P1 Module Tool Interconnection CVD | 1804 | C |  | O3 detector | 45001 | 45029 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 100000 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2209015A | 100000 | F21P1 Slurry package | 1467 | C | -01 | TSMC MIC Fab Chemical, Piping and Electrical Design | 2022/9/15 2023/2/1 | 2022/9/19 2023/2/6 | 90000 | 10000 | V |  |  |  | KAEKO, Inc | PR Approved | PO Approved | USCSB2207010A Change order | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 96990 | 0.9699 | 3010 | 0 | 3010 | 0 | [25 empty] | 30000 |  |  | 66990 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312043A | 100000 | F21P1-0404_H_labor for 50 tools_MICU | 3036 | C |  | Shared material. labels and label makers. Open PO | 45267 | 45275 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 98559.81 | 0.9856 | 1440.19 | 0 | 1440.19 | 0 | [45 empty] | 0 | 0 | 0 | 534 | 0 | 1419.39 | 9856 | 0 | 0 | 33335.8 |  | 0 |  | 1567.92 |  |  |  | 12542.75 |  |  |  | 89.99 |  | 37824 |  | 1389.96 | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2306001A | 100000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2036 | C |  | Brycon Cleanroom cancelled contract | 45078 | 45097 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 62288.08 |  |  |  |  | 0 | 24454.75 | 0 | 0 |  | 13257.17 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Housekeeping | Main Contract Scope | CDS | Chemical | Mechanical | Housekeeping | USC21C005 | USCSB2309112A | 100000 | F21P1 Chemical & WCCS package | 2584 | C |  | Site Housekeeping | 45188 | 45188 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 97960 | 2040 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC22C006 | USCSB2308139A | 100000 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 2434 | C |  | Liberty May 03 | 45161 | 45163 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 100000 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C059 | USCSB2310155A | 100000 | F21P1 Foundation T&M | 2810 | C |  | Foundation T&M for PCI | 45223 | 45238 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 39524 | 0.39524 | 60476 | 0 | 60476 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 3116 | 0 |  |  | 0 | 0 | 2624 |  | 0 |  | 19188 |  | 3444 | [5 empty] | 1312 |  |  |  | 9840 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Electrical | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2204002A | 100000 | F21P1 WWT package (Installation and 2 batch tanks) | 1352 | C |  | MICU人力支援 | 44652 | 44657 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 100000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312012A | 99953.6 | Tool Interconnection Project (Main Tool & Module) | 562 | P |  | KPAN02-S LIT 1 UMEC | 45262 | 45266 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 99953.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 99953.6 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | The budget execution does not pertain to this project | AMC THC | Low Voltage | Mechanical | M+L | USC21C008 | USCSB2403263A | 99907.93 | F21P1 CCTV & Security | 3956 | C |  | F21 P1 EBO AMC gas hookup | 45378 | 45383 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 99907.93 | 1 | 0 | 0 | 0 | 99907.93 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 19982 |  |  |  | 19982 | 99907.93 | 24976.98 |  | - | 24976.98 | 44958.57 | $14,987.00 | 4995.4
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2306135A | 99625 | F21P1 Chemical & WCCS package | 2168 | C |  | TSMC Offload June | 45106 | 45132 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 99625 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 99625 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Outsourcing |  |  | Others |  |  | USC22C008 | USCSB2307068A | 99600 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2235 | C |  | TEOPM-Team Member Staffing of Alexander Martinez | 45122 | 45127 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 87818.18 | 0.88171 | 11781.82 | 0 | 11781.82 | 0 | [38 empty] | 9183 |  | 16762 | 0 | 16185 | 0 |  | 0 | 15808.18 | 0 | 13280 | 16600 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2306001A | 99600 | Tool Interconnection Project (Main Tool & Module) | 286 | P |  | Travis Hand -Project Coordinator (6 month) | 45079 | 45083 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 87991.12 | 0.88344 | 11608.88 | 0 | 11608.88 | 0 | [33 empty] | 0 |  |  | 11855.72 |  | 14715.4 |  | 16600 | 0 | 12450 | 0 |  | 0 | 16600 | 0 | 15770 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2312062A | 99600 | Tool Interconnection Project (Main Tool & Module) | 608 | P |  | Project Coordinator, Robert Almanza, Tool Interconnect, 6 month contract at $16,600 | 45276 | 45280 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 43701.7 | 0.43877 | 55898.3 | 0 | 55898.3 | 0 | [45 empty] | 0 | 16786.02 | 12805.68 | 14110 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2207022A | 99600 | F21P1 WWT package (Installation and 2 batch tanks) | 1437 | C |  | Water Systems Superintendent _Rod Copas | 44768 | 44776 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After Acceptanc | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 92742.52 | 0.93115 | 6857.48 | 0 | 6857.48 | 0 | [16 empty] | 12991.16 |  | 18855.02 |  | 17845 |  | 17015 |  | 18504.02 |  | 7532.32 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Outsourcing |  |  | Others |  |  | USC22C008 | USCSB2311034A | 99600 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2889 | C |  | TEOPM Functional Area Staffing Proposal for Coordinator Emmanuel Urias | 45238 | 45244 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 77276.2 | 0.77587 | 22323.8 | 0 | 22323.8 | 0 | [43 empty] | 0 |  | 0 | 35645.02 | 18121 | 7553 | 0 | 15957.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2306006A | 99600 | Tool Interconnection Project (Main Tool & Module) | 291 | P |  | Roberto Almanza-Superintendent (6 month) | 45079 | 45084 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 99600 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 31209.76 |  | 16679 |  | 16790 |  | 15978.9 | 0 | 16730 | 0 |  | 0 | 2212.34 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2312036A | 99600 | Tool Interconnection Project (Main Tool & Module) | 583 | P |  | For the PO renewal of Daniel Dircio, in the Project Coordinator (Tool Interconnect) position. 6 month PO for the amount of 99,600.00 | 45268 | 45273 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 40778.6 | 0.40942 | 58821.4 | 0 | 58821.4 | 0 | [45 empty] | 0 | 0 | 0 | 40778.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Outsourcing |  |  | Others |  |  | USC22C008 | USCSB2306090A | 99600 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2123 | C |  | TEOPM | 45098 | 45104 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 92068.27 | 0.92438 | 7531.73 | 0 | 7531.73 | 0 | [33 empty] | 0 |  | 16279.65 | 37811 |  | 19785.5 |  | 18192.12 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2306005A | 99600 | Tool Interconnection Project (Main Tool & Module) | 290 | P |  | Cody Seery-Project Coordinator (6 month) | 45079 | 45084 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 99395 | 0.99794 | 205 | 0 | 205 | 0 | [33 empty] | 0 |  |  | 16600 |  | 8300 |  | 16600 | 0 | 16600 | 0 |  | 0 | 16600 | 0 | 24695 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2306003A | 99600 | Tool Interconnection Project (Main Tool & Module) | 288 | P |  | Josue Daniel Dircio-Project Coordinator (6 month) | 45079 | 45084 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 99568.24 | 0.99968 | 31.76 | 0 | 31.76 | 0 | [33 empty] | 0 | 11441.88 |  | 16860 |  | 17035 |  | 17398.38 | 0 | 20624.2 | 0 |  | 0 | 1708.78 | 0 | 14500 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404019A | 99495 | Tool Interconnection Project (Main Tool & Other Vendors) | 974 | P |  | KPE604-S EUV ASML Cabinet Connection Support Labor | 45386 | 45393 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 99495 | 0 | 99495 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312015A | 99334.7 | Tool Interconnection Project (Main Tool & Module) | 564 | P |  | KPAP02-S LIT 1 UMEC | 45262 | 45266 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 99334.7 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 99334.7 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C008 | USCSB2410011A | 99255.87 | UPW B Side Project | 4956 | C |  | UPW Mezz 3 & 4 Painting | 45566 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 99255.87 | 0 | 99255.87 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407113A | 99000 | TSMC Fab 21 P1B Tool Hook Up | 4528 | C |  | independent QAQC services to MIC | 45492 | 45498 | [6 empty] | Independent QA/QC Services Inc. | PR Approved | PO Approved | [14 empty] | 17568 | 0.17745 | 81432 | 66132 | 15300 | 0 | [73 empty] | 17568 |  |  | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2403244A | 98660 | F21P1 Chemical & WCCS package | 3937 | C |  | CDS INSTALL VMB WITH SUPPORTS TSMC-008 | 45377 | 45378 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 84899.61 | 0.86053 | 13760.39 | 13760.39 | 0 | 4933 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 93727 | 84899.61 |  |  |  |  | 4933 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401141A | 98379 | F21P1-0404_H_labor for 50 tools_MICU | 3326 | C |  | Terminal for HK power trade | 45310 | 45310 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 79794 | 0.81109 | 18585 | 26727 | -8142 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 58296 |  | 4053 |  | 4218 | [12 empty] | 0 |  | 13227 | 0 | 0 | 0
Base-Build | W-H2SO4 |  | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2405166A | 98303 | F21P1 WWT package (Installation and 2 batch tanks) | 4194 | C |  | WSR 廢硫酸缺料接點 | 45441 | 45446 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 98303 | 0 | 98303 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2401177A | 97923.66 | F21P1 UPW | 3362 | C |  | REI PCOs 26,28,37,39,46,52 | 45314 | 45316 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 97923.66 | 1 | 0 | 97923.66 | -97923.66 | 195847.32 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 97923.66 |  | 97923.66 | 0 | 97923.66 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404007A | 97601.09 | Tool Interconnection Project (Main Tool & Other Vendors) | 962 | P |  | KDCCS3- DNS SCREEN INTERCONNECTS 3/8-3/27/2024 | 45384 | 45387 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 97601.09 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 97601.09 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312074A | 97468.5 | F21P1-0404_H_labor for 50 tools_MICU | 3066 | C | -01 | Tool Hookup Terminals a Replacement for USCSB2311101 | 45273 | 2023/12/15 2023/12/19 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Change Comletion Date |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 97468.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 74476.4 |  |  | 0 | 0 | 6114.1 |  | 9860.4 |  | 7017.6 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Equipment | Main Contract Scope | SDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USCSB2209032A | 97367 | F21P1 Slurry package | 1484 | C |  | Slurry VMBs | 44834 | 44838 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | USC2112014A Change Order (credit $45,408) | 30%-30%-30% by progress-Net 30days-After acceptance; 10% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 74961.12 | 0.76988 | 22405.88 | 0 | 22405.88 | 22405.88 | [20 empty] | 74961.12 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 22405.88 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Civil | M+L | USC24C006 | USCSB2408077A | 97275 | WWT B side Project | 4693 | C |  | WWT - FRP membrane atpads- dike walls around Tmah expansion LB2 N.5 | 45520 | 45534 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 97275 | 77820 | 19455 | 0 | [73 empty] | -
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2309013A | 96801 | F21P1-0404_H_Hallway plate install_MICU | 2491 | C |  | AWT room angle supports installation | 45175 | 45198 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 70739.19 | 0.73077 | 26061.81 | 0 | 26061.81 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 22338.69 | 0 |  |  | 0 | 0 | 11169.35 |  | 0 |  |  |  | 37231.15 | [10 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C055 | USCSB2410040A | 96500 | F21P1-0404_H_labor for 50 tools_MICU | 4983 | C |  | HK_Wholetech_Equipment Rental_1st PO_End date 12/31/2024 | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 96500 | 0 | 96500 | 0
Base-Build | UPW | Material | The budget execution does not pertain to this project | Penetration Pipe | WWT | Civil | M+L | USC21C003 | USCSB2211019A | 96460 | F21P1 UPW | 1553 | C |  | Embedded pipes fire sealants | 2022/11/16 2023/2/17 | 44994 | [6 empty] | Kinpo Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 0 | 0 | 96460 | 0 | 96460 | 57876 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 48230 | [5 empty] | 0 |  | - | 28938 | 0 | 28938
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USC2112016A | 96000 | F21P1 Slurry package | 83 | P |  | Chemical Resistant Tubing | 44539 | 44546 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 90% by received, Net 30days; 10% by acceptance, Net 30days(after acceptance in 60days). | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 96000 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 96000 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | UMEC | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2403048A | 95913 | F21P1 Chemical & WCCS package | 3755 | C |  | CDS UPW - 8-195 AOR HFC HFD Chem Drains | 45357 | 45363 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 95913 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 91117 | 0 |  | 4796 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Site Expense | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404166A | 95487 | WWT B side Project | 4148 | C |  | WIDOS WELDING MACH. | 45405 | 45407 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 95487 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 95487 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USC2111018A | 94829.03 | F21P1 UPW | 32 | P | -01 | pressure transmitter | 44511 | 44546 | 1920.24 | 92908.79 |  |  |  |  | Ashcroft Inc. | PR Approved | PO Approved | 5/27採購異動(規格變05/06item) | 100% up front. | York Yeh | FOB- Stratford, CT | 2 years | Sterling Ellis | York Yeh | N | 44566 | Matt |  | N | 5000 |  | 94829.03 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 60000 | [11 empty] | 12580.79 |  | 22248.24 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | Main Contract Scope | CDS | Chemical | Electrical | Housekeeping | USC21C005 | USCSB2306130A | 94800 | F21P1 Chemical & WCCS package | 2163 | C |  | Hua Yi housekeeping | 45106 | 45124 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 94800 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 94800 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C007 | USCSB2305009B | 94680 | F21P1 Module Tool Interconnection PVD1-2 | 1934 | C |  | TSMC AZ F21 DI MAX | 45049 | 2023/5/11 2023/6/16 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 94680 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 85212 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9468 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2302033A | 94400 | Tool Hookup Material (UPW&Chemical) | 1714 | C |  | HK Chemical Bushing | 44971 | 44978 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 94400 | 0 | 94400 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C012 | USCSB2402149A | 94329 | F21 Barcode RFID System | 3582 | C |  | UPW-UMEC-LB2 A.5/L10 Q.5 Design change | 45337 | 45344 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 86577 | 0.91782 | 7752 | 0 | 7752 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 86577 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USC2111009A | 93800 | F21P1 Chemical & WCCS package | 28 | P |  | I LINE PANEL,Mains Panel | 44509 | 44515 | [6 empty] | OEG ISG - Integrated Systems Group | PR Approved | PO Approved |  | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh | DDP | 24 months warranty after received | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 93800 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 93800 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403096A | 93500 | F21P1-0404_H_labor for 50 tools_MICU | 3798 | C |  | BUR BTCGC1/0SS GROUND CLAMP | 45360 | 45363 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 93500 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 93500 | - | 0 | 0 | 0
Base-Build | Water | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2312035A | 93494 | WWT Change Order (Piping) | 3028 | C |  | WWT-UPW RO to T780 and 780 temp plates | 45288 | 45288 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 93494 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 88819 | 0 | 0 | 0 |  | 4675 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical |  | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2406051A | 93450 | F21P1 Chemical & WCCS package | 4276 | C |  | FAB A CDS-WCCS Permit Revision | 45450 | 45454 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 93450 | 53220 | 40230 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2212027A | 93422.41 | F21P1 WWT package (Installation and 2 batch tanks) | 1600 | C |  | 1st Set of Clamps | 44911 | 44916 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 85363.72 | 0.91374 | 0 | 0 | 0 | 0 | [26 empty] | 83828.73 |  | 1534.99 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 3736.8964 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | 200 Plate | Equipment |  |  | Others |  |  | USC22C006 | USCSB2303086A | 93360 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1823 | C |  | 200 Distribution Plates | 45009 | 45016 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 93360 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 93360 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404110A | 92838 | Chemical & WCCS B Side Project | 4095 | C |  | CPVC 料補齊.1 | 45397 | 45399 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 92838 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 76428 |  |  |  | 16410 | 16410 | [5 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Equipment |  |  | Others |  |  | USC23C002 | USCSB2309012A | 92837.8 | F21P1-0404_H_Hallway plate install_MICU | 2490 | C |  | 3 first floor EUV pump foundations installation | 45175 | 45194 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 88195.91 | 0.95 | 4641.89 | 0 | 4641.89 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 88195.91 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC23C058 | USCSB2312066A | 92660 | F21 EUV Steel Plates | 3058 | C |  | EUV Temp Power Generator Rental 4 M | 45269 | 45275 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 92660 | 0 | 92660 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C007 | USCSB2404219A | 92648 | F21P1 Module Tool Interconnection PVD1-2 | 3970 | C |  | F21 AMAT PVD DI MAX *37 SET | 45412 | 45427 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 92648 | 92648 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409022A | 92440.86 | Tool Interconnection Project (Main Tool & Other Vendors) | 1225 | P |  | Pipe removal and added construction 3/8" *4/1/4" X3/8" *6 (KCANN2) | 45547 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 92440.86 | 0 | 92440.86 | 0 | [73 empty] | -
Base-Build | CCTV | Material | The budget execution does not pertain to this project | 0 | Low Voltage | Electrical | M+L | USC21C008 | USCSB2201009A | 92382.74 | F21P1 CCTV & Security | 1326 | C | -01 | Access Control/Wifi/CCTV in new Office/Warehouse | 44589 | 44602 | 3946.98 | 88435.76 | V | V |  |  | Galaxy3 LLC | PR Approved | PO Approved | Some material/work was not necessary/changed, so the price has been reduced | According to Contract 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | N | [6 empty] | 92382.74 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 92382.74 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2308108A | 92340.75 | F21P1 UPW | 2405 | C |  | Page Observation for FAB and WRC UPW | 45157 | 45163 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 92340.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 92340.75 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Heating Jacket | Labor |  |  | Others |  |  | USC23C035 | USCSB2404136A | 92000 | TSMC F21 Heating Jacket Installation | 4120 | C |  | Heating Jacket Manpower | 45399 | 45401 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | [14 empty] | 34500 | 0.375 | 57500 | 11500 | 46000 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 11500 | [9 empty] | 11500 | 0 | 11500 | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2205027A | 91640 | F21P1 WWT package (Installation and 2 batch tanks) | 1389 | C | -01 | SYNERGY/MICU tsmc F21 Arizona On-site Engineer | 2022/5/26 2024/5/7 | 2022/5/27 2024/5/7 | -8360 | 100000 | V |  |  |  | SYNERGY Engineering Consultants | PR Approved | PO Approved | R1: As per SYNERGY:Ting Sheng Wang to closed out the PR | 100% by progress(after design documents hand over)-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 91640 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 50000 |  |  |  | 0 |  | 41640 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2302023A | 91234 | F21P1-0404_H_Hallway plate install_MICU | 1704 | C |  | 600Kits urgent ABglue for foundation | 44967 | 44974 | [6 empty] | White Cap, LP | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 91234 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 91234 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Material | USC24C005 | USCSB2406115A | 91105.48 | Chemical & WCCS B Side Project | 4355 | C |  | F21P1 HPM L10B CDU/DHL CDA/GN2 | 45465 | 45469 |  | 65 |  |  |  |  | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 75213.52 | 0.82557 | 15891.96 | 32376.94 | -16484.98 | 0 | [66 empty] | 15344.62 |  | 29433.62 |  | 13950.3 |  |  | 16484.98 |  |  | 0
Base-Build | WWT | Equipment | CO Scope (adding/additional scope) | WWT | WWT | Civil | M+L | USC23C045 | USCSB2310100A | 91000 | WWT Change Order (Piping) | 2762 | C |  | WWT-Swing gate | 45216 | 45219 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 85670 | 0.94143 | 5330 | 0 | 5330 | 5933.2 | [41 empty] | 0 | 0 | 0 |  | 0 | 41210 | 0 | 0 | 0 |  | 1560 | 0 | 37960 | 2600 |  | 0 |  | 1040 |  |  |  | 390 |  |  | 2730 |  |  |  | 3640 |  | 0 | 910 | - | 0 | 0 | 0 | 5933.2
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2407125A | 90936.22 | F21P1 AMHS Power Panel | 4539 | C |  | HPM Area Tray Relocation Material | 45493 | 45497 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 90936.22 | 90936.22 | 0 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401005A | 90929.86 | Tool Interconnection Project (Main Tool & Other Vendors) | 629 | P |  | KPOCS1 Exhaust Install Labor | 45300 | 45311 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 90929.86 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 90929.86 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306020A | 90663.8 | Tool Interconnection Project (Main Tool & Module) | 305 | P |  | KPOCT5-S UMEC LABOR | 45085 | 45100 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 90663.8 | 0 | 90663.8 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405049A | 90194.58 | Tool Interconnection Project (Main Tool & Other Vendors) | 1091 | P |  | KDCCS1-DNS SCREEN INTERCONNECTS | 45426 | 45429 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 90194.58 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 90194.58 | [10 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2401052A | 90000 | F21P1 AMAT Interconnection | 3242 | C |  | overtime for Day & Night workers | 45301 | 45306 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 90000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 29700 | 0 | 60300 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311029A | 90000 | Tool Interconnection Project (Main Tool & Module) | 503 | P |  | KPE603-T HYC LABOR | 45240 | 45247 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 90000 | 0 | 90000 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401095A | 90000 | Tool Interconnection Project (Main Tool & Other Vendors) | 712 | P |  | KPE605-S Labor | 45321 | 45325 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 90000 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 90000 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC24C005 | USCSB2405132A | 90000 | Chemical & WCCS B Side Project | 4160 | C |  | F21P1A L10 Pump area WLS Aegis panel 工程 | 45435 | 45451 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 90000 | 0 | 90000 | 0 | [73 empty] | - |  |  | 0
Base-Build | VOC | Material | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Labor | USC21C007 | USCSB2203005A | 90000 | F21P1 VOC package （Installation ) | 1340 | C |  | 轉輪及煙囪預組裝費用 | 44624 | 44627 | [6 empty] | Desiccant Technology Corporation | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | VOC(N) | [6 empty] | 85500 | 0.95 | 4500 | 0 | 4500 | 4500 | [26 empty] | 85500 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 4500
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2402032A | 89971.2 | F21P1-0404_H_labor for 50 tools_MICU | 3475 | C |  | filter | 45325 | 45335 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 89971.2 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 89971.2 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C047 | USCSB2406034A | 89813.46 | F21P1 HK Seismic Installation | 4260 | C |  | QR, EBO seismic installation. Replacement of PR USCSB2308029 | 45449 | 45454 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 89813.46 | 0 | 89813.46 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404182A | 89754 | Chemical & WCCS B Side Project | 4163 | C |  | L30 HPM Y line divider fixed (A side) | 45406 | 45407 | [6 empty] | JY TECHS INC. | PR Approved | PO Approved | [14 empty] | 89754 | 1 | 0 | 0 | 0 | 89754 | [54 empty] | 0 |  | 0 | [9 empty] | 89754 |  |  |  |  | 89754 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407111A | 89625.85 | WWT B side Project | 4526 | C |  | Installation of Drip Pan (PVC Bag) 追加工程 | 45492 | 45513 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved | [14 empty] | 0 | 0 | 89625.85 | 0 | 89625.85 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401016A | 89040 | Tool Interconnection Project (Main Tool & Other Vendors) | 640 | P |  | KPAN02-T Labor | 45302 | 45309 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 89040 | 0 | 89040 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2306056A | 89000 | F21P1 UPW | 2090 | C |  | Mezzanine Doors and Installation | 45092 | 45106 | [6 empty] | Suncoast Glass & Glazing,LLC dba Mirror Works dba Horn Doors | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 89000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 77180 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 11820 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C001 | USCSB2302038A | 88946.51 | TEL Main Tool Interconnection | 1719 | C |  | Shelving for tool interconnect | 44974 | 44980 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 88946.51 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 66709.88 | 22236.63 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Greenberry | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C011 | USCSB2306118A | 87915 | F21 TMAH System | 2151 | C |  | WRC 2nd floor rack (WWT under TMAH) | 45104 | 45140 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 83519.25 | 0.95 | 4395.75 | 0 | 4395.75 | 87915 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 13187.25 |  |  |  | 13187.25 |  |  | 83519.25 | 13187.25 |  | 17583 |  | - | 17583 | 17583 | 17583 | 17583
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308021A | 87904.5 | Tool Interconnection Project (Main Tool & Module) | 371 | P |  | KPAE01-S UMEC LABOR PAY | 45166 | 45174 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 85101.38 | 0.96811 | 2803.12 | 0 | 2803.12 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 85101.38 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308037A | 87904.5 | Tool Interconnection Project (Main Tool & Module) | 387 | P |  | KPI401-S UMEC LABOR PAY | 45168 | 45199 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 87904.5 | 0 | 87904.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308034A | 87904.5 | Tool Interconnection Project (Main Tool & Module) | 384 | P |  | KPAN01-S UMEC LABOR PAY | 45168 | 45199 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 87904.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 87904.5 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308036A | 87904.5 | Tool Interconnection Project (Main Tool & Module) | 386 | P |  | KPAN02-S UMEC LABOR PAY | 45168 | 45198 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 87904.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 87904.5 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308032A | 87904.5 | Tool Interconnection Project (Main Tool & Module) | 382 | P |  | KPAP01-S UMEC LABOR PAY | 45167 | 45176 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 87904.5 | 0 | 87904.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2207001A | 87671.96 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1416 | C | -01 | Big AZ Tent | 44744 | 44753 | 3731.96 | 83940 |  | V |  |  | Barton Dynamics, LLC dba Big AZ Tents & Events | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 87671.96 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 87671.96 | [7 empty] | 0 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC |  | The budget execution does not pertain to this project | VOC | Low Voltage | Electrical | Labor | USC24C007 | USCSB2405126A | 87354 | Low Voltage B Side Project | 4154 | C |  | F21 P1 VOC system extension GC (MAY/2024) | 45434 | 45451 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 87354 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 87354 | [6 empty] | - |  |  | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC23C045 | USCSB2403249A | 87328 | WWT Change Order (Piping) | 3942 | C |  | UPW-UMEC-COs for MA-137, 162, 172 and 182 | 2024/3/26 2024/7/16 | 2024/5/6 2024/7/16 | -887 | 88215 |  |  |  |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | Order was subsequently revised to new amount. |  | 0 | [11 empty] | 83804 | 0.95965 | 3524 | 0 | 3524 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 49864 |  |  |  | 27632 |  |  | 0 | 6308 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC24C006 | USCSB2405068A | 87147.49 | WWT B side Project | 4088 | C |  | WWT B Side Instrument Batch 1 | 45423 | 45505 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 87147.49 | 0 | 87147.49 | 0 | [56 empty] | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2211024A | 87049.1 | F21P1 UPW | 1558 | C |  | Temp Power Supplier | 44883 | 44886 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 86027.8 | 0.98827 | 1021.3 | 0 | 1021.3 | 0 | [23 empty] | 86027.8 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Equipment | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2301007A | 87026.68 | F21P1 Chemical & WCCS package | 265 | P |  | 2023 Pro XD Mid- Size Crew | 44944 | 44960 | [6 empty] | Iron City Polaris | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 87026.68 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 87026.68 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC23C054 | USCSB2401240A | 86906 | UPW Change Order | 3421 | C |  | UPW-UMEC-B side ACF loading | 45321 | 45321 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 78215 | 0.9 | 8691 | 0 | 8691 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 69525 | 0 |  | 8690 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC24C008 | USCSB2405080A | 86810 | UPW B Side Project | 4100 | C |  | Train 2 ICPMS CO To UMEC | 45426 | 45427 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 65159 | 0.75059 | 21651 | 17310 | 4341 | 0 | [56 empty] | 0 |  |  |  | 65159 | [12 empty] | - |  |  | 0
Base-Build | Base-Build | Internet | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2110001A | 86667 | F21P1 UPW | 1291 | C |  | DIA 200M, Pole, Extension, CPE | 44470 | 44477 | [6 empty] | Chunghwa Telecom Global, Inc | PR Approved | PO Approved |  | 100% after completion (Net 30 Days). | York Yeh | Deliver on Site | 1 year hardware warranty, 8x5xNBD, is included. | Ka In Wong Lane | York Yeh | N | 44519 | Matt |  | N |  |  | 86667 | 1 | 0 | 0 | 0 | 0 |  |  |  | 86667 | [24 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2311113A | 86100 | F21 TMAH System | 2964 | C |  | WWT -Stripper-2"packing for 2 towers | 45258 | 45260 | [6 empty] | LICI PLASTIC INDUSTRY CO. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 86100 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 9828 | 0 | 0 | 0 | 0 |  |  | 55692 | 0 | 0 |  | 0 |  |  |  |  | 4305 |  |  |  | 4305 | 20580 |  |  | 4305 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | 0 | Chemical | Electrical | Material | USC21C009 | USCSB2312116A | 85937.06 | F21P1 WWT package (Installation and 2 batch tanks) | 3106 | C |  | CDS CED MIC A side 2 of 2 per Paul | 45276 | 45280 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 85510.44 | 0.99504 | 426.62 | 0 | 426.62 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 16072.57 | 5133.67 |  | 0 | 0 | 0 |  | 0 |  | 64304.2 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | NUUO | The budget execution does not pertain to this project | AMC THC | Low Voltage | Electrical | M+L | USC21C009 | USCSB2312198A | 85830 | F21P1 WWT package (Installation and 2 batch tanks) | 3185 | C |  | F21 AMC B side Network Engineering | 45290 | 45357 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 81522.75 | 0.94982 | 4307.25 | 126 | 4181.25 | 4422.25 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 51498 | 73230.75 |  |  | 17166 | 8166 |  |  | 126 |  |  | 0 | 4422.25
Base-Build | VOC |  |  |  | Low Voltage | Mechanical | M+L | USC22C013 | USCSB2406127A | 85711.22 | F21P1 QR Lab Security & CCTV | 4366 | C |  | F21-P1_B-Side mask room gas piping hookup_batch 2/2 | 45468 | 2024/7/3 2024/7/8 | 19235.7 | 66475.52 |  |  |  |  | Welmade Technology Corporation | PR Approved | PO Approved | R1: Per supplier request to split the amount to align with quote item# for USCSB2406126A & 127A - Total stays the same | [13 empty] | 0 | 0 | 85711.22 | 0 | 85711.22 | 85711.22 | [73 empty] | - | 12856.68 | 17142.24 | 51426.74 | 4285.56
Base-Build | Chemical | Labor | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC24C005 | USCSB2404184A | 85680 | Chemical & WCCS B Side Project | 4165 | C |  | FAB B Chemical Electrical Permit + CA | 45406 | 45408 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 56380 | 0.65803 | 29300 | 0 | 29300 | 85680 | [54 empty] | 0 |  | 0 | [5 empty] | 20790 | [5 empty] | 35590 |  |  | 85680 |  | - | 0 | 0 | 0
Base-Build | Speed Gate | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC21C002 | USCSB2103005A | 85570 | TSMC AZ Temp Office Speed Gate | 1271 | C |  | tsmc AZ office speed gate engineering | 44278 | 44279 | [6 empty] | B&D Industries, Inc. | PR Approved | PO Approved |  | 100% by progress , T/T 7 Days | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang |  |  | Henry |  | N |  |  | 85570 | 1 | 0 | 0 | 0 | 0 | 85570 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2309125A | 85355.14 | F21P1 Chemical & WCCS package | 2596 | C |  | Boxes for bridge/HPM/clean room of CDS system. | 45190 | 45194 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 85355.14 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 85355.14 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2301059A | 85302 | F21P1 UPW | 1675 | C |  | Temp CP piping labor | 44954 | 44967 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 85302 | 0 | 85302 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC21C014 | USCSB2309080A | 85243.41 | F21P1 WH2SO4 | 2554 | C |  | F21 P1 CCTV Engineering | 45184 | 45200 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 85243.41 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 85243.41 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408043A | 85235.57 | Tool Interconnection Project (Main Tool & Other Vendors) | 1192 | P |  | KEPST4 Conduit and Wire Pull | 45521 | 45532 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 85235.57 | 85235.57 | 0 | 0 | [73 empty] | -
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2206007A | 85200 | F21P1 WWT package (Installation and 2 batch tanks) | 1398 | C |  | DOCK COORDINATOR | 44715 | 44725 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 85200 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 12170.82 |  | 14200 |  | 14200 |  | 12170.82 |  | 16330 |  | 15265 |  | 863.36 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310066A | 85000 | F21P1-0404_H_labor for 50 tools_MICU | 2727 | C |  | HK Exhaust Galvanized Hardware | 45210 | 45209 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 85000 | 0 | 85000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401201A | 84512 | F21P1 Chemical & WCCS package | 3386 | C |  | CDS Required maintenance and pressure switches for the CO2 systems, 24 for Lorry and 52 for Fab A | 45316 | 45320 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 84512 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 21128 | 63384 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C011 | USCSB2304004A | 84250 | F21 TMAH System | 1845 | C |  | MIC MAU Generator | 45017 | 45020 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 84250 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 84250 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Labor | USC24C006 | USCSB2408070A | 84115.95 | WWT B side Project | 4686 | C |  | WWT CDA system branch - CRG | 45519 | 45520 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 84115.95 | 0 | 84115.95 | 0 | [73 empty] | -
Base-Build | Base-Build | Labor | Main Contract Scope | UPW | UPW | Electrical | QAQC | USC21C003 | USCSB2307070A | 84100 | F21P1 UPW | 2237 | C |  | Shermco Special Inspection Test | 45125 | 45128 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 23200 | 0.27586 | 60900 | 0 | 60900 | 0 | [37 empty] | 11600 |  |  | 0 | 0 | 0 | 0 |  | 0 | 11600 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USC2404044A | 83827.14 | F21P1 AMAT Interconnection | 998 | P |  | 2,4,6,8,10,12 AWG wire | 45391 | 45399 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | 0 | [11 empty] | 83827.14 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 8589.5 |  | 75237.64 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402028A | 83728 | Tool Interconnection Project (Main Tool & Other Vendors) | 754 | P |  | KPAN03-T Labor | 45325 | 45336 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 83728 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 83728 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Steel | Labor | USC23C045 | USCSB2406066A | 83260 | WWT Change Order (Piping) | 4298 | C |  | Pipe support _Hua Yi close PR_ batch 1/2 | 45455 | 45462 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 83260 | 0 | 83260 | 99912 | [71 empty] | 41630 |  | - | 24978 | 24978 | 8326 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2409056A | 82865.99 | F21P1 AMHS Power Panel | 4852 | C |  | Urgent AMHS Material for NUUO | 45552 | [7 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 82865.99 | 0 | 82865.99 | 0 | [73 empty] | -
Base-Build | Base-Build | Scaffolding | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C045 | USCSB2308141A | 82841.89 | WWT Change Order (Piping) | 2436 | C |  | Liberty May 05 | 45161 | 45163 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 82841.89 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 82841.89 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308044A | 82663.8 | Tool Interconnection Project (Main Tool & Module) | 394 | P |  | KPOCT9-T UMEC LABOR PAY | 45168 | 45177 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 82663.8 | 0 | 82663.8 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308042A | 82663.8 | Tool Interconnection Project (Main Tool & Module) | 392 | P |  | KPOCT4-T UMEC LABOR PAY | 45168 | 45180 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 54397.65 | 0.65806 | 28266.15 | 0 | 28266.15 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 54397.65 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308033A | 82545.8 | Tool Interconnection Project (Main Tool & Module) | 383 | P |  | KPAN01-T UMEC LABOR PAY | 45168 | 45176 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 82545.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308020A | 82545.8 | Tool Interconnection Project (Main Tool & Module) | 370 | P |  | KPAE01-T UMEC LABOR PAY | 45166 | 45174 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 82545.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308039A | 82545.8 | Tool Interconnection Project (Main Tool & Module) | 389 | P |  | KPD801-T LABOR PAY | 45168 | 45177 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 72102.83 | 0.87349 | 10442.97 | 0 | 10442.97 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 72102.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306025A | 82545.8 | Tool Interconnection Project (Main Tool & Module) | 310 | P |  | KPE601-T UMEC LABOR | 45085 | 45100 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 8338.76 | 13034.1 |  |  |  | 0 | 0 | 0 | 0 |  | 61172.94 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306026A | 82545.8 | Tool Interconnection Project (Main Tool & Module) | 311 | P |  | KPOCS1 LIT 3 SCREEN UMEC - LABOR Piping installation system. | 45085 | 45100 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 82545.8 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308030A | 82545.8 | Tool Interconnection Project (Main Tool & Module) | 380 | P |  | KPAP01-T UMEC LABOR PAY | 45167 | 45199 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 82545.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308040A | 82357.7 | Tool Interconnection Project (Main Tool & Module) | 390 | P |  | KPD801-S UMEC LABOR PAY | 45168 | 45201 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82357.7 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 82357.7 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Outsourcing | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C003 | USCSB2311013A | 82153.68 | F21P1 UPW | 2868 | C |  | UPW-commissioning manpower | 45232 | 45237 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 35632.51 | 0.43373 | 46521.17 | 0 | 46521.17 | 0 | [42 empty] | 0 | 0 |  | 0 | 22082.88 | 9282.38 | 0 | 4267.25 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208009A | 82057.95 | F21P1 UPW | 210 | P |  | AECC License | 44785 | 44805 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved |  | T/T 0 Day (paid by wire transfer) | Yi En Wong |  |  | Chiehwen Chen | Yi En Wong | [7 empty] | 0 | 0 | 82057.95 | 0 | 82057.95 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2403240A | 81734.33 | WWT Change Order (Piping) | 3933 | C |  | WWT PVC Pipes_20240325 (B Side) | 45377 | 45378 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 81734.32 | 1 | 0.01 | 0 | 0.01 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 12260.1495 | 81734.32 |  |  | 12260.1495 |  |  |  | 12260.1495 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Water | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2311095A | 81287.41 | F21P1 WWT package (Installation and 2 batch tanks) | 2946 | C |  | Southwest Fastener Monthly Order for Water Team | 45250 | 45335 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 81287.41 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 14457 | 66830.41 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404043A | 81064.8 | WWT B side Project | 4038 | C |  | WWT PVC Glue & Primer_20240327_B side | 45386 | 45391 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 81064.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 71840.76 |  | 9224.04 | 12159.72 |  |  |  | 12159.72 |  |  |  | 12159.72 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311027A | 81000 | Tool Interconnection Project (Main Tool & Module) | 501 | P |  | KPAN02-T HYC LABOR | 45239 | 45253 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 81000 | 0 | 81000 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Material | USC24C005 | USCSB2407061A | 80641.31 | Chemical & WCCS B Side Project | 4458 | C |  | CED 化學系統線0710 | 45484 | 45488 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 80641.31 | 80641.31 | 0 | 0 | [73 empty] | - |  |  | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2401193A | 80122.43 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3378 | C | -01 | TSMC F21P1 STK#KCSK97 Height Change | 45315 | 2024/2/28 2024/3/7 | [6 empty] | Murata Machinery, Ltd. | PR Approved | PO Approved | R1: Trade Term and Payment Term Change |  | Yikang Wang | [11 empty] | 0 | 0 | 80122.43 | 0 | 80122.43 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309174A | 80000 | WWT Change Order (Piping) | 2643 | C |  | WWT -Open PO for urgent materials | 45197 | 45202 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 79525.73 | 0.99407 | 474.27 | 0 | 474.27 | 795.2573 | [40 empty] | 0 | 0 | 0 | 4751 | 1974 | 2862.02 | 8364.95 | 0 | 32815.64 | 0 | 28758.12 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 795.2573
[5 empty] | Others |  |  | USC24C018 | USCSB2410043A | 80000 | Tool Hook Up E2 Trade Equipment Rental | 4986 | C |  | HK_Third_Equipment Rental_2nd PO_End date 8/31/2024 | 45568 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 80000 | 0 | 80000 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Electrical | E2 | USC21C006 | USCSB2401223A | 80000 | F21P1 Slurry package | 3405 | C |  | CDS Cheng Shing extension open PO | 45317 | 45323 | [6 empty] | Cheng Shing MEP Taiwan Co. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 45959.33 | 0.57449 | 34040.67 | 0 | 34040.67 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 45959.33 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2406118A | 80000 | F21P1 AMAT Interconnection | 4358 | C |  | F21 AMAT PVD last 4 machine | 45468 | 45469 | [6 empty] | AUCAN INC | PR Approved | PO Approved | [14 empty] | 80000 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 80000 |  |  |  |  | - |  |  | 0
Non-TSMC | Micron - Material |  |  |  | Others |  |  | USC24C001 | USCSB2406091A | 79600 | Micron - Chemical SOLBLE RN3000 | 4326 | C |  | SOLBLE RN3000 250kg x 4 drums for Micron Manassas facility, Virginia | 45461 | 45467 | [6 empty] | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved | [14 empty] | 79600 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 79600 |  |  | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408046A | 79560 | Tool Interconnection Project (Main Tool & Other Vendors) | 1195 | P |  | KPAE02-T Exhaust Labor | 45524 | 45528 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 79560 | 0 | 79560 | 0 | [73 empty] | -
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2310135A | 79358.9 | F21P1-0404_H_labor for 50 tools_MICU | 2792 | C | -01 | Installer Lead Labor | 45219 | 45224 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | R1:Remark Information Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 77658.38 | 0.97857 | 1700.52 | 0 | 1700.52 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 11183.25 | 0 | 10933.5 | 11516.25 | 13888.88 |  | 0 | 0 | 13736.25 |  | 4495.5 |  | 11904.75 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2308165A | 79358.9 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2459 | C |  | Electric OPS | 45166 | 45188 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7520.25 | 0.094763 | 71838.65 | 0 | 71838.65 | 0 | [40 empty] | 2025.75 | 5494.5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403092A | 79137.11 | Tool Interconnection Project (Main Tool & Other Vendors) | 908 | P |  | KRWRS1&4-DNS SCREEN INTERCONNECTS-labor 2/17-3/15/2024 | 45372 | 45376 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 79137.11 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 79137.11 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2303017A | 78960 | F21P1-0404_H_Hallway plate install_MICU | 1759 | C |  | Thick waffle slab | 44988 | 45033 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 64580 | 0.81788 | 14380 | 0 | 14380 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 64580 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2308111A | 78732 | F21P1 WWT package (Installation and 2 batch tanks) | 2408 | C |  | Field Observation for FAB WWT & WWD | 45157 | 45180 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 47239.2 | 0.6 | 31492.8 | 0 | 31492.8 | 28343.52 | [40 empty] | 0 | 0 | 0 | 47239.2 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3936.6 |  |  |  | 7873.2 |  |  |  | 7873.2 |  | 7085.88 |  | - | 7085.88 | 14171.76 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403132A | 78701.1 | Tool Interconnection Project (Main Tool & Other Vendors) | 947 | P |  | 5402010 1” 90 ELBOW SWP EXT LEG BF HP CPN-P-TIC-I-PD-EB-025 PVDF 230PSI | 45379 | 45383 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 78701.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 78701.1 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Greenberry | CO Scope (adding/additional scope) | WWT | WWT | Steel | M+L | USC21C009 | USCSB2310202A | 78040 | F21P1 WWT package (Installation and 2 batch tanks) | 2853 | C |  | Fabricate,paint & Install 6 NGR Stands | 45230 | 45232 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 74138 | 0.95 | 3902 | 0 | 3902 | 3706.9 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 74138 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 3706.9
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309005A | 78000 | Tool Interconnection Project (Main Tool & Module) | 400 | P |  | KPE601-T HYC LABOR PAY | 45176 | 45180 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 78000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 78000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C063 | USCSB2402040A | 78000 | F21P1-0423_H_T&M Hardware_MICU | 3482 | C |  | MMI Tile alignment T&M (Hank) | 45328 | 45335 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 78000 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 35319.5 | 0 | 0 |  | 42680.5 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405043A | 77987.27 | Tool Interconnection Project (Main Tool & Other Vendors) | 1085 | P |  | KEPST4-TEL INTERCONNECTS | 45426 | 45432 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 77987.27 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 77987.27 | [10 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2311104A | 77874.6 | F21P1 WWT package (Installation and 2 batch tanks) | 2955 | C | -01 | A side valve lacking, confirmed by MU all valves for A side. | 2023/11/22 2023/11/29 2023/12/15 | 2023/12/2 2023/12/29 | 3597.3 | 74277.3 |  | V |  |  | Mega Union Technology Inc. | PR Approved | PO Approved | PR R1:Renew quotation PO R1: Renew quotation |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 77874.6 | 0 | 77874.6 | 77874.6 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 11681.19 |  |  |  | 11681.19 |  |  |  | 11681.19 |  | 19468.65 |  | - | 19468.65 | 19468.65 | 19468.65 | 0
Non-TSMC | EDG | Site Expense |  |  | Others |  |  | USC22C003 | USCSB2401131A | 77620 | TSMC Fab21 Project Phase 1 EDG Package | 3317 | C | -01 | TSMC Fiber Optic Electrical to CUP | 45309 | 2024/2/13 2024/2/15 | [5 empty] | V | D.P. Electric, Inc. | PR Approved | PO Approved | R1: completion date change |  | Ta Wei Wang | [11 empty] | 38810 | 0.5 | 38810 | 0 | 38810 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 7762 | [13 empty] | 31048 | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USC2112025A | 77500 | F21P1 Slurry package | 88 | P |  | General hoses | 44548 | 44572 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | NO CF | 90% by shipment, and last 10% invoice within 60 days of receiving the goods. All invoices are NET 30. | York Yeh | FOB Osaka port, for the tubing, the trade term is DDP Phoenix and for fittings, the trade term is FOB Japan. | 24 months | Chih-Chien Hung | York Yeh | N |  | Martin | PFA Tube | N | 5000 |  | 77500 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 77500 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Oil drain pipe work | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C009 | USCSB2301050A | 77300 | F21P1 230kV MTR Oil and Drain Pipe work | 1667 | C |  | Electrical room level gauge | 44951 | 44955 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 57975 | 0.75 | 19325 | 0 | 19325 | 14493.75 | [27 empty] | 38650 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 19325 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 2898.75 |  | - | 2898.75 | 2898.75 | 2898.75 | 2898.75
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC21C009 | USCSB2407163A | 77222.59 | F21P1 WWT package (Installation and 2 batch tanks) | 4586 | C |  | CO from tsmc for Enzyme to improve, we take the B side to fill A side need first | 45501 | 45506 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 77222.59 | 0 | 77222.59 | [74 empty] | -
Base-Build | Chemical Lab | Labor | The budget execution does not pertain to this project | Penetration Pipe | WWT | Mechanical | M+L | USC22C021 | USCSB2210017A | 77055 | F21P1 Chemical Lab setup | 1500 | C |  | FAB L10, L20 HPM Drain Piping Penetration | 44845 | 44847 | [6 empty] | Silicone Future Manufacturing Company Ltd | PR Approved | PO Approved |  | 100% by received-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 77055 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 77055 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC21C005 | USCSB2310065B | 77013 | F21P1 Chemical & WCCS package | 2726 | C |  | Hardware for Chemical YaoHong work at Lorry FNDP, CDA at L20. | 45245 | 45245 | [6 empty] | JUWEI ENGINEERING CO LTD | PR Approved | PO Approved | Originally want to change the supplier name, but the materials have already been shipped out |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 77013 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 36205 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 40808 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408015A | 76701.42 | Tool Interconnection Project (Main Tool & Other Vendors) | 1185 | P |  | INT--ETCH/WET/CVD/PVD/ME--CGS(Mar.&Apr.) | 45518 | 45523 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 76701.42 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 76701.42 |  |  | -
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2302058A | 76700.22 | F21P1 UPW | 1739 | C |  | UPW B Side Disconnect Switch & Stand | 44985 | 45008 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 76700.22 | 1 | 0 | 3909.91 | -3909.91 | 7819.82 | [28 empty] | 0 |  | 13963.98 |  | 58648.72 | 0 |  |  | 177.61 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 3909.91 | 3909.91 | 0 | 3909.91
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2407145A | 76644.45 | F21P1 AMAT Interconnection | 4570 | C |  | Wires & Terminals for AMAT 36 machines | 45497 | 45506 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 76644.45 | 76365.24 | 279.21 | 0 | [73 empty] | - |  |  | 0
Others | AMHS | Housekeeping |  |  | AMHS |  |  | USC22C031 | USCSB2311032A | 76370 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2887 | C |  | Materials for detail clean | 2023/11/8 2023/12/19 | 45293 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | Higher amount includes Freight Charges of $6,370 ie 70% of Shipping Fee |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 76370 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 76370 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Labor | USC24C005 | USCSB2408133A | 76000 | Chemical & WCCS B Side Project | 4743 | C |  | F21 P1B區Chemical赴美管路工程施工by人月 For 2 month | 45533 | 45555 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 76000 | 0 | 76000 | 0 | [73 empty] | -
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2308182A | 75936.12 | F21P1 UPW | 2475 | C |  | Repair damages on site | 45169 | 45189 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 75936.12 | 1 | 0 | 3796.81 | -3796.81 | 7593.62 | [40 empty] | 0 | 0 | 0 | 0 |  | 72139.31 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 3796.81 | 3796.81 | 0 | 3796.81
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309157A | 75652.96 | F21P1-0404_H_labor for 50 tools_MICU | 2628 | C |  | Galvanized Tool Install - 6b | 45195 | 45198 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 75652.96 | 0 | 75652.96 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C001 | USCSB2309049A | 75600 | TEL Main Tool Interconnection | 2526 | C | -03 | KPOCT8-T HYC | 45181 | 45198 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 75600 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 75600 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403088A | 75095 | Tool Interconnection Project (Main Tool & Other Vendors) | 905 | P |  | U1AT1000-062 TUBING-CUT STOCK 451 HPJ 1IN | 45372 | 45377 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 75095 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 49285 | [5 empty] | 25810 |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307004A | 75000.01 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2178 | C |  | Linde Gas & Equipment Inc. | 45108 | 45138 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4014.46 | 0.053526 | 70985.55 | 0 | 70985.55 | 0 | [38 empty] | 3926.96 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 87.5 | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USC2111033A | 75000 | F21P1 UPW | 44 | P |  | Flanged Heater | 44517 | 44543 | [6 empty] | Wattco Inc. | PR Approved | PO Approved | 12/10 (無supplier's sheet) | 70% in advance, 30% before shipping. | York Yeh | EXW | 1 year | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | 5000 |  | 75000 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 52500 |  |  | 22500 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2404057A | 74928.2 | F21P1 AMAT Interconnection | 4050 | C |  | 16 remaining tools for AMAT interconnection, per TSMC need to order asap. | 45388 | 45391 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 74923.6 | 0.99994 | 4.6 | 0 | 4.6 | 0 | [52 empty] | 0 | 0 | 0 |  | 74923.6 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2406102A | 74880 | F21P1 AMHS Power Panel | 4337 | C |  | AMHS DP Meggar Testing CO | 45463 | 45468 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 74880 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 74880 | [8 empty] | - |  |  | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC22C010 | USCSB2405023A | 74783.1 | F21 P1 LSC CMS and DPM 5G System | 3995 | C |  | F21 P1 parking gates installation-(10/11) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 74783.1 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 74783.1 | [6 empty] | - |  | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2305099A | 74708.31 | F21 TMAH System | 2020 | C | -02 | FAB A PVDF | 2023/5/20 2023/6/13 | 2023/5/30 2023/6/27 2023/7/4 | -79927.69 | 154636 | V |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R2:The trade terms should be FOB R1:Adjusting the amount based on the new quotation. (USD 134,608.66+119.2-60,019.55(PO USCSB2306042) ) |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 71476.47 | 0.95674 | 3231.84 | 0 | 3231.84 | 2859.0588 | [33 empty] | 0 |  | 18373.53 | 50456.44 |  |  |  | 0 | 2096.5 | 0 | 0 |  | 550 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 2859.0588
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2401123A | 74477.41 | F21P1-0423_H_T&M Hardware_MICU | 3310 | C |  | Pumping Line Material Order_Tungyi | 45309 | 45315 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 73247.02 | 0.98348 | 1230.39 | 0 | 1230.39 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 3766.2 | 26689.08 |  | 0 | [7 empty] | 42791.74 | [6 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2303029A | 74449.5 | F21P1 Module Tool Interconnection CVD | 1771 | C |  | Swagelok consume material gasket/nut/gland | 44992 | 45007 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 74449.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 32521 | 29181.5 | 3518 |  | 0 | 2355 | 6874 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303007A | 74357.27 | F21P1 Module Tool Interconnection DIF1-2 | 1749 | C |  | F21P1 CG300 cabinet & e-sensor cable (22AWG/2C, 22AWG/4C) | 44987 | 45001 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 74357.27 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  | 11259.99 |  |  | 63097.28 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2406084A | 73400 | Chemical & WCCS B Side Project | 4320 | C |  | 化學系統控制線材0613 for priority 3 | 45457 | 45461 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 73400 | 73400 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | UPW | Equipment | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2309170A | 73373.74 | F21P1 UPW | 2639 | C |  | Veolia turbo bed-final | 45197 | 45202 | [6 empty] | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 73373.74 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 73373.74 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2409040A | 73316.13 | WWT B side Project | 4825 | C |  | WWT - WRC Platform Flashing | 45542 | 45547 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 73316.13 | 0 | 73316.13 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2302045A | 73260 | F21P1 WWT package (Installation and 2 batch tanks) | 1726 | C |  | Flange fittings | 44980 | 44992 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 73260 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 60826.46 |  | 0 | [6 empty] | 12433.54 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC24C008 | USCSB2405005A | 73158 | UPW B Side Project | 3981 | C |  | FAB LB2 MAU Bypass | 45413 | 45416 | 5062 | 78220 | V |  |  |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 65842 | 0.9 | 7316 | 0 | 7316 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 65842 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2402136A | 73038 | F21P1 WWT package (Installation and 2 batch tanks) | 3572 | C |  | WWT FRP coating in WRC&FAB | 45337 | 45344 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 73038 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 73038 |  |  |  |  | 10955.7 |  |  |  | 10955.7 |  |  |  | 10955.7 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2408105A | 72618 | F21P1 Module Tool Interconnection CVD | 4755 | C |  | P1B_CVD1_CIP_GAS_LINE_CT_CT-202407160001_CT-202407160002 | 45527 | [7 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 72618 | 0 | 72618 | 0 | [73 empty] | -
Base-Build | WWT | Greenberry | Main Contract Scope | WWT | WWT | Steel | M+L | USC23C045 | USCSB2309041A | 72481 | WWT Change Order (Piping) | 2518 | C |  | WWT FAB Install (16) Agitator Installation | 45180 | 45189 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 51375.05 | 0.70881 | 21105.95 | 0 | 21105.95 | 14898.7645 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 51375.05 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3624.05 |  |  |  | 3624.05 |  |  |  | 3624.05 |  | 4110.004 |  | - | 4110.004 | 4110.004 | 2568.7525 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2309084A | 72000 | F21_AZQR_Hookup_ Interconnection | 2557 | C |  | QR: LAN CABLE TRAY INSTALL | 45184 | 45197 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 72000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 72000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C011 | USCSB2306097A | 72000 | F21 TMAH System | 2130 | C |  | WWT Tank Agitator Blade Epoxy | 45098 | 45124 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 49500 | 0.6875 | 22500 | 0 | 22500 | 3240 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 13500 | 0 |  |  | 15000 | 0 | 0 |  | 0 |  |  |  |  | 7200 | 12000 |  |  | 7200 |  |  |  | 7200 | 9000 | 0 |  | - | 0 | 0 | 0 | 3240
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2206024A | 72000 | F21P1 WWT package （USA EQ-FRP tank) | 1413 | C |  | FRP tank Painting | 44741 | 44749 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Chengtung Liu | Yi En Wong | Y | [6 empty] | 72000 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 72000 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405073A | 71965 | Chemical & WCCS B Side Project | 4093 | C |  | CHEM_WCCS _Consumable hardware C_Cush A clamp_USA_ 01-00167404_ 0510 | 45423 | 45432 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 71965 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 39352.26 | 71965 |  |  |  |  | 32612.74 |  |  | - |  |  | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2304080A | 71927.12 | F21P1 UPW | 1918 | C |  | ORGANO temp resin | 45044 | 45051 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 71927.12 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 71927.12 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2203004A | 71730 | F21P1 UPW | 1339 | C |  | FRP/PP Tank Change Order | 44621 | 44624 | [6 empty] | An-Cor Industrial Plastics, Inc. | PR Approved | PO Approved | PO USC2110015A異動追加 | Based on T&C 25% upon all submittals approved-net 45 days; 20% upon the order-net 45 days; 50% upon fabrication completion of the tanks-net 45 days; 5% due within 60 days after delivery on site-net 45 days) | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N |  |  |  | N |  |  | 71730 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 14346 | 8966.25 | 8966.25 | [19 empty] | 0 |  |  |  |  | 0 |  |  |  | 32926.3 | 6525.2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2406029A | 71600 | Chemical & WCCS B Side Project | 4255 | C |  | F21P1 B Side EES Porder Coating Cable Tray | 45448 | 45448 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 71600 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 71600 | [10 empty] | - |  |  | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2407155A | 71497 | WWT B side Project | 4564 | C |  | LB2 VS1380 steel pipes_WWT | 45499 | 45511 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 71497 | 0 | 71497 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2306128A | 71296.77 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2161 | C |  | Grainger Hand tool | 45105 | 45118 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 71296.77 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 70696.57 | 600.2 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2301031A | 71287.6 | F21P1 WWT package (Installation and 2 batch tanks) | 1652 | C |  | Harrington Pipe | 44939 | 44945 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 71287.6 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 71287.6 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | AMC THC | Equipment | The budget execution does not pertain to this project | AMC THC | Low Voltage | Mechanical | M+L | USC21C009 | USCSB2312201A | 70997.28 | F21P1 WWT package (Installation and 2 batch tanks) | 3187 | C |  | F21 Litho AMC Utility GAS piping Engineering | 45290 | 45324 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Yikang Wang (Ta Wei Wang) | [11 empty] | 70997.28 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 70997.28 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2406085A | 70906.95 | F21P1 WWT package (Installation and 2 batch tanks) | 4321 | C |  | Mess remaining painting Jeff | 45458 | 45464 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 67361.6 | 0.95 | 3545.35 | 0 | 3545.35 | 0 | [70 empty] | 67361.6 | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404024A | 70701.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 979 | P |  | KDSNS1-DNS SCREEN INTERCONNECTS 3/4-3/28/2024 | 45386 | 45387 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 70701.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 70701.4 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2311141A | 70670 | F21P1 QR Lab Security & CCTV | 2991 | C |  | F21 EBO CCTV & Security Equipment | 45260 | 45261 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 62587 | 0.88562 | 8083 | 0 | 8083 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 25620 | 0 |  | 0 | [7 empty] | 36967 | [6 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C059 | USCSB2409118A | 70660 | F21P1 Foundation T&M | 4936 | C |  | 4th waffle covers from MMI | 45563 | 45567 | [7 empty] | PR Approved | PO Approving | [14 empty] | 0 | 0 | 70660 | 0 | 70660 | 0
Others | Tiger Team | Labor |  |  | Others |  |  | USC23C041 | USCSB2306023A | 70638.68 | TSMC F21 HK Tiger Team | 2059 | C |  | TSMC F21 HK TIGER TEAM(Electric OPS) | 45083 | 45090 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 50129.49 | 0.70966 | 20509.19 | 0 | 20509.19 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 22135.1 |  |  |  | 1484.63 |  | 7861.76 |  | 18648 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404055A | 70580 | WWT B side Project | 4049 | C |  | WWT Welding machine | 45387 | 45391 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 57169.8 | 0.81 | 13410.2 | 0 | 13410.2 | 17637.942 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 10587 | 14116 |  | 21879.8 | 10587 |  |  | 21174 | 10587 |  | 5399.37 |  | - | 5399.37 | 6839.202 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409001A | 70557 | Tool Interconnection Project (Main Tool & Other Vendors) | 1208 | P |  | KPE607-S CW PIPING TIG WELDING EXRA COSTS REV1: TIG WELDING | 45539 | 45545 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 70557 | 0 | 70557 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409003A | 70557 | Tool Interconnection Project (Main Tool & Other Vendors) | 1210 | P |  | KPE604-S: CW PIPING TIG WELDING EXTRA COSTS REV1: TIG WELDING | 45539 | 45545 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 70557 | 0 | 70557 | 0 | [73 empty] | -
Base-Build | Base-Build | Site Expense | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Instrument | USC21C005 | USCSB2307113A | 70264 | F21P1 Chemical & WCCS package | 2277 | C |  | Temporary Lighting & Power | 45133 | 45134 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 70264 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 70264 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C003 | USCSB2307098A | 70219.99 | F21P1 UPW | 2264 | C |  | LV 3 – 3rd Party Inspection - June | 45128 | 45135 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved | Will be back-charged to TSMC |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 70219.99 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 70219.99 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2308072A | 70136 | F21P1 Chemical & WCCS package | 2370 | C |  | Lorry A&B Crossover Steps | 45153 | 45168 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 70136 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 52602 | 0 |  | 0 | 14027.7 | 0 | 0 | 0 |  |  | 3506.3 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT |  |  | USC24C006 | USCSB2409072A | 70080 | WWT B side Project | 4865 | C |  | Iron plate installation and positioning | 45554 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 70080 | 0 | 70080 | 0 | [73 empty] | -
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2402013A | 70061 | F21P1 UPW | 3456 | C |  | UPW-UMEC-TSMC-CO for B side ACM-C expansion | 45323 | 45327 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 66558 | 0.95 | 3503 | 0 | 3503 | 0 | [48 empty] | 0 | 0 |  |  | 59552 | 0 | 0 |  | 7006 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309016A | 70000 | Tool Interconnection Project (Main Tool & Module) | 407 | P |  | cable rework for 8395 | 45185 | 45303 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 70000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 70000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405165A | 70000 | F21P1-0404_H_labor for 50 tools_MICU | 4193 | C |  | Linde previous unpaid | 45441 | 45446 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 70000 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 46542.97 |  | 16235 |  | 7222.03 | [8 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405047A | 70000 | WWT B side Project | 4054 | C |  | WWT: OPEN PO II | 45420 | 45428 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 69485.71 | 0.99265 | 514.29 | 0 | 514.29 | 712.8 | [56 empty] | 0 | [9 empty] | 720 |  | 54271.88 |  | 11017.49 | 712.8 | 3476.34 | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2302048A | 69910 | F21P1 Module Tool Interconnection CVD | 1729 | C |  | Mithril Heater Band | 44981 | 44999 | [6 empty] | Astro Thermal Technology Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 69910 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 69910 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USC2111052A | 69874.42 | F21P1 Slurry package | 53 | P |  | Valves for SDS | 44523 | 44532 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | scope Changed after reviewing rev02-6/17 scope changed (material raised up ) from 2467383 to 2485140.6 | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 69874.42 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 62702.68 |  | 754.92 |  | 5661.9 | [15 empty] | 754.92 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2308178A | 69045.01 | F21P1-0404_H_labor for 50 tools_MICU | 2471 | C |  | TW E2 Hookup GF Welding Machine | 45168 | 45169 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 69045.01 | 1 | 0 | 12295.2 | -12295.2 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 3003.02 | 3669 | 0 | 0 | 0 | 44659.7 | 1950 | 11007 | 0 | 0 |  | 0 |  |  |  | 4756.29 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2311118A | 69039.23 | F21P1 WWT package (Installation and 2 batch tanks) | 2969 | C |  | L30 PP/PVC Material Needed to Complete B-side | 45258 | 45265 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 69039.23 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 61152.91 | 7886.32 |  | 0 | [8 empty] | 2071.1769 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | EUV Steel Plate | Labor |  |  | Others |  |  | USC23C058 | USCSB2308164A | 68860 | F21 EUV Steel Plates | 2458 | C |  | MIC Temp Power Crane ReLocate | 45166 | 45181 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 68860 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 68860 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403036A | 68773.55 | F21P1-0404_H_labor for 50 tools_MICU | 3744 | C | -01 | TSMC Straight Shoe Tee Fitting w/Flange for HK Exhaust trade | 45356 | 2024/3/7 2024/3/11 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved | R1: Revise ship-to address and delivery instructions |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 44905.34 | 0.65294 | 23868.21 | 13020.48 | 10847.73 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 23347.34 |  | 10830.84 |  | 10727.16 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2304009A | 68400 | F21P1 UPW | 1850 | C |  | 360 pic battery charge | 45022 | 45033 | [6 empty] | Gruber Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 68400 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 45600 |  | 22800 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2406112A | 68309.09 | WWT B side Project | 4352 | C |  | WWT - PR Brahma A-Side FRP T-740AA-AB-AC Tank Interconnection Spools(A side) | 45465 | 45471 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 68042.31 | 0.99609 | 266.78 | 0 | 266.78 | 0 | [70 empty] | 68042.31 | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2403221A | 68189.46 | WWT Change Order (Piping) | 3916 | C |  | WWT 009 _B SIDE P clamp | 45372 | 45376 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 68189.46 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 10228.419 | 68189.46 |  |  | 10228.419 |  |  |  | 10228.419 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Civil | M+L | USC21C003 | USCSB2404101A | 68027 | F21P1 UPW | 4088 | C |  | SUPPLY MATERIAL/ BUILD SHAFT WALL/ APPLY DRYWALL AND SHAFT WALL TO FRAMING/ TAPE AND SAND DRYWALL TO PAINT PREP FINISH/INSTAL | 45393 | 45405 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 68027 | 0 | 68027 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304013A | 68009.6 | F21P1 WWT package (Installation and 2 batch tanks) | 1854 | C |  | WWT SUS CDA all A side material (requested by PSS) | 45023 | 45037 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 66984.15 | 0.98492 | 1025.45 | 0 | 1025.45 | 1339.683 | [33 empty] | 0 |  | 61931.15 | 5053 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 1339.683
Base-Build | WWT | CCE | Main Contract Scope | WWT | WWT | Electrical | M+L | USC21C009 | USCSB2207024A | 68000 | F21P1 WWT package (Installation and 2 batch tanks) | 1439 | C |  | CCE Conduit, Cable Tray and Cable label | 44772 | 44776 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | USCSB2202002A Change Order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 68000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 68000 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | Tiger Team | Labor |  |  | Others |  |  | USC23C041 | USCSB2306022A | 67881.05 | TSMC F21 HK Tiger Team | 2058 | C | -01 | TSMC F21 HK TIGER TEAM | 45083 | 45090 | -11584 | 79465.05 |  |  |  |  | Onsight Live, LLC | PR Approved | PO Approved | The PR needs to revised due to the amount change/The sub has reduced the labor hours. The labor rate does not change. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 67881.05 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 67881.05 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | Liquid Penetrant | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C035 | USCSB2310152A | 67876.26 | CAP_A_90772_F21 Phone call base build and Liquid penetrant testing system | 2808 | C |  | F21 Phone call base build and Liquid penetrant testing system engineering | 2023/10/24 2024/8/1 | 2023/10/26 2024/8/7 | -9290.64 | 77166.9 | V |  |  |  | NUUO US Inc. | PR Approved | PO Approved | R1: Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 67876.26 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 43096.26 |  | 0 |  | 24780 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2405169A | 67725 | F21P1-0404_H_Hallway plate install_MICU | 4197 | C |  | Additional P1A B6-1 foundation, KEPSLD, KEPSLE for MMI | 45442 | 45450 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 27291 | 0.40297 | 40434 | 0 | 40434 | 0 | [70 empty] | 27291 |  |  | - |  |  | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Electrical | Instrument | USC23C045 | USCSB2406015A | 67302.18 | WWT Change Order (Piping) | 4241 | C |  | T140 discharge panel modification | 45444 | 45472 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved | [14 empty] | 67302.18 | 1 | 0 | 0 | 0 | 80762.616 | [70 empty] | 67302.18 | 33651.09 |  | - | 20190.654 | 20190.654 | 6730.218 | 0
Base-Build | Slurry | MMI | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2306085A | 67129 | F21P1 Chemical & WCCS package | 2118 | C |  | Slurry Raise Trench Grating | 45097 | 45124 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 63772.55 | 0.95 | 3356.45 | 0 | 3356.45 | 3356.45 | [33 empty] | 0 |  |  | 46990.3 |  | 6712.9 |  | 0 | 0 | 0 | 10069.35 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 3356.45
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408051A | 67091 | Tool Interconnection Project (Main Tool & Other Vendors) | 1199 | P |  | KPOCTK Exhaust Labor | 45525 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 67091 | 0 | 67091 | 0 | [73 empty] | -
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC21C006 | USCSB2312011A | 66929.4 | F21P1 Slurry package | 3006 | C |  | CDS HongDong 2023 Nov construction work | 45262 | 45274 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 66929.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 66929.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Greenberry | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C014 | USCSB2304055A | 66708 | F21P1 WH2SO4 | 1894 | C |  | WSR tank Install | 45036 | 45078 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 66708 | 0 | 66708 | 66708 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 10006.2 |  |  |  | 10006.2 |  |  |  | 10006.2 |  | 16677 |  | - | 16677 | 16677 | 16677 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2409049A | 66675 | F21P1 AMHS Wiring Work Outline | 4833 | C |  | 25,000 FT #6/3C Wire_AMHS | 45547 | 45551 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 66675 | 0 | 66675 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312040A | 66506.4 | Tool Interconnection Project (Main Tool & Module) | 587 | P |  | KPAP02-S LIT 1 STREIMERS | 45269 | 45275 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11084.4 | 0.16667 | 55422 | 0 | 55422 | 0 | [45 empty] | 0 | 0 | 1847.4 | 0 | 0 |  |  | 9237 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312039A | 66506.4 | Tool Interconnection Project (Main Tool & Module) | 586 | P |  | KPAN02-S LIT 1 STREIMERS | 45269 | 45274 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 13901.69 | 0.20903 | 52604.71 | 0 | 52604.71 | 0 | [45 empty] | 0 | 0 | 2771.1 | 0 | 0 |  |  | 11130.59 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306054A | 66506.4 | Tool Interconnection Project (Main Tool & Module) | 335 | P |  | KPE601-T STREIMERS EXHAUST LABOR PAY | 45105 | 45135 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 40641.78 | 0.6111 | 25864.62 | 0 | 25864.62 | 0 | [39 empty] | 38794.38 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 1847.4 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308031A | 66506.4 | Tool Interconnection Project (Main Tool & Module) | 381 | P |  | KPAP01-S STREIMERS LABOR PAY | 45167 | 45176 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 66506.4 | 0 | 66506.4 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2309022A | 66446.93 | F21P1-0404_H_labor for 50 tools_MICU | 2499 | C |  | Cable glands and conduit | 45176 | 45182 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 66446.93 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 66446.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401103A | 66377 | Tool Interconnection Project (Main Tool & Other Vendors) | 720 | P |  | KPSOT1 Vex Duct Material | 45321 | 45323 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 66377 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 66377 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2302047A | 66000 | F21P1 Module Tool Interconnection CVD | 1728 | C |  | EMMA Heater Band | 44981 | 44999 | [6 empty] | Astro Thermal Technology Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 66000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 66000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310083A | 66000 | F21P1-0404_H_labor for 50 tools_MICU | 2744 | C |  | HK YAHO Accommodation | 45212 | 45222 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 66000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 66000 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Site Expense | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2311102A | 66000 | F21P1 WWT package (Installation and 2 batch tanks) | 2953 | C |  | WWT - 450 welder | 45251 | 45252 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 66000 | 0 | 66000 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 9900 |  |  |  | 9900 |  |  |  | 9900 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312164A | 65808.5 | F21P1-0404_H_labor for 50 tools_MICU | 3152 | C | -01 | ground clamp, wall receptacle for power trade | 45282 | 2023/12/27 2024/1/4 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Remark Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 65808.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 1501.5 |  |  | 0 | 0 | 64307 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310198A | 65745.05 | F21P1-0404_H_labor for 50 tools_MICU | 2849 | C |  | straight tee fittings w/ flanges for HL | 45230 | 45237 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 65745.05 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 40957.45 | 0 | 0 | 1009.5 |  | 0 | 0 | 23778.1 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | FMCS | Material |  |  | Others |  |  | USC22C007 | USCSB2311114A | 65527 | TSMC F21 FMCS Installation | 2965 | C |  | tsmc F21P1 FMCS Cycber Security_Onshore | 45258 | 45260 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 42449 | 0.64781 | 23078 | 0 | 23078 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 42449 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Material | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C014 | USCSB2308170A | 65025.05 | F21P1 WH2SO4 | 2464 | C |  | WRC Additional Concrete | 45167 | 45181 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 55025.05 | 0.84621 | 10000 | 0 | 10000 | 8253.7575 | [40 empty] | 0 | 0 | 23825.05 | 0 |  | 0 | 31200 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1950.7515 |  |  |  | 1950.7515 |  |  |  | 2601.002 |  | 2751.2525 |  | - | 2751.2525 | 2751.2525 | 0 | 0
Base-Build | Base-Build | Housekeeping |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC23C058 | USCSB2311055A | 65024 | F21 EUV Steel Plates | 2910 | C |  | Transparent table mat, PE blue and white canvas and cleanroom tape for A side housekeeping and epoxy protecting. | 45241 | 45264 | [6 empty] | Xiang Sheng Hardware Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 65024 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 65024 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Triazole | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC22C022 | USCSB2304073A | 65023.22 | F21P1 Triazole treatment system | 1912 | C |  | Triazole Poly/PVC material | 45042 | 45051 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 65023.22 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 30703.79 | 2901.97 |  | 533.63 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 30883.83 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2311020A | 65000 | F21P1 WWT package (Installation and 2 batch tanks) | 2875 | C |  | Mezzanine shaft wall paint | 45234 | 45248 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 41326.16 | 0.63579 | 23673.84 | 0 | 23673.84 | 65000 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 9750 |  |  |  | 9750 |  |  | 41326.16 | 9750 |  | 16250 |  | - | 16250 | 16250 | 16250 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2209012A | 64660.89 | F21P1 WWT package (Installation and 2 batch tanks) | 1464 | C |  | WWT tank welding | 44819 | 44825 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  | 100% upon completion of work-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 61427.85 | 0.95 | 3233.04 | 0 | 3233.04 | 0 | [20 empty] | 34427.85 |  | 27000 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | LSC connector | Material |  |  | Others |  |  | USC23C048 | USCSB2306088A | 64498.12 | F21P1-0423_H_LSC connectors_MICU | 2121 | C |  | Pipe Fittings for TSMC/Kanken | 45098 | 45110 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | Pipe fittings will be delivery to Kanken Warehouse via RTW. TSMC has agreed to be invoiced the full sum upon delivery. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 64498.12 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 64498.12 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2305010A | 64375.51 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1935 | C |  | Lighting for warehouse | 45049 | 45063 | [6 empty] | Red Mountain Lighting | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 64375.51 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 9656.32 | 0 | [5 empty] | 54719.19 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Site Expense | USC24C006 | USCSB2404002A | 64323.97 | WWT B side Project | 3999 | C |  | WWT LJ Tools_20240329 | 45384 | 45392 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 64323.97 | 0 | 64323.97 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 9648.5955 |  |  |  | 9648.5955 |  |  |  | 9648.5955 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2308012A | 64096 | F21P1 WWT package (Installation and 2 batch tanks) | 2314 | C |  | Fab 21 B LB2 (7 Tank Media Loading) Phoenix, Arizona | 45141 | 45168 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 64096 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 38632.86 |  | 0 | 25463.14 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC22C013 | USCSB2405024A | 63539.96 | F21P1 QR Lab Security & CCTV | 3996 | C |  | F21 P1 parking gates installation-(11/11) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 63539.96 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 63539.96 | [6 empty] | - |  | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2407068A | 63489.56 | Tool Hookup Material (UPW&Chemical) | 4462 | C |  | Ryan Herco USCSB2204014A extension PO | 45485 | 45489 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 63489.56 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 63489.56 | [8 empty] | - |  |  | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2206008A | 63250 | F21P1 UPW | 1399 | C |  | Insulation spec change | 44720 | 44726 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | USCSB2108001A的Change Order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 0 | 0 | 63250 | 0 | 63250 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405173A | 63239.02 | Chemical & WCCS B Side Project | 4201 | C |  | Extremely Urgent_RFQ_MICU Chemical Team Request Material_05232024_Semitorr | 45442 | 45446 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 63228.63 | 0.99984 | 10.39 | 0 | 10.39 | 0 | [68 empty] | 63228.63 |  |  |  |  | - |  |  | 0
Base-Build | Triazole | Equipment | DCR Scope | WWT | WWT | Electrical | M+L | USC21C009 | USCSB2402081A | 63146.26 | F21P1 WWT package (Installation and 2 batch tanks) | 3522 | C |  | TRIAZOLE & NH3 stripper pad scopes | 45330 | 45352 | [6 empty] | Revolution Industrial LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 63146.26 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 63146.26 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406003A | 63121.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1123 | P |  | KDCRS4 - rework (change order)-DNS SCREEN INTERCONNECTS-5/1-5/10/24 | 45450 | 45461 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 63121.6 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 63121.6 | [6 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406035A | 63121.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1141 | P |  | Man-Power Pay to re-work (change Order)-DNS SCREEn Interconnects. 5/1 thru 5/10/2024 | 45472 | 45475 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 63121.6 | 0 | 63121.6 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311030A | 62850 | F21P1-0404_H_labor for 50 tools_MICU | 2885 | C |  | Wire THNN 500Foot, copper conductor material for Third for ATF-BO7, AET-F14, ATF-C15, and ATF-A04 | 45237 | 45239 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 62850 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 62850 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401006A | 62713.51 | Tool Interconnection Project (Main Tool & Other Vendors) | 630 | P |  | KPI401-S Labor | 45300 | 45310 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 62713.51 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 62713.51 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC21C008 | USCSB2402241A | 62593.07 | F21P1 CCTV & Security | 3667 | C |  | F21 CCTV Engineering (T&M) | 45346 | 45352 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 62593.07 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 62593.07 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2406002A | 62544.05 | Chemical & WCCS B Side Project | 4231 | C |  | CED 五金料件0531-1 | 45444 | 45447 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 41584.84 | 0.66489 | 20959.21 | 62650.38 | -41691.17 | 0 | [73 empty] | 41584.84 |  |  | 0
Others | VEX duct | Material |  |  | Others |  |  | USC22C038 | USCSB2301023A | 62527.54 | MISC_(21417931_522/T0)VEX duct adaptor | 1645 | C |  | VEX SUS adaptor | 44937 | 44948 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 62527.54 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 62527.54 | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Southland | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | M+L | USC21C006 | USCSB2308162A | 62489 | F21P1 Slurry package | 2456 | C |  | F21 P1 VOC Change Order(southland)_3 | 45164 | 45184 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 62489 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 62489 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2305055A | 62400 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1978 | C |  | KPAP01-S LIT 1 Hua Yi | 45058 | 45068 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 62400 | 0 | 62400 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | CCTV | Labor | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | M+L | USC22C013 | USCSB2404036A | 62180 | F21P1 QR Lab Security & CCTV | 4031 | C |  | F21 P1 Gown Office IT Room speed gate engineering | 45385 | 45390 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 59071 | 0.95 | 3109 | 0 | 3109 | 3109 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 59071 |  |  | 59071 |  | 0 |  | - | 0 | 0 | 0 | 3109
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2403238A | 62172.48 | F21P1 AMAT Interconnection | 3931 | C |  | MIC internal Manpower: Labor | 45374 | 45380 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 27778 | 0.44679 | 34394.48 | 0 | 34394.48 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 27778 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405086A | 62133.4 | Chemical & WCCS B Side Project | 4106 | C |  | CHEM_CDS SDS project for valve_ SemiTorr Group_Qte1526621 | 45427 | 45447 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 62133.4 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [8 empty] | 64308.6 |  |  | 62133.4 |  |  |  |  | - |  |  | 0
Base-Build | WWT |  |  |  | WWT | Civil | M+L | USC24C006 | USCSB2408140A | 62000 | WWT B side Project | 4749 | C |  | WWT A+B side punch which is paid by tsmc_水泥基座填塞 | 45533 | 45553 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 62000 | 0 | 62000 | 0 | [73 empty] | -
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2308103A | 62000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2400 | C |  | Hua Yi Construction Az On-site Clean Room Construction | 45156 | 45163 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 62000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 58900 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 3100 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403026A | 61727 | Tool Interconnection Project (Main Tool & Other Vendors) | 852 | P |  | KPOCT2 Vex, Power, and Mechanical Labor | 45358 | 45363 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 61727 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 61727 | [8 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG | Labor |  |  | Others |  |  | USC22C003 | USCSB2306069A | 61698 | TSMC Fab21 Project Phase 1 EDG Package | 2102 | C |  | Remove and Replace Discharge Ducts | 45093 | 45096 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved | Back Charge to Customer Fu Energy with 10% Mark-up |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 61698 | 3147 | 58551 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2209021A | 61618.95 | F21P1 QR Lab Security & CCTV | 1473 | C |  | F21P1 QR Lab_Security&CCTV Package | 44824 | 44830 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 50569 | 0.82067 | 11049.95 | 0 | 11049.95 | 0 | [28 empty] | 0 |  |  |  | 50569 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405164A | 61556.2 | Chemical & WCCS B Side Project | 4192 | C |  | Swagelok pressure-reducing redgulators and compressionto npt adaptors | 45441 | 45442 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 61556.2 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 4701.4 | [7 empty] | 28427.4 |  | 28427.4 | - |  |  | 0
Base-Build | CCTV |  | The budget execution does not pertain to this project | Chemical | Chemical | Electrical | Material | USC22C013 | USCSB2406069A | 61428 | F21P1 QR Lab Security & CCTV | 4301 | C |  | F21 Chemical system control cable | 45455 | 45460 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 61428 | 61428 | 0 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401075A | 61122.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 695 | P |  | KRKRS1 AND KRWRS4 MANPOWER PAY BRAHMA GROUP, INC. | 45316 | 45318 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 56938.57 | 0.93155 | 4183.55 | 0 | 4183.55 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 56938.57 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308027A | 60964.2 | Tool Interconnection Project (Main Tool & Module) | 377 | P |  | KPAE01-S STREIMER LABOR PAY | 45167 | 45203 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 60964.2 | 0 | 60964.2 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2307085A | 60948.92 | WWT Change Order (Piping) | 2251 | C |  | WWT -L20 Sludge | 45127 | 45133 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 60948.92 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 32822.77 | 0 | 3029.85 | 0 | 0 |  | 25096.3 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2310183A | 60742.5 | F21P1 Chemical & WCCS package | 2835 | C |  | CDS L10 CPVC chemical pipes | 45227 | 45241 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 60742.5 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 60742.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Organo |  |  |  | Others |  |  | USC24C013 | USCSB2405141A | 60510.53 | Organo USA - UPW Electrical | 4165 | C |  | CIP Motor Change | 45436 | 45462 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 30255.27 | 0.5 | 30255.26 | 30255.27 | -0.01 | 0 | [73 empty] | 30255.27 |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307004A | 60480 | Tool Interconnection Project (Main Tool & Module) | 340 | P |  | Mechanical Interconnect Labor and materials KDSNB1 | 45118 | 45138 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 50849.99 | 0.84077 | 9630.01 | 0 | 9630.01 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 50849.99 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | 光阻櫃 | Labor | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Labor | USC22C012 | USCSB2304084A | 60470 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1923 | C |  | F21 Transportation | 45044 | 45061 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 54423 | 0.9 | 6047 | 6006.5 | 40.5 | 0 | [33 empty] | 0 |  |  | 24188 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 24228.5 |  |  |  |  | 0 |  | 6006.5 | 0 | 0 | 0
Base-Build | CCTV | CCE | The budget execution does not pertain to this project | Labor Incentive | Low Voltage | Electrical | Labor | USC23C045 | USCSB2310171A | 60460.5 | WWT Change Order (Piping) | 2825 | C |  | F21 CCTV system incentive for CCE | 10/27/2023 9/25/2024 | 11/8/2023 9/26/2024 | -85880.5 | 146341 |  |  |  |  | Commercial Comm and Electric Inc | PR Approved | PO Approved | R1: As per PM Paul to close out this PO. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 60460.5 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 60460.5 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2407167A | 60338 | F21P1 AMAT Interconnection | 4590 | C |  | rework KCENA6 & KCENA4, CO KCEPA3 | 45503 | 45510 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 60338 | 1 | 0 | 60338 | -60338 | 0 | [73 empty] | 60338 |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402087A | 60289 | Tool Interconnection Project (Main Tool & Other Vendors) | 802 | P |  | KPOCT7 Labor | 45344 | 45357 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 60289 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 60289 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402029A | 60289 | Tool Interconnection Project (Main Tool & Other Vendors) | 755 | P |  | KPOCT6 Labor | 45325 | 45336 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 60289 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 60289 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC22C001 | USCSB2310049A | 60216 | F21 P1 Office and WH Security and CCTV | 2709 | C |  | F21 P1 Security and CCTV Engineering | 45206 | 45216 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 60216 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 60216 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC21C008 | USCSB2405016A | 60187.83 | F21P1 CCTV & Security | 3988 | C |  | F21 P1 parking gates installation-(3/11) | 45415 | 2024/5/15 2024/8/6 | -1136.87 | 61324.7 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PO R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. | [13 empty] | 58676.94 | 0.9749 | 1510.89 | 0 | 1510.89 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 58676.94 | [6 empty] | - |  | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C003 | USCSB2307099A | 60083.66 | F21P1 UPW | 2265 | C |  | LV 3 – 3rd Party Inspection - July | 45128 | 45135 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved | Will be back-charged to TSMC |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 60083.66 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 60083.66 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2306042A | 60019.55 | F21 TMAH System | 2076 | C | -01 | FAB A PVDF - 02 | 45090 | 2023/6/26 2023/7/4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1:The trade terms need to be FOB. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 47634.98 | 0.79366 | 12384.57 | 0 | 12384.57 | 10003.3458 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 47634.98 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 2381.749 |  | - | 2381.749 | 2381.749 | 2858.0988 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2206001A | 60000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1393 | C |  | MICU Glendale Warehouse Project Management Service | 44714 | 44718 | [6 empty] | Pivotal Project Management LLC | PR Approved | PO Approved |  | 100%-by progress-net 30 days (There has been made an additional $10,000 deposit) | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 50000 | 0.83333 | 10000 | 0 | 10000 | 0 | [9 empty] | 10000 |  | 10000 |  |  | 10000 |  | 10000 |  | 10000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2312018A | 60000 | Tool Interconnection Project (Main Tool & Module) | 567 | P |  | Build ASML EUV Gas Line & QC | 45264 | 45268 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 60000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 60000 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2312017A | 60000 | Tool Interconnection Project (Main Tool & Module) | 566 | P |  | Build ASML EUV Gas Line and QC | 45264 | 45268 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 60000 | 0 | 60000 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2309033A | 60000 | Tool Interconnection Project (Main Tool & Module) | 422 | P |  | Build and qualify gas line | 45192 | 45239 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 60000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 60000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2312020A | 60000 | Tool Interconnection Project (Main Tool & Module) | 569 | P |  | Build ASML EUV Gas Line and QC | 45265 | 45269 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 60000 | 0 | 60000 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2312021A | 60000 | Tool Interconnection Project (Main Tool & Module) | 570 | P |  | Build ASML EUV Gas Line and QC | 45265 | 45268 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 60000 | 0 | 60000 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2208012A | 60000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1449 | C |  | MICU Glendale Warehouse Project Management Service (Extension) | 44798 | 44803 | [6 empty] | Pivotal Project Management LLC | PR Approved | PO Approved | USCSB2206001A extension order | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 30000 | 0.5 | 30000 | 0 | 30000 | 0 | [20 empty] | 10000 |  | 10000 |  | 10000 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | M+L | USC24C005 | USCSB2405034A | 60000 | Chemical & WCCS B Side Project | 4043 | C |  | SDS L3 Add one VMB | 45419 | 45426 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved | [14 empty] | 54000 | 0.9 | 6000 | 0 | 6000 | 60000 | [56 empty] | 0 | [9 empty] | 54000 |  |  |  |  | 60000 |  | - |  |  | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC24C005 | USCSB2405142A | 60000 | Chemical & WCCS B Side Project | 4166 | C |  | Lorry A/B缺失工程 | 45436 | 45443 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved | [14 empty] | 54000 | 0.9 | 6000 | 54000 | -48000 | 0 | [73 empty] | 54000 |  |  | 0
Base-Build | WWT |  |  |  | WWT | Civil | M+L | USC24C006 | USCSB2407051A | 59656.95 | WWT B side Project | 4450 | C |  | Painting mess CO | 45483 | 45489 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 56674.1 | 0.95 | 2982.85 | 56674.102 | -53691.252 | 0 | [71 empty] | 0 |  | 56674.1 | 0 | 0 | 0 | 0
Base-Build | W-H2SO4 | Trident | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC22C022 | USCSB2404044A | 59604.44 | F21P1 Triazole treatment system | 4039 | C |  | Main CO Trident WSR | 45386 | 45394 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | 0 | [11 empty] | 48711.73 | 0.81725 | 10892.71 | 0 | 10892.71 | 8768.1114 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 48711.73 | [6 empty] | 2435.5865 |  | - | 2435.5865 | 3896.9384 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401119A | 59500 | F21P1-0404_H_labor for 50 tools_MICU | 3306 | C |  | HK GENII IDEAS Equipment Rental_1st PO_End date 12/31/2023 | 45308 | 45310 | [6 empty] | GENII IDEAS Co., Ltd. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 59500 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 37720 | 0 |  |  | 0 | 21780 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Greenberry | DCR Scope | WWT | WWT | Steel | M+L | USC23C045 | USCSB2403024A | 59468.46 | WWT Change Order (Piping) | 3733 | C |  | WWT Tunnel additional rack on expansion loop | 45353 | 45357 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 59468.46 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 59468.46 | 8920.269 |  |  |  | 8920.269 |  |  |  | 8920.269 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405046A | 59338.94 | Tool Interconnection Project (Main Tool & Other Vendors) | 1088 | P |  | KDCRS5-DNS SCREEN INTERCONNECTS | 45426 | 45432 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 59338.94 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 59338.94 | [10 empty] | - |  |  | 0
Base-Build | TMAH | MMI | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C011 | USCSB2402085A | 59283 | F21 TMAH System | 3526 | C |  | Tmah ACF expansion Rack for MMI. | 45330 | 45336 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 49048 | 0.82735 | 10235 | 0 | 10235 | 8338.16 | [49 empty] | 0 |  |  | 0 | 0 | 3950 |  | 0 |  | 34863 |  |  |  | 10235 | [8 empty] | 2452.4 |  | - | 2452.4 | 3433.36 | 0 | 0
Base-Build | Slurry |  | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2406088A | 59110 | F21P1 Chemical & WCCS package | 4323 | C |  | FAB A SDS Observation | 45458 | 45463 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 2015 | 0.034089 | 57095 | 975 | 56120 | 0 | [72 empty] | 2015 | - |  |  | 0
Base-Build | VOC |  |  |  | Low Voltage | Mechanical | Labor | USC22C013 | USCSB2407020A | 58950 | F21P1 QR Lab Security & CCTV | 4421 | C |  | F21 P1 VOC duct insulation | 45475 | 45479 | [6 empty] | Petrochem Insulation, Inc | PR Approved | PO Approved | [14 empty] | 53587 | 0.90902 | 5363 | 38217 | -32854 | 43580 | [72 empty] | 15370 | 38217 | 43580 |  | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Material | USC21C003 | USCSB2304031A | 58931 | F21P1 UPW | 1871 | C |  | UPW Bussman 170M6013 Fuse | 45029 | 45033 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 58931 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 58931 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2302002A | 58817 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1683 | C | -01 | Camera and access control for Glendale warehouse | 2023/2/2 2023/6/2 | 2023/2/6 2023/6/13 | 2000 | 56817 |  |  |  |  | Bay Alarm Company | PR Approved | PO Approved | dding additional $2000 to the CCTV system due to the change order. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 58817 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 8522.55 |  | 0 |  |  |  |  | 48294.45 |  |  | 2000 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403018A | 58620.79 | Tool Interconnection Project (Main Tool & Other Vendors) | 845 | P |  | KDSTL1 Interconnects-LAM IC KDSTL1- LAM IC KDSTL1- Labor | 45358 | 45362 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 58620.79 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 58620.79 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Equipment | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2402165A | 58500 | F21P1 Slurry package | 3596 | C |  | SDS HPM L20 H2O2&KOH VMB Control | 45339 | 45344 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 35100 | 0.6 | 23400 | 0 | 23400 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 35100 |  |  | 35100 | [6 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312038A | 58449.14 | Tool Interconnection Project (Main Tool & Module) | 585 | P | -01 | KPAN01-S LIT 1 Streimers | 45269 | 2023/12/14 2024/1/31 | -8057.26 | 66506.4 |  |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PR R1: Total amount change after 100% completion |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 58449.14 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 58449.14 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2303021A | 58406.39 | F21P1-0404_H_Hallway plate install_MICU | 1763 | C |  | 2nd DUV foundation | 44988 | 44995 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 40826.56 | 0.69901 | 17579.83 | 0 | 17579.83 | 0 | [28 empty] | 0 |  | 36871 |  |  | 0 | 3955.56 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2302036A | 58406.39 | F21P1-0404_H_Hallway plate install_MICU | 1717 | C |  | Hookup DUV Foundation Installation | 44973 | 44974 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 40826.56 | 0.69901 | 17579.83 | 0 | 17579.83 | 0 | [28 empty] | 0 |  | 36871 |  |  | 0 | 3955.56 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC21C013 | USCSB2405014A | 58327.5 | F21P1 AMC THC Monitoring System | 3986 | C |  | F21 P1 parking gates installation-(1/11 ) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 58327.5 | 0 | 58327.5 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C004 | USCSB2210044A | 58232.1 | F21P1 WWT package （USA EQ-FRP tank) | 1526 | C |  | FAB Sump Pit Pump RT Fitting | 44860 | 44861 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 58232.1 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 58232.1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC21C005 | USCSB2312010A | 58200 | F21P1 Chemical & WCCS package | 3005 | C |  | CDS IPA Thinner-3 boxes email "Clamp quantity" | 45261 | 45273 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 58200 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 58200 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310064A | 58080 | F21P1-0404_H_labor for 50 tools_MICU | 2724 | C |  | Hansen Quote 10/06 | 45210 | 45224 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 58080 | 0 | 58080 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2308136A | 58000 | F21P1 Chemical & WCCS package | 2431 | C |  | Additional Dry Type Transformer Testing | 45161 | 45161 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 54157.5 | 0.93375 | 3842.5 | 0 | 3842.5 | 0 | [39 empty] | 7250 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 46907.5 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C007 | USCSB2302010A | 57838.09 | F21P1 Module Tool Interconnection PVD1-2 | 1691 | C |  | DI Max chiller line 20 set (include connector ) | 44964 | 44965 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 57838.09 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 52054.28 | 0 | [5 empty] | 5783.81 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309073A | 57823.5 | WWT Change Order (Piping) | 2547 | C |  | TW team material request for LJ | 45183 | 45188 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 57731.1 | 0.9984 | 92.4 | 0 | 92.4 | 0 | [40 empty] | 0 | 0 | 43254.88 | 14476.22 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | UMEC | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2402219A | 57820 | F21P1 Chemical & WCCS package | 3646 | C |  | CDS TSMC 8-188 M1 Poly 700 | 45344 | 45353 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 54929 | 0.95 | 2891 | 0 | 2891 | 2891 | [52 empty] | 0 | 54929 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 2891
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407004A | 57776 | Tool Interconnection Project (Main Tool & Other Vendors) | 1145 | P |  | KPAE02-S PVC Pipe Installation Labor | 45482 | 45489 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 57776 | 0 | 57776 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312026A | 57600 | Tool Interconnection Project (Main Tool & Module) | 575 | P |  | KDSTS2 Mechanical Work and material | 45265 | 45268 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 57031.6 | 0.99013 | 568.4 | 0 | 568.4 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 44696.32 |  | 0 | 12335.28 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | cabinet transport | Equipment | The budget execution does not pertain to this project | chemical safety cabinet | Chemical | Mechanical | Labor | USC23C049 | USCSB2307032A | 57546 | Cabinets transport and installation | 2202 | C |  | F21 Emergency Response Cabinet | 45115 | 45126 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 57546 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 31650.3 |  | 0 | 0 | 11509 | 0 |  | 2877.5 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 11509.2 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2306136A | 57530 | F21P1 UPW | 2169 | C |  | UPW CO-Add | 45106 | 45133 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 57530 | 0 | 57530 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Material | USC21C003 | USCSB2303037A | 57263.7 | F21P1 UPW | 1779 | C |  | UPW Panel Material | 44993 | 44999 | [6 empty] | Service Construction Supply - Division of Darragh Company | PR Approved | PO Approved | Need TSMC Additional PO |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 51051.54 | 0.89152 | 6212.16 | 0 | 6212.16 | 0 | [28 empty] | 0 |  |  |  | 39716.11 | 0 | 11335.43 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C031 | USCSB2409033A | 57081.62 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4800 | C |  | AMHS Hole Framing 2 | 45541 | 45555 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 57081.62 | 0 | 57081.62 | 0 | [73 empty] | -
Non-TSMC | FMCS | Labor |  |  | Others |  |  | USC22C007 | USCSB2403254A | 57058 | TSMC F21 FMCS Installation | 3947 | C |  | Overtime for Fiber Cable Pulls & Splicers 3 Weeks | 45378 | 45378 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 57058 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 57058 | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310009A | 57021.97 | F21P1-0404_H_labor for 50 tools_MICU | 2672 | C |  | Tool and Material for Taiwan team | 45202 | 45209 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 56507.17 | 0.99097 | 514.8 | 0 | 514.8 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 46622.05 | 0 | 0 | 9885.12 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2407104A | 56996.67 | F21P1 AMAT Interconnection | 4519 | C |  | P1B Material | 45490 | 45503 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 54128.5 | 0.94968 | 2868.17 | 55447.11 | -52578.94 | 0 | [72 empty] | 732.57 | 53395.93 |  |  | 0
Base-Build | TMAH |  | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2406092A | 56795.35 | F21 TMAH System | 4327 | C |  | PR Harrington WWT - TMAH Expansion Material (PP) | 45461 | 45464 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 56795.35 | 1 | 0 | 1043.13 | -1043.13 | 0 | [68 empty] | 55584.91 |  | 167.31 | 0 |  | 1043.13 | 0 | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2408042A | 56700 | F21P1 AMHS Wiring Work Outline | 4633 | C |  | 30,000 FT #8/3C Wire_AMHS | 45513 | 45517 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 56700 | 1 | 0 | 56700 | -56700 | [74 empty] | 56700
Base-Build | W-H2SO4 | Trident | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C014 | USCSB2403213A | 56625.5 | F21P1 WH2SO4 | 3908 | C |  | 2023 H2SO4 Labor Incentive Change Order | 45372 | 45377 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 56625.5 | 0 | 56625.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 8493.825 |  |  |  | 8493.825 |  |  |  | 8493.825 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC22C026 | USCSB2401254A | 56500 | F21P1-0423_H_Unistrut Support Frame_MICU | 3435 | C |  | raised floor | 45322 | 45327 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 56500 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 56500 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2404108A | 56430 | F21P1 AMAT Interconnection | 4093 | C |  | NUUO Change Order: terminations | 45395 | 45419 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 56430 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [7 empty] | 15390 |  | 41040 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311003A | 56376.12 | Tool Interconnection Project (Main Tool & Module) | 478 | P |  | KDSNB1 Mechanical Work 12 working days | 45232 | 45245 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 49053.01 | 0.8701 | 7323.11 | 0 | 7323.11 | 0 | [42 empty] | 0 | 0 |  | 0 | 49053.01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311004A | 56376.12 | Tool Interconnection Project (Main Tool & Module) | 479 | P |  | KDCRS3 Mechanical Work. 12 days | 45232 | 45245 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 55076.49 | 0.97695 | 1299.63 | 0 | 1299.63 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 28048.35 |  | 0 | 27028.14 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410035A | 56000 | Tool Hook Up E2 Trade Equipment Rental | 4978 | C |  | HK Chuan Ta Technology Corp Equipment rental End date 08/31/2024 | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 56000 | 0 | 56000 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2306132A | 55981 | F21 TMAH System | 2165 | C |  | WWT Repair Leak T-140AA Tank | 45106 | 45140 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 55981 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 55981 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2310150A | 55825.84 | F21P1 Chemical & WCCS package | 2806 | C |  | Professional Plastics custom the parts for VMB of A side | 45223 | 45226 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 55825.84 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 55825.84 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2308179A | 55500 | WWT Change Order (Piping) | 2472 | C |  | WWT -TW-Maxiplast | 2023/8/30 2023/9/6 | 45176 | [6 empty] | Widos Taiwan Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 55500 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 31500 | 0 | 0 | 0 | 0 |  | 24000 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW |  | Main Contract Scope | UPW | UPW | Electrical | Labor | USC24C008 | USCSB2405168A | 55484 | UPW B Side Project | 4196 | C |  | Horiba Calibration Service | 45442 | 2024/6/26 2024/7/4 | [6 empty] | HORIBA Instruments Incorporated | PR Approved | PO Approved | R1: Add Billing Address per request | [13 empty] | 0 | 0 | 55484 | 0 | 55484 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Greenberry | Main Contract Scope | WWT | WWT | Steel | M+L | USC23C045 | USCSB2312006A | 55414 | WWT Change Order (Piping) | 3001 | C |  | WWT Tunnel support | 45261 | 45269 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 55414 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8312.1 | 55414 |  |  | 8312.1 |  |  |  | 8312.1 |  | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2408091A | 55339.39 | F21P1 AMHS Wiring Work Outline | 4705 | C |  | Salary Delta of Sinfonia Engineers from 2/28/24 to 5/31/24 | 45525 | 45532 | [6 empty] | SINFONIA ENGINEERING CO., LTD. TAIWAN BRANCH | PR Approved | PO Approved | [14 empty] | 49744.07 | 0.89889 | 5595.32 | 0 | 5595.32 | 0 | [70 empty] | 49744.07 |  |  | -
Base-Build | WWT | Material | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C009 | USCSB2405090A | 55281.6 | F21P1 WWT package (Installation and 2 batch tanks) | 4110 | C |  | WWT-Enzyme for TSMC urgent request on 5/13 | 45427 | 45429 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved | [14 empty] | 55281.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 |  |  |  | 55281.6 | [10 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2209016A | 55125 | F21P1 UPW | 1468 | C |  | Horiba SLIA Reagent | 44820 | 44826 | [6 empty] | HORIBA Instruments Incorporated | PR Approved | PO Approved |  | 100% by received-Net 30 days-After acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [5 empty] | 5000 |  | 55125 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 55125 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2404107A | 55105.01 | F21P1 AMAT Interconnection | 3923 | C |  | non materila provided by trade | 45395 | 45436 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 55105.01 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 55105.01 | [6 empty] | - |  |  | 0
Non-TSMC | MIC - Material | Material |  |  | Others |  |  | USC22C016 | USCSB2210011A | 54894.23 | Asahi Valve and Positioner from Harrington |  | C |  | Asahi Valve and Positioner from Harrington | 44841 | 44843 | [23 empty] | 54894.23 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 54371.57 | 522.66 | [5 empty] | 0 | [11 empty] | 0 |  | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405005A | 54720.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 1064 | P |  | KEBCT3- TEL INTERCONECTS-4/1-4/9/2024 | 45416 | 45422 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 54720.12 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 54720.12 | [10 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2302029A | 54673.09 | F21P1 WWT package (Installation and 2 batch tanks) | 1710 | C |  | PVC fittings for 6.5 | 44971 | 45063 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 53741.24 | 0.98296 | 931.85 | 0 | 931.85 | 1074.8248 | [28 empty] | 0 |  |  |  |  | 0 | 51680.44 |  | 2060.8 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 1074.8248
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC21C006 | USCSB2402143A | 54626.4 | F21P1 Slurry package | 3576 | C |  | CDS HongDong recent construction work by 02/06/24 | 45337 | 45349 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 54626.4 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 54626.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404005A | 54585.17 | Tool Interconnection Project (Main Tool & Other Vendors) | 960 | P |  | KRWRS3 DNS SCREEN INETRCONNE 3/13-3/27/2024CTS | 45384 | 45388 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 54585.17 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 54585.17 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2308001A | 54525 | F21P1 WWT package (Installation and 2 batch tanks) | 2306 | C |  | WWT Tank Crossover Platform Bracket Bonding (112 Bonds Total) | 45139 | 45151 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 54525 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8178.75 |  |  |  | 8178.75 | 54525 |  |  | 8178.75 |  | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C018 | USCSB2410037A | 54400 | Tool Hook Up E2 Trade Equipment Rental | 4980 | C |  | Laien Parts Technology Co.， Ltd Equipment rental End date 08/31/2024 | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 54400 | 0 | 54400 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C034 | USCSB2211036A | 54320 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/N2/APK/UPK/ASRS | 1569 | C |  | TSMC F21P1 FAB and HPM AMHS Infrastructure Non-AMHS Device Power Hook-up | 44889 | 44894 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 54320 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 25487 |  | 20975 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 7247 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 611 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407175A | 54289.81 | WWT B side Project | 4598 | C |  | WWT shortage of fitting materials on the B side | 45504 | 45506 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 33067.63 | 0.60909 | 21222.18 | 28665.27 | -7443.09 | [73 empty] | 25624.54 | 7443.09
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401004A | 54219.71 | Tool Interconnection Project (Main Tool & Other Vendors) | 628 | P |  | KPD801-S Labor | 45300 | 45307 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 54219.71 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 54219.71 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404027A | 54177.84 | Tool Interconnection Project (Main Tool & Other Vendors) | 982 | P |  | KRWRS7-DNS SCREEN INTERCONNECTS 3/13-3/28/2024 | 45386 | 45387 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 54177.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 54177.84 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Southland | The budget execution does not pertain to this project | VOC | Low Voltage | Mechanical | M+L | USC21C014 | USCSB2309136A | 54039 | F21P1 WH2SO4 | 2607 | C |  | F21 P1 VOC DPI Added Material | 45190 | 45197 | [6 empty] | Southland Industries | PR Approved | PO Approved | Change order corresponds and chargeable against D-Tech (PR Form Note) |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 54038.9 | 1 | 0.1 | 0 | 0.1 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 48635 | 5403.9 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2308177A | 54000 | F21P1 Chemical & WCCS package | 2470 | C |  | Epoxy Misc Pads in Roof | 45168 | 45194 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 54000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 54000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2307014A | 53900 | F21P1-0404_H_Hallway plate install_MICU | 2186 | C |  | 50 single barricades | 45113 | 45127 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 53900 | 0 | 53900 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | CO Scope (adding/additional scope) | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | M+L | USC21C003 | USCSB2305092A | 53862.4 | F21P1 UPW | 2013 | C |  | TSMC EMERGENCY TFMB #2 | 45065 | 45124 | [6 empty] | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 49010.75 | 0.90993 | 4851.65 | 0 | 4851.65 | 0 | [35 empty] | 25059.38 | 15484.18 |  |  |  | 5824.93 | 2642.26 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404025A | 53692.42 | Tool Interconnection Project (Main Tool & Other Vendors) | 980 | P |  | KRWRS6-DNS SCREEN INTERCONNECTS 2/22-3/28/2024 | 45386 | 45387 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 53692.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 53692.42 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2308021A | 53527.38 | F21P1 Chemical & WCCS package | 2323 | C | -01 | F21 P1 CDS POWER CABLE | 2023/8/4 2023/8/9 | 2023/8/7 2023/8/15 | 26763.69 | 26763.69 |  |  | V |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1:revise QTY and price (Double QTY) |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 53527.38 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 53527.38 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2303008A | 53403.33 | F21P1 Module Tool Interconnection CVD | 1750 | C |  | LSC cabinet signal cable (22AWG/2C, 22AWG/4C) | 44987 | 45012 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 53403.33 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 53403.33 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405128A | 53373 | F21P1-0404_H_labor for 50 tools_MICU | 4156 | C |  | Quote of 100 argon cylinders for HK shared by all system | 45434 | 45437 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 53373 | 1 | 0 | 1725 | -1725 | 0 | [62 empty] | 1514.69 |  | 13194.25 |  | 9425.85 |  | 14849.81 |  | 11964.24 |  | 2424.16 | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310047A | 53298 | Tool Interconnection Project (Main Tool & Module) | 465 | P |  | Work Post TM Reconciliation | 2023/10/21 2023/11/4 | 45307 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved | PR R1: THIS IS ORIGINAL BETWEEN TONY LEE AND TRIDENT |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 53298 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 53298 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2312042A | 53160 | Tool Interconnection Project (Main Tool & Module) | 589 | P |  | KPE603-S Cabinets | 45271 | 45275 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 41730.6 | 0.785 | 11429.4 | 0 | 11429.4 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 10632 | 0 | 0 |  | 0 |  | 18911.67 | [11 empty] | 12186.93 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2406146A | 53131.05 | WWT B side Project | 4384 | C |  | WWT - Brahma T-140AC-AC Carboline Flange Coating | 45471 | 45476 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 38618.12 | 0.72685 | 14512.93 | 0 | 14512.93 | 0 | [70 empty] | 38618.12 | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | Main Contract Scope | CDS | Chemical | Mechanical | Housekeeping | USC21C005 | USCSB2305079A | 53099.12 | F21P1 Chemical & WCCS package | 2000 | C |  | BHTC housekeeping | 45063 | 45077 | [6 empty] | BHTC Arizona, LLC | PR Approved | PO Approved | Extension for USCSB2211009A for paying final invoice |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 53099.12 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 53099.12 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2310025A | 53075.77 | WWT Change Order (Piping) | 2688 | C |  | 9/19/23 to 10/20/23 Southwest Fastener Monthly Order for Water Team | 45203 | 45239 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 53075.77 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 19697.77 | 33378 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308019A | 53032 | Tool Interconnection Project (Main Tool & Module) | 369 | P |  | KPAE01-T ONSIGHT LIVE LABOR PAY | 45166 | 45174 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 53032 | 0 | 53032 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | CCE | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2302001A | 52780 | F21P1 UPW | 1682 | C |  | X1 Line Temp Power Cable Relocation | 44959 | 44966 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 52780 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 52780 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402111A | 52138 | F21P1-0404_H_labor for 50 tools_MICU | 3549 | C |  | Liquid argon shared by all HK system | 45334 | 45337 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 52138 | 1 | 0 | 150 | -150 | 0 | [49 empty] | 0 |  | 21445.48 | 0 | 0 | 19170.97 |  | 7025.22 |  |  |  | 3995.84 |  | 500.49 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311072A | 52134.12 | F21P1-0404_H_labor for 50 tools_MICU | 2926 | C |  | Liquid Argon for CHY PCW. Tool id: KCANN1, KDALS1, KCENA1 KECOA1 KCEPA1 KDPOT2 KEMEL1 KECOT2 KPAE01-S KESRT4 | 45246 | 45267 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 52076.22 | 0.99889 | 57.9 | 83.75 | -25.85 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 50245.27 | 0 | 0 | 0 |  | 0 | [5 empty] | 1830.95 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC23C045 | USCSB2309057A | 52125 | WWT Change Order (Piping) | 2533 | C |  | Epoxy Misc Pads in Fab LB2 | 45182 | 45188 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 52125 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 52125 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | GF Agru Material | Material |  |  | WWT | Mechanical | Material | USC22C023 | USCSB2210023A | 52079.75 | AZ GF Agru Material | 1506 | C |  | GF PP&PVDF Material UANGYIH | 44847 | 44851 | [6 empty] | Uangyih-Tech Industrial Co., LTD | PR Approved | PO Approved |  | 100% by progress-Net 60 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 52079.75 | 1 | 0 | 0 | 0 | 0 | [21 empty] | 52079.75 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | VOC | Southland | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2212021A | 52049.16 | F21P1 VOC package （Installation ) | 1594 | C |  | VOC Duct/Pipe Labels | 44908 | 44923 | [6 empty] | Southland Industries | PR Approved | PO Approved | USCSB2109008A-1 change order |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 52049.16 | 0 | 52049.16 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 13013 |  |  |  | - |  |  | 0
Base-Build | VOC | Southland | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC21C007 | USCSB2301060A | 52049.16 | F21P1 VOC package （Installation ) | 1676 | C |  | VOC Duct / Pipe Lables | 44954 | 44970 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 52048.77 | 0.99999 | 0.39 | 0 | 0.39 | 0 | [28 empty] | 0 |  |  |  | 28721 | 0 | [6 empty] | 10151 | 0 | 0 | 0 |  | 0 | 0 | 3581 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 9595.77 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312163A | 52005.25 | F21P1-0404_H_labor for 50 tools_MICU | 3151 | C |  | chemical system materials, for the next 300 machines, tool hookup | 2023/12/22 2024/9/18 | 2023/12/26 2024/9/18 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | PR R1: To match the requisition amount and the PO amount |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 52005.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 52005.25 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2210032A | 52000 | F21P1 WWT package (Installation and 2 batch tanks) | 1515 | C |  | PHP-Tank Painting | 44853 | 44855 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved | Harrington Paint white (incorrect), PHP repaint and Harrington will pay 50% |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 52000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 52000 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2407095A | 52000 | F21P1 Module Tool Interconnection ETC1-3 | 4522 | C |  | YAHO_KEVILE_KEMEL2 | 45489 | [7 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 52000 | 0 | 52000 | [74 empty] | -
Base-Build | Chemical |  |  |  | Chemical | Electrical | Labor | USC24C005 | USCSB2407004A | 52000 | Chemical & WCCS B Side Project | 4406 | C |  | 泉太 MICU E2 支援報價單(2個月) | 45474 | 45478 | [6 empty] | CHEN-TAI-ENTERPRISE CO.,LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 52000 | 0 | 52000 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402050A | 51570.94 | Tool Interconnection Project (Main Tool & Other Vendors) | 770 | P |  | 2/5/2024: KPSP11: 3" FLEX HOSE INSTALLATION | 45329 | 45366 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 51570.94 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 51570.94 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2301024A | 51498.43 | F21P1 Chemical & WCCS package | 1646 | C |  | Flame Arrester | 44937 | 44950 | [6 empty] | Caltrol Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 51498.43 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 13701.28 |  | 37797.15 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | DCR Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2205026A | 51232.6 | F21P1 Chemical & WCCS package | 1388 | C | -01 | CDS Change Order for UPW at Lorry | 2022/5/22 2024/6/13 | 2022/5/24 2024/6/13 | -204930.4 | 256163 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny to cancel all Harder orders. R0: USCSB2201007A的Change Order | 95% by progress-T/T 30 days-after acceptance; 5% as-built drawing & punch list-T/T 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 51232.6 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 51232.6 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2309163A | 51160 | F21P1-0404_H_Hallway plate install_MICU | 2633 | C |  | MMI 0527~0528 overtime for B6-1 foundation | 45196 | 45202 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 51160 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 51160 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2408071A | 51123.62 | WWT B side Project | 4687 | C |  | WWT - WRC Agitator Support Extensions | 45519 | 45541 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 51123.62 | 35123.62 | 16000 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401071A | 50935.1 | Tool Interconnection Project (Main Tool & Other Vendors) | 691 | P |  | Labor and materials for KDSTS2 | 45316 | 45320 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 48587.9 | 0.95392 | 2347.2 | 0 | 2347.2 | 0 | [47 empty] | 0 | 0 | 0 | 16431.99 |  | 0 | 32155.91 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2212033A | 50858 | F21P1 Chemical & WCCS package | 1605 | C |  | Lorry Vertical Support | 44912 | 44916 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 50858 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 3950 |  | 21488.5 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 50858 |  |  |  |  | 25419.5 |  |  |  |  | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C025 | USCSB2409124A | 50855.5 | Tool Hookup Material (UPW&Chemical) | 4942 | C |  | AC box relocation _AMHS | 45563 | 45566 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 50855.5 | 0 | 50855.5 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307012A | 50750 | Tool Interconnection Project (Main Tool & Module) | 347 | P |  | KPAN01-S Onsight Live- Proposal no # | 45136 | 45169 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 50750 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 50750 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C008 | USCSB2204011A | 50600 | F21P1 CCTV & Security | 1360 | C |  | TSMC - CCTV Panel Builds | 44679 | 44680 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 50600 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 40986 | 0 |  | 9614 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2406054A | 50410 | F21P1 Chemical & WCCS package | 4287 | C |  | FAB A WCCS Observation | 45450 | 45455 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 14697.5 | 0.29156 | 35712.5 | 3645 | 32067.5 | 0 | [68 empty] | 11437.5 |  |  |  | 3260 | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2312173A | 50171.7 | F21P1 WWT package (Installation and 2 batch tanks) | 3161 | C |  | TSMC 12.18 PVDF material item | 45283 | 44929 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 50171.7 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 50171.7 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C025 | USCSB2410020A | 50072.4 | Tool Hookup Material (UPW&Chemical) | 4963 | C |  | Additional Material needs for P1B AMHS 1/3,6/3,8/3,10/3 wire_2/3 batch | 45567 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 50072.4 | 0 | 50072.4 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2306072A | 50000 | F21P1 Chemical & WCCS package | 2105 | C |  | TSMC F21 CDS DC Panel | 45093 | 45099 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 50000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 50000 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2406113A | 50000 | WWT B side Project | 4353 | C |  | WWT: CCR Scope Initial Funding to Start Work | 45465 | 45475 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 50000 | 0 | 50000 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC23C045 | USCSB2402261A | 50000 | WWT Change Order (Piping) | 3687 | C |  | WWT Chemical Area Safety Paint(OPEN PR) | 45350 | 45352 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 50000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 7500 | 50000 |  |  | 7500 |  |  |  | 7500 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Rosendin | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC23C054 | USCSB2403137A | 50000 | UPW Change Order | 3838 | C |  | PCO 82 Contract Pricing Adjustment, Continuation of Work Phase 2, Revision 0(batch 2/2) | 45365 | 45365 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 50000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 50000 | [6 empty] | 50000 |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Scaffolding |  |  | Others |  |  | USC23C055 | USCSB2312184A | 50000 | F21P1-0404_H_labor for 50 tools_MICU | 3171 | C |  | OPEN PO scaffold services labor, material, and equipment for hook up shared by all system | 45287 | 45315 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 32500 | 0.65 | 17500 | 0 | 17500 | 0 | [47 empty] | 0 | 0 | 0 | 32500 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2311022A | 50000 | WWT Change Order (Piping) | 2877 | C |  | WWT-BMWC-LSR -Train A | 45234 | 45258 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 47500 | 0.95 | 2500 | 0 | 2500 | 2375 | [43 empty] | 0 |  | 0 | 0 | 47500 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 2375
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408092A | 49910 | TSMC Fab 21 P1B Tool Hook Up | 4706 | C |  | Liquid Argon for Gas, Chemical, PCW, and PPL for HK | 45526 | 45532 | [6 empty] | Linde Gas & Equipment Inc. | PR Approved | PO Approved | [14 empty] | 18153.56 | 0.36373 | 31756.44 | 12495 | 19261.44 | 0 | [72 empty] | 18153.56 | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C005 | USCSB2308074A | 49904 | F21P1 Module Tool Interconnection DIF1-2 | 2372 | C |  | DIFF1: KDAPK2-4, Install triple layer containment | 45153 | 45216 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 49904 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 49904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2407046A | 49800 | F21P1 AMHS Power Panel | 4445 | C |  | A Side AC Panel Relocation | 45483 | 45485 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 47310 | 0.95 | 2490 | 47310 | -44820 | 0 | [73 empty] | 47310 |  |  | 0
Base-Build | UPW | Equipment | CO Scope (adding/additional scope) | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | M+L | USC21C003 | USCSB2304033A | 49464.61 | F21P1 UPW | 1873 | C |  | TSMC EMERGENCY TFMB | 45031 | 45124 | [6 empty] | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 49464.61 | 1 | 0 | 0 | 0 | 0 | [35 empty] | 37830.06 | 8972.12 |  |  |  | 2662.43 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2304051A | 49452 | F21P1 UPW | 1891 | C |  | Tanks underlayment | 45035 | 45055 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 49452 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 49452 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C009 | USCSB2208013A | 49350 | F21P1 WWT package (Installation and 2 batch tanks) | 1450 | C |  | TSMC Phoenix Fab Advantech Design Services | 44799 | 44805 | [6 empty] | Advantech Facility Design Inc. | PR Approved | PO Approved | Previously paid by APN, but rejected by accounting, so issue PO | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 49350 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 49350 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2304049A | 49206.08 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1889 | C |  | HK UPW PVDF Flare Transition Fittings | 45035 | 45042 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 49206.08 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 12249.04 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 36957.04 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC24C006 | USCSB2408024A | 49200 | WWT B side Project | 4619 | C |  | WWT: Farnsworth assist EOR with Design Change Review and Revisions | 45511 | 45524 | [6 empty] | Farnsworth Group, Inc | PR Approved | PO Approved | [14 empty] | 49200 | 1 | 0 | 49200 | -49200 | [74 empty] | 49200
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306029A | 49000 | Tool Interconnection Project (Main Tool & Module) | 314 | P |  | KPAE01 ONSIGHT LIVE ELECTRICAL INTERCONNECT | 45086 | 45096 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 49000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 49000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308009A | 49000 | Tool Interconnection Project (Main Tool & Module) | 359 | P |  | KPD801-T ONSIGHT LIVE LABOR PAY | 45141 | 45149 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 49000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 34300 | 0 | 0 | 0 | 14700 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2302013A | 49000 | F21P1 UPW | 1694 | C |  | Tanks water test | 44964 | 45033 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 49000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 49000 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2305014A | 49000 | Tool Interconnection Project (Main Tool & Module) | 281 | P |  | KPAP01 ONSIGHT LIVE ELECTRICAL INTERCONNECT | 45077 | 45090 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 45500 | 0.92857 | 3500 | 0 | 3500 | 0 | [33 empty] | 0 |  |  | 35000 |  |  | 10500 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403031A | 48991.25 | Tool Interconnection Project (Main Tool & Other Vendors) | 857 | P |  | U1AT375-062 TUBING-CUT STOCK 451 HPJ 3/8IN | 45359 | 45363 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 48991.25 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 44811.25 | 4180 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Southland | DCR Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2307037A | 48798 | F21P1 Chemical & WCCS package | 2206 | C |  | 5222338-CO #096 Lorry PTFE Drain Redesign-Material | 45118 | 45133 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 48798 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 48798 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | MMI | Main Contract Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2307047A | 48625 | F21P1 Slurry package | 2216 | C |  | TSMC FAB L30 Floor penetration supports Per RFI #034 | 45119 | 45145 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 48625 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 48625 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405134A | 48583.04 | Tool Interconnection Project (Main Tool & Other Vendors) | 1111 | P |  | Quote 0877- KSCTT1 8395 Certification and cable pull and admin fee | 45434 | 45437 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 48583.04 | 0 | 48583.04 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2203013A | 48390 | F21P1 WWT package (Installation and 2 batch tanks) | 1348 | C |  | TSMC Trench Cover Plates | 44644 | 44645 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT (N) | [6 empty] | 48390 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 34790 |  |  |  | 13600 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C037 | USCSB2305044A | 48283.4 | F21P1 Screen Main tool interconnection | 1969 | C | -01 | Mechanical Interconnect | 45057 | 45099 | 0 | 48283.4 |  |  |  |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | Better payment terms |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 48283.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 6071.76 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 42211.64 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2209011A | 48140 | F21P1 UPW | 1463 | C |  | Horiba Conductivity/Resistivity Meter | 44818 | 44819 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved | 此張單因貨幣關係重開以美金計價(原單為USCSB2208018A以日幣計價) | 100% after goods arrival date-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 48140 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 38470.45 |  | 9669.55 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC24C005 | USCSB2404156A | 48048 | Chemical & WCCS B Side Project | 4140 | C |  | F21 P1B區 Chemical赴美管路工程施工by機具租賃 | 45402 | 45405 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 24024 | 0.5 | 24024 | 16016 | 8008 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 48048 |  |  |  |  | 8008 |  |  |  | 8008 | 0 |  | 8008 | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Labor | USC24C005 | USCSB2408134A | 48000 | Chemical & WCCS B Side Project | 4744 | C |  | 支援F21帆宣電力工程-點工(不含機具) for 1 month | 45533 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 48000 | 0 | 48000 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401216A | 47980 | F21P1-0404_H_labor for 50 tools_MICU | 3398 | C |  | Spiral pipe and flat flange for HK Exhaust trade | 45317 | 45317 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 22048.8 | 0.45954 | 25931.2 | 0 | 25931.2 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 12164 |  | 0 |  | 9884.8 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2210034A | 47962.09 | F21P1 WWT package (Installation and 2 batch tanks) | 1517 | C |  | Confined Space Entry manwatch | 44854 | 44867 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 40802.09 | 0.85072 | 0 | 0 | 0 | 0 | [26 empty] | 40802.09 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1438.8627 |  |  |  | 1438.8627 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2309148A | 47932.86 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2619 | C |  | Hua Yi Construction Az On-site Clean Room Construction | 45192 | 45203 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 47932.86 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 47932.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C003 | USCSB2410017A | 47864 | F21P1 Module Tool Interconnection CVD | 4961 | C |  | LAM CVD Module CIP gas line modification for Tools: KCANN5/KCAPN2/KCOXNM/KCOCN2/KCOXNB/KCOXNA/KCOXNH/KCOXND/KCOXNN/KCANN4/KCT | 45567 | [7 empty] | 0 | PR Approving | PR Applying | [14 empty] | 0 | 0 | 47864 | 0 | 47864 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403198A | 47858.4 | F21P1 WWT package (Installation and 2 batch tanks) | 3894 | C |  | [B side] Welding machine rental from Harrington 12”*1/20”*1 - 2nd rental | 45371 | 45371 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 41143.69 | 0.8597 | 6714.71 | 0 | 6714.71 | 11751.943 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 7178.76 | 16788.49 |  |  | 7178.76 |  |  | 11963.69 | 7178.76 |  | 5875.9715 | 12391.51 | - | 5875.9715 | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C014 | USCSB2410026A | 47762.44 | F21P1 AMHS Power Panel | 4969 | C |  | DP Design Change_AMHS_3/7 batch | 45568 | [7 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 47762.44 | 0 | 47762.44 | 0
Base-Build | UPW | Material | DCR Scope | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2204001A | 47674 | F21P1 UPW | 1351 | C |  | Additional Submain 01 | 44652 | 44657 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | 原PO:USCSB2203014A異動 | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 47674 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 19162.62 |  |  |  | 28511.38 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310128A | 47643.57 | F21P1-0404_H_labor for 50 tools_MICU | 2787 | C |  | CED Building Wire; THHN STR; 250 kcmil; 1-Conductor; Copper; Black; 500 Ft. for Third | 45219 | 45234 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 47643.57 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 47643.57 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2408146A | 47541 | F21P1 Module Tool Interconnection DIF1-2 | 4754 | C |  | DIFF1-2: KDPOT3, KDAPK5, KDSRK1, KDTNK2, KDRIM2, KIMIS1: INSTALL SIGNAL & POWER CABLES | 45534 | 45539 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 47541 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 47541 | -
Base-Build | Base-Build | Labor | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C005 | USCSB2302021A | 47500 | F21P1 Chemical & WCCS package | 1702 | C |  | MRT Design- Additional Service amendment | 44967 | 44978 | [6 empty] | MRT DESIGN LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 30000 | 0.63158 | 17500 | 0 | 17500 | 0 | [26 empty] | 10000 |  | 5000 |  |  | 5000 | 7500 | 0 |  |  | 2500 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USC2111048A | 47296.04 | F21P1 Chemical & WCCS package | 49 | P | -01 | Power Panels | 2021/11/23 2021/12/29 | 2021/12/9 2022/01/21 | 2033.9 | 45262.14 | V |  | V |  | Kelso-Burnett Co. | PR Approved | PO Approved | Rev02-change in quantity and additional year warranty Rev01-Adding cost for warranty, additonal 12 months of warranty, please provide final quotation. | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 0 | 0 | 47296.04 | 0 | 47296.04 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | 5G | Material | The budget execution does not pertain to this project | WWT | WWT | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C010 | USCSB2210004A | 47294.07 | F21 P1 LSC CMS and DPM 5G System | 1488 | C |  | TSMC-F21P1-Temporary outfall monitoring | 44835 | 44842 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved | TSMC hasn't issued PO to us. Once TSMC issues, we will back charge this portion with profit markup. The reason why it uses the budget here is simply because we have sufficient room in this project | 15% prepayment-Net 30 days; 75% by progress-Net 30 days-after acceptance; 10% after final acceptance (site acceptable test)-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [5 empty] | 5000 |  | 44882.71 | 0.94901 | 2411.36 | 0 | 2411.36 | 2364.7 | [22 empty] | 33600.84 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 11281.87 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 2364.7
Base-Build | UPW | Equipment | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2308092A | 47217.47 | F21P1 UPW | 2389 | C |  | Veolia turbo bed-3rd | 45155 | 45157 | [6 empty] | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 47217.47 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 47217.47 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408055A | 47136 | F21P1 Module Tool Interconnection LIT2-3 | 4673 | C |  | Lit 3: KPAP02-T: Rework | 45517 | 45519 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 47136 | 47136 | 0 | 0 | [73 empty] | -
Base-Build | Chemical | MMI | 0 | 0 | Chemical | Steel | M+L | USC21C009 | USCSB2312112A | 47068 | F21P1 WWT package (Installation and 2 batch tanks) | 3102 | C |  | CDS A side platform rail | 45276 | 45288 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 47068 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 22357.3 | 23534 |  | 0 |  | 1176.7 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403030A | 47000 | Tool Interconnection Project (Main Tool & Other Vendors) | 856 | P |  | KPCD04: CABLE PULL | 2024/3/7 2024/3/16 | 45369 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 47000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 47000 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Labor | USC21C013 | USCSB2307076A | 47000 | F21P1 AMC THC Monitoring System | 2243 | C |  | F21 P1 THC DPT flow meter installation | 45125 | 45131 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 43605 | 0.92777 | 3395 | 0 | 3395 | 940 | [39 empty] | 3420 | 10640 | 0 | 2280 | 0 |  | 0 | 5415 | 0 | 0 | 12255 | 9595 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 940 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401100A | 46994 | Tool Interconnection Project (Main Tool & Other Vendors) | 717 | P |  | KPD802-S Labor | 45321 | 45323 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 46994 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 46994 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2204008A | 46538.7 | F21P1 UPW | 1357 | C |  | MIC trailer office network | 44670 | 44672 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 46538.7 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 46538.7 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2212050A | 46502.72 | F21P1 QR Lab Security & CCTV | 1621 | C |  | F21P1 CCD_Security&CCTV Package | 44924 | 44948 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 35915 | 0.77232 | 10587.72 | 0 | 10587.72 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 8185 | 0 |  | 0 | [7 empty] | 27730 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC22C012 | USCSB2405020A | 46468.8 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3992 | C |  | F21 P1 parking gates installation-(7/11) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 46468.8 | 0 | 46468.8 | 44145.36 | [54 empty] | 0 |  | 0 | [14 empty] | 44145.36 |  | - |  | 0 | 0
Non-TSMC | Micron - Material | Material |  |  | Others |  |  | USC24C001 | USCSB2401129A | 46250 | Micron - Chemical SOLBLE RN3000 | 3315 | C |  | Chemical SOLBLE RN3000 for Micron Manassas facility, Virginia | 45309 | 45310 | [6 empty] | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 46250 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 46250 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C001 | USCSB2309046A | 46200 | TEL Main Tool Interconnection | 2523 | C |  | KPOCT9 HYC | 45181 | 45216 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 46200 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 46200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C009 | USCSB2403033A | 46091 | F21P1 WWT package (Installation and 2 batch tanks) | 3742 | C |  | WWT - T&M Proposal to Work Stainless Line in LB2 | 45356 | 45359 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2861.4 | 0.062082 | 43229.6 | 0 | 43229.6 | 46091 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 6913.65 |  |  |  | 6913.65 |  |  |  | 6913.65 | 2861.4 | 11522.75 |  | - | 11522.75 | 11522.75 | 11522.75 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C009 | USCSB2402123A | 46091 | F21P1 WWT package (Installation and 2 batch tanks) | 3560 | C |  | WWT - T&M Proposal to Work Stainless Line in LB2 | 45336 | 45337 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 46091 | 0 | 46091 | 46091 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 6913.65 |  |  |  | 6913.65 |  |  |  | 6913.65 |  | 11522.75 |  | - | 11522.75 | 11522.75 | 11522.75 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2401192A | 45952 | WWT Change Order (Piping) | 3377 | C |  | WWT -MIC BMWC T&M SUS team 6*60hr | 45315 | 45315 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 43654.4 | 0.95 | 2297.6 | 0 | 2297.6 | 2182.72 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 43654.4 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 2182.72
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312037A | 45921.75 | Tool Interconnection Project (Main Tool & Module) | 584 | P | -01 | KPOCS2 Exhaust Hookup | 2023/12/8 2024/3/26 | 2023/12/12 2024/3/27 | 4355.25 | 41566.5 | V |  |  | V | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PR R1: Updated amount for KPOCS2 billing issue. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 45921.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 45921.75 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C025 | USCSB2402116A | 45728.4 | AMHS TSMC Instrustructure and Branch Circuits | 3554 | C |  | AMHS F21 Side B 8 Additional DP Installation | 45335 | 45338 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 45728.4 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 45728.4 | [8 empty] | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405127A | 45566.81 | WWT B side Project | 4155 | C |  | WWT Fittings_20240521 (B Side) | 45434 | 45436 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 45566.81 | 1 | 0 | 0 | 0 | 11331.745 | [64 empty] | 11283.91 |  | 11379.58 |  | 22903.32 |  |  | 5665.8725 |  | - | 5665.8725 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2312145A | 45550 | F21P1 Chemical & WCCS package | 3134 | C |  | Pipe, tube and fitting from MIC TW-1 | 45279 | 45281 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 45550 | 0 | 45550 | 45550 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 45550
Base-Build | UPW | Equipment | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2307026A | 45500 | F21P1 UPW | 2198 | C |  | Purchase and Install Safety Gates on Tanks(UPW swing gate) | 45114 | 45119 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 45500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 13325 | 2860 | 0 |  | 0 | 20995 | 0 | 0 | 0 | 3900 | 3510 | 0 | 0 | 0 |  | 0 |  | 910 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308003A | 45417.4 | Tool Interconnection Project (Main Tool & Module) | 353 | P | -01 | KPAE01 STREIMER EXHAUST LABOR PAY | 2023/8/2 2024/2/1 | 2023/8/11 2024/2/1 | -15546.8 | 60964.2 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | To adjust for actual completion of work |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 45417.4 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 45417.4 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C003 | USCSB2209006A | 45237.65 | F21P1 UPW | 1459 | C |  | MMF media procurement | 44813 | 44816 | [6 empty] | Northern Filter Media, Inc. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 44665.25 | 0.98735 | 572.4 | 0 | 572.4 | 0 | [20 empty] | 3538.35 |  |  | 41126.9 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2202008A | 45125 | F21P1 WWT package (Installation and 2 batch tanks) | 1333 | C |  | FRP Tank Color work | 44607 | 44615 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 25% upon all submittals approved-Net 30 Days; 20% upon receipt of materials-Net 30 Days; 50% upon ready to ship status; 5% upon commissioning & acceptance-within 60 days cap from shipping date or the product commission date, whichever is earlier-Net 30 Days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N |  |  | 45125 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 45125 | [17 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311001A | 45000 | Tool Interconnection Project (Main Tool & Module) | 476 | P |  | Install 45 power and 11 signals; cable pulls from l30 to l20, l20 to l20, and 8395 organization: WBS:Power-Power,Signal | 45231 | 45240 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 45000 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312075A | 45000 | Tool Interconnection Project (Main Tool & Module) | 618 | P |  | KPAP02-S INTERCONNECT LABOR | 45282 | 45287 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 45000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403056A | 45000 | Tool Interconnection Project (Main Tool & Other Vendors) | 879 | P |  | KPAN03-S Cable Pull Labor | 45364 | 45365 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 45000 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | Labor | USC21C009 | USCSB2303033A | 45000 | F21P1 WWT package (Installation and 2 batch tanks) | 1775 | C |  | Agitator Chemical Coating | 44993 | 44999 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 27000 |  |  | 0 |  |  |  | 18000 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312076A | 45000 | Tool Interconnection Project (Main Tool & Module) | 619 | P | -01 | KPAN02-S INTERCONNECT LABOR | 45282 | 2023/12/28 2024/1/4 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | R1: Remark Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 45000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2301002A | 44907.78 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1625 | C | -01 | Swagelok ASML Project | 44931 | 2023/1/9 2023/2/1 | 3166.46 | 41741.32 | v | v |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 44907.78 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 41906.33 |  |  |  | 0 | [6 empty] | 3001.45 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2406144A | 44781.12 | WWT B side Project | 4382 | C |  | WWT- Brahma T-740Bs FRP Interconnection, T-110Bs Additional Flange Coating | 45471 | 45476 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 43754.24 | 0.97707 | 1026.88 | 0 | 1026.88 | 0 | [70 empty] | 43754.24 | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | The budget execution does not pertain to this project | Chemical | Chemical | Mechanical | M+L | USC21C006 | USCSB2403258A | 44754 | F21P1 Slurry package | 3951 | C |  | TSMC UPW - 8-201 Remote Cabinet Drains (L20) | 45378 | 45449 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 42516 | 0.94999 | 2238 | 0 | 2238 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 42516 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C006 | USCSB2404010A | 44724 | WWT B side Project | 4006 | C |  | Harness and SRL for WWT x100 | 45384 | 45387 | [6 empty] | Palo Verde First Aid-Fire-Safety-Shredding | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 44724 | 0 | 44724 | 53668.8 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 6708.6 |  |  |  | 6708.6 |  |  |  | 6708.6 |  | 22362 |  | - | 13417.2 | 13417.2 | 4472.4 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2407101A | 44712.14 | WWT B side Project | 4516 | C |  | LB2 B 12 Added supports for punch and WRC lab | 45490 | 45493 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 44712.14 | 44712.14 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403201A | 44700 | F21P1-0404_H_labor for 50 tools_MICU | 3897 | C |  | Vinyl Mat for Hook-up team All Trades | 45371 | 45378 | [6 empty] | Xiang Sheng Hardware Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 44700 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 44700 | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310022A | 44482 | F21P1 Chemical & WCCS package | 2685 | C |  | Acrylic boards used in normal status and used for every each VMB of A/B side. | 45203 | 45206 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 44482 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 44482 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Civil | M+L | USC21C009 | USCSB2212032A | 44435 | F21P1 WWT package (Installation and 2 batch tanks) | 1604 | C |  | WRC WWT Stripper Side Foundation | 44912 | 44916 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 42196.05 | 0.94961 | 2238.95 | 0 | 2238.95 | 2109.8025 | [28 empty] | 42196.05 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 2109.8025
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2210039A | 44368.92 | F21P1 WWT package (Installation and 2 batch tanks) | 1521 | C |  | Tank blinding and davit arm weld | 44855 | 44867 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 44368.92 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 44368.92 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C004 | USCSB2210046A | 44343.4 | F21P1 WWT package （USA EQ-FRP tank) | 1528 | C |  | WRC Sump Pit Pump RT Fitting | 44860 | 44861 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 44343.4 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 44343.4 |  |  | 6651.51 |  |  |  | 6651.51 |  |  |  | 6651.51 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2212034A | 44320 | F21P1 UPW | 1606 | C |  | WRC C,7-D,8 UMEC Pipe Support | 44912 | 44916 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 42104 | 0.95 | 2216 | 2216 | 0 | 0 | [26 empty] | 42104 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403074A | 44220 | F21P1-0404_H_labor for 50 tools_MICU | 3778 | C |  | Mobile helium leak detector 100 to 230 V (± 10%) 50/60 Hz for HK PPL trade | 45358 | 45362 | [6 empty] | INFICON Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 44200 | 0.99955 | 20 | 0 | 20 | 0 | [52 empty] | 44200 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401158A | 44220 | F21P1-0404_H_labor for 50 tools_MICU | 3343 | C |  | Cable Tray clamp request for HK Power trade | 45311 | 45316 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 44220 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 39360 |  | 0 |  | 4860 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402012A | 44200 | F21P1-0404_H_labor for 50 tools_MICU | 3455 | C |  | Mobile helium leak detector for tool hookup team | 45323 | 45345 | [6 empty] | INFICON Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 44200 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  | 44200 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Helix | Main Contract Scope | WWT | WWT | Electrical | Labor | USC21C009 | USCSB2405065A | 44126 | F21P1 WWT package (Installation and 2 batch tanks) | 4085 | C |  | WWT A-Side Sand Blast Room Cable Pulling Requirement_20240509 | 45423 | 45425 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved | [14 empty] | 44126 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 44126 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2307011B | 44097.4 | Tool Interconnection Project (Main Tool & Module) | 346 | P |  | FORD TRANSIT-350 15 PASSENGER VAN | 45135 | 45175 | [6 empty] | One Stop Auto Mall LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 44097.4 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 44097.4 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Organo |  |  |  | Others |  |  | USC24C013 | USCSB2405158A | 44049 | Organo USA - UPW Electrical | 4186 | C |  | CIP Pump Change Scaffold | 45441 | 45443 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 44049 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 26429 | [7 empty] | 17620 | - |  |  | 0
Base-Build | Chemical | Labor | The budget execution does not pertain to this project | 0 | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USC2309038B | 44000 | F21P1 Chemical & WCCS package | 427 | P |  | Manpower Pay Qty, 1 Pipe Fitter | 45196 | 45358 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 44000 | 30812.28 | 13187.72 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Labor | USC24C006 | USCSB2408138A | 44000 | WWT B side Project | 4747 | C |  | WWT Flange repair - Belzona | 2024/8/29 2024/9/20 | 2024/9/13 2024/9/20 | [6 empty] | DCP Coatings, LLC | PR Approved | PO Approved | PO R1: Revised completion date and term 9 to non-warranty per vendor's request and confirmation with Thomas and Eugene. | [13 empty] | 0 | 0 | 44000 | 0 | 44000 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2307141A | 43660 | F21 TMAH System | 2303 | C |  | WWT Stripper-packing | 45136 | 45138 | [6 empty] | LICI PLASTIC INDUSTRY CO. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 43660 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 6549 |  |  | 0 | 0 | 0 | 0 |  | 0 | 37111 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2405027A | 43646.6 | F21P1-0404_H_Hallway plate install_MICU | 4037 | C |  | P1A additional foundations installation for KMVX81 and KMVIE1 | 45416 | 45426 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 43646.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 43646.6 | [8 empty] | - |  |  | 0
Base-Build | CCTV | Labor | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC23C045 | USCSB2309151A | 43200 | WWT Change Order (Piping) | 2622 | C |  | Provide the manpower only for installation of CCTV on the A side | 45192 | 45202 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 43200 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 43200 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401009A | 43184.2 | F21P1-0404_H_labor for 50 tools_MICU | 3200 | C |  | HK Carson Sales 11 invoices Oct and Nov | 45295 | 45297 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 43184.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 43184.2 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Barcode | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C012 | USC2201015A | 43061.4 | F21 Barcode RFID System | 109 | P |  | 19" rack cabinet | 44586 | 44617 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  | 1% 10th Prox, Net 15th Prox, Free Shipping-After Acceptance-Invoice Received | Yi En Wong |  |  | Hsiang Cheng Lee | Yi En Wong | N | [6 empty] | 43061.4 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 43061.4 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2408029A | 43003.56 | WWT B side Project | 4624 | C |  | Additional support for punch and emergency pumps_WWT | 45511 | 45541 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 43003.56 | 43003.56 | 0 | [74 empty] | -
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC24C016 | USCSB2408046A | 43000 | AMAT Mozart New Scope | 4637 | C |  | AMAT Mozart New Scope | 45513 | 45520 | [6 empty] | AUCAN INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 43000 | 43000 | 0 | [74 empty] | -
Base-Build | Slurry | Equipment | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2310070A | 42959.15 | F21P1 Slurry package | 2731 | C |  | USC21C006 SLURRY B SIDE VMB Production Engineering | 45211 | 45231 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 42959.15 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 42959.15 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C011 | USCSB2402231A | 42875 | F21 TMAH System | 3658 | C |  | install house keeping pads and Dike wall in Fab LB2/WRC | 45346 | 45350 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 41560 | 0.96933 | 1315 | 0 | 1315 | 3158.56 | [52 empty] | 0 | 0 | 39482 |  | 0 | [13 empty] | 2078 | 0 |  | - | 0 | 0 | 0 | 3158.56
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407126A | 42780.26 | TSMC Fab 21 P1B Tool Hook Up | 4540 | C |  | MAST LIFT 25FT DRIVABLE LCS BATT for HK | 45493 | 45499 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 5352.09 | 0.12511 | 37428.17 | 1531.43 | 35896.74 | 0 | [72 empty] | 1030.75 | 4321.34 |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310124A | 42620 | F21P1-0404_H_labor for 50 tools_MICU | 2784 | C |  | CED Clamps for Third | 45218 | 45239 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 42620 | 0 | 42620 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2408064A | 42590 | Tool Hookup Material (UPW&Chemical) | 4680 | C |  | TSMC UPW P1B additional materials_2nd_4 materials | 45518 | 45520 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 38054 | 0.8935 | 4536 | 2905 | 1631 | 0 | [72 empty] | 35149 | 2905
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408005A | 42546.14 | Tool Interconnection Project (Main Tool & Other Vendors) | 1177 | P |  | 2 MALL INS BUSH | 45507 | 45518 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 42546.14 | 35717.88 | 6828.26 | 0 | [73 empty] | -
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USC2109019A | 42455.71 | F21P1 WWT package （USA EQ-FRP tank) | 18 | P | -01 | WASTE Tank (Last 5 tanks) | 2021/9/29 2021/11/4 | 2021/10/6 2021/11/5 | 10875.14 | 53330.85 |  | V |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | 異動簽核中因為取消3個桶槽 | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | 2021/10/22 2021/11/16 11/9/2021 | Henry |  | N | 5000 |  | 0 | 0 | 42455.71 | 0 | 42455.71 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 6368.3565 |  |  |  | 6368.3565 |  |  |  | 6368.3565 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404097A | 42375 | Chemical & WCCS B Side Project | 4084 | C |  | 鐵管2" 90度彎曲加工 | 45393 | 45409 | [6 empty] | Chukar SB&F LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 42375 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 41019 |  | 1356 | 42375 | [5 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405024A | 42334.21 | Tool Interconnection Project (Main Tool & Other Vendors) | 1083 | P |  | KDSTSA - rework | 45419 | 45421 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 42334.21 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 42334.21 | [10 empty] | - |  |  | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2310024A | 42268.48 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2687 | C | -01 | Southwest Hand Tool_0828 requirement | 45203 | 2023/10/10 2023/10/13 | -16797.14 | 59065.62 |  |  |  |  | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | PO transaction due to pricing change (Zero out Qty for 1 item) |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 37220.66 | 0.88058 | 5047.82 | 480.56 | 4567.26 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 37220.66 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2306083A | 42242 | F21P1 UPW | 2116 | C |  | Crating and packing for pipes on site | 45097 | 45103 | [6 empty] | Crating Technology, INC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 42242 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 42242 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Barcode | Rosendin | The budget execution does not pertain to this project | UPW | UPW | Electrical | M+L | USC21C012 | USCSB2403200A | 42234.76 | F21 Barcode RFID System | 3896 | C |  | PCO 81, Revision 1: Repull One Fiber Optic Cable from CP1 to CP31 | 45371 | 45371 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 42234.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 42234.76 | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Electrical | Labor | USC24C005 | USCSB2404116A | 42220 | Chemical & WCCS B Side Project | 4101 | C |  | F21 B side L30 Tray安裝工程 | 45397 | 45419 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 40109 | 0.95 | 2111 | 0 | 2111 | 2111 | [54 empty] | 0 |  | 0 |  |  |  |  | 21110 | 33776 |  |  | 18999 |  |  |  |  | 6333 | 2111 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2308053A | 42180 | F21P1 Module Tool Interconnection DIF1-2 | 2351 | C |  | AMAT WIRE FOR POWER TRANSFORMER CONNECTION | 45147 | 45153 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 42180 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 42180 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2406090A | 42178.61 | WWT B side Project | 4325 | C |  | PR Harrington WWT - WRC Material Line Rework Chem Lines 203, 204, 103, 104(A side) | 45461 | 45464 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 42178.61 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 40765.51 |  | 1413.1 | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Greenberry | DCR Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2402005A | 42159 | F21P1 WWT package (Installation and 2 batch tanks) | 3448 | C |  | MIC-009-23 -Fabricate, paint & Install additional X Line to Tunnel supports | 45323 | 45328 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 40051.05 | 0.95 | 2107.95 | 0 | 2107.95 | 2002.5525 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 6323.85 | 40051.05 |  |  | 6323.85 |  |  |  | 6323.85 |  | 0 |  | - | 0 | 0 | 0 | 2002.5525
Interconnection | interconnection | Labor |  |  | Others |  |  | USC23C032 | USCSB2311142A | 42100.97 | F21_AZQR_Hookup_ Interconnection | 2992 | C |  | QR: KXPTR1, KXPTR2: INSTALL ELECTROPOLISHED STAINLESS STEEL (EP SS) & PFA TUBING TO SUPPORT GAS LINE INSTALL. | 11/30/2023 9/24/2024 | 12/11/2023 9/26/2024 | -195.34 | 42296.31 |  |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: Returning the rest of the funds back to the account. Close PO. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 42100.97 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 42100.97 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2405097A | 42082 | F21P1 AMAT Interconnection | 4128 | C |  | Scaffolding | 45428 | 45448 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 42082 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 28850 |  | 13232 |  |  | - |  |  | 0
Base-Build | Frontage Line Hydrant | Material |  |  | Water Line | Civil | M+L | USC22C018 | USCSB2209025A | 42000 | US Fab Frontage line hydrants | 1477 | C |  | TSMC 16" Water Line Re-Chlorination | 44827 | 44836 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-After Acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 42000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 42000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312074A | 42000 | Tool Interconnection Project (Main Tool & Module) | 617 | P |  | KPI401-S INTERCONNECT LABOR | 45282 | 45287 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 42000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 42000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308038A | 42000 | Tool Interconnection Project (Main Tool & Module) | 388 | P |  | KPI401-T ONSIGHTLIGHT LABOR | 45168 | 45191 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 42000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 42000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC22C001 | USCSB2308116A | 41938 | F21 P1 Office and WH Security and CCTV | 2413 | C | -01 | F21 P1 CCTV Engineering (San Tan Fire, LLC) | 2023/8/19 2023/12/12 | 2023/9/6 2023/12/29 | -158062 | 200000 | V |  |  |  | San Tan Fire, LLC | PR Approved | PO Approved | R1: As per Paul: This order is T&M, and there is no further manpower requirement. |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 41938 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 41938 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2407057A | 41930 | F21P1 AMAT Interconnection | 4475 | C |  | ATF-C/ KCUVA7 QC work, KCUVA1/ KCUVA2 Tube Work, KCUVA1/ KCUVA2 QC Work | 45484 | 45510 | [6 empty] | CT-TECH USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 41930 | 0 | 41930 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC24C006 | USCSB2403259A | 41840 | WWT B side Project | 3952 | C |  | WWT: TSMC Approved CO, Design Change to Relocate 18.5 line CuCMP and CWD line | 45378 | 45386 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 41840 | 0 | 41840 | 50208 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 6276 |  |  |  | 6276 |  |  |  | 6276 |  | 20920 |  | - | 12552 | 12552 | 4184 | 0
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2308109A | 41760 | F21P1 UPW | 2406 | C |  | Field Observation for FAB UPW | 45157 | 45180 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 41760 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 25056 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 16704 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Labor | DCR Scope | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C007 | USCSB2308110A | 41760 | F21P1 VOC package （Installation ) | 2407 | C |  | Field Observation for FAB VOC | 45157 | 45180 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 41760 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 41760 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2308023A | 41750 | Tool Interconnection Project (Main Tool & Module) | 373 | P | -01 | KPE602-S TRIDENT MECHANICAL - MATERIAL PAY | 2023/8/29 2024/1/29 | 2023/9/26 2024/1/29 | -935 | 42685 | V |  |  |  | Trident Mechanical Services | PR Approved | PO Approved | Final amount to be paid for completed work |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 41750 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 41750 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306012A | 41566.5 | Tool Interconnection Project (Main Tool & Module) | 297 | P |  | KPOCT5 LIT 3 FOR STREIMER- LABOR | 45083 | 45084 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11546.25 | 0.27778 | 30020.25 | 0 | 30020.25 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1385.55 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10160.7 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2404054A | 41554.75 | F21P1 AMAT Interconnection | 4048 | C |  | Bulk Power Cables | 45387 | 45391 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 41554.75 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 41554.75 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C012 | USCSB2409004A | 41530.89 | F21P1 Hot DI Machine Hookup | 4774 | C |  | REVISED VARTEAGA Invoice No. MICU-010 @ T^0M WORK_CDS L10_L20_L30 Cleanroom CPVC_SS_PFA Chemical System Tubes_ Batch 2/3 | 45539 | 45546 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 41530.89 | 41530.89 | 0 | 0 | [73 empty] | -
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C009 | USCSB2212046A | 41388.06 | F21P1 WWT package (Installation and 2 batch tanks) | 1617 | C |  | WWT- DCR-Sulfate analyzer | 44923 | 44943 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 41388.06 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  | 41388.06 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2403101A | 41280.2 | F21P1 AMAT Interconnection | 3803 | C |  | Power Cables | 2024/3/9 2024/3/16 | 45379 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved | PR R1:Adjusting the amount between quotation and the PR. |  | Yikang Wang |  |  |  | 0 | [7 empty] | 41268.93 | 0.99973 | 11.27 | 0 | 11.27 | 0 | [52 empty] | 0 | 6975.57 | 4384.25 |  | 2234.98 | [5 empty] | 27674.13 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2304034A | 41250 | F21P1 Module Tool Interconnection DIF1-2 | 1874 | C |  | T4A-0S-00500-049B0, 1/2" Valex Tube, EP .049 316L 401 10Ra | 45031 | 45037 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 41242.5 | 0.99982 | 7.5 | 0 | 7.5 | 0 | [32 empty] | 41242.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2311019A | 41120.78 | WWT Change Order (Piping) | 2874 | C |  | WWT-FRP-piping-T710AA | 45234 | 45241 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 41120.78 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 41120.78 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2212009A | 41110 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1582 | C |  | Mechanical Dock and Uni-chock | 44902 | 44909 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 41110 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 41110 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG | Labor |  |  | Others |  |  | USC22C003 | USCSB2306068A | 41040 | TSMC Fab21 Project Phase 1 EDG Package | 2101 | C |  | TSMC F21P1 (AZ) MICU-LSW CO Upgrade All Gens to Level 1 Emergency Service | 45093 | 45096 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | Back Charge to Customer Fu Energy with 8% Mark-up | 100% by progress-net 30 days-after acceptance | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 41040 | 1 | 0 | 4308 | -4308 | 0 | [33 empty] | 0 |  |  |  |  | 19500 |  | 0 | 0 | 2154 | 0 | 2154 | 0 | 2154 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2154 | [5 empty] | 2154 | [8 empty] | 0 | 6462 | 4308 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2405003A | 40860 | Tool Interconnection Project (Main Tool & Other Vendors) | 1061 | P |  | 鐵氟龍軟管(1/4"） 6.35*4.35 (透)-DAIKlN | 45415 | 45421 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved | [14 empty] | 40860 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 40860 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C009 | USCSB2312156A | 40825.4 | F21P1 WWT package (Installation and 2 batch tanks) | 3145 | C |  | WWT-Chemical H2SO4/HCl | 45281 | 45286 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 12795.88 | 0.31343 | 28029.52 | 0 | 28029.52 | 5337.728 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 6123.81 |  |  |  | 6123.81 | 6279.68 |  | 6516.2 | 6123.81 |  | 0 |  | - | 0 | 5337.728 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Steel | Labor | USC21C009 | USCSB2402073A | 40824 | F21P1 WWT package (Installation and 2 batch tanks) | 3515 | C |  | WWT Add Litho Drain Pipe Supports | 2024/2/8 2024/8/21 | 2024/2/21 2024/8/21 | -17496 | 58320 | V |  |  | V | Mirador Construction Service, LLC | PR Approved | PO Approved | PR R1: As per Jim to revise the PO amount to $40,824 for close out. |  | Ta Wei Wang | [11 empty] | 0 | 0 | 40824 | 40824 | 0 | 58320 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8748 |  |  |  | 8748 |  |  |  | 8748 |  | 14580 |  | - | 14580 | 14580 | 14580 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USC2408007A | 40800 | TSMC Fab 21 P1B Tool Hook Up | 1176 | P |  | Swagelok M200 Orbital Welding System Training | 45511 | 45518 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 40800 | 0 | 40800 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404109A | 40737.6 | Chemical & WCCS B Side Project | 4094 | C |  | 2吋SUSBA 3280 ft購買 | 45397 | 45401 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 40737.6 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 40737.6 |  |  | 40737.6 | [5 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403055A | 40711 | Tool Interconnection Project (Main Tool & Other Vendors) | 878 | P |  | KPAN03-S PVDF 3/4" Piping Labor | 45364 | 45365 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 40711 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 40711 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2311091A | 40341.23 | F21P1 Chemical & WCCS package | 2942 | C |  | CDS L10 cleanroom SS chemical tubes | 45248 | 45253 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 40341.23 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 40341.23 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2203002A | 40194.97 | F21P1 Chemical & WCCS package | 1337 | C |  | CO2 Bottle Racks | 44621 | 44637 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  | 20% upon received material and approved submittal-Net 45 days; 60% due on delivery with evidence-Net 45 days; 20% by received and after acceptance-Net 45 days | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | N | [6 empty] | 40194.96 | 1 | 0.01 | 0 | 0.01 | 0 | [7 empty] | 8038.99 |  |  | 24116.98 |  | 8038.99 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405008A | 40084.8 | Tool Interconnection Project (Main Tool & Other Vendors) | 1067 | P |  | KDMRS4-DNS SCREEN INTERCONNECTS-3/27-4/2/2024 | 45416 | 45420 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 40083.8 | 0.99998 | 1 | 0 | 1 | 0 | [56 empty] | 0 | [5 empty] | 40083.8 | [10 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401199A | 40084 | F21P1 Chemical & WCCS package | 3384 | C |  | CDS 1-1/4 Over Tube and Coax Elbow 90 | 45316 | 45316 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 40084 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 40084 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401016A | 40000 | F21P1-0404_H_labor for 50 tools_MICU | 3207 | C |  | HK Da Yi Chen Equipment Rental for 3 months | 45295 | 45310 | [6 empty] | DA YI CHENG Technology Co., Ltd. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 40000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 40000 |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Base-Build | Labor |  |  | Base-Build |  |  | USC23C002 | USC2309044B | 40000 | F21P1-0404_H_Hallway plate install_MICU | 434 | P |  | Manpower Pay for 7 General Labor, 1 fork lift, and 2 carpenters | 45196 | 45355 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | Contract changed from Hua Yi to RS Payroll |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 40000 | 65997.62 | -25997.62 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2203008A | 39900 | F21P1 WWT package (Installation and 2 batch tanks) | 1343 | C |  | Lorry Box | 44635 | 44637 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  | 20% upon received material and approved submittal-Net 45 days; 60% due on delivery with evidence-Net 45 days; 20% by received and after acceptance-Net 45 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N |  |  | 39900 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 7980 |  | 31920 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2304037A | 39892.89 | F21P1 WWT package (Installation and 2 batch tanks) | 1877 | C |  | WWT Lab Funiture | 45033 | 45033 | [6 empty] | LabTech Supply Company Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 39892.89 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 7978.58 |  | 31914.31 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407143A | 39806 | TSMC Fab 21 P1B Tool Hook Up | 4554 | C |  | Cord grip for HK power trade for 80 tools | 45497 | 45499 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 39806 | 39806 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical Lab | Material | The budget execution does not pertain to this project | Chemical Lab | Chemical | Electrical | Labor | USC22C021 | USCSB2309032A | 39611.26 | F21P1 Chemical Lab setup | 2509 | C |  | GC Lab Electrical | 45177 | 45217 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 39611.26 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 39611.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C034 | USCSB2211035A | 39600 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/N2/APK/UPK/ASRS | 1568 | C |  | TSMC F21P1 FAB and HPM AMHS Infrastructure GEX and PV Hook-up | 44889 | 44894 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 33720 | 0.85152 | 5880 | 0 | 5880 | 0 | [26 empty] | 33720 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2211037A | 39537.5 | F21P1 WWT package (Installation and 2 batch tanks) | 1570 | C |  | PP Material | 44895 | 44897 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 39537.5 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 39537.5 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310001A | 39480 | Tool Interconnection Project (Main Tool & Module) | 435 | P |  | labor for 8395 cable routing rework | 45202 | 45230 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 32200 | 0.8156 | 7280 | 0 | 7280 | 0 | [40 empty] | 0 | 0 | 32200 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404014A | 39282 | Tool Interconnection Project (Main Tool & Other Vendors) | 969 | P |  | KPE605-S Cable Support Labor | 45385 | 45386 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 39282 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 39282 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Water | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2311076A | 39200 | F21P1 WWT package (Installation and 2 batch tanks) | 2930 | C |  | FAB 1A UPW, WWT CA Suppport (Electrical) | 45246 | 45251 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5407.5 | 0.13795 | 33792.5 | 0 | 33792.5 | 4583.8 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 1610 | 0 | 0 |  | 1075 |  | 460 |  |  | 5880 | 2185 |  |  | 5880 |  |  | 77.5 | 5880 |  | 0 |  | - | 4583.8 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2407084A | 39080.38 | WWT B side Project | 4500 | C |  | LB2 B 24 Added supports for punch_WWT | 45489 | 45505 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 39080.38 | 0 | 39080.38 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2305111A | 39040.44 | F21P1 WWT package （USA EQ-FRP tank) | 2028 | C |  | WWT T196AA | 45072 | 45079 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 39040.44 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 39040.44 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC21C005 | USCSB2312152A | 39031.2 | F21P1 Chemical & WCCS package | 3141 | C |  | CDS Day Tank Vent Labor | 45281 | 45282 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 29273.4 | 0.75 | 9757.8 | 0 | 9757.8 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 29273.4 |  | 0 | [12 empty] | 9757.8 |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C001 | USCSB2305028A | 39000 | TEL Main Tool Interconnection | 1951 | C |  | Electrical cable routing labor | 45052 | 45078 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 39000 | 0 | 39000 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2403106A | 38953 | F21P1-0404_H_Hallway plate install_MICU | 3808 | C |  | PCI AWT-A-01~07 foundations rework | 45362 | 45365 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 38952.97 | 1 | 0.03 | 0 | 0.03 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 38952.97 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Helix | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC24C006 | USCSB2405094A | 38923 | WWT B side Project | 4114 | C |  | WWT B Side Battery Panel Rigging and Installation | 45428 | 45433 | [6 empty] | Helix Electric, Inc. | PR Approved | PO Approved | [14 empty] | 38923 | 1 | 0 | 38923 | -38923 | 0 | [56 empty] | 0 | [14 empty] | 0 |  | 38923 | 0 | 0 | 0 | 0
Base-Build | Base-Build | MMI | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2310162A | 38885 | WWT Change Order (Piping) | 2816 | C |  | stripper pad duct rework (3areas) | 45224 | 45232 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 38885 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 38885 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC |  |  |  | Low Voltage | Mechanical | Material | USC22C013 | USCSB2407135A | 38874 | F21P1 QR Lab Security & CCTV | 4548 | C |  | F21 P1 VOC duct material | 45496 | 45502 | [6 empty] | Ducts, Inc. | PR Approved | PO Approved | [14 empty] | 38874 | 1 | 0 | 0 | 0 | 38874 | [70 empty] | 13000 |  | 25874 | - | 38874 |  | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2312017A | 38869.5 | F21P1-0404_H_labor for 50 tools_MICU | 3011 | C |  | Tool Hook Up warehouse supplies | 45265 | 45266 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 38869.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 38869.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404060A | 38826.88 | Tool Interconnection Project (Main Tool & Other Vendors) | 1013 | P |  | KCOXN3 Pull and route cables, install core hole sleeves/Tray dividers. | 45394 | 45399 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 38826.88 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 38826.88 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Penetration Pipe | Material | Main Contract Scope | WWT | WWT | Civil | Labor | USC22C020 | USCSB2209031A | 38750 | F21P1 Penetration Pipe | 1483 | C |  | Core Drill and Grouting with Rebar | 44834 | 44847 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 38750 | 1 | 0 | 0 | 0 | 1840.625 | [22 empty] | 33950 | [5 empty] | 0 |  |  |  | 2862.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 1937.5 | - | 0 | 0 | 0 | 1840.625
[5 empty] | Others |  |  | USC23C055 | USCSB2410041A | 38660 | F21P1-0404_H_labor for 50 tools_MICU | 4984 | C |  | HK_HuengLuei Equipment Rental_1st PO_End date 12/31/2023 | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 38660 | 0 | 38660 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2409041A | 38654.87 | WWT B side Project | 4826 | C |  | WWT - WRC Clarifier Platform Compliance Modification | 45545 | 45546 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 38654.87 | 0 | 38654.87 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2303011A | 38613 | F21P1 Module Tool Interconnection ETC1-3 | 1753 | C |  | F21P1 ETC pumping and gas line | 44987 | 45005 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 38613 | 0 | 38613 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2406053A | 38592 | F21P1 Module Tool Interconnection ETC1-3 | 4286 | C |  | Delta Wye Manpower to install and label DAQ cables | 45450 | 45456 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 38592 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 38592 | [6 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2309099A | 38566.9 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2572 | C |  | Banner Industries Welding Equipment Pre Fab Construction | 45185 | 45196 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 38566.9 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3924.9 | 15220 | 19422 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Steel | M+L | USC23C045 | USCSB2310181A | 38500 | WWT Change Order (Piping) | 2833 | C |  | Provide and install rocking 8 feet tall 42 inch wideth 30 feet long | 45227 | 45246 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 38500 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 38500 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2404172A | 38491.25 | F21P1 WWT package (Installation and 2 batch tanks) | 4153 | C |  | WWT blower GIP&SUS material | 45405 | 45406 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 38476.62 | 0.99962 | 14.63 | 0 | 14.63 | 8637.4926 | [54 empty] | 0 |  | 0 |  |  |  |  | 5773.6875 | 25404.39 |  |  | 5773.6875 |  |  | 13072.23 | 5773.6875 |  | 5080.878 |  | - | 3556.6146 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311075A | 38400 | F21P1-0404_H_labor for 50 tools_MICU | 2929 | C |  | Tool Hook Up ManPower- 6 general workers | 45246 | 45251 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 38400 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 38400 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | 0 | 0 | UPW | Steel | Labor | USC23C002 | USC2309037A | 38400 | F21P1-0404_H_Hallway plate install_MICU | 425 | P |  | Manpower Pay for General Labor for Kate Wu | 45195 | 45216 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 38400 | 0 | 38400 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2304015A | 38334 | F21P1 WWT package (Installation and 2 batch tanks) | 1856 | C |  | WWT Center rings extra for A+B (total) | 45023 | 45035 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 38333.4 | 0.99998 | 0.6 | 0 | 0.6 | 0 | [32 empty] | 11500.11 | 0 |  |  |  | 26833.29 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2210036A | 38265.86 | F21P1 WWT package (Installation and 2 batch tanks) | 1519 | C |  | PVC SCH80 Pipes-Litho Fab GF/RHFS | 44854 | 44855 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 38265.86 | 0 | 38265.86 | 38265.86 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 5739.879 |  |  |  | 5739.879 |  |  |  | 5739.879 |  | 9566.465 |  | - | 9566.465 | 9566.465 | 9566.465 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404083A | 38234.64 | Tool Interconnection Project (Main Tool & Other Vendors) | 1037 | P |  | SP-S835015SS 1-1/2 PVC FEM ADAPTER SOCXSSFPT SCH 3-5 DAYS ARO; 75 X $290.933 | 45406 | 45408 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 38234.64 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 37624.01 | [5 empty] | 610.63 |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404088A | 38000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1041 | P |  | KEBCT3 Internal Connect hook up. | 45406 | 45406 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 38000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 38000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406038A | 37947.91 | Tool Interconnection Project (Main Tool & Other Vendors) | 1143 | P |  | Manpower pay for Tool: KDSTSA for Brahma Work Performed- ITT rework on 5/2, 5/3, 5/8, 5/14, 5/14, 5/16/2024 | 45472 | 45476 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 37947.91 | 0 | 37947.91 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406005A | 37947.91 | Tool Interconnection Project (Main Tool & Other Vendors) | 1125 | P |  | KDSTSA - rework (change order)-DNS SCREEN INTERCONNECTS-5/2-5/16/2024. | 45450 | 45458 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 37947.91 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 37947.91 | [6 empty] | - |  |  | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C031 | USCSB2211029A | 37847.64 | CAP_E_F21P1 AMHS MML Seismic Foundation | 1562 | C |  | APK & UPK Iron Plates | 44887 | 44897 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 37847.64 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 20817 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 17030.64 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2310116A | 37700 | F21P1 Chemical & WCCS package | 2777 | C |  | CDS Eyeball Lorry Thinner Pressure Test | 45218 | 45224 | [6 empty] | Eyeball Precision Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 37700 | 0 | 37700 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2303087A | 37536 | F21P1 Chemical & WCCS package | 1824 | C |  | CDS system Added BOX Items | 45009 | 45028 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 37536 | 0 | 37536 | 37536 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 37536
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310165A | 37500 | F21P1-0404_H_labor for 50 tools_MICU | 2819 | C |  | QC Labels Yaho. shared by different trades | 45224 | 45225 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 37500 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 34200 | 0 |  | 3300 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2305056A | 37455.11 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1979 | C |  | KPAP01-S LIT 1 STREIMERS | 2023/5/12 2024/9/9 | 2023/7/21 2024/9/17 | -29238.09 | 66693.2 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PO R1: Case Closed -- adjust the PO amount to reflect the actual total |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 37455.11 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 37455.11 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2407088A | 37436.5 | F21P1 WWT package (Installation and 2 batch tanks) | 4504 | C |  | CGS Global Support Onsite Manpower | 45489 | 45503 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 37436.5 | 0 | 37436.5 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312087A | 37200 | F21P1-0404_H_labor for 50 tools_MICU | 3079 | C |  | Tube clamp, | 45274 | 45275 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 37200 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 28200 | 9000 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Southland | DCR Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2205016A | 37158.01 | F21P1 Chemical & WCCS package | 1379 | C |  | WCCS additional material for LB1 & LB2 | 44694 | 44697 | [6 empty] | Southland Industries | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 37158 | 1 | 0.01 | 0 | 0.01 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 37158 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403134A | 37140 | Tool Interconnection Project (Main Tool & Other Vendors) | 949 | P |  | U1AT750-062 TUBING-CUT STOCK 451 HPJ 3/4IN | 45380 | 45383 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 37140 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 37140 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401085A | 37086.24 | F21P1-0404_H_labor for 50 tools_MICU | 3274 | C |  | labels and ribbons for Brady M610 label printer for HK power trade QAQC | 45303 | 45307 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 36978.95 | 0.99711 | 107.29 | 0 | 107.29 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 36978.95 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C014 | USCSB2306011A | 37066.92 | F21P1 WH2SO4 | 2045 | C |  | WRC Material temp use + [CO] Sluge expansion Hopper out | 45080 | 45089 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 32171.04 | 0.86792 | 4895.88 | 0 | 4895.88 | 4182.2352 | [33 empty] | 0 |  |  | 13757.7 |  |  |  | 0 | 0 | 0 | 18413.34 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1112.0076 |  |  |  | 1112.0076 |  |  |  | 1112.0076 |  | 1608.552 |  | - | 1608.552 | 965.1312 | 0 | 0
Base-Build | WWT | CCE | Main Contract Scope | WWT | WWT | Electrical | M+L | USC21C009 | USCSB2206012A | 37047.6 | F21P1 WWT package (Installation and 2 batch tanks) | 1402 | C |  | X1 cable tray hanger re-install | 44722 | 44725 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 37047.6 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 37047.6 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C063 | USCSB2402229A | 36968.83 | F21P1-0423_H_T&M Hardware_MICU | 3656 | C | -01 | Portable Handheld VOC Monitor | 45345 | 3/11/2024 3/14/2024 | [6 empty] | FASTENAL COMPANY | PR Approved | PO Approved | R1: Correct Payment Term |  | Yikang Wang | [11 empty] | 36968.83 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 18478 | 0 | 0 | 0 |  | 0 |  | 18490.83 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Heating Jacket | Labor |  |  | Others |  |  | USC22C014 | USCSB2403155A | 36799.98 | F21P1 AMHS Power Panel | 3854 | C |  | Yaho support for Heating Jacket(01/26/2024~04/30/2024) | 45366 | 45369 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 36799.98 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 13799.98 |  | 0 | [5 empty] | 23000 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC24C008 | USCSB2405060A | 36569.82 | UPW B Side Project | 4064 | C |  | Train 2 Materials from ORGANO | 45421 | 45422 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 36569.82 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 36569.82 | [8 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307013A | 36534 | Tool Interconnection Project (Main Tool & Module) | 348 | P |  | KPAN01-T UMEC LABOR PAY | 45136 | 45140 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36534 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 23464.05 |  |  | 0 | 0 | 0 | 0 |  | 13069.95 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C001 | USC2306014A | 36534 | TEL Main Tool Interconnection | 299 | P |  | KPOCT5 LIT 3 UMEC-LABOR | 45083 | 45091 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36534 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 34854.33 |  |  | 0 | 0 | 0 | 0 |  | 1679.67 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308010A | 36534 | Tool Interconnection Project (Main Tool & Module) | 360 | P |  | KPOCT3 UNIVERSITY MECHANICAL & ENGINEERING CONTRACTORS LABOR PAY | 45141 | 45153 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36534 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 36534 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C032 | USCSB2404175A | 36481.28 | F21_AZQR_Hookup_ Interconnection | 4156 | C |  | QR LAB: KXPTR1 & KXPTR2: C/O TUBING REWORK FOR GAS INSTALL | 45405 | 45412 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 36481.28 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 36481.28 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2408143A | 36475 | WWT B side Project | 4751 | C |  | PR BMWC WWT - CCR CO-1 | 45534 | 45542 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 36475 | 0 | 36475 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306013A | 36400 | Tool Interconnection Project (Main Tool & Module) | 298 | P |  | KPOCT5 LIT3 HUA YI CONSTRUCTION-LABOR | 45083 | 45091 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 34580 | 0.95 | 1820 | 0 | 1820 | 0 | [33 empty] | 0 | [6 empty] | 34580 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C001 | USCSB2305020A | 36400 | TEL Main Tool Interconnection | 1943 | C |  | KPOCT3 LIT 3 Hua Yi | 45051 | 45055 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36400 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 34580 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 1820 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2308011A | 36400 | Tool Interconnection Project (Main Tool & Module) | 361 | P |  | KPOCT3-S LIT 3 hua Ti Construction | 45141 | 45149 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 36400 | 0 | 36400 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405056A | 36379 | Chemical & WCCS B Side Project | 4061 | C |  | CHEM_WCCS _Consumable hardware A_QT04357379-1 | 45421 | 45422 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 36379 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [8 empty] | 36379 | 36379 | [6 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2408001A | 36254 | F21P1 Module Tool Interconnection CVD | 4600 | C |  | O3 Double Containment | 45505 | 45513 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | [14 empty] | 36254 | 1 | 0 | 36254 | -36254 | [74 empty] | 36254
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2312048A | 36096.83 | F21P1 WWT package (Installation and 2 batch tanks) | 3041 | C |  | WWT-FRP-piping-T780AA | 45268 | 45271 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 36096.83 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 36096.83 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC23C015 | USCSB2405046A | 36050.08 | F21P1 AMHS Wiring Work Outline | 4053 | C |  | 12,000 Feet 1 AWG 1/C PSP Cable | 45420 | 45422 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 36050.08 | 1 | 0 | 36050.08 | -36050.08 | 0 | [56 empty] | 0 | [16 empty] | 36050.08 |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404089A | 36000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1042 | P |  | KDSET1 Internal Connect hook up | 45406 | 45406 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 36000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 36000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409029A | 35765.5 | TSMC Fab 21 P1B Tool Hook Up | 4796 | C |  | 500 Thick Waffle Covers for HK safety | 2024/9/6 2024/9/17 | 2024/9/16 2024/9/17 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | PO R1: Incorrect ship-to address | [13 empty] | 0 | 0 | 35765.5 | 0 | 35765.5 | 0 | [73 empty] | -
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC21C009 | USCSB2405103A | 35730.22 | F21P1 WWT package (Installation and 2 batch tanks) | 4121 | C |  | WWT A side Heat Exchanger Insulation | 45429 | 45433 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved | [14 empty] | 35730.22 | 1 | 0 | 0 | 0 | 42876.264 | [56 empty] | 0 | [14 empty] | 17865.11 | 35730.22 | - | 10719.066 | 10719.066 | 3573.022 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C007 | USCSB2306015A | 35689.15 | F21P1 VOC package （Installation ) | 2049 | C |  | TIG 3rd party inspections | 45083 | 45089 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 35689.15 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 35689.15 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC24C006 | USCSB2406089A | 35680.03 | WWT B side Project | 4324 | C |  | WWT B Side Instrument Batch 2 | 45458 | 45463 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 35680.03 | 0 | 35680.03 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2310052A | 35606.74 | F21P1-0404_H_labor for 50 tools_MICU | 2712 | C |  | field labor | 45209 | 45222 | [6 empty] | IMCOR - Interstate Mechanical | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 35606.74 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 35606.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C001 | USCSB2309056A | 35552.29 | TEL Main Tool Interconnection | 2532 | C |  | KPI401-T STREIMERS | 2023/9/12 2024/9/17 | 2023/9/27 2024/9/17 | -8785.31 | 44337.6 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PR R1: Case Closed -- adjust the PO amount to reflect the actual total |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 35552.29 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 35552.29 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C034 | USCSB2401182A | 35480 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/N2/APK/UPK/ASRS | 3367 | C |  | FAB-1A Post IFP Owner Revisions | 45340 | 45342 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 35480 | 0 | 35480 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311038A | 35460 | F21P1-0404_H_labor for 50 tools_MICU | 2893 | C |  | Pan Lug terminal for Third. Tool id KDIGA3 KECOT1 KETRT7 KKDB03 KPOV04 KKDB04 KKSV02 | 45238 | 45244 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 35460 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 19643 | 1197 |  |  | 0 | 0 | 0 |  | 14620 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2402144A | 35190 | F21P1-0423_H_T&M Hardware_MICU | 3577 | C |  | MMI Tile alignment RMF bolts. T&M Hardware for Hank | 45337 | 45350 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 35190 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 35190 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | DCR Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C013 | USCSB2404153A | 35004 | F21P1 AMC THC Monitoring System | 4137 | C | -01 | F21 P1 WRC Building Flow meters & Temp installation engineering of stack | 45402 | 2024/5/1 2024/5/4 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved | R1: Discount applies to Item 005 instead of 002 | [13 empty] | 35004 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [15 empty] | 35004 | - |  | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Material | USC24C005 | USCSB2407116A | 34994.9 | Chemical & WCCS B Side Project | 4531 | C |  | F21P1 Bside WCCS-SUS Spare & Combine Valve | 45492 | 45507 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 34994.9 | 0 | 34994.9 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2310044A | 34978 | WWT Change Order (Piping) | 2705 | C |  | WWT -BMWC -X123(WWT Tunnel Trestle scope - Change order for continuing priority lines) | 45206 | 45216 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 34978 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 33229.1 | 0 | 0 | 0 |  |  | 1748.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Electrical | Material | USC24C006 | USCSB2407041A | 34977.25 | WWT B side Project | 4440 | C |  | A site punch | 45482 | 2024/7/12 2024/7/15 | -734.4 | 35711.65 |  |  |  |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Supplier offer better price after negotiation | [13 empty] | 0 | 0 | 34977.25 | 34977.25 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2212005A | 34810 | F21P1 WWT package (Installation and 2 batch tanks) | 1578 | C |  | Alliance - trucking cost 910AA/AB TANKS | 44896 | 44900 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 34810 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 34810 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403086A | 34789.81 | F21P1 WWT package (Installation and 2 batch tanks) | 3789 | C |  | WWT Bolt Sets_Copper State(B side) | 45359 | 45362 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 34789.81 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 22970.77 |  | 0 |  |  |  | 11819.04 | 5218.4715 |  |  |  | 5218.4715 |  |  |  | 5218.4715 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2212045A | 34760 | F21P1 Chemical & WCCS package | 1616 | C |  | F21P1 MIC foot fixed steel | 44918 | 44924 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 0 | 0 | 34760 | 0 | 34760 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | M+L | USC21C003 | USCSB2311134A | 34700 | F21P1 UPW | 2984 | C |  | UPW-ladder lock | 45259 | 45261 | [6 empty] | Scenic Industries, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 34700 | 0 | 34700 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402033A | 34669.29 | Tool Interconnection Project (Main Tool & Other Vendors) | 757 | P |  | KETRTB L30-L20 cable drop, L20-L10 cable drop, routing cables and 8395 | 45328 | 45330 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 34669.29 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 34669.29 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2312078A | 34626 | F21P1 Chemical & WCCS package | 3070 | C |  | CDS DHL Upper level walking steps for A side two catwalks | 45273 | 45274 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 34626 | 1 | 0 | 0 | 0 | 3376.04 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 31249.96 | 0 | 0 |  | 0 | [5 empty] | 3376.04 | [8 empty] | 0 |  | - | 0 | 0 | 3376.04
[5 empty] | Others |  |  | USC24C006 | USCSB2410031A | 34611 | WWT B side Project | 4974 | C |  | WWT LSR Heat Exchanger insulation | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 34611 | 0 | 34611 | 0
Base-Build | CCTV | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC22C001 | USCSB2310104A | 34525 | F21 P1 Office and WH Security and CCTV | 2766 | C |  | F21 Warehouse CCTV Engineering | 45216 | 45217 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 34525 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 34525 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401018A | 34510 | Tool Interconnection Project (Main Tool & Other Vendors) | 642 | P |  | KPOCT1 Labor | 45302 | 45311 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 34510 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 34510 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409087A | 34418 | TSMC Fab 21 P1B Tool Hook Up | 4899 | C |  | Safety PPE, Tool hookup team | 45556 | 45560 | [6 empty] | Diversified Products USA | PR Approved | PO Approved | [14 empty] | 0 | 0 | 34418 | 0 | 34418 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2309068A | 34398 | WWT Change Order (Piping) | 2542 | C |  | WWT -BMWC mobilization and support | 45182 | 45196 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 34398 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 32678.1 | 0 | 0 | 0 |  |  | 1719.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | Labor | USC23C045 | USCSB2403272A | 34293 | WWT Change Order (Piping) | 3965 | C |  | WWT: HPM L10/L20 Rack Fabrication and Installation | 45379 | 45380 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 34293 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 5143.95 | 10478 |  |  | 5143.95 | 23815 |  |  | 5143.95 |  | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2407050A | 34292.54 | F21P1 AMHS Wiring Work Outline | 4449 | C |  | 7 YCF AMHS Engineers support Muratec from 6/10/24~12/10/24 | 2024/7/10 2024/9/27 | 2024/7/27 2024/9/30 | 15392.54 | 18900 | V |  |  |  | YUNG CHENG FENG ENGINEERING CO.,LTD. | PR Approved | PO Approved | R1: Adjust price and terms due to DBA compliance requirements | [13 empty] | 0 | 0 | 34292.54 | 0 | 34292.54 | 0 | [73 empty] | - |  |  | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C031 | USCSB2407033A | 34286.4 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4432 | C |  | Opening 10 B Side STKs | 45482 | 45486 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 34286 | 0.99999 | 0.4 | 0 | 0.4 | 0 | [70 empty] | 34286 |  |  | - |  |  | 0
Base-Build | Base-Build | Equipment | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C008 | USCSB2210052A | 34272 | F21P1 CCTV & Security | 1534 | C |  | Radio Rental | 44862 | 44867 | [6 empty] | Code Red Safety & Rental, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 32009.13 | 0.93397 | 2262.87 | 0 | 2262.87 | 0 | [23 empty] | 3424.92 | 2856 |  | 2856 |  | 2856 |  | 2880.21 |  | 2856 | 0 | 2856 |  |  | 2856 | 5712 |  | 0 | 2856 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404064A | 34257.6 | WWT B side Project | 4056 | C |  | WWT PVC Glue & Primer | 45388 | 45391 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 34257.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 34257.6 |  |  | 5138.64 |  |  |  | 5138.64 |  |  |  | 5138.64 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2309061A | 34116.24 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2536 | C |  | Border States Electrical Work Material PreFab Area | 45182 | 45196 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 34116.24 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 34116.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C007 | USCSB2403091A | 34098 | F21P1 VOC package （Installation ) | 3793 | C |  | VOC System K-type wire and temperature controller | 45360 | 45363 | [6 empty] | Desiccant Technology Corporation | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 34098 | 1 | 0 | 0 | 0 | 24550.56 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 9648 |  |  | 32394 |  |  |  |  | 24450 | 24550.56 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2310020A | 34009 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2683 | C |  | Yih Jiun Hand Tool_0828 requirement | 45203 | 45205 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 34009 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 34009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404090A | 34000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1043 | P |  | KDMRS4 Internal Connect hook up. | 45406 | 45406 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 34000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 34000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404082A | 34000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1036 | P |  | KDMRS3 Internal Connect hook up. | 45406 | 45407 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 34000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 34000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405089A | 33975 | Chemical & WCCS B Side Project | 4109 | C |  | CHEM_WCCS _Unistrut | 45427 | 45427 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 33975 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [8 empty] | 33975 |  |  | 33975 |  |  |  |  | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401090A | 33942.12 | F21P1 Chemical & WCCS package | 3279 | C |  | CDS ASRS Leakage detector | 45304 | 45306 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 33942.12 | 1 | 0 | 0 | 0 | 33942.12 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 33942.12 | 0 |  | - | 0 | 0 | 33942.12
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401011A | 33900 | F21P1-0404_H_labor for 50 tools_MICU | 3202 | C |  | HK Huengluei Equipment Rental for 3 months | 45295 | [8 empty] | PR Approved | PO Processing |  |  | 0 | [11 empty] | 0 | 0 | 33900 | 0 | 33900 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401099A | 33868.8 | Tool Interconnection Project (Main Tool & Other Vendors) | 716 | P |  | KPE603-S Labor | 45321 | 45324 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 33868.8 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 33868.8 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2307084A | 33789 | F21P1 UPW | 2250 | C |  | 8-97 MA-174 Additional Scope L20 to L30 Added Valves | 45127 | 45140 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 33789 | 0 | 33789 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 30410.1 |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407023A | 33621.98 | Tool Interconnection Project (Main Tool & Other Vendors) | 1159 | P |  | Labor for Electrical cable pull for tool ID# KDFAD1 | 45492 | 45495 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved | [14 empty] | 33621.98 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 33621.98 |  |  |  |  | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2303023A | 33476 | F21P1 Chemical & WCCS package | 1765 | C |  | 8-400A breakers in UIS' panels for CDS and SDS PPBs. | 44988 | 45001 | [6 empty] | LayerZero Power Systems, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [5 empty] | Y |  | 33476 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 33476 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408009A | 33432.41 | Tool Interconnection Project (Main Tool & Other Vendors) | 1180 | P |  | 10" SUS304 Dust 1.2M | 45513 | 45524 | -43953.1 | 77385.51 |  |  |  | V | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | PO R1: Per request, place order only for Quote MICU-07-11-099 | [13 empty] | 0 | 0 | 33432.41 | 0 | 33432.41 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409020A | 33402 | Tool Interconnection Project (Main Tool & Other Vendors) | 1223 | P |  | KPAN03-T: LUMP SUM REWORK SCOPE | 45546 | 45549 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 33402 | 33402 | 0 | 0 | [73 empty] | -
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C047 | USCSB2306063A | 33374 | F21P1 HK Seismic Installation | 2097 | C |  | QR Lab cutting tiles | 45092 | 45125 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 33374 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 33374 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408111A | 33292.33 | TSMC Fab 21 P1B Tool Hook Up | 4725 | C |  | Hand tools for HK Power trade Third for 297 tools | 45528 | 45538 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | [14 empty] | 0 | 0 | 33292.33 | 30504.33 | 2788 | 0 | [73 empty] | -
Base-Build | Barcode | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C012 | USC2111028A | 33250 | F21 Barcode RFID System | 42 | P |  | alarm,wall-mounted | 44516 | 44551 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | Cherry Chang |  |  | Hsiang Cheng Lee | Cherry Chang | N | 44565 | Martin |  | N | 5000 |  | 33250 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 33250 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2305063A | 33102 | F21P1-0404_H_Hallway plate install_MICU | 1985 | C |  | 27 single barricades | 45059 | 45069 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 33102 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 33102 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309139A | 33000 | F21P1 Chemical & WCCS package | 2610 | C | -01 | 90 deg Coax elbows (Spare parts). | 45191 | 2023/10/3 2023/10/10 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | PO R1:Change in Net Terms |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 33000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 5280 | 23760 | 3960 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2309100A | 33000 | F21P1 WWT package (Installation and 2 batch tanks) | 2573 | C |  | Mini-Line Certificate(batch 1/2) | 45185 | 45191 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8250 | 0.25 | 24750 | 0 | 24750 | 0 | [40 empty] | 0 | 0 | 0 | 8250 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | CO Scope (adding/additional scope) | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2309102A | 33000 | F21P1 UPW | 2574 | C |  | Mini-Line Certificate(batch 2/2) | 45185 | 45191 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 33000 | 0 | 33000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2409055A | 32975.97 | F21P1 AMHS Power Panel | 4851 | C |  | TSMC Added Cables for 3 DPs_AMHS | 45549 | 45553 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 32975.97 | 0 | 32975.97 | 0 | [73 empty] | -
Base-Build | Base-Build | Other Scope |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C058 | USCSB2310187A | 32813.63 | F21 EUV Steel Plates | 2839 | C |  | MIC EUV Crane Temp Power Final Removal | 45227 | 45238 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 32813.63 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 32813.63 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C006 | USCSB2311094A | 32775.86 | F21P1 Slurry package | 2945 | C |  | Southwest Fastener Monthly Order for Chemical Team 11/2023~01/2024 | 45250 | 45337 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 31213.36 | 0.95233 | 1562.5 | 0 | 1562.5 | 0 | [49 empty] | 0 | 31213.36 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1562.5 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408023A | 32760 | Tool Interconnection Project (Main Tool & Other Vendors) | 1188 | P |  | 3 CABLE PULL LEAD FOR 1 MONTH | 45520 | 45525 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 32760 | 15632.56 | 17127.44 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2403050A | 32705.6 | WWT Change Order (Piping) | 3757 | C |  | WWT SUS SCH40 Pipes_20240305 (A Side) | 45357 | 45358 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 32705.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 32705.6 |  | 0 |  |  |  |  | 4905.84 |  |  |  | 4905.84 |  |  |  | 4905.84 |  | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC | EDG |  |  |  | Others |  |  | USC22C003 | USCSB2407137A | 32647 | TSMC Fab21 Project Phase 1 EDG Package | 4550 | C |  | TSMC Diesel Pump Power Circuit Relocate | 45497 | 45498 | [6 empty] | D.P. Electric, Inc. | PR Approved | PO Approved | [14 empty] | 32647 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 32647 | - |  |  | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2404148A | 32584 | F21P1 UPW | 4132 | C |  | UPW-UMEC-COs for CE148 and 157 | 45401 | 45405 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 28256 | 0.86717 | 4328 | 0 | 4328 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 28256 | 32584 | [9 empty] | 0 |  | - | 0 | 0 | 0
Others | EUV Steel Plate | Equipment |  |  | Others |  |  | USC23C058 | USCSB2312147A | 32510 | F21 EUV Steel Plates | 3136 | C |  | DP-213/221/223/B06 Door kits | 45280 | 45281 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 32510 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 32510 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Electrical | M+L | USC21C007 | USCSB2207012A | 32497.3 | F21P1 VOC package （Installation ) | 1427 | C |  | VOC Cable Tray Change Order #2 | 44751 | 44755 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 32497.3 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 32497.3 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Equipment | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USCSB2204006A | 32427 | F21P1 Slurry package | 1355 | C |  | Slurry system panels | 44665 | 44666 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved | 原PO:USC2112003A異動為0 | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 32427 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 16213.5 | [10 empty] | 12970.8 |  |  | 3242.7 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2305030A | 32388 | F21P1 UPW | 1953 | C |  | UPW CO-PVDF0025 clash | 45056 | 45057 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 32388 | 0 | 32388 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Triazole | Material | Main Contract Scope | WWT | WWT | Civil | M+L | USC22C022 | USCSB2306099A | 32381 | F21P1 Triazole treatment system | 2132 | C |  | WWT Triazole pads | 45098 | 45124 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 30981 | 0.95676 | 1400 | 0 | 1400 | 1239.24 | [33 empty] | 0 |  |  |  |  | 30981 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 1239.24
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2312149A | 32359.45 | F21P1 Chemical & WCCS package | 3138 | C |  | CDS pressure test materials | 45280 | 45282 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 32262.55 | 0.99701 | 96.9 | 0 | 96.9 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 32262.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401183A | 32069.58 | F21P1-0404_H_labor for 50 tools_MICU | 3368 | C |  | MOBILE BAR AND PIPE RACK, 18 for Gas, 10 for Plastic and 2 for UPW | 45314 | 45315 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 32040.06 | 0.99908 | 29.52 | 0 | 29.52 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 32040.06 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2404025A | 32064.57 | F21P1 Module Tool Interconnection LIT2-3 | 4021 | C |  | Lit 3: KPPTT1, KPPTT2, & KPPTT2 Exhaust Hard Duct CIP Material | 45385 | 45392 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 32064.57 | 32064.57 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403022A | 32055 | Tool Interconnection Project (Main Tool & Other Vendors) | 848 | P |  | KPCD01: CABLE PULL | 45358 | 45364 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 32055 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 32055 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Triazole | Scaffolding | Main Contract Scope | WWT | WWT | Civil | M+L | USC22C022 | USCSB2307065A | 32051 | F21P1 Triazole treatment system | 2232 | C |  | TSMC WRC Pump Pads(WWT Triazole epoxy) | 45122 | 45183 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 32051 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 32051 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2305002A | 31941.1 | F21P1 WWT package (Installation and 2 batch tanks) | 1926 | C |  | WWT material for drain & system | 45048 | 45058 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31941.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 25784.8 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 638.822 |  |  | 6156.3 | 958.233 |  |  |  | 1597.055 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Water | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2310138A | 31920.87 | F21P1 WWT package (Installation and 2 batch tanks) | 2796 | C |  | 10/21/23 to 11/20/23 Southwest Fastener Monthly Order for Water Team | 45220 | 45300 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31920.87 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 31920.87 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403138A | 31904.41 | Tool Interconnection Project (Main Tool & Other Vendors) | 953 | P |  | KDSTS2 Mechanical work | 45380 | 45384 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 31904.41 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 31904.41 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2309124A | 31864 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2595 | C |  | Genesis Technology Cabling Install OFC Office Build | 45190 | 45202 | [6 empty] | Genesis Technology (USA) Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 31864 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 4779.6 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 27084.4 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USC2111051A | 31860 | F21P1 Chemical & WCCS package | 52 | P |  | Ball Valve | 44523 | 44588 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | CF (Trade term check)) | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh | FOB -- ship 4 weeks after receipt of order and we would invoice at that time |  | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 31860 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 31860 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | M+L | USC21C003 | USCSB2308010A | 31839.45 | F21P1 UPW | 2313 | C | -01 | UPW HP1037 & HP1137 Additional DS(TSMC F21P1 UPW Electrical and Controls) | 45140 | 2023/8/11 2023/9/19 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | R1:T & C dispute |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 28655.51 | 0.9 | 3183.94 | 0 | 3183.94 | 31839.44 | [40 empty] | 0 | 0 | 0 | 0 | 15919.73 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 12735.78 | [8 empty] | 15919.72 |  | - | 0 | 15919.72 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC21C005 | USCSB2312007A | 31800 | F21P1 Chemical & WCCS package | 3002 | C |  | CDS expansion joint F1 lorry | 45261 | 45273 | [6 empty] | HONGDONG INTERNATIONAL CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 31800 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 31800 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403139A | 31732 | Tool Interconnection Project (Main Tool & Other Vendors) | 954 | P |  | Manpoer Pay for Delta Wye for Tool ID: KETRTA ETC 3 | 45381 | 45385 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 31732 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 31732 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307015A | 31710.63 | Tool Interconnection Project (Main Tool & Module) | 350 | P | -01 | KPE601-T STREIMERS LABOR PAY | 2023/7/29 2024/2/1 | 2023/8/15 2024/2/1 | -34795.77 | 66506.4 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | To adjust for actual completion of work |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31710.63 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 31710.63 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404004A | 31687.42 | Tool Interconnection Project (Main Tool & Other Vendors) | 959 | P |  | KEPSL1-LAM INETRCONNECTS 3/5-3/26/2024 | 45384 | 45385 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 31687.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 31687.42 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402112A | 31582.96 | F21P1 Chemical & WCCS package | 3550 | C |  | CDS Materials for CRG | 45335 | 45335 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 19413.05 | 0.61467 | 12169.91 | 0 | 12169.91 | 0 | [49 empty] | 0 |  |  | 0 | 14843.05 | 4570 |  | 0 |  |  |  |  | 12169.91 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2401071A | 31552 | F21P1 UPW | 3260 | C |  | UPW-ORGANO-ACM-C-added PVDF | 45303 | 45307 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31552 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 31552 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311009A | 31388.9 | F21P1-0404_H_labor for 50 tools_MICU | 2864 | C |  | Flexible Type UL approval, UA/LA style, Gray jacket color steel coore material | 45232 | 45244 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31388.9 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 31388.9 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2202011A | 31200 | F21P1 WWT package (Installation and 2 batch tanks) | 1335 | C |  | Modular pipe support assembly design (Tunnel section) | 44617 | 44623 | [6 empty] | The Blackfin Group | PR Approved | PO Approved |  | 25% at kickoff-net 30 days-after acceptance; 75% submission of draft report-net 30 days-after acceptance; T&M billed on a monthly basis (with supporting timesheets) | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT |  |  |  | Y |  |  | 31200 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 7800 |  | 23400 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C059 | USCSB2404170A | 31192.78 | F21P1 Foundation T&M | 4151 | C |  | 3 in 1 project for HK Power system | 45405 | 45406 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 31192.78 | 1 | 0 | 30426.98 | -30426.98 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 765.8 |  |  | 0 |  | 30426.98 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C019 | USCSB2404028A | 31175 | F21P1 Hitachi Interconnection | 4024 | C |  | ME: KPCD03, KPCD13, KPCD17-19: CABLE PULLS | 45385 | 45387 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 31175 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 31175 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C008 | USCSB2112001A | 31129 | F21P1 CCTV & Security | 1313 | C |  | tsmc security 4th floor | 44531 | 44539 | [6 empty] | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Hsiang Cheng Lee | York Yeh | N |  | Martin |  | N |  |  | 31129 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 31129 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2307035A | 31004 | F21P1 UPW | 2205 | C |  | TSMC UPW Package-CO-Add | 45118 | 45132 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 31004 | 0 | 31004 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402100A | 31000 | Tool Interconnection Project (Main Tool & Other Vendors) | 814 | P |  | KPE601-S and KPE602-S Labor: H2/AR_VENT_S-gland Damage modifications | 45346 | 45348 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 31000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 31000 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C007 | USCSB2307132A | 30916 | F21P1 Module Tool Interconnection PVD1-2 | 2294 | C |  | Di Max pipe threading | 45135 | 45141 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4978 | 0.16102 | 25938 | 0 | 25938 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 497.8 | 0 | 1991.2 |  | 0 | [5 empty] | 2489 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310022A | 30843 | Tool Interconnection Project (Main Tool & Module) | 451 | P |  | Labor | 45211 | 45308 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 30843 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 30843 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2307089A | 30843 | F21P1 UPW | 2255 | C |  | 8-112 Sight Glass Reinforcement | 45127 | 45142 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 30843 | 0 | 30843 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 12337 |  |  |  | 15421 |  |  |  | 27758.7 |  | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2403279A | 30817.02 | F21P1 AMAT Interconnection | 3972 | C |  | powercable | 45380 | 45380 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 30816.97 | 1 | 0.05 | -1001.15 | 1001.2 | 0 | [52 empty] | 0 | 0 | 0 |  | 29527.82 |  | 1289.15 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USC2112005A | 30764 | F21P1 UPW | 73 | P |  | SDI analyzer | 44533 | 44539 | [6 empty] | MABAT Chemical systems Ltd | PR Approved | PO Approved |  | 100% before shipping | York Yeh | DAP | 12 months from startup, or 18 months from delivery (whichever is earliest). | Chia-Yi Chang | York Yeh | N | 44546 | Matt |  | N | 5000 |  | 30764 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 30764 | [23 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Labor | USC22C009 | USCSB2403232A | 30720 | F21P1 230kV MTR Oil and Drain Pipe work | 3925 | C |  | UPW DC Bank Panel to Panel Termination & Cable Pull | 45373 | 45378 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 30720 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 30720 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404212A | 30690 | WWT B side Project | 3963 | C |  | WWT PVC Glue & Primer_20240429 | 45411 | 45412 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 30690 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 2788.25 |  | 27901.75 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2404145A | 30652.8 | F21P1 AMAT Interconnection | 3942 | C |  | Borrowed San Tan labor 3/11/24 - 4/12/24 | 45400 | 45423 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 30652.8 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 30652.8 | [10 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310010A | 30618 | F21P1-0404_H_labor for 50 tools_MICU | 2673 | C |  | Bulkhead union | 45202 | 45206 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8570.71 | 0.27992 | 22047.29 | 0 | 22047.29 | 0 | [40 empty] | 0 | 0 | 2447.01 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 6123.7 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2210009A | 30498.48 | F21P1 UPW | 1493 | C |  | UPW A Side Disconnect Switch Stands Change Order | 44839 | 44852 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A-01 Change Order (Disconnect Switch Stand) | 95% by progress-Net 30 days-After acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 30498.48 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 9607.02 |  | 9607.02 |  | 9607.02 |  | 1677.42 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2205030A | 30450 | F21P1 Chemical & WCCS package | 1392 | C |  | Lorry Building Rack Design | 44709 | 44712 | [6 empty] | The Blackfin Group | PR Approved | PO Approved |  | 25% at kickoff-net 30 days-after acceptance; 75% after acceptance of submission-net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 30450 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 7612.5 |  |  | 22837.5 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405176A | 30281.9 | WWT B side Project | 4204 | C |  | WWT Ball Valves Purchase(A & B side) | 45442 | 45449 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 30281.9 | 0 | 30281.9 | 36338.28 | [71 empty] | 15140.95 |  | - | 9084.57 | 9084.57 | 3028.19 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409083A | 30153.96 | TSMC Fab 21 P1B Tool Hook Up | 4895 | C |  | Flexible Conduit for HK power tool base 45 | 45556 | 45558 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 30153.96 | 0 | 30153.96 | 0 | [73 empty] | -
Base-Build | AMC THC | Southland | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | Material | USC21C007 | USCSB2307130A | 30080 | F21P1 VOC package （Installation ) | 2292 | C |  | 5222329-059- THC Scope_Added Material | 45135 | 45140 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 30080 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 9277 | 0 | 0 | 0 | 5609 | 0 | 0 | 15194 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2209005A | 30000 | F21P1 WWT package (Installation and 2 batch tanks) | 1458 | C |  | MRT Design-Additional Services amendment | 44813 | 44816 | [6 empty] | MRT DESIGN LLC | PR Approved | PO Approved | 原都以APN請款，因財務要求而轉開PO | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 27500 | 0.91667 | 2500 | 0 | 2500 | 0 | [16 empty] | 15000 |  | 12500 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404081A | 30000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1035 | P |  | KDMRS2 Internal Connect hook up | 45406 | 45407 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 30000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 30000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C005 | USCSB2310057A | 30000 | F21P1 Chemical & WCCS package | 2717 | C |  | FAB B Chemical/ UPW Permitting(batch1/2) | 45210 | 45216 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 30000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 30000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2404062A | 29967.24 | F21P1-0404_H_labor for 50 tools_MICU | 4054 | C | -01 | Wire for HK power trade | 2024/4/6 2024/4/13 | 2024/4/10 2024/04/23 |  |  |  | V | V |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Previous item 2 not available and replaced by item 1 |  | Lisa Chan | [11 empty] | 29967.24 | 1 | 0 | 29967.24 | -29967.24 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 29967.24 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403261A | 29967.24 | F21P1-0404_H_labor for 50 tools_MICU | 3954 | C | -01 | Cable for HK Power trade | 2024/3/27 2024/4/23 | 2024/4/11 2024/4/23 |  |  |  | V |  |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Previous item 2 not available |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 29967.24 | 0 | 29967.24 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2308004A | 29946 | F21P1 Chemical & WCCS package | 2308 | C |  | Support for CCB Filling Port (tsmc F21P1 Materials) | 45139 | 45148 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 29946 | 0 | 29946 | 29946 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 29946
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Labor | USC24C005 | USCSB2407142A | 29740.47 | Chemical & WCCS B Side Project | 4553 | C |  | CHEM_Addition project for B side DHL's walking path | 45497 | 45500 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29740.47 | 0 | 29740.47 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401012A | 29600 | F21P1-0404_H_labor for 50 tools_MICU | 3203 | C |  | HK Laien Parts Equipment Rental for 3 months | 45449 | 45449 | [6 empty] | Laien Parts Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 29600 | 0 | 29600 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2302056A | 29552.21 | F21P1 Chemical & WCCS package | 1737 | C |  | PP&M EST 8501 MIC NE Replacement Tube | 44985 | 44993 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 26883.57 | 0.9097 | 2668.64 | 0 | 2668.64 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 26883.57 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 2659.7 | [5 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2405163A | 29510 | F21P1-0404_H_Hallway plate install_MICU | 4191 | C |  | Hilti bolts for foundation works in P1B. | 45441 | 45446 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29510 | 0 | 29510 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2306102A | 29504 | F21P1 Chemical & WCCS package | 2135 | C |  | TSMC F21 PDP Panel Breaker Change | 45099 | 45114 | [6 empty] | OEG ISG - Integrated Systems Group | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 29504 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 29504 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2310074A | 29376 | F21P1 Chemical & WCCS package | 2735 | C | -01 | CDS Platform 3 Raised Grating | 45211 | 2023/10/19 2023/10/31 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | R1: Quotation No. Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 29376 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10000 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 29376 |  |  |  |  | 19376 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2406124A | 29353.4 | WWT B side Project | 4363 | C |  | F21 A Side Lorry Expansion Joint | 45468 | 45474 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29353.4 | 0 | 29353.4 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | CCTV | Equipment | The budget execution does not pertain to this project | 0 | Low Voltage | Electrical | Material | USC21C008 | USCSB2206020A | 29328 | F21P1 CCTV & Security | 1409 | C |  | GOWN Power Panel | 44729 | 44740 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 29328 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 23755.68 | 0 |  | 5572.32 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG | MIMO/Rigging |  |  | Others |  |  | USC22C003 | USCSB2308144A | 29261 | TSMC Fab21 Project Phase 1 EDG Package | 2439 | C |  | ATS Polisher Change Location | 45162 | 45163 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 27771 | 0.94908 | 1490 | 1490 | 0 | 0 | [40 empty] | 0 | 0 | 27771 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C001 | USCSB2305021A | 29227.2 | TEL Main Tool Interconnection | 1944 | C |  | KPOCT3 LIT 3 UMEC | 45051 | 45055 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 29227 | 0.99999 | 0.2 | 0 | 0.2 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 29227 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406017A | 29214 | Tool Interconnection Project (Main Tool & Other Vendors) | 1137 | P |  | KPAE02-S Exhaust Installation | 45465 | 45471 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29214 | 0 | 29214 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2401222A | 29212.94 | F21P1-0404_H_labor for 50 tools_MICU | 3404 | C |  | RS Labor for Tool Hookup: October- December | 45317 | 45320 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 29212.94 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 29212.94 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C001 | USCSB2302018A | 29200 | TEL Main Tool Interconnection | 1699 | C |  | Camera and access control for Surprise warehouse | 44965 | 44984 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 29200 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 4380 | 0 |  |  |  | 24820 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2401047A | 29188.16 | F21P1 Module Tool Interconnection CMP1 | 3237 | C |  | CMP: MKS-2 & MKS-3: INSTALL PVC & PFA TUBING TO NEWLY INSTALLED LAB EQUIP. TOOLS & INSTALL GEX. | 2024/1/9 2024/8/5 | 2024/1/19 2024/8/5 | -11950.1 | 41138.26 | V |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: Returned remaining funds as the invoice was smaller than the quote. Revised to actual invoices. |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 29188.16 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 9262.65 |  | 0 | 0 | 0 |  | 0 |  |  |  | 19925.51 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C001 | USCSB2305023A | 29187.07 | TEL Main Tool Interconnection | 1946 | C |  | KPOCT3 LIT 3 Streimers | 2023/5/5 2024/9/9 | 2023/10/17 2024/9/17 | -4627.83 | 33814.9 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PO R1: Case Closed -- adjust the PO amount to reflect the actual total |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 29187.07 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 29187.07 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407014A | 29170 | Tool Interconnection Project (Main Tool & Other Vendors) | 1152 | P |  | KPAE02-S Cable Routing Labor | 45486 | 45490 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29170 | 0 | 29170 | 0 | [73 empty] | - |  |  | 0
Base-Build | CCTV | Labor | The budget execution does not pertain to this project | 0 | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC22C001 | USCSB2306074A | 29150 | F21 P1 Office and WH Security and CCTV | 2107 | C |  | PD Sensor Installation and Transformer Testing | 45093 | 45104 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 29150 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 3500 |  |  |  | 25650 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Hot DI | UMEC | 0 | 0 | Chemical | Mechanical | M+L | USC23C012 | USCSB2306108A | 29119 | F21P1 Hot DI Machine Hookup | 2141 | C | -01 | Hot DI piping | 45100 | 2023/7/6 2023/7/20 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | R1:To include WO scope into signed Contract |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27663 | 0.95 | 1456 | 0 | 1456 | 1455.95 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 27663 | [10 empty] | 0 |  | - | 0 | 0 | 1455.95
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408049A | 29103 | Tool Interconnection Project (Main Tool & Other Vendors) | 1197 | P |  | Rework aquired for KKDB02, cables are running through popout that is in direct conflict with another tools foundation | 45525 | 45526 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29103 | 29103 | 0 | 0 | [73 empty] | -
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406056A | 28986.5 | Chemical & WCCS B Side Project | 4289 | C |  | F21P1 Marketech QUO8338 WCCS.SDS B-Side Labels | 45451 | 45454 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 28986.5 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 28986.5 | [6 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311054A | 28976.95 | Tool Interconnection Project (Main Tool & Module) | 526 | P |  | Cooling water material. CW Pipe, CW Valves, Cushion Clamps | 45248 | 45258 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 28976.95 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 28864.81 |  |  | 0 | 112.14 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404079A | 28868.8 | Chemical & WCCS B Side Project | 4069 | C |  | PVDF料補齊.1 20240408 | 45391 | 45392 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Sian-Ning Pei | [11 empty] | 28868.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 28868.8 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405009A | 28833.72 | Tool Interconnection Project (Main Tool & Other Vendors) | 1068 | P |  | KDMRS3-DNS SCREEN INTERCONNECTS 3/21, 3/27-3/28, 4/15-2024 | 45416 | 45421 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 28833.72 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 28833.72 | [10 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409088A | 28805 | TSMC Fab 21 P1B Tool Hook Up | 4900 | C |  | Safety PPE, Tool hookup team | 45556 | 45560 | [6 empty] | Diversified Products USA | PR Approved | PO Approved | [14 empty] | 0 | 0 | 28805 | 0 | 28805 | 0 | [73 empty] | -
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC23C045 | USCSB2310071A | 28785 | WWT Change Order (Piping) | 2732 | C |  | WWT FAB/WWT centralizer | 45211 | 45224 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 28785 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 28785 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2305001A | 28724.82 | Tool Hookup Material (UPW&Chemical) | 1925 | C |  | EBO UPW DP Parts | 45048 | 45143 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 28724.81 | 1 | 0.01 | 0 | 0.01 | 0 | [33 empty] | 0 |  |  |  | 2624.84 |  |  | 24111.01 | 0 | 1988.96 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C027 | USCSB2410016A | 28552.26 | CAP_E_F21P1 Autoshelf Installation 4 set | 4960 | C |  | Additional Material needs for P1B AMHS 1/3,6/3,8/3,10/3 wire_ 1/3 batch | 45567 | [7 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 28552.26 | 0 | 28552.26 | 0
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Material | USC24C005 | USCSB2407013A | 28521 | Chemical & WCCS B Side Project | 4414 | C |  | F21P1 HPM CDU/DHL CDA/GN2 | 45475 | 45479 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 28521 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 28521 | [6 empty] | - |  |  | 0
Others | 光阻櫃 | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC22C012 | USCSB2307067A | 28500 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 2234 | C |  | P1A Mask Room Proposal – Side A utility Piping Scaffolding | 45122 | 45125 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 28500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 28500 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405131A | 28265.23 | Tool Interconnection Project (Main Tool & Other Vendors) | 1108 | P |  | LABOR & MATERIAL FOR GALVANIZED DUCT/ELBOWS FOR BLOWER BOX IN LB1.INSTALLATION OF H-BAR IN L10 FOR KDFAD1 | 45432 | 45435 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | [14 empty] | 28265.23 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 28265.23 | [12 empty] | - |  |  | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2306084A | 28251 | F21P1 Chemical & WCCS package | 2117 | C |  | 1000 Series Pump Support Base | 45097 | 45125 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25044.75 | 0.88651 | 3206.25 | 0 | 3206.25 | 0 | [33 empty] | 0 |  |  | 19273.5 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 2565 | 0 | 0 |  | 0 | [8 empty] | 6412.5 |  |  |  |  | 3206.25 | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405115A | 28236.06 | Chemical & WCCS B Side Project | 4144 | C |  | CHEM_B side L20/ L30_R-TEE _GN2 | 45433 | 45435 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 28236.06 | 0 | 28236.06 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403091A | 28234.54 | Tool Interconnection Project (Main Tool & Other Vendors) | 907 | P |  | TEL INTERCONNECTS-KDSET1 2/27-3/15/2024 | 45372 | 45377 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 28234.54 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 28234.54 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401170A | 28147.3 | F21P1-0404_H_labor for 50 tools_MICU | 3355 | C |  | Cord grip for power trade | 45314 | 45314 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 26860.6 | 0.95429 | 1286.7 | 0 | 1286.7 | 0 | 26860.6 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2301064A | 28050 | F21P1 Module Tool Interconnection CVD | 1680 | C |  | AMAT Olympia glass fiber insulation | 44957 | 44980 | [6 empty] | Astro Thermal Technology Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 28050 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 28050 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2307041A | 28028 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2210 | C |  | AMHS Hole Framing and Cover Removal (AMHS VC L20 Steel Plate Removal) | 45118 | 45127 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 28028 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 7007 |  | 0 | 0 | 4204.2 | 0 |  | 0 | 0 | 0 | 11211.2 | 0 |  |  | 0 | 0 | 5605.6 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C001 | USCSB2304039A | 28000 | TEL Main Tool Interconnection | 1879 | C |  | Cable ties | 45033 | 45033 | [6 empty] | Kai Suh Suh Enterprise Co., LTD. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 28000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 14000 |  | 14000 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312064A | 27991.24 | Tool Interconnection Project (Main Tool & Module) | 610 | P |  | Pay for San Tan for Tools KEBCT1, KEBCT2, KEPST1, KEPST2 | 45279 | 45290 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27991.24 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 27991.24 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C001 | USCSB2301053A | 27957.8 | TEL Main Tool Interconnection | 1670 | C |  | KLA interconnect flex hose and duct | 44953 | 44964 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27957.8 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 27957.8 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC21C009 | USCSB2409032A | 27906.25 | F21P1 WWT package (Installation and 2 batch tanks) | 4799 | C |  | WWT - Brahma A-Side Carboline Flange Coating CO-1 | 45541 | 45547 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 27906.25 | 0 | 27906.25 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406006A | 27842.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1126 | P |  | KEPST4-TEL INTERCONNECTS-5/1-5/3/2024 | 45450 | 45458 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 27842.6 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 27842.6 | [6 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406036A | 27842.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1142 | P |  | Man-Power Pay Install Finish (Change Order)-2+ days no work waiting on permits. 5/1, 5/2, and 5/3/2024 | 45472 | 45476 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 27842.6 | 0 | 27842.6 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403103A | 27790.98 | Tool Interconnection Project (Main Tool & Other Vendors) | 919 | P |  | DNS SCREEN INTERCONNECTS-KRWRS5-3/8-313/2024 | 45374 | 45377 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 27790.98 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 27790.98 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407130A | 27627.47 | WWT B side Project | 4544 | C |  | WWT Termination Fitting for chem lines and missing material for SL2 | 45496 | 45497 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 27627.47 | 0 | 27627.47 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2306095A | 27616 | F21 TMAH System | 2128 | C |  | WWT-T665AA relocation | 45098 | 45126 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 27616 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 13808 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 13808 |  | 0 | [8 empty] | 2761.6 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2308014A | 27595 | F21P1 Module Tool Interconnection CVD | 2316 | C |  | Modify, orbital weld and install existing spools. Fabricate, orbital weld, and install new spools for KCANN1 and KCANN2 | 45141 | 45141 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27595 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 27595 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309114A | 27588 | F21P1 Chemical & WCCS package | 2586 | C |  | 90 deg Coax elbows for Chemical team and Harder | 45188 | 45204 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27588 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 27588 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV |  | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC24C007 | USCSB2405122A | 27500 | Low Voltage B Side Project | 4150 | C |  | F21P1 Gown Office Security PFA area Security & CCTV | 45434 | 45436 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 24750 | 0.9 | 2750 | 0 | 2750 | 26125 | [70 empty] | 24750 | 13750 |  | - | 12375 |  | 0
Base-Build | Hot DI | Equipment | 0 | 0 | Chemical | Mechanical | Material | USC23C012 | USCSB2302050A | 27484.71 | F21P1 Hot DI Machine Hookup | 1731 | C | -01 | Hot DI BOX make | 2/25/2023 2024/5/8 | 3/17/2023 2024/5/15 | 4995.55 | 22489.16 |  |  |  |  | FusionHPX LLC | PR Approved | PO Approved | R2: As per engineer TJ to update the quote. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 27484.71 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 27484.71 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406023A | 27420 | Chemical & WCCS B Side Project | 4249 | C |  | TCELC-F21P1 CDS support 追加 quotation | 45447 | 45449 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 27420 | 0 | 27420 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | Labor | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2403183A | 27215.03 | F21P1 Chemical & WCCS package | 3880 | C |  | prep and epoxy housekepping pads in Fab LB1,L10 and L20 37 PADS TOTAL | 45370 | 45372 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 27215.03 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 27215.03 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2406011A | 27214.5 | Chemical & WCCS B Side Project | 4237 | C |  | F21P1 CED Y-Conduit | 45444 | 45447 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 8592.1 | 0.31572 | 18622.4 | 27214.5 | -8592.1 | 0 | [73 empty] | 8592.1 |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303012A | 27164.13 | F21P1 WWT package (Installation and 2 batch tanks) | 1754 | C |  | 20" stub end | 44987 | 45005 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 27164.13 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 14879.49 | 0 | 12284.64 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2311098A | 27061 | F21P1 WWT package (Installation and 2 batch tanks) | 2949 | C |  | WWT Heat Exchanger Additional Support | 45251 | 45252 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 27061 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 25707.95 | 0 |  |  | 1353.05 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Steel | Material | USC24C005 | USCSB2407043A | 26940 | Chemical & WCCS B Side Project | 4442 | C |  | CHEM_WCCS SUS project_ for CDS/ SDS VMB supports | 45482 | 45483 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved | [14 empty] | 26940 | 1 | 0 | 26940 | -26940 | 0 | [73 empty] | 26940 |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2211023A | 26884.38 | F21P1 WWT package (Installation and 2 batch tanks) | 1557 | C |  | WWT welding machines rentals from Harrington | 44883 | 44886 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 25162.11 | 0.93594 | 1722.27 | 0 | 1722.27 | 1509.7266 | [28 empty] | 0 |  | 11754.45 |  | 4469.22 | 3060.25 | 4469.22 | 1408.97 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 537.6876 |  | 0 |  | - | 0 | 0 | 0 | 1509.7266
Base-Build | Base-Build | Equipment | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2205007A | 26856.34 | F21P1 UPW | 168 | P |  | 2022 Polaris Pro XD Crew Diesel Com 21, Model D22P4ED4B4 Construction site #2 Polaris | 44709 | 44719 | [6 empty] | Iron City Polaris | PR Approved | PO Approved |  | 100% T/T 0 day (no deposit, all should be paid before delivery) | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 26856.34 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 26856.34 | [18 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2309088A | 26733 | F21P1 Chemical & WCCS package | 2561 | C |  | Load cell work at Mixing boxes/tanks | 45184 | 45192 | [6 empty] | Michelli Measurement Group, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 26733 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 26733 |  |  | 26733 | [9 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307083A | 26620 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2249 | C |  | Airgas USA | 45126 | 45142 | [6 empty] | Airgas USA, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19809.38 | 0.74415 | 6810.62 | 0 | 6810.62 | 0 | [38 empty] | 3602.76 | 2753.2 | 111.75 | 2347.2 | 0 | 0 | 1349.9 | 3713.21 | 372 | 0 | 285 | 0 | 3321.5 |  | 156.15 | 0 | 0 |  | 1272.86 |  | 408.26 | [9 empty] | 115.59 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical Lab | MMI | The budget execution does not pertain to this project | Chemical Lab | Chemical | Mechanical | M+L | USC22C021 | USCSB2307023A | 26560 | F21P1 Chemical Lab setup | 2195 | C |  | GC Lab Anchor and Materials | 45113 | 45127 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 26560 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 6640 |  | 3623 | 0 | 0 | 0 |  | 0 | 8148.5 | 0 | 8148.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC21C012 | USCSB2405018A | 26549.6 | F21 Barcode RFID System | 3990 | C |  | F21 P1 parking gates installation-(5/11) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 26549.6 | 0 | 26549.6 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310119A | 26474.24 | F21P1-0404_H_labor for 50 tools_MICU | 2779 | C |  | Grainger September monthly order. shared material | 45218 | 45225 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 24741.8 | 0.93456 | 1732.44 | 0 | 1732.44 | 0 | [42 empty] | 24741.8 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2301063A | 26380 | F21P1 Module Tool Interconnection CVD | 1679 | C |  | ASM tool interconnect semic | 44957 | 44964 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 26380 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 26380 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2309051A | 26304.18 | F21P1 Chemical & WCCS package | 2527 | C |  | Lasair III 110 Particle Counter and HPD II-150 High Pressure Diffuser | 45181 | 45192 | [6 empty] | Particle Measuring Systems, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 26304.18 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26304.18 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401195A | 26302.38 | F21P1-0404_H_labor for 50 tools_MICU | 3380 | C |  | Locknut for hk power trade | 45315 | 45316 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 26302.38 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 26302.38 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409002A | 26259 | Tool Interconnection Project (Main Tool & Other Vendors) | 1209 | P |  | KPE606-S: CW PIPING REWORK CLASHES: L30 | 45539 | 45547 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 26259 | 26259 | 0 | 0 | [73 empty] | -
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2306094A | 26247.69 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2127 | C |  | Hand Tool - Home Depot | 45098 | 45118 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 26247.69 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 22173.27 | 4074.42 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C007 | USCSB2305078A | 26070.88 | F21P1 VOC package （Installation ) | 1999 | C |  | BHTC housekeeping | 45063 | 45077 | [6 empty] | BHTC Arizona, LLC | PR Approved | PO Approved | Extension for USCSB2211009A for paying final invoice |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 26070.88 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 26070.88 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2310097B | 26066.7 | F21P1-0404_H_labor for 50 tools_MICU | 2759 | C |  | Uline security cart | 45216 | 2023/10/25 2024/01/12 2024/01/26 | 26066.7 | 0 | V |  |  |  | Thomas Scientific Holdings LLC | PR Approved | PO Approved | PO B: change supplier to Thomas Scientific PO R2: change supplier from ULINE to Thomas Scientific PO R1: Negotiated Unit Rate |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 26066.7 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 26066.7 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2212047A | 26056.92 | F21P1 WWT package (Installation and 2 batch tanks) | 1618 | C |  | WWT mini line material | 44923 | 44923 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 21255.49 | 0.81573 | 4801.43 | 0 | 4801.43 | 3825.9882 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 21255.49 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 781.7076 |  |  |  | 781.7076 |  |  |  | 781.7076 |  | 1062.7745 |  | - | 1062.7745 | 1700.4392 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2407097A | 26052 | F21P1-0404_H_Hallway plate install_MICU | 4512 | C |  | 4th 1000pcs tile swap | 45490 | 45496 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 26052 | 0 | 26052 | 0 | [73 empty] | - |  |  | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2403108A | 26052 | F21P1-0404_H_Hallway plate install_MICU | 3810 | C |  | 2nd 1000pcs tiles swap | 45363 | 45365 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 26052 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 26052 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2406036A | 26052 | F21P1-0404_H_Hallway plate install_MICU | 4262 | C |  | 3rd 1000pcs tile swap | 45449 | 45451 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 26052 | 26052 | 0 | 0 | [73 empty] | - |  |  | 0
[5 empty] | Others |  |  | USC23C002 | USCSB2410032A | 26052 | F21P1-0404_H_Hallway plate install_MICU | 4975 | C |  | 5th 1000pcs tile swap | 45568 | [7 empty] | 0 | PR Approving | PR Applying | [14 empty] | 0 | 0 | 26052 | 0 | 26052 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404084A | 26000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1038 | P |  | KEBCT1 Internal Connect hook up. | 45406 | 45407 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 26000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 26000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2311008A | 26000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2863 | C |  | Apex Precision Welding Mobil Welding LLC TSMC Unistrut Hanger Hole Rework | 45231 | 45232 | [6 empty] | Apex Precision Mobile Welding, LLC DBA Apex Precision | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 17370 | 0.66808 | 8630 | 0 | 8630 | 0 | [42 empty] | 0 | 10000 |  | 0 | 0 | 6370 | 1000 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2212007A | 26000 | F21P1 WWT package (Installation and 2 batch tanks) | 1580 | C |  | WWT CDA cooper tube and fittings | 44898 | 44909 | [6 empty] | Chien Tai Valves & Pipe Fittings Co. Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 26000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 26000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Equipment | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2308097A | 26000 | F21P1 Chemical & WCCS package | 2394 | C |  | Lorry tank (CDS+WCCS) self-closing swing door. | 45155 | 45169 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 26000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 26000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2305009A | 26000 | Tool Interconnection Project (Main Tool & Module) | 277 | P |  | Cables for LAM-Labor-Labor takes place at 23040 N. 11Th Ave Suite 100 - total 173 cabels | 45071 | 45120 | [6 empty] | Kaleidescope Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 26000 | 0 | 26000 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408013A | 25989.5 | TSMC Fab 21 P1B Tool Hook Up | 4635 | C |  | P1-B Hardware for Plastic system, Tool hookup team | 45507 | 45523 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 25989.5 | 0 | 25989.5 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311043A | 25969.31 | F21P1-0404_H_labor for 50 tools_MICU | 2898 |  |  | Fittings flange blind for Third. Tool id: KDIGA3 KECOT1 KETRT7 KKDB03 KPOV04 KKDB04 KKSV02 | 45239 | 45276 | [6 empty] | Apollo Sheet Metal, Inc. DBA Apollo Mechanical Contractors | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 25969.31 | 0 | 25969.31 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2403303A | 25945.36 | F21 TMAH System | 3995 | C |  | B side remaining pipe MU can't supply . | 45381 | 45384 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 25945.36 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 25945.36 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | W-H2SO4 | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C014 | USCSB2306010A | 25937.61 | F21P1 WH2SO4 | 2044 | C |  | WRC Material final from Harrington | 45080 | 45089 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25937.61 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 25671.91 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 265.7 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405149A | 25818.75 | WWT B side Project | 4178 | C |  | WWT materials (B side)_WIDOS INSERTS | 45436 | 45440 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 25818.75 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 25818.75 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408034A | 25810.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 1189 | P |  | ISO-KF Weld Stub Flange, NW25, 1.0in. Tube OD, 0.5in. Length 304 S. S | 45520 | 45523 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 24619.8 | 0.95388 | 1190.4 | 24747.81 | -23557.41 | 0 | [73 empty] | 24619.8
Others | 光阻櫃 | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Material | USC22C012 | USCSB2209027A | 25806.45 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1479 | C |  | F21 Large Stainless cabinet&Photo resist cabinet Seismic 材料 | 44828 | 44832 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved |  | 100% after shipped-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 11557.36 | 0.44785 | 14249.09 | 0 | 14249.09 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 11557.36 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408050A | 25722.48 | Tool Interconnection Project (Main Tool & Other Vendors) | 1198 | P |  | P1A_SUS 6" exhaust for 30' RHC line_KDTNK1_KDSRK6_KDCUK1_KDCUK2_KDCUK3 | 45525 | 45532 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | [14 empty] | 25722.46 | 1 | 0.02 | 0 | 0.02 | 0 | [72 empty] | 25722.46 | -
Base-Build | Base-Build | Equipment | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204001A | 25719.01 | F21P1 UPW | 148 | P |  | 2022 Polaris PRO XD Crew Diesel Com 21 902D PROXD, EPS | 44656 | 44664 | [6 empty] | Iron City Polaris | PR Approved | PO Approved |  | 100% T/T 0 days (no deposit, all should be paid before delivery) | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 0 | 0 | 25719.01 | 0 | 25719.01 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407021A | 25668.15 | F21P1-0404_H_labor for 50 tools_MICU | 4422 | C |  | Mast Lift 25ft for HK shared by all systems | 45476 | 45482 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 9653.54 | 0.37609 | 16014.61 | 3460.95 | 12553.66 | 0 | [73 empty] | 9653.54 |  |  | 0
Base-Build | CCTV |  |  |  | Low Voltage | Electrical | M+L | USC22C001 | USCSB2409010A | 25656.57 | F21 P1 Office and WH Security and CCTV | 4780 | C |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 3/6 | 45539 | 45542 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 25656.57 | 1 | 0 | 25656.57 | -25656.57 | 0 | [73 empty] | 25656.57
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310045A | 25650 | Tool Interconnection Project (Main Tool & Module) | 463 | P |  | Six 40' storage containers | 45220 | 45228 | [6 empty] | Adaptive Shelters, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 25650 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 25650 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405018A | 25636.83 | Tool Interconnection Project (Main Tool & Other Vendors) | 1077 | P |  | MANPOWER: PINNACLE PEAK WAREHOUSES: 04/23-05/31/24 REG HRS | 2024/5/7 2024/9/12 | 2024/5/8 2024/9/12 | 8068.83 | 17568 |  |  |  | V | CGS Global Support, LLC | PR Approved | PO Approved | PR R1: Addtl' 179 REG HRS & 16.50 OT HRS combined for Ernesto Limon from 06/09-07/07. | [13 empty] | 0 | 0 | 25636.83 | 8828.73 | 16808.1 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Steel | M+L | USC21C005 | USCSB2306086A | 25630 | F21P1 Chemical & WCCS package | 2119 | C |  | WRC Acid Zone UPW Stair | 45097 | 45124 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25630 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 25630 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402226A | 25628.6 | F21P1 Chemical & WCCS package | 3653 | C |  | CDS Cush Clamps | 45345 | 45349 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 25626.6 | 0.99992 | 2 | 0 | 2 | 0 | [52 empty] | 0 | 0 | 24162.06 |  | 0 |  | 1312.74 |  |  | 154.54 | 93.61 |  |  |  | 58.19 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | DCR Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2304056A | 25626 | F21P1 Chemical & WCCS package | 1895 | C |  | CDS Additional EQ Relocation | 45036 | 45054 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25626 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 25626 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2210035A | 25364.67 | F21P1 WWT package (Installation and 2 batch tanks) | 1518 | C |  | PVC SCH80 Fittings Litho Fab Spears | 44854 | 44855 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 25364.67 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 25364.67 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405041A | 25292.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1083 | P |  | KDCCS3 - rework DNS SCREEN INTERCONNECTS 4/4-4/6 | 45426 | 45427 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 25292.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 25292.6 | [10 empty] | - |  |  | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2303063A | 25254 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1802 | C |  | MIC West Wall Power Outlet | 45001 | 45015 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25253.84 | 0.99999 | 0.16 | 0 | 0.16 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 5872.84 | 19381 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC23C045 | USCSB2401218A | 25247.39 | WWT Change Order (Piping) | 3400 | C |  | WWW-HKPs epoxy | 45317 | 45320 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 25247.39 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 25247.39 |  | 0 |  |  |  |  | 3787.1085 |  |  |  | 3787.1085 |  |  |  | 3787.11 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404225A | 25213.35 | WWT B side Project | 3975 | C |  | WWT Fittings for O3_20240429 (B Side) | 45412 | 45413 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 25213.35 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 6737.48 |  | 18475.87 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310008A | 25155 | F21P1-0404_H_labor for 50 tools_MICU | 2671 | C |  | Label | 45202 | 45213 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 25155 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 25155 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USC2112028A | 25074.45 | F21P1 UPW | 91 | P |  | vortex flowmeter | 44552 | 44571 | [6 empty] | Oval Corporation of America | PR Approved | PO Approved | NO CF/NO Vendor sheet | 90% by received (Net 30 days) , 10% after acceptance in 60 days (Net 30 days). | York Yeh | EXW from Oval Houston Office | 24 months after shipping | Sterling Ellis | York Yeh | N |  | Matt |  | N | 5000 |  | 25074.45 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 25074.45 | [18 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2404146A | 25013 | F21P1 Module Tool Interconnection CVD | 4130 | C |  | KCOLA3 Olympia Project | 45401 | 45408 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 25013 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 25013 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2402009A | 25009 | WWT Change Order (Piping) | 3452 | C |  | UMEC overtime for Blackout Testing Sunday Work | 45323 | 45325 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 25009 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 23759 | 0 | 0 |  | 0 |  | 1250 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | chemical safety cabinet | MIMO/Rigging | Main Contract Scope | Chemical Lab | Chemical | Mechanical | Labor | USC23C042 | USCSB2306129A | 25007 | F21P1 Chemical Safety Cabinet Installation | 2162 | C |  | Safety Cabinet Move-in | 45105 | 45140 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25007 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 12503.5 |  | 0 | 0 | 12503.5 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2309185A | 25000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2654 | C |  | San Tan Fire LLC Welding Electrical Work | 45198 | 45202 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 25000 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404080A | 25000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1034 | P |  | KDMRS1 Internal Connect hook up. | 45406 | 45407 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 25000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 25000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | UMEC | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2403075A | 24859 | F21P1 Chemical & WCCS package | 3779 | C |  | CDS UPW - 8-194 Chem UPW Loops | 45358 | 45363 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 24859 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 23616 | 0 |  | 1243 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C014 | USCSB2308066A | 24830 | F21P1 WH2SO4 | 2364 | C |  | MIC Three and Seven Trailer Hookup | 45149 | 45153 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 24830 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 24830 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310050A | 24782 | Tool Interconnection Project (Main Tool & Module) | 468 | P |  | KPOCS3-S GREENBERRY EXHAUST | 45224 | 45241 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 23542.9 | 0.95 | 1239.1 | 0 | 1239.1 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 23542.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306037A | 24780 | Tool Interconnection Project (Main Tool & Module) | 321 | P |  | KPD801-T ALVARADO ELECTRIC - LABOR | 45087 | 45131 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12240 | 0.49395 | 12540 | 0 | 12540 | 0 | [33 empty] | 0 | [5 empty] | 12240 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306036A | 24780 | Tool Interconnection Project (Main Tool & Module) | 320 | P |  | KPAN01-T ALVARADO ELECTRIC-L | 45087 | 45131 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7860 | 0.31719 | 16920 | 0 | 16920 | 0 | [33 empty] | 0 | [5 empty] | 7860 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306035A | 24780 | Tool Interconnection Project (Main Tool & Module) | 319 | P |  | KPAE01-T ALVARADO ELECTRIC - LABOR | 45087 | 45129 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12060 | 0.48668 | 12720 | 0 | 12720 | 0 | [33 empty] | 0 | [5 empty] | 12060 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC |  |  |  | Low Voltage | Electrical | M+L | USC24C007 | USCSB2409005A | 24728 | Low Voltage B Side Project | 4775 | C |  | F21 P1 VOC Electricity Change Order _CO#32,CO#33,CO#34,CO#36,CO#40 | 45539 | 45542 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 24728 | 1 | 0 | 24728 | -24728 | 0 | [73 empty] | 24728
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303031A | 24723 | F21P1 Module Tool Interconnection DIF1-2 | 1773 | C |  | DIF swagelok SWG connector | 44992 | 45007 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 24723 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 20128 |  | 0 | 4595 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401010A | 24703.97 | F21P1-0404_H_labor for 50 tools_MICU | 3201 | C |  | gas storage tools. Tool hookup team | 45295 | 45300 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 24703.97 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 24703.97 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USC2403035A | 24658.73 | F21P1 AMAT Interconnection | 861 | P |  | Power Cable Materials from WESCO for KSMGA1, KSMGA2, KSHMA3, KEEBA1, KEPAA1 | 45359 | 45364 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 24130.01 | 0.97856 | 528.72 | 0 | 528.72 | 0 | [52 empty] | 0 | 820.52 | 268.17 |  | 5889.33 |  | 8419.48 |  |  |  | 8732.51 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MIMO/Rigging | DCR Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2403257A | 24635 | F21P1 Chemical & WCCS package | 3950 | C |  | 24-097 CDS Platform 3 Move Quote (cat work move) | 45378 | 45412 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 24635 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 24635 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2301029A | 24616 | F21P1 Chemical & WCCS package | 1650 | C |  | Third - Breaker | 44938 | 44944 | [6 empty] | Third Enterprise | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 24616 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 24616 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC24C005 | USCSB2404060A | 24562.5 | Chemical & WCCS B Side Project | 4052 | C |  | FAB A SDS, CDS, WCCS Pressure Test | 45388 | 45391 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 18740 | 0.76295 | 5822.5 | 0 | 5822.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6895 |  |  | 6123.11 |  |  | 6935 | 6140.63 |  |  | 4910 | 5403.75 |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2305007A | 24500 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1931 | C |  | KPE602-S MMI Industrial & Steel | 45049 | 45054 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2937 | 0.11988 | 21563 | 0 | 21563 | 0 | [33 empty] | 0 | [6 empty] | 2937 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404216A | 24493.17 | WWT B side Project | 3967 | C |  | WWT Ball Valve&Cap_20240426 (B Side) | 45412 | 45413 | [6 empty] | Supertung Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 24493.17 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 12246 | [5 empty] | 12247.17 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2407174A | 24452.28 | F21P1 Module Tool Interconnection ETC1-3 | 4597 | C |  | MISUMI | 45504 | 45507 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 24452.28 | 0 | 24452.28 | [74 empty] | -
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2312014A | 24435 | F21P1 WWT package (Installation and 2 batch tanks) | 3008 | C |  | WWT - FRP Bond (55) Post on TMAH Tanks for Handrail | 45265 | 45268 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 24435 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3665.25 |  |  | 24435 | 3665.25 |  |  |  | 3665.25 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404204A | 24411 | WWT B side Project | 4183 | C |  | WWT DS & LCB (B side material) | 45408 | 45411 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 24411 | 0 | 24411 | 29293.2 | [54 empty] | 0 |  | 0 |  |  |  |  | 3661.65 |  |  |  | 3661.65 |  |  |  | 3661.65 |  | 12205.5 |  | - | 7323.3 | 7323.3 | 2441.1 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2110011A | 24306 | F21P1 WWT package (Installation and 2 batch tanks) | 1300 | C |  | WWT CS Tank Inspection | 44482 | 44484 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | 44488 | Henry |  | N |  |  | 24306 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 24306 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2410002A | 24300 | TSMC Fab 21 P1B Tool Hook Up | 4949 | C |  | Cleanroom tape for HK Power for 200 tools | 45566 | 45567 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approving | [14 empty] | 0 | 0 | 24300 | 0 | 24300 | 0
Base-Build | Speed Gate | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C001 | USCSB2111004A | 24299 | tsmc AZ Temporary Office Physical Security | 1308 | C |  | CCTV System | 44517 | 44522 | [6 empty] | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved |  | 100% by progress, T/T 30 days. | York Yeh | DDP | 1 year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | York Yeh |  | 44525 | Henry/Martin |  | N |  |  | 24299 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 24299 | [23 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2404018A | 24240 | F21P1 AMHS Wiring Work Outline | 4014 | C | -01 | Additional Modules M166M188 and 27 STKs PR | 2024/4/2 2024/4/11 | 2024/4/2 2024/4/11 | 910 | 23330 | V |  |  |  | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | R1: updated to reflect the newest quote w/ total $24,240 LSW sent us at the end of Feb. The old quote with final price of $23,330 |  | Yi En Wong | [11 empty] | 24240 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 19420 |  |  |  |  | 0 |  | 4820 | 0 | 0 | 0
Base-Build | VOC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C013 | USCSB2312185A | 24195 | F21P1 AMC THC Monitoring System | 3172 | C |  | FAB B VOC Electrical CA service | 45288 | 45302 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5718 | 0.23633 | 18477 | 1143.6 | 17333.4 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 2287.2 |  |  |  | 1143.6 | [5 empty] | 1143.6 |  |  |  | 1143.6 | - |  | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404008A | 24111.63 | Tool Interconnection Project (Main Tool & Other Vendors) | 963 | P |  | KCSCS7-DNS SCREEN INTERCONNECTS 3/11-3/26/2024 | 45384 | 45387 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 24111.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 24111.63 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | FMCS |  |  |  | Others |  |  | USC22C007 | USCSB2407093A | 24007 | TSMC F21 FMCS Installation | 4509 | C |  | LB PULL BACK & CUP POWER CABLES | 45489 | 45498 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved | [14 empty] | 0 | 0 | 24007 | 0 | 24007 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2308161A | 24000 | F21P1-0404_H_labor for 50 tools_MICU | 2455 | C | -01 | Traffic Cone and Pole Order | 45164 | 2023/8/31 2023/9/6 | [6 empty] | HSIEH SHUN HING CO., LTD. | PR Approved | PO Approved | R1:remark not embedded |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 24000 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 4800 |  | 0 | 0 | 0 | 0 |  | 19200 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C040 | USCSB2305100A | 23981.12 | TSMC F21 Clean Room Suit | 2021 | C |  | Industrial Coverall with Hood | 45069 | 45070 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 23981.12 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 23981.12 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404078A | 23969.51 | Tool Interconnection Project (Main Tool & Other Vendors) | 1032 | P |  | 800-015 1-1/2" PIPE P/E PVC SCH80 CPN-P-TIC-PV-S8PI-042 | 45405 | 45407 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 23969.51 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 14473.26 |  | 7142.85 |  | 2353.4 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2406086A | 23942.3 | WWT B side Project | 4322 | C |  | WWT Ball Valve_20240613 (B Side) | 45458 | 45463 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23942.3 | 0 | 23942.3 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Slurry | MMI | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2401079A | 23928 | F21P1 Slurry package | 3268 | C |  | SDS Slurry A side plates | 45303 | 45304 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 23928 | 1 | 0 | 0 | 0 | 1196.4 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 22731.6 |  |  |  | 1196.4 | [8 empty] | 0 |  | - | 0 | 0 | 1196.4
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408041A | 23911.99 | TSMC Fab 21 P1B Tool Hook Up | 4632 | C |  | Straight tee fittings w/ flanges for Exhaust HL for 50 tools | 45513 | 45518 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23911.99 | 1814.82 | 22097.17 | [74 empty] | -
Base-Build | Base-Build | Equipment | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2206026A | 23901 | F21P1 WWT package (Installation and 2 batch tanks) | 1415 | C |  | 3rd party QC for CS tanks | 44742 | 44747 | [6 empty] | Weld Spec, Inc. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 23764.38 | 0.99428 | 136.62 | 0 | 136.62 | 0 | [13 empty] | 956.5 | 6676.25 |  | 6003.25 |  | 5961.38 |  | 4167 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USC2112002A | 23872.51 | F21P1 Chemical & WCCS package | 70 | P |  | Ball Valve | 44531 | 44586 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | CF (Trade term check)) | Arrival (delivery) 100.00% NET 30days after shipping | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 23872.52 | 1 | -0.01 | 0 | -0.01 | 0 | [28 empty] | 0 | 2929.2 |  |  |  | 0 |  |  | 20943.32 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Speed Gate | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C002 | USCSB2111005A | 23843 | TSMC AZ Temp Office Speed Gate | 1309 | C |  | Access Systrm | 44517 | 44522 | [6 empty] | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved |  | 100% by progress, T/T 30 days. | York Yeh | DDP | 1 year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | York Yeh |  | 44525 | Henry/Martin |  | N |  |  | 23843 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 23843 | [23 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | MMI | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2307101A | 23810 | F21 TMAH System | 2267 | C |  | MIC T-140AA Lining | 45128 | 45148 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 23810 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 23810 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USC2111034A | 23801.52 | F21P1 UPW | 45 | P |  | Hydrogen Peroxide Analyzer | 44517 | 44543 | [6 empty] | Precision Integrated Systems, LLC | PR Approved | PO Approved | (無CF &Supplier's sheet) 12/13 採購單簽核 | 90% by received, Net 30days; 10% by acceptance, Net 30days(after acceptance in 60days). | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | N |  | Matt |  | N | 5000 |  | 23701.52 | 0.9958 | 100 | 0 | 100 | 0 | [6 empty] | 21331.37 | 2370.15 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MIMO/Rigging | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2405129A | 23750 | WWT B side Project | 4157 | C |  | WWT T-780BABB Header rigging | 45434 | 45443 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 23750 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 23750 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Material | USC24C005 | USCSB2407001A | 23743.52 | Chemical & WCCS B Side Project | 4403 | C |  | CED 化學系統電力訊號五金0627 (CED Chem Signal Cable Hardware) | 45474 | 45474 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23743.52 | 23840.11 | -96.59 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404139A | 23684.7 | Chemical & WCCS B Side Project | 4123 | C |  | F21 B side電與訊號線購買01 | 45400 | 45419 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 23684.7 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 23684.7 |  |  | 23684.7 | [5 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408009A | 23652.95 | TSMC Fab 21 P1B Tool Hook Up | 4606 | C |  | Hardware for P1-B project, Gas and Chemical system | 45507 | 45513 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23652.95 | 0 | 23652.95 | [74 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404042A | 23602 | Tool Interconnection Project (Main Tool & Other Vendors) | 996 | P |  | Manpower Pay for Delta Wye for Tool ID: KETRTD Timecards for 3.26, 3.27,3.28, 3.29, 4.1, & 4.2.2024 | 45391 | 45393 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 23602 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 23602 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2308044A | 23550.84 | WWT Change Order (Piping) | 2342 | C |  | WWT -Sludge/Triazole shortage materials | 45146 | 45153 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 13848.24 | 0.58801 | 9702.6 | 0 | 9702.6 | 5677.7784 | [40 empty] | 0 | 0 | 0 | 11035.15 |  | 0 | 0 | 0 | 0 | 0 | 2813.09 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1177.542 |  |  |  | 2355.084 |  |  |  | 2355.084 |  | 2769.648 |  | - | 2908.1304 | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2306131A | 23500 | F21 TMAH System | 2164 | C |  | Taiwan D180/225 MU material | 45106 | 45110 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 23500 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 18450.6 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 5049.4 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2312140A | 23381.3 | F21P1-0404_H_labor for 50 tools_MICU | 3129 | C |  | Pallet truck, jobsite box, storage for third | 45279 | 45288 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 23381.3 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 23381.3 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Greenberry |  |  | WWT | Steel | Labor | USC23C014 | USCSB2304005A | 23225 | F21P1 Labor incentive program-MICU | 1846 | C |  | 2022, 2023 holiday incentive (Nov, Dec, Jan) | 45022 | 45042 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 23225 | 0 | 23225 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Micron - Material | Material |  |  | Others |  |  | USC24C001 | USCSB2401128A | 23200 | Micron - Chemical SOLBLE RN3000 | 3314 | C |  | Chemical SOLBLE RN3000 for Micron Boise faclity, Idaho | 45309 | 45310 | [6 empty] | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 23200 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 23200 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2308046A | 23172 | F21P1 UPW | 2344 | C |  | TSMC UPW – 8-128 WRC HCl Flange Break | 45146 | 45149 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 23172 | 0 | 23172 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2307049A | 23119.22 | F21 TMAH System | 2218 | C |  | Big / Small size bolts | 45119 | 45121 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 23119.22 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 11191.45 |  | 10170.93 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1756.84 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402099A | 23000 | Tool Interconnection Project (Main Tool & Other Vendors) | 813 | P |  | F21P1-KPE602-S Labor: Removal and addition of GAS Pipelines | 45346 | 45348 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 23000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 23000 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403089A | 22900.81 | Tool Interconnection Project (Main Tool & Other Vendors) | 906 | P |  | 212304PS10 2-1/2 S10 304L WLD PIPE === 60FT STOCK BALANCE 1 WEEK | 45372 | 45376 | [6 empty] | Industrial Pipe and Valve Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 22900.81 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 22900.81 | [12 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C025 | USCSB2409125A | 22770 | Tool Hookup Material (UPW&Chemical) | 4943 | C |  | AMHS Zip Stocker Removal | 45563 | 45566 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 22770 | 0 | 22770 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2311074A | 22673.37 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2928 | C |  | Border States Electrical Work Material PreFab Area Open Statement Invoices | 45246 | 45252 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20823.38 | 0.91841 | 1849.99 | 0 | 1849.99 | 0 | [43 empty] | 0 | 20823.38 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310200A | 22615 | F21P1-0404_H_labor for 50 tools_MICU | 2851 | C |  | Blank off Flange in various sizes for pumping line QC test. Tunyi | 45230 | 45232 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 20015 | 0.88503 | 2600 | 0 | 2600 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 20015 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402146A | 22575.43 | F21P1 WWT package (Installation and 2 batch tanks) | 3579 | C |  | WWT PTFE coating bolt | 2024/2/15 2024/2/21 2024/3/13 | 45369 | [6 empty] | LIGHTNING BOLT & SUPPLY, INC. | PR Approved | PO Approved | PR R2:As per purchasing team Oneil to revise the freight. PR R1:Revise PR amount after confirmation of shipping charge |  | Kuan-Chung Su | [11 empty] | 22575.43 | 1 | 0 | 0 | 0 | 0 | 22575.43 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC | EDG | Labor |  |  | Others |  |  | USC22C003 | USCSB2305110A | 22570 | TSMC Fab21 Project Phase 1 EDG Package | 2027 | C |  | LSW Change Orders | 45072 | 45078 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 16570 | 0.73416 | 6000 | 0 | 6000 | 0 | [33 empty] | 0 |  |  |  | 398 | 7891 |  | 0 | 0 | 780 | 0 |  | 0 | 3750.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 3750.5 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Material | USC21C013 | USCSB2303022A | 22552.6 | F21P1 AMC THC Monitoring System | 1764 | C |  | Dual-Stage Pressure Regulator | 44988 | 44991 | [6 empty] | Matheson Tri-Gac Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 22552.6 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 22552.6 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404069A | 22525.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 1023 | P |  | 3353.005 +NRT+ SYGEF BCF PLUS UNION 1/2" NON-CANCELABLE, NON-RETURNABLE MFG P/N 735.528.626 | 45399 | 45401 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 22525.5 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 19677.3 |  | 2848.2 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | The budget execution does not pertain to this project | 0 | Low Voltage | Electrical | Labor | USC21C008 | USCSB2209013A | 22499.56 | F21P1 CCTV & Security | 1465 | C |  | TSMC Dunlap Office turnstile and metal detector installation | 9/15/2022 9/14/2024 | 9/20/2022 9/26/2024 | -0.44 | 22500 |  |  |  |  | BPG Technologies, LLC | PR Approved | PO Approved | 替代CCE USCSB2202006A-1 R1: As per PM Paul and Debby to close out this PO. | 95% by progress-T/T 30 days-After Acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 22499.56 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 22499.56 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | -
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2303098A | 22491.13 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1835 | C |  | Glendale Warehouse OSC Office Construction | 45014 | 45020 | [6 empty] | Western Slope Signs and Service LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 22491.12 | 1 | 0.01 | 0 | 0.01 | 0 | [29 empty] | 11245.56 |  |  |  | 0 | [5 empty] | 11245.56 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401014A | 22487.1 | Tool Interconnection Project (Main Tool & Other Vendors) | 638 | P |  | P-NF-1/2: NUT, FEMALE, HTC | 45302 | 45309 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 18649.05 | 0.82932 | 3838.05 | 0 | 3838.05 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 18649.05 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307081A | 22389 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2247 | C | -01 | Southwest Fastener Hand Tool | 2023/7/19 2023/8/7 | 2023/7/20 2023/8/8 | -1237.43 | 23626.43 |  |  |  |  | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | R1:007 item changed from model 45 to model 44 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18595 | 0.83054 | 3794 | 0 | 3794 | 0 | [38 empty] | 15727 | 2868 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404075A | 22386.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 1029 | P |  | Manpower Pay for Delta Wye Tool ID:KESRT5 Time cards on 4.3, 4.4, 4.5, 4.8,4.9 and 4.10.2024 | 2024/4/20 2024/4/23 | 45407 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | PR R1: Corrected work hours for 3 employees on three different days | [13 empty] | 22386.5 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 22386.5 | [12 empty] | 0 |  | - | 0 | 0 | 0
Others | 光阻櫃 | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC22C012 | USCSB2210002A | 22348 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1486 | C | -01 | 宇承_工作桌&推車 | 2022/10/1 2023/4/18 | 2022/10/3 2023/4/19 | 3735 | 18613 |  |  |  | V | Yu Cheng Kid Enterprise Co., | PR Approved | PO Approved | Adding $3,735 overtime pay in (originally should be in USCSB2210003A) | 100% by received-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 22348 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 22348 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C014 | USCSB2307077A | 22345.88 | F21P1 AMHS Power Panel | 2244 | C |  | AMHS Channel Tray for Muratec Interconnection | 45126 | 45127 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 22345.88 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 10747.92 |  | 0 | 0 | 0 | 0 |  | 0 | 11597.96 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2311015A | 22319.84 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2870 | C |  | Electric Ops Electrical Work within Glendale Whs OSC Prefab-Taiwan Vendor Support | 45233 | 45236 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 22319.84 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 22319.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2403220A | 22277 | F21P1 Module Tool Interconnection CVD | 3915 | C |  | CVD AMAT Interconnect Oil Piping on KCOLA1 | 45372 | 45376 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 22277 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 22277 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C004 | USCSB2306019A | 22178.07 | F21P1 WWT package （USA EQ-FRP tank) | 2053 | C |  | WWT -HACH-lab | 45083 | 45096 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 22178.07 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 22178.07 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403104A | 22163.91 | Tool Interconnection Project (Main Tool & Other Vendors) | 920 | P |  | KRWRS2-DNS SCREEN INTERCONNECTS - 3/8-3/15/2024. | 45374 | 45378 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 22163.91 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 22163.91 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2311018A | 22098 | WWT Change Order (Piping) | 2873 | C |  | WWT-Ysgasket | 2023/11/4 2023/11/9 | 45239 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | PR R1:Renew quotation |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 22098 | 1 | 0 | 0 | 0 | 22098 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3314.7 |  |  |  | 3314.7 |  |  | 22098 | 3314.7 |  | 5524.5 |  | - | 5524.5 | 5524.5 | 5524.5 | 0
Base-Build | Slurry | Labor | Main Contract Scope | SDS | Chemical | Electrical | Labor | USC21C005 | USCSB2403037A | 22080 | F21P1 Chemical & WCCS package | 3745 | C |  | SDS H2O2 to equipment wiring | 2024/3/5 2024/6/12 | 45457 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved | PR R1: After negotiations by Engineer Johnny with the supplier, the PR amount was adjusted. |  | 0 |  |  |  | 0 | [7 empty] | 0 | 0 | 22080 | 0 | 22080 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [12 empty] | 25000 |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2302055A | 22070.94 | F21P1 Chemical & WCCS package | 1736 | C |  | New box PP make | 44985 | 44993 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 22070.94 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 22070.94 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2203011A | 22016 | F21P1 WWT package (Installation and 2 batch tanks) | 1346 | C |  | Outsourcing Service General Worker | 44638 | 44641 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 21764.47 | 0.98858 | 251.53 | 0 | 251.53 | 0 | [7 empty] | 1263.38 | 1633.97 | 1579.61 | 2539.64 | 14747.87 | [16 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2309082A | 22000 | F21P1 UPW | 2555 | C | -01 | Battery Charge B Side 10 Cabinets | 45184 | 2023/9/20 2023/10/10 | 3000 | 19000 |  |  |  |  | Gruber Industries | PR Approved | PO Approved | R1:revise price |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 22000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 22000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404087A | 22000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1040 | P |  | KEPST2 Internal Connect hook up. | 45406 | 45406 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 22000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 22000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404085A | 22000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1039 | P |  | KEPST1 Internal Connect hook up. | 45406 | 45406 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 22000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 22000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401015A | 21947 | Tool Interconnection Project (Main Tool & Other Vendors) | 639 | P |  | KPOV05 Exhaust Piping Labor | 45302 | 45309 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 21947 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403062A | 21947 | Tool Interconnection Project (Main Tool & Other Vendors) | 885 | P |  | KPOV12 Exhaust Piping Labor | 45365 | 45370 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 21947 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403061A | 21947 | Tool Interconnection Project (Main Tool & Other Vendors) | 884 | P |  | KPOV11 Exhaust Piping Labor | 45365 | 45370 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 21947 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402026A | 21947 | Tool Interconnection Project (Main Tool & Other Vendors) | 752 | P |  | KPOV07 Exhaust Piping Labor | 45325 | 45331 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402025A | 21947 | Tool Interconnection Project (Main Tool & Other Vendors) | 751 | P |  | KPOV06 Exhaust Piping Labor | 45325 | 45331 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402027A | 21947 | Tool Interconnection Project (Main Tool & Other Vendors) | 753 | P |  | KPOV08 Exhaust Piping Labor | 45325 | 45331 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403024A | 21947 | Tool Interconnection Project (Main Tool & Other Vendors) | 850 | P |  | KPOV10 Exhaust Piping Labor | 45358 | 45362 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403009A | 21947 | Tool Interconnection Project (Main Tool & Other Vendors) | 836 | P |  | KPOV09 Exhaust Piping Labor | 45355 | 45359 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | MIMO/Rigging | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2312018A | 21922 | F21 TMAH System | 3012 | C |  | Tmah ACF expansion EQ move in | 45265 | 45269 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21922 | 1 | 0 | 0 | 0 | 1041.295 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 3123.88 |  | 8933.22 | 0 | 8768.8 |  | 0 | [13 empty] | 1096.1 | 0 |  | - | 0 | 0 | 0 | 1041.295
Base-Build | WWT |  |  |  | WWT | Mechanical | M+L | USC24C006 | USCSB2408066A | 21911.91 | WWT B side Project | 4682 | C |  | WWT LSR system - Okland | 45519 | 45524 | [6 empty] | Okland Construction Company, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21911.91 | 0 | 21911.91 | 0 | [73 empty] | -
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2306059A | 21873 | F21P1-0404_H_Hallway plate install_MICU | 2093 | C |  | ATF-D-09 installation | 45092 | 45113 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 20779.35 | 0.95 | 1093.65 | 0 | 1093.65 | 0 | [33 empty] | 0 | [6 empty] | 20779.35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C034 | USCSB2401181A | 21770 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/N2/APK/UPK/ASRS | 3366 | C |  | AMHS Additional 140 AC Boxes Design | 45314 | 45314 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 21770 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 21770 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2305006A | 21710 | Tool Interconnection Project (Main Tool & Module) | 275 | P | -01 | CVD2 Material-UHP Bourdon Tube Pressure Gauge | 45063 | 2023/6/14 2023/06/23 | -2012 | 23722 |  |  |  |  | Motion Automation Intelligence | PR Approved | PO Approved | Better pricing sourced lower pricing |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21710 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 21710 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407013A | 21637 | Tool Interconnection Project (Main Tool & Other Vendors) | 1151 | P |  | KPAE02-S Insulation Labor | 45486 | 45490 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21637 | 0 | 21637 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | Internet | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C008 | USCSB2205002A | 21616 | F21P1 CCTV & Security | 1366 | C |  | MIC Modular Office Fiber | 44685 | 44692 | [6 empty] | Chunghwa Telecom Global, Inc | PR Approved | PO Approved |  | 100% after completion-after acceptance-net 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 21616 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 21616 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310082B | 21590 | F21P1-0404_H_labor for 50 tools_MICU | 2743 | C |  | Tool Hookup L40 Warehouse | 45212 | 45246 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8149.98 | 0.37749 | 13440.02 | 0 | 13440.02 | 0 | [43 empty] | 0 |  | 0 | 0 | 8149.98 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Material | USC21C005 | USCSB2406121A | 21551.14 | F21P1 Chemical & WCCS package | 4360 | C |  | [Pure] SS box door | 45468 | 45474 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | [14 empty] | 15085.8 | 0.7 | 6465.34 | 0 | 6465.34 | 0 | [72 empty] | 15085.8 | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2311027A | 21528.4 | WWT Change Order (Piping) | 2882 | C |  | Hand tools for TW team | 45237 | 45241 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 21528.4 | 0 | 21528.4 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3229.26 |  |  |  | 3229.26 |  |  |  | 3229.26 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409025A | 21524 | Tool Interconnection Project (Main Tool & Other Vendors) | 1228 | P |  | WIRE 6-04TC-VN #6AWG/4C All Insulated ‘per 1000’ | 45548 | 45551 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21524 | 0 | 21524 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408056A | 21493 | F21P1 Module Tool Interconnection LIT2-3 | 4674 | C |  | Lit 3: KPAP02-T: BB Rework | 45517 | 45520 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 21493 | 1 | 0 | 21493 | -21493 | 0 | [73 empty] | 21493
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401019A | 21474 | Tool Interconnection Project (Main Tool & Other Vendors) | 643 | P |  | MANPOWER PAY FOR CCE | 45303 | 45337 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 21474 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 21474 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401022A | 21451.81 | Tool Interconnection Project (Main Tool & Other Vendors) | 645 | P |  | KETRT8- 11/15-12/20/2023 Cable pulls for power & signal interconnect. Cable rework for Ewah suggestions that were considered and implemented during our initial cable pulls. | 45303 | 45309 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 21451.81 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 21451.81 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC22C036 | USCSB2301003A | 21413.59 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1626 | C |  | Armaflex Insulation | 44931 | 44944 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 21413.59 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 21413.59 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402001A | 21400 | F21P1 Chemical & WCCS package | 3444 | C |  | CDS B side support L30 coating | 45323 | 45324 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 21400 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 21400 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical Lab | UMEC | The budget execution does not pertain to this project | Chemical Lab | Chemical | Mechanical | M+L | USC22C021 | USCSB2309048A | 21374 | F21P1 Chemical Lab setup | 2525 | C |  | 8-134 FAB Gas Chem Lab Hook-Up Reroute(GC Lab Piping Change Order) | 45181 | 45195 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 20306 | 0.95003 | 1068 | 0 | 1068 | 1068 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 19237 | 0 | 1069 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 1068
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401263A | 21369.16 | F21P1 Chemical & WCCS package | 3443 | C |  | CDS B side support L30 materials | 45322 | 45324 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 21369.16 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 1766.13 | 19603.03 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407144A | 21364 | TSMC Fab 21 P1B Tool Hook Up | 4555 | C |  | Cord grip for HK power trade for 80 tools | 45497 | 45499 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1442.07 | 0.0675 | 19921.93 | 0 | 19921.93 | 0 | [72 empty] | 1442.07 | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306043A | 21245.1 | Tool Interconnection Project (Main Tool & Module) | 327 | P |  | KPE603-S EXHAUST INSTALLATION - STREIMERS | 45094 | 45096 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16903.71 | 0.79565 | 4341.39 | 0 | 4341.39 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 2771.1 | 0 | 0 |  |  | 14132.61 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV |  | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC21C001 | USCSB2102001A | 21171 | tsmc AZ Temporary Office Physical Security | 1231 | C |  | AZ temporary office CCTV installation | 44243 | 44245 | [6 empty] | B&D Industries, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21171 | 0 | 21171 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404003A | 21164.63 | Tool Interconnection Project (Main Tool & Other Vendors) | 958 | P |  | KDMRS1-DNS SCREEN INTERCONNECTS 3/5-3/26/2024 | 45384 | 45386 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 21164.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 21164.63 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C053 | USCSB2407176A | 21152 | AMAT Interconnection (TSMC) | 4599 | C |  | scaffolding assembly/dismantling | 45504 | 45517 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 19383 | 0.91637 | 1769 | 0 | 1769 | [69 empty] | 13232 |  | 6151 |  |  | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407164A | 21130 | TSMC Fab 21 P1B Tool Hook Up | 4587 | C |  | Wire TCXH for HK Power Trade | 45502 | 45503 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21130 | 0 | 21130 | [74 empty] | -
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USC2111047A | 21112 | F21P1 Chemical & WCCS package | 48 | P |  | power panels for Chemical system | 44523 | 44532 | [6 empty] | OEG ISG - Integrated Systems Group | PR Approved | PO Approved | 專案回覆待確認中(CF)，trade term 修改DAP 12/3 採購單成立 | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 21112 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 21112 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2306046A | 21074.6 | F21P1 WWT package (Installation and 2 batch tanks) | 2080 | C |  | WWT Tanks diamond labels | 45090 | 45104 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 21074.6 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 21074.6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Equipment | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2209004A | 21031.43 | F21P1 UPW | 229 | P |  | Cushman Hauler Pro-X Elite 2023 Battery operated type is trail green color hood | 44806 | 44816 | [6 empty] | Pohle NV Center, Inc. | PR Approved | PO Approved | Golf Cart with written approval | 100% Prepayment-Net 30 days | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 0 | 0 | 21031.43 | 0 | 21031.43 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401043A | 21016.44 | Tool Interconnection Project (Main Tool & Other Vendors) | 665 | P |  | KPAN01-S Nov 2023 Invoice for Labor | 45311 | 45316 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21016.44 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 21016.44 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408087A | 21013 | TSMC Fab 21 P1B Tool Hook Up | 4702 | C |  | Flat flange for HK Exhaust trade for 52 tools | 45525 | 45527 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21013 | 2284 | 18729 | 0 | [73 empty] | -
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401015A | 21000 | F21P1-0404_H_labor for 50 tools_MICU | 3206 | C |  | HK Chuan Ta Equipment Rental for 3 months | 2024/1/4 2024/1/17 | 2024/1/26 | [6 empty] | Chuan Ta Technology Corp. | PR Approved | PO Approved | PR R1: Adjusting the PR to align with actual rental date. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 21000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 21000 | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306055A | 21000 | Tool Interconnection Project (Main Tool & Module) | 336 | P |  | KPOV04 Onsite Live Labor Pay | 45105 | 45132 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 21000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2310043A | 20990.4 | WWT Change Order (Piping) | 2704 | C |  | Material for drain PN6 | 45206 | 45211 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 20990.4 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 17990.4 | 0 | 0 | 0 |  | 0 |  |  |  |  | 419.808 |  |  | 3000 | 629.712 |  |  |  | 1049.52 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310172A | 20890.32 | F21P1-0404_H_labor for 50 tools_MICU | 2826 | C |  | Liquid argon for welding. Mainly shared by CYH, Tunyi. | 45226 | 45230 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20833.42 | 0.99728 | 56.9 | 542.5 | -485.6 | 0 | [42 empty] | 0 | 0 |  | 3450 | 0 | 0 | 0 | 0 |  | 2419.26 | 0 | 0 | 1183.47 |  | 12202.99 |  |  |  | 591.25 |  | 986.45 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310095A | 20890.32 | F21P1-0404_H_labor for 50 tools_MICU | 2756 | C |  | Linde Liquid Argon | 45213 | 45219 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 20833.42 | 0.99728 | 56.9 | 348.75 | -291.85 | 0 | [41 empty] | 0 | 0 | 0 | 15224.61 | 2477.27 | 0 | 0 | 0 | 0 |  | 2486.74 | 0 | 0 | 0 |  | 0 | [5 empty] | 644.8 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309097A | 20890.32 | F21P1-0404_H_labor for 50 tools_MICU | 2570 | C |  | Refrigerated Liquid 2.2 & LC230 PSI. Cylinder Rent | 45185 | 45192 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 20890.32 | 1 | 0 | 620 | -620 | 0 | [40 empty] | 0 | 2055.16 | 9725.72 | 0 | 1027.58 | 0 | 0 | 0 | 0 | 0 |  | 2874.7 | 0 | 0 | 0 |  | 2960.5 |  | 2191.26 |  |  |  | 55.4 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2308002A | 20800 | Tool Interconnection Project (Main Tool & Module) | 352 | P |  | KPE601-t Hua Yi Construction Labor Pay | 45140 | 45149 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 20800 | 0 | 20800 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C021 | USCSB2404181A | 20797.71 | F21P1 KLA Interconnection | 4162 | C |  | ME: KKDB02: 10" EXHAUST DUCTING INSTALLATION | 45406 | 45411 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 20797.71 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 20797.71 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310134A | 20724.75 | F21P1-0404_H_labor for 50 tools_MICU | 2791 | C |  | Tool Hook UP Warehouse Storage Tool | 45219 | 45231 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 20724.75 | 0 | 20724.75 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2402275A | 20713 | F21P1-0404_H_Hallway plate install_MICU | 3700 | C | -01 | 2rd MMI ASML special barricade | 45351 | 2024/3/14 2024/4/17 | -1260 | 21973 |  |  |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | PO R1: Supplier agreed to remove overtime |  | Kuan-Chung Su | [11 empty] | 20713 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 20713 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Steel | Labor | USC21C009 | USCSB2402072A | 20700 | F21P1 WWT package (Installation and 2 batch tanks) | 3514 | C |  | WWT Blind Flange installation | 45330 | 45343 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 20700 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 20700 |  |  | 3105 |  |  |  | 3105 |  |  |  | 3105 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408058A | 20671 | F21P1 Module Tool Interconnection LIT2-3 | 4676 | C |  | Lit 3: KPE601-T: PFA Rework | 45517 | 45519 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 20671 | 20671 | 0 | 0 | [73 empty] | -
Hookup | Foundation | Labor |  |  | Others |  |  | USC22C028 | USCSB2210042A | 20638 | CAP_E_F21P1 Autoshelf Foundation | 1524 | C |  | auto shelf foundation installation | 44859 | 44859 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 11578 | 0.561 | 9060 | 0 | 9060 | 0 | [24 empty] | 8180 |  | 3398 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2306033A | 20600 | F21P1 Module Tool Interconnection DIF1-2 | 2068 | C |  | DIFF: STAINLESS STEEL TUBING FOR DOUBLE CASING CONNECTION | 45086 | 45101 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20600 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 11200 |  | 9400 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | DCR Scope | CDS | Chemical | Electrical | Labor | USC24C005 | USCSB2405131A | 20590 | Chemical & WCCS B Side Project | 4159 | C |  | F21P1A L30 Slurry VMB 訊號及氣源管拉設 | 45435 | 45451 | [6 empty] | DFK Tech, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 20590 | 0 | 20590 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405032A | 20403.36 | Tool Interconnection Project (Main Tool & Other Vendors) | 1090 | P |  | KEPST1-TEL INTERCONNECTS | 45419 | 45419 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 20403.36 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 20403.36 | [6 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401083A | 20316.7 | Tool Interconnection Project (Main Tool & Other Vendors) | 703 | P | -01 | ME: KKDB03: 10" Exhaust Ducting Installation | 2024/1/27 2024/4/6 | 2024/2/1 2024/4/10 | 16361.8 | 3954.9 |  |  | V |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: Addtl' hrs/days added. Broken down from preparing, install, & rental/materials. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20316.7 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 20316.7 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406155A | 20279.1 | F21P1-0404_H_labor for 50 tools_MICU | 4402 | C |  | Ryan Herco: Rental fee cover April and May. | 45473 | 45475 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 20279.1 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 20279.1 | [8 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312078A | 20260 | Tool Interconnection Project (Main Tool & Module) | 621 | P |  | KPAN02-S Labor | 45282 | 45288 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20260 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 20260 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2302009A | 20229.5 | F21P1 Module Tool Interconnection CMP1 | 1690 | C |  | EBARA chiller line hose material x 25 set | 44964 | 44965 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20229.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 18206.55 | 0 | [5 empty] | 2022.95 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2310151A | 20193.59 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2807 | C |  | Southwest Hand tool_0828 requirement_2 batch | 45223 | 45223 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20193.59 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 20193.59 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404017A | 20169 | Tool Interconnection Project (Main Tool & Other Vendors) | 972 | P |  | Manpower Pay for Delta Wye for Tool ID: KETRT2 Time cards 3.1, 3.4, 3.5, 3.7, 3.8, 3.11, and 3.16.2024 | 45385 | 45388 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 20169 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 20169 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408057A | 20168.8 | Tool Interconnection Project (Main Tool & Other Vendors) | 1203 | P |  | WIRE TCXH2/4G | 45527 | 45531 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 20168.8 | 20168.8 | 0 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2404179A | 20160.61 | F21P1 WWT package (Installation and 2 batch tanks) | 4160 | C |  | WWT Fittings for 60606_20240423 (A Side) | 45406 | 45411 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 20160.61 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 20160.61 | 3024.0915 |  |  |  | 3024.0915 |  |  |  | 3024.0915 |  | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C028 | USCSB2410021A | 20147.79 | CAP_E_F21P1 Autoshelf Foundation | 4964 | C |  | Additional Material needs for P1B AMHS 1/3,6/3,8/3,10/3 wire_3/3 batch | 45567 | [7 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 20147.79 | 0 | 20147.79 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2406125A | 20109.6 | WWT B side Project | 4364 | C |  | A區系統區閥件追加_球閥及接頭部分 | 45468 | 45476 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 20109.6 | 0 | 20109.6 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303084A | 20005.85 | F21P1 Module Tool Interconnection DIF1-2 | 1821 | C |  | KE air duct x19 | 45008 | 45013 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20005.85 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 20005.85 | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC24C005 | USCSB2407117A | 20000 | Chemical & WCCS B Side Project | 4532 | C |  | FAB A CDS-WCCS Permit Revision Change Order | 45492 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 20000 | 0 | 20000 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2208002A | 20000 | F21P1 UPW | 1441 | C |  | Signal Booster System installation | 44777 | 44778 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 20000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 20000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Steel | M+L | USC21C003 | USCSB2210051A | 20000 | F21P1 UPW | 1533 | C |  | F21P1-FAB LB2-LOOP 2 STAGE modifications | 44862 | 44867 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 20000 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 19000 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 1000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2305035A | 20000 | F21P1 WWT package (Installation and 2 batch tanks) | 1958 | C |  | Shermco Special Inspection | 45056 | 45061 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved | This is an open PO |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18895 | 0.94475 | 1105 | 0 | 1105 | 0 | [33 empty] | 1950 |  | 8700 |  | 8245 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2307040A | 19961 | F21P1 Chemical & WCCS package | 2209 | C |  | Pure Plastics Pipe Supports | 45118 | 45145 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19961 | 1 | 0 | 0 | 0 | 998.05 | [38 empty] | 12974.65 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 5988.3 | 0 | 0 | 0 |  | 0 |  |  |  |  | 19961 | 998.05 | [8 empty] | 0 |  | - | 0 | 0 | 998.05
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C032 | USCSB2310050A | 19920 | F21_AZQR_Hookup_ Interconnection | 2710 | C |  | QR: CHAD/FAD LABS: INTERCONNECT & CHILLERS FOR 9 TOOLS | 45206 | 45212 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 19920 | 0 | 19920 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Civil | M+L | USC24C006 | USCSB2408015A | 19907.14 | WWT B side Project | 4611 | C |  | RE: 8 CTI Stripper Pad duct flange sealing with Vinyl | 45507 | 45532 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 19907.14 | 18911.79 | 995.35 | [74 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2401069A | 19881 | F21P1-0423_H_T&M Hardware_MICU | 3258 | C |  | 第四批短期需求用料[MIC代採購_T&M] | 45302 | 45308 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 19881 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 159.3 |  | 15293.85 | 3516.8 | 0 |  | 911.05 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2304054A | 19844.7 | Tool Hookup Material (UPW&Chemical) | 1893 | C |  | HK Chemical C-PVC-Adaptor | 45036 | 45040 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | Replace item #1 & #2 in Harrington WO USCSB2210030A |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 19844.7 | 0 | 19844.7 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C021 | USCSB2404070A | 19820 | F21P1 KLA Interconnection | 4062 | C |  | ME: MULTIPLE TOOLS: MANPOWER FOR APRIL 1ST - 26TH 2024 | 45390 | 45422 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 6982.5 | 0.3523 | 12837.5 | 0 | 12837.5 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 6982.5 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2404185A | 19800 | F21P1 UPW | 4166 | C |  | FAB A UPW Observation (LB1 to L30) | 45407 | 45413 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 19800 | 5900 | 13900 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312046A | 19800 | F21P1-0404_H_labor for 50 tools_MICU | 3039 | C |  | PowerStudies, Inc. agrees to furnish training materials and an instructor to teach the Low Voltage Qualified (Arc Flash and NFPA 70E) | 45267 | 45274 | [6 empty] | PowerStudies, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 19800 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 19800 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2311001A | 19800 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2856 | C |  | EUV Foundation Drilling and Tapping | 45231 | 45259 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 19800 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 19800 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | NUUO | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Electrical | M+L | USC22C019 | USCSB2401074A | 19800 | AMC monitor 595T0 | 3263 | C |  | F21 AMC Reroute and retest fiber engineering | 45303 | 45359 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 17622.5 | 0.89003 | 2177.5 | 0 | 2177.5 | 2177.5 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 17622.5 |  | 0 | [14 empty] | 594 |  | - | 594 | 0 | 0 | 989.5
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409057A | 19737.03 | TSMC Fab 21 P1B Tool Hook Up | 4853 | C |  | Ladder for P1-B project, tool hookup team | 45552 | 45555 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 19737.03 | 0 | 19737.03 | 0 | [73 empty] | -
Base-Build | Pipeline | Material |  |  | Water Line | Civil | M+L | USC21C010 | USCSB2309001A | 19674 | tsmc AZ sewer and water pipeline installation | 2479 | C |  | Fire Hydrant Remove and Replace | 45170 | 45197 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19674 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 19674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical |  | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC24C005 | USCSB2405100A | 19650 | Chemical & WCCS B Side Project | 4119 | C |  | FAB A and Lorry Chemical Electrical Special Observations | 45428 | 45433 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | [14 empty] | 7962.5 | 0.40522 | 11687.5 | 3422.5 | 8265 | 0 | [56 empty] | 0 | [5 empty] | 2197.5 |  |  | 19650 |  |  | 4472.5 |  |  |  | 1292.5 | - |  |  | 0
Base-Build | UPW | MIMO/Rigging | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2309042A | 19635 | F21P1 UPW | 2519 | C |  | MMI temp resin move-in | 45181 | 45217 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 19635 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 15295 | 0 |  | 4340 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG | Labor |  |  | Others |  |  | USC22C003 | USCSB2306105A | 19560 | TSMC Fab21 Project Phase 1 EDG Package | 2138 | C |  | TSMC Relay Testing | 45099 | 45104 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved | Back Charge to Customer with 8% Mark-up |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 19560 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 19560 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2405124A | 19560 | F21P1 Chemical & WCCS package | 4152 | C |  | A side Scaffolding building-Waste PVDF Submain add support | 45434 | 45435 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 19560 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 19560 |  |  | - |  |  | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2307024A | 19539 | F21P1 Chemical & WCCS package | 2196 | C |  | L10 Equipment Relocation | 45114 | 45145 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19539 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 19539 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310044A | 19455 | Tool Interconnection Project (Main Tool & Module) | 462 | P |  | labor Invoice for Netcome | 45219 | 45224 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 19455 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 19455 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209007A | 19396.88 | F21P1 Chemical & WCCS package | 232 | P0 |  | AECC License | 44825 | 44826 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 19396.88 | 1 | 0 | 0 | 0 | 0 | 19396.88 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2210007A | 19391.15 | F21P1 UPW | 1491 | C |  | Horiba Conductivity/Resistivity Meter Batch 3 | 44838 | 44838 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved | Replace part of USC2111003A scope (same request for USCSB2209011A but different batch because of lead time) | 100% after goods arrival date-T/T 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 19391.15 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 19391.15 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312052A | 19372 | Tool Interconnection Project (Main Tool & Module) | 598 | P |  | KPOCS3-S Labor | 45274 | 45275 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 18403.4 | 0.95 | 968.6 | 0 | 968.6 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 18403.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2309122A | 19368 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2594 | C | -02 | Genesis Technology Cabling Install OFC Office Build | 2023/9/21 2023/11/30 | 2023/10/3 2023/12/5 2023/12/12 | -13263 | 32631 |  |  |  | V | Genesis Technology (USA) Inc. | PR Approved | PO Approved | PO R2:Warranty Correction PO R1: There was a reduced work scope involving the original quote and approved W.O A-02: Change Warranty |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 19368 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 19368 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405045A | 19357.3 | Tool Interconnection Project (Main Tool & Other Vendors) | 1087 | P |  | KDSNB1- SHIB INTERCONNECTS | 45426 | 45426 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 19357.3 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 19357.3 | [10 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402088A | 19311 | F21P1-0404_H_labor for 50 tools_MICU | 3529 | C |  | HOS90190 "KLAM" hose25' X 1-1/2" w/ male & female ends, for gas 300 tools, tool hookup team | 45331 | 45357 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 19311 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 19311 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402048A | 19203.58 | Tool Interconnection Project (Main Tool & Other Vendors) | 768 | P |  | 01/29: PREPARE TO INSTALL DUCT WORK. | 45329 | 45331 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 19203.58 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 19203.58 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Material | USC21C013 | USCSB2304044A | 19170 | F21P1 AMC THC Monitoring System | 1884 | C |  | Regulator | 45034 | 45035 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 19170 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 3220 | 0 | 0 | 6220 | 0 | 9155 | 0 | 575 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2308150A | 19131 | F21P1 Module Tool Interconnection ETC1-3 | 2445 | C |  | KESDA1 Time and Material pricing for work related to the ETC iPUP Mechanical scope | 45162 | 45180 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19131 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 19131 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2311023A | 19131 | F21P1 Module Tool Interconnection ETC1-3 | 2878 | C |  | KEMEA5 ETC iPUP Mechanical R2 | 45234 | 45241 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 19131 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 19131 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2308122A | 19131 | F21P1 Module Tool Interconnection ETC1-3 | 2419 | C |  | Greenberry’s Time and Material pricing for work related to the ETC iPUP Mechanical s | 45157 | 45160 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18174.45 | 0.95 | 956.55 | 0 | 956.55 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 13478.6 | 0 | 4695.85 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403144A | 19090.8 | F21P1 WWT package (Installation and 2 batch tanks) | 3844 | C |  | WWT - Field-12 Rental for (120 days) | 45365 | 45369 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 16227.18 | 0.85 | 2863.62 | 0 | 2863.62 | 4581.792 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 2863.62 | 6522.69 |  | 4931.79 | 2863.62 |  |  | 4772.7 | 2863.62 |  | 2290.896 |  | - | 2290.896 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2312002A | 19082.4 | Tool Hookup Material (UPW&Chemical) | 2997 | C |  | HK Chemical PVDF HP Adaptor | 45261 | 45266 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 19082.4 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 19082.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2401115A | 19000 | F21P1 WWT package (Installation and 2 batch tanks) | 3302 | C |  | FRP repair Fab LB2/WRC | 45308 | 45310 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 19000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 19000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408012A | 18958.46 | Tool Interconnection Project (Main Tool & Other Vendors) | 1183 | P |  | KIHIB2: EXHAUST, SIGNAL & POWER CABLE INSTALL | 45514 | 45531 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 18958.46 | 0 | 18958.46 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2306093A | 18948.56 | F21 TMAH System | 2126 | C |  | WWT-MU-PVC Sparger | 45098 | 45125 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 18948.56 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 11352.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7596.06 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407073A | 18936 | WWT B side Project | 4490 | C |  | WWT CrPVC pipes for dump | 45486 | 45488 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 18936 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 | 18936 | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404007A | 18932.5 | WWT B side Project | 4003 | C |  | WWT Bside clamp / Copperstate 1st order | 45384 | 45385 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 18932.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1833.05 |  | 0 |  | 3874.3 |  | 9085.15 | 2839.875 | 4140 |  |  | 2839.875 |  |  |  | 2839.875 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2212052A | 18929.75 | F21P1 UPW | 1623 | C |  | 12/3C w/ Ground BOYG | 44926 | 44926 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 18929.75 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 18929.75 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2402218A | 18902.9 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3645 | C |  | RS PAYROLL SERVICES, TIMECARD PAYMENT FOR ASSOCIATES | 45344 | 45348 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 9384.53 | 0.49646 | 9518.37 | 9518.37 | 0 | 0 | [52 empty] | 9384.53 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC21C007 | USCSB2405022A | 18856.6 | F21P1 VOC package （Installation ) | 3994 | C |  | F21 P1 parking gates installation-(9/11) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 18856.6 | 0 | 18856.6 | 17913.77 | [54 empty] | 0 |  | 0 | [14 empty] | 17913.77 |  | - |  | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309018A | 18840 | WWT Change Order (Piping) | 2495 | C |  | WWT -LJ-Miniplast | 45176 | 45181 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 17064.92 | 0.90578 | 1775.08 | 0 | 1775.08 | 3803.1616 | [40 empty] | 0 | 0 | 0 | 1215.6 |  | 6284.92 | 0 | 0 | 0 | 0 | 6082.2 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 1358.272 | 3482.2 | - | 1358.272 | 1086.6176 | 0 | 0
Base-Build | VOC THC | Material | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | M+L | USC21C013 | USCSB2311089A | 18831 | F21P1 AMC THC Monitoring System | 2941 | C |  | F21 P1 VOC WWT line temporary support and THC ICA tack of point valves engineering | 45247 | 45251 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18831 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 18831 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | DCR Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2305081A | 18824 | F21P1 Chemical & WCCS package | 2002 | C |  | Modify CDS DHL EQ caster wheels | 45064 | 45071 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 18824 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 18824 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C009 | USCSB2312110A | 18788.56 | F21P1 WWT package (Installation and 2 batch tanks) | 3100 | C |  | CDS ICP Mass CDA GN2 regulators and parts to fix design issue by John Wu | 45276 | 45279 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 18788.56 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 18788.56 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2401148A | 18769.66 | F21P1 WWT package (Installation and 2 batch tanks) | 3333 | C |  | WWT-Weld machines rental for PSS | 45310 | 45315 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 18769.66 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 18769.66 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2403143A | 18760.63 | F21P1-0404_H_Hallway plate install_MICU | 3843 | C |  | RS Payroll Onsite Manpower General Labor Foundations | 45365 | 45385 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 18760.63 | 18760.63 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401198A | 18735.37 | F21P1-0404_H_labor for 50 tools_MICU | 3383 | C |  | UPW hardware for JACO, customized hose connector, tool hook up team | 45316 | 45323 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 18735.37 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 18735.37 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2208004A | 18706.07 | F21P1 Chemical & WCCS package | 1442 | C |  | PFA Tubing | 44783 | 44785 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | USCSB2205023A change order | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 18706.07 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 18706.07 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401103A | 18680.22 | F21P1-0404_H_labor for 50 tools_MICU | 3290 | C |  | Cord grip locknut O-Ring for HK Power trade | 45306 | 45307 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 18679.04 | 0.99994 | 1.18 | 0 | 1.18 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 18031.6 | 0 |  | 0 | [5 empty] | 647.44 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Scaffolding |  |  | Others |  |  | USC24B002 | USC2405004A | 18654 | Tool Interconnection Project (Main Tool & Other Vendors) | 1063 | P |  | KCSOA6/Scaffold Tag 111966/3-11-2024 | 45416 | 45419 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 18654 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 18654 |  |  |  |  | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407056A | 18642.08 | TSMC Fab 21 P1B Tool Hook Up | 4454 | C |  | P1B EEW PPE for HK Power for 100 tools | 45484 | 45498 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 10029.42 | 0.538 | 8612.66 | 0 | 8612.66 | 0 | 3240 | [67 empty] | 6789.42 |  |  |  |  | - |  |  | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2406028A | 18603.07 | Chemical & WCCS B Side Project | 4254 | C |  | F21P1 B Side material CED - Eletrical/Signal | 45448 | 45448 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 13207.27 | 0.70995 | 5395.8 | 18363.25 | -12967.45 | 0 | [73 empty] | 13207.27 |  |  | 0
Base-Build | CCTV | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2403188A | 18599.9 | F21P1 QR Lab Security & CCTV | 3885 | C |  | F21 P1 Gown Office IT Room speed gate | 45370 | 45370 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 18599.9 | 17669.91 | 929.99 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 17670 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C013 | USCSB2304043A | 18531 | F21P1 AMC THC Monitoring System | 1883 | C |  | Gas Cylinder | 45034 | 45035 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18531 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 9295 | 0 | [5 empty] | 2480 | 0 | 0 | 5706 | 0 |  | 0 | 1050 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2210040A | 18500 | F21P1 WWT package (Installation and 2 batch tanks) | 1522 | C |  | Blind Flanges for Hydrostatic Testing | 44855 | 44859 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 18500 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 17575 |  | 925 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C035 | USCSB2410014A | 18491.95 | TSMC F21 Heating Jacket Installation | 4958 | C |  | 400 CGB's for distribution panels. 8 addtional panels not part of orginal scope And DP changes _AMHS | 45567 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 18491.95 | 0 | 18491.95 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2302025A | 18480 | F21P1-0404_H_Hallway plate install_MICU | 1706 | C |  | Wet foundation modification | 44967 | 44985 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 18480 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 9240 |  |  | 0 |  |  |  | 9240 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C014 | USCSB2308105A | 18434.62 | F21P1 AMHS Power Panel | 2402 | C |  | AMHS L40 Relocation | 45156 | 45162 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 10529.16 | 0.57116 | 7905.46 | 0 | 7905.46 | 0 | [40 empty] | 10529.16 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409030A | 18366.75 | Tool Interconnection Project (Main Tool & Other Vendors) | 1232 | P |  | Fire Retardant Snap Tubing 50m Grey | 45549 | 45554 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 18366.75 | 0 | 18366.75 | 0 | [73 empty] | -
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2310067A | 18240 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2728 | C |  | Hua Yi Construction Az General Labor Costs for Material Handling & Moving Supplies | 45210 | 45212 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 18240 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 18240 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401108A | 18235.74 | F21P1-0404_H_labor for 50 tools_MICU | 3295 | C |  | HK power trade materials | 45307 | 45308 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 17138.84 | 0.93985 | 1096.9 | 1096.9 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 6679.8 |  | 4104.61 |  |  |  | 6354.43 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical Lab | MIMO/Rigging | The budget execution does not pertain to this project | Chemical Lab | Chemical | Mechanical | Labor | USC22C021 | USCSB2305041A | 18220 | F21P1 Chemical Lab setup | 1966 | C |  | GC Lab Move-in | 45057 | 45068 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 18220 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 18220 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303026A | 18182.84 | F21P1 Module Tool Interconnection DIF1-2 | 1768 | C |  | F21P1 DIF1 3 VMB cable and ethernet cable | 44992 | 45007 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 18182.84 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 9750 |  | 8432.84 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Equipment | 0 | 0 | Chemical | Electrical | Material | USC21C009 | USCSB2312114A | 18142.08 | F21P1 WWT package (Installation and 2 batch tanks) | 3104 | C |  | USC21C006 SLURRY A&B SIDE HUB BOX | 45276 | 45282 | [6 empty] | Avex-SG Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 18142.08 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 18142.08 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405146A | 18097.34 | WWT B side Project | 4170 | C |  | WWT Fittings_20240523 (B Side) | 45436 | 45441 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 18097.34 | 1 | 0 | 0 | 0 | 1522.612 | [66 empty] | 1673.2 |  | 16424.14 |  |  | 1522.612 |  | - | 0 | 0 | 0 | 0
Hookup | Interconnection | Material |  |  | Others |  |  | USC23C002 | USCSB2312025A | 18089.81 | F21P1-0404_H_Hallway plate install_MICU | 3018 | C |  | ASML Special barricade for TSMC EUV team | 45265 | 45365 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 18089.81 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 18089.81 | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303071A | 18068.39 | F21P1 WWT package (Installation and 2 batch tanks) | 1810 | C |  | Bolts/Gaskets | 45002 | 45008 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 16095.52 | 0.89081 | 1972.87 | 0 | 1972.87 | 1770.5072 | [28 empty] | 0 | 4256.94 |  |  |  | 0 | 11838.58 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 542.0517 |  |  |  | 542.0517 |  | 804.776 |  | - | 965.7312 | 0 | 0 | 0
Base-Build | VOC |  |  |  | Low Voltage | Electrical | M+L | USC22C019 | USCSB2409015A | 17971.39 | AMC monitor 595T0 | 4785 | C |  | F21 P1 VOC Electricity Change Order _CO#30_Batch 2/2 | 45539 | 9/7/2024 9/12/2024 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | PO R1: Revise Payment Term in Remark | [13 empty] | 17971.39 | 1 | 0 | 17971.39 | -17971.39 | 0 | [73 empty] | 17971.39
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2401257A | 17961 | WWT Change Order (Piping) | 3437 | C |  | WWT Supplemental Material&WWT Premium Time 11.25-11.26 | 45322 | 45325 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 17961 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 17063 | 0 | 0 |  | 0 |  | 898 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Triazole | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC22C022 | USCSB2404032A | 17944 | F21P1 Triazole treatment system | 4028 | C |  | copper tubing | 45385 | [8 empty] | PR Approved | PO Processing |  |  | 0 | [11 empty] | 0 | 0 | 17944 | 0 | 17944 | 21532.8 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 8972 |  | - | 5383.2 | 5383.2 | 1794.4 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2301004A | 17936.33 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1627 | C |  | Harrington PVC&PVDF MICU F21 TOOL | 44931 | 44937 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 17936.33 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 17936.33 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2210001A | 17880.48 | F21P1 Chemical & WCCS package | 246 | P0 |  | Dell Laptop/Dell 27in Monitor | 44835 | 44848 | [6 empty] | Dell Technologies | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 17880.48 | 1 | 0 | 0 | 0 | 0 | 17880.48 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2308159A | 17850 | F21P1 UPW | 2453 | C |  | Horiba Resistivity Meter B Side | 45164 | 45166 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 17850 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 17850 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2308051A | 17818.4 | F21_AZQR_Hookup_ Interconnection | 2349 | C |  | QRLAB: Special request per TSMC. Installing conduit/tray for LAN cables for PCs in the QR Labs area. | 45147 | 45164 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16339.96 | 0.91703 | 1478.44 | 0 | 1478.44 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 8669.18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 7670.78 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2302004A | 17800 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1685 | C |  | Teardown and relocation | 44959 | 44963 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 17800 | 0 | 17800 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C013 | USCSB2310096A | 17710 | F21P1 AMC THC Monitoring System | 2757 | C | -01 | Puressuring testing certificat for THC (A+B) and AMC (B) | 45216 | 2023/10/20 2023/10/23 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | PO R1: Remark Information Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6722 | 0.37956 | 10988 | 0 | 10988 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1422 |  |  | 0 | 0 | 0 |  | 0 |  | 5300 | [14 empty] | - | 0 | 0 | 0
Non-TSMC | FMCS | Material |  |  | Others |  |  | USC22C007 | USCSB2312124A | 17635 | TSMC F21 FMCS Installation | 3115 | C |  | Strand fiber SM armored cables | 45276 | 45279 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 17635 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 17635 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2312070A | 17619.4 | WWT Change Order (Piping) | 3062 | C |  | MU/Hand welding machines for WWT | 45272 | 45294 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 17619.4 | 0 | 17619.4 | 17619.4 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 2642.91 |  |  |  | 2642.91 |  |  |  | 2642.91 |  | 5285.82 |  | - | 5285.82 | 7047.76 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306027A | 17610 | Tool Interconnection Project (Main Tool & Module) | 312 | P |  | KPOCS1 LIT 3 SCREEN ALVARADO - LABOR | 45085 | 45096 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 17600 | 0.99943 | 10 | 0 | 10 | 0 | [33 empty] | 0 | 17600 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2402167A | 17594.31 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3598 | C | -01 | RMF hole penetration repairs | 45339 | 45370 | -2168.57 | 19762.88 |  |  |  |  | Greenberry Industrial | PR Approved | PO Approved | R1:Lower manhour negotiated |  | Tiong Sheng Poh | [11 empty] | 17594.31 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 17594.31 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403264A | 17575 | F21P1-0404_H_labor for 50 tools_MICU | 3957 | C |  | Locknut, tapes, and ties for HK Power system | 45378 | 45392 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 17575 | 1 | 0 | 10548.17 | -10548.17 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 20 |  |  | 0 | 7006.83 | 10548.17 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C021 | USCSB2404102A | 17561.15 | F21P1 KLA Interconnection | 4089 | C |  | ME: KPIN01: INSTALL GEX L20 TO L30 & CABLE PULLS | 45394 | 45412 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 17561.15 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 17561.15 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2308040A | 17524.98 | F21P1-0404_H_Hallway plate install_MICU | 2338 | C |  | Swap 1000 pcs tiles from Greenberry | 45146 | 45149 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 12852.82 | 0.7334 | 4672.16 | 0 | 4672.16 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 12852.82 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2308183A | 17523 | F21P1 Module Tool Interconnection CVD | 2476 | C |  | Greenberry T&M for CVD Vent Line Retrofit | 45169 | 45187 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 17523 | 0 | 17523 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2201006A | 17494.8 | F21P1 WWT package (Installation and 2 batch tanks) | 1323 | C | -01 | Modular Pipe Support Assembly Design | 2022/1/19 2022/2/25 | 2022/1/27 2022/2/25 | 6394.8 | 11100 | V | V |  | V | The Blackfin Group | PR Approved | PO Approved | Scope increase because of TSMC design change | 25% at kickoff-net 30 days; 75% submission of draft report-net 30 days-after acceptance; T&M billed on a monthly basis (with supporting timesheets) | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT |  |  |  | Y |  |  | 17494.8 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 17494.8 | [21 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2408067A | 17493.45 | WWT B side Project | 4683 | C |  | WWT_ Copper Tube request for B side_茂迅 | 45519 | 45520 | [6 empty] | SWIFT ENGINEERING CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 17493.45 | 0 | 17493.45 | 0 | [73 empty] | -
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2310054A | 17352 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2714 | C |  | TSMC High Speed Door Frame at L30 | 45209 | 45212 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 17352 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 17352 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405048A | 17350.06 | Tool Interconnection Project (Main Tool & Other Vendors) | 1090 | P |  | KDCCS2-DNS SCREEN INTERCONNECTS | 45426 | 45426 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 17350.06 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 17350.06 | [10 empty] | - |  |  | 0
Base-Build | VOC | MMI | DCR Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC21C012 | USCSB2310091A | 17329 | F21 Barcode RFID System | 2752 | C |  | VOC Unistrut Support | 45213 | 45219 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 17329 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 4750 |  | 7596.91 | 0 | 0 |  | 0 |  | 4982.09 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2304061A | 17304.2 | F21P1-0404_H_Hallway plate install_MICU | 1900 | C |  | KXME02 Foundation Installation | 45037 | 45051 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 16438.99 | 0.95 | 865.21 | 0 | 865.21 | 0 | [33 empty] | 0 | [6 empty] | 16438.99 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MIMO/Rigging | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2307039A | 17300 | F21P1 Chemical & WCCS package | 2208 | C |  | CO2 Cylinder Move In | 45118 | 45144 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 17300 | 1 | 0 | 1730 | -1730 | 1730 | [38 empty] | 12110 |  | 0 | 0 | 3460 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 1730 | 0 | 0 | 1730
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2311042A | 17280 | F21P1 WWT package (Installation and 2 batch tanks) | 2897 | C |  | install Dikewall around Tank 1985AA | 45239 | 45240 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 17280 | 1 | 0 | 0 | 0 | 820.8 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 16416 | 0 | 0 | 0 |  | 0 | [13 empty] | 864 | 0 |  | - | 0 | 0 | 0 | 820.8
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Electrical | Instrument | USC21C003 | USCSB2406016A | 17250 | F21P1 UPW | 4242 | C |  | WWT B Side Battery Recharge 2_R2 | 45446 | 45448 | [6 empty] | Gruber Industries | PR Approved | PO Approved | [14 empty] | 17250 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 17250 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405141A | 17198 | Tool Interconnection Project (Main Tool & Other Vendors) | 1116 | P |  | KCSCN5 4/18/24 Scaffold Tag 111733 | 45436 | 45443 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 17198 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 17198 |  |  | - |  |  | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2312169A | 17134.38 | F21P1 UPW | 3157 | C |  | UPW-XHHW500YELcable | 45282 | 45282 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 17134.38 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 17134.38 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2310072A | 17008 | F21P1 UPW | 2733 | C |  | UPW-UMEC-L20-Enermech-repair | 45211 | 45218 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 17008 | 0 | 17008 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 17008 | [7 empty] | 16157.6 |  | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C059 | USCSB2404037A | 17001.18 | F21P1 Foundation T&M | 4032 | C |  | tools for HK PPL trade | 45385 | 45429 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | [14 empty] | 17001.18 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 14173.78 |  | 2827.4 |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Labor |  |  | Others |  |  | USC23C032 | USCSB2311120A | 16992 | F21_AZQR_Hookup_ Interconnection | 2971 | C |  | EBO: CHAD/FAD LABS - CHANGE ORDER OF THE ORIGINAL CONTRACT C23331D | 45258 | 45259 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 16992 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 16992 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | DCR Scope | CDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2405039A | 16900 | F21P1 Slurry package | 4048 | C |  | CDS B side move in Night shift | 45420 | 45430 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 8450 | 0.5 | 8450 | 0 | 8450 | 0 | [56 empty] | 0 | [8 empty] | 16900 | 8450 | [6 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308024A | 16900 | Tool Interconnection Project (Main Tool & Module) | 374 | P |  | KPE601-S Trident Labor Pay | 45167 | 45184 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16900 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 16900 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USC2404045A | 16889.74 | F21P1 AMAT Interconnection | 999 | P |  | 2,4,6,8,10,12 AWG lug | 45391 | 45393 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 16889.74 | 1 | 0 | 1763.62 | -1763.62 | 0 | [52 empty] | 0 | 0 | 0 |  | 10754.54 |  | 4371.58 | [12 empty] | 0 |  | 1763.62 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2401250A | 16794.97 | F21P1 WWT package (Installation and 2 batch tanks) | 3431 | C |  | FAB A&B labels | 45321 | 45336 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 16767.03 | 0.99834 | 27.94 | 0 | 27.94 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 16767.03 |  | 0 |  |  |  |  | 2519.2455 |  |  |  | 2519.2455 |  |  |  | 2519.2455 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309021A | 16780 | Tool Interconnection Project (Main Tool & Module) | 411 | P |  | labor for install PCW&ACC insulation | 45191 | 45209 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 15941 | 0.95 | 839 | 0 | 839 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 15941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402062A | 16774 | Tool Interconnection Project (Main Tool & Other Vendors) | 780 | P |  | KPOV14, KKSS01, KPSP08: CABLE PULL | 45336 | 45338 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 14858 | 0.88578 | 1916 | 0 | 1916 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 14858 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C006 | USCSB2404040A | 16768.8 | F21P1 Slurry package | 4035 | C |  | Rent 2 IR units for 2 months | 45385 | 45387 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 15232.05 | 0.90836 | 1536.75 | 0 | 1536.75 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 10900 | 13072.76 | [5 empty] | 0 | 4332.05 | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405026A | 16764.53 | Tool Interconnection Project (Main Tool & Other Vendors) | 1085 | P |  | KRWRS2 - rework-DNS SCREEN INTERCONNECTS | 45419 | 45419 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 16764.53 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 16764.53 | [10 empty] | - |  |  | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Material | USC24C005 | USCSB2407042A | 16608.23 | Chemical & WCCS B Side Project | 4441 | C |  | EES 防爆接線盒0708 | 45482 | 45483 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 16608.23 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 16608.23 |  |  | - |  |  | 0
Non-TSMC | EDG | Labor |  |  | Others |  |  | USC22C003 | USCSB2206005A | 16600 | TSMC Fab21 Project Phase 1 EDG Package | 1396 | C |  | TSMC F21P1 EDG Package Additional City Requirements | 44715 | 44718 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 16600 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 6721 |  | 5515.5 |  |  |  |  | 0 | 621 |  |  | 3742.5 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2308149A | 16574.85 | F21P1 Chemical & WCCS package | 2444 | C |  | Lorry FNDP room parts for Chemical welding. | 45162 | 45163 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 16256.48 | 0.98079 | 318.37 | 0 | 318.37 | 0 | [40 empty] | 0 | 16256.48 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 318.37 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC |  |  |  | Low Voltage | Electrical | M+L | USC21C007 | USCSB2409009A | 16567.6 | F21P1 VOC package （Installation ) | 4779 | C |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 2/6 | 45539 | 45542 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 16567.6 | 1 | 0 | 16567.6 | -16567.6 | 0 | [73 empty] | 16567.6
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405082A | 16564 | Tool Interconnection Project (Main Tool & Other Vendors) | 1103 | P |  | Payment for Materials: 1. Supply fittings 1’’ and above per BOM for KPE606-S | 45429 | 45435 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 16564 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [13 empty] | 16564 |  |  | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2210013A | 16496.16 | F21P1 WWT package (Installation and 2 batch tanks) | 1496 | C |  | F21P1 WWT urgent Hardware | 44840 | 44848 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  | 100% by received-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 16496.16 | 1 | 0 | 0 | 0 | 0 | [19 empty] | 16496.16 | [8 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2408030A | 16465.8 | WWT B side Project | 4625 | C |  | WWT_ Copper Tube request for B side. | 45512 | 45512 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 16423.9 | 0.99746 | 41.9 | 0 | 41.9 | [71 empty] | 13294.8 |  | 3129.1 | -
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401130A | 16456.78 | F21P1-0404_H_labor for 50 tools_MICU | 3316 | C |  | equipment for all systems, Tool hook up team | 45309 | 45310 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 16456.78 | 1 | 0 | 0 | 0 | 0 | 16456.78 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2402024A | 16456.08 | WWT Change Order (Piping) | 3467 | C |  | WWT A side remaining unistrut 2024.1E1 | 45324 | 45324 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 16456.08 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 | 16456.08 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | CO Scope (adding/additional scope) | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303040A | 16297.34 | F21P1 WWT package (Installation and 2 batch tanks) | 1782 | C |  | T140 discharge loop | 44994 | 45091 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16297.34 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 16297.34 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Civil | M+L | USC21C009 | USCSB2302006A | 16264 | F21P1 WWT package (Installation and 2 batch tanks) | 1687 | C |  | Stripper Pad Dike Modification | 44960 | 44972 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 15428 | 0.9486 | 836 | 0 | 836 | 771.4 | [28 empty] | 0 |  |  |  |  | 0 | 15428 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 771.4
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2408073A | 16231.48 | F21P1 AMAT Interconnection | 4689 | C |  | INT--AMAT--CGS(Mar.&Apr.) | 45519 | 45523 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 16231.48 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 16231.48 |  |  | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406013A | 16215.26 | Tool Interconnection Project (Main Tool & Other Vendors) | 1133 | P |  | KDBCS1 - rework (change order)-DNS SCREEN INTERCONNECTS-5/1-5/8/2024 | 45461 | 45462 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 16215.26 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 16215.26 | [6 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403094A | 16213.05 | Tool Interconnection Project (Main Tool & Other Vendors) | 910 | P |  | KEPST2 -TEL INTERCONNECTS - Labor 3/2-3/15/2024 | 45372 | 45377 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 16213.05 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 16213.05 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2308018A | 16204.5 | Tool Interconnection Project (Main Tool & Module) | 368 | P |  | 2-1/2 SS S10 304L A312 WELD PIPE (FERGUSON WILL PAY FOR THE FREIGHT) | 45163 | 45180 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16204.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 16204.5 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | The budget execution does not pertain to this project | Shared Cost | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2403230A | 16203.5 | F21P1 WWT package (Installation and 2 batch tanks) | 3786 | C |  | CGS Global Support Onsite Manpower Tent 1 | 2024/3/22 2024/6/19 | 45491 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | RPR R1::Updated budget cost. | [13 empty] | 0 | 0 | 16203.5 | 0 | 16203.5 | 16203.5 | [71 empty] | 8101.75 |  | - | 8101.75 | 0 | 0 | 0
Base-Build | Chemical | MIMO/Rigging | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2309132A | 16203 | F21P1 Chemical & WCCS package | 2603 | C |  | CDS L30 Panel Move-in and install. | 45190 | 45197 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 16203 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 2000 | 0 | 13392.85 | 0 | 0 | 0 |  |  | 810.15 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USC2210017A | 16201 | F21P1 WWT package (Installation and 2 batch tanks) | 259 | P |  | WRC Chem Room Epoxy | 44854 | 44855 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 16201 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 15391 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 810 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307021A | 16188.11 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2193 | C |  | 羿軍 hand tool | 45113 | 45113 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 16188.11 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 16188.11 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401013A | 16183.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 637 | P |  | 1 1/4" S/10S LR 90 A/SA 403 WP 304/L-W | 45302 | 45323 | [6 empty] | Industrial Pipe and Valve Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 16183.32 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 16183.32 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2308160A | 16181 | F21P1 Chemical & WCCS package | 2454 | C |  | TSMC drum car*5 and Flush car*2 | 2023/8/26 2023/10/17 | 45217 | [6 empty] | Yu Cheng Kid Enterprise Co., | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 16181 | 0 | 16181 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405042A | 16050.64 | Tool Interconnection Project (Main Tool & Other Vendors) | 1084 | P |  | KDSTS6-rework DNS SCREEN INTERCONNECTS | 45426 | 45427 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 16050.64 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 16050.64 | [10 empty] | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2310090A | 16013.95 | F21P1 Chemical & WCCS package | 2751 | C |  | CDS Hardware for YaoHong work at Lorry FNDP_2nd | 45213 | 45219 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 16013.95 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 16013.95 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG | Equipment |  |  | Others |  |  | USC22C003 | USCSB2306122A | 16009 | TSMC Fab21 Project Phase 1 EDG Package | 2155 | C |  | Herc cable rental | 45105 | 45112 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | Will be charge back to Fu Energy |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 16009 | 0 | 16009 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2403118A | 16000 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3820 | C |  | Support Safety Badges Check | 45363 | 45365 | [6 empty] | Mirador Construction Service, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 16000 | 0 | 16000 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | M+L | USC21C012 | USCSB2310105A | 16000 | F21 Barcode RFID System | 2767 | C |  | F21 P1 VOC WWT line engineering | 45216 | 45222 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 16000 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 16000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309119A | 15992 | F21P1 Chemical & WCCS package | 2591 | C |  | 90 deg Coax elbows. 2"x 1-1/2" be used by YaHo at Lorry FNDP. | 45189 | 45198 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15992 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 15992 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2312100A | 15967.75 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3091 | C | -01 | Copper State Bolt & Nut Co outstanding account invoices of materials | 45275 | 2023/12/18 2023/12/28 | 39.7 | 15928.05 | V |  |  |  | Copper State Bolt & Nut Company | PR Approved | PO Approved | PO R1: Tax amount change for invoice I05599590 and I05688809 |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 15967.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 15967.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2112006A | 15956.13 | F21P1 UPW | 1318 | C | -01 | Module office cabling Work | 2021/12/17 2022/1/27 | 2022/1/21 2022/2/9 | 998.13 | 14958 | V |  | V |  | Galaxy3 LLC | PR Approved | PO Approved | Revise the previous quote and price with the new one due to additional internet AP | 100% by progress, Net 30days (after acceptance). | York Yeh |  |  | Yi-Hsin Lee | York Yeh | N |  | Matt |  | N |  |  | 15956.13 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 15956.13 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2311059A | 15916.8 | WWT Change Order (Piping) | 2914 | C |  | WWT 10T Termination Flange | 45244 | 45251 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15916.8 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 15916.8 |  |  |  |  | 2387.52 |  |  |  | 2387.52 |  |  |  | 2387.52 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | TMAH | Equipment | Main Contract Scope | WWT | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2401217A | 15912 | F21P1 WWT package (Installation and 2 batch tanks) | 3399 | C |  | TMAH expansion tank move in | 45317 | 45321 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 15912 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 15912 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404059A | 15886.72 | Tool Interconnection Project (Main Tool & Other Vendors) | 1012 | P |  | KSCBH4 Route and pull Cables install core hole sleeves/tray dividers | 45394 | 45399 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 15886.72 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 15886.72 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Mechanical | M+L | USC23C045 | USCSB2401189A | 15886 | WWT Change Order (Piping) | 3374 | C |  | WWT -24-096 Stripper Platform FRP Ducting Modifications Quote | 45314 | 45314 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 15886 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 15091.7 | 0 | 0 |  | 0 |  | 794.3 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409064A | 15825.25 | TSMC Fab 21 P1B Tool Hook Up | 4859 | C |  | MIC HK power team hardwareBrady ribbon and label for 200 tools | 45553 | 45554 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15825.25 | 0 | 15825.25 | 0 | [73 empty] | -
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2311136A | 15820 | EBO21- Tool interconnection | 2986 | C |  | EBO: ZASCS5-1: CABLE TRAY INSTALL | 45259 | 45265 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 15820 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 15820 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409043A | 15750 | Tool Interconnection Project (Main Tool & Other Vendors) | 1246 | P |  | RENTAL OF A IR 63 FOR 2 TOOLS FOR 45 DAYS | 45555 | 45560 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15750 | 0 | 15750 | 0 | [73 empty] | -
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC23C045 | USCSB2311005A | 15749 | WWT Change Order (Piping) | 2860 | C |  | TSMC CO Work for OBR to Install (2) Spacer on the Stripper Ducting. | 45231 | 45233 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15749 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 15749 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403099A | 15744.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 915 | P |  | Manpower Pay for Tool ID: KETRT9 for Delta Wye | 45373 | 45381 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 15744.5 | 0 | 15744.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | Main Contract Scope | UPW | UPW | Civil | M+L | USC21C003 | USCSB2401171A | 15718.13 | F21P1 UPW | 3356 | C |  | UPW-HKPs epoxy | 45314 | 45314 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15718.13 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 15718.13 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405075A | 15686.9 | Chemical & WCCS B Side Project | 4095 | C |  | CHEM_WCCS SUS project_LINDE_ ARGON, REFRIGERATED LIQUID*30pcs | 45423 | 45427 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 15536.12 | 0.99039 | 150.78 | 0 | 150.78 | 0 | [56 empty] | 0 | [5 empty] | 9847.96 |  | 2538.39 | 15686.9 | 3149.77 | [6 empty] | - |  |  | 0
Base-Build | UPW and Chemical | UMEC | The budget execution does not pertain to this project | Chemical | Chemical | Mechanical | M+L | USC21C005 | USCSB2402278A | 15659 | F21P1 Chemical & WCCS package | 3702 | C |  | CDS UPW - 8-189 TMAH Interface Modification L10 | 45351 | 45351 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 15659 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 14876 | 0 |  | 783 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402224A | 15633.2 | F21P1 WWT package (Installation and 2 batch tanks) | 3651 | C | -01 | WWT E2 missing material 202402 | 45345 | 2024/2/26 2024/2/29 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Trade Term Changes from DDP to FOB |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 15633.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2158.54 |  | 10274.66 |  | 3200 |  |  | 2344.98 |  |  |  | 2344.98 |  |  |  | 2344.98 |  | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC24C002 | USCSB2403145A | 15624.11 | [RM]F21 EUV Crane service contract | 3845 | C |  | Mennens Cleanroom Cranes EUV Crane Support Annual Inspections | 45365 | 45394 | [6 empty] | Mennens Cleanroom Cranes B.V. | PR Approved | PO Approved | WO amount € 13,582.69 (@1.1501) Pay in Euro, MICU hereby agrees to assume the responsibility of paying in Euro, thereby accepting the associated currency exchange risk. Furthermore, MICU acknowledges and agrees to cover any additional international wire transfer charges or fees that may accrue during the payment process. |  | Yikang Wang | [11 empty] | 13585 | 0.86949 | 2039.11 | 0 | 2039.11 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 13585 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2303019A | 15617 | F21P1-0404_H_Hallway plate install_MICU | 1761 | C |  | 10 single barricade | 44988 | 45013 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 15617 | 0 | 15617 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Heating Jacket | Material |  |  | Others |  |  | USC23C035 | USCSB2305060A | 15598.88 | TSMC F21 Heating Jacket Installation | 1982 | C | -01 | Heating Jacket | 2023/5/13 2024/2/16 | 2023/8/4 2024/2/17 | -2834401.12 | 2850000 |  |  | V | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | Descope and to be replaced by Kinpo Order for the same scope |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 15598.88 | 0 | 15598.88 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | 0 | Chemical | Steel | Material | USC21C009 | USCSB2401042A | 15598 | F21P1 WWT package (Installation and 2 batch tanks) | 3232 | C |  | CDS galvanized 4*4 cm-10ft(L) | 45299 | 45314 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 15598 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 15598 |  |  | 15598 | [6 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2211038A | 15565.24 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1571 | C |  | Cantilever Arms | 44895 | 44897 | [6 empty] | Toyotalift of Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 15565.24 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 8910.62 | [5 empty] | 0 | 6654.62 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2212024A | 15545.13 | F21P1 WWT package (Installation and 2 batch tanks) | 1597 | C |  | WWT Mini Line missing material | 44908 | 44914 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 15520.28 | 0.9984 | 24.85 | 0 | 24.85 | 0 | [28 empty] | 0 |  |  |  |  | 15520.28 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C011 | USCSB2404014A | 15526 | F21 TMAH System | 4010 | C |  | WWT: Fabricate and Install (2) Ladders for TMAH Expansion | 45384 | 45385 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 15526 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7763 |  |  | 2328.9 | 7763 |  |  | 2328.9 |  |  |  | 2328.9 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405019A | 15523.92 | Tool Interconnection Project (Main Tool & Other Vendors) | 1078 | P |  | Manpower Pay to Brahma Group for Tool ID: KEMEL2 Daililies for 3.28, 4.2, 4.3, 4.4, and 4.16.2024 | 45419 | 45426 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 15523.92 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 15523.92 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312066A | 15510 | Tool Interconnection Project (Main Tool & Module) | 612 | P |  | KPD801-S Labor | 45280 | 45287 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 14734.5 | 0.95 | 775.5 | 0 | 775.5 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 14734.5 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC24C005 | USCSB2406060A | 15500 | Chemical & WCCS B Side Project | 4293 | C |  | F21P1 B Side Lorry to CDU & DHL to CDU CPVC installation | 45454 | 45454 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved | [14 empty] | 15500 | 1 | 0 | 15500 | -15500 | 0 | [73 empty] | 15500 |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405058A | 15499.28 | Tool Interconnection Project (Main Tool & Other Vendors) | 1099 | P |  | KSECN3 connecting plastic chiller lines, certifying clear PVC double containment. Pulling and connecting PFA lines for chillers and double containment line for chemical drain. | 45428 | 45435 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 15499.28 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 15499.28 | [10 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402259A | 15490.8 | F21P1 Chemical & WCCS package | 3685 | C | -01 | CDS VCR parts etc | 45350 | 3/1/2024 3/5/2024 | 1925 | 17415.8 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: Price Change per Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15490.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 12274.8 | 3216 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Civil | M+L | USC24C006 | USCSB2408078A | 15472 | WWT B side Project | 4694 | C |  | WWT - Lower Level Guage Assembly Tee's | 45520 | 45525 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15472 | 14698.4 | 773.6 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403222A | 15424 | F21P1-0404_H_labor for 50 tools_MICU | 3917 | C |  | M6 Printer kit for HK Power trade | 45372 | 45377 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 15424 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 15424 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402131A | 15421.2 | F21P1 Chemical & WCCS package | 3568 | C |  | CDS Pipes and fittings, etc | 45336 | 2024/2/19 2024/3/7 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 15421.2 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 14193.68 | 1227.52 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2210053A | 15402.62 | F21P1 WWT package (Installation and 2 batch tanks) | 1535 | C |  | 7 Davit Arms and Manways Install | 44863 | 44867 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 14632.49 | 0.95 | 770.13 | 0 | 770.13 | 0 | [24 empty] | 14632.49 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2409071A | 15400 | F21P1 Module Tool Interconnection ETC1-3 | 4864 | C |  | P1B_Dry Etch_Module CIP(Pumping Line)_KEMEA9 | 45554 | 45555 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15400 | 0 | 15400 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2409074A | 15400 | F21P1 Module Tool Interconnection ETC1-3 | 4867 | C |  | P1B_Dry Etch_Module CIP(Pumping Line)_KESDA6 | 45554 | 45565 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15400 | 0 | 15400 | 0 | [73 empty] | -
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2209022A | 15393.94 | F21P1 QR Lab Security & CCTV | 1474 | C |  | F21P1 OWMC_Security&CCTV Package | 44824 | 44830 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 15393.94 | 0 | 15393.94 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303091A | 15370.4 | F21P1 Module Tool Interconnection DIF1-2 | 1828 | C |  | QR lab cable tray | 45009 | 45013 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 15370.4 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 15370.4 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2406035A | 15360.4 | F21P1-0404_H_Hallway plate install_MICU | 4261 | C |  | P1A KDMRA1(ADI-C-11) foundation installation | 45449 | 45451 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 15360 | 0.99997 | 0.4 | 0 | 0.4 | 0 | [66 empty] | 15360 | [6 empty] | - |  |  | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2312105A | 15262.2 | F21P1-0404_H_labor for 50 tools_MICU | 3095 | C |  | security cart for漢科 | 45275 | 45279 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15262.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 15262.2 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV |  | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC21C001 | USCSB2102002A | 15248 | tsmc AZ Temporary Office Physical Security | 1232 | C |  | Metal gate installation | 44243 | 44245 | [6 empty] | B&D Industries, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15248 | 0 | 15248 | 0 | [73 empty] | -
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2404088A | 15232 | F21P1 AMAT Interconnection | 4076 | C |  | MICU CGS Manpower | 45392 | 45449 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 15232 | 0 | 15232 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2308090A | 15105.54 | F21P1-0404_H_labor for 50 tools_MICU | 2387 | C |  | Straight connector for liquid tight conduit | 45154 | 45157 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 15105.54 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 15105.54 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2212043A | 15105 | F21P1 UPW | 1614 | C |  | XHHW 1/0 STR GRN | 44918 | 44924 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 15105 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 15105 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2405011A | 15084.2 | F21P1-0404_H_labor for 50 tools_MICU | 4022 | C |  | Cable connector and outlet plate for HK Power Trade | 45415 | 45447 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 2000.46 | 0.13262 | 13083.74 | 15084.2 | -2000.46 | 0 | [56 empty] | 0 | [16 empty] | 2000.46 |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306042A | 15060 | Tool Interconnection Project (Main Tool & Module) | 326 | P |  | ELECTRICAL TRADE FOR KPSP05 & KPSP06 | 45091 | 45135 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 15060 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 15060 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2403193A | 15000 | F21P1 Module Tool Interconnection ETC1-3 | 3889 | C |  | KEMEA1 iPUP Mechanical Piping Rev1 | 45370 | 45378 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 15000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 15000 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C005 | USCSB2307134A | 15000 | F21P1 Chemical & WCCS package | 2296 | C |  | Lorry PFD Appeal Chang Order | 45135 | 45139 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 15000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 15000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C005 | USCSB2307136A | 15000 | F21P1 Chemical & WCCS package | 2298 | C |  | FAB PFD Appeal Change Order | 45135 | 45139 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 15000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 15000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2405072A | 15000 | F21P1 AMAT Interconnection | 4092 | C |  | Mechanical iPUP | 45423 | 45447 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 15000 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 15000 | [6 empty] | - |  |  | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2307009A | 15000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2182 | C |  | Gensler Minor Changes During Construction | 45111 | 45119 | [6 empty] | M. Arthur Gensler Jr. & Associates, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7866.11 | 0.52441 | 7133.89 | 0 | 7133.89 | 0 | [38 empty] | 3612 |  | 0 | 0 | 0 | 0 | 4204.51 | 0 | 49.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2310125A | 14963.45 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2785 | C |  | Hand tool - ACME | 45218 | 45224 | [6 empty] | ACME Construction Supply Co Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 14338.01 | 0.9582 | 625.44 | 0 | 625.44 | 0 | [41 empty] | 0 | 0 | 0 |  | 320 | 463.44 | 0 | 0 | 234.17 | 13320.4 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306028A | 14955.18 | Tool Interconnection Project (Main Tool & Module) | 313 | P |  | Labeling for waterlines, gas pipes, and exhaust-all functional areas. | 45085 | 45113 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 14955.18 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 13384.22 | 0 | 0 | 0 |  | 0 | 1570.96 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402096A | 14912.29 | F21P1-0404_H_labor for 50 tools_MICU | 3536 | C |  | DI polycell wipes, shared for all systems, Tool hookup team | 45332 | 45336 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 6924.45 | 0.46435 | 7987.84 | 0 | 7987.84 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 6924.45 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2304047A | 14878.3 | F21P1 WWT package (Installation and 2 batch tanks) | 1887 | C | -01 | WWT Tanks tags | 2023/4/19 2024/1/10 | 2023/4/21 2023/1/12 |  |  |  | V |  |  | PostNet of Anthem, LLC | PR Approved | PO Approved | Payment term change from 100% Upon Receipt -Net 30 Days- After Final Acceptance to 20% in Advance - Net 30 Days - After Acceptance. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11361.32 | 0.76362 | 3516.98 | 5054.03 | -1537.05 | 730.3456 | [33 empty] | 0 | [6 empty] | 0 | 0 | 993.98 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 | 5902.71 | 0 |  | 0 |  |  |  |  | 446.349 | 2079.71 |  |  | 743.915 | 152.92 |  |  | 743.915 |  | 0 |  | 2232 | 0 | 0 | 0 | 730.3456
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2408037A | 14816.7 | F21P1 AMHS Wiring Work Outline | 4629 | C |  | L30 3in Conduit and Strut Order_Materials | 45512 | 45516 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14816.7 | 14816.7 | 0 | [74 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2301062A | 14815.62 | F21P1 Module Tool Interconnection CVD | 1678 | C |  | Gas line VCR connector & fitting | 44957 | 44964 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 14814.44 | 0.99992 | 1.18 | 0 | 1.18 | 0 | [28 empty] | 0 | 14814.44 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407029A | 14782.56 | Tool Interconnection Project (Main Tool & Other Vendors) | 1162 | P |  | 1/2-13 x 10' All Thread Rod Zinc | 45496 | 45499 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 14782.59 | 1 | -0.03 | 0 | -0.03 | 0 | [70 empty] | 14635.8 |  | 146.79 | - |  |  | 0
Base-Build | WWT | Site Expense | The budget execution does not pertain to this project | Shared Cost | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2211005A | 14770 | F21P1 WWT package (Installation and 2 batch tanks) | 1540 | C |  | TSMC-Grounding & Permitting Herc/MIC Rentals | 44869 | 44897 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 14770 | 0 | 14770 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 2215.5 |  |  |  | 2215.5 |  |  |  | 2215.5 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2408136A | 14700 | WWT B side Project | 4745 | C |  | WWT B Side Electrical DS Stand | 45533 | 45541 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14700 | 0 | 14700 | 0 | [73 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405134A | 14662.5 | Chemical & WCCS B Side Project | 4162 | C |  | 2" SUS Pipe Bending Reuqest--400R | 45435 | 45444 | [6 empty] | Chukar SB&F LLC | PR Approved | PO Approved | [14 empty] | 14662.5 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 14662.5 | [8 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408128A | 14645.71 | TSMC Fab 21 P1B Tool Hook Up | 4739 | C |  | Generators rentals for HK for 8 months | 45532 | 45534 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14645.71 | 0 | 14645.71 | 0 | [73 empty] | -
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2406132A | 14641.06 | WWT B side Project | 4371 | C |  | 0613 缺料明細材料報價 | 45469 | 45475 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14641.06 | 0 | 14641.06 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402092A | 14604.4 | F21P1-0404_H_labor for 50 tools_MICU | 3532 | C |  | Nilfisk GM-80 CR Vacuum 10 - Industrial with ULPA (01790150), for Gas 300 tools, tool hook up team | 45331 | 45337 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 14604.4 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 14604.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404094A | 14560 | Tool Interconnection Project (Main Tool & Other Vendors) | 1038 | P |  | Xavier | 45406 | 45420 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14560 | 0 | 14560 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402084A | 14524.22 | Tool Interconnection Project (Main Tool & Other Vendors) | 799 | P |  | 02/16/2024: KKDB02-1: 10" DUCT INSTALL | 45344 | 45362 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 14524.22 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 14524.22 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Civil | M+L | USC24C006 | USCSB2409080A | 14474.5 | WWT B side Project | 4872 | C |  | WWT change order (Galvanized Bar-Grate) from TSMC in the Fab | 45555 | 45561 | [6 empty] | Pride Development & Construction, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14474.5 | 0 | 14474.5 | 0 | [73 empty] | -
Base-Build | UPW | MMI | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2309045A | 14472 | F21P1 UPW | 2522 | C |  | MMI-WRC-L20-RO rack modify | 45181 | 45217 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 14472 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 5000 | 0 | 0 | 8748.4 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 723.6 |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C063 | USCSB2404158A | 14445.8 | F21P1-0423_H_T&M Hardware_MICU | 4142 | C |  | Plastic_CV三合一物料儲存工具 | 2024/4/20 2024/4/25 | 45408 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | PR R1:Per end user request, add one more item in this order. | [13 empty] | 13843.8 | 0.95833 | 602 | 0 | 602 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 13843.8 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2406046A | 14440 | F21P1 Module Tool Interconnection ETC1-3 | 4272 | C |  | Delta Wye | 45449 | 45456 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 14440 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 14440 |  |  |  |  | - |  |  | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2311135A | 14400 | EBO21- Tool interconnection | 2985 | C |  | EBO: ZCOAT-1: CABLE TRAY INSTALL | 45259 | 45265 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 14400 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 14400 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2312039A | 14382.74 | Tool Hookup Material (UPW&Chemical) | 3032 | C |  | F21EBO ZASC5-1 UPW hookup material | 45267 | 45271 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 14382.74 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 13845.74 | [5 empty] | 537 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403140A | 14318.75 | Tool Interconnection Project (Main Tool & Other Vendors) | 955 | P |  | Manpoer Pay for Delta Wye for Tool ID: KETRTE ETC 3 | 45381 | 45383 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 14318.75 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 14318.75 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402025A | 14238 | F21P1 Chemical & WCCS package | 3468 | C |  | CDS 1" CPVC and Coupling | 45324 | 45324 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 14238 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 14238 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312056A | 14219 | Tool Interconnection Project (Main Tool & Module) | 602 | P |  | Manpower Pay for KESTT1 for DELTA WYE | 45274 | 45352 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 14219 | 0 | 14219 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2311025A | 14216 | F21P1 UPW | 2880 | C |  | UPW-UMEC-skid repair-3 | 45237 | 45239 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 14216 | 0 | 14216 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 13505.2 |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2403084A | 14189.19 | F21P1 WWT package （USA EQ-FRP tank) | 3787 | C |  | WWT - T-135AA Repair(MMI will reimburse) | 45359 | 45363 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 14189.19 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 2128.3785 | 14189.19 |  |  | 2128.3785 |  |  |  | 2128.3785 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405092A | 14175 | Chemical & WCCS B Side Project | 4112 | C |  | CHEM_ HANSEN_ Chemical label | 45428 | 45428 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 14175 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 14175 |  |  | 14175 | [7 empty] | - |  |  | 0
Base-Build | VOC THC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C013 | USCSB2311077A | 14160 | F21P1 AMC THC Monitoring System | 2931 | C |  | FAB 1A VOC, AMC, THC CA Support (Electrical) | 45246 | 45250 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 14160 | 0 | 14160 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 14160 |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311037A | 14145.6 | F21P1-0404_H_labor for 50 tools_MICU | 2892 | C |  | Flex cable for Third. Tool id KDIGA3 KECOT1 KETRT7 KKDB03 KPOV04 KKDB04 KKSV02 | 45238 | 45245 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 14145.6 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 14145.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402022A | 14128.04 | F21P1 Chemical & WCCS package | 3465 | C | -01 | CDS LB2 SS parts | 45324 | 2024/2/2 2024/2/8 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | PO R1: Change Trade Term: 100% NET 45 -> 100% NET 30 |  | Ta Wei Wang | [11 empty] | 14077.5 | 0.99642 | 50.54 | 0 | 50.54 | 0 | [48 empty] | 0 | 0 |  | 14077.5 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311040A | 14121.2 | F21P1-0404_H_labor for 50 tools_MICU | 2895 | C |  | Label Ribbon Kit For Printer, Shared product, Tool ID:KDSTS2, KDSTL1, KDSTS1 | 45239 | 45240 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10645.54 | 0.75387 | 3475.66 | 0 | 3475.66 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 8923.54 | [5 empty] | 1722 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409102A | 14105 | TSMC Fab 21 P1B Tool Hook Up | 4910 | C |  | Power hardware request_ Cable tie 9/23 for 100 tools | 45561 | 45562 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14105 | 0 | 14105 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401039A | 14103.03 | Tool Interconnection Project (Main Tool & Other Vendors) | 662 | P |  | KPI401-S Nov 2023 Invoice for Labor | 45310 | 45314 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 14103.03 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 14103.03 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | DCR Scope | CDS | Chemical | Electrical | QAQC | USC21C005 | USCSB2306026A | 14100 | F21P1 Chemical & WCCS package | 2061 | C |  | Particle Test Service | 45084 | 45092 | [6 empty] | Propersys Corp | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 14100 | 1 | 0 | 0 | 0 | 705 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 13395 | 14100 | 0 |  | - | 0 | 705 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2309026A | 14100 | F21P1 Chemical & WCCS package | 2503 | C |  | particle counter for cycle purge | 45177 | 45190 | [6 empty] | Propersys Corp | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 14100 | 0 | 14100 | 7050 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 7050 |  | 6345 |  | - | 0 | 0 | 705
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2306091A | 14090 | F21P1 Chemical & WCCS package | 2124 | C |  | Lorry Pipe Crossover Platform | 45098 | 45125 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 14090 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 14090 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2310114A | 14070 | F21P1 AMHS Wiring Work Outline | 2775 | C |  | FAB-1A Additional Modules M165,M187 | 45217 | 45220 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 14070 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 7035 | 0 | 0 |  | 7035 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2305088A | 14045.1 | F21P1 Chemical & WCCS package | 2009 | C |  | MIC F21 Commission Requirements-Swagelok | 45065 | 45077 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 14045.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 11599.1 | 2446 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307008A | 14040 | Tool Interconnection Project (Main Tool & Module) | 344 | P |  | Labor Cable Pull KDSTS2/KDCRS3/KCSCS5 | 45129 | 45132 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2600 | 0.18519 | 11440 | 0 | 11440 | 0 | [40 empty] | 2600 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405027A | 14022.11 | Tool Interconnection Project (Main Tool & Other Vendors) | 1086 | P |  | KDSTS9 - rework - DNS SCREEN INTERCONNECTS | 45419 | 45419 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 14022.11 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 14022.11 | [10 empty] | - |  |  | 0
Hookup | 5G | Material | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC22C010 | USCSB2212014A | 14000 | F21 P1 LSC CMS and DPM 5G System | 1587 | C |  | DPM Connection Project | 44904 | 44909 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 14000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 14000 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2401232A | 14000 | F21P1 AMHS Wiring Work Outline | 3414 | C |  | TSMC F21 E2 VISA Yisin manpower for maruta | 45317 | 45324 | [6 empty] | Yi Sin Mechanical LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 14000 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 14000 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | temp PVC curtain | Material |  |  | Others |  |  | USC22C030 | USCSB2301044A | 14000 | F21_AZCHAD_Hookup_ temp PVC curtain | 1661 | C |  | PVC Curtain for TSMC F21 | 44947 | 44958 | [6 empty] | LI YEI Enterprise Co | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 14000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 14000 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407115A | 13977.68 | WWT B side Project | 4530 | C |  | WWT B區工程缺料 | 45492 | 45496 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 150.36 | 0.010757 | 13827.32 | 3958.68 | 9868.64 | 0 | [71 empty] | 0 |  | 150.36 | 0 | 0 | 0 | 0
Base-Build | VOC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Electrical | M+L | USC21C008 | USCSB2402049A | 13954 | F21P1 CCTV & Security | 3491 | C | -01 | VOC Electric CO17&CO28 | 45328 | 2024/2/20 2024/3/15 | -23890 | 37844 |  | V |  | V | Spectra Electrical Services, Inc. | PR Approved | PO Approved | Amount applied for includes claims for Davis Bacon Act training, which may if any be reimbursed upon receipt of funds from Chips Act |  | Tiong Sheng Poh | [11 empty] | 13954 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 13954 | [6 empty] | - | 0 | 0 | 0
Base-Build | Chemical | MIMO/Rigging | DCR Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2306049A | 13930 | F21P1 Chemical & WCCS package | 2083 | C |  | 2 Tank &1 EQ Move in CO 9 | 45091 | 45113 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 13930 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 13930 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2402103A | 13851 | F21P1-0423_H_T&M Hardware_MICU | 3543 | C |  | Plastic第五批短期採購, Tool hookup team for tsmc | 45332 | 45337 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 13851 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 13851 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409004A | 13834.26 | Tool Interconnection Project (Main Tool & Other Vendors) | 1211 | P |  | Equipment SP-110 v3 | 45539 | 45541 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13834.26 | 0 | 13834.26 | 0 | [73 empty] | -
Base-Build | chemical safety cabinet | MMI | Main Contract Scope | Chemical Lab | Chemical | Mechanical | Labor | USC23C042 | USCSB2307072A | 13811.04 | F21P1 Chemical Safety Cabinet Installation | 2239 | C |  | F21 Emergency Cabinets B-2 | 45125 | 45145 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 13811.04 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 13811.04 | [8 empty] | 13811.04 | 0 |  | - | 0 | 0 | 0
Others | cabinet transport | Equipment | The budget execution does not pertain to this project | chemical safety cabinet | Chemical | Mechanical | Labor | USC23C049 | USCSB2307071A | 13811.04 | Cabinets transport and installation | 2238 | C |  | F21 Emergency Cabinets B-1 | 45125 | 45145 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 13811.04 | 1 | 0 | 0 | 0 | 7805 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3936.14 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 1382 | 9874.9 | 2072 |  | - | 2763 | 2970 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409024A | 13782 | TSMC Fab 21 P1B Tool Hook Up | 4792 | C |  | cord grips kit 2'' for HK Power | 45540 | 45546 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13782 | 13782 | 0 | 0 | [73 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402195A | 13776.86 | F21P1 Chemical & WCCS package | 3622 | C |  | CDS CRG Lorry punch | 45343 | 45348 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 13776.76 | 0.99999 | 0.1 | 0 | 0.1 | 0 | [52 empty] | 0 | 0 | 13776.76 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2303032A | 13736.09 | F21P1 Chemical & WCCS package | 1774 | C |  | 16AWG-3/C 600V Shielded wire | 44993 | 45006 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 13736.09 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 13736.09 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2407049A | 13719.85 | F21P1 AMHS Wiring Work Outline | 4448 | C |  | 9 YCF AMHS Engineers support Muratec from 12/13/23~3/27/24 | 45483 | 45511 | [6 empty] | YUNG CHENG FENG ENGINEERING CO.,LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13719.85 | 0 | 13719.85 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C005 | USCSB2308112A | 13713.7 | F21P1 Module Tool Interconnection DIF1-2 | 2409 | C |  | Labor for Rosendin DIFF Mainframe Tansformer Power System (Vulcan/Mozart) install a 4/0 4W Tray Cable from the Mainframe tran | 45157 | 45160 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6856.85 | 0.5 | 6856.85 | 0 | 6856.85 | 0 | [40 empty] | 0 | 0 | 6856.85 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2407028A | 13684.48 | WWT B side Project | 4427 | C |  | Modify 6 Beams on Cable Tray Rack LB2 B side | 45477 | 45483 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13684.48 | 13684.48 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW |  |  |  | UPW | Mechanical | M+L | USC24C008 | USCSB2407149A | 13675 | UPW B Side Project | 4559 | C |  | MA 200 Pipe Adjustment_UPW | 45498 | 45499 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13675 | 0 | 13675 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Labor | DCR Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2403134A | 13654.97 | F21P1 WWT package (Installation and 2 batch tanks) | 3836 | C |  | WWT - GB-PCO 108- Common Rack addition 6/N.5 | 45365 | 45366 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 12972.22 | 0.95 | 682.75 | 0 | 682.75 | 648.611 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 2048.2455 |  |  | 12972.22 | 2048.2455 |  |  |  | 2048.2455 |  | 0 |  | - | 0 | 0 | 0 | 648.611
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2403260A | 13626.15 | WWT Change Order (Piping) | 3953 | C |  | WWT-FRP-piping-T780&710 repair (A side) | 45378 | 45380 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 13626.15 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 13626.15 |  |  | 2043.9225 |  |  |  | 2043.9225 |  |  |  | 2043.9225 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401036A | 13612.48 | Tool Interconnection Project (Main Tool & Other Vendors) | 659 | P |  | Installers from SantanFire to conduct & complete interconnection work on KCSCN5 | 45309 | 45309 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 13612.48 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 13612.48 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401035A | 13612.48 | Tool Interconnection Project (Main Tool & Other Vendors) | 658 | P |  | Installers from SantanFire to conduct & complete interconnection work on KSHMU1 | 45309 | 45309 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 13612.48 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 13612.48 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Site Expense |  |  | Others |  |  | USC23B002 | USC2309015A | 13609.61 | Tool Interconnection Project (Main Tool & Module) | 406 | P |  | Electric Scissor Lift, 19' Micro | 45185 | 45191 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 13048.81 | 0.95879 | 560.8 | 0 | 560.8 | 0 | [40 empty] | 2299.35 | 0 | 2299.35 | 0 | 2299.35 | 0 | 2299.35 | 0 | 1047.31 | 0 | 2804.1 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405021A | 13588.66 | Tool Interconnection Project (Main Tool & Other Vendors) | 1080 | P |  | KEPSS1-DNS SCREEN INTERCONNECTS | 45419 | 45420 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 13588.66 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 13588.66 | [10 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Site Expense | USC23C045 | USCSB2403217A | 13585 | WWT Change Order (Piping) | 3912 | C |  | U-Line - Taiwan Installer team | 45372 | 45376 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 12350 | 0.90909 | 1235 | 0 | 1235 | 1111.5 | [52 empty] | 0 | 0 | 0 |  | 12350 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 1111.5
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405060A | 13572.57 | Tool Interconnection Project (Main Tool & Other Vendors) | 1101 | P |  | KUECN2 - pressure test. Pressure testing, removing caps and installing ferrals and connected line, restoring lines to tool and labeling | 45428 | 45435 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 13572.57 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 13572.57 | [6 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311083A | 13572 | Tool Interconnection Project (Main Tool & Module) | 550 | P |  | KPSP01: CABLE PULL | 2023/11/30 2023/12/19 | 45286 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved | PR R1: Uploaded revised invoice 38242 for $3,456. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 13572 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 13572 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | The budget execution does not pertain to this project | 0 | Low Voltage | Electrical | Material | USC21C008 | USCSB2207019A | 13536 | F21P1 CCTV & Security | 1434 | C |  | TSMC Warehouse Panels | 44763 | 44768 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 13536 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 12182.4 |  |  |  |  | 0 |  |  | 1353.6 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C021 | USCSB2405155A | 13500 | F21P1 KLA Interconnection | 4245 | C |  | ME: KKDB02: CO FOR EXHAUST DUCT REROUTING | 45441 | 45498 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 13500 | 1 | 0 | 13500 | -13500 | 0 | [73 empty] | 13500 |  |  | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C025 | USCSB2304022A | 13500 | AMHS TSMC Instrustructure and Branch Circuits | 1863 | C |  | TSMC F21P1 AMHS On-Call Support | 45024 | 45026 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12300 | 0.91111 | 1200 | 0 | 1200 | 0 | [33 empty] | 0 | 2310 |  | 7560 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2430 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407128A | 13446.8 | WWT B side Project | 4542 | C |  | 儀表管路需求 Mateials for pipeline_WWT | 45493 | 45498 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 1450.43 | 0.10786 | 11996.37 | 0 | 11996.37 | 0 | [70 empty] | 285.51 | 0 | 1164.92 | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2407089A | 13355.75 | WWT B side Project | 4505 | C |  | T-780BA/BB handrail fabrication and installation_WWT | 45489 | 45499 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13355.75 | 13355.75 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Greenberry | DCR Scope | WWT | WWT | Steel | M+L | USC23C045 | USCSB2309020A | 13345 | WWT Change Order (Piping) | 2497 | C |  | WWT-LB2 rack modification | 45176 | 45180 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12677.75 | 0.95 | 667.25 | 0 | 667.25 | 633.8875 | [40 empty] | 0 | 0 | 0 | 0 |  | 12677.75 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 633.8875
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2403207A | 13343.35 | WWT Change Order (Piping) | 3902 | C |  | WWT Caps_20240319 | 45372 | 45376 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 13343.35 | 1 | 0 | 0 | 0 | 2878.2177 | [52 empty] | 0 | 0 | 4171.33 |  | 0 |  |  |  |  | 2001.5025 |  |  |  | 2001.5025 |  |  | 9172.02 | 2001.5025 |  | 2878.2177 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2312196A | 13300 | F21P1 UPW | 3183 | C |  | UPW-swing gate train B | 45290 | 45306 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 13300 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 12740 |  | 0 |  | 560 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Penetration Pipe | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC22C020 | USCSB2309149A | 13281.46 | F21P1 Penetration Pipe | 2620 | C |  | WWT-LB1 embedded pipes | 45192 | 45197 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 13281.46 | 0 | 13281.46 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC22C009 | USCSB2402230A | 13236 | F21P1 230kV MTR Oil and Drain Pipe work | 3657 | C |  | UPW-UMEC-COs for ORGANO180, 183 and 186 | 45346 | 45351 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12574 | 0.94998 | 662 | 0 | 662 | 0 | [52 empty] | 0 | 11912 | 0 |  | 662 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Material | USC24C005 | USCSB2406151A | 13230 | Chemical & WCCS B Side Project | 4398 | C |  | CED 化學系統電力訊號線0627 (CED Cat 6 Plenum Rated Cable) | 45472 | 45474 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13230 | 13230 | 0 | 0 | [73 empty] | - |  |  | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC22C031 | USCSB2310092A | 13230 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2753 | C |  | TSMC-F21P1 AMHS_Hardware_CT | 45213 | 45219 | [6 empty] | Third Enterprise | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 13230 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 13230 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403081A | 13176.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 900 | P |  | 9863001 Rental SP 110-S (V3) 20mm-110mm 1 IR welding tool | 45370 | 45371 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6329.49 | 0.48036 | 6847.11 | -174.5 | 7021.61 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2137.18 |  | 4192.31 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2406063A | 13168.2 | F21 TMAH System | 4296 | C |  | WWT - Harrington Fusion Machine Rental TMAH EXP | 45454 | 45462 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 10754.03 | 0.81667 | 2414.17 | 2227.3 | 186.87 | 0 | [68 empty] | 3950.46 |  |  | 0 | 6803.57 | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C010 | USCSB2407110A | 13158 | tsmc AZ sewer and water pipeline installation | 4525 | C |  | CGS Global Support Onsite Manpower | 45491 | 45499 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13158 | 0 | 13158 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408001A | 13126 | Tool Interconnection Project (Main Tool & Other Vendors) | 1172 | P |  | KPE606-T Scaffolding Labor | 45506 | 45510 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 13126 | 1 | 0 | 0 | 0 | [71 empty] | 13126 |  |  | -
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2209001A | 13115.52 | F21P1 UPW | 1455 | C |  | Tunnel GF fix point fitting | 44806 | 44816 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 13115.52 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 13115.52 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402049A | 13113 | Tool Interconnection Project (Main Tool & Other Vendors) | 769 | P |  | KETRT8 MANPOWER PAY FOR CCE | 45329 | 45337 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 13113 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 13113 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402086A | 13068.24 | F21P1 Chemical & WCCS package | 3527 | C |  | CDS HPM Punch materials | 45331 | 45341 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 13068.24 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 13068.24 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | MIMO/Rigging | DCR Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2402276A | 13050 | F21 TMAH System | 3701 | C |  | Un install and re install steel for tank move in | 45351 | 45352 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 12397.5 | 0.95 | 652.5 | 0 | 652.5 | 619.875 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 12397.5 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 619.875
Base-Build | Triazole | UMEC | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC22C022 | USCSB2403107A | 12999 | F21P1 Triazole treatment system | 3809 | C |  | 03/10 overtime work to finish triazole | 45362 | 45363 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 12999 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 12349 | 0 |  | 0 |  | 650 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2308180A | 12997.06 | F21P1 Chemical & WCCS package | 2473 | C |  | Pour Additional Pads Not In Scope | 45169 | 45196 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 12997.06 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 12997.06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Equipment |  |  | AMHS |  |  | USC23C015 | USCSB2310018A | 12970 | F21P1 AMHS Wiring Work Outline | 2681 | C |  | 40 beakers purchase from Taiwan | 45203 | 45209 | [6 empty] | Third Enterprise | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12970 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 12970 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2308135A | 12959.18 | F21P1 Chemical & WCCS package | 2430 | C |  | Southwest Fastener Monthly Order | 45161 | 45163 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12586.95 | 0.97128 | 372.23 | 0 | 372.23 | 0 | [39 empty] | 4733.33 | 7853.62 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 372.23 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2308067A | 12950 | F21P1 UPW | 2365 | C |  | WRC UPW Electrical Permit Drawing Revision | 45149 | 45155 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 12900 | 0.99614 | 50 | 0 | 50 | 0 | [39 empty] | 12900 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2312204A | 12908.64 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3190 | C |  | United Rentals for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45290 | 45294 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11975.74 | 0.92773 | 932.9 | 0 | 932.9 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 3494.62 |  | 8481.12 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2208010A | 12903.68 | F21P1 UPW | 1447 | C |  | UPW Prominent H2O2 Analyzer | 44793 | 44799 | [6 empty] | Precision Integrated Systems, LLC | PR Approved | PO Approved | related to USC2111034A | 100% by received-net 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 12903.68 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 12903.68 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C008 | USCSB2410007A | 12874 | F21P1 Module Tool Interconnection LIT2-3 | 4954 | C |  | Lit 2: KPE604-S: GMS Box Rework | 45566 | 45569 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 12874 | 0 | 12874 | 0
Base-Build | WWT | Equipment | CO Scope (adding/additional scope) | WWT | WWT | Electrical | Instrument | USC21C009 | USCSB2304041A | 12854.23 | F21P1 WWT package (Installation and 2 batch tanks) | 1881 | C | -01 | WWT NH4 analyzer | 2023/4/17 2023/6/6 | 2023/5/25 2023/6/7 | -1016.26 | 13870.49 | V |  |  | V | Winn Marion Barber, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 12854.23 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 12854.23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2305016A | 12830.19 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1941 | C |  | KPE602-S Streimers | 2023/5/4 2023/5/11 2024/9/9 | 2023/10/17 2024/9/17 | -3244.05 | 16074.24 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | R1:Scott Weary increased amount due to revaluation of budget numbers. PO R1: Case Closed -- adjust the PO amount to reflect the actual total. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12830.19 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 12830.19 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USC2403004A | 12828 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 831 | P | -01 | MANPOWER: PINNACLE PEAK WAREHOUSE | 45353 | 2024/3/15 2024/3/29 | 4348 | 8480 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: Manpower Adjusted from -3/04-03/22/24 with 1 HR OT. |  | Ta Wei Wang | [11 empty] | 0 | 0 | 12828 | 0 | 12828 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404222A | 12824.48 | Chemical & WCCS B Side Project | 3973 | C |  | CHEM_WCCS SUS project_hardware 240415020003_ (01-00166939) | 45412 | 45412 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved | [14 empty] | 12824.48 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 12824.48 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2307006A | 12765.4 | Tool Interconnection Project (Main Tool & Module) | 342 | P |  | 400CL-015H-20 1-1/2" PIPE P/E CLR PVC SCH40 20'LENGTH | 45119 | 45124 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12765.4 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 12765.4 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2207005A | 12724.25 | Tool Hookup Material (UPW&Chemical) | 1420 | C |  | Tool HK Chemical Material PFA Fitting (Valin) | 44748 | 44754 | [6 empty] | Valin Corporation | PR Approved | PO Approved |  | 100% after final acceptance-Net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 12717.3 | 0.99945 | 6.95 | 0 | 6.95 | 0 | [14 empty] | 200.26 | [10 empty] | 4637.64 | 2859.95 |  | 0 |  | 5019.45 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2304069A | 12708.2 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1908 | C |  | Change Order for Marketech Fab and Office TI | 45041 | 45047 | [6 empty] | M. Arthur Gensler Jr. & Associates, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7038.29 | 0.55384 | 5669.91 | 0 | 5669.91 | 0 | [32 empty] | 5200 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 1838.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401097A | 12700.8 | Tool Interconnection Project (Main Tool & Other Vendors) | 714 | P |  | KPE603-S Labor | 45321 | 45323 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12700.8 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 12700.8 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Material | USC21C003 | USCSB2303041A | 12682.26 | F21P1 UPW | 1783 | C |  | UPW Panel Material | 44994 | 45011 | [6 empty] | Avex-SG Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12682.07 | 0.99999 | 0.19 | 0 | 0.19 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 12682.07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C011 | USCSB2303081A | 12650.88 | F21 TMAH System | 1818 | C |  | Mechanical Inspection | 45006 | 45008 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12650.88 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 12650.88 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2304064A | 12608.5 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1903 | C |  | KPE601-S STREIMER EXHAUST | 2023/4/22 2024/9/10 | 2023/5/4 2024/9/10 | -816.14 | 13424.64 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PO R1: Case Closed -- adjust the PO amount to reflect the actual total |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12608.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 6211.88 | 0 | 0 | 0 | 0 |  | 0 | 0 | 6396.62 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405183A | 12603.4 | WWT B side Project | 4211 | C |  | WWT Fittings_20240530 (B Side) | 45443 | 45447 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 6798.02 | 0.53938 | 5805.38 | 5805.38 | 0 | 3147.7032 | [66 empty] | 5829.08 |  | 968.94 |  |  | 3147.7032 |  | - | 0 | 0 | 0 | 0
Base-Build | W-H2SO4 | Trident | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C014 | USCSB2402083A | 12590 | F21P1 WH2SO4 | 3524 | C |  | Tunnel Thermal Expansion 2.7.24 | 45330 | 45336 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 12590 | 0 | 12590 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1888.5 |  |  |  | 1888.5 |  |  |  | 1888.5 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310031A | 12581.2 | F21P1 Chemical & WCCS package | 2694 | C |  | 9/19/23 to 10/20/23 Southwest Fastener Monthly Order for Chemical Team | 45204 | 45239 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 11365.23 | 0.90335 | 1215.97 | 0 | 1215.97 | 0 | [43 empty] | 851.42 | 4931.3 | 600 | 0 | 0 | 2505.59 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 2476.92 | 3648.55 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404075A | 12563 | WWT B side Project | 4066 | C |  | WWT PVC 10_Pipes_20240408 (B Side) | 45391 | 45393 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 12563 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 12563 |  |  | 1884.45 |  |  |  | 1884.45 |  |  |  | 1884.45 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC24C006 | USCSB2404167A | 12555.53 | WWT B side Project | 3928 | C |  | WIRE SECURITY CAGE/ COLLAPSIBLE WIRE CONTAINER WITH CASTERS | 45405 | 45419 | [6 empty] | Global Equipment Company Inc. | PR Approved | PO Approved | [14 empty] | 12555.53 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 11059.75 |  | 1495.78 | [10 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2211018A | 12549 | F21P1 WWT package (Installation and 2 batch tanks) | 1552 | C |  | Custom flanges and bolts | 44881 | 44881 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 12549 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 11921.55 |  | 627.45 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408010A | 12547.34 | Tool Interconnection Project (Main Tool & Other Vendors) | 1181 | P |  | 1-IN INSUL GRND BUSH | 2024/8/9 2024/9/24 | 2024/8/14 2024/9/24 | -42.49 | 12504.85 |  |  |  |  | Independent Electric Supply, Inc. | PR Approved | PO Approved | PR R1: Supplier send extra #24 PP DIN 1W FRL materials, PM decide to keep them | [13 empty] | 2934.75 | 0.23389 | 9612.59 | 12547.29 | -2934.7 | 0 | [73 empty] | 2934.75
Base-Build | Chemical | Material | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2307092A | 12546.18 | F21P1 Chemical & WCCS package | 2258 | C | -01 | NFPA Diamond Signs Lorry HPM BSGS CUP | 2023/7/20 2023/7/28 | 2023/7/24 2023/8/4 | 712.38 | 11833.8 | V |  |  | V | Pensacola Hardware Company | PR Approved | PO Approved | R1:Revise item1/item 2 description and price |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10758.98 | 0.85755 | 1787.2 | 0 | 1787.2 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 10758.98 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2312188A | 12542.98 | F21P1 WWT package (Installation and 2 batch tanks) | 3175 | C |  | WWT-Material-A side SUS (77 item 12/21list ) | 45288 | 45293 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 12542.98 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 11727.45 |  | 0 | 0 | 815.53 |  | 0 | [8 empty] | 250.8596 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2403034A | 12518.62 | WWT Change Order (Piping) | 3743 | C |  | WWT - Replacement Couplings for F21P1 WWT Goulds pumps | 45356 | 45366 | [6 empty] | Phoenix Pumps, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 12518.62 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 12518.62 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402184A | 12510.99 | F21P1-0404_H_labor for 50 tools_MICU | 3613 | C |  | For PCW and all system, tool hookup team | 45343 | 45343 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 12510.99 | 1 | 0 | 0 | 0 | 0 | 12510.99 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C002 | USC2409055A | 12503.77 | F21P1-0404_H_Hallway plate install_MICU | 1256 | P |  | PR-PO for PRPS opening invoice for Foundations | 45562 | 45562 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 12503.77 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 12503.77
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2407047A | 12500 | F21P1 AMHS Wiring Work Outline | 4446 | C |  | 5 Yisin AMHS Engineers support Muratec | 45483 | 45489 | [6 empty] | Yi Sin Mechanical LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 12500 | 0 | 12500 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2404221A | 12427.5 | F21P1-0404_H_labor for 50 tools_MICU | 3972 | C |  | Cord connector for HK Power system for 10 tools | 45412 | 45422 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 6414.95 | 0.51619 | 6012.55 | 11618.56 | -5606.01 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 808.94 |  |  | 0 |  | 5606.01 | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2402151A | 12418 | F21P1 Chemical & WCCS package | 3584 | C |  | CDS DHL Platform Extensions | 45337 | 45341 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 12418 | 1 | 0 | 0 | 0 | 620.9 | [49 empty] | 0 |  |  | 0 | 0 | 11797.1 |  | 0 | [5 empty] | 620.9 | [8 empty] | 0 |  | - | 0 | 0 | 620.9
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2301009A | 12401.41 | F21P1 UPW | 1632 | C |  | UPW TempCP-2” HP-PP pipes | 44932 | 44935 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 12401.41 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 12401.41 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2406149A | 12400 | F21P1 Module Tool Interconnection DIF1-2 | 4397 | C |  | QA/QC for Gas Piping System in Furnace for Diffusion for tool ID#KDTNK2 | 45471 | 45478 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | [14 empty] | 12400 | 1 | 0 | 12400 | -12400 | 0 | [73 empty] | 12400 |  |  | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C021 | USCSB2408117A | 12385.5 | F21P1 KLA Interconnection | 4730 | C |  | ME: KPSP07, KPSP04, KPCD05, KPCD02, KKSV04, KKDB03, KKDB01-03: INSTALL SIGNAL/POWER CABLES & MOVE CHILLER HOSES. | 45531 | 45534 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 12385.5 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 12385.5 | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310040A | 12374.74 | F21P1-0404_H_labor for 50 tools_MICU | 2702 | C |  | Bush | 45205 | 45212 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 12374.74 | 0 | 12374.74 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402201A | 12365 | F21P1 WWT package (Installation and 2 batch tanks) | 3628 | C |  | Stripper packing procurement | 45343 | 45348 | [6 empty] | LANTEC PRODUCTS INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 12365 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 12365 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403102A | 12312 | Tool Interconnection Project (Main Tool & Other Vendors) | 911 | P |  | Eliseo Perez - 3/25-4/30/2024 | 45374 | 45435 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 12312 | 0 | 12312 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C018 | USCSB2409065A | 12295.2 | Tool Hook Up E2 Trade Equipment Rental | 4860 | C |  | Ryan Herco: Rental fee cover August | 45553 | 45554 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 0 | 0 | 12295.2 | 0 | 12295.2 | 0 | [73 empty] | -
Base-Build | VOC |  |  |  | Low Voltage | Electrical | M+L | USC21C013 | USCSB2409012A | 12271.61 | F21P1 AMC THC Monitoring System | 4782 | C |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 5/6 | 45539 | 45542 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 12271.61 | 1 | 0 | 12271.61 | -12271.61 | 0 | [73 empty] | 12271.61
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311031A | 12239.26 | F21P1-0404_H_labor for 50 tools_MICU | 2886 | C |  | Wire TCXH6/4G for Third for ATF-BO7, AET-F14, ATF-C15, and ATF-A04 | 45237 | 45239 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 12239.26 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 12239.26 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2306114A | 12216 | F21P1 UPW | 2147 | C |  | Hach Start up | 45101 | 45107 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12216 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 12216 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Triazole | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC22C022 | USCSB2304074A | 12154.62 | F21P1 Triazole treatment system | 1913 | C |  | Triazole SUS material | 45042 | 45051 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 12154.62 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 12154.62 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408016A | 12153.69 | TSMC Fab 21 P1B Tool Hook Up | 4612 | C |  | Ryan Herco: Rental fee cover June | 45507 | 45514 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 12153.69 | 1 | 0 | 0 | 0 | [69 empty] | 12153.69 |  |  |  |  | -
Base-Build | WWT | Labor | DCR Scope | WWT | WWT | Steel | M+L | USC21C011 | USCSB2403218A | 12152.2 | F21 TMAH System | 3913 | C |  | WWT009 - GB-PCO 110- Remove and Reinstall main rack LB2 B-side supports (N.5-P/19-19.5) | 45372 | 45377 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 11544.59 | 0.95 | 607.61 | 0 | 607.61 | 577.2295 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1822.83 |  |  | 11544.59 | 1822.83 |  |  |  | 1822.83 |  | 0 |  | - | 0 | 0 | 0 | 577.2295
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208004A | 12122.25 | F21P1 UPW | 205 | P |  | Fire extinguishers, Inspection | 44778 | 44790 | [6 empty] | Cintas Corporation | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 12122.25 | 1 | 0 | 0 | 0 | 0 | [15 empty] | 12122.25 | [12 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209008A | 12074.01 | F21P1 Chemical & WCCS package | 233 | P0 |  | AutoCAD | 44825 | 44826 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 12074.01 | 1 | 0 | 0 | 0 | 0 | 12074.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | M+L | USC24C005 | USCSB2405032A | 12000 | Chemical & WCCS B Side Project | 4041 | C |  | SDS L3 CES5003-2.5 Drain revise (Urgent) | 45419 | 45425 | [6 empty] | Yun Cheng International Co., Ltd | PR Approved | PO Approved | [14 empty] | 10800 | 0.9 | 1200 | 0 | 1200 | 12000 | [56 empty] | 0 | [5 empty] | 10800 | [8 empty] | 12000 |  | - |  |  | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2301056A | 12000 | F21P1 WWT package (Installation and 2 batch tanks) | 1673 | C |  | Weld Spec inspection | 44954 | 44957 | [6 empty] | Weld Spec, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 9496.5 | 0.79138 | 2503.5 | 0 | 2503.5 | 1994.265 | [24 empty] | 8650.5 |  | 846 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 600 |  |  |  | 600 |  | 949.65 |  | - | 1044.615 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C007 | USC2404105A | 12000 | F21P1 Module Tool Interconnection PVD1-2 | 1055 | P |  | KSSBA5,KSSBA4,KSHMA2,KSHMA3 DI-max hard pipe install | 45408 | 45413 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 12000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 12000 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2401122A | 12000 | F21P1 Module Tool Interconnection CVD | 3309 | C |  | KCANN3 Mechanical CIP work. YAHO completing chamber-divert lines and returning completed parts for installation | 45309 | 45328 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12000 | 1 | 0 | 12000 | -12000 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 12000 | 0 | 0 | 0
Base-Build | VOC |  | The budget execution does not pertain to this project | VOC | Low Voltage | Mechanical | M+L | USC22C013 | USCSB2406107A | 12000 | F21P1 QR Lab Security & CCTV | 4342 | C |  | B side VOC duct modification | 45464 | 45465 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 8687.62 | 0.72397 | 3312.38 | 0 | 3312.38 | 12000 | [70 empty] | 8687.62 |  |  | - | 12000 |  | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2404019A | 11999 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4015 | C |  | MMI MST M194 Open & Recovery | 45384 | 45385 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 11999 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 11999 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2312020A | 11994 | F21P1 Chemical & WCCS package | 3014 | C |  | CDS 1-1/2"x2" 90 ELBOW 316LEP/304AP | 2023/12/5 2023/12/7 | 45268 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11994 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 11994 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC22C022 | USCSB2403119A | 11968 | F21P1 Triazole treatment system | 3821 | C |  | WWT: Triazole Tank Anchoring and Crossover Platform Modification | 45364 | 45364 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 11968 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1795.2 | 11968 |  |  | 1795.2 |  |  |  | 1795.2 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402266A | 11932.16 | F21P1 WWT package (Installation and 2 batch tanks) | 3691 | C | -01 | WWT Pipes_20240227 (A Side) | 45350 | 45350 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Trade Term Changes from DDP to FOB |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 11932.16 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 10197.26 | 205.6 |  | 437.6 | [7 empty] | 1091.7 | 357.9648 |  |  |  | 596.608 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | VOC | MMI | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Steel | M+L | USC21C007 | USCSB2403284A | 11912 | F21P1 VOC package （Installation ) | 3977 | C |  | VOC Additional Welding - Modifications | 45380 | 45380 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 11912 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 11912 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Electrical | M+L | USC21C011 | USCSB2401175A | 11900 | F21 TMAH System | 3360 | C |  | WWT-TMAH-LCMSMS-Power | 45314 | 45317 | [6 empty] | 2000 GOLD LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11900 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 11900 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2303060A | 11900 | F21P1 UPW | 1799 | C |  | Tanks aeration pipe | 45000 | 45008 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11900 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 11900 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Southland | DCR Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2308147A | 11857.9 | F21P1 Slurry package | 2442 | C |  | Cut slurry CDA/GN2(14 ea) caps and reweld | 45162 | 45188 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 11857.9 | 0 | 11857.9 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408057A | 11837 | F21P1 Module Tool Interconnection LIT2-3 | 4675 | C |  | Lit 3: KPD802-T: PFA BB Rework | 45517 | 45519 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11837 | 11837 | 0 | 0 | [73 empty] | -
Non-TSMC | EDG | Equipment |  |  | Others |  |  | USC22C003 | USCSB2306121A | 11832 | TSMC Fab21 Project Phase 1 EDG Package | 2154 | C |  | Run & Support 480V Temp Power Feeds in FAB-1 | 45105 | 45113 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved | Will charge back to Fu Energy |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11832 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 11832 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2304057A | 11803.71 | F21P1 Chemical & WCCS package | 1896 | C |  | F21P1 CDS-01-FNN Integration | 45036 | 45055 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 11803.71 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 8853.77 |  |  |  |  | 0 | 0 | 2949.94 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409067A | 11754.9 | TSMC Fab 21 P1B Tool Hook Up | 4862 | C |  | BBP 37 label ribbon for PORT label | 45553 | 45554 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11754.9 | 0 | 11754.9 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402108A | 11675.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 820 | P |  | Manpoer Pay for Delta Wye | 45349 | 45351 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11675.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 11675.5 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408050A | 11667 | F21P1 Module Tool Interconnection LIT2-3 | 4668 | C |  | Lit 2: KPE603.S, KPE604.S, KPE605.S, KPE606.S, KPE607.S: EUV RF Cable Tray Cover Installation | 45514 | 45519 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11667 | 0 | 11667 | 0 | [73 empty] | -
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C021 | USCSB2405138A | 11656.5 | F21P1 KLA Interconnection | 4168 | C |  | ME: NO TOOL ID: MANPOWER (UBALDO FERREYRA JR) FOR JUNE 2024 | 2024/5/23 2024/9/18 | 2024/6/11 2024/9/18 | 2536.5 | 9120 | V |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | PR R1 :This is to include the OT HRS WE 06/09 for $256.50 & REG HRS WE 07/04 for $2,280.00. See 2nd page. | [13 empty] | 11656.5 | 1 | 0 | 11656.5 | -11656.5 | 0 | [73 empty] | 11656.5 |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2310041A | 11648.26 | WWT Change Order (Piping) | 2703 | C |  | WWT Drain Pipe PP PN6 | 45205 | 45211 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11648.26 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 6070.22 |  | 5578.04 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401044A | 11619.89 | Tool Interconnection Project (Main Tool & Other Vendors) | 666 | P |  | KPAE01-S Nov 2023 Invoice for Labor | 45311 | 45314 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10062.94 | 0.86601 | 1556.95 | 0 | 1556.95 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 10062.94 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C063 | USCSB2404003A | 11607.67 | F21P1-0423_H_T&M Hardware_MICU | 4000 | C |  | Plastic 儲物工具報價(新增), tool hookup team | 45384 | 45384 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 11607.67 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 11607.67 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407171A | 11605.69 | WWT B side Project | 4594 | C |  | LB2 VS1380 steel pipes material_WWT | 45504 | 45506 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 11605.69 | 1 | 0 | 0 | 0 | [73 empty] | 11605.69 | -
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C019 | USCSB2404030A | 11598 | F21P1 Hitachi Interconnection | 4026 | C |  | ME: KPCD10: CABLE PULL | 45385 | 45387 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 11598 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 11598 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304072A | 11591.07 | F21P1 WWT package (Installation and 2 batch tanks) | 1911 | C |  | Sump pipe PVC | 45041 | 45048 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 11591.07 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 10812.07 | 779 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401208A | 11575 | F21P1-0404_H_labor for 50 tools_MICU | 3393 | C |  | Hardware request for HK Power/PPL trade | 45316 | 45316 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11575 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 11575 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2210006A | 11545.85 | F21P1 UPW | 1490 | C |  | Horiba Conductivity/Resistivity Meter Batch 2 | 44838 | 44838 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved | Replace part of USC2111003A scope (same request for USCSB2209011A but different batch because of lead time) | 100% after goods arrival date-T/T 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 11545.85 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 11545.85 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2403285A | 11530.68 | WWT Change Order (Piping) | 3978 | C |  | WWT Fittings_20240328 (B Side) | 45380 | 45381 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 11530.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 11188.38 |  |  | 1729.602 |  |  | 342.3 | 1729.602 |  |  |  | 1729.602 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405056A | 11530 | Tool Interconnection Project (Main Tool & Other Vendors) | 1097 | P |  | KSECN2-CIP Work with PFA lines - for PFA line modifications and line testing. | 45427 | 45429 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 11530 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 11530 |  |  |  |  | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C037 | USCSB2305043A | 11520 | F21P1 Screen Main tool interconnection | 1968 | C |  | Electric Interconnection | 45057 | 45083 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11520 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 11520 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2305002A | 11450 | Tool Interconnection Project (Main Tool & Module) | 271 | P |  | CVD2 Tool interconnection materials | 45063 | 45068 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11450 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 11450 | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408045A | 11424 | TSMC Fab 21 P1B Tool Hook Up | 4636 | C |  | Stainless steel materials for L30 clean room area, P1-B construction, Tool hookup team | 45513 | 45513 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11424 | 0 | 11424 | [74 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311054A | 11402.7 | F21P1-0404_H_labor for 50 tools_MICU | 2909 | C |  | Wire TCXH For Third KDIGA3 KECOT1 KETRT7 KKDB03 KPOV04 KKDB04 KKSV02 | 45241 | 45251 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11402.7 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 11402.7 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2304007A | 11402.54 | F21P1 WWT package (Installation and 2 batch tanks) | 1848 | C |  | (2) Sediment Tank Boxes for Sandblasting Lab | 45022 | 45027 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 11402.54 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 2280.51 | 0 | [5 empty] | 9122.03 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2311081A | 11394.53 | Tool Interconnection Project (Main Tool & Other Vendors) | 549 | P |  | KETRT8 - Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards. | 45259 | 45331 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 10595.16 | 0.92985 | 799.37 | 8737.08 | -7937.71 | 0 | [49 empty] | 0 |  |  | 1614.06 | 0 | 0 |  | 8981.1 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405029A | 11300.93 | Tool Interconnection Project (Main Tool & Other Vendors) | 1088 | P |  | KDCRS1-rework - DNS SCREEN INTERCONNECTS | 45419 | 45420 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 11300.93 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 11300.93 | [10 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2405116A | 11297 | F21P1 WWT package (Installation and 2 batch tanks) | 4145 | C | -01 | WWT - Material Modify Chemical Tanks Level Guage to Flange Connection | 2024/5/21 2024/6/10 | 2024/5/22 2024/6/13 | 3887 | 7410 | V |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | PR R1: Due to Harrington made a mistake when pricing the flanges. | [13 empty] | 11297 | 1 | 0 | 0 | 0 | 11297 | [70 empty] | 11297 | 5648.5 |  | - | 5648.5 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404137A | 11250 | Chemical & WCCS B Side Project | 4121 | C |  | CPVC 料補齊.T2 | 45400 | 45400 | [6 empty] | ZHENGTONG INTERNATIONAL LIMITED | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11250 | 0 | 11250 | 0 | [54 empty] | 0 |  | 0 | [8 empty] | 11250 | [5 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C037 | USCSB2301030A | 11248.44 | F21P1 Screen Main tool interconnection | 1651 | C |  | DIF LA3000U Exhaust material | 44938 | 44948 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11248.44 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 10123.6 | 0 | [5 empty] | 1124.84 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Micron - Material |  |  |  | Others |  |  | USC24C001 | USCSB2408124A | 11200 | Micron - Chemical SOLBLE RN3000 | 4735 | C |  | SOLBLE RN3000 20kg x 7 drums | 45531 | 45533 | [6 empty] | MITSUBISHI GAS CHEMICAL TRADING, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11200 | 11200 | 0 | 0 | [73 empty] | -
Non-TSMC | Organo |  |  |  | Others |  |  | USC24C013 | USCSB2407077A | 11135 | Organo USA - UPW Electrical | 4493 | C |  | Foxboro B Side Calibration | 45486 | 45491 | [6 empty] | Kaoten Scientific Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 11135 | 0 | 11135 | 0 | [73 empty] | - |  |  | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2405013A | 11135 | F21P1 UPW | 4024 | C |  | Kaoten Foxboro Calibration A Side | 45415 | 45433 | [6 empty] | Kaoten Scientific Co., Ltd | PR Approved | PO Approved | [14 empty] | 11135 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 11135 |  |  |  |  | - |  |  | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2404022A | 11123.04 | F21P1 Slurry package | 4018 | C |  | TSMC/ FAB21:A Side Chem Temp Hand Rail Fab and Install | 45384 | 45385 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 11123.04 | 11123.04 | 0 | 11123.04 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 11123.04 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2405074A | 11115 | F21P1 AMAT Interconnection | 4094 | C |  | Borrowed Delta Wye People | 45423 | 45446 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 11115 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 11115 | [8 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312019A | 11110.46 | Tool Interconnection Project (Main Tool & Module) | 568 | P | -01 | KST-70R Tube | 45265 | 2023/12/8 2023/12/15 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved | Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11110.46 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 11110.46 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV |  |  |  | Low Voltage | Electrical | M+L | USC21C008 | USCSB2409007A | 11099 | F21P1 CCTV & Security | 4777 | C |  | F21 P1 VOC Electricity Change Order _CO#35 | 45539 | 45542 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 11099 | 1 | 0 | 11099 | -11099 | 0 | [73 empty] | 11099
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C003 | USCSB2305112A | 11084.61 | F21P1 UPW | 2029 | C |  | WWT CCB materials | 45072 | 45083 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 11024.98 | 0.99462 | 59.63 | 0 | 59.63 | 110.2498 | [33 empty] | 0 |  | 3304.26 | 7606.93 |  | 113.79 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 110.2498
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312079A | 11084.4 | Tool Interconnection Project (Main Tool & Module) | 622 | P |  | KPOCS1 & KPOCS3 Labor Lit 3 Streimers Install | 45282 | 45287 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1847.4 | 0.16667 | 9237 | 0 | 9237 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 1847.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical Lab | UMEC | The budget execution does not pertain to this project | Chemical Lab | Chemical | Mechanical | Labor | USC22C021 | USCSB2401174A | 11081 | F21P1 Chemical Lab setup | 3359 | C |  | GC Lab Pressure Test | 45314 | 45315 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11081 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 10527 | 0 | 0 |  | 554 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C006 | USCSB2402170A | 11057.3 | F21P1 Slurry package | 3600 | C |  | CDS Divider_HPM_MIC_EA001_24_AZ03 | 45339 | 45367 | [6 empty] | JY TECHS INC. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 11057.3 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 11057.3 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2402102A | 11053.44 | F21P1-0423_H_T&M Hardware_MICU | 3542 | C |  | Plastic第五批短期採購_(MICU_T&M), tool hookup team for tsmc | 45332 | 45337 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 11053.44 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 841.44 | 5045.28 |  | 5166.72 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2305042A | 11042 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1967 | C |  | KPE601-S LIT 2 MMI | 45057 | 45159 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8105 | 0.73402 | 2937 | 0 | 2937 | 0 | [33 empty] | 0 | [6 empty] | 8105 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2311067A | 11034.5 | F21P1 AMAT Interconnection | 2921 | C |  | change order: KCBDA1 Wire Demo and Repull | 45245 | 45260 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11034.5 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 11034.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2312059A | 11030.8 | F21P1 Chemical & WCCS package | 3051 | C |  | CDS Argon for Chemical welding. Blanket order | 45268 | 45273 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10862.89 | 0.98478 | 167.91 | 0 | 167.91 | 0 | [45 empty] | 0 | 0 | 0 | 989.04 | 1994.04 | 2230.4 |  | 0 | 0 | 1208.83 |  | 191.25 |  | 2960.5 |  | 1027.58 | 429.16 | 261.25 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407030A | 11027.53 | F21P1-0404_H_labor for 50 tools_MICU | 4429 | C |  | Generators rentals for HK MIMO for 6 months | 45477 | 2024/7/9 2024/7/11 | -1818.97 | 12846.5 |  |  |  |  | Herc Rentals Inc. | PR Approved | PO Approved | PO R1: James McCormick got a lower price revised quotation from Herc | [13 empty] | 3964.12 | 0.35947 | 7063.41 | 1982.06 | 5081.35 | 0 | [72 empty] | 1982.06 | 1982.06 |  |  | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309021A | 11025.8 | F21P1-0404_H_labor for 50 tools_MICU | 2498 | C |  | Refrigerated Liquid 2.2 & LC230 PSI. Cylinder Rent | 45176 | 45182 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6463.5 | 0.58622 | 4562.3 | 0 | 4562.3 | 0 | [40 empty] | 0 | 0 | 5921 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 253.75 | 0 | 0 | 0 |  | 0 |  | 288.75 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2307126A | 11025.8 | F21P1 Chemical & WCCS package | 2289 | C |  | Argon for Chemical welding. | 45134 | 45139 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | This is a blanket order. Payment will be made based on actual consumption. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10925.64 | 0.99092 | 100.16 | 0 | 100.16 | 0 | [39 empty] | 1027.58 | 0 | 5982.12 | 611.45 | 544.35 |  | 0 | 1628.94 | 20.2 | 0 | 0 |  | 529.15 | 0 | 0 | 0 |  | 0 |  |  |  |  | 661.55 | 37.5 | [5 empty] | 544.35 |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2309188A | 11024 | F21P1-0404_H_labor for 50 tools_MICU | 2656 | C |  | Clamps | 45198 | 45202 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8880.84 | 0.80559 | 2143.16 | 0 | 2143.16 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 3150.66 | 0 | 0 | 5730.18 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401246A | 11022 | F21P1-0404_H_labor for 50 tools_MICU | 3427 | C |  | Poly bags for HK Power trade Third | 45321 | 45321 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 11022 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 11022 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2208014A | 11000 | F21P1 UPW | 1451 | C |  | ABB 150A Circuit Breakers | 44799 | 44804 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 11000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 8910 |  |  |  |  | 0 | 2090 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C014 | USCSB2307058A | 11000 | F21P1 WH2SO4 | 2225 | C | -01 | WH2SO4 HUB BOX | 45120 | 2023/7/25 2023/7/26 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  | WO R1:Trade Term Change (User Informed) | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1650 |  |  | 11000 | 1650 |  |  |  | 1650 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2205014A | 11000 | F21P1 WWT package (Installation and 2 batch tanks) | 1377 | C |  | Modular Pipe Support Assembly Design change order | 44694 | 44697 | [6 empty] | The Blackfin Group | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 11000 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 11000 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2301018A | 10990 | F21P1 WWT package (Installation and 2 batch tanks) | 1640 | C |  | ClearPVC shortage | 44936 | 44944 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 10990 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 10990 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2308117B | 10965 | F21P1 UPW | 2415 | C |  | TOC Replacement Parts | 45157 | 2023/8/22 2023/9/26 2023/9/27 | [6 empty] | Veolia WTS Analytical Instruments, Inc. | PR Approved | PO Approved | R1:incorrect Veolia entity |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 10965 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10965 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408084A | 10960 | F21P1 Module Tool Interconnection LIT2-3 | 4700 | C |  | Lit 2: KPE604-S, KPE606-S, and KPE607-S: Install Dry Laser Anchor | 45521 | 45525 | [6 empty] | Top Chain Construction Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10960 | 0 | 10960 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404001A | 10913.84 | Tool Interconnection Project (Main Tool & Other Vendors) | 956 | P |  | KDMRS2-DNS SCREEN INTERCONNECTS 3/19-3/20/2024 | 45384 | 45391 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 10913.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 10913.84 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2401077A | 10895.74 | Tool Interconnection Project (Main Tool & Other Vendors) | 697 | P |  | Nitrogen, Compressed, 2.2 Nitrogen T | 45317 | 45316 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 10895.74 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 10895.74 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2403047A | 10867.68 | F21P1 Module Tool Interconnection CVD | 3754 | C |  | Cable Sleeving - Snap Tube, Small Box (KST-70R) for LAM tool KCOXN7 | 45357 | 45363 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 10867.68 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 10867.68 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Steel | Material | USC21C009 | USCSB2405150A | 10857.7 | F21P1 WWT package (Installation and 2 batch tanks) | 4179 | C |  | WRC A side platform recover (material) | 45437 | 45442 | [6 empty] | Fibergrate Composite Structures Inc | PR Approved | PO Approved | [14 empty] | 10857.7 | 1 | 0 | 0 | 0 | 10857.7 | [70 empty] | 10857.7 | 5428.85 |  | - | 5428.85 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402264A | 10855.74 | F21P1 WWT package (Installation and 2 batch tanks) | 3689 | C | -01 | WWT Fitting_20240227 (A Side) | 45350 | 45351 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Trade Term Changes from DDP to FOB |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 10855.74 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1811.38 | 1132.52 |  | 7911.84 |  |  |  |  | 542.787 |  |  |  | 1085.574 |  |  |  | 1628.36 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2405120A | 10841.82 | F21P1 WWT package (Installation and 2 batch tanks) | 4148 | C |  | WWT - T-665AA Tank Repair | 45434 | 45436 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 10841.82 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 10841.82 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2310045A | 10800.18 | WWT Change Order (Piping) | 2706 | C |  | WWT- hardware for LJ | 45206 | 45209 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10800.18 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 278.6 | 6398.36 | 4123.22 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Speed Gate | Material | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C008 | USCSB2302027A | 10800 | F21P1 CCTV & Security | 1708 | C |  | Speed Gate/Turnstile | 2023/2/11 2023/2/11 | 44994 | [6 empty] | TUV SUD America, Inc | PR Approved | PO Approved | PR:adding additional scope to this PR |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 10800 | 0 | 10800 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - |  | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311007A | 10800 | F21P1-0404_H_labor for 50 tools_MICU | 2862 | C |  | test pipe pout under different sizes for Yaho | 45231 | [8 empty] | PR Approved | PO Processing |  |  | 0 | [11 empty] | 0 | 0 | 10800 | 0 | 10800 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408132A | 10790.5 | TSMC Fab 21 P1B Tool Hook Up | 4765 | C |  | 8'x8'x40' Mobile Storage Container for HK for 8 months | 45533 | 45552 | [6 empty] | Allied Storage Containers | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10790.5 | 0 | 10790.5 | 0 | [73 empty] | -
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Steel | Labor | USC23C045 | USCSB2310190A | 10775.2 | WWT Change Order (Piping) | 2842 | C |  | WWT FAB drain rigging for common rack installation | 45230 | 45232 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1616.28 |  |  |  | 1616.28 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | W-H2SO4 | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C014 | USCSB2306028A | 10764.51 | F21P1 WH2SO4 | 2063 | C |  | PVDF Material for Vertical Rack | 45085 | 45090 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10764.51 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 10764.51 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2401121A | 10750 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3308 | C |  | Southwest Fastener Open Statement Orders | 45309 | 45309 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10750 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 10750 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2408003A | 10731.44 | WWT B side Project | 4602 | C |  | WWT shortage of Stainless materials on the B side | 45506 | 45513 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 7799 | 0.72674 | 2932.44 | 7799 | -4866.56 | [74 empty] | 7799
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401255A | 10704.3 | F21P1-0404_H_labor for 50 tools_MICU | 3436 | C |  | HK QAQC labels | 45322 | 45324 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 10704.3 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 10704.3 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404016A | 10704.11 | Tool Interconnection Project (Main Tool & Other Vendors) | 971 | P |  | Manpower Pay for RS Payroll for Tool ID: KEMGT1 Time cards 22.13, 2.14, 2.22,2.23, 2.24, 2.26, and 2.28.2024 | 45385 | 45387 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 10704.11 | 0 | 10704.11 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  | Main Contract Scope | UPW | UPW | Mechanical | Material | USC24C008 | USCSB2406055A | 10699.88 | UPW B Side Project | 4288 | C |  | Materials from ORGANO | 45451 | 45454 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 10699.88 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 10699.88 |  |  |  |  | - |  |  | 0
Base-Build | UPW | MMI | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2306027A | 10691 | F21P1 UPW | 2062 | C |  | MMI -ORGANO-RO Re-rotate | 45085 | 45100 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10691 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 10691 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC22C035 | USCSB2405021A | 10686.2 | CAP_A_90772_F21 Phone call base build and Liquid penetrant testing system | 3993 | C |  | F21 P1 parking gates installation-(8/11) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10686.2 | 0 | 10686.2 | 10151.89 | [54 empty] | 0 |  | 0 | [14 empty] | 10151.89 |  | - |  | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203019A | 10665.88 | F21P1 UPW | 141 | P |  | Switch 48 Port、PoE Switch 48 Port、Transceiver Module | 44637 | 44657 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 95% by received-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 10665.88 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 10665.88 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | CRG | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2309029A | 10661.19 | F21P1 Chemical & WCCS package | 2506 | C |  | NFPA Diamond Signs support and install | 45177 | 45182 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7343.45 | 0.6888 | 3317.74 | 0 | 3317.74 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 7343.45 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 3304.97 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2405012A | 10654 | WWT Change Order (Piping) | 3985 | C |  | WWT-UMEC-2023Veteran's day_Overtime | 45415 | 45425 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 10121 | 0.94997 | 533 | 0 | 533 | 506.05 | [54 empty] | 0 |  | 0 |  |  |  | 10121 | [10 empty] | 0 |  | - | 0 | 0 | 0 | 506.05
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2402200A | 10647 | F21P1-0404_H_labor for 50 tools_MICU | 3627 | C |  | Crimper Kit for HK Power trade | 45343 | 45348 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10647 | 1 | 0 | 0 | 0 | 0 | 10647 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C015 | USCSB2409123A | 10646.8 | F21P1 AMHS Wiring Work Outline | 4941 | C |  | 3 person YCF Engineers support to Muratec(20240930~20241230) | 45563 | 45562 | [6 empty] | YUNG CHENG FENG ENGINEERING CO.,LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10646.8 | 0 | 10646.8 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401160A | 10630.34 | F21P1-0404_H_labor for 50 tools_MICU | 3345 | C |  | HK Power Trade Amazon order: Poly bags, tapes, and connectors for QAQC | 45311 | 45327 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 8831.46 | 0.83078 | 1798.88 | 0 | 1798.88 | 0 | 8831.46 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2404096A | 10602 | F21P1 WWT package (Installation and 2 batch tanks) | 4083 | C |  | WRC WWT Observation (Change Order) | 45393 | 45395 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 10602 | 0 | 10602 | 10602 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1590.3 |  |  |  | 1590.3 |  |  |  | 1590.3 |  | 5301 |  | - | 5301 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402047A | 10584 | Tool Interconnection Project (Main Tool & Other Vendors) | 767 | P |  | KETRT4 MANPOWER PAY FOR CCE | 45329 | 45337 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 10584 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 10584 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2406003A | 10566 | Chemical & WCCS B Side Project | 4232 | C |  | CED Wire 0531-1 | 45444 | 45446 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 10566 | 1 | 0 | 10566 | -10566 | 0 | [73 empty] | 10566 |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404033A | 10547.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 988 | P |  | Interconnect cable pull, routing, and 8395 compliance for KSCBH5,6,7,8. Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45393 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 10547.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 10547.2 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404101A | 10547.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 1051 | P |  | Interconnect Cable Pull for KCOXN7. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45408 | 45412 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 10547.2 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 10547.2 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404102A | 10547.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 1052 | P |  | Interconnect Cable Pull for KCTEN2. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45408 | 45412 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 10547.2 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 10547.2 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404103A | 10547.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 1053 | P |  | Interconnect Cable Pull for KCTOA2. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45408 | 45411 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 10547.2 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 10547.2 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403061A | 10542.84 | F21P1-0404_H_labor for 50 tools_MICU | 3766 | C |  | COLLAPSIBLE WIRE CONTAINER WITH CASTERS, for TSMC construction team | 45357 | 45363 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 10542.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 10542.84 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2401191A | 10520.27 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3376 | C |  | Global Solutions LLC Scissor lift EUV Crane Maintenance | 45315 | 45322 | [6 empty] | Global Solutions LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10520.27 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 10520.27 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311033A | 10497 | Tool Interconnection Project (Main Tool & Module) | 507 | P |  | KPI401-S (LIT 1) - CA Exhaust Insulation Labor - Greenberry | 45244 | 45247 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9972.15 | 0.95 | 524.85 | 0 | 524.85 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 9972.15 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311034A | 10497 | Tool Interconnection Project (Main Tool & Module) | 508 | P |  | KPD801-S (LIT 1) - CA Exhaust Insulation Labor - Greenberry | 45244 | 45247 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 9972.15 | 0.95 | 524.85 | 0 | 524.85 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 9972.15 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405186A | 10494.72 | Chemical & WCCS B Side Project | 4229 | C |  | Ryan Herco CPVC/PP/PVDF 0530 | 45443 | 45446 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 10494.72 | 1 | 0 | 6794.42 | -6794.42 | 0 | [64 empty] | 269.36 |  | 3430.94 | [6 empty] | 6794.42 |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311062A | 10469.57 | Tool Interconnection Project (Main Tool & Module) | 531 | P |  | FLEX LT3UAGRY | 45251 | 45258 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 10469.59 | 1 | -0.02 | 0 | -0.02 | 0 | [43 empty] | 0 |  | 10469.59 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312067A | 10451.37 | Tool Interconnection Project (Main Tool & Module) | 613 | P |  | RP350 BATRY PRESS TOOL NO JAWS 4-PCS RP350 STOCK CHANDLER | 45280 | 45280 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10451.37 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 10451.37 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403008A | 10440 | Tool Interconnection Project (Main Tool & Other Vendors) | 835 | P |  | MANPOWER PAY FOR CCE | 45353 | 45363 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 10440 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 10440 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2308102A | 10434.99 | WWT Change Order (Piping) | 2399 | C |  | WWT-double pipe certification | 45156 | 45168 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10234.99 | 0.98083 | 200 | 0 | 200 | 204.6998 | [40 empty] | 0 | 10234.99 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 204.6998
Base-Build | WWT | Scaffolding | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C007 | USCSB2305045A | 10428 | F21P1 VOC package （Installation ) | 1970 | C |  | Scaffold for WWT | 45057 | 45078 | [6 empty] | BrandSafway Solutions, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10428 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 10428 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Equipment | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2209006A | 10396 | F21P1 UPW | 231 | P |  | portable fans 48" 120V/1PH 12 foot power cord | 44806 | 44818 | [6 empty] | Delta T, LLC dba Big Ass Fans | PR Approved | PO Approved |  | 100% by shipping-Net 30 days-After Acceptance | Yi En Wong |  |  | Mirielli Terres | Yi En Wong | [7 empty] | 10396 | 1 | 0 | 0 | 0 | 0 | [17 empty] | 10396 | [10 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401190A | 10388 | F21P1-0404_H_labor for 50 tools_MICU | 3375 | C |  | Cord grip for power trade | 45315 | 45324 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 10388 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 9548 | [7 empty] | 840 |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C005 | USCSB2306051A | 10384 | F21P1 Module Tool Interconnection DIF1-2 | 2085 | C |  | DIFF: ELECTRICAL TRADE - KDAPK2 & KDAPK3 | 45091 | 45137 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 10384 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 10384 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2302017A | 10383 | F21P1 UPW | 1698 | C |  | UPW-Seal pot replacement | 44965 | 44970 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10383 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 10383 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2402272A | 10355 | F21P1 WWT package (Installation and 2 batch tanks) | 3697 | C |  | Davit Arms and Manway Covers | 45350 | 45350 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10355 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 10355 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405121A | 10318.9 | WWT B side Project | 4149 | C |  | WWT Ball Valve_20240521 (B Side) | 45434 | 45436 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 10318.9 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 9531.55 |  | 787.35 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2406018A | 10292.29 | Tool Interconnection Project (Main Tool & Other Vendors) | 1138 | P |  | SS012316S10WPE 1/2 10S 316 WELD PIPE | 45465 | 45470 | [6 empty] | Industrial Pipe and Valve Inc. | PR Approved | PO Approved | [14 empty] | 10292.29 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 10292.29 |  |  |  |  | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USC2111061A | 10252.19 | F21P1 Chemical & WCCS package | 62 | P |  | Ball Valve | 44524 | 44586 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | CF (Trade term check)) | Arrival (delivery) 100.00% NET 30days after shipping | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 10252.19 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 0 |  |  |  | 0 |  |  | 10252.19 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2309167A | 10246.5 | F21P1 Chemical & WCCS package | 2636 | C | -02 | VMB-576A for TS-135 at HPM 20. | 45196 | 2023/10/3 2023/10/6 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | PO R1:Payment Term and Quotation Number Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 10246.5 | 0 | 10246.5 | 10246.5 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 10246.5
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409048A | 10214 | Tool Interconnection Project (Main Tool & Other Vendors) | 1251 | P |  | 8" SUS304 Elbow 90° | 45556 | 45560 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10214 | 0 | 10214 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2404061A | 10181.6 | F21P1 Module Tool Interconnection ETC1-3 | 4053 | C |  | KEMEA1 & KEPPA2 THHN PVC CABLE TRAYS | 45388 | 45394 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 10181.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 10181.6 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USCSB2212016A | 10181 | F21P1 Slurry package | 1589 | C |  | TSMC F21P1 MIC | 44904 | 44909 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 10181 | 0 | 10181 | 10181 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 10181
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2301006A | 10157.5 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1629 | C |  | Harrington PVC&PVDF MICU F21 TOOL NXT | 44931 | 44935 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 10157.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 10157.5 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401033A | 10141 | Tool Interconnection Project (Main Tool & Other Vendors) | 656 | P |  | KPOCS2 Labor | 45308 | 45309 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10141 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 10141 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402202A | 10135 | F21P1 Chemical & WCCS package | 3629 | C | -01 | CDS Air Valves | 45343 | 2024/3/11 2024/4/1 |  |  |  | V |  |  | Marketech International Corp. | PR Approved | PO Approved | R1: Combine the item one&two into 'PFA裡襯球閥150#RF(PB12) +單動常關氣缸:2 |  | Ta Wei Wang | [11 empty] | 10135 | 1 | 0 | 0 | 0 | 10135 | [52 empty] | 0 | 0 | 0 |  | 0 | [13 empty] | 10135 | 0 |  | - | 0 | 0 | 10135
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309010A | 10132.6 | F21P1 Chemical & WCCS package | 2488 | C |  | CDS Southwest Fastener Monthly Order 8/20/23 to 9/20/23 | 45171 | 45224 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8181.79 | 0.80747 | 1950.81 | 0 | 1950.81 | 0 | [41 empty] | 0 | 7160.31 | 0 |  | 1021.48 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1925.19 | [9 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2310039A | 10121.55 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2701 | C | -01 | Border States Electrical Work Material PreFab Area | 45205 | 2023/10/10 2023/10/13 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved | Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10121.55 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 10118.23 | 3.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2308099A | 10119.46 | F21P1 UPW | 2396 | C |  | MCP Bottom Plates | 45155 | 45159 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10119.46 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 10119.46 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2207021A | 10117.89 | F21P1 UPW | 1436 | C |  | Signal amplify equipment | 44765 | 44768 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  | 100% by received-Net 30 days-after acceptance | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 10117.89 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 10117.89 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402092A | 10103.72 | Tool Interconnection Project (Main Tool & Other Vendors) | 807 | P |  | Double contained plastic line and chiller power line from module to tool in L30 for KSECN3 | 45345 | 45349 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 10103.72 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 10103.72 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402067A | 10075.75 | F21P1 WWT package (Installation and 2 batch tanks) | 3509 | C |  | WWT material 01.26 (A Side) | 45330 | 45336 | 10075.75 | [5 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 8936.58 | 0.88694 | 1139.17 | 0 | 1139.17 | 983.0238 | [49 empty] | 0 |  |  | 3358.59 | 0 | 0 |  | 0 |  |  |  | 3683.19 | 503.7875 | 1894.8 |  |  | 1007.575 |  |  |  | 1007.575 |  | 983.0238 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2403212A | 10065 | F21P1 AMAT Interconnection | 3907 | C |  | 350kcmil 3C+GND Power Cable | 45372 | 45381 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 10065 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 10065 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC22C021 | USCSB2309104A | 10000 | F21P1 Chemical Lab setup | 2576 | C |  | Page Observation for FAB and WRC UPW Reimbursement | 45188 | 45191 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 10000 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | CO Scope (adding/additional scope) | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2310058A | 10000 | F21P1 UPW | 2718 | C |  | FAB B Chemical/ UPW Permitting(batch2/2) | 45210 | 45216 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 10000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C005 | USCSB2310059A | 10000 | F21P1 Chemical & WCCS package | 2719 | C |  | Lorry additional 16 RU systems | 45210 | 45234 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 10000 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2212003A | 10000 | F21P1 WWT package (Installation and 2 batch tanks) | 1576 | C |  | FRP Tank Repairs | 44896 | 44897 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Open PO |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 5647 | 0.5647 | 4353 | 0 | 4353 | 451.76 | [28 empty] | 0 |  | 200 |  |  | 4394 | [6 empty] | 0 | 0 | 0 | 0 |  | 1053 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 500 |  |  |  | 500 |  |  |  | 1000 |  | 0 |  | - | 0 | 0 | 0 | 451.76
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Steel | M+L | USC21C003 | USCSB2311116A | 9968 | F21P1 UPW | 2967 | C |  | UPW-WRCL20-MMI-rack revise | 45258 | 45258 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9469.6 | 0.95 | 498.4 | 0 | 498.4 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 9469.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2311060A | 9955.83 | F21P1 AMAT Interconnection | 2915 | C |  | KSSBA3 Wire Demo and Repull | 45245 | 45246 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9955.83 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 9955.83 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407112A | 9954.41 | WWT B side Project | 4527 | C |  | WWT stainless steel material for CDA B | 45492 | 45492 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 9219.67 | 0.92619 | 734.74 | 0 | 734.74 | 0 | [70 empty] | 9219.67 | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404073A | 9914 | Tool Interconnection Project (Main Tool & Other Vendors) | 1027 | P |  | Manpower Pay for Delta Wye Tools KETRTA and KETRTD for Time cards on 4.11, 4.12, and 4.15,2024 | 45401 | 45404 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 9914 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 9914 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2305076A | 9900 | F21P1 WWT package (Installation and 2 batch tanks) | 1997 | C |  | WWT Tanks hydrotest | 5/17/2023 8/17/2024 | 6/6/2023 8/24/2024 | -89100 | 99000 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: As per Jim to closeout the PO. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9900 | 1 | 0 | 0 | 0 | 792 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 14850 | 9900 |  |  | 14850 |  |  |  | 14850 |  | 0 |  | - | 0 | 0 | 0 | 792
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2404103A | 9888 | F21P1 Module Tool Interconnection CVD | 4090 | C |  | CVD Labor | 45413 | 45413 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 9888 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 9888 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407012A | 9859 | Tool Interconnection Project (Main Tool & Other Vendors) | 1150 | P |  | KPAE02-S Pressure Testing Labor | 45485 | 45486 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9859 | 0 | 9859 | 0 | [73 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C019 | USCSB2404218A | 9847 | F21P1 Hitachi Interconnection | 3969 | C |  | ME: KPCD15: CABLE PULLS | 45412 | 45413 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 9847 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [7 empty] | 9847 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2401083A | 9834.74 | F21P1 WWT package (Installation and 2 batch tanks) | 3272 | C |  | WWT: Repair (2) 1" Stripper Tank Nozzle Flanges and FRP New Standoff to Relocate Sandblasting Lab Tank T-196AA Ladder | 45303 | 45303 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 4505.69 | 0.45814 | 5329.05 | 0 | 5329.05 | 360.4552 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1475.211 | 4505.69 |  |  | 1475.211 |  |  |  | 1475.211 |  | 0 |  | - | 0 | 0 | 0 | 360.4552
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C032 | USCSB2403281A | 9829 | F21_AZQR_Hookup_ Interconnection | 3974 | C |  | QR: CHAD LABS (KXIM01-07): INSTALL GAS LINES | 45380 | 45383 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 9829 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 9829 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407092A | 9806.9 | WWT B side Project | 4508 | C |  | WWT CCR system SUS material | 45489 | 45490 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 9806.9 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 9806.9 | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405091A | 9806 | Tool Interconnection Project (Main Tool & Other Vendors) | 1104 | P |  | KPE606-S Exhaust Installation Labor | 45429 | 45435 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 9806 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [13 empty] | 9806 |  |  | - |  |  | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2403296A | 9780.2 | F21P1 AMAT Interconnection | 3988 | C |  | THHN PVC tray cable KCEPA2 & KDGA1 | 45381 | 45395 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | 0 | [11 empty] | 9780.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 9780.2 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404012A | 9775.61 | Tool Interconnection Project (Main Tool & Other Vendors) | 967 | P |  | Connecting PFA chiller lines to chillers and tool, pressure testing lines for KSECN3 3/22-3/23/2024. | 45385 | 45386 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 9775.61 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 9775.61 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | CRG | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406104A | 9775 | Chemical & WCCS B Side Project | 4339 | C |  | TSMC / FAB21: BEND 85 EACH 90 DEGREE ELBOWS WITH A 16" RADIUS WITH 2" DIAMETER .065 WALL 316 SS. | 45463 | 45471 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9775 | 0 | 9775 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406012A | 9753.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 1132 | P |  | KDMRS4-Change order-DNS SCREEN INTERCONNECTS-5/18/2024 and 6/5/2024 | 45458 | 45462 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 9753.4 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 9753.4 | [6 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2311096A | 9748 | F21P1 WWT package (Installation and 2 batch tanks) | 2947 | C |  | WWT-PP Materials | 45251 | 45253 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 9748 | 6738 | 3010 | 9748 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1462.2 |  |  |  | 1462.2 |  |  |  | 1462.2 |  | 2924.4 |  | - | 2924.4 | 3899.2 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402075A | 9723 | Tool Interconnection Project (Main Tool & Other Vendors) | 791 | P |  | Regular interconnect cable pull for PVD2 KSCBH1. Pull cables from L30 to L20, routing cables in cable trays/ conduits, following 8395 routing procedures. | 45343 | 45345 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9723 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 9723 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Labor |  |  | AMHS |  |  | USC23C015 | USCSB2310113A | 9720 | F21P1 AMHS Wiring Work Outline | 2774 | C |  | FAB-1A MML NRTL Nameplate Changes | 45217 | 45220 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9720 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 | 9720 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2305005A | 9701.79 | Tool Interconnection Project (Main Tool & Module) | 274 | P |  | Printer and label to label cables | 45063 | 45084 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9701.79 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 2968.8 |  | 6732.99 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2403073A | 9698.84 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3777 | C |  | RS PAYROLL SERVICES, TIMECARD PAYMENT FOR ASSOCIATES INVOICE#4729 | 45358 | 45362 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 9698.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 9698.84 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408052A | 9648.03 | TSMC Fab 21 P1B Tool Hook Up | 4670 | C |  | Equipment 2331025 Scissor lifts rentals 08/12-12/02 | 45517 | 45518 | [6 empty] | United Rentals | PR Approved | PO Approved | [14 empty] | 2521.15 | 0.26131 | 7126.88 | 0 | 7126.88 | 0 | [72 empty] | 2521.15 | -
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209009A | 9643.39 | F21P1 Chemical & WCCS package | 234 | P0 |  | AECC License | 44835 | 44839 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Chiehwen Chen | Yi En Wong | [7 empty] | 9643.39 | 1 | 0 | 0 | 0 | 0 | 9643.39 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2211034A | 9600 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1567 | C |  | F21-P0176 Foundation Reorder | 44889 | 44894 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved | Damaged Foundation because of 3PL wrongly handling; we will back charge to 3PL |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 9600 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 9600 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309072A | 9599.67 | F21P1 Chemical & WCCS package | 2546 | C |  | Ball valve to work at H20 and slurry sump | 45183 | 45198 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9599.67 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 9599.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C058 | USCSB2309091A | 9591 | F21 EUV Steel Plates | 2564 | C |  | Provide 10lb fire extinguisher and bracket at scaffold entrances (required for fire inspection) | 45184 | 45191 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 9591 | 0 | 9591 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311036A | 9588 | Tool Interconnection Project (Main Tool & Module) | 510 | P |  | Labor to route qty (20) hoses, no connection points. II. Labor to routte and connect qty (2) hoses THC Sub-Fab cabinet. III. Furnish unistrut, clamps and zip ties as required. IV. Furnish Supervision and general conditions. | 45244 | 45253 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9588 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 9588 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2402208A | 9588 | F21P1 WWT package (Installation and 2 batch tanks) | 3635 | C |  | WWT: Fabricate and Install T-1985 Ladder | 45344 | 45348 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9588 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1438.2 | 9588 |  |  | 1438.2 |  |  |  | 1438.2 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2408028A | 9483.94 | WWT B side Project | 4623 | C |  | Water seal pot and pump cable box_WWT | 45511 | 45511 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9483.94 | 0 | 9483.94 | [74 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404041A | 9478.26 | WWT B side Project | 4036 | C |  | WWT Hardware_20240402 (B Side) | 45385 | 45392 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 9478.26 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3799.92 |  | 0 |  | 4293.51 |  | 1384.83 | 1421.739 |  |  |  | 1421.739 |  |  |  | 1421.739 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2206023A | 9476 | F21P1 Slurry package | 1412 | C |  | F21 Raised Floor Pipe engineering | 44735 | 44740 | [6 empty] | SDB, Inc. dba SDB Contracting Services | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | [7 empty] | 9476 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 9476 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402255A | 9459 | F21P1 WWT package (Installation and 2 batch tanks) | 3681 | C |  | WWT materials-2 | 45349 | 45350 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9459 | 1 | 0 | 0 | 0 | 9459 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1418.85 |  |  |  | 1418.85 |  |  | 9459 | 1418.85 |  | 4729.5 |  | - | 4729.5 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2210021A | 9449.04 | F21P1 UPW | 1504 | C |  | Nagano JM31-1L3 | 44847 | 44848 | [6 empty] | Ashcroft Inc. | PR Approved | PO Approved | USC2111018A-01 misorder JM31 | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 9449.04 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 7086.78 |  | 2362.26 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2306125A | 9442.83 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2158 | C |  | Hand tool - Cintas Fire Extinguisher | 45105 | 45110 | [6 empty] | Cintas Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 9442.83 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 9442.83 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308014A | 9440 | Tool Interconnection Project (Main Tool & Module) | 364 | P |  | TEL Interconnect cable pull for KESRT4 (ETC1) | 45155 | 45162 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9440 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 9440 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2403286A | 9412.45 | WWT Change Order (Piping) | 3979 | C |  | WWT SUS Fittings & Pipes_20240328 (A Side) | 45380 | 45380 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 8196.37 | 0.8708 | 1216.08 | 0 | 1216.08 | 1065.5281 | [52 empty] | 0 | 0 | 8196.37 |  | 0 |  |  |  |  | 1411.8675 |  |  |  | 1411.8675 |  |  |  | 1411.8675 |  | 409.8185 |  | - | 655.7096 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310176A | 9398.92 | F21P1-0404_H_labor for 50 tools_MICU | 2829 | C |  | cap/sus 304L for Tunyi. | 45226 | 45240 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9398.92 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 9398.92 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2310163A | 9390 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2817 | C |  | FRP Grating Urgent Request | 45224 | 45225 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9390 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 8920.5 | 0 | 0 | 0 |  |  | 469.5 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2403136A | 9384.48 | Tool Interconnection Project (Main Tool & Other Vendors) | 944 | P |  | Michael Rodriguez 4/2-4/30/2024 - 21 days x 8hrs. | 45380 | 45435 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9384.48 | 0 | 9384.48 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Base-Build | Barcode | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C012 | USC2201003A | 9380.8 | F21 Barcode RFID System | 98 | P |  | warning light (flashing type) | 44572 | 44580 | [6 empty] | ADAMS International LLC | PR Approved | PO Approved |  | 100% Prepayment. | York Yeh |  |  | Hsiang Cheng Lee | York Yeh | N | 44581 | Martin |  |  | 5000 |  | 9380.8 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 9380.8 |  |  | 冲销 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2312036A | 9375.2 | F21 TMAH System | 3029 | C |  | MICU Coating bolts for Tmah. | 45266 | 45269 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9375.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 9375.2 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2407133A | 9365 | WWT B side Project | 4546 | C |  | WWT - A-420AA Support Extensions | 45496 | 45497 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 9365 | 1 | 0 | 9365 | -9365 | 0 | [71 empty] | 0 |  | 9365 | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306015A | 9360 | Tool Interconnection Project (Main Tool & Module) | 300 | P |  | KPOCT5 LIT3- MMI LABOR | 45083 | 45093 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 9360 | 0 | 9360 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404224A | 9339.11 | WWT B side Project | 3974 | C |  | WWT Fittings for Remaining Fittings for Drain_20240429 (B Side) | 45412 | 45413 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 9339.11 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 6667.13 |  | 1432.92 |  | 1239.06 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404061A | 9332.47 | Tool Interconnection Project (Main Tool & Other Vendors) | 1014 | P |  | Manpower Pay for RS Payroll Services . Timecards for 1.30, 2.26, 2.27, 2.28, 2.29, 3.1, and 3.4.2024 | 45398 | 45399 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9332.47 | 0 | 9332.47 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2301034A | 9326 | F21P1 WWT package (Installation and 2 batch tanks) | 1655 | C |  | PP Material - fittings | 44943 | 44959 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 9326 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 9326 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405033A | 9296.25 | Tool Interconnection Project (Main Tool & Other Vendors) | 1091 | P |  | MANPOWER: PINNACLE PEAK WAREHOUSES: 05/06-05/31/2024 REG HRS | 45420 | 2024/5/10 2024/8/2 | -249.75 | 9546 |  |  |  |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | PO R1: Updated the correct reg. & OT hrs to match the invoice. | [13 empty] | 9296.25 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 9296.25 |  |  |  |  | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402061A | 9288.8 | Tool Interconnection Project (Main Tool & Other Vendors) | 779 | P |  | Pulling cables from L30 to L20 and L10 using ladders, scissor lifts, scaffolding, and hand tools. KCSOA5, KCANN3, KCAPN1, KSCTT1, KSHMU1 2/13-3/82024. | 45336 | 45379 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2257.92 | 0.24308 | 7030.88 | 2551.92 | 4478.96 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2257.92 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403271A | 9262.02 | F21P1-0404_H_labor for 50 tools_MICU | 3964 | C |  | Truck Stakebed rental for HK | 45379 | 45401 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 3663.98 | 0.39559 | 5598.04 | 0 | 5598.04 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 3663.98 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Site Expense | USC21C009 | USCSB2401002A | 9254.33 | F21P1 WWT package (Installation and 2 batch tanks) | 3194 | C |  | WWT tools for MU | 45294 | 45296 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9206.45 | 0.99483 | 47.88 | 0 | 47.88 | 92.0645 | 9206.45 | [44 empty] | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 92.0645
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310141A | 9243.21 | F21P1 Chemical & WCCS package | 2799 | C |  | Pillar parts used for VMB of B side. | 45220 | 45224 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9243.21 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 447.47 | 0 |  |  | 0 | 487.55 | 0 |  | 8308.19 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409046A | 9239 | TSMC Fab 21 P1B Tool Hook Up | 4831 | C |  | VOC Detector Shipping & Handling | 45547 | 45549 | [6 empty] | FASTENAL | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9239 | 0 | 9239 | 0 | [73 empty] | -
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2312142A | 9206 | F21P1-0404_H_labor for 50 tools_MICU | 3131 | C |  | HK Fixture Latch for welding training | 45279 | 45295 | [6 empty] | Potex Technologies Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 9206 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 9206 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406010A | 9200 | Tool Interconnection Project (Main Tool & Other Vendors) | 1131 | P |  | Aluminum perforated sheet staggered hole | 45457 | 45460 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9200 | 0 | 9200 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311009A | 9200 | Tool Interconnection Project (Main Tool & Module) | 483 | P |  | accessory material | 45233 | 45250 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9200 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 9200 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | DCR Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2403170A | 9200 | F21P1 WWT package (Installation and 2 batch tanks) | 3867 | C |  | WWT - GB PCO #104 / New Misc. Support Modifications on X/2 | 45367 | 45369 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 9200 | 0 | 9200 | 9200 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 1380 |  |  |  | 1380 |  |  |  | 1380 |  | 4600 |  | - | 4600 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408041A | 9174.16 | Tool Interconnection Project (Main Tool & Other Vendors) | 1190 | P |  | 10/4 VNTC CABLE | 45520 | 45523 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9174.16 | 9173.32 | 0.84 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310137A | 9134.97 | F21P1-0404_H_labor for 50 tools_MICU | 2795 | C |  | Trusval entegris PFA | 45220 | 45223 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9134.97 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 9134.97 |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407037A | 9134 | Tool Interconnection Project (Main Tool & Other Vendors) | 1167 | P |  | KPE605-S CW Whip Connection Support Labor | 45499 | 45502 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 9134 | 1 | 0 | 9134 | -9134 | 0 | [73 empty] | 9134 |  |  | 0
Base-Build | Base-Build | MMI | Main Contract Scope | WWT | WWT | Steel | M+L | USC23C045 | USCSB2310164A | 9125 | WWT Change Order (Piping) | 2818 | C |  | 5.5 Missing Rack Steel | 45224 | 45224 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9125 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 8668.75 | 0 | 0 | 0 |  |  | 456.25 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304029A | 9108.04 | F21P1 WWT package (Installation and 2 batch tanks) | 1869 | C |  | Stainless Steel Pipe in Lorry | 45029 | 45047 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 9108.04 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 9108.04 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2404197A | 9099.81 | F21P1 WWT package (Installation and 2 batch tanks) | 4176 | C |  | WWT Fittings (A Side)_Ryan Herco_20240424 | 45408 | 45412 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 9099.81 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 1364.9715 |  |  |  | 1364.9715 | 9099.81 |  |  | 1364.9715 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2302015A | 9088.5 | F21P1 WWT package (Installation and 2 batch tanks) | 1696 | C |  | PVC from Harrington | 44965 | 44971 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 9088.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 9088.5 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402109A | 9078 | Tool Interconnection Project (Main Tool & Other Vendors) | 821 | P |  | Manpoer Pay for Delta Wye | 45349 | 45353 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 9078 | 0 | 9078 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2308028A | 9066.6 | F21 TMAH System | 2329 | C |  | WWT material for drain & system | 45143 | 45153 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5855.1 | 0.64579 | 3211.5 | 0 | 3211.5 | 2049.285 | [40 empty] | 0 | 0 | 0 | 0 |  | 5855.1 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 453.33 |  |  |  | 906.66 |  |  |  | 453.33 |  | 2049.285 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312053A | 9066 | Tool Interconnection Project (Main Tool & Module) | 599 | P |  | KPOCT1 Labor | 45274 | 45274 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 9066 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 9066 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2403190A | 9007.94 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3887 | C |  | RS Payroll Services manpower labor cost from previous work assigned- open invoices | 45370 | 45372 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 5191.44 | 0.57632 | 3816.5 | 0 | 3816.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 5191.44 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2301065A | 9000.2 | F21P1 Module Tool Interconnection ETC1-3 | 1681 | C |  | ETC E-sensor cable material | 44957 | 44957 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9000.09 | 0.99999 | 0.11 | 0 | 0.11 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 818.19 | 8181.9 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | CO Scope (adding/additional scope) | WWT | WWT | Electrical | Instrument | USC21C009 | USCSB2302014A | 9000 | F21P1 WWT package (Installation and 2 batch tanks) | 1695 | C |  | 40 pic battery charge | 44964 | 44972 | [6 empty] | Gruber Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 9000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 9000 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2301016A | 9000 | F21P1 WWT package (Installation and 2 batch tanks) | 1638 | C |  | FRP Tanks samples | 44936 | 44944 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6000 | 0.66667 | 3000 | 0 | 3000 | 480 | [28 empty] | 0 |  | 6000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 450 |  |  |  | 900 |  |  |  | 450 |  | 0 |  | - | 0 | 0 | 0 | 480
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C003 | USCSB2307090A | 9000 | F21P1 UPW | 2256 | C |  | Aid in Tank Inspection | 45127 | 45131 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 9000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 9000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Southland | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | M+L | USC21C006 | USCSB2308163A | 8990.85 | F21P1 Slurry package | 2457 | C |  | F21 P1 VOC Change Order(southland)_4 | 45164 | 45187 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8990.85 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 8990.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical Lab | MIMO/Rigging | The budget execution does not pertain to this project | Chemical Lab | Chemical | Mechanical | Labor | USC22C021 | USCSB2306127A | 8988 | F21P1 Chemical Lab setup | 2160 | C |  | GC Lab Move-in | 45105 | 45132 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8538.6 | 0.95 | 449.4 | 0 | 449.4 | 0 | [33 empty] | 0 | [6 empty] | 8538.6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 449.4 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2212008A | 8977 | F21P1 Chemical & WCCS package | 1581 | C |  | sample box 640 & 645 | 44898 | 44900 | [6 empty] | Collabratech Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 8977 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 8977 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2312061A | 8955.18 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3053 | C |  | Lee Collins Air Conditioning Installation of HVAC Systems mini split configuration clean rooms | 45269 | 45272 | [6 empty] | Lee Collins Air Conditioning | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8955.18 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 8955.18 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C011 | USCSB2402054A | 8949.45 | F21 TMAH System | 3496 | C | -01 | WWT-TMAH-LCMSMS-set up chemicals | 45329 | 2024/2/9 2024/5/21 2024/7/12 | [6 empty] | Agilent Technologies, Inc. | PR Approved | PO Approved | R1: Change per New Quote R2: Change payment term |  | Yi En Wong | [11 empty] | 0 | 0 | 8949.45 | 0 | 8949.45 | 8949.45 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1342.4175 |  |  |  | 1342.4175 |  |  |  | 1342.4175 |  | 4474.725 |  | - | 4474.725 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2305036A | 8948 | F21P1 WWT package (Installation and 2 batch tanks) | 1959 | C |  | 20" EP+PTFE gaskets | 45056 | 45061 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8762 | 0.97921 | 186 | 0 | 186 | 175.24 | [33 empty] | 0 | [6 empty] | 8593.18 | 0 | 168.82 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 175.24
Base-Build | UPW | Rosendin | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2306014A | 8892.58 | F21P1 UPW | 2048 | C |  | Motor Rewire | 45083 | 45100 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 8892.58 | 0 | 8892.58 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403067A | 8871.1 | F21P1-0404_H_labor for 50 tools_MICU | 3772 | C |  | Desk mat is required in the laydown area for materials and tools to prevent damage. Shared by all HK system | 45358 | 45363 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 7818.85 | 0.88138 | 1052.25 | 0 | 1052.25 | 0 | 7818.85 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408082A | 8853.54 | TSMC Fab 21 P1B Tool Hook Up | 4698 | C |  | Hand tools for HK power trader JY for 200 tools | 45520 | 45527 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 8486.94 | 0.95859 | 366.6 | 8853.54 | -8486.94 | 0 | [73 empty] | 8486.94
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C004 | USCSB2404173A | 8816 | F21P1 Module Tool Interconnection CMP1 | 4154 | C |  | CMP: KMOPA5: ROUTE PFA LINE TO CPVC DOUBLE CONTAINMENT PIPE. ROUTE TO DIO3 GENERATOR. | 45405 | 45412 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 8816 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [7 empty] | 8816 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C003 | USCSB2308126A | 8802 | F21P1 UPW | 2423 | C |  | UPW-8/20 Sunday work for commissioning check | 45160 | 45161 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 8802 | 0 | 8802 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8802 | [7 empty] | 8361.9 |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401078A | 8797.97 | Tool Interconnection Project (Main Tool & Other Vendors) | 698 | P |  | Cable pull KETRT1. - L30 to L20 Power/Signal - L30 to L10 Signals - L20 to L20 Power/Signal - L30 to L20 Chiller Hoses (QTY 2) - Install Signal Wrap - 8395 | 45317 | 45348 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5965.27 | 0.67803 | 2832.7 | 16750.7 | -13918 | 0 | [52 empty] | 0 | 0 | 0 |  | 5965.27 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Material |  |  | AMHS |  |  | USC23C015 | USCSB2308065A | 8792.8 | F21P1 AMHS Wiring Work Outline | 2363 | C |  | Channel Tray Elbows and Covers | 45148 | 45152 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8792.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 8792.8 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC24C008 | USCSB2405079A | 8760 | UPW B Side Project | 4099 | C |  | ICPMS LAB Train 2 CO To ORGANO | 45425 | 45427 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8760 | 0 | 8760 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310056A | 8760 | F21P1 Chemical & WCCS package | 2716 | C |  | Welder equipment for Chemical welding. | 45210 | 45211 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8760 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 5840 | 2920 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2312089A | 8732.4 | F21P1-0423_H_T&M Hardware_MICU | 3081 | C |  | Shared materials for plastic system, tool hook up | 45274 | 45279 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8732.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 5157.5 | 0 | 1682.99 |  | 938.61 | 578.1 | 375.2 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402256A | 8732.06 | F21P1-0404_H_labor for 50 tools_MICU | 3682 | C |  | for UPW system 預置區, tool hookup team | 45349 | [7 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 8096 | 0.92716 | 636.06 | 0 | 636.06 | 0 | [52 empty] | 8096 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC24C009 | USCSB2405059A | 8715 | F21P1 Nova Interconnection | 4094 | C |  | PCA: NOVA: KUECN4: CuDD SLIP STREAM CONNECTION FLOW. | 45421 | 45447 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 8715 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 8715 | [6 empty] | - |  |  | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2308057A | 8700 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2355 | C |  | Uline Hand Tool | 45147 | 45152 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8700 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 8700 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409105A | 8694 | TSMC Fab 21 P1B Tool Hook Up | 4913 | C |  | MICU Spotter Quote | 45561 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 8694 | 0 | 8694 | 0 | [73 empty] | -
Base-Build | CCTV | NUUO | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Labor | USC22C001 | USCSB2405017A | 8663.34 | F21 P1 Office and WH Security and CCTV | 3989 | C |  | F21 P1 parking gates installation-(4/11) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8663.34 | 0 | 8663.34 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311073A | 8651 | Tool Interconnection Project (Main Tool & Module) | 541 | P |  | Unistrut clamps and zip ties | 45258 | 45266 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8218.45 | 0.95 | 432.55 | 0 | 432.55 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 8218.45 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311040A | 8651 | Tool Interconnection Project (Main Tool & Module) | 514 | P |  | I. Labor to route qty (18) hoses, no connection points. II. Labor to routte and connect qty (2) hoses THC Sub-Fab cabinet. III. Furnish unistrut, clamps and zip ties as required. IV. Furnish Supervision and general conditions. | 45245 | 45250 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8218.45 | 0.95 | 432.55 | 0 | 432.55 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 8218.45 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304028A | 8624.85 | F21P1 WWT package (Installation and 2 batch tanks) | 1868 | C |  | TMAH bolts / Small size bolts | 45029 | 45042 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8624.6 | 0.99997 | 0.25 | 0 | 0.25 | 0 | [33 empty] | 0 | 3009.2 |  |  |  | 5615.4 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C035 | USCSB2410024A | 8608.27 | TSMC F21 Heating Jacket Installation | 4967 | C |  | DP Design Change_AMHS_1/7 batch | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 8608.27 | 0 | 8608.27 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407127A | 8588.7 | WWT B side Project | 4541 | C |  | MIC/BMWC/Okland B side缺料_WWT | 45493 | 45496 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 8588.7 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1360.77 | 0 | 7227.93 | - | 0 | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2401172A | 8569 | F21P1 WWT package (Installation and 2 batch tanks) | 3357 | C |  | WWT:Design,fabricate,Deliver,and install 2 ladders in FAB/LB2 to replace staircases on platforms that clashing with dike wall | 45314 | 45314 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 8569 | 1 | 0 | 428.45 | -428.45 | 407.0275 | [47 empty] | 0 | 0 | 0 |  |  | 8140.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 428.45 | 0 | 0 | 0 | 407.0275
Base-Build | UPW |  |  |  | UPW | Mechanical | M+L | USC24C008 | USCSB2407120A | 8548 | UPW B Side Project | 4534 | C |  | L20 Loop 3 Pipe Adjustment_UPW | 45492 | 45499 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8548 | 0 | 8548 | 0 | [73 empty] | - |  |  | 0
Base-Build | Slurry | MMI | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2401078A | 8524 | F21P1 Slurry package | 3267 | C |  | SDS A side expansion two cabinets | 45303 | 45303 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8524 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 8097.8 | 0 | 0 |  | 0 |  | 426.2 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406014A | 8521.44 | Tool Interconnection Project (Main Tool & Other Vendors) | 1134 | P |  | KRWRS1 - rework (change order)-DNS SCREEN INTERCONNECTS-5/1, 5/6, and 5/8/2024 | 45461 | 45465 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 8521.44 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 8521.44 |  |  | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403009A | 8506.8 | F21P1 WWT package (Installation and 2 batch tanks) | 3717 | C |  | WWT LSR SUS material | 45352 | 45356 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 8506.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 8506.8 |  | 0 |  |  |  |  | 1276.02 |  |  |  | 1276.02 |  |  |  | 1276.02 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401118A | 8506.39 | F21P1-0404_H_labor for 50 tools_MICU | 3305 | C | -01 | D-ring anchorage for PPL trade | 45308 | 2024/1/18 2024/1/22 | [5 empty] | V | WW Grainger Inc | PR Approved | PO Approved | R1: Due to Grainger line of credit limit, change the payment terms from Net 30 Days to 100% prepayment by Credit Card |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8506.39 | 1 | 0 | 0 | 0 | 0 | 8506.39 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308013A | 8496 | Tool Interconnection Project (Main Tool & Module) | 363 | P |  | TEL interconnect Cable pull KECOT2 | 45154 | 45162 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8496 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 8496 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C001 | USCSB2310131A | 8496 | TEL Main Tool Interconnection | 2789 | C |  | San Tan Fire Warehouse Labor | 45219 | 45223 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 8496 | 0 | 8496 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | CCE | DCR Scope | WWT | WWT | Electrical | Material | USC23C045 | USCSB2311109A | 8485.34 | WWT Change Order (Piping) | 2960 | C |  | WWT CCE Change Orders_DC 680V cable CO | 45253 | 45259 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8485.34 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 8485.34 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC24C005 | USCSB2405106A | 8449.1 | Chemical & WCCS B Side Project | 4137 | C |  | CHEM_B side FB1-F20 VMB construction | 45430 | 45432 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 8449.1 | 1 | 0 | 8449.1 | -8449.1 | 0 | [73 empty] | 8449.1 |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USC2112017A | 8448 | F21P1 Chemical & WCCS package | 84 | P |  | Ball Valve | 44541 | 44566 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | NO CF | 100% by delivery (Net 30 days) | Cherry Chang |  | twelve (12) months following delivery | Stephon Dean | Cherry Chang | N | 44571 | Henry |  | N | 5000 |  | 8448 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 4048 | 176 | [5 empty] | 4224 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403123A | 8437.76 | Tool Interconnection Project (Main Tool & Other Vendors) | 938 | P |  | Regular interconnect cable pull on KCTOA1 for L30, L20, and L10 | 45378 | 45380 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 8437.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 8437.76 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402076A | 8437.76 | Tool Interconnection Project (Main Tool & Other Vendors) | 792 | P |  | Pulling interconnect cabling on KSCTT1 from L30 to L20 and L10. Pulling cables from L30 to L20 and L10, using cable tray and conduit, and following the 8395 cable routing specifications. | 45343 | 45345 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8437.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 8437.76 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309009A | 8437.5 | Tool Interconnection Project (Main Tool & Module) | 403 | P |  | Electrical cable pull for KESRT4-TEL | 45182 | 45204 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8437.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 8437.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310201A | 8436.65 | F21P1-0404_H_labor for 50 tools_MICU | 2852 | C |  | grainger hardware shared materials | 45230 | 45232 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8436.65 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 | 8424.23 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 12.42 | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309017A | 8425 | Tool Interconnection Project (Main Tool & Module) | 408 | P |  | install ACC 10" duct insulation | 45185 | 45205 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8003.75 | 0.95 | 421.25 | 0 | 421.25 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 8003.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405006A | 8420.79 | Tool Interconnection Project (Main Tool & Other Vendors) | 1065 | P |  | KCSCS6-DNS SCREEN INTERCONNECTS-4/15-4/16/2024 | 45416 | 45422 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 8420.79 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 8420.79 | [10 empty] | - |  |  | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2403174A | 8404.77 | F21P1-0404_H_labor for 50 tools_MICU | 3871 | C |  | Scissor lift for HK department | 45367 | 45369 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2682.2 | 0.31913 | 5722.57 | 0 | 5722.57 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 2682.2 | - | 0 | 0 | 0
Base-Build | Slurry |  | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USCSB2406017A | 8385 | F21P1 Slurry package | 4243 | C |  | FAB A SDS Permit Revision | 45447 | 45449 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8385 | 8385 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2311053A | 8381.9 | F21P1 Chemical & WCCS package | 2908 | C |  | CDS B side anchor plates | 45240 | 45251 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8381.9 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 8381.9 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2404124A | 8372 | F21P1 Module Tool Interconnection ETC1-3 | 3965 | C |  | KEMEL8 NEED TO INSTALL DAQ E-SENSOR AN CABLE ROUTING | 45398 | 45456 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8372 | 0 | 8372 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405045A | 8360 | Chemical & WCCS B Side Project | 4052 | C |  | CHEM_WCCS _hardware for standing by materials (TCELC) | 45420 | 45422 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved | [14 empty] | 8360 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 4560 |  |  | 8360 | 3800 | [6 empty] | - |  |  | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USCSB2404031A | 8350 | F21P1 Slurry package | 4027 | C |  | 帆宣計價單-美國tsmc CPVC 平接 | 45385 | 45393 | [6 empty] | JHENGTONG INTERNATIONAL LIMITED | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 8350 | 0 | 8350 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 8350 | [5 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2403012A | 8307.1 | F21P1 AMAT Interconnection | 3720 | C | -01 | Core hole Conduit | 3/1/2024 4/4/2024 | 3/18/2024 4/5/2024 | 2507.75 | 5799.35 |  |  | V |  | Wesco Distribution, Inc. | PR Approved | PO Approved | PR R1: The quantity adjustment is made in accordance with the subcontractor's request and has been approved by the AMAT PM. |  | Yikang Wang | [11 empty] | 7167.21 | 0.86278 | 1139.89 | 0 | 1139.89 | 0 | [52 empty] | 0 | 7167.21 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406142A | 8300 | F21P1-0404_H_labor for 50 tools_MICU | 4380 | C |  | HK P1B NFPA 70E Electrical Hazards Training required for people working with or around electricity. | 45471 | 45476 | [6 empty] | LC LIND, LLC | PR Approved | PO Approved | [14 empty] | 8300 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 8300 |  |  |  |  | - |  |  | 0
Base-Build | Chemical | Material | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308049A | 8298.35 | F21P1 Chemical & WCCS package | 2347 | C |  | TGCM Duty Room items – Tan lockers (Qty:10) | 45146 | 45152 | [6 empty] | High Density, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8298.35 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 8298.35 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403045A | 8245.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 871 | P |  | BPT 437SLTI 3IN STR L/T CONN STEEL 3IN MALL LTI CONNECTOR | 45363 | 45363 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 8245.11 | 1 | 0.01 | 0 | 0.01 | 0 | [52 empty] | 0 | 0 | 0 |  | 8245.11 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404056A | 8240 | Tool Interconnection Project (Main Tool & Other Vendors) | 1009 | P |  | KDSET1 - TEL INTERCONNECTS 1/29/24-3/8/24 | 45393 | 45394 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 8240 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 8240 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C034 | USCSB2410027A | 8225.65 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/ N2/APK/UPK/ASRS | 4970 | C |  | DP Design Change_AMHS_4/7 batch | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 8225.65 | 0 | 8225.65 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC22C012 | USCSB2403014A | 8225 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3723 | C |  | UPW-Tomoe valve for train B | 45352 | 45355 | [6 empty] | Tomoe USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 8225 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 8225 |  |  |  |  | 7813.75 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209014A | 8214.22 | F21P1 Chemical & WCCS package | 239 | P0 |  | Dell Laptop | 44825 | 44826 | [6 empty] | Dell Technologies | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 8214.22 | 1 | 0 | 0 | 0 | 0 | 8214.22 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402244A | 8213.4 | F21P1-0404_H_labor for 50 tools_MICU | 3670 | C |  | Clear PVC Y-Strainers with PP Filter(20mesh), tool hookup team | 45347 | 45350 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8213.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 8213.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309019A | 8210 | Tool Interconnection Project (Main Tool & Module) | 410 | P |  | install ACC 10" duct insulation | 45185 | 45202 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7799.5 | 0.95 | 410.5 | 0 | 410.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7799.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309018A | 8210 | Tool Interconnection Project (Main Tool & Module) | 409 | P |  | install ACC 10" duct insulation | 45185 | 45205 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7799.5 | 0.95 | 410.5 | 0 | 410.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7799.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405023A | 8185.36 | Tool Interconnection Project (Main Tool & Other Vendors) | 1082 | P |  | KDMRS2 - rework | 45419 | 45419 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 8185.36 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 8185.36 | [10 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209010A | 8177.29 | F21P1 Chemical & WCCS package | 235 | P0 |  | Dell Laptop | 44825 | 44826 | [6 empty] | Dell Technologies | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 8177.29 | 1 | 0 | 0 | 0 | 0 | 8177.29 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2312197A | 8174.12 | F21P1-0404_H_labor for 50 tools_MICU | 3184 | C |  | markers, dish soap, security cart, suction cup, and wire cart for PCW trade CYH | 45290 | 45293 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8174.12 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 8174.12 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2309044A | 8171 | F21P1 Chemical & WCCS package | 2521 | C |  | 200 ea. CDS Seismic Corner Anchor Brackets. | 45181 | 45195 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8171 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7762.45 | 0 | 0 | 0 |  |  | 408.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Steel | M+L | USC23C045 | USCSB2311063A | 8160 | WWT Change Order (Piping) | 2918 | C |  | WWT-Safetystep for HPM | 45245 | 45250 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 8160 | 0 | 8160 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1224 |  |  |  | 1224 |  |  |  | 1224 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USC2404041A | 8160 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 995 | P |  | MANPOWER: PINNACLE PEAK WAREHOUSE | 45391 | 45399 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8160 | 0 | 8160 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403016A | 8142.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 843 | P |  | KCSCS1 Pressure test | 45356 | 45359 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8142.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 8142.5 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311016A | 8113.92 | F21P1-0404_H_labor for 50 tools_MICU | 2871 | C |  | Plastic Submersible Cord Grip, NPT Threads for Third | 45233 | 45241 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8113.92 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 8113.92 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402087A | 8108.79 | F21P1 Chemical & WCCS package | 3528 | C |  | CDS HPM Punch materials | 45331 | 45337 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 8108.79 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 8108.79 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2305119A | 8085 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2034 | C |  | Additional outlet | 45077 | 45091 | [6 empty] | RMJ Electrical Contractors Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8085 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 8085 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404076A | 8076.18 | WWT B side Project | 4067 | C |  | WWT Fittings for 60604_20240408 (B Side) | 45391 | 45393 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lisa Chan | [11 empty] | 8076.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 8076.18 |  |  | 1211.427 |  |  |  | 1211.427 |  |  |  | 1211.427 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Steel | M+L | USC21C003 | USCSB2401203A | 8025 | F21P1 UPW | 3388 | C |  | UPW-mezz 3-egress ladder revise | 45316 | 45321 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7623.75 | 0.95 | 401.25 | 0 | 401.25 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 7623.75 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2306013A | 8012.83 | F21P1 Chemical & WCCS package | 2047 | C |  | NFPA Diamond Signs for chemical tanks | 45080 | 45089 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8012.83 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 8012.83 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309162A | 8002.24 | WWT Change Order (Piping) | 2632 | C |  | Small order: TW material PVC insert fitting | 45195 | 45202 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8002.24 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 8002.24 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401126A | 8001.2 | F21P1-0404_H_labor for 50 tools_MICU | 3313 | C |  | Gasket and seal for HK Power trade | 45309 | 45314 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8001.2 | 1 | 0 | 2700.2 | -2700.2 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 5301 |  | 0 | [14 empty] | 0 |  | 2700.2 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2212041A | 8000 | F21P1 WWT package (Installation and 2 batch tanks) | 1612 | C |  | MIC Water Tanks Painting | 44916 | 44916 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 8000 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 8000 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C003 | USCSB2312016A | 8000 | F21P1 UPW | 3010 | C |  | UPW-Linde-Nitrogen for test(Open PO) | 45265 | 45268 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 717.14 | 0.089643 | 7282.86 | 0 | 7282.86 | 0 | [45 empty] | 0 | 0 | 568.81 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 148.33 | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407056B | 7995.67 | TSMC Fab 21 P1B Tool Hook Up | 4485 | C |  | P1B EEW PPE for HK Power for 100 tools | 45484 | 45499 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7995.67 | 7995.68 | -0.01 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406004A | 7962.62 | Tool Interconnection Project (Main Tool & Other Vendors) | 1124 | P |  | KDCRS1-rework - DNS SCREEN INTERCONNECTS-4/30/24 | 45450 | 45456 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 7962.62 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 7962.62 | [6 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306033A | 7953.5 | Tool Interconnection Project (Main Tool & Module) | 317 | P | -01 | Lugs for LAM Cable - cable manufacturing for LAM | 2023/6/10 2023/8/2 | 2023/6/23 2023/08/09 | -716 | 8669.5 |  |  |  |  | Motion Automation Intelligence | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7953.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 1448 | 0 |  | 0 | 0 | 2212.5 | 0 | 0 |  |  | 0 | 0 | 4293 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C014 | USCSB2406074A | 7950 | F21P1 AMHS Power Panel | 4306 | C |  | AMHS DP Breakers due to TSMC Design Change | 45457 | 45471 | [6 empty] | THIRD ENTERPRISE CO., LTD | PR Approved | PO Approved | [14 empty] | 7950 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 7950 | - |  |  | 0
Base-Build | VOC | Material | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Electrical | Material | USC21C007 | USCSB2304085A | 7939.06 | F21P1 VOC package （Installation ) | 1924 | C |  | Control wire for VOC 2 & 3 | 45045 | 45048 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7939.06 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 7939.06 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311037A | 7937.09 | Tool Interconnection Project (Main Tool & Module) | 511 | P |  | Manpower Labor for Tool KECOT5 | 45245 | 45330 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1770.16 | 0.22302 | 6166.93 | 14589.22 | -8422.29 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1770.16 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C004 | USCSB2210045A | 7926.2 | F21P1 WWT package （USA EQ-FRP tank) | 1527 | C |  | TUNNEL Sump Pit Pump RT Fitting | 44860 | 44861 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 7926.2 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 7926.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404032A | 7910.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 987 | P |  | Interconnect cable pull, routing, and 8395 compliance for KCSOA3.Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45392 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404031A | 7910.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 986 | P |  | Interconnect cable pull, routing, and 8395 compliance for KCSAO5. Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45392 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404034A | 7910.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 989 | P |  | Interconnect cable pull, routing, and 8395 compliance for KCOXN8. Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45394 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404035A | 7910.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 990 | P |  | Interconnect cable pull, routing, and 8395 compliance for KCTEN1. Pull cables from L30 to L20 and L10, follow 8395 specifications, route ca | 45387 | 45394 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404036A | 7910.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 991 | P |  | Interconnect cable pull, routing, and 8395 compliance for KCTOA1.Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45394 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405107A | 7910.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 1105 | P |  | Interconnect Cable Pull for KCSCN4-Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45429 | 45435 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 7910.4 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403023A | 7896 | Tool Interconnection Project (Main Tool & Other Vendors) | 849 | P |  | KKDB06: EXAHUST INSTALL ADDTL DAYS | 45358 | 45362 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 7896 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7896 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | DCR Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2307131A | 7891.61 | F21P1 Chemical & WCCS package | 2293 | C |  | Additional for GF price increase | 45135 | 45139 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7891.6 | 1 | 0.01 | 0 | 0.01 | 0 | [36 empty] | 7891.6 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2307016A | 7878.8 | F21P1 Module Tool Interconnection CVD | 2188 | C |  | CVD HVCR interconnect materials -CVD HVCR connectors for interconnection for tool ID KCANN2, KCANN1, KCANN3, KCSCN3, KDALS2, | 45113 | 45119 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7878.8 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 7878.8 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310055A | 7866 | F21P1 Chemical & WCCS package | 2715 | C |  | 1" 316 EP tube for Yaho work at Lorry FNDP | 45210 | 45212 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7752.15 | 0.98553 | 113.85 | 0 | 113.85 | 0 | [40 empty] | 0 | 0 | 0 | 7752.15 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 78.66 | [9 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311012A | 7860 | F21P1-0404_H_labor for 50 tools_MICU | 2867 | C | -01 | Mesh bins, shoe covers & racks | 45232 | 2023/11/6 2023/11/14 | -190 | 8050 |  | V |  |  | U-Line Corporation | PR Approved | PO Approved | PO R1:tax exempt, no longer need shoe cover |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 7860 | 0 | 7860 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C029 | USCSB2402029A | 7858 | EBO21- Tool interconnection | 3472 | C |  | EBO: ZFP3-1: INSTALL GEX EXHAUST | 45325 | 45331 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 7858 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 7858 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401105A | 7830.28 | F21P1-0404_H_labor for 50 tools_MICU | 3292 | C |  | Male cord grip for HK Power trade | 45307 | 45351 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 7830.28 | 1 | 0 | 0 | 0 | 0 | 7830.28 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401067A | 7825 | Tool Interconnection Project (Main Tool & Other Vendors) | 687 | P |  | KPE606-S Labor | 45316 | 45317 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7825 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 7825 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401065A | 7825 | Tool Interconnection Project (Main Tool & Other Vendors) | 685 | P |  | KPE603-S Labor | 45316 | 45317 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7825 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 7825 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401066A | 7825 | Tool Interconnection Project (Main Tool & Other Vendors) | 686 | P |  | KPE605-S Labor | 45316 | 45317 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7825 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 7825 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401068A | 7825 | Tool Interconnection Project (Main Tool & Other Vendors) | 688 | P |  | KPE607-S Labor | 45316 | 45317 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 7825 | 0 | 7825 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401061A | 7825 | Tool Interconnection Project (Main Tool & Other Vendors) | 682 | P |  | KPE603-S Labor | 45314 | 45316 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7825 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 7825 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402035A | 7808.95 | Tool Interconnection Project (Main Tool & Other Vendors) | 759 | P |  | KETRTE and KETRTC labor-cable pull, L30-L20 cable drop, routing cables and 8395 | 45329 | 45330 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 7808.95 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 7808.95 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2402179A | 7808 | F21P1-0404_H_labor for 50 tools_MICU | 3608 | C |  | M18 18V Lithium-Ion Cordless Force Logic 600 MCM Crimper Kit with 600 MCM Copper U-Style Die Kit for HK Power trade | 45342 | 45343 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7098 | 0.90907 | 710 | 0 | 710 | 0 | 7098 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312065A | 7808 | Tool Interconnection Project (Main Tool & Module) | 611 | P |  | Labor for KCAOA4 - EMT conduit and liquid tie conduit, run wire between L10, L20, L30 | 45279 | 45279 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 7808 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 7808 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C013 | USCSB2401089A | 7800 | F21P1 AMC THC Monitoring System | 3278 | C |  | FAB EBO AMC Hookup - Permitting | 45304 | 45307 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7800 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 3305 | [9 empty] | 4495 | 4496 |  | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | MIMO/Rigging | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Equipment ( Tank 等工程相關的設備) | USC21C011 | USCSB2308095A | 7796 | F21 TMAH System | 2392 | C |  | MIC-116-23 Equipment Move in FAB LB2 column A.5/10 | 45155 | 45161 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7796 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 7796 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401086A | 7778.56 | Tool Interconnection Project (Main Tool & Other Vendors) | 704 | P |  | KCSOA1 regular interconnect for cable pull | 45321 | 45322 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 7778.56 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 7778.56 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401087A | 7778.56 | Tool Interconnection Project (Main Tool & Other Vendors) | 705 | P |  | KCANN3 regular interconnect and cable pull | 45321 | 45322 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 7778.56 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 7778.56 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2301054A | 7770 | F21P1 UPW | 1671 | C |  | Anchor sensor plates | 44953 | 44963 | [6 empty] | An-Cor Industrial Plastics, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7770 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 7770 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2405170A | 7742.98 | F21P1 Module Tool Interconnection ETC1-3 | 4198 | C |  | Grainer One Hiole Lug compression connectors: 8 / 6 AWG | 45442 | 45449 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 2848.1 | 0.36783 | 4894.88 | 0 | 4894.88 | 0 | [66 empty] | 2848.1 | [6 empty] | - |  |  | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307020A | 7734 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2192 | C |  | 湧心 Hand Tool | 45113 | 45113 | [6 empty] | YONGXIN Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7734 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 7734 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Labor | The budget execution does not pertain to this project | VOC | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Safety | USC21C014 | USCSB2310023A | 7709.6 | F21P1 WH2SO4 | 2686 | C |  | VOC 02 & VOC 03 resolve moldy by decontaminating the crates. | 45203 | 45206 | [6 empty] | Clean Harbors Environmental Services Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7709.6 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 7709.6 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311035A | 7708.99 | Tool Interconnection Project (Main Tool & Module) | 509 | P |  | Manpower Labor for Tool KECOT1 | 45244 | 45314 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4227.22 | 0.54835 | 3481.77 | 0 | 3481.77 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3402.5 | 824.72 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C029 | USCSB2402089A | 7683 | EBO21- Tool interconnection | 3530 | C |  | EBO: ZASC5-1: TUBE WELDING & 4% H2/He INSTALL | 45331 | 45335 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 7683 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 7683 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406015A | 7672 | Tool Interconnection Project (Main Tool & Other Vendors) | 1135 | P |  | KUECN5/6/7 PFA Install - Route (2) PFA lines on (3) separate tools. Pressure test all (6) lines after routing is completed. | 45462 | 45471 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7672 | 7672 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2307107A | 7653.9 | F21 TMAH System | 2272 | C | -02 | (35) Joints PP PN6 D110 for Submains | 2023/7/22 2023/9/19 | 2023/8/13 2023/9/19 2023/9/26 | -5800 | 13453.9 |  |  |  |  | Ferguson Enterprises, LLC | PR Approved | PO Approved | R2:Freight negotiated with a third party R1:Freight negotiated with a third party |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7653.9 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 7653.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2409075A | 7635.62 | F21P1 AMAT Interconnection | 4868 | C |  | RS Payroll AMAT #5113 6/13/2024 | 45554 | 45561 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 7635.62 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 7635.62
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405006A | 7605 | WWT B side Project | 3982 | C |  | WWT 4-5/8" Clamps_20240429 (B Side) | 45413 | 45415 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 7605 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 7605 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C001 | USCSB2309055A | 7600 | TEL Main Tool Interconnection | 2531 | C |  | KPD801-T HYC | 45181 | 45192 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6880 | 0.90526 | 720 | 0 | 720 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 6880 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308043A | 7592 | Tool Interconnection Project (Main Tool & Module) | 393 | P |  | KPOCT5-T GREENBERRY LABOR PAY | 45168 | 45177 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7212.4 | 0.95 | 379.6 | 0 | 379.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7212.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309042A | 7592 | Tool Interconnection Project (Main Tool & Module) | 430 | P |  | KPOCT4-T GREENBERRY EXHAUST INSTALLATION | 45196 | 45205 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7212.4 | 0.95 | 379.6 | 0 | 379.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 7212.4 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | Labor | USC21C011 | USCSB2401084A | 7562 | F21 TMAH System | 3273 | C |  | WWT: Manufacture TMAH Handrail Standoffs and Install | 45303 | 45307 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7562 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 7183.9 | 0 | 0 |  | 0 |  | 378.1 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311005A | 7552 | Tool Interconnection Project (Main Tool & Module) | 480 | P |  | Labor - Cable Installation for KCSNA1 | 45232 | 45239 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7552 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7552 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311053A | 7552 | Tool Interconnection Project (Main Tool & Module) | 525 | P |  | Manpower pay for SanTan Tool ID KEPRL7 | 45248 | 45253 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3923.5 | 0.51953 | 3628.5 | 0 | 3628.5 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 3923.5 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405157A | 7538.91 | F21P1-0404_H_labor for 50 tools_MICU | 4185 | C |  | open po for invoice past due, tool hookup team | 45441 | 45443 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 6617.61 | 0.87779 | 921.3 | 0 | 921.3 | 0 | [60 empty] | 6617.61 | [12 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2309189A | 7516 | F21P1-0404_H_labor for 50 tools_MICU | 2657 | C |  | OD Tube Strut Clamp EG | 45198 | 45201 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7516 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7516 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311051A | 7511.92 | Tool Interconnection Project (Main Tool & Module) | 523 | P |  | P-NF-1/2: NUT, FEMALE, HTC | 45248 | 45253 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6200.91 | 0.82548 | 1311.01 | 0 | 1311.01 | 0 | [43 empty] | 0 |  | 0 | 0 | 5416.74 | 0 | 0 |  |  | 0 | 784.17 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2303089A | 7511 | F21P1 Chemical & WCCS package | 1826 | C |  | Chemical Tank Bottom Plate | 45009 | 45016 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7511 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 7511 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2312176A | 7500 | F21P1 WWT package (Installation and 2 batch tanks) | 3163 | C |  | WWT-Clamp from 8-16” for A side back up. | 45283 | 45288 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7500 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 7500 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C003 | USCSB2301013A | 7496.5 | F21P1 UPW | 1636 | C |  | UPW-MMF-Anthracite procurement | 44933 | 44935 | [6 empty] | Northern Filter Media, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7496.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 1132.5 |  |  |  | 6364 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | ESP | Equipment | The budget execution does not pertain to this project | 光阻櫃 | Others | Electrical | Material | USC22C033 | USCSB2211031A | 7480 | F21 ESP equipment(include labor fee) | 1564 | C |  | F21 ISEP ESP system implementation and hardware equipment purchase | 44887 | 44897 | [6 empty] | Ying Pao Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 7480 | 0 | 7480 | 7106 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 7106 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2301007A | 7478.05 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1630 | C |  | Harrington PVC&PVDF MICU F21 TOOL XT | 44931 | 44935 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 7478.05 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 3418.05 | 4060 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | M+L | USC21C005 | USCSB2308050A | 7475.4 | F21P1 Chemical & WCCS package | 2348 | C |  | Strut Anchor for construction work.(Qty:90) | 45147 | 45154 | [6 empty] | Jendco Safety Supply | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7475.4 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 7475.4 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2306134A | 7473.5 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2167 | C | -01 | HSIEH SHUN HING hand tool | 2023/6/29 2023/7/14 | 2023/7/5 2023/7/17 | 1304.9 | 6168.6 | V |  |  |  | HSIEH SHUN HING CO., LTD. | PR Approved | PO Approved | R1:packing fee |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7473.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 7473.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310016A | 7470 | Tool Interconnection Project (Main Tool & Module) | 448 | P |  | labor for install cabinet anchor | 45204 | 45226 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7470 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7470 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403033A | 7425.1 | Tool Interconnection Project (Main Tool & Other Vendors) | 859 | P |  | SUS304 10" DUCT(1.2M) | 45359 | 45372 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 7425.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [13 empty] | 7425.1 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2408061A | 7407.77 | WWT B side Project | 4678 | C |  | WWT shortage of fitting materials on the B side Sump Pump | 45517 | 45519 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 5842.97 | 0.78876 | 1564.8 | 7533.49 | -5968.69 | 0 | [73 empty] | 5842.97
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403059A | 7406.93 | Tool Interconnection Project (Main Tool & Other Vendors) | 882 | P |  | KST-70R TUBE (SIGNAL CABLE WRAPS) | 45364 | 45369 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 7406.93 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 7406.93 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312029A | 7406.93 | Tool Interconnection Project (Main Tool & Module) | 578 | P |  | KST-70R Tube | 45266 | 45270 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 7406.93 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 7406.93 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404057A | 7402.59 | Tool Interconnection Project (Main Tool & Other Vendors) | 1010 | P |  | PFA-T12-062-50 3/4" PFA TUBING 062 WALL, 50' | 45394 | 45399 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7402.59 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 7402.59 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2305024A | 7350 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1947 | C |  | Glendale Office West Side - Alarm and Surveillance | 45051 | 45054 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7350 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 1102.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 6247.5 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308041A | 7315 | Tool Interconnection Project (Main Tool & Module) | 391 | P |  | KPD801-T GREENBERRY LABOR PAY | 45168 | 45188 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6949.25 | 0.95 | 365.75 | 0 | 365.75 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 6949.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308029A | 7315 | Tool Interconnection Project (Main Tool & Module) | 379 | P |  | KPAE01-T GREENBERRY LABOR PAY | 45167 | 45176 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6949.25 | 0.95 | 365.75 | 0 | 365.75 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 6949.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2403031A | 7311 | F21P1 WWT package (Installation and 2 batch tanks) | 3740 | C |  | WWT Center Ring_20240304 (A Side) | 45356 | 45358 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7311 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7311 |  |  | 1096.65 |  |  |  | 1096.65 |  |  |  | 1096.65 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Greenberry | DCR Scope | WWT | WWT | Steel | Labor | USC23C014 | USCSB2401043A | 7300 | F21P1 Labor incentive program-MICU | 3233 | C |  | Tunnel&WWT_9-5 Holiday pay incentive (Labor Day) | 45300 | 45306 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 7300 | 0 | 7300 | 7300 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1095 |  |  |  | 1095 |  |  |  | 1095 |  | 3650 |  | - | 3650 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2308013A | 7274 | F21 TMAH System | 2315 | C |  | WWT 6in CPVC | 45141 | 45149 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7274 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 7274 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403199A | 7266.13 | F21P1 Chemical & WCCS package | 3895 | C |  | CDS LB1 B side supports materials | 45371 | 45372 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 7266.13 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7266.13 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310048A | 7242 | Tool Interconnection Project (Main Tool & Module) | 466 | P |  | kpe602S temp cda line build COR | 45220 | 45224 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7242 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 7242 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Material | USC21C003 | USCSB2303036A | 7238 | F21P1 UPW | 1778 | C |  | UPW Panel Material | 44993 | 45006 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7238 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 7238 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405132A | 7204 | Tool Interconnection Project (Main Tool & Other Vendors) | 1109 | P |  | Cable Pull KCSCS4 | 45434 | 45443 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 7204 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 7204 | [6 empty] | - |  |  | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2312077A | 7199.22 | F21P1-0404_H_labor for 50 tools_MICU | 3069 | C |  | Home Depot tools for 漢科. New arrival trade new tools request | 45273 | 45276 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7199.22 | 1 | 0 | 0 | 0 | 0 | 7199.22 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2405035A | 7194.11 | F21P1 WWT package (Installation and 2 batch tanks) | 4044 | C |  | Temporary chemical leak kit_20/45-10 | 45419 | 45423 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7194.11 | 0 | 7194.11 | 7194.11 | [56 empty] | 0 | [14 empty] | 7194.11 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2309144A | 7184.08 | F21P1 Chemical & WCCS package | 2615 | C |  | Circuit Breakers for Fab L10/L20 | 45191 | 45197 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7184.08 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 7184.08 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2306018A | 7150 | F21P1 UPW | 2052 | C |  | UPW Degan tank HKP rev&clean | 45083 | 45100 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7150 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 7150 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2402017A | 7130.9 | WWT Change Order (Piping) | 3460 | C |  | Clamps for A side 2024.1.31-1 | 45323 | 45324 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 7130.9 | 1 | 0 | 0 | 0 | 7130.9 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1069.635 |  |  |  | 1069.635 |  |  | 7130.9 | 1069.635 |  | 3565.45 |  | - | 3565.45 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309195A | 7129.48 | WWT Change Order (Piping) | 2663 | C |  | material for LJ W339 order#3 | 45199 | 45203 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6082.08 | 0.85309 | 1047.4 | 0 | 1047.4 | 912.312 | [40 empty] | 0 | 0 | 0 | 675.44 |  | 5406.64 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 213.8844 |  |  |  | 356.474 |  | 912.312 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311071A | 7121.99 | F21P1-0404_H_labor for 50 tools_MICU | 2925 | C |  | Vern Nut, regulator for | 45246 | 45252 | [6 empty] | Vern Lewis Welding Supply, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7042.99 | 0.98891 | 79 | 0 | 79 | 0 | [43 empty] | 0 |  | 0 | 0 | 4630.09 | 0 | 0 |  | 2412.9 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308026A | 7112.49 | Tool Interconnection Project (Main Tool & Module) | 376 | P | -01 | KPOV04 STREIMER EXHAUST LABOR | 2023/8/29 2024/2/1 | 2023/10/6 2024/2/1 | -9514.11 | 16626.6 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | Final amount to be paid for completed work |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7112.49 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 7112.49 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2403178A | 7110 | F21P1 Chemical & WCCS package | 3875 | C |  | CDS Box | 45367 | 45371 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 7110 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 7110 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Material | USC24C005 | USCSB2407003A | 7106 | Chemical & WCCS B Side Project | 4405 | C |  | EES 防爆接線盒0627 (Made-to-Order Explosion Proof Box) | 45474 | 45476 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 7106 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 7106 |  |  | - |  |  | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2306036A | 7100 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2071 | C |  | Bay Alarm Company | 45087 | 45104 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7100 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 7100 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C006 | USCSB2308123A | 7086 | F21P1 Module Tool Interconnection EPI | 2420 | C |  | EPI Pump Fore Line Adapter Vent Connection R2 | 45157 | 45160 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 7086 | 0 | 7086 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C006 | USCSB2308151A | 7086 | F21P1 Module Tool Interconnection EPI | 2446 | C |  | Greenberry labor- Offsite labor to drill and hand weld SS-8-VCR-3-8MTW to 0050-53004 pumping line adapter | 45162 | 45180 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6731.7 | 0.95 | 354.3 | 0 | 354.3 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 6731.7 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | UMEC | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2402007A | 7085 | F21P1 Chemical & WCCS package | 3450 | C |  | CDS TSMC UPW 8-178 Chemical Scope (T&M) | 45323 | 45325 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 7085 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 6731 | 0 | 0 |  | 354 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404074A | 7073.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 1028 | P |  | Manpower Pay for Delta Wye Tool ID: KEMGH2 for Time cards on 4.2, 4.3, 4.4, 4.5, and 4.10.2024 | 45401 | 45407 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 7073.5 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 7073.5 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309030A | 7065.45 | F21P1 Chemical & WCCS package | 2507 | C |  | Manual chemical liquid valve | 45177 | 45197 | [6 empty] | CKD USA CORPORATION | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7065.45 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 7065.45 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Material | USC24C005 | USCSB2407156A | 7061 | Chemical & WCCS B Side Project | 4581 | C |  | Chem Team Fitting KS23 to Replace KS17 (CED 化學訊號fitting換料0725) | 45499 | 45503 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7061 | 7061 | 0 | [74 empty] | -
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2301010A | 7051.64 | F21P1 UPW | 1633 | C |  | UPW-skids cover replacement | 44932 | 44937 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 7051.64 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 7051.64 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Site Expense |  |  | Others |  |  | USC22C008 | USCSB2403056A | 7047.64 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3761 | C |  | United Rentals/Scissor Lift 39-40 Electric 45-48 Wide/ item#297951AH/ Scissor lift 39-40' Electric 45-48" Wide item 199199AH | 45357 | 45358 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7047.64 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 7047.64 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | Labor | USC21C009 | USCSB2302031A | 7013.5 | F21P1 WWT package (Installation and 2 batch tanks) | 1712 | C |  | T-130AA/AB Agitator Chemical Coating | 44971 | 44979 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7013.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 7013.5 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408058A | 7004 | Tool Interconnection Project (Main Tool & Other Vendors) | 1204 | P |  | Labor for Multiple Tool Cabling | 45528 | 45530 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7004 | 7004 | 0 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C011 | USCSB2309110A | 7000 | F21 TMAH System | 2582 | C |  | F21 WWT system material (Gibabit) | 45188 | 45194 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7000 | 1 | 0 | 0 | 0 | 7000 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1050 |  |  |  | 1050 |  |  |  | 1050 | 7000 | 3500 |  | - | 3500 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405001A | 6993 | Tool Interconnection Project (Main Tool & Other Vendors) | 1059 | P |  | KPE603-T Grounding Box Installation Labor | 45414 | 45415 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 6993 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404020A | 6993 | Tool Interconnection Project (Main Tool & Other Vendors) | 975 | P |  | KPAN02-T Cable Grounding Installation Labor | 45386 | 45387 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 6993 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404021A | 6993 | Tool Interconnection Project (Main Tool & Other Vendors) | 976 | P |  | KPAP02-T Cable Grounding Installation Labor | 45386 | 45387 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 6993 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404022A | 6993 | Tool Interconnection Project (Main Tool & Other Vendors) | 977 | P |  | KPE602-T Cable Grounding Installation Labor | 45386 | 45387 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 6993 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404107A | 6993 | Tool Interconnection Project (Main Tool & Other Vendors) | 1051 | P |  | KPAN03-T Cable Grounding Installation Labor | 45409 | 45411 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 6993 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404110A | 6993 | Tool Interconnection Project (Main Tool & Other Vendors) | 1054 | P |  | KPE606-T Grounding Box Installation Labor | 45412 | 45413 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 6993 | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404111A | 6993 | Tool Interconnection Project (Main Tool & Other Vendors) | 1055 | P |  | KPE607-T Cable Grounding Installation Labor | 45412 | 45413 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6993 | 0 | 6993 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405002A | 6993 | Tool Interconnection Project (Main Tool & Other Vendors) | 1060 | P |  | KPE605-T Grounding Box Installation Labor | 45414 | 45415 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 6993 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404112A | 6993 | Tool Interconnection Project (Main Tool & Other Vendors) | 1056 | P |  | KPE604-T Cable Grounding Installation Labor | 45412 | 45413 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 6993 | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2310142A | 6982.49 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2800 | C |  | Southwest Fastener Open Statement Orders 08/20/23- 09/20/23 | 45220 | 45225 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6778.53 | 0.97079 | 203.96 | 0 | 203.96 | 0 | [42 empty] | 0 | 6685.53 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 93 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2312139A | 6975 | F21P1 Chemical & WCCS package | 3128 | C | -01 | CDS Fix L10 HNO3 ST250 HKP | 2023/12/19 2023/12/26 | 2023/12/20 2023/12/26 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved | Ship-to address cgange |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 6975 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 6626.25 | 0 | 0 |  | 0 | [8 empty] | 348.75 |  |  |  |  | 348.75 | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408053A | 6962 | F21P1 Module Tool Interconnection LIT2-3 | 4671 | C |  | Lit 2: KPE601-S, KPE602-S, KPE603-S, KPE604-S, KPE605-S, KPE606-S, KPE607-S: GMS Fittings Fabrications | 45517 | 45520 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6962 | 0 | 6962 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C029 | USCSB2407067A | 6951.97 | EBO21- Tool interconnection | 4485 | C |  | EBO: ZKT-6 ENVIRONMENTAL ENCLOSURE | 45485 | 45490 | [6 empty] | Brycon Corporation | PR Approved | PO Approved | [14 empty] | 6951.97 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 6951.97 | - |  |  | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | Labor | USC23C045 | USCSB2309131A | 6924 | WWT Change Order (Piping) | 2602 | C |  | WRC Rack 215/220 Modification for PSS Clash | 45190 | 45197 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6924 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 6924 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310037A | 6890 | Tool Interconnection Project (Main Tool & Module) | 457 | P | -01 | ELECTRICAL CABLE PULL | 45216 | 2023/10/25 2023/11/03 | 650 | 6240 |  |  |  |  | OE Electric | PR Approved | PO Approved | R1: The original PO amount was lower, but the invoice charged, the PM agreed upon. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6890 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 6890 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2306133A | 6888 | F21P1-0404_H_Hallway plate install_MICU | 2166 | C |  | 6 single barricades | 45106 | 45135 | 1148 | [5 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6888 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 6888 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Southland | DCR Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2302039A | 6886 | F21P1 Chemical & WCCS package | 1720 | C |  | M1, M2, H2SO4 Design Change | 44975 | 44981 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6886 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 6886 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2304036A | 6875.9 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1876 | C |  | Dock seals and lights | 45031 | 45044 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6875.9 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 6875.9 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2310192A | 6868 | F21P1 Chemical & WCCS package | 2844 | C |  | CDS Lorry unistrut cages at Room 13, 12, 30,31 | 45230 | 45231 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6868 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 6524.6 | 0 | 0 | 0 |  |  | 343.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409028A | 6862.12 | TSMC Fab 21 P1B Tool Hook Up | 4814 | C |  | Glove Guard Cable Safe Hook Extreme, Yellow, 12 Inch Hook (25 Pack) | 45540 | 45551 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 6862.12 | 1 | 0 | 0 | 0 | 0 | 6862.12 | [72 empty] | -
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2312042A | 6859.58 | F21P1 Module Tool Interconnection CVD | 3035 | C |  | KCSOA4, KCSNA1 Material request from WESCO for Seal-Tite cable conduit and hardware | 45267 | 45272 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6859.58 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 6100.26 | 759.32 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | Material | USC23C045 | USCSB2311021A | 6858 | WWT Change Order (Piping) | 2876 | C |  | WWT 18" backing ring | 45234 | 45241 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6858 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 6515.1 | 0 | 0 | 0 |  |  | 342.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310077A | 6851.04 | F21P1-0404_H_labor for 50 tools_MICU | 2738 | C |  | Label Hansen POWER | 45211 | 45218 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6836.49 | 0.99788 | 14.55 | 0 | 14.55 | 0 | [41 empty] | 0 | 0 | 0 | 1277.96 | 0 | 0 | 0 | 5558.53 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2403002A | 6845.83 | F21P1 WWT package (Installation and 2 batch tanks) | 3710 | C | -01 | WWT - Marquis CO 1 Media loading for for four hour delay and Specialty PPE to work in TMAH | 45352 | 2024/3/2 2024/3/4 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved | R1: Changed Remark Contract Scope |  | Ta Wei Wang | [11 empty] | 6845.83 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 6845.83 |  | 0 |  |  |  |  | 1026.8745 |  |  |  | 1026.8745 |  |  |  | 1026.87 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW |  |  |  | UPW | Mechanical | M+L | USC24C008 | USCSB2407168A | 6825 | UPW B Side Project | 4591 | C |  | CIP Pump Replacement_UPW | 45503 | 45506 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6825 | 0 | 6825 | [74 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401008A | 6824.64 | F21P1-0404_H_labor for 50 tools_MICU | 3199 | C |  | Cable wire stripper kit for HK power trade | 45295 | 45296 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6824.64 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 6824.64 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2403176A | 6817.62 | F21P1 Chemical & WCCS package | 3873 | C |  | CDS 6awg 5C | 45367 | 45371 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 6567.62 | 0.96333 | 250 | 0 | 250 | 0 | [52 empty] | 0 | 0 | 0 |  | 6567.62 | [8 empty] | 250 | [5 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406021A | 6813.78 | Chemical & WCCS B Side Project | 4247 | C |  | pad prep/epoxy and yellow safety paint of 1 pad in Fab L10 HPM Bside Bed 457*113(inch) | 45447 | 45450 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 6813.78 | 1 | 0 | 6813.78 | -6813.78 | 0 | [73 empty] | 6813.78 |  |  | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2305054A | 6801 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1977 | C |  | Starlink installation at TransPak warehouse for OSC | 45058 | 45061 | [6 empty] | GeoTech Enterprises LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6801 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 6801 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401005A | 6798.77 | F21P1-0404_H_labor for 50 tools_MICU | 3197 | C |  | WIRE, for Chemical system, Tool hookup team | 45294 | 45296 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6798.77 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 6765.07 | 33.7 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309022A | 6773.79 | Tool Interconnection Project (Main Tool & Module) | 412 | P |  | CHNL BTB 14GA 120IN | 45191 | 45201 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 6773.79 | 0 | 6773.79 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405151A | 6773.75 | Chemical & WCCS B Side Project | 4180 | C |  | TSMC F21 B SIDE SDS ATRS Regulator | 45440 | 45442 | [6 empty] | Flodraulic Group | PR Approved | PO Approved | [14 empty] | 6773.75 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 6657.15 |  | 116.6 | [8 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C009 | USCSB2307027A | 6760.1 | F21P1 WWT package (Installation and 2 batch tanks) | 2199 | C |  | WRC NaOH Tank Tranfer to Drums (WWT-T615A-empty chemical) | 45114 | 45187 | [6 empty] | Clean Harbors Environmental Services Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3334.6 | 0.49328 | 3425.5 | 0 | 3425.5 | 266.768 | [40 empty] | 0 | 0 | 0 | 3334.6 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 676.01 |  |  |  | 676.01 |  |  |  | 676.01 |  | 0 |  | - | 0 | 0 | 0 | 266.768
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C007 | USCSB2405028A | 6752 | F21P1 Module Tool Interconnection PVD1-2 | 4038 | C |  | DI-max greenberry KSANA1&KSRHA1 | 45416 | 45441 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6752 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 6752 | [6 empty] | - |  |  | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2308064A | 6706 | F21P1-0404_H_Hallway plate install_MICU | 2362 | C |  | TSMC FAB1 TI Foundations(ABS-A-03 re-work) | 45148 | 45163 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6706 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 6706 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409042A | 6700 | TSMC Fab 21 P1B Tool Hook Up | 4827 | C |  | QAQC WELDER CERTIFICATION | 45545 | 45568 | [6 empty] | Independent QA/QC Services Inc. | PR Approved | PO Approving | [14 empty] | 0 | 0 | 6700 | 0 | 6700 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2307087A | 6680 | F21P1 Module Tool Interconnection CVD | 2253 | C |  | O&E Electric labor cable pull for KCANN1 and KCANN2 | 45127 | 45133 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1820 | 0.27246 | 4860 | 0 | 4860 | 0 | [40 empty] | 1820 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401188A | 6662.42 | F21P1-0404_H_labor for 50 tools_MICU | 3373 | C |  | 1221 Plastic儲存工具到貨核對 | 45314 | 45316 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6662.42 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 6662.42 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308035A | 6645 | Tool Interconnection Project (Main Tool & Module) | 385 | P |  | KPAN01-T GREENBERRY LABOR PAY | 45168 | 45177 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6312.75 | 0.95 | 332.25 | 0 | 332.25 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 6312.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312034A | 6637.11 | Tool Interconnection Project (Main Tool & Module) | 581 | P |  | PVC MALE ADPT N80 2.5" SXMT SPEA MFG P/N 836-025 | 45268 | 45272 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 6637.04 | 0.99999 | 0.07 | 0 | 0.07 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 6383.74 | 253.3 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310076A | 6629.76 | F21P1-0404_H_labor for 50 tools_MICU | 2737 | C |  | Hansen label for pumping line | 10/12/2023 8/22/2024 | 10/19/2023 8/24/2024 | [5 empty] | V | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6629.76 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 6629.76 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312051A | 6625 | F21P1-0404_H_labor for 50 tools_MICU | 3044 | C |  | Cable tie for high pressure hose. Trade: CYH PCW. Top 100 tools | 45268 | 45272 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 6625 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 6625 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405147A | 6610.11 | WWT B side Project | 4171 | C |  | WWT Hardware_20240523 (B Side) | 45436 | 45440 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 6610.11 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2639.01 |  | 3971.1 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2404133A | 6587.89 | F21P1-0404_H_labor for 50 tools_MICU | 4117 | C |  | Ground bush for HK Power Luis for 60 tools | 45399 | 45425 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 6587.89 | 1 | 0 | 6587.89 | -6587.89 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | 6587.89 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406070A | 6550 | F21P1-0404_H_labor for 50 tools_MICU | 4302 | C |  | breakers for TSMC Grant Chen for P1B tools | 45456 | 45459 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6550 | 6550 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402074A | 6515.1 | F21P1 WWT package (Installation and 2 batch tanks) | 3516 | C | -01 | Temporary chemical leak kit 10/45-10 | 45330 | 2024/2/14 2024/4/3 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | R1: Switch payment method to Credit Card per Angela's request |  | Jen-Ping Tsai | [11 empty] | 6515.1 | 1 | 0 | 0 | 0 | 0 | 6515.1 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 977.265 |  |  |  | 977.265 |  |  |  | 977.265 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2402066A | 6507.2 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3508 | C | -01 | Orbit Industrial Services & Maintenance/Weight scales for EUV maintenance. | 45329 | 2/15/2024 3/7/2024 | [6 empty] | ORBIT industrial service & maintenance LLC | PR Approved | PO Approved | R1: completion date change |  | Yikang Wang | [11 empty] | 6507.2 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 6507.2 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310139A | 6507.04 | F21P1 Chemical & WCCS package | 2797 | C |  | 10/21/23 to 11/20/23 Southwest Fastener Monthly Order for Chemical team | 45220 | 45303 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6507.04 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 2355.7 | 3026.4 | 0 |  |  | 1124.94 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Electrical | Material | USC24C006 | USCSB2407014A | 6482.99 | WWT B side Project | 4415 | C |  | Wires for chemical tank area | 45475 | 45478 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6482.99 | 6482.99 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408149A | 6482 | TSMC Fab 21 P1B Tool Hook Up | 4764 | C |  | Struct anchor for HK Safety | 45534 | 45551 | [6 empty] | Diversified Products USA | PR Approved | PO Approved | [14 empty] | 6482 | 1 | 0 | 6482 | -6482 | 0 | [73 empty] | 6482
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403142A | 6467.05 | F21P1-0404_H_labor for 50 tools_MICU | 3842 | C |  | Clear 20-Gauge Plastic Sheeting after epoxy shared by all HK system | 45365 | 45370 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 6466.95 | 0.99998 | 0.1 | 0 | 0.1 | 0 | 6466.95 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404030A | 6454.1 | Tool Interconnection Project (Main Tool & Other Vendors) | 985 | P |  | DOT MB381 MACHINE BOLT | 45387 | 45390 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6454.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 5729.72 |  | 724.38 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Equipment | 0 | 0 | Chemical | Mechanical | Material | USC24C005 | USCSB2404098A | 6450 | Chemical & WCCS B Side Project | 4085 | C |  | SDS VMB Pneumatic Spare Parts | 45393 | 45397 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 6450 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6450 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USC2112023A | 6420 | F21P1 Slurry package | 87 | P |  | Bellows Valve | 44547 | 44571 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | confirmed ok | 100% by delivery (Net 30 days) | Cherry Chang | FOB | twelve (12) months following delivery | Chih-Chien Hung | Cherry Chang | N |  | Henry |  | N | 5000 |  | 6420 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 535 | 0 |  | 5885 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C013 | USCSB2310034A | 6400 | F21P1 AMC THC Monitoring System | 2697 | C | -01 | F21 P1 IMS Wipe Test | 45204 | 2023/10/10 2023/10/17 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved | PO R1:Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6400 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Outsourcing |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C008 | USCSB2407105A | 6384 | UPW B Side Project | 4520 | C |  | CGS Global Support Onsite Manpower | 45490 | 45499 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6384 | 0 | 6384 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2301014A | 6368.07 | F21P1 WWT package (Installation and 2 batch tanks) | 1637 | C |  | Mini Line Hardware | 44933 | 44935 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6368.07 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 6368.07 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312047A | 6365 | Tool Interconnection Project (Main Tool & Module) | 593 | P |  | 12/6/2023-12/20/2023 KESRT2 cable pull in-house manpower EOPS | 45273 | 45306 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 6365 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 6365 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403045A | 6360 | F21P1-0404_H_labor for 50 tools_MICU | 3752 | C |  | Hole Seal; 1/2 In.; Gasketed, Oil Tight; Steel for HK Electrical PM | 45357 | 45362 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6360 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3122.76 |  | 3237.24 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408127A | 6348 | F21P1 Module Tool Interconnection LIT2-3 | 4738 | C |  | Lit 3: KPAN03-T: E4B, E6B Flex Replacement (Live Tool) | 45532 | 45541 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6348 | 0 | 6348 | 0 | [73 empty] | -
Base-Build | VOC | Material | DCR Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C007 | USCSB2310085A | 6330.8 | F21P1 VOC package （Installation ) | 2746 | C |  | VOC MC cable for LowNox | 45212 | 45218 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6087.83 | 0.96162 | 242.97 | 0 | 242.97 | 242.97 | [40 empty] | 0 | 0 | 0 | 0 |  | 6087.83 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 242.97
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310178A | 6330 | F21P1-0404_H_labor for 50 tools_MICU | 2831 | C |  | CED cable tray ground clamp for Third | 45226 | 45230 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6330 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 6330 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404047A | 6328.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 1000 | P |  | Interconnect Cable Pull for KCSCN1 Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45392 | 45393 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Sian-Ning Pei | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6328.32 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402097A | 6328.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 811 | P |  | Regular cable interconnect for KCOXN7. Pull cables from L30 to L20 and L10, following NEC code and TSMC 8395 routing specifications. | 45345 | 45348 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 6328.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403125A | 6328.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 940 | P |  | Regular interconnect cable pull for KCOCN1 on L30, L20, and L10 | 45378 | 45379 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6328.32 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404049A | 6328.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 1002 | P |  | Interconnect Cable Pull for KCOXN6. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45392 | 45393 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Sian-Ning Pei | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6328.32 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404050A | 6328.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 1003 | P |  | Interconnect Cable Pull for KCOXN2. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45392 | 45392 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6328.32 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404052A | 6328.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 1005 | P |  | Interconnect Cable Pull for KCOXN1. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45392 | 45392 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 6328.32 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402095A | 6328.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 809 | P |  | Regular interconnect cable pull for PVD2 KCTEN1. Pull cables from L30 to L20, routing cables in cable trays/ conduits, following 8395 routing procedures. | 45345 | 45348 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 6328.32 | 1 | 0 | 257.25 | -257.25 | 0 | [52 empty] | 0 | 0 | 0 |  | 6328.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402096A | 6328.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 810 | P |  | Regular interconnect cable pull for PVD2 KSCBH2. Pull cables from L30 to L20, routing cables in cable trays/ conduits, following 8395 routing procedures. | 45345 | 45348 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 6328.32 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405184A | 6328.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 1118 | P |  | 8395 Certification Cable Pull KCSCN4 4techs x 8hrs = 32hrs 32hrs x 3 days = 96hrs | 45443 | 45448 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 6328.32 | [8 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408062A | 6321.5 | TSMC Fab 21 P1B Tool Hook Up | 4679 | C |  | IR 63 welding machine calibration | 45518 | 45520 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6321.5 | 0 | 6321.5 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406033A | 6315.37 | Tool Interconnection Project (Main Tool & Other Vendors) | 1139 | P |  | WIRE SOOW2/4C 558089 | 45471 | 45476 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6315.37 | 6315.37 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310021A | 6290 | F21P1 Chemical & WCCS package | 2684 | C |  | Acrylic boards used in chemical in status and used for every each VMB of A/B side. | 45203 | 45206 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6290 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 6290 | 6290 | [9 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2404080A | 6289 | F21P1 AMAT Interconnection | 4070 | C |  | Bulk Lugs | 45391 | 45391 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6289 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 5669 | [5 empty] | 620 | [6 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402283A | 6272 | F21P1-0404_H_labor for 50 tools_MICU | 3706 | C |  | Plate, box, and outlet for HK power trade | 45351 | 45352 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6272 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3839.13 |  | 2432.87 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2402105A | 6270.32 | F21P1-0423_H_T&M Hardware_MICU | 3544 | C | -01 | 第五批短期採購需求, tool hookup for tsmc plastic system | 2024/2/10 2024/3/2 2024/7/31 | 2024/2/15 2024/3/2 2024/8/1 | 496.54 | 5773.78 | V |  |  |  | WW Grainger Inc | PR Approved | PO Approved | R1: Change Delivery Method to Self Pickup per requested R2: Per purchasing team request, this should change to the correct amount. R3: Adding Tax |  | Yikang Wang | [11 empty] | 5697.64 | 0.90867 | 572.68 | 0 | 572.68 | 0 | 5697.64 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2308132A | 6261.75 | F21P1 Chemical & WCCS package | 2427 | C |  | Lorry A FNDP001 Materials | 45160 | 45162 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 6261.75 | 0 | 6261.75 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2311070A | 6254.1 | F21P1 WWT package (Installation and 2 batch tanks) | 2924 | C |  | WWT-MU-H910/T130 H/A680 | 45246 | 45251 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 6254.1 | 0 | 6254.1 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 938.115 |  |  |  | 938.115 |  |  |  | 938.115 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Site Expense | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2402168A | 6254 | F21P1 WWT package (Installation and 2 batch tanks) | 3599 | C |  | ASME IX P8 WPS and Welder Qualification | 45339 | 45374 | [6 empty] | Phoenix National Laboratories, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 3330 | 0.53246 | 2924 | 0 | 2924 | 266.4 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 938.1 |  |  |  | 938.1 | 3330 |  |  | 938.1 |  | 0 |  | - | 0 | 0 | 0 | 266.4
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312181A | 6249.95 | F21P1-0404_H_labor for 50 tools_MICU | 3168 | C |  | Locknut for hk power trade. steel UL | 45287 | 45293 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6249.95 | 1 | 0 | 66.5 | -66.5 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 1271.25 |  | 0 |  | 4058.9 | [5 empty] | 279.3 |  |  |  | 574 |  |  | 0 |  | 66.5 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C001 | USCSB2305022A | 6240 | TEL Main Tool Interconnection | 1945 | C |  | KPOCT3 LIT3 MMI | 45051 | 45055 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 6240 | 0 | 6240 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C008 | USCSB2307029A | 6240 | F21P1 CCTV & Security | 2201 | C |  | CCTV speed gates UL on-site inspection/evaluation | 45115 | 45119 | [6 empty] | TUV SUD America, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 6240 | 0 | 6240 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - |  | 0 | 0
Base-Build | WWT | Site Expense | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C045 | USCSB2309094A | 6238.65 | WWT Change Order (Piping) | 2567 | C |  | WWT -LJ lift training | 45185 | 45209 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 6238.65 | 0 | 6238.65 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 935.7975 |  |  |  | 935.7975 |  |  |  | 935.7975 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2312136A | 6225 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3125 | C |  | RMJ ELECTRICAL CONTRACTORS TRASH COMPACTOR | 45279 | 45286 | [6 empty] | RMJ Electrical Contractors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 6225 | 0 | 6225 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405044A | 6218.06 | Tool Interconnection Project (Main Tool & Other Vendors) | 1086 | P |  | KDSTS8-DNS SCREEN INTERCONNECTS | 45426 | 45427 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 6218.06 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 6218.06 | [10 empty] | - |  |  | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202002A | 6213.7 | F21P1 UPW | 112 | P |  | Smartsheet Dynamic view Pro-rated license | 44603 | 44608 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved | Fixed Assets (Software:Dynamic View) | Fixed Assets (Software:Dynamic View) | Yi En Wong |  |  | Eric Lin | Yi En Wong | N |  |  |  | N |  |  | 6213.7 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 6213.7 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2402159A | 6204.96 | F21P1 Chemical & WCCS package | 3591 | C | -01 | CDS Pressure tests | 45338 | 2/27/2024 3/28/2024 | -11424.12 | 17629.08 |  |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: Removed Items Per Request |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 6204.96 | 0 | 6204.96 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [8 empty] | 6204.96 | [5 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C032 | USCSB2309039A | 6201 | F21_AZQR_Hookup_ Interconnection | 2516 | C |  | QR: KXEX01/KXEX02 – INSTALL 1” EMT FOR TOOLS. | 45178 | 45184 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6201 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 6201 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403097A | 6196.14 | F21P1 WWT package (Installation and 2 batch tanks) | 3799 | C |  | WWT Fittings_20240308 (A Side) | 45360 | 45363 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 6196.14 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 1143.86 |  | 5052.28 |  |  | 929.421 |  |  |  | 929.421 |  |  |  | 929.421 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2311057A | 6184 | WWT Change Order (Piping) | 2912 | C |  | WWT: Reposition T-780AA-2 Ladder | 45241 | 45246 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6184 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 5581.06 | 0 | 0 |  | 0 | [5 empty] | 602.94 |  |  | 185.52 |  |  |  | 123.68 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Electrical | Material | USC24C006 | USCSB2407052A | 6178.61 | WWT B side Project | 4451 | C |  | Onsite Trailers | 45483 | 45485 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6178.61 | 6178.61 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | UMEC | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2309103A | 6172 | F21P1 UPW | 2575 | C |  | LB2-UIS A2.5 spool remove | 45187 | 45195 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 6172 | 0 | 6172 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 5863.4 |  | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C053 | USCSB2311061A | 6140.05 | AMAT Interconnection (TSMC) | 2916 | C |  | KECOA1 Core Hole Sleeve Installation, Cable Tray and Dividers | 45245 | 45271 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6140.05 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 6140.05 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308028A | 6120 | Tool Interconnection Project (Main Tool & Module) | 378 | P |  | Cable ties KEPRL6 | 45167 | 45176 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6120 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 6120 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403083A | 6109.2 | F21P1 WWT package (Installation and 2 batch tanks) | 3786 | C |  | WWT Blind Flange_20240307 (A Side) | 45359 | 45363 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 6109.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 4753.99 |  | 1355.21 |  |  | 916.38 |  |  |  | 916.38 |  |  |  | 916.38 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2308080A | 6085.75 | F21P1 Module Tool Interconnection DIF1-2 | 2377 | C |  | DIF: 21 TOOLS - ?” VCR gland, Female nuts and gasket | 2023/8/15 2024/8/6 | 2023/8/17 2024/8/7 | -0.05 | 6085.8 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | To revise final invoice amount |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6085.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 6085.75 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | MIC - Material | Material |  |  | Others |  |  | USC22C016 | USCSB2312125A | 6081.02 | Asahi Valve and Positioner from Harrington |  |  |  | Gasket from Harrington_1207 request | [25 empty] | 6081.02 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 6081.02
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403095A | 6073.77 | Tool Interconnection Project (Main Tool & Other Vendors) | 911 | P |  | KEBCT1-TEL INTERCONNECTS - Labor 3/13/2024 | 45372 | 45377 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 6073.77 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6073.77 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2406024A | 6069 | F21P1 AMAT Interconnection | 4250 | C |  | multi conductor tray cable | 45448 | 45449 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6069 | 6034 | 35 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403138A | 6036.8 | F21P1 WWT package (Installation and 2 batch tanks) | 3839 | C |  | WWT - (20) 5" PVC Blind Flanges | 45365 | 45364 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 6036.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6036.8 |  |  | 905.52 |  |  |  | 905.52 |  |  |  | 905.52 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | CCTV | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC22C013 | USCSB2209024A | 6025.84 | F21P1 QR Lab Security & CCTV | 1476 | C |  | F21P1 FAB_Security&CCTV Package - 01 | 44824 | 44830 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 6025.84 | 0 | 6025.84 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407035A | 6012 | Tool Interconnection Project (Main Tool & Other Vendors) | 1166 | P |  | KPE602-S, KPE603-S, KPE605-S, and KPE607-S EUV Cable Rerouting Labor | 45498 | 45500 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6012 | 0 | 6012 | 0 | [73 empty] | - |  |  | 0
Hookup | AMHS | Labor |  |  | AMHS |  |  | USC22C025 | USC2309043B | 6000 | AMHS TSMC Instrustructure and Branch Circuits | 432 | P |  | Manpower Pay for AMHS Infrastructure and Branch Circuits | 45196 | 45315 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2155.56 | 0.35926 | 3844.44 | 0 | 3844.44 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 2155.56 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2306062A | 6000 | F21P1-0404_H_Hallway plate install_MICU | 2096 | C |  | 500pcs grinded iron plate | 2023/6/15 2023/6/27 | 45113 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | PR-R1:Revised from 500 to 200 pcs per TSMC's request. | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 6000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303030A | 6000 | F21P1 Module Tool Interconnection DIF1-2 | 1772 | C |  | Build VMB support frame | 44992 | 45007 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 6000 | 0 | 6000 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C032 | USCSB2306137A | 6000 | F21_AZQR_Hookup_ Interconnection | 2170 | C |  | QR LAB: MECHANICAL LABOR: 11 TOOLS FOR BOX INSTALL. 2 TO REWORK. | 45106 | 45160 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 6000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2402228A | 6000 | F21P1 UPW | 3655 | C |  | UPW-ORGANO-L10 Q-6.5 Line Design Mod | 45345 | 45349 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 6000 | 0 | 6000 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material |  |  | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2406148A | 5985 | WWT B side Project | 4396 | C |  | 儀表採樣箱收缺失之材料 | 45471 | 45476 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5985 | 0 | 5985 | 5985 | [71 empty] | 2992.5 |  | - | 2992.5 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309030A | 5980 | Tool Interconnection Project (Main Tool & Module) | 419 | P |  | Labor for KPAP01-T Exhaust | 45192 | 45205 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5681 | 0.95 | 299 | 0 | 299 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 5681 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309032A | 5980 | Tool Interconnection Project (Main Tool & Module) | 421 | P |  | KPE602-T GREENBERRY EXHAUST LABOR | 45192 | 45205 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5681 | 0.95 | 299 | 0 | 299 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 5681 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408123A | 5977.02 | TSMC Fab 21 P1B Tool Hook Up | 4734 | C |  | welding training/ certification materials | 45531 | 45538 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5977.02 | 1490 | 4487.02 | 0 | [73 empty] | -
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2307097A | 5968.25 | F21P1 UPW | 2263 | C |  | chemical Room UPW/Tank repairs UPW(sight glass flang) | 45128 | 45145 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 5968.25 | 0 | 5968.25 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 5669.84 |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309029A | 5959 | Tool Interconnection Project (Main Tool & Module) | 418 | P |  | Electrical cable pull for KECOT2. TEL Interconnect cable pull for KECOT2 (ETC2) | 45192 | 45198 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5959 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 5959 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | 光阻櫃 | Labor | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Labor | USC24C007 | USCSB2405083A | 5946.48 | Low Voltage B Side Project | 4103 | C |  | F21-P1_B-Side mask room exhaust hookup designs | 45426 | 45426 | [6 empty] | MornstAir Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5946.48 | 0 | 5946.48 | 0 | [56 empty] | 0 | [12 empty] | 5947 |  |  |  | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406105A | 5939.07 | F21P1-0404_H_labor for 50 tools_MICU | 4340 | C |  | Hand tools shared by all HK trades | 45463 | 45464 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 4877.15 | 0.8212 | 1061.92 | 0 | 1061.92 | 0 | 4877.15 | [72 empty] | - |  |  | 0
Base-Build | UPW | Labor | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2311047A | 5932.68 | F21P1 UPW | 2902 | C |  | UPW-Cleanharbor ERC service | 45240 | 45240 | [6 empty] | Clean Harbors Environmental Services Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 5932.68 | 0 | 5932.68 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Hot DI | Material | 0 | 0 | Chemical | Mechanical | Material | USC23C012 | USCSB2307142A | 5887.76 | F21P1 Hot DI Machine Hookup | 2304 | C |  | Hot DI long lead parts from Taiwan | 45136 | 45138 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5887.76 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 5887.76 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408076A | 5881 | F21P1 Module Tool Interconnection LIT2-3 | 4692 | C |  | Lit 3: KPOCT2: Exhaust Rework | 45520 | 45523 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5881 | 5881 | 0 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408065A | 5879.09 | TSMC Fab 21 P1B Tool Hook Up | 4681 | C |  | Extension ladder for HK exhaust trade for 300 tools | 45518 | 45530 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 1941.93 | 0.33031 | 3937.16 | 5879.09 | -1941.93 | 0 | [73 empty] | 1941.93
Base-Build | Base-Build | Greenberry | DCR Scope | WWT | WWT | Steel | M+L | USC22C022 | USCSB2308184A | 5859 | F21P1 Triazole treatment system | 2477 | C |  | 140 DISCHARGE EXTRA SUPPORT AND T125AC/AD MIS SUPPORT | 45169 | 45197 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 5859 | 0 | 5859 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402248A | 5838.06 | F21P1-0404_H_labor for 50 tools_MICU | 3674 | C |  | Fiberglass Routing S-Hook for 2-3/4" Maximum Bundle Diameter, Yellow, Tool hookup | 45347 | 45349 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 5384.67 | 0.92234 | 453.39 | 0 | 453.39 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 5384.67 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402067A | 5833.92 | Tool Interconnection Project (Main Tool & Other Vendors) | 784 | P |  | Tool ID KEBCT2, Perform cable pull to all relevant units per cable lists and 8395 per TSMC spec. | 45336 | 45337 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5833.92 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5833.92 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402064A | 5833.92 | Tool Interconnection Project (Main Tool & Other Vendors) | 781 | P |  | Tool ID KEBCT1, Perform cable pull to all relevant units per cable lists and 8395 per TSMC spec. | 45336 | 45338 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 5833.92 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5833.92 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402065A | 5833.92 | Tool Interconnection Project (Main Tool & Other Vendors) | 782 | P |  | Tool ID KEPST1, Perform cable pull to all relevant units per cable lists and 8395 per TSMC spec. | 45336 | 45337 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5833.92 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5833.92 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402066A | 5833.92 | Tool Interconnection Project (Main Tool & Other Vendors) | 783 | P |  | Tool ID KEPST2, Perform cable pull to all relevant units per cable lists and 8395 per TSMC spec. | 45336 | 45337 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5833.92 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5833.92 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2304025A | 5830 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1865 | C | -02 | Dock signal light hook up and outlet install | 2023/4/11 2023/5/4 2023/5/12 | 2023/4/20 2023/5/5 2023/5/16 | 1300 | 4530 | V |  |  | V | RMJ Electrical Contractors Inc | PR Approved | PO Approved | Camera Power Rate Increase |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2540 | 0.43568 | 3290 | 0 | 3290 | 0 | [33 empty] | 0 |  |  | 2540 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2406059A | 5792.42 | WWT B side Project | 4292 | C |  | WWT Fittings & Pipes_20240607 (B Side) | 45454 | 45455 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 5792.42 | 1 | 0 | 0 | 0 | 5792.42 | [68 empty] | 5489.17 |  | 303.25 | 2896.21 |  | - | 2896.21 | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2212026A | 5789 | F21P1 WWT package （USA EQ-FRP tank) | 1599 | C |  | T-125 tank flanges and gaskets | 44910 | 44910 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 5789 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 5789 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2404064A | 5774.42 | Tool Interconnection Project (Main Tool & Other Vendors) | 1017 | P |  | ABAA0158012 Armaflex 1-5/8 X 1/2 | 45398 | 45400 | [6 empty] | Bay Insulation | PR Approved | PO Approved | [14 empty] | 5774.42 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 5774.42 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207013A | 5772.65 | F21P1 UPW | 193 | P0 |  | Lenovo Laptop | 44771 | 44784 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 5772.65 | 1 | 0 | 0 | 0 | 0 | 5772.65 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405161A | 5770 | WWT B side Project | 4189 | C |  | WWT Center Rings_20240528 (B Side) | 45441 | 45450 | [6 empty] | HSIUNG CHANG Enterprise Co., Ltd. | PR Approved | PO Approved | [14 empty] | 5770 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 5770 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C009 | USCSB2307019A | 5768.1 | F21P1 WWT package (Installation and 2 batch tanks) | 2191 | C |  | WWT-CCB dry-run | 45113 | 45187 | [6 empty] | Clean Harbors Environmental Services Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5745.2 | 0.99603 | 22.9 | 0 | 22.9 | 0 | [40 empty] | 0 | 0 | 0 | 5745.2 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2307017A | 5760 | F21P1 WWT package (Installation and 2 batch tanks) | 2189 | C |  | FRP Resin for welding FRP pipe | 45113 | 45120 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5760 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 5760 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2208005A | 5760 | F21P1 UPW | 1443 | C |  | Harrington Ladder Standoff on the Tank | 44784 | 44785 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | USC2110005A Change order | 95% by progress-T/T 30 days-After acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Shengxu Yan | Yi En Wong | [7 empty] | 5760 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 5760 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2306071A | 5750 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2104 | C |  | Starlink additional support for OSC | 45093 | 45102 | [6 empty] | GeoTech Enterprises LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5750 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 5750 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401042A | 5746.06 | Tool Interconnection Project (Main Tool & Other Vendors) | 664 | P |  | KPAP01-S Nov 2023 Invoice for Labor | 45311 | 45315 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 5746.06 | 0 | 5746.06 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404029A | 5723.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 984 | P |  | 1304P 1 SCH 10 304L WLD PIPE === 100FT STOCK BALANCE 1 WEEK | 45386 | 45387 | [6 empty] | Industrial Pipe and Valve Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 5612.98 | 0.98067 | 110.62 | 0 | 110.62 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 5612.98 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402038A | 5712.38 | Tool Interconnection Project (Main Tool & Other Vendors) | 761 | P |  | KETRT4 San Tan Fire Manpower Pay | 45329 | 45332 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 5712.38 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5712.38 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403137A | 5712 | Tool Interconnection Project (Main Tool & Other Vendors) | 945 | P |  | Xavier Niesen 4/1-4/30/2024 | 45380 | 45435 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5712 | 0 | 5712 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USC2112011A | 5678.1 | F21P1 Chemical & WCCS package | 79 | P |  | Straight Union Reducer | 44537 | 44572 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | CF (Trade term check)) | 90% by shipment,and last 10% invoice within 60 days of receiving the goods, All invoices are NET 30. | Cherry Chang | FOB Osaka port | 24 months | Chih-Chien Hung | Cherry Chang | N |  | Henry | Fittings | N | 5000 |  | 5678.1 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 5678.1 | [17 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C007 | USCSB2309134A | 5664 | F21P1 Module Tool Interconnection PVD1-2 | 2605 | C |  | Cable Pull and 8395 KSMGS1-Pull Vendor supplied cables from L30,L20 QTY 30 | 45190 | 45195 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5664 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 5664 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2401011A | 5650.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 635 | P |  | Armaflex 1-1/8 X 1/2; 900ft X 1.3220 | 45301 | 45309 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 5650.12 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 5650.12 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401012A | 5647.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 636 | P |  | SS-QTM4A-B-6PM: SS QT BODY QC 3/8" MNPT | 45302 | 45310 |  |  |  | USCSB2401172A |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5647.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 4740.2 | 0 | 0 | 907.4 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C005 | USCSB2306106A | 5630.62 | F21P1 Module Tool Interconnection DIF1-2 | 2139 | C |  | DIFF1: MECHANICAL LABOR FOR KDAPK2-4 | 45099 | 45114 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5630.62 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 5630.62 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402243A | 5625 | F21P1-0404_H_labor for 50 tools_MICU | 3669 | C |  | M10(1.5) X 12 HEX SC 18-8 SS, T&M project, tool hookup team | 45347 | 45350 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5625 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 5625 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2311033A | 5620.4 | WWT Change Order (Piping) | 2888 | C |  | Swagelok Tubing &connector | 45238 | 45240 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5620.4 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 5620.4 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2307052A | 5611 | F21P1-0404_H_Hallway plate install_MICU | 2221 | C |  | APH-D-09 shift 4.5cm modification | 45120 | 45145 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5330.45 | 0.95 | 280.55 | 0 | 280.55 | 0 | [40 empty] | 5330.45 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C011 | USCSB2402041A | 5610 | F21 TMAH System | 3483 | C |  | Cleaning Material(ishine floor finish) | 45328 | 45330 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 4537.8 | 0.80888 | 1072.2 | 0 | 1072.2 | 862.182 | 4537.8 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 862.182 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C007 | USCSB2407058A | 5600 | F21P1 Module Tool Interconnection PVD1-2 | 4455 | C |  | PVD CIP DI-max | 45484 | 45485 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 5600 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 5600 |  |  | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2402234A | 5599.62 | F21P1 Chemical & WCCS package | 3660 | C |  | CDS electrical materials | 45346 | 45350 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5599.62 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 5599.62 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Southland | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2401235A | 5590.8 | F21P1 Chemical & WCCS package | 3417 | C |  | WCCS CO#172 W-A515 L20 | 45318 | 45322 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5590.8 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 5590.8 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | Material | The budget execution does not pertain to this project | CCTV | Low Voltage | Mechanical | M+L | USC22C001 | USCSB2404015A | 5576 | F21 P1 Office and WH Security and CCTV | 4011 | C |  | F21 P1 CUP L30 Glass Baffle Railing | 45384 | 45395 | [6 empty] | Southwest Metalsmiths, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 5576 | 1 | 0 | 5576 | -5576 | 5576 | [52 empty] | 0 | 0 | 0 |  | 0 | [12 empty] | 5298 |  | 0 |  | 5576 | 5576 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312023A | 5572.37 | Tool Interconnection Project (Main Tool & Module) | 572 | P |  | Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards KETRT7 | 45265 | 45268 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5572.37 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 5572.37 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | UMEC | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2307123A | 5563 | F21P1 UPW | 2286 | C |  | WRC Temp Mixed Bed Resin Temp Hose | 45134 | 45156 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 5563 | 0 | 5563 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309034A | 5560 | F21P1 Chemical & WCCS package | 2511 | C |  | Lorry 90 deg Coax elbows | 45177 | 45182 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5560 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 5560 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material |  |  | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407011A | 5553 | WWT B side Project | 4412 | C |  | B side gasket 補料 | 45475 | 45477 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5553 | 0 | 5553 | 5553 | [71 empty] | 2776.5 |  | - | 2776.5 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2312104A | 5550 | F21P1 AMAT Interconnection | 3094 | C |  | Time and Materials pricing for the KIHIT4 Signal Cable Install | 45275 | 45279 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5550 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 5550 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C004 | USCSB2403179A | 5544.35 | F21P1 WWT package （USA EQ-FRP tank) | 3876 | C |  | U-Line - MIMO - Move In/Move Out Team | 45369 | 45370 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5110 | 0.92166 | 434.35 | 0 | 434.35 | 0 | [52 empty] | 0 | 0 | 0 |  | 5110 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307010A | 5537.74 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2183 | C |  | Arbon Equipment Corporation Glendale Warehouse Door Repair | 45111 | 45119 | [6 empty] | Arbon Equipment Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5537.74 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 5537.74 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2311138A | 5534.57 | WWT Change Order (Piping) | 2988 | C |  | WWT LSR CS material | 45259 | 45260 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5534.57 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 5534.57 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | W-H2SO4 | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C014 | USCSB2302005A | 5527.5 | F21P1 WH2SO4 | 1686 | C |  | W-H2SO4 2X4 Center rings - Pure Plastix | 44959 | 44963 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5527.5 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 1105.5 |  | 0 | 30.15 | 4391.85 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405160A | 5502 | WWT B side Project | 4188 | C |  | WWT PP軟管及接頭_20240528 (B Side) | 45441 | 45446 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5502 | 0 | 5502 | 5502 | [71 empty] | 5502 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2405064A | 5491.18 | F21P1 WWT package (Installation and 2 batch tanks) | 4067 | C |  | WWT Fittings_20240509 (A Side) | 45422 | 45425 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 5491.18 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 2617.33 |  | 2873.85 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC24C009 | USCSB2406101A | 5490 | F21P1 Nova Interconnection | 4371 | C |  | PCA: NOVA: KUECN4-7: CO PRESSURE TESTING | 45463 | 45498 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5490 | 5490 | 0 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312011A | 5487 | Tool Interconnection Project (Main Tool & Module) | 561 | P |  | Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards.Istall conduit and cable tray dividers. KCWCN1 | 45262 | 45268 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 5487 | 0 | 5487 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C036 | USCSB2311010A | 5481 | F21P1 AMAT Interconnection | 2865 | C |  | SHARK CAGES & LOCKS | 45232 | 45237 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 5481 | 0 | 5481 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Material | USC21C005 | USCSB2406117A | 5444.44 | F21P1 Chemical & WCCS package | 4357 | C |  | CED-訊號電力材料_20240621 (Signal Wire Material) | 45467 | 45468 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5444.44 | 1394.45 | 4049.99 | 0 | [73 empty] | - |  |  | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2309129A | 5432.16 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2600 | C |  | Swagelok 2nd batch hand tools | 45190 | 45203 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5432.16 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 5432.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C036 | USCSB2310199A | 5427 | F21P1 AMAT Interconnection | 2850 | C |  | AMAT Shark Cages & Locks | 45230 | 45232 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 5427 | 0 | 5427 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC22C012 | USCSB2403011A | 5426 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3719 | C |  | UPW-Ebro valves for train B | 45352 | 45355 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5426 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 5426 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402210A | 5424.32 | F21P1 Chemical & WCCS package | 3637 | C |  | CDS Monstair cleanroom hardware needs | 45344 | 45351 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5424.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 5424.32 | 5424.32 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402078A | 5422.1 | Tool Interconnection Project (Main Tool & Other Vendors) | 794 | P |  | Interconnect cable pull for ETC1 KESRT1 10/25, 10/26, 10/27, 11/8, and 11/9 2023 | 45343 | 45345 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5422.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 5422.1 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C003 | USCSB2311035A | 5400 | F21P1 Module Tool Interconnection CVD | 2890 | C |  | Rebuild KCWNCN1 Loa Lock Lines: -Orbital Weld VCR Micro Glands and Corresponding Male/Female Connector (MICU Provided) 3/8"Ma | 45238 | 45253 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5400 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 5400 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC22C019 | USCSB2403301A | 5400 | AMC monitor 595T0 | 3993 | C |  | FAB A+B VOC Plumbing and NG Observation | 45381 | 45383 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 540 | 0.1 | 4860 | 0 | 4860 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 540 |  |  | 5400 | [5 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409025A | 5400 | TSMC Fab 21 P1B Tool Hook Up | 4793 | C |  | Y terminals_Panduit_PV10-8F-D for HK Power for 297 tools | 45540 | 45545 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5400 | 0 | 5400 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406106A | 5395.25 | F21P1-0404_H_labor for 50 tools_MICU | 4341 | C |  | HK 6 Scissor lifts rental for 4 week | 45464 | 45464 | [6 empty] | United Rentals | PR Approved | PO Approved | [14 empty] | 1581.49 | 0.29313 | 3813.76 | 0 | 3813.76 | 0 | [72 empty] | 1581.49 | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403029A | 5394 | Tool Interconnection Project (Main Tool & Other Vendors) | 855 | P |  | Manpower Pay for CCE | 45358 | 45363 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 5394 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 5394 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2311058A | 5378 | WWT Change Order (Piping) | 2913 | C | -01 | Material request E2 #4 | 45244 | 2023/11/20 2023/11/22 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | PO R1: Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5378 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 5378 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310149A | 5373 | F21P1 Chemical & WCCS package | 2805 | C |  | CDS 1-1/2"x2" 45 ELBOW 316LEP/304AP | 45223 | 45223 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5373 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 5373 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2406075A | 5372 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 4307 | C |  | M0495 Foundation manufacture_2 | 45457 | 45474 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 5372 | 1 | 0 | 5732 | -5732 | 0 | [73 empty] | 5372 |  |  | 0
Base-Build | Triazole | MMI | Main Contract Scope | WWT | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC22C022 | USCSB2309002A | 5357 | F21P1 Triazole treatment system | 2480 | C |  | Additional Steel for Catwalk to Tank Connection(Triazole Catwalk) | 45170 | 45203 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | Additional Steel for Catwalk to Tank Connection(Triazole Catwalk) |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4495 | 0.83909 | 862 | 0 | 862 | 719.2 | [40 empty] | 0 | 0 | 4495 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 719.2 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403077A | 5354.12 | F21P1-0404_H_labor for 50 tools_MICU | 3780 | C |  | Liquidtight Flex Connector for HK Power trade | 45358 | 45363 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 5354.12 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 5354.12 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2212042A | 5342.85 | F21P1 WWT package (Installation and 2 batch tanks) | 1613 | C |  | CCE Gaskets | 44917 | 44924 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 5342.85 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 4854.25 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 488.6 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310168A | 5331.05 | F21P1-0404_H_labor for 50 tools_MICU | 2822 | C |  | CED Bur terminal for Third | 45225 | 45225 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5331.05 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 5331.05 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material |  |  | UPW | Steel | Material | USC24C008 | USCSB2406141A | 5310 | UPW B Side Project | 4379 | C |  | Ladder Safety System Materials | 45471 | 45474 | [6 empty] | Diversified Products USA | PR Approved | PO Approved | [14 empty] | 5310 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 5310 |  |  | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C032 | USCSB2405029A | 5308 | F21_AZQR_Hookup_ Interconnection | 4068 | C |  | QR: KXNP01: CABLE TRAY INSTALL | 45418 | 45446 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 5308 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 5308 | [8 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407017A | 5302 | F21P1-0404_H_labor for 50 tools_MICU | 4418 | C |  | Mobile Storage Container Combo Office for HK | 2024/7/2 2024/7/4 | 45479 | [6 empty] | Allied Storage Containers | PR Approved | PO Approved | PR R1:Revise to 6 months | [13 empty] | 3960.7 | 0.74702 | 1341.3 | 498.7 | 842.6 | 0 | [66 empty] | 2052 |  |  |  | 993.7 |  | 495 | 420 |  |  | 0
Base-Build | UPW | MIMO/Rigging | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2305048A | 5300 | F21P1 UPW | 1973 | C |  | MMI temp resin move-in | 45057 | 45069 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5300 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 3180 |  |  |  | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG |  |  |  | Others |  |  | USC22C003 | USCSB2408088A | 5300 | TSMC Fab21 Project Phase 1 EDG Package | 4703 | C |  | Cup Fiber termination, installation and testing report project | 45525 | 45526 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 5035 | 0.95 | 265 | 5035 | -4770 | 0 | [73 empty] | 5035
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408047A | 5272.3 | TSMC Fab 21 P1B Tool Hook Up | 4665 | C |  | Liquid Argon for Gas, PCW, and PPL | 45514 | 45516 | [6 empty] | Linde Gas & Equipment Inc. | PR Approved | PO Approved | [14 empty] | 4583.36 | 0.86933 | 688.94 | 391.25 | 297.69 | 0 | [72 empty] | 4583.36 | -
Others | AMHS |  |  |  | AMHS |  |  | USC22C031 | USCSB2407107A | 5270 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4522 | C |  | LB1 Planking Scaffold | 45491 | 45493 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5270 | 0 | 5270 | 0 | [73 empty] | - |  |  | 0
Base-Build | CCTV | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC22C001 | USCSB2310079A | 5260 | F21 P1 Office and WH Security and CCTV | 2739 | C |  | Gown Access Control Permit Assistance | 45211 | 45217 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5260 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 3616.5 | 1643.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406061A | 5249.5 | Chemical & WCCS B Side Project | 4294 | C |  | CHEM_R325 bent_ SUS 316L BA tube | 45454 | 45455 | [6 empty] | Chukar SB&F LLC | PR Approved | PO Approved | [14 empty] | 5249.5 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 5249.5 | [8 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404065A | 5239.84 | WWT B side Project | 4057 | C |  | WWT Ball Valve_20240404(A&B Side) | 45388 | 45391 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 5239.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 785.976 |  |  |  | 785.976 | 5239.84 |  |  | 785.976 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402046A | 5203.94 | F21P1 WWT package (Installation and 2 batch tanks) | 3488 | C |  | WWT Hardware for punches | 45328 | 45330 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5203.94 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  | 1653.35 | 80.08 | 3470.51 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C003 | USCSB2311017A | 5200 | F21P1 UPW | 2872 | C |  | UPW-Degan-ACF-torque | 45234 | 45240 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5200 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 5200 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307007A | 5200 | Tool Interconnection Project (Main Tool & Module) | 343 | P |  | Electrical cable pull for KECOT2-Labor | 45128 | 45132 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5200 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 5200 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310029A | 5200 | F21P1 Chemical & WCCS package | 2692 | C |  | 45 deg Coax elbows 1 ?” x 1 for Harder work at north mains L20 FAB. | 45204 | 45209 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5200 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 5200 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2206003A | 5188.48 | F21P1 UPW | 1395 | C |  | GF Chlorine Instrument | 44715 | 44719 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  | Arrival (delivery) 100%-net 30 days-after acceptance/shipping | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 5188.48 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 5188.48 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403132A | 5180.2 | F21P1-0404_H_labor for 50 tools_MICU | 3834 | C |  | Label Roll for Power System | 45364 | 45364 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5172.54 | 0.99852 | 7.66 | 0 | 7.66 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 4383.56 | [5 empty] | 788.98 |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403101A | 5175 | Tool Interconnection Project (Main Tool & Other Vendors) | 917 | P |  | Manpower Pay for Tool ID: KEMGT1 for CGS | 45373 | 45379 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 5175 | 0 | 5175 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2405071A | 5175 | F21P1 UPW | 4091 | C |  | Fall Protection System | 45423 | 45446 | [6 empty] | Safe Keeper Safety Products LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5175 | 0 | 5175 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310046A | 5151 | Tool Interconnection Project (Main Tool & Module) | 464 | P |  | Work Post TM Reconciliation | 2023/10/21 2023/11/4 | 45307 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved | PR R1: THIS IS ORIGINAL BETWEEN TONY LEE AND TRIDENT |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5151 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 5151 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2307053A | 5145.44 | Tool Hookup Material (UPW&Chemical) | 2222 | C | -02 | HK Chemical PFA CAP | 45120 | 2023/7/25 2023/7/26 2023/8/4 | [6 empty] | Valin Corporation | PR Approved | PO Approved | WO R1:Payment Term Change WO R2:Payment Term Change Again(Remove -After acceptance) |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5145.44 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 4344.64 |  | 0 | 0 | 0 |  | 0 | [5 empty] | 800.8 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404013A | 5140 | WWT B side Project | 4009 | C |  | B-side_WWT_(25) D225 PN10 Ends Caps of Drains | 45384 | 45386 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5140 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 771 | 5140 |  |  | 771 |  |  |  | 771 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2312102A | 5123.2 | F21P1-0423_H_T&M Hardware_MICU | 3093 | C |  | Shared materials for plastic system, tool hook up | 45275 | 45278 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5123.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 3888.08 | 0 | 965.12 |  | 270 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C008 | USCSB2303074A | 5122 | F21P1 Module Tool Interconnection LIT2-3 | 1812 | C |  | 90 degree PCW welding elbow | 45002 | 45057 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 5122 | 0 | 5122 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310052A | 5108 | Tool Interconnection Project (Main Tool & Module) | 469 | P |  | Manpower | 45225 | 45273 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2923.89 | 0.57241 | 2184.11 | 0 | 2184.11 | 0 | [43 empty] | 0 |  | 0 | 0 | 2923.89 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Labor | USC21C003 | USCSB2212023A | 5100 | F21P1 UPW | 1596 | C |  | UPW-Design tanks repair | 44908 | 44910 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 5100 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5100 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2312041A | 5100 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3034 | C |  | LSW Engineers Additional electrical installation to support TSMC & Taiwan Vendors | 45267 | 45271 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5100 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 4100 |  |  | 0 | 1000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Organo |  |  |  | Others |  |  | USC24C013 | USCSB2406018A | 5100 | Organo USA - UPW Electrical | 4244 | C |  | WRC UPW Pump Revision - Observation | 45447 | 45449 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5100 | 0 | 5100 | 0 | [73 empty] | - |  |  | 0
Base-Build | Water | Material | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2311132A | 5098.4 | F21P1 WWT package (Installation and 2 batch tanks) | 2982 | C |  | Hand tools for TW team | 45259 | 45261 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5098.4 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 5098.4 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408072A | 5097 | F21P1 Module Tool Interconnection LIT2-3 | 4688 | C |  | Lit 3: KPE605-T: BB Rework | 45519 | 45524 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5097 | 5097 | 0 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2302019A | 5088.75 | F21P1 WWT package (Installation and 2 batch tanks) | 1700 | C |  | Hander bolt | 44966 | 44988 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5088.75 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 5088.75 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2312096A | 5088 | F21P1 AMAT Interconnection | 3087 | C |  | Greenberry’s Time and Materials pricing for the KIHIT3 Signal Cable Install at TSMC | 45274 | 45275 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4833.6 | 0.95 | 254.4 | 0 | 254.4 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 3610 |  | 0 | 0 | 1223.6 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401082A | 5080.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 702 | P |  | Lit 2: KPE602-S: Labor: RF Cable Tray Mesh Cover Installation | 45318 | 45322 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5080.32 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 5080.32 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401089A | 5080.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 706 | P |  | Lit 2: KPE603-S: RF Cable Tray Mesh Cover Installation | 45321 | 45322 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5080.32 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 5080.32 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401046A | 5080.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 668 | P |  | KPE601-S RF Cable Tray Mesh Cover Installation | 45311 | 45314 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5080.32 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 5080.32 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2301005A | 5076 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1628 | C |  | Teesing - ASML Tool | 44931 | 44937 | [6 empty] | Teesing USA, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 3225.6 | 0.63546 | 1850.4 | 0 | 1850.4 | 0 | [28 empty] | 0 |  |  | 3225.6 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2309040A | 5071.7 | EBO21- Tool interconnection | 2517 | C |  | EBO: NO TOOL ID: Interconnection material Strut channel, SAE washer | 45178 | 45194 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5071.7 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 868.37 | 4203.33 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2404125A | 5055.97 | WWT Change Order (Piping) | 4110 | C |  | WWT Stripper P-1231AA/AC insulation repair | 45398 | 45399 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5055.97 | 0 | 5055.97 | 5055.97 | [54 empty] | 0 |  | 0 |  |  |  |  | 758.3955 |  |  |  | 758.3955 |  |  |  | 758.3955 |  | 5055.97 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2309009A | 5051.69 | WWT Change Order (Piping) | 2487 | C |  | WWT missing material found by tsmc thu inventory | 45170 | 45175 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5051.69 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 4492.71 | 72.82 | 0 |  | 0 | 0 | 0 | 486.16 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS | Scaffolding |  |  | AMHS |  |  | USC22C031 | USCSB2403282A | 5024 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3975 | C |  | F21 L30 Column S/9.5 Scaffold. | 45380 | 45384 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 5024 | 0 | 5024 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2410055A | 5022.9 | TSMC Fab 21 P1B Tool Hook Up | 4995 | C |  | PCW CYH Hand tool Purchase request 10/2 for 200 tools | 45569 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 5022.9 | 0 | 5022.9 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C053 | USCSB2406052A | 5022 | AMAT Interconnection (TSMC) | 4277 | C |  | scaffolding assembly/dismantling KCENA3 ,KEARA1 , KEMEA2, | 45450 | 45454 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 5022 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 5022 |  |  | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407034A | 5018.08 | Tool Interconnection Project (Main Tool & Other Vendors) | 1165 | P |  | SS-QTM4A-B-6PM SS QT BODY QC 3/8" MNPT M-TIC-MNPT-009 | 45498 | 45504 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 5018.08 | 1 | 0 | 1246 | -1246 | 0 | [70 empty] | 3772.08 |  |  | 1246 |  |  | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2310123A | 5000 | F21P1 WWT package (Installation and 2 batch tanks) | 2783 | C |  | MICU Electrical On-Call Support (UPW amd WWT) | 45218 | 45225 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4945 | 0.989 | 55 | 0 | 55 | 49.45 | [41 empty] | 0 | 0 | 0 |  | 0 | 2530 | 0 | 0 | 1610 |  |  | 805 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 49.45
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2303003A | 5000 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1745 | C |  | Remove and Replace Light Pole Heads | 44986 | 44999 | [6 empty] | Graylo Construction, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 5000 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Labor | The budget execution does not pertain to this project | Shared Cost | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C013 | USCSB2310108A | 5000 | F21P1 AMC THC Monitoring System | 2770 | C |  | MICU Electrical On-Call Support | 45217 | 45219 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2687.5 | 0.5375 | 2312.5 | 0 | 2312.5 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 1035 | 0 | 0 | 0 |  |  | 460 | 0 | 0 |  | 0 |  | 345 |  |  |  | 847.5 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C006 | USCSB2408144A | 4982 | WWT B side Project | 4752 | C |  | WWT Tent 9 materials container | 45534 | 45545 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4982 | 0 | 4982 | 0 | [73 empty] | -
Base-Build | Base-Build | MIMO/Rigging |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C014 | USCSB2401134A | 4970 | F21P1 Labor incentive program-MICU | 3319 | C |  | Laydown Material - U Line | 45309 | 45314 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4970 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 4970 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C009 | USCSB2211013A | 4963.2 | F21P1 WWT package (Installation and 2 batch tanks) | 1548 | C |  | Distribution Panels | 44875 | 44875 | [6 empty] | Larson Electronics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 0 | 4963.2 | 0 | 4963.2 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 744.48 |  |  |  | 744.48 |  |  |  | 744.48 |  | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS | Scaffolding |  |  | AMHS |  |  | USC22C031 | USCSB2401112A | 4960 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3299 | C |  | AMHS MML Scaffold | 45308 | 45309 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2976 | 0.6 | 1984 | 0 | 1984 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 2976 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC22C031 | USCSB2407106A | 4960 | CAP_E_F21P1 AMHS MML Seismic Foundation | 4521 | C |  | L10 H.5-14 and A.5-14 Scaffolds | 45491 | 45491 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 2976 | 0.6 | 1984 | 2976 | -992 | 0 | [73 empty] | 2976 |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2312050A | 4950 | F21P1 WWT package (Installation and 2 batch tanks) | 3043 | C |  | WRC Lab Exhaust Hood | 45268 | 45271 | [6 empty] | Silicone Future Manufacturing Company Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4950 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 4950 |  |  | 742.5 |  |  |  | 742.5 |  |  |  | 742.5 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403069A | 4941.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 886 | P |  | Manpower pay for CGS Global for Tooll ID: KETRTE for time cards on 3.14, 3.15, 3.18, and 3.19.2024 | 45367 | 45426 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4941.12 | 0 | 4941.12 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403010A | 4935.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 837 | P |  | KPAN02-S, KPAP02-S CABLE TRAY LABOR | 45356 | 45356 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 4935.6 | 0 | 4935.6 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402045A | 4918.44 | Tool Interconnection Project (Main Tool & Other Vendors) | 765 | P |  | Electrical cable pull for KESRT5 | 45329 | [7 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 4918.44 | 8841.16 | -3922.72 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2310041A | 4917.27 | Tool Interconnection Project (Main Tool & Module) | 460 | P |  | INTERCONNECTION CABLE PULL FOR KEPCH2.G.5-L30 ELECTRICAL LABOR. 4 PEOPLE FOR 3 DAYS. For the work that was completed starting 2023/10/23 | 45218 | 45251 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4917.27 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 4917.27 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403021A | 4916.22 | F21P1 WWT package (Installation and 2 batch tanks) | 3730 | C |  | WWT Fitting_20240301 (A Side) | 45353 | 45356 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4916.22 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2445.61 |  | 2470.61 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2309145A | 4912.93 | F21P1 Module Tool Interconnection ETC1-3 | 2616 | C |  | / Butterfly Clamp Center Ring Clamp Flange Elbow Bellows | 45191 | 45222 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4912.93 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 4912.93 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2402078A | 4908.24 | F21P1 AMAT Interconnection | 3520 | C |  | KKSV03, KKDD03, KKDB05 AMAT Terminations | 45330 | 45332 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1472.47 | 0.3 | 3435.77 | 0 | 3435.77 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 1472.47 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C006 | USCSB2305108A | 4906.98 | F21P1 Module Tool Interconnection EPI | 2025 | C | -01 | Swagelok for AMAT EPI | 2023/5/24 2024/6/11 | 2023/5/30 2024/6/11 | -23498.25 | 28405.23 |  | V |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | Lower final order amount due to partial cancellation of items from total order. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4906.98 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 4906.98 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309008A | 4896 | Tool Interconnection Project (Main Tool & Module) | 402 | P |  | LAM Interconnect cable pull for KEMEL1 (ETC3) | 45181 | 45199 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3751.75 | 0.76629 | 1144.25 | 0 | 1144.25 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3751.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306039A | 4877.95 | Tool Interconnection Project (Main Tool & Module) | 323 | P |  | WIC. THHN 4 STR GRN MR COPPER BUILDING WIRE COILED & NR COPPER WIRE COILED | 45090 | 45178 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4877.94 | 1 | 0.01 | 0 | 0.01 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 4877.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C003 | USCSB2303002A | 4874.6 | F21P1 UPW | 1744 | C |  | Tank Diamond Labels | 44986 | 44992 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4874.6 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 4874.6 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | NUUO | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2402214A | 4864.6 | F21P1 Chemical & WCCS package | 3641 | C |  | CDS Fire Barrier Sealant materials | 45344 | 45344 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4864.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 4864.6 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401186A | 4863.16 | F21P1-0404_H_labor for 50 tools_MICU | 3371 | C |  | D-Ring for Safety, Weld-On PVC Cement for plastic and chemical system as hardware, tool hookup team | 45314 | 45315 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4490.89 | 0.92345 | 372.27 | 0 | 372.27 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 4490.89 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402103A | 4861.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 816 | P |  | KETRT1 labor-cable pull. - RMF L30-L20 Signal Pull - L20 8395 | 45349 | 45348 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4861.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 4861.6 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | Labor | USC21C009 | USCSB2403171A | 4852 | F21P1 WWT package (Installation and 2 batch tanks) | 3868 | C |  | WWT: Hopper Anchor Modifications | 45367 | 45369 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 4852 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 4852 |  |  | 727.8 |  |  |  | 727.8 |  |  |  | 727.8 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307074A | 4828 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2241 | C |  | Tech South Hand Tool | 45125 | 45127 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4828 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 4828 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404099A | 4817.18 | WWT B side Project | 4086 | C |  | WWT Fittings_20240409 (B Side) | 45393 | 45397 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 4817.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 4053.34 | 722.577 | 552.4 |  | 211.44 | 722.577 |  |  |  | 722.577 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2403197A | 4793.49 | F21P1 Module Tool Interconnection CVD | 3893 | C |  | L-gland, nut, gasket | 45370 | 45382 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 4793.49 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 4793.49 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2312130A | 4790.5 | F21P1-0404_H_labor for 50 tools_MICU | 3119 | C |  | erasable pens, wet floor signs, clipboards, cleanroom bags, pointer pen, and storage shelves shared by all system | 2023/12/18 2024/1/3 | 45294 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | PR R1:tax was not included |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4255.42 | 0.8883 | 535.08 | 0 | 535.08 | 0 | 4255.42 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C021 | USCSB2403278A | 4788 | F21P1 KLA Interconnection | 3971 | C |  | ME: KPMI04: CABLE PULL | 45380 | 45383 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 4788 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 4788 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2303094A | 4773 | Tool Hookup Material (UPW&Chemical) | 1831 | C |  | HK Chemical PFA Tee | 45013 | 45019 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4773 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1670.55 |  |  |  | 0 | 0 | 0 | 0 |  | 3102.45 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2311123A | 4761.54 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2974 | C |  | Items for Surprise warehouse | 45259 | 45261 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4761.54 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 4761.54 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2310032A | 4745.86 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2695 | C |  | Grainger General Electrical Warehouse Crimpers | 45204 | 45209 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 4745.86 | 0 | 4745.86 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USC2407039A | 4740 | TSMC Fab 21 P1B Tool Hook Up | 1171 | P |  | TIG Welding Certification and Training for Took Hook-Up through MSR-FSR for 27 welders | 45503 | 45504 | [6 empty] | MSR FSR LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4740 | 0 | 4740 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409005A | 4738 | Tool Interconnection Project (Main Tool & Other Vendors) | 1212 | P |  | RELOCATE CONEX BOXES | 45539 | 45540 | [6 empty] | Southwest Industrial Rigging | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4738 | 0 | 4738 | 0 | [73 empty] | -
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2408074A | 4725 | F21P1 AMHS Wiring Work Outline | 4690 | C |  | Shipment Cost for Backup DP Parts | 45520 | 45524 | [6 empty] | THIRD ENTERPRISE CO., LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4725 | 0 | 4725 | 0 | [73 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2308166A | 4725 | F21P1 Chemical & WCCS package | 2460 | C |  | Grade Three MIC Laydown Areas / Lots | 45167 | 45169 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4725 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 4725 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405182A | 4724.96 | WWT B side Project | 4210 | C |  | WWT Hardware_20240529 (B Side) | 45443 | 45446 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 4724.96 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 1332 |  | 3392.96 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408011A | 4720 | TSMC Fab 21 P1B Tool Hook Up | 4608 | C |  | Wire Thnn for HK Power trade Third for 12 tools | 45507 | 45510 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4720 | 4720 | 0 | [74 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408035A | 4718.91 | TSMC Fab 21 P1B Tool Hook Up | 4655 | C |  | Hardware for P1-B project, Plastic and Gas system | 45512 | 45518 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 4129.28 | 0.87505 | 589.63 | 0 | 589.63 | 0 | 4129.28 | [72 empty] | -
[5 empty] | Others |  |  | USC22C028 | USCSB2410028A | 4714.21 | CAP_E_F21P1 Autoshelf Foundation | 4971 | C |  | DP Design Change_AMHS_5/7 batch | 45568 | [7 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 4714.21 | 0 | 4714.21 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2403097A | 4713.66 | Tool Interconnection Project (Main Tool & Other Vendors) | 913 | P |  | ABAA0158012 Armaflex 1-5/8 X 1/2 | 45373 | 45372 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 4713.59 | 0.99999 | 0.07 | 0 | 0.07 | 0 | [52 empty] | 0 | 0 | 0 |  | 4713.59 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402114A | 4698.9 | F21P1 Chemical & WCCS package | 3552 | C |  | CDS caps and gaskets | 45335 | 45335 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 4698.9 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 4698.9 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401041A | 4679.78 | F21P1 Chemical & WCCS package | 3231 | C |  | CDS Unions etc. | 45300 | 45301 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4679.78 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 4679.78 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409100A | 4655.16 | TSMC Fab 21 P1B Tool Hook Up | 4908 | C |  | HK Power trade Hand tool_consumable Request 9/23 for 200 tools | 45561 | 45562 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4655.16 | 0 | 4655.16 | 0 | [73 empty] | -
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406012A | 4648 | Chemical & WCCS B Side Project | 4238 | C |  | F21P1 SUS B-Flange | 45444 | 45446 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 4648 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 4648 | [8 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401010A | 4616.65 | Tool Interconnection Project (Main Tool & Other Vendors) | 634 | P |  | KPAN01-T Labor | 45301 | 45307 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4616.65 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 4616.65 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2308034A | 4609 | F21P1-0404_H_Hallway plate install_MICU | 2334 | C |  | AET-G-05 Rework | 45145 | 45145 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4378.55 | 0.95 | 230.45 | 0 | 230.45 | 0 | [40 empty] | 4378.55 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403032A | 4593 | Tool Interconnection Project (Main Tool & Other Vendors) | 858 | P |  | KPAP02-S PVC Rework Labor | 45359 | 45358 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4593 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 4593 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311004A | 4589.55 | F21P1-0404_H_labor for 50 tools_MICU | 2859 | C |  | mobile bar and pipe rack, wire mesh bins for UPW offsite construction | 45231 | 45233 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 4589.55 | 0 | 4589.55 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | MMI | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2308015A | 4587 | F21P1 Slurry package | 2317 | C |  | Slurry Room Raised Gratings. | 45141 | 45142 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4587 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 4587 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C013 | USCSB2312153A | 4570 | F21P1 AMC THC Monitoring System | 3142 | C |  | FAB LITHO AMC Pressure Testing | 45281 | 45286 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4570 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 4570 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409046A | 4568 | Tool Interconnection Project (Main Tool & Other Vendors) | 1249 | P |  | KPE607-S Ball Valves | 45556 | 45559 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4568 | 0 | 4568 | 0 | [73 empty] | -
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2312150A | 4564.29 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3139 | C |  | Consolidated Electrical Distributors material for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45280 | 45280 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4564.29 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 4564.29 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2301027A | 4562.91 | F21P1 Chemical & WCCS package | 1649 | C |  | F18P4 Switch Box | 44938 | 44949 | [6 empty] | Clayton Controls | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 4562.91 | 0 | 4562.91 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 4562.91 | [9 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312190A | 4562.82 | F21P1-0404_H_labor for 50 tools_MICU | 3177 | C |  | Grainger anchor for PPL trade. Urgent per TSMC sponsor 陳俊源's request | 45289 | 45289 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4562.82 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 4498.5 |  | 0 | 0 | 0 |  | 0 | [9 empty] | 64.32 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402020A | 4560.23 | F21P1 Chemical & WCCS package | 3463 | C |  | CDS HPM Punch materials | 45324 | 45324 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 4560.23 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 4560.23 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405030A | 4549.05 | Tool Interconnection Project (Main Tool & Other Vendors) | 1089 | P |  | KEPST2 - rework - DNS SCREEN INTERCONNECTS | 45419 | 45419 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 4549.05 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 4549.05 | [10 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402160A | 4545 | F21P1-0404_H_labor for 50 tools_MICU | 3592 | C |  | TCBC105 刀刃 | 45338 | 45342 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 4545 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 4545 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406014A | 4541.8 | Chemical & WCCS B Side Project | 4240 | C |  | Hardware for Chemical System | 45444 | 45446 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 4541.8 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2105.8 | [5 empty] | 2436 |  |  | - |  |  | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2406077A | 4533 | F21P1-0404_H_Hallway plate install_MICU | 4309 | C |  | One additional tile for KDSET1_ AIB-C-06 | 45457 | 45461 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 4533 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 4533 |  |  | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402262A | 4529.9 | F21P1 Chemical & WCCS package | 3688 | C |  | CDS strut and hardware | 45350 | 45351 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 4529.9 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 4321.4 |  | 0 |  |  |  | 26.65 | 208.5 | 181.85 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2306138A | 4508 | F21P1 Module Tool Interconnection CVD | 2171 | C |  | CVD2_MACH 1+ KCANN1~7, 7 tools, Male Fujikin 1/2" Diaphragm manual valve. Interconnect Materials. | 45107 | 45118 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4508 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 4508 | - | 0 | 0 | 0
Base-Build | Slurry | Equipment | Main Contract Scope | SDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USCSB2211039A | 4491.74 | F21P1 Slurry package | 1572 | C |  | SLURRY VMB INSTALL KIT - SIDE A | 44895 | 44897 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 4491.74 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 4491.74 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409037A | 4454 | TSMC Fab 21 P1B Tool Hook Up | 4822 | C |  | Terminal Lugs for HK Power for 200 Tools | 45542 | 45545 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4454 | 0 | 4454 | 0 | [73 empty] | -
Interconnection | Interconnection | Scaffolding |  |  | Others |  |  | USC23B002 | USC2311038A | 4440 | Tool Interconnection Project (Main Tool & Module) | 512 | P |  | Action Equipment & Scaffold Co. Invoice Payment | 45245 | 45247 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 4440 | 0 | 4440 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Equipment | Main Contract Scope | SDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C006 | USCSB2303068A | 4438.85 | F21P1 Slurry package | 1807 | C |  | Add side B slurry box ingredients | 45001 | 45006 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4438.85 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 4438.85 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USC2203001A | 4429.5 | F21P1 Chemical & WCCS package | 126 | P |  | Short Reducer | 44623 | 44627 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  | 100% delivery-Net 30 days-after acceptance | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | N | [6 empty] | 4429.5 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 3239 |  | 831.5 | [17 empty] | 0 |  |  |  |  | 0 |  |  | 359 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2303038A | 4420 | F21P1 WWT package (Installation and 2 batch tanks) | 1780 | C |  | Low Voltage MCC Special Inspection Testing | 44993 | 44999 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4420 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 4420 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405057A | 4416.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1098 | P |  | KUECN3 -fixing a leak and replacing a 90-degree elbow. Identifying leaking fitting, re-terminating leaking fitting for QC, replacing fitting with missing compression rings. | 45428 | 45434 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 4416.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 4416.6 | [10 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C019 | USCSB2408120A | 4416 | F21P1 Hitachi Interconnection | 4731 | C |  | ME: KPCD07: CABLE PULL | 45531 | 45534 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 4416 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 4416 | -
Hookup | Warehouse | Site Expense |  |  | Others |  |  | USC22C008 | USCSB2403049A | 4414.44 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3756 | C |  | United Rentals Branch DK8/Item# 11292094 Boom 45-50' Telescopic 4WD Make :Gene Model: S-45XC | 45357 | 45357 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4414.44 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 4414.44 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406009A | 4414 | Tool Interconnection Project (Main Tool & Other Vendors) | 1130 | P |  | Change Order EUV Reservoir Boxes Installation Labor | 45457 | 45460 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4414 | 4414 | 0 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2308145A | 4401.61 | F21P1-0404_H_labor for 50 tools_MICU | 2440 | C |  | Machine to move personnel and equipment in a vertical direction | 2023/8/24 2023/9/2 | 45238 | 1275.49 | 3126.12 |  |  |  |  | United Rentals | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 4401.61 | 0 | 4401.61 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2305097A | 4400 | F21P1 UPW | 2018 | C |  | UPW T1035B ladder | 45066 | 45079 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4400 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 4400 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Scaffolding |  |  | Others |  |  | USC23B002 | USC2311045A | 4395 | Tool Interconnection Project (Main Tool & Module) | 519 | P |  | Pay for Action Equip & Scaffold | 45246 | 45248 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 4395 | 0 | 4395 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401259A | 4363.42 | F21P1-0404_H_labor for 50 tools_MICU | 3439 | C |  | KNAACK Cabinet Workbench, Tool hookup team | 45322 | 45323 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 4363.42 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 4363.42 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2305040A | 4362.14 | EBO21- Tool interconnection | 1965 | C |  | EBO-ZFP3 | 45057 | 45068 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4362.14 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 4362.14 | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312041A | 4352.46 | Tool Interconnection Project (Main Tool & Module) | 588 | P |  | Installer Lead - Robert Nelson | 45271 | 45272 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4352.46 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 4352.46 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403223A | 4352 | F21P1-0404_H_labor for 50 tools_MICU | 3918 | C |  | Ring Tongue for HK Power trade | 45372 | 45377 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 4352 | 1 | 0 | 2708 | -2708 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1644 | [12 empty] | 0 |  | 2708 | 0 | 0 | 0
Base-Build | WWT | Material | DCR Scope | WWT | WWT | Steel | M+L | USC21C009 | USCSB2406049A | 4350 | F21P1 WWT package (Installation and 2 batch tanks) | 4274 | C |  | WWT-GB PCO #112_Cut and extend 2 supports on X/2 | 45450 | 45454 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4350 | 0 | 4350 | 4350 | [71 empty] | 2175 |  | - | 2175 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408002A | 4350 | TSMC Fab 21 P1B Tool Hook Up | 4601 | C |  | Extension cord for welding machine, Tool hookup team | 45506 | 45506 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4350 | 4350 | 0 | [74 empty] | -
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2312049A | 4341.32 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3042 | C |  | MK Products Welding equipment in support of OSC & TSMC | 45268 | 45287 | [6 empty] | MK Products, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4341.32 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 4341.32 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401253A | 4324.2 | F21P1-0404_H_labor for 50 tools_MICU | 3434 | C |  | Cord grips for HK Power trade | 45322 | 45330 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 4324.2 | 0 | 4324.2 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2409034A | 4320 | WWT B side Project | 4820 | C |  | P-760AB Removal and Transportation | 45541 | 45545 | [6 empty] | Phoenix Pumps, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4320 | 0 | 4320 | 0 | [73 empty] | -
Base-Build | Slurry | Equipment | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USCSB2404020A | 4317.5 | F21P1 Slurry package | 4016 | C |  | Hot box change | 45384 | 45385 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 4317.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 4317.5 | 4317.5 | [5 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403068A | 4316.8 | Tool Interconnection Project (Main Tool & Other Vendors) | 891 | P |  | Michael Rodriguez 3/18-3/29 | 45367 | 45387 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 4316.8 | 0 | 4316.8 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USC2401007A | 4314.67 | F21P1 Module Tool Interconnection ETC1-3 | 631 | P |  | SAN TAN FIRE, LLC. MANPOWER PAY | 45300 | 45307 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4314.67 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 4314.67 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401169A | 4306.7 | F21P1-0404_H_labor for 50 tools_MICU | 3354 | C |  | Non-metallic twin screw for HK Power trade | 45312 | 45313 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4306.7 | 1 | 0 | 0 | 0 | 0 | 4306.7 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409068A | 4295.94 | TSMC Fab 21 P1B Tool Hook Up | 4863 | C |  | Exhaust hand tool-consumables Requested for 200 tools | 45554 | 45555 | [6 empty] | WW Grainger Inc (DBA Grainger) | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4295.94 | 0 | 4295.94 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401236A | 4288 | F21P1-0404_H_labor for 50 tools_MICU | 3418 | C |  | 40 – 8/8/4 Shoe Tee fittings with flat flanges for HK Exhaust trade | 45318 | 45320 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 4288 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 4288 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C031 | USCSB2310046A | 4286 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2707 | C |  | Distribution Panel Fillers | 45206 | 45209 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 4286 | 3428.8 | 857.2 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Greenberry | DCR Scope | WWT | WWT | Steel | M+L | USC23C045 | USCSB2308176A | 4272 | WWT Change Order (Piping) | 2469 | C |  | WWT-LB2 rack modification | 2023/8/30 2023/9/22 | 45191 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | PR R1:Request to change the price, per engineer. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 4272 | 0 | 4272 | 4272 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 640.8 |  |  |  | 640.8 |  |  |  | 640.8 |  | 2136 |  | - | 2136 | 0 | 0 | 0
Base-Build | VOC | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C007 | USCSB2302042A | 4268.64 | F21P1 VOC package （Installation ) | 1723 | C |  | Labels | 44978 | 44999 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4264.12 | 0.99894 | 4.52 | 0 | 4.52 | 0 | [28 empty] | 0 |  |  | 2944 |  | 1274.64 | 45.48 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2403161A | 4266.62 | F21P1 Module Tool Interconnection ETC1-3 | 3860 | C |  | ETC3 LAM Conduit Change Order - Material Order for Conduit Installation on 7 LAM Tools 1. KEMEL2 2. KEMEL3 3. KEMEL5 4. KEMEL | 45366 | 45377 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 4266.62 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 4266.62 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Site Expense | The budget execution does not pertain to this project | Shared Cost | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2212019A | 4260 | F21P1 WWT package (Installation and 2 batch tanks) | 1592 | C |  | WRC Generator Grounding & Permitting | 44908 | 44909 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved | USCSB2211005A CHANGE ORDER |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 4260 | 0 | 4260 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 639 |  |  |  | 639 |  |  |  | 639 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2401196A | 4260 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3381 | C |  | Global Roofing Glendale Warehouse roof inspection and roof repair | 45315 | 45352 | [6 empty] | Sprayfoam Southwest Inc, DBA Global Roofing Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 4260 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  | 4260 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C013 | USCSB2310120A | 4250 | F21P1 AMC THC Monitoring System | 2780 | C |  | FAB A Litho Electrical Permit and CA Service | 45218 | 45219 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4250 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 2565 | 0 | 0 | 1685 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2306045A | 4243.4 | F21P1 UPW | 2079 | C |  | UPW Train-A-GF valves | 45090 | 45103 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4243.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 681.29 | 0 |  |  | 3562.11 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401054A | 4235 | F21P1-0404_H_labor for 50 tools_MICU | 3243 | C |  | 5 traditional Shark Cages | 45301 | 45301 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4235 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 4235 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404053A | 4218.88 | Tool Interconnection Project (Main Tool & Other Vendors) | 1006 | P |  | Fabricating cables at MICU office for KCOXN1,2,6, and KCSCN1. Pulling cable from reels out to specified lengths, cutting and stripping cables for terminals, terminating cables, and labeliing for use in cable pulls. | 45392 | 45393 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 4218.88 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 4218.88 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C003 | USCSB2310093A | 4198.32 | F21P1 UPW | 2754 | C |  | H2O2 chemical storage in LB2 | 45213 | 45217 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4198.32 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 4198.32 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2403283A | 4176.7 | F21P1 WWT package (Installation and 2 batch tanks) | 3976 | C |  | Apollo Forklift - WWT | 45380 | 45383 | [6 empty] | Apollo Forklift LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 4176.7 | 0 | 4176.7 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 626.505 |  |  |  | 626.505 |  |  |  | 626.505 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405040A | 4176.24 | Tool Interconnection Project (Main Tool & Other Vendors) | 1082 | P |  | KRWRS1 - rework-DNS SCREEN INTERCONNECTS 4/11/2024 | 45426 | 45427 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 4176.24 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 4176.24 | [8 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C005 | USCSB2306050A | 4160 | F21P1 Module Tool Interconnection DIF1-2 | 2084 | C | -01 | DIFF: ELECTRICAL TRADE - KDAPK3 | 2023/6/14 2024/6/5 | 2023/7/27 2024/6/7 | -25840 | 30000 |  |  | V | V | Onsight Live, LLC | PR Approved | PO Approved | Order is adjusted to settle completed work only |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4160 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 4160 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401039A | 4156.91 | F21P1-0404_H_labor for 50 tools_MICU | 3229 | C |  | shared materials for UPW and chemical system first 100 Tools, Tool hook up | 45297 | 45302 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3783.62 | 0.9102 | 373.29 | 0 | 373.29 | 0 | 3783.62 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403082A | 4150 | F21P1-0404_H_labor for 50 tools_MICU | 3785 | C |  | Shared for all system, tool hookup team | 45359 | 45372 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 4150 | 0 | 4150 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2302022A | 4141.93 | F21P1 WWT package (Installation and 2 batch tanks) | 1703 | C |  | CCB-adding material | 44967 | 44978 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4141.93 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 1678.74 | 2463.19 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408054A | 4133 | F21P1 Module Tool Interconnection LIT2-3 | 4672 | C |  | Lit 2: KPE604-S: BTS Base Block Relocation | 45517 | 45519 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 4133 | 1 | 0 | 4133 | -4133 | 0 | [73 empty] | 4133
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2308169A | 4125 | F21P1 Chemical & WCCS package | 2463 | C |  | Epoxy Misc Pads in Fab L10 and Lorry 1.5 | 45167 | 45170 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4125 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 4125 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2308185A | 4111 | F21P1 Module Tool Interconnection CMP1 | 2478 | C |  | Greenberry’s Time and Material pricing for work related to the CMP MKS 1, 2, and 5 Vent Lines | 45169 | 45183 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4111 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 4111 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | DCR Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2308172A | 4101 | F21P1 Chemical & WCCS package | 2466 | C | -01 | HNO3 & ST-250 Cabinet Anchoring | 2023/8/29 2023/11/14 | 2023/9/1 2023/11/17 | -16789 | 20890 | V |  | V | V | Milling Machinery, Inc. | PR Approved | PO Approved | PO R1:Renew quotation |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4101 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 4101 |  |  | 4101 |  | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2307060A | 4100.76 | F21P1 UPW | 2227 | C |  | Crating and packing for pipes on site CO | 45121 | 45132 | [6 empty] | Crating Technology, INC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4100.76 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 4100.76 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2406068A | 4091 | F21P1 WWT package (Installation and 2 batch tanks) | 4300 | C |  | install MIC supplied Door hardware on fire doors at mezzanines 1 and 2, (5 sets of doors total) | 2024/6/12 2024/7/02 | 2024/6/25 2024/7/02 | [5 empty] | V | ISEC Incorporated | PR Approved | PO Approved | PR R1: Per ISEC's request- revised the terms and completion dates | [13 empty] | 4091 | 1 | 0 | 0 | 0 | 4091 | [70 empty] | 4091 | 2045.5 |  | - | 2045.5 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405059A | 4088.17 | Tool Interconnection Project (Main Tool & Other Vendors) | 1100 | P |  | KUECN1 - fixing a leak - Identifying leaking fitting, re-terminating fitting for QC. | 45428 | 45434 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 4088.17 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 4088.17 | [10 empty] | - |  |  | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2312131A | 4080 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3120 | C |  | ULINE Welding screens in support of TSMC & Taiwan Vendors Prefab Work | 45279 | 45280 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 4080 | 0 | 4080 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2306038A | 4075 | F21P1 Chemical & WCCS package | 2072 | C |  | Welder equipment for Chemical welding | 45087 | 45099 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4075 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 4075 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USC2112018A | 4068 | F21P1 Slurry package | 85 | P |  | Ball Valve | 44541 | 44566 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | NO CF | 100% by delivery (Net 30 days) | Cherry Chang |  | twelve (12) months following delivery | Stephon Dean | Cherry Chang | N |  | Henry |  | N | 5000 |  | 4068 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 0 |  | 4068 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403015A | 4062.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 842 | P |  | KCSCS3 Pressure test | 45356 | 45356 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4062.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 4062.32 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2403297A | 4055.18 | F21 TMAH System | 3989 | C |  | WWT Hardware_20240329 (B Side) | 45381 | 45383 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 4055.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3965.22 |  | 0 |  | 85.75 |  |  | 608.277 |  |  |  | 608.277 | 4.21 |  |  | 608.277 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Triazole | Labor | DCR Scope | WWT | WWT | Civil | Labor | USC22C022 | USCSB2310005A | 4050 | F21P1 Triazole treatment system | 2668 | C |  | Triazole pad modification in WRC | 45202 | 45205 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4050 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 4050 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C006 | USCSB2308025A | 4046.02 | F21P1 Module Tool Interconnection EPI | 2326 | C |  | Cable trays and related hardware for AMAT EPI KCENA1 | 45142 | 45145 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4046.02 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 4046.02 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407136A | 4042.61 | WWT B side Project | 4549 | C |  | WWT_B Side Hardware | 45496 | 45498 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 4042.61 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3780.11 | 0 | 262.5 | - | 0 | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309053A | 4041.84 | F21P1-0404_H_labor for 50 tools_MICU | 2529 | C |  | Extension cords for welding machines | 45181 | 45189 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4041.84 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 4041.84 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C017 | US2SB2409003A | 4040 | MIC Glendale Warehouse Management | 3 | C |  | Uline | 45563 | 45565 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4040 | 0 | 4040 | 0
[5 empty] | Others |  |  | USC24C006 | USCSB2409117A | 4025.36 | WWT B side Project | 4935 | C |  | WWT shortage materials on the B side L10, LB1, L20 Drain exhaust | 45562 | 45562 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4025.36 | 0 | 4025.36 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407005A | 4013.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 1146 | P |  | Lit 1,2,&3 Connex Move Labor | 45482 | 45486 | [6 empty] | Southwest Industrial Rigging | PR Approved | PO Approved | [14 empty] | 2041.27 | 0.5086 | 1972.23 | 0 | 1972.23 | 0 | [70 empty] | 2041.27 |  |  | - |  |  | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2306057A | 4008 | F21P1-0404_H_Hallway plate install_MICU | 2091 | C |  | AFC-A-02 dismantle and reinstallation | 45092 | 45113 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3807.6 | 0.95 | 200.4 | 0 | 200.4 | 0 | [33 empty] | 0 | [6 empty] | 3807.6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Barcode | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C012 | USCSB2110006A | 4002.14 | F21 Barcode RFID System | 1295 | C | -02 | F21P1 Barcode & RFID System Electrical | 2021/10/8 2023/6/16 2023/8/24 | 2021/10/14 2023/6/19 2023/10/25 | -95997.86 | 100000 |  |  |  |  | BPG Technologies, LLC | PR Approved | PO Approved | R2: BPG is expelled from MICU recently and the PR needs to be adjusted to actual payment amount according to PM. R1: Adjusting this PR amount based on PM's request. BPG will be expel from the work recently. | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | BARCODE | 44517 | Martin |  | Y | *5005 |  | 4002.14 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 4002.14 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401063A | 3997.78 | Tool Interconnection Project (Main Tool & Other Vendors) | 683 | P | -01 | Manpower to pull cable for KDANT4 1/22/2024-1/26/2024 ( RSPS ) | 2024/1/25 2024/3/14 | 2024/2/7 2024/3/14 | 92.7 | 3905.08 | V |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | PO R1: PR needed to be adjusted to Match Invoices From RSPS |  | Tiong Sheng Poh | [11 empty] | 3997.74 | 0.99999 | 0.04 | 0 | 0.04 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 3997.74 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C004 | USCSB2306017A | 3987.42 | F21P1 WWT package （USA EQ-FRP tank) | 2051 | C |  | All-thread stud | 45083 | 45091 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3987.39 | 0.99999 | 0.03 | 0 | 0.03 | 0 | [33 empty] | 0 |  |  |  |  | 3987.39 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403149A | 3981.3 | F21P1 Chemical & WCCS package | 3849 | C |  | Amazon - MIMO - Move In/Move Out Team | 45365 | 45370 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3446.04 | 0.86556 | 535.26 | 0 | 535.26 | 0 | 3446.04 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC24C006 | USCSB2405009A | 3978 | WWT B side Project | 3983 | C |  | WWT Center Ring 3x1.5_20240501 (B Side) | 45414 | 45419 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | [14 empty] | 3978 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 3978 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Safety | USC24C006 | US8SB2408001A | 3975 | WWT B side Project | 1 | C |  | Electrical Hazards Training required for people working with or around electricity | 45518 | 45518 | [6 empty] | LC LIND, LLC | PR Approved | PO Approved | [14 empty] | 3975 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 3975 | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402181A | 3955 | F21P1-0404_H_labor for 50 tools_MICU | 3610 | C |  | HK Power team tool request | 45342 | 45342 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3955 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 3955 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401163A | 3950 | F21P1-0404_H_labor for 50 tools_MICU | 3348 | C |  | WELDING and fragile welding label for QAQC, tool hookup team | 45311 | 45313 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3950 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 3950 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2301052A | 3940 | F21P1-0404_H_Hallway plate install_MICU | 1669 | C |  | Foundation Modification | 44953 | 44964 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3940 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 1955 |  | 1955 | 0 |  |  | 30 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2409038A | 3936.91 | WWT B side Project | 4823 | C |  | WWT shortage of fitting materials for B Side, Fab Exhaust, LSR Non-Oxidant Biocide, P-810 | 45542 | 45545 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3936.91 | 3025.51 | 911.4 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402115A | 3925.19 | Tool Interconnection Project (Main Tool & Other Vendors) | 825 | P |  | GSTRT GC112-300ASMBL COND CLAMP RGD COND CLP 3IN 12GA EG STEEL | 45351 | 45352 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3925.19 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3925.19 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2409091A | 3915.15 | TSMC Fab 21 P1B Tool Hook Up | 4913 | C |  | label shared for all systems, P1-B Tool hook up team | 45560 | 45566 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3915.15 | 0 | 3915.15 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311026A | 3914.6 | F21P1-0404_H_labor for 50 tools_MICU | 2881 | C |  | Panduit Terminal for Third for tool ATF-B07, AET-F14, ATF-C15, ATF-A04 | 45237 | 45240 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3914.6 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 3914.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407158A | 3909.6 | TSMC Fab 21 P1B Tool Hook Up | 4583 | C |  | FLOW/REG 356-AR/HE-580 DUAL for Gas trade | 45500 | 45502 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 3909.6 | 1 | 0 | 0 | 0 | [71 empty] | 3909.6 |  |  | -
Base-Build | Base-Build | MIMO/Rigging | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2403180A | 3907.96 | F21P1 Chemical & WCCS package | 3877 | C |  | Zoro - MIMO - Move In/Move Out Team | 2024/3/18 2024/3/28 | 45383 | [6 empty] | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3407.96 | 0.87206 | 500 | 0 | 500 | 0 | [52 empty] | 0 | 0 | 1988.34 |  | 1419.62 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC23C045 | USCSB2311082A | 3903.38 | WWT Change Order (Piping) | 2935 | C |  | TW team tool - threaded machine(YAHO) | 45247 | 45248 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3903.38 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 3903.38 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2402174A | 3900 | F21P1-0404_H_labor for 50 tools_MICU | 3603 | C |  | Crimper Kit for HK Power trade | 45340 | 45342 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3549 | 0.91 | 351 | 0 | 351 | 0 | 3549 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402091A | 3892.26 | F21P1 WWT package (Installation and 2 batch tanks) | 3531 | C |  | WWT Hardware for A side punches | 45331 | 45335 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3892.26 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 3597.9 | 192.8 | 101.56 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW |  |  |  | UPW | Mechanical | M+L | USC24C008 | USCSB2409050A | 3891 | UPW B Side Project | 4834 | C |  | T&M WRC L20 Rack Welding | 45548 | 45548 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3891 | 0 | 3891 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401034A | 3889.28 | Tool Interconnection Project (Main Tool & Other Vendors) | 657 | P |  | Installers from SantanFire to conduct & complete interconnection work on KUECN1 | 45308 | 45308 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3889.28 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 3889.28 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | E2 | USC21C005 | USCSB2309086A | 3889 | F21P1 Chemical & WCCS package | 2559 | C |  | Hardware for Chemical YaoHong work at Lorry FNDP. | 45184 | 45188 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3889 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 3889 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311079A | 3881.96 | Tool Interconnection Project (Main Tool & Module) | 547 | P |  | 6" FLEXIBLE DUCT (MD-13) | 45259 | 45261 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3881.96 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 3881.96 | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2312109A | 3872.83 | F21P1 WWT package (Installation and 2 batch tanks) | 3099 | C |  | WWT_18" Galvanized P-Clamps | 45276 | 45278 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3810.3 | 0.98385 | 62.53 | 0 | 62.53 | 76.206 | [45 empty] | 0 | 0 | 0 | 275.88 | 0 |  |  | 1731.03 | 1803.39 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 76.206
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C032 | USCSB2401234A | 3867.61 | F21_AZQR_Hookup_ Interconnection | 3416 | C |  | QR LAB: KXPS/KXFX/KXSM: CABLE TRAY CLAMPS, STRUT NUT, WEDGE ANCHOR | 45317 | 45330 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3867.61 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 3867.61 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311077A | 3856.85 | Tool Interconnection Project (Main Tool & Module) | 545 | P |  | WIRE THHN6STRGRN | 45258 | 45259 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3816.94 | 0.98965 | 39.91 | 0 | 39.91 | 0 | [43 empty] | 0 |  | 3816.94 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2312002A | 3850 | Tool Interconnection Project (Main Tool & Module) | 554 | P |  | Grounding Box and Wiring | 45261 | 45279 | [6 empty] | Advanced Technical Solutions, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3850 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 3850 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310117A | 3841.6 | F21P1 Chemical & WCCS package | 2778 | C | -01 | CDS Unions to replace all Union Box accessories of Lorry to HPM IPA and PFA to SUS. | 2023/10/19 2023/10/19 | 2023/10/23 2023/10/25 | 1812.6 | 2029 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1:As per responsible engineer to revise QTY |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3841.6 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 3841.6 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307005A | 3840 | Tool Interconnection Project (Main Tool & Module) | 341 | P |  | Run power and signal cables accordingly, Get TSMC & EE’s to sign off to make sure everything is safe/qualified per TSMC standard. | 45118 | 45127 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3445 | 0.89714 | 395 | 0 | 395 | 0 | [40 empty] | 3445 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2307088A | 3840 | F21P1 Module Tool Interconnection CVD | 2254 | C |  | Alvarado Electric labor Cable Pull Labor for KCANN1 and KCANN2 | 2023/7/20 2024/8/14 | 2023/7/27 2024/8/15 | -2840 | 6680 | V |  |  |  | Alvarado Electric LLC. | PR Approved | PO Approved | To release excess budgeted contract sum |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3840 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 2640 | 1200 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402070A | 3832 | Tool Interconnection Project (Main Tool & Other Vendors) | 786 | P |  | KPSP10: CABLE PULL | 45336 | 45337 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 3832 | 1 | 0 | 4290.93 | -4290.93 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 3832 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403135A | 3827.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 950 | P |  | BLINE 73A120 for DRY ETC | 45380 | 45381 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3827.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 3827.5 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2205009A | 3825 | F21P1 UPW | 1373 | C |  | Modular Office Miscellaneous Works | 44691 | 44692 | [6 empty] | Design Modulars Inc. | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 3825 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 3825 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405140A | 3824.19 | Tool Interconnection Project (Main Tool & Other Vendors) | 1115 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45436 | 45441 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 3824.19 | 1 | 0 | 3824.19 | -3824.19 | 0 | [73 empty] | 3824.19 |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401069A | 3800 | Tool Interconnection Project (Main Tool & Other Vendors) | 689 | P |  | KPE602-S Labor | 45316 | 45325 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3800 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 3800 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C003 | USCSB2310197A | 3800 | F21P1 Module Tool Interconnection CVD | 2848 | C | -02 | Rebuild KCANN2 Loa Lock Lines: -Orbital Weld VCR Micro Glands and Corresponding Male/Female Connector (MICU Provided) 3/8"Mal | 45230 | 2023/11/1 2023/11/8 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved | PO R1:Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3800 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 3800 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C003 | USCSB2310193A | 3800 | F21P1 Module Tool Interconnection CVD | 2845 | C |  | Rebuild KCANN1 Loa Lock Lines: -Orbital Weld VCR Micro Glands and Corresponding Male/Female Connector (MICU Provided) 3/8"Mal | 45230 | 45232 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3800 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 3800 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Electrical | Material | USC24C006 | USCSB2407054A | 3800 | WWT B side Project | 4453 | C |  | To supplement the damage and missing leak sensor cable for site A and site B. | 45483 | 45486 | [6 empty] | Autotronic Enterprise Co., Ltd | PR Approved | PO Approved | [14 empty] | 3800 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 3800 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Steel | M+L | USC24C006 | USCSB2408010A | 3799.21 | WWT B side Project | 4607 | C |  | HPM Beam removal_WWT | 45507 | 45511 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3799.21 | 3799.21 | 0 | [74 empty] | -
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208026A | 3798.35 | F21P1 UPW | 225 | P0 |  | Dell BIM Laptop | 44800 | 44820 | [6 empty] | Dell Technologies | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3798.35 | 1 | 0 | 0 | 0 | 0 | 3798.35 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2312126A | 3796.5 | F21P1 WWT package (Installation and 2 batch tanks) | 3116 | C |  | WWT_18" Galvanized P-Clamps_LSD Asiede + Bisde 18” Clamp needed. | 45276 | 45278 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3796.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 3796.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2410022A | 3794.53 | TSMC Fab 21 P1B Tool Hook Up | 4965 | C |  | Hand tool-consumable for HK power | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 3794.53 | 0 | 3794.53 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C031 | USCSB2401063A | 3790.44 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3252 | C |  | Housekeeping Material | 45302 | 45313 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3407.64 | 0.89901 | 382.8 | 0 | 382.8 | 0 | 3407.64 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403013A | 3788 | Tool Interconnection Project (Main Tool & Other Vendors) | 840 | P |  | ZLMS01: CABLE PULLS | 45356 | 45364 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3788 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3788 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401008A | 3787.17 | Tool Interconnection Project (Main Tool & Other Vendors) | 632 | P |  | KPOCT4 Labor | 45301 | 45308 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3787.17 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 3787.17 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2401228A | 3785.8 | F21P1 WWT package (Installation and 2 batch tanks) | 3410 | C |  | Tmah + L20 Sludge CDA materials | 45317 | 45318 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3785.8 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  | 3785.8 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311015A | 3776 | Tool Interconnection Project (Main Tool & Module) | 488 | P |  | Labor | 45234 | 45239 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2475 | 0.65546 | 1301 | 0 | 1301 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 2475 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311061A | 3776 | Tool Interconnection Project (Main Tool & Module) | 530 | P |  | SANTAN PAY FOR KEBCT2 | 45251 | 45252 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3776 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311014A | 3776 | Tool Interconnection Project (Main Tool & Module) | 487 | P |  | MECHANICAL LABOR | 45234 | 45238 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3776 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311012A | 3776 | Tool Interconnection Project (Main Tool & Module) | 485 | P |  | Cable pull for KDSTS1 | 45233 | 45237 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3304 | 0.875 | 472 | 0 | 472 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 3304 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401025A | 3776 | Tool Interconnection Project (Main Tool & Other Vendors) | 648 | P |  | LABOR | 45304 | 45308 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 3776 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311060A | 3776 | Tool Interconnection Project (Main Tool & Module) | 529 | P |  | SANTAN PAY FOR KEBCT1 | 45251 | 45253 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 3776 | 0 | 3776 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311059A | 3776 | Tool Interconnection Project (Main Tool & Module) | 528 | P |  | SANTAN PAY FOR KEPST2 | 45251 | 45252 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3776 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311057A | 3776 | Tool Interconnection Project (Main Tool & Module) | 527 | P |  | SANTAN PAY FOR KEPST1 | 45251 | 45252 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3776 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407044A | 3750 | WWT B side Project | 4443 | C |  | WWT- threaded machine | 2024/7/10 2024/7/11 | 45483 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | PR R1:No need buffer as we found out can be purchased from Ferguson | [13 empty] | 3750 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3750 | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2406013A | 3749.82 | Chemical & WCCS B Side Project | 4239 | C |  | F21P1 - Electric conduit | 45444 | 45446 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 3749.82 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 3749.82 | [10 empty] | - |  |  | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2306080A | 3748.37 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2113 | C0 |  | amazon-hand tool (technician Project) | 45097 | 45105 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3748.37 | 1 | 0 | 0 | 0 | 0 | 3748.37 | [32 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401153A | 3714 | F21P1-0404_H_labor for 50 tools_MICU | 3338 | C |  | materials for all systems, tool hookup team | 45310 | 45310 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3330 | 0.89661 | 384 | 0 | 384 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 3330 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404097A | 3711.96 | Tool Interconnection Project (Main Tool & Other Vendors) | 1047 | P |  | Manpower pay to RS Payroll Services for Tool ID: KEPRL3 for Timecards 2.6, 2.8, 2.9, 2.12, and 3.7.2024 | 45407 | 45408 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3711.96 | 0 | 3711.96 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | UMEC | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402135A | 3709 | F21P1 WWT package (Installation and 2 batch tanks) | 3571 | C |  | WWT UMEC copper tubing to instrument | 45337 | 45338 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3709 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 3524 | 0 | 0 |  | 185 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | MMI | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2309171A | 3702 | F21P1 UPW | 2640 | C |  | MMI-T1034B-ladder repair | 45197 | 45202 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3702 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3516.9 | 0 | 0 | 0 |  |  | 0 | 0 | 185.1 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C036 | USCSB2308055A | 3700 | F21P1 AMAT Interconnection | 2353 | C |  | Raised Floor For AMAT Tools to Meet NEC Co | 45147 | 45148 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3700 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 3700 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2311117A | 3683.55 | F21P1 Chemical & WCCS package | 2968 | C | -01 | CDS LORRY TO BRIDGE PFA Tin in Swagelok SUS material Insert EP(Electro Polishing) | 45258 | 2023/11/30 2023/12/5 | 705.6 | 2977.95 | V |  |  |  | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | PO R1:Renew quotation |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3683.55 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 3683.55 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2305004A | 3679.5 | Tool Interconnection Project (Main Tool & Module) | 273 | P |  | CVD2 Tool interconnection materials | 45063 | 45064 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3672.53 | 0.99811 | 6.97 | 0 | 6.97 | 0 | [33 empty] | 0 |  |  | 3672.53 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2405040A | 3653.67 | F21P1 UPW | 4049 | C |  | Materials for Train 2 from Taiwan Supplier | 45420 | 45422 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 3653.67 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 3653.67 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311074A | 3647.98 | Tool Interconnection Project (Main Tool & Module) | 542 | P |  | 13/16 x 10' PRE-GALV BACK TO BACK HALF SLOT STRUT | 45258 | 45259 | [6 empty] | TRI STAR INDUSTRIAL LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3647.98 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 3622.66 | 25.32 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312097A | 3633.9 | F21P1-0404_H_labor for 50 tools_MICU | 3088 | C |  | Boxes for shipping out material and supplies | 45274 | 45275 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 468.2 | 0.12884 | 3165.7 | -60.3 | 3226 | 0 | [45 empty] | 0 | 0 | 0 | 72.9 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 395.3 | [6 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402070A | 3625 | F21P1-0404_H_labor for 50 tools_MICU | 3512 | C |  | ULINE UTILITY CART, for gas system | 45330 | 45332 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 3625 | 1 | 0 | 0 | 0 | 0 | 3625 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | The budget execution does not pertain to this project | 0 | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USC2402072A | 3620.25 | F21P1 Chemical & WCCS package | 788 | P |  | manpower - general labors | 2024/2/16 2024/4/25 | [8 empty] | PR Approved | PO Processing | PR R1:Uploading supporting documents |  | 0 | [11 empty] | 0 | 0 | 3620.25 | 2188.83 | 1431.42 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404077A | 3615.7 | Tool Interconnection Project (Main Tool & Other Vendors) | 1031 | P |  | Manpower Pay for CCE Tool ID: KEMGT1 Timecards 2.28 and 2.28.2024 | 45402 | 45406 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3615.7 | 0 | 3615.7 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2308154A | 3615.06 | F21P1 Module Tool Interconnection CMP1 | 2448 | C |  | CMP: NO TOOL ID: SINGLE TILE BARRICADE | 45162 | 45167 | [6 empty] | Metzfab Industries | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3615.06 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 3615.06 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2406020A | 3610.78 | WWT B side Project | 4246 | C |  | WWT Beam Clamps & Base_20240603 (B Side) | 45447 | 45447 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3610.78 | 0 | 3610.78 | 3610.78 | [71 empty] | 1805.39 |  | - | 1805.39 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2408141A | 3608.9 | WWT B side Project | 4750 | C |  | WWT shortage materials on the B side LSR, CCR, and ACF-1928 | 45533 | 45534 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3608.9 | 3922.67 | -313.77 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402060A | 3606.8 | Tool Interconnection Project (Main Tool & Other Vendors) | 778 | P |  | Manpower pay to RS Payroll Services for Tool ID: KEPRL1 for Timecards 2.15, 2.16, 2.19, and 2.20.2024 | 45336 | 45392 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 3606.8 | 2308.31 | 1298.49 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C034 | USCSB2410004A | 3604.35 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/ N2/APK/UPK/ASRS | 4951 | C |  | 10/3 wire for AMHS Scope | 45566 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 3604.35 | 0 | 3604.35 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407070A | 3600 | TSMC Fab 21 P1B Tool Hook Up | 4488 | C |  | M200 calibration service | 45486 | 45489 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Processing | 因機台為MICU對下包以租賃形式，所有維修、校正皆不須由MICU負擔，故取消此單 | [13 empty] | 0 | 0 | 3600 | 0 | 3600 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2403214A | 3600 | F21P1 Module Tool Interconnection CVD | 3909 | C |  | Labor: Torque and Seal AMAT CVD | 45372 | 45380 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3600 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 3600 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2402199A | 3600 | F21P1-0404_H_labor for 50 tools_MICU | 3626 | C |  | general labor for RS Payroll services | 45343 | 45349 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 3600 | 0 | 3600 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Electrical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407012A | 3598 | WWT B side Project | 4413 | C |  | These instruments will be installed for control system of B site. | 45475 | 45475 | [6 empty] | Process Technology, Inc | PR Approved | PO Approved | [14 empty] | 3598 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3598 | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403127A | 3591.01 | Tool Interconnection Project (Main Tool & Other Vendors) | 942 | P |  | 30XT36 Ring Terminal,Bare,6 AWG,6 AWG,PK10 | 45378 | 45379 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 3591.01 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3591.01 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2312065A | 3591 | F21P1 Chemical & WCCS package | 3057 | C |  | CDS Lorry Crossover Steps. | 45269 | 45273 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3591 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 3411.45 |  | 0 |  | 179.55 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2310075A | 3591 | F21P1 Chemical & WCCS package | 2736 | C |  | CDS Lorry Crossover Steps. | 45211 | 45217 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3591 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3411.45 | 0 | 0 | 0 |  |  | 179.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2406044A | 3586.55 | WWT B side Project | 4270 | C |  | WWT CDA B SUS material | 45449 | 45454 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 3586.55 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 3586.55 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C011 | USCSB2409081A | 3585 | F21P1 AMHS MML Power Design - Muratech | 4873 | C |  | 150 3-Pole DP Fillers_AMHS | 45555 | 45560 | [6 empty] | HD Supply, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3585 | 0 | 3585 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402063A | 3582.69 | F21P1-0404_H_labor for 50 tools_MICU | 3505 | C |  | Fiberglass Routing S-Hook for 2-3/4" Maximum Bundle Diameter, Yellow | 45329 | 45329 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3582.69 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 3582.69 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2403004A | 3580 | F21P1 WWT package (Installation and 2 batch tanks) | 3712 | C |  | WWT Center Ring_20240228 (A Side) | 45352 | 45352 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3580 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3580 |  | 0 |  |  |  |  | 537 |  |  |  | 537 |  |  |  | 537 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Labor | Main Contract Scope | UPW | UPW | Electrical | QAQC | USC21C003 | USCSB2304030A | 3575 | F21P1 UPW | 1870 | C |  | MCP-1,4 Special Inspection | 45029 | 45035 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3575 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 3575 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312046A | 3567.88 | Tool Interconnection Project (Main Tool & Module) | 592 | P |  | KESRT1 in-house manpower EOPS | 45273 | 45303 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3567.88 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 895.63 | 2672.25 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403106A | 3565.25 | Tool Interconnection Project (Main Tool & Other Vendors) | 922 | P |  | Manpower Pay for Tool ID: KESRT5 for CCE | 45374 | 45402 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 3565.25 | 0 | 3565.25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402077A | 3563.78 | Tool Interconnection Project (Main Tool & Other Vendors) | 793 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45343 | 45344 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3563.78 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3563.78 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2312016A | 3562.22 | Tool Interconnection Project (Main Tool & Other Vendors) | 565 | P |  | PPW: MANPOWER: 2 PEOPLE 12/07-12/15 & MILEAGE. | 45262 | 45400 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 3562.22 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 3562.22 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Housekeeping | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C009 | USCSB2404149A | 3556.74 | F21P1 WWT package (Installation and 2 batch tanks) | 4133 | C |  | Amazon - UPW Clean up and equipment maintenance | 2024/4/19 2024/4/30 | 45427 | [6 empty] | A&A Materials | PR Approved | PO Approved | rpr r1: Original vendor is out of the rock necessary, found a new vendor information is now updated and entered. | [13 empty] | 3233.4 | 0.90909 | 323.34 | 0 | 323.34 | 0 | 3233.4 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202006A | 3554.47 | F21P1 UPW | 115 | P0 |  | Autodesk AECC License | 44604 | 44609 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3554.47 | 1 | 0 | 0 | 0 | 0 | 3554.47 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2305025A | 3550 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1948 | C |  | Glendale Office West Side - Alarm and Surveillance | 45051 | 45054 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3550 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 532.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 3017.5 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2403071A | 3538.29 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3775 | C |  | RS PAYROLL SERVICES, TIMECARD PAYMENT FOR ASSOCIATES INVOICE#4721 | 45358 | 45358 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3538.29 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3538.29 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407063A | 3536 | WWT B side Project | 4460 | C |  | WWT FAB Chemical dump centralizer | 45484 | 45488 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | [14 empty] | 3536 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3536 | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2210004A | 3528.33 | F21P1 Chemical & WCCS package | 249 | P0 |  | AECC License | 44835 | 44839 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3528.33 | 1 | 0 | 0 | 0 | 0 | 3528.33 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405114A | 3515.4 | F21P1-0404_H_labor for 50 tools_MICU | 4143 | C |  | Knaack jobsite box for HK PPL trade | 45433 | 45433 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 3515.4 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 3515.4 | [10 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209013A | 3511.5 | F21P1 Chemical & WCCS package | 238 | P0 |  | Lenovo Laptop | 44825 | 44826 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3511.5 | 1 | 0 | 0 | 0 | 0 | 3511.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312077A | 3511 | Tool Interconnection Project (Main Tool & Module) | 620 | P |  | KPAP01-S Labor | 45282 | 45287 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3335.45 | 0.95 | 175.55 | 0 | 175.55 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 3335.45 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402006A | 3507.19 | Tool Interconnection Project (Main Tool & Other Vendors) | 734 | P |  | 92240A911; 18-8 Stainless Steel Hex Head Screw, 3/8"-16 Thread Size, 1" Long, Packs of 25 | 45323 | 45323 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3507.19 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 3507.19 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309003A | 3507.19 | Tool Interconnection Project (Main Tool & Module) | 398 | P |  | 92240A911 18-8 SS HEX HEAD SCREW 3/8"-16 THREAD SIZE, 1" LONG, PACKS OF 25 | 45176 | 45180 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3507.19 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 3507.19 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402006A | 3502 | F21P1 Chemical & WCCS package | 3449 | C |  | CDS pipe labels | 45323 | 45323 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 3502 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 3502 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Labor | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC22C019 | USCSB2312154A | 3500 | AMC monitor 595T0 | 3143 | C |  | FAB B VOC Mechanical Observation | 45281 | 45280 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 3500 | 0 | 3500 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 3500 |  | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2311039A | 3500 | F21P1 UPW | 2894 | C |  | Prominent H2O2 Starup service | 45238 | 45240 | [6 empty] | Precision Integrated Systems, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1750 | 0.5 | 1750 | 0 | 1750 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 1750 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2406047A | 3500 | F21P1 AMAT Interconnection | 4273 | C |  | Rework KSSWA1 | 45449 | 45454 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 3500 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3500 |  |  | - |  |  | 0
[5 empty] | Others |  |  | USC24C013 | USCSB2410049A | 3500 | Organo USA - UPW Electrical | 4991 | C |  | Door frame & door for Mezz#3 | 45569 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 3500 | 0 | 3500 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C005 | USCSB2307102A | 3500 | F21P1 Module Tool Interconnection DIF1-2 | 2268 | C |  | KPADK2-4: SIGNAL CABLES INSTALLATION | 45129 | 45146 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3500 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 3500 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402016A | 3497 | Tool Interconnection Project (Main Tool & Other Vendors) | 742 | P |  | KPE602-S & KPE603-S Labor | 45324 | 45327 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3497 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 3497 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2311093A | 3492.06 | WWT Change Order (Piping) | 2944 | C |  | WWT 300lb SUS Flange | 45248 | 45252 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3492.06 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 3492.06 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407019A | 3486.7 | F21P1-0404_H_labor for 50 tools_MICU | 4420 | C |  | HK Power Luis escape strap request | 45475 | 45491 | [6 empty] | Paramount Corp DBA Oberon | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3486.7 | 0 | 3486.7 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405077A | 3482 | WWT B side Project | 4097 | C |  | WWT Welding Rod_20240510 (B Side) | 45423 | 45427 | [6 empty] | Supertung Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 3482 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 3482 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408068A | 3449 | F21P1 Module Tool Interconnection LIT2-3 | 4684 | C |  | Lit 3: KPE605-T: Cable Tray Modifications | 45519 | 45520 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3449 | 3449 | 0 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402028A | 3442.64 | F21P1 WWT package (Installation and 2 batch tanks) | 3471 | C |  | SUS added to A side 02/01 all drop not finish 1st order(SUS WWTSP1E2024-1) | 45324 | 45324 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3442.64 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 | 3442.64 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2311088A | 3441.93 | F21P1 AMAT Interconnection | 2940 | C |  | Change Order: KSSBA3 Wire Demo and Repull | 45247 | 45250 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 3441.93 | 0 | 3441.93 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2310006A | 3441.93 | F21P1 AMAT Interconnection | 2669 | C |  | Change Order total for KSSBA3 | 45202 | 45206 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 3441.93 | 0 | 3441.93 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403059A | 3428 | F21P1-0404_H_labor for 50 tools_MICU | 3764 | C |  | Security cart for HK power trade | 45357 | 45358 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3428 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3428 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2312054A | 3428 | Tool Interconnection Project (Main Tool & Other Vendors) | 600 | P |  | Manpower Pay for KEPOT1 for RS PAYROLL | 45274 | 45362 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 0 | 0 | 3428 | 4129.55 | -701.55 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2406045A | 3427.2 | F21P1 Chemical & WCCS package | 4271 | C |  | CGS Global Manpower Labor for painting of housekeeping pads | 45449 | 45450 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 3427.2 | 1 | 0 | 1713.6 | -1713.6 | 0 | [66 empty] | 1713.6 | [6 empty] | 1713.6 |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304026A | 3423.5 | F21P1 WWT package (Installation and 2 batch tanks) | 1866 | C |  | Small pipe reinforcement | 45028 | 45043 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 3423.5 | 0 | 3423.5 | 3765.85 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 513.525 |  |  |  | 513.525 |  |  |  | 513.525 |  | 3423.5 |  | - | 342.35 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208023A | 3418.27 | F21P1 UPW | 222 | P0 |  | Lenovo Laptop | 44800 | 44810 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3418.27 | 1 | 0 | 0 | 0 | 0 | 3418.27 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406025A | 3416.23 | F21P1-0404_H_labor for 50 tools_MICU | 4251 | C | -01 | 4-40' Rental Containers for HK shared by all system | 2024/6/5 2024/6/20 | 2024/6/6 2024/6/20 | 2100 | 1316.23 |  |  | V |  | Allied Storage Containers | PR Approved | PO Approved | Additional amount is for extension of rental from 1 to 6 months. | [13 empty] | 2612.35 | 0.76469 | 803.88 | 36.12 | 767.76 | 0 | [66 empty] | 1736.23 |  |  |  | 456.12 |  | 420 | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407026A | 3413.95 | F21P1-0404_H_labor for 50 tools_MICU | 4425 | C |  | Fresh water tank for 6 months for HK shared by all system | 45476 | 45479 | [6 empty] | United Rentals | PR Approved | PO Approved | [14 empty] | 838.17 | 0.24551 | 2575.78 | 44.09 | 2531.69 | 0 | [68 empty] | 749.99 |  |  |  | 44.09 | 44.09 |  |  | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307048A | 3409.9 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2217 | C |  | Global Industrial | 45119 | 45125 | [6 empty] | Global Equipment Company Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3409.9 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 3409.9 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2211016A | 3408 | F21P1 WWT package (Installation and 2 batch tanks) | 1550 | C |  | Ebro Butterfly Valve | 44877 | 44896 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 3408 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 3408 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2306061A | 3397 | F21P1-0404_H_Hallway plate install_MICU | 2095 | C | -01 | Soft barricade | 2023/6/15 2023/7/17 | 2023/6/29 2023/7/18 | 255 | 3142 | V |  |  |  | HSIEH SHUN HING CO., LTD. | PR Approved | PO Approved | R1:packing fee |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 1559 | 0.45893 | 1838 | 0 | 1838 | 0 | [33 empty] | 0 |  |  |  |  | 1559 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2311133A | 3360 | F21P1 UPW | 2983 | C |  | UPW-ORGANO-flexible joints | 45259 | 45261 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3360 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2409027A | 3359.73 | Tool Interconnection Project (Main Tool & Other Vendors) | 1230 | P |  | 400CL-012H 1-1/4" PIPE P/E CLR PVC SCH40 CPN-P-TIC-CPV-PI-035 | 45548 | 45551 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 50% down payment, 50% after acceptance, T/T 7 days. | Eddie |  |  | Chia-Yi Chang | Eddie |  |  | Henry |  | N |  |  | 0 | 0 | 3359.73 | 2473.4 | 886.33 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | PSS | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2311137A | 3357.6 | F21P1 WWT package (Installation and 2 batch tanks) | 2987 | C |  | WWT-PSS-motor valve installation | 45259 | 45261 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 503.64 |  |  |  | 503.64 | [5 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2210014A | 3355.7 | F21P1 UPW | 257 | P0 |  | Lenovo Laptop | 44842 | 44859 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3355.7 | 1 | 0 | 0 | 0 | 0 | 3355.7 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Electrical | Material | USC24C005 | USCSB2407086A | 3355 | Chemical & WCCS B Side Project | 4502 | C |  | F21P1 B side 電力訊號貼紙_Chemical | 45489 | 45489 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3355 | 0 | 3355 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2305069A | 3355 | F21P1 Chemical & WCCS package | 1991 | C |  | TSMC F21P1 Items | 45062 | 45069 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 0 | 0 | 3355 | 0 | 3355 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2305068A | 3348.64 | F21P1 UPW | 1990 | C |  | UPW pipe pressure test nitrogen | 45062 | 45065 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3348.64 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 1330.88 | 612.52 | 888.76 | 273.18 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 243.3 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C017 | USCSB2408122A | 3346.5 | F21P1 ASML Interconnection | 4733 | C |  | ME: KKSS02: CABLE PULL | 45531 | 45534 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 3346.5 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 3346.5 | -
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C006 | USCSB2407140A | 3345 | WWT B side Project | 4552 | C |  | WWT Tent 9 WMS Service Order(12 month) | 45497 | 45504 | [6 empty] | 3PL Central LLC dba Extensiv | PR Approved | PO Approved | [14 empty] | 1371.55 | 0.41003 | 1973.45 | 0 | 1973.45 | 0 | [70 empty] | 535.3 | 0 | 836.25 | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2303014A | 3344.96 | F21P1 UPW | 1756 | C |  | UPW tank sight glasses and angle stops | 44987 | 45000 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3344.96 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 3344.96 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311011A | 3342.53 | Tool Interconnection Project (Main Tool & Module) | 484 | P |  | KPAP02-S Stainless Material for XCHA Line | 45233 | 45237 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3342.41 | 0.99996 | 0.12 | 0 | 0.12 | 0 | [42 empty] | 0 | 0 |  | 0 | 3342.41 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2305089A | 3325.52 | F21P1 Chemical & WCCS package | 2010 | C |  | EW NEW BOX ADD | 45065 | 45077 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3325.52 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 3325.52 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2408006A | 3319 | WWT B side Project | 4604 | C |  | WWT: (400 Total) Centralizer for H2SO2 and NaOH Rework | 45506 | 45512 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | [14 empty] | 3319 | 1 | 0 | 0 | 0 | [73 empty] | 3319 | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306040A | 3314.22 | Tool Interconnection Project (Main Tool & Module) | 324 | P |  | ENCLOSURE JUNCTION BOX, GROUNDING CONNECTOR | 45090 | 45181 | [6 empty] | RS AMERICAS, INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3314.22 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 1438.52 | 0 | 0 | 498.72 |  | 0 | 0 | 0 | 1376.98 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2401034A | 3304 | F21P1 Chemical & WCCS package | 3225 | C |  | CDS Move C02 Cylinder 不追加 | 45297 | 45299 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3304 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 3138.8 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3304 |  |  |  |  | 165.2 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403065A | 3300.36 | Tool Interconnection Project (Main Tool & Other Vendors) | 888 | P |  | PFA-T10M-1M-30M 30m COIL 10M PFA Tubing | 45366 | 45365 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 3300.36 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3300.36 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C008 | USCSB2303066A | 3300 | F21P1 Module Tool Interconnection LIT2-3 | 1805 | C |  | TSMC Machine panel fabrication ( cut the hole ) | 45001 | 45012 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 3300 | 0 | 3300 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Site Expense |  |  | Others |  |  | USC22C037 | USCSB2305004A | 3300 | F21P1 Screen Main tool interconnection | 1928 | C |  | ESD Jumpsuit with Hood | 45048 | 45048 | [6 empty] | Super Starnix SDN BHD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3300 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 3300 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208021A | 3285.55 | F21P1 UPW | 220 | P0 |  | Lenovo Laptop | 44800 | 44810 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3285.55 | 1 | 0 | 0 | 0 | 0 | 3285.55 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USC2112015A | 3282.49 | F21P1 Chemical & WCCS package | 82 | P |  | Sleeve | 44539 | 44572 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | CF (Trade term check)) | 90% by shipment, and last 10% invoice within 60 days of receiving the goods. All invoices are NET 30. | York Yeh | FOB Osaka port | 24 months | Chih-Chien Hung | York Yeh | N |  | Henry | Fittings | N | 5000 |  | 3282.49 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 3282.49 | [17 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2303061A | 3280 | F21P1 UPW | 1800 | C |  | UPW MCP-1, 4 Engineering Design | 45000 | 45008 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3280 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 3280 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | CO Scope (adding/additional scope) | UPW | UPW | Electrical | Labor | USC21C003 | USCSB2303001A | 3280 | F21P1 UPW | 1743 | C |  | TSMC F21P1 WRC UPW MCP-21 Temp Feed | 44986 | 44986 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3280 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 3280 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2312177A | 3279.22 | F21P1 WWT package (Installation and 2 batch tanks) | 3164 | C |  | WWT-lab-duct pipe connector | 45283 | 45303 | [6 empty] | Chern Shuo System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3279.22 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 3279.22 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409045A | 3278.1 | TSMC Fab 21 P1B Tool Hook Up | 4830 | C |  | 4) 26' clean room ready, 2-man scissor lifts | 45546 | 45551 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3278.1 | 0 | 3278.1 | 0 | [73 empty] | -
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407121A | 3277.69 | WWT B side Project | 4535 | C |  | CDA System Hardware_WWT | 45493 | 45497 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 564.93 | 0.17236 | 2712.76 | 0 | 2712.76 | 0 | [70 empty] | 564.93 | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403093A | 3275.69 | Tool Interconnection Project (Main Tool & Other Vendors) | 909 | P |  | KEBCT2-TEL INTERCONNECTS-labor 3/11/2024 | 45372 | 45372 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 3275.69 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3275.69 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C009 | USC2401115A | 3273.2 | F21P1 Module Tool Interconnection ETC1-3 | 731 | P |  | ULINE H-2084 48"X24"X69" SECURITY CART | 45322 | 45323 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2740 | 0.8371 | 533.2 | 0 | 533.2 | 0 | 2740 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406008A | 3272.32 | Tool Interconnection Project (Main Tool & Other Vendors) | 1128 | P |  | KRWRS4 - rework (change order)-DNS SCREEN INTERCONNECTS-5/1 and 5/3/2024. | 45450 | 45453 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 3272.32 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 3272.32 | [6 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2402014A | 3266 | WWT Change Order (Piping) | 3457 | C |  | WWT Stripper Fan Connection | 45323 | 45323 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 3266 | 3266 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 489.9 |  |  |  | 489.9 |  |  |  | 489.9 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2405081A | 3264.45 | F21P1-0404_H_labor for 50 tools_MICU | 4101 | C |  | HK Electrical PM material request | 45426 | 45427 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 2752.4 | 0.84314 | 512.05 | 0 | 512.05 | 0 | 2752.4 | [55 empty] | 0 | [16 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403237A | 3254.42 | F21P1-0404_H_labor for 50 tools_MICU | 3930 | C |  | Extension Cord, Faceshield Bracket, Flashlight, Screwdriver, TOOL HOOKUP | 45374 | 45376 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3254.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3254.42 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2307100A | 3249.7 | F21P1 Module Tool Interconnection CVD | 2266 | C |  | Kcann1 Kcann2 change order 4" flex conduit | 45128 | 45138 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3249.7 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 3249.7 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C045 | USCSB2402130A | 3246.65 | WWT Change Order (Piping) | 3567 | C |  | WWT 7 Chemical - 1 | 45336 | 45379 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3111.84 | 0.95848 | 134.81 | 0 | 134.81 | 124.4736 | [52 empty] | 0 | 0 | 0 |  | 528.67 |  |  |  | 2583.17 | 486.9975 |  |  |  | 486.9975 |  |  |  | 486.9975 |  | 0 |  | - | 0 | 0 | 0 | 124.4736
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403247A | 3238.5 | F21P1-0404_H_labor for 50 tools_MICU | 3940 | C |  | plastic wrap and lock and zip lock, tool hookup team | 45377 | 45387 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3238.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 3238.5 | [6 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2312095A | 3238 | F21P1 AMAT Interconnection | 3086 | C |  | Labor to Install and Route of (7) signal cables on KIHIT2 | 45274 | 45276 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3076.1 | 0.95 | 161.9 | 0 | 161.9 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1083 |  | 0 | 0 | 1993.1 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2312106A | 3238 | F21P1 AMAT Interconnection | 3096 | C |  | Time and Materials pricing for the KIHIT5 Signal Cable Install | 45275 | 45281 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3076.1 | 0.95 | 161.9 | 0 | 161.9 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1624.5 |  | 0 | 0 | 1451.6 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  |  |  | UPW | Electrical | M+L | USC21C003 | USCSB2409048A | 3237.92 | F21P1 UPW | 4832 | C |  | Foxboro Instrument Swap A Side T&M | 45547 | 45548 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3237.92 | 0 | 3237.92 | 0 | [73 empty] | -
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208003A | 3236.97 | F21P1 UPW | 204 | P0 |  | Lenovo Laptop | 44777 | 44784 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3236.97 | 1 | 0 | 0 | 0 | 0 | 3236.97 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C006 | USCSB2401225A | 3227 | F21P1 Slurry package | 3407 | C |  | CDS WLS SS anchor brackets | 45317 | 45320 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3227 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 3227 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2311097A | 3225 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2948 | C |  | Progressive Commercial Interiors LLC- PCI Draper Roller Shade Installation | 45251 | 45252 | [6 empty] | Progressive Commercial Interiors, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3225 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 3225 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402172A | 3200.49 | F21P1 Chemical & WCCS package | 3602 | C |  | CDS HPM Punch materials etc | 45339 | 45344 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 3199.13 | 0.99958 | 1.36 | 0 | 1.36 | 0 | [52 empty] | 0 | 0 | 3199.13 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2307002A | 3200 | Tool Interconnection Project (Main Tool & Module) | 338 | P |  | KPE601-S RL MECHANICAL HVAC LABOR PAY | 45115 | 45131 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3200 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 3200 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306046A | 3200 | Tool Interconnection Project (Main Tool & Module) | 330 | P |  | KPE602-S RL MECHANICAL LABOR PAY | 45098 | 45114 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3200 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 3200 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2312032A | 3190.2 | F21P1 WWT package (Installation and 2 batch tanks) | 3025 | C |  | Tmah extra bolts requirement (MU) | 45266 | 45268 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3190.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 2830.67 | 0 | 0 |  | 359.53 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Barricade | Material |  |  | Others |  |  | USC23C002 | USCSB2404143A | 3180 | F21P1-0404_H_Hallway plate install_MICU | 4127 | C |  | ASML special barricade accessories | 45400 | 45407 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3180 | 0 | 3180 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405001A | 3173.32 | WWT B side Project | 3977 | C |  | WWT Diaphragm_20240430 (B Side) | 45413 | 45413 | [6 empty] | Hwa Chi Technology Co., Ltd | PR Approved | PO Approved | [14 empty] | 3173.32 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 3173.32 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208027A | 3170.1 | F21P1 UPW | 226 | P0 |  | Iphones, Ipads | 44800 | 44820 | [6 empty] | T-Mobile USA Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3170.1 | 1 | 0 | 0 | 0 | 0 | 3170.1 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Material | Main Contract Scope | WWT | WWT | Civil | Labor | USC21C014 | USCSB2308171A | 3165 | F21P1 WH2SO4 | 2465 | C |  | Modify Trench In WRC L20 | 45167 | 45170 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3165 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 3165 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401051A | 3164.22 | F21P1-0404_H_labor for 50 tools_MICU | 3241 | C |  | Tool for trade HL | 45300 | 45306 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3164.22 | 1 | 0 | 0 | 0 | 0 | 3164.22 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | interconnection | Equipment |  |  | Others |  |  | USC23C036 | USCSB2312022A | 3143.19 | F21P1 AMAT Interconnection | 3016 | C |  | SHARK CAGES & LOCKS | 45265 | 45267 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3143.19 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 79.12 | 0 | 0 |  |  | 0 | 0 | 0 |  | 3064.07 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112009A | 3137.42 | F21P1 UPW | 77 | P0 |  | Dell Laptop/Nest Wifi Router and AP | 44533 | 44543 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 3137.42 | 1 | 0 | 0 | 0 | 0 | 3137.42 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403071A | 3124 | Tool Interconnection Project (Main Tool & Other Vendors) | 893 | P |  | Armando Pisqueria 3/18-3/22/2024 | 45367 | 45387 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1241 | 0.39725 | 1883 | 0 | 1883 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1241 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401003A | 3122.76 | F21P1-0404_H_labor for 50 tools_MICU | 3195 | C |  | flowmeter regulator for HK PPL trade | 45294 | 45296 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3122.76 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 3122.76 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2309175A | 3116.25 | F21_AZQR_Hookup_ Interconnection | 2644 | C |  | QR: CHAD/FAD LABS: INTERCONNECT MATERIALS FOR LAN CABLE TRAY | 45197 | 45202 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3116.25 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 3116.25 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2405004A | 3106 | F21P1 Module Tool Interconnection CVD | 3980 | C |  | KCOLA3 Olympia Project Material | 45413 | 45416 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 3106 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 3106 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Rosendin |  |  | UPW | Electrical | M+L | USC21C003 | USCSB2408012A | 3102.4 | F21P1 UPW | 4609 | C |  | PCO 89, Foxboro RIAs, Revision 0 | 45507 | 45512 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | [14 empty] | 3102.4 | 1 | 0 | 3102.4 | -3102.4 | [74 empty] | 3102.4
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2406143A | 3098.6 | WWT B side Project | 4381 | C |  | WWT Contain-it double pipe | 45471 | 45471 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2432.4 | 0.785 | 666.2 | 951.91 | -285.71 | 0 | [68 empty] | 1908.7 |  |  | 0 | 523.7 | - | 0 | 0 | 0 | 0
Base-Build | TMAH | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2402011A | 3097.89 | F21 TMAH System | 3454 | C |  | HFC/Tmah sealant tool | 45323 | 45323 | [6 empty] | Southern Industrial Supply, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3097.89 | 1 | 0 | 0 | 0 | 0 | 3097.89 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C053 | USCSB2401058A | 3094.48 | AMAT Interconnection (TSMC) | 3247 | C |  | KDIGA3 DIF2 (Install a 4/0W Tray Cable from the Mainframe transformers to the MF AC Rack.) | 45301 | 45303 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 3094.48 | 0 | 3094.48 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402055A | 3093.7 | Tool Interconnection Project (Main Tool & Other Vendors) | 773 | P |  | BRADY***B30C-1125-595-YL | 45330 | 45331 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 3093.7 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 3093.7 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2402037A | 3080.34 | F21P1 AMAT Interconnection | 3480 | C |  | KCASA4 Dividers and AC Cover Modifications | 45325 | 45329 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 3080.34 | 0 | 3080.34 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306030A | 3077.6 | Tool Interconnection Project (Main Tool & Module) | 315 | P |  | KPE601-T LIT3 VERO VERIA CORP | 45086 | 45117 | [6 empty] | VERO VERIA CORPORATION | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3077.6 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 3077.6 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402249A | 3073.39 | F21P1-0404_H_labor for 50 tools_MICU | 3675 | C |  | Shared for all system, tool hookup team | 45347 | 45349 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2244.4 | 0.73027 | 828.99 | 0 | 828.99 | 0 | 2244.4 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2404093A | 3062 | F21P1 AMAT Interconnection | 4080 | C |  | CVD1 Tool Interconnection Dividers for KCUVA1, KCUVA2, KCBDA6 | 45393 | 45392 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3062 | 1 | 0 | 3606.03 | -3606.03 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 3062 | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2303006A | 3060 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1748 | C |  | 2 Portable Bathrooms | 44986 | 44991 | [6 empty] | National Construction Rentals, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 3060 | 0 | 3060 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401045A | 3054.2 | F21P1-0404_H_labor for 50 tools_MICU | 3235 | C |  | D-ring anchorage for PPL trade | 45300 | 45300 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3054.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 3054.2 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405038A | 3054.12 | Chemical & WCCS B Side Project | 4047 | C |  | CHEM_WCCS WLS CDA/ GN2 _HF1000-10PC2FSM CV=29.0*2ea | 45419 | 45419 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 3054.12 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 3054.12 |  |  | 3054.12 | [7 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2404078A | 3042.12 | F21P1 AMAT Interconnection | 4068 | C |  | Cable management | 45391 | 45391 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3042.12 | 1 | 0 | 0 | 0 | 0 | 3042.12 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C009 | USCSB2405105A | 3040 | F21P1 WWT package (Installation and 2 batch tanks) | 4122 | C |  | WWT LC/MS/MS Acrylic Dust Cover | 45429 | 45430 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | [14 empty] | 3040 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 3040 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2404082A | 3035.6 | F21P1-0404_H_labor for 50 tools_MICU | 4071 | C |  | Misc tools for HK Exhaust trade HL. For 300 tools | 45391 | 45408 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 2773.1 | 0.91353 | 262.5 | 0 | 262.5 | 0 | 2773.1 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2402107A | 3031.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 819 | P |  | LIBRATON 2PCs Pipe Cutter Replacement Blade for Pipe Cutter for Cutting Pipes of Aluminum, Copper, PVC, Thin Stainless Steel Tube | 45349 | 45350 | [6 empty] | Amazon | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2752.05 | 0.90782 | 279.45 | 0 | 279.45 | 0 | 2752.05 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403046A | 3024 | Tool Interconnection Project (Main Tool & Other Vendors) | 870 | P |  | Manpower Pay for CGS for Tool ID: KETRTA Time cards on 3.8, 3.11, and 3.13.2924 | 45363 | 45412 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3024 | 0 | 3024 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307082A | 3024 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2248 | C |  | Pillar hand tool | 45126 | 45127 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3024 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 3024 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2401111A | 3014.4 | F21P1 Module Tool Interconnection DIF1-2 | 3298 | C |  | 316L VAR VCR FITTING, SHORT TUBE BUTT WELD GLAND,1/2 VCR X 3/8 X 0.035 TBW, 0.75 (19.1 MM) EXT | 45308 | 45309 | -9.29 | 3023.69 |  |  |  |  | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3014.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 3014.4 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | Liquid Penetrant | Labor | The budget execution does not pertain to this project | 光阻櫃 | Others | Mechanical | Labor | USC22C035 | USCSB2402056A | 3000 | CAP_A_90772_F21 Phone call base build and Liquid penetrant testing system | 3498 | C |  | Mask Room Viewtile (T&M) | 45329 | 45328 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1568.96 | 0.52299 | 1431.04 | 794.2 | 636.84 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 774.76 | [14 empty] | 0 |  | 794.2 | 0 | 0 | 0
Base-Build | Base-Build | Labor | DCR Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2209007A | 3000 | F21P1 Chemical & WCCS package | 1460 | C |  | Lorry Building Module Rack - change order | 44813 | 44816 | [6 empty] | The Blackfin Group | PR Approved | PO Approved | USCSB2205030A change order | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 3000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 3000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2307034A | 3000 | F21P1 Chemical & WCCS package | 2204 | C |  | MIC assistance FusionHPX help Harder job | 2023/7/11 2023/7/13 | 45121 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | PR-R1:Add item 2 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3000 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 3000 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | DCR Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2308069A | 3000 | F21P1 Chemical & WCCS package | 2367 | C |  | Lorry PFD Review and S&S Rupture Disk Calculation | 45150 | 45162 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 3000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409007A | 3000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1214 | P |  | PRECISION CUTS KPE607-S BTS | 45540 | 45541 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3000 | 3000 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403027A | 3000 | Tool Interconnection Project (Main Tool & Other Vendors) | 853 | P |  | Precision Cuts KPE-604-S BTS | 45358 | 45358 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 3000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403012A | 3000 | Tool Interconnection Project (Main Tool & Other Vendors) | 839 | P |  | KPE606-S BTS Precision Tube Cutting Labor | 45356 | 45359 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 3000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409047A | 3000 | Tool Interconnection Project (Main Tool & Other Vendors) | 1250 | P |  | KPOCS4 & KPOCS5 SS Flat Flange Cuts | 45556 | 45559 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3000 | 0 | 3000 | 0 | [73 empty] | -
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC22C009 | USCSB2405019A | 2996.7 | F21P1 230kV MTR Oil and Drain Pipe work | 3991 | C |  | F21 P1 parking gates installation-(6/11) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2996.7 | 0 | 2996.7 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2304003A | 2993 | F21P1 Chemical & WCCS package | 1844 | C |  | CDS system Added BOX Items | 45017 | 45020 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 2257.5 | 0.75426 | 735.5 | 0 | 735.5 | 0 | [32 empty] | 2257.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 735.5 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207019A | 2978.04 | F21P1 UPW | 199 | P0 |  | Lenovo Laptop | 44771 | 44784 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2978.04 | 1 | 0 | 0 | 0 | 0 | 2978.04 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207020A | 2978.04 | F21P1 UPW | 200 | P0 |  | Lenovo Laptop | 44771 | 44784 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2978.04 | 1 | 0 | 0 | 0 | 0 | 2978.04 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209018A | 2973.28 | F21P1 Chemical & WCCS package | 243 | P0 |  | Lenovo Laptop | 44825 | 44826 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2973.28 | 1 | 0 | 0 | 0 | 0 | 2973.28 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209015A | 2973.28 | F21P1 Chemical & WCCS package | 240 | P0 |  | Lenovo Laptop | 44825 | 44826 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2973.28 | 1 | 0 | 0 | 0 | 0 | 2973.28 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2211001A | 2971.5 | F21P1 WWT package (Installation and 2 batch tanks) | 1537 | C |  | WWT adapter | 44866 | 44867 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 2971.5 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 2971.5 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Slurry | Equipment | Main Contract Scope | SDS | Chemical | Mechanical | Labor | USC21C006 | USCSB2402119A | 2965 | F21P1 Slurry package | 3557 | C |  | Urgent Lorry Tank Repair | 45335 | 45336 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 2965 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 2965 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404010A | 2963.08 | Tool Interconnection Project (Main Tool & Other Vendors) | 965 | P |  | WIRE SO10/4 10/4 SOW-A SO TYPE; 250 FT; 250 LENGTH IN FT; COPPER CONDUCTOR MATERIAL; 600 V VOLTAGE RATING; -40 TO 60 DEG C TEMPERATURE RATING; 4 CONDUCTOR(S); EPDM RUBBER INSULATION MATERIAL; 10 AWG CONDUCTOR SIZE; COIL PACKAGE TYPE; 104 STRANDS STRANDING; BLACK JACKET COLOR | 45385 | 45385 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2963.07 | 1 | 0.01 | 0 | 0.01 | 0 | [52 empty] | 0 | 0 | 0 |  | 2963.07 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401029A | 2958 | F21P1-0404_H_labor for 50 tools_MICU | 3220 | C |  | HK Parking for exhaust dust for trade HR. TSMC Polyethylene Foam Gasket | 45296 | 45299 | [6 empty] | Pacific Air Reps Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2958 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 2958 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2312053A | 2951.71 | F21P1-0404_H_labor for 50 tools_MICU | 3046 | C |  | office supplies for tool hookup department | 2023/12/8 2024/7/25 | 2023/12/11 2024/7/26 | 245.2 | 2706.51 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1 - Inclusion of sales tax |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2720.4 | 0.92164 | 231.31 | 0 | 231.31 | 0 | 2720.4 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409092A | 2950 | TSMC Fab 21 P1B Tool Hook Up | 4902 | C |  | BLANK PLASTIC TAGS for tube share for gas and plastic system, P1-B tool hookup team | 45560 | 45562 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2950 | 0 | 2950 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403060A | 2949.69 | F21P1-0404_H_labor for 50 tools_MICU | 3765 | C |  | Wire mesh bin for HK PPL trade | 45357 | 45370 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2949.69 | 1 | 0 | 0 | 0 | 0 | 2949.69 | [51 empty] | 0 | 0 | 0 | [16 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2403246A | 2946.6 | F21P1 WWT package (Installation and 2 batch tanks) | 3939 | C |  | WWT_Premium White T-Shirt Rags | 45377 | 45379 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2946.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2946.6 |  |  | 441.99 |  |  |  | 441.99 |  |  |  | 441.99 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403148A | 2944.4 | F21P1-0404_H_labor for 50 tools_MICU | 3848 | C |  | Cleanroom paper shared by all hk systems | 45365 | 45366 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 2944.4 | 0 | 2944.4 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2402065A | 2944.4 | F21P1-0404_H_labor for 50 tools_MICU | 3507 | C |  | Cleanroom paper shared by all hk systems | 45330 | 45334 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2944.4 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 2944.4 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C007 | USCSB2310084A | 2943.5 | F21P1 VOC package （Installation ) | 2745 | C |  | VOC Fiber cable for re-pull | 45212 | 45217 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2943.5 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 2943.5 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408060A | 2931.65 | TSMC Fab 21 P1B Tool Hook Up | 4677 | C |  | Label printer for printing location ID and Tool ID | 45517 | 45518 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 2931.65 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 2931.65 |  |  | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2311003A | 2931.52 | EBO21- Tool interconnection | 2858 | C |  | EBO: ZFP3-1: INTERCONNECTION MATERIAL SUS304 DUCT & ELBOW | 45231 | 45233 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2931.52 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 2931.52 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C059 | USCSB2408089A | 2923.2 | F21P1 Foundation T&M | 4704 | C |  | M10*80mm Socket Countersunk for Foundation | 45525 | 45527 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2923.2 | 2328.48 | 594.72 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403130A | 2917.2 | F21P1-0404_H_labor for 50 tools_MICU | 3832 | C |  | Band Saw Blade for HK Exhaust trade | 45364 | 45364 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2572.44 | 0.88182 | 344.76 | 0 | 344.76 | 0 | 2572.44 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306038A | 2901.96 | Tool Interconnection Project (Main Tool & Module) | 322 | P |  | KPOCT5 -S GRAINER | 45090 | 45126 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2901.96 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2901.96 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2307125A | 2900 | F21P1-0404_H_Hallway plate install_MICU | 2288 | C |  | P0201 foundation modification | 45134 | 45135 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2900 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 2900 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308019A | 2899 | F21P1 Chemical & WCCS package | 2321 | C | -01 | TGCM Duty Room items – fridge | 45142 | 2023/9/27 2024/3/5 | -457.91 | 3356.91 | V |  |  |  | Zoro Tools, Inc. | PR Approved | PO Approved | R1: Change Ship-to Address and lower the amount to align with actual order |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2899 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2899 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C053 | USCSB2409077A | 2893.65 | AMAT Interconnection (TSMC) | 4889 | C |  | CEMQ-PCA: NO TOOL ID: 4 MONTHS OF SCISSOR LIFTS | 45554 | 45559 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2893.65 | 0 | 2893.65 | 0 | [73 empty] | -
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC22C037 | USCSB2408017A | 2891 | F21P1 Screen Main tool interconnection | 4613 | C |  | WET-SEE TOOL LIST-P1B BULK MATERIALS | 45507 | 45516 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2891 | 1 | 0 | 1011.85 | -1011.85 | [74 empty] | 2891
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C032 | USCSB2305116A | 2884.28 | F21_AZQR_Hookup_ Interconnection | 2032 | C |  | MOUSER ELEC: QR LABS - QE43620 SENSING BAND & SENSOR | 45077 | 45113 | [6 empty] | Mouser Electronics | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2884.28 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2884.28 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2401178A | 2877 | F21P1 Module Tool Interconnection DIF1-2 | 3363 | C | -01 | DIFF，Interconnection material Flexible Duct | 45314 | 2024/1/24 2024/1/31 | [5 empty] | V | Marketech International Corp. | PR Approved | PO Approved | PR R1: Change Trade Term |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2877 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 2877 |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2312057A | 2874.08 | Tool Interconnection Project (Main Tool & Other Vendors) | 603 | P |  | Perform interconnection on KEPCH1 | 45274 | 45318 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2551.57 | 0.88779 | 322.51 | 0 | 322.51 | 0 | [47 empty] | 0 | 0 | 1667.08 |  |  | 0 | 0 | 0 |  | 884.49 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2406043A | 2856 | F21P1 WWT package (Installation and 2 batch tanks) | 4269 | C |  | CGS Global Manpower Labor for painting of housekeeping pads | 45449 | 45465 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 2856 | 1 | 0 | 2856 | -2856 | 2856 | [71 empty] | 1428 |  | 2856 | 1428 | 0 | 0 | 0
Base-Build | UPW |  | Main Contract Scope | UPW | UPW | Civil | Project Outsourcing (專案管理外包人力) | USC21C003 | USCSB2406038A | 2856 | F21P1 UPW | 4264 | C |  | CGS Global Manpower Labor for painting of housekeeping pads | 45449 | 45465 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 1303.06 | 0.45625 | 1552.94 | 1303.06 | 249.88 | 0 | [73 empty] | 1303.06 |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C004 | USCSB2312080A | 2853.14 | F21P1 WWT package （USA EQ-FRP tank) | 3072 | C | -01 | WWT - Lab glassware | 45273 | 2023/12/14 2023/12/19 | [6 empty] | Laboratory Sales and Service | PR Approved | PO Approved | PO R1:Changing payment options from NET 30 to Prepayments |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2853.14 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 2853.14 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203010A | 2850.58 | F21P1 UPW | 134 | P0 |  | Laptop | 44629 | 44643 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2850.58 | 1 | 0 | 0 | 0 | 0 | 2850.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203011A | 2850.58 | F21P1 UPW | 135 | P0 |  | Laptop | 44629 | 44643 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2850.58 | 1 | 0 | 0 | 0 | 0 | 2850.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202018A | 2850.58 | F21P1 UPW | 125 | P0 |  | Lenovo Laptop | 44614 | 44635 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2850.58 | 1 | 0 | 0 | 0 | 0 | 2850.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203005A | 2850.58 | F21P1 UPW | 130 | P0 |  | Laptop | 44629 | 44635 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2850.58 | 1 | 0 | 0 | 0 | 0 | 2850.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409010A | 2839.47 | Tool Interconnection Project (Main Tool & Other Vendors) | 1216 | P |  | 2304PIPE: 2 304 WELD PIPE S10 A312 | 45541 | 45541 | [6 empty] | Industrial Pipe & Valve Inc. | PR Approved | PO Approved | [14 empty] | 1614.47 | 0.56858 | 1225 | 1614.47 | -389.47 | 0 | [73 empty] | 1614.47
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2403185A | 2835.63 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3882 | C |  | RS Payroll Services manpower labor cost from previous work assigned- open invoices | 45370 | 45371 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 2835.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2835.63 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | MIC - Material | Material |  |  | Others |  |  | USC22C016 | USCSB2212036A | 2833.95 | Asahi Valve and Positioner from Harrington |  | C |  | Asahi valve from Harrington | 44915 | 44917 | [23 empty] | 2833.95 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 986.9 |  |  | 0 |  |  | 1847.05 | [8 empty] | 0 |  | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311041A | 2832 | Tool Interconnection Project (Main Tool & Module) | 515 | P |  | Pay for San Tan for Tool KDSTL1 | 45245 | 45247 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2832 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 2832 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311042A | 2832 | Tool Interconnection Project (Main Tool & Module) | 516 | P |  | Pay for San Tan for Tool KRWRS1 | 45246 | 45247 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2832 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 2832 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | 5G | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC22C010 | USCSB2309155A | 2832 | F21 P1 LSC CMS and DPM 5G System | 2626 | C |  | 5G CMS material for rubber adhesive cable tie mount | 45195 | 45208 | [6 empty] | GLA Arizona, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 2832 | 0 | 2832 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311043A | 2832 | Tool Interconnection Project (Main Tool & Module) | 517 | P |  | Pay for San Tan for Tool KRWRS4 | 45246 | 45247 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2832 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 2832 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2312021A | 2808 | F21P1 Chemical & WCCS package | 3015 | C | -01 | CDS MY-TE 100AB Standard Electric Winch-Hoist for Lorry work | 45265 | 2023/12/7 2023/12/12 | [6 empty] | Certex USA LLC | PR Approved | PO Approved | change payment term from 45 day to 30 day |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2808 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 2808 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | The budget execution does not pertain to this project | CCTV | Low Voltage | Electrical | Labor | USC22C019 | USCSB2405015A | 2803.5 | AMC monitor 595T0 | 3987 | C |  | F21 P1 parking gates installation-(2/11) | 45415 | 45427 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2803.5 | 0 | 2803.5 | 0 | [54 empty] | 0 |  | 0 | [16 empty] | - |  | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2309120A | 2803.2 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2592 | C |  | Techsouthinc Hand Tool 3rd batch | 45189 | 45198 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2803.2 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 2803.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308025A | 2800 | Tool Interconnection Project (Main Tool & Module) | 375 | P |  | KPE601-S RL MECHANICAL LABOR PAY | 45167 | 45169 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2800 | 0 | 2800 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Site Expense | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402043A | 2800 | F21P1 Chemical & WCCS package | 3485 | C |  | CDS Welder rental for Chemical welding. | 45328 | 45328 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 2800 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 2800 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406026A | 2794.2 | Chemical & WCCS B Side Project | 4252 | C |  | F21P1 B Side material RH- PVDF 1/2"x3/4" ADPT | 45448 | 45448 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 2794.2 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2794.2 | [8 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405119A | 2793.9 | WWT B side Project | 4147 | C |  | WWT 6X4 Reducing Tee_20240520 (B Side) | 45434 | 45435 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2793.9 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 2793.9 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2307064A | 2788.4 | F21P1 Chemical & WCCS package | 2231 | C |  | Cush Clamps for Chemical welding. | 45121 | 45125 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2788.4 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 2788.4 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2307011A | 2788.16 | F21P1 UPW | 2184 | C |  | UPW-TSMC OP material-harrington | 45113 | 45127 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2361.16 | 0.84685 | 427 | 0 | 427 | 0 | [38 empty] | 2361.16 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2305120A | 2785 | F21P1 UPW | 2035 | C |  | UPW Ebro | 45077 | 45097 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2785 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 2785 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2404159A | 2781 | F21P1 AMAT Interconnection | 4143 | C |  | KCBDA2 San Tan Fire Borrow | 45402 | 45405 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 2781 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 2781 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204006A | 2770.88 | F21P1 UPW | 153 | P0 |  | Lenovo Laptop | 44673 | 44764 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2770.88 | 1 | 0 | 0 | 0 | 0 | 2770.88 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405144A | 2767.52 | Chemical & WCCS B Side Project | 4168 | C |  | CHEM_WCCS_Ladder + EXT cord for F21 project use | 45436 | 45440 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 2767.52 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 2767.52 | [10 empty] | - |  |  | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2401030A | 2761.66 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3221 | C |  | Grainger EUV Crane Maintenance Service | 45296 | 45299 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2751.6 | 0.99636 | 10.06 | 0 | 10.06 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 2751.6 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Labor | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C013 | USCSB2305026A | 2756 | F21P1 AMC THC Monitoring System | 1949 | C |  | Fiber Splicing | 45052 | 45061 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2756 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 2756 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2405143A | 2753.64 | WWT B side Project | 4167 | C |  | WWT - Supply (4) 18inch FRP Flanges to Complete T-740BA-BB-BC Interconnection | 45436 | 45448 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2753.64 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 2753.64 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403007A | 2750.08 | F21P1 Chemical & WCCS package | 3715 | C |  | CDS lcp ms CDA parts | 45352 | 45357 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2750.08 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 2750.08 |  |  |  |  | 2750.08 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409027A | 2749.95 | TSMC Fab 21 P1B Tool Hook Up | 4795 | C |  | EEW PPE Torque Wrench for 200 tools | 45540 | 45544 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 2499.95 | 0.90909 | 250 | 0 | 250 | 0 | 2499.95 | [72 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409016A | 2749.27 | Tool Interconnection Project (Main Tool & Other Vendors) | 1220 | P |  | Position sensor, 0-6000 mm, Profinet, M4, Linearity 0,02% | 45542 | 45545 | [6 empty] | Mennens Cleanroom Cranes B.V. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2749.27 | 0 | 2749.27 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403028A | 2746.88 | F21P1 WWT package (Installation and 2 batch tanks) | 3737 | C |  | WWT Hardware_20240229 (A Side) | 45356 | 45355 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2746.88 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 469.1 | 1918.23 |  | 0 |  |  |  | 359.55 | 137.344 |  |  |  | 274.688 |  |  |  | 412.032 |  | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS | Site Expense |  |  | AMHS |  |  | USC23C052 | USCSB2401017A | 2740 | F21 P1A AMHS PSP & DP Power source breakers | 3208 | C |  | CPE Shoe Covers | 45295 | 45309 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2740 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2740 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208015A | 2736.3 | F21P1 UPW | 214 | P0 |  | 55 inch black zenstyle computer desk | 44796 | 44798 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2736.3 | 1 | 0 | 0 | 0 | 0 | 2736.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2403083A | 2732.58 | Tool Interconnection Project (Main Tool & Other Vendors) | 897 | P |  | Manpower for Tool ID KETRT6 for RS Payroll | 45370 | 45457 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2732.58 | 0 | 2732.58 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308001A | 2730 | Tool Interconnection Project (Main Tool & Module) | 351 | P |  | kpap01-s rl mechanical labor pay | 45139 | 45148 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2730 | 0 | 2730 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310026A | 2728.53 | F21P1 Chemical & WCCS package | 2689 | C |  | Coil .093 rd T 316L SS to 1 13/16 od max x 1 17/32 id min 6 pitch for YaHo work at Lorry FNDP. | 45203 | 45212 | [6 empty] | Chukar PTS LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2728.53 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 2728.53 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2402069A | 2727.44 | F21P1-0423_H_T&M Hardware_MICU | 3511 | C |  | Quick-Clamp High-Vacuum Fitting for Stainless Steel Tubing, Straight Reducer for 1-1/2" x 1" Tube | 45330 | 45331 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2714.8 | 0.99537 | 12.64 | 0 | 12.64 | 0 | [49 empty] | 0 |  |  | 0 | 2714.8 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206005A | 2726.76 | F21P1 UPW | 173 | P0 |  | Amazon Zenstyle Black 55 inch desk trailers for subs | 44722 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2726.76 | 1 | 0 | 0 | 0 | 0 | 2726.76 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Project Outsourcing (專案管理外包人力) | USC21C009 | USCSB2404138A | 2726 | F21P1 WWT package (Installation and 2 batch tanks) | 4004 | C |  | CGS Global Support Onsite Manpower | 45400 | 45495 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2726 | 0 | 2726 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312141A | 2724.27 | F21P1-0404_H_labor for 50 tools_MICU | 3130 | C |  | Brother label tape, gas and UPW share materials, Tool hookup team | 45279 | 45280 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2470.14 | 0.90672 | 254.13 | 0 | 254.13 | 0 | 2470.14 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312133A | 2712.5 | F21P1-0404_H_labor for 50 tools_MICU | 3122 | C |  | weatherproof bell boxes, for 100 tools demand, TOOL HOOKUP TEAM | 45279 | 45280 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2712.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 1117.44 | 1595.06 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2401001A | 2708.04 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3193 | C |  | United Rentals Manpower Associates Scissor Lift & Fall Protection Certification & Training | 45293 | 45294 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2708.04 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 2708.04 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2410048A | 2700 | TSMC Fab 21 P1B Tool Hook Up | 4990 | C |  | 3-plex cleaning services | 45569 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 2700 | 0 | 2700 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402042A | 2688.58 | F21P1 Chemical & WCCS package | 3484 | C |  | CDS Conduit Tee | 45328 | 45328 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2688.58 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 2688.58 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312179A | 2687.5 | F21P1-0404_H_labor for 50 tools_MICU | 3166 | C |  | Stainless Steel VCR Face Seal Fitting, Gas system, Tool hookup | 45287 | 45286 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2687.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 2687.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408040A | 2664.83 | TSMC Fab 21 P1B Tool Hook Up | 4631 | C |  | Struct clamp for HK PPL trade for 100 tools | 45513 | 45513 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved | [14 empty] | 2664.83 | 1 | 0 | 0 | 0 | [73 empty] | 2664.83 | -
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2404089A | 2664 | F21P1 AMAT Interconnection | 4077 | C |  | MICU RS Payroll Manpower | 45392 | 45397 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 2664 | 0 | 2664 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401248A | 2663.15 | F21P1-0404_H_labor for 50 tools_MICU | 3429 | C |  | 625 psi high pressure regulators and N2 cylinder | 45321 | 45323 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 2663.15 | 0 | 2663.15 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402094A | 2663.15 | F21P1-0404_H_labor for 50 tools_MICU | 3534 | C |  | psi high pressure regulators ang N2 cylinder, Tool hook up for gas 300 tools | 45332 | 45332 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1190.33 | 0.44696 | 1472.82 | 0 | 1472.82 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 1190.33 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2302057A | 2652 | F21P1 UPW | 1738 | C |  | Adapters for Circuit Breakers in uis Panel | 44985 | 44992 | [6 empty] | LayerZero Power Systems, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2652 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 2652 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409047A | 2649.96 | TSMC Fab 21 P1B Tool Hook Up | 4844 | C |  | Cleanroom paper shared by all hk systems | 45547 | 45551 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2649.96 | 2649.96 | 0 | 0 | [73 empty] | -
Base-Build | UPW | MMI | The budget execution does not pertain to this project | WWT | WWT | Civil | Labor | USC21C003 | USCSB2308061A | 2647 | F21P1 UPW | 2359 | C |  | WRC L20 Lab Island and Fume Hood | 45148 | 45150 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2647 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 2647 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206008A | 2638.8 | F21P1 UPW | 175 | P0 |  | Zenstyle Computer Desk 55 inch sub trailers | 44722 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2638.8 | 1 | 0 | 0 | 0 | 0 | 2638.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C011 | USCSB2402221A | 2625 | F21 TMAH System | 3648 | C |  | TMAH Customized Clear PVC Cover | 45344 | 45344 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2625 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2625 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403036A | 2622 | Tool Interconnection Project (Main Tool & Other Vendors) | 862 | P |  | MANPOWER PAY FOR CGS | 45359 | 45362 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 0 | 0 | 2622 | 0 | 2622 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401080A | 2622 | Tool Interconnection Project (Main Tool & Other Vendors) | 700 | P |  | MECHANICAL LABOR | 45317 | 45318 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2622 | 0 | 2622 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2402082A | 2613.84 | F21P1 AMAT Interconnection | 3523 | C |  | Change Order KCSMA6 Dividers and AC Cover Modifications | 45330 | 45332 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2613.84 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 2613.84 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2309133A | 2611.25 | F21P1 UPW | 2604 | C |  | UPW-Nagano Pressure Gauge＆Flow Indicator | 45190 | 45194 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2611.25 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 212.5 | 0 | 0 | 2398.75 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2301046A | 2609.62 | F21P1 WWT package (Installation and 2 batch tanks) | 1663 | C |  | WWT WRC Mini Line D75 fitting/ PVC bushing material | 44950 | 2023/1/26 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2609.62 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 2609.62 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206013A | 2606.37 | F21P1 UPW | 180 | P0 |  | Dell Laptop | 44724 | 44764 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2606.37 | 1 | 0 | 0 | 0 | 0 | 2606.37 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206014A | 2606.37 | F21P1 UPW | 181 | P0 |  | Dell Laptop | 44724 | 44764 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2606.37 | 1 | 0 | 0 | 0 | 0 | 2606.37 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206003A | 2606.1 | F21P1 UPW | 171 | P0 |  | Zenstyle black 55 inch computer desk for sub trailers construction | 44722 | 44736 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2606.1 | 1 | 0 | 0 | 0 | 0 | 2606.1 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206004A | 2606.1 | F21P1 UPW | 172 | P0 |  | Zenstyle black 55 inch computer desk for sub trailers construction | 44722 | 44736 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2606.1 | 1 | 0 | 0 | 0 | 0 | 2606.1 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C006 | USC2408006A | 2605.34 | WWT B side Project | 1178 | P |  | Mobile Computers, Zebra TC22, WiFi 6, SE4710, 6 Display, 6GB64GB, 16MP RFC, 5MP FFC, 2Pin Back IO, Standard Battery, NFC, Bluetooth, USBC, GMS, NA | 45510 | 45512 | [6 empty] | Barcodes LLC | PR Approved | PO Approved | [14 empty] | 938 | 0.36003 | 1667.34 | 1083.95 | 583.39 | 0 | [73 empty] | 938
Base-Build | WWT |  |  |  | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407114A | 2602 | WWT B side Project | 4529 | C |  | sump pump rubber bushing and welding rod_WWT | 45492 | 45496 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2602 | 0 | 2602 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2307106A | 2600 | F21P1 AMAT Interconnection | 2271 | C |  | F76mmPedestal/2P Raised Floor F76mmPedestal/1P Raised Floor | 45129 | 45141 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2600 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 2600 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | CO Scope (adding/additional scope) | WWT | WWT | Electrical | Instrument | USC21C009 | USCSB2312171A | 2594 | F21P1 WWT package (Installation and 2 batch tanks) | 3159 | C |  | WWT-NH3-outdoor cabinet | 45282 | 45287 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2594 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 2594 |  |  | 389.1 |  |  |  | 389.1 |  |  |  | 389.1 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2405050A | 2589 | F21P1 Module Tool Interconnection CVD | 4057 | C |  | Ball valves KCOLA1 KCOLA2 KCOLA3 | 45420 | 45421 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 2589 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 2589 | [10 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Material | USC21C009 | USCSB2403288A | 2587.34 | F21P1 WWT package (Installation and 2 batch tanks) | 3980 | C |  | Amazon - Waste Water Team | 45381 | 45385 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 2587.34 | 0 | 2587.34 | 2587.34 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 388.101 |  |  |  | 388.101 |  |  |  | 388.101 |  | 1293.67 |  | - | 1293.67 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2309146A | 2583.6 | F21P1 Module Tool Interconnection CVD | 2617 | C |  | Change Order for KCBDA1 Under RMF Chamber Enclosures | 45191 | 45197 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 2583.6 | 0 | 2583.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406011A | 2580 | Tool Interconnection Project (Main Tool & Other Vendors) | 1132 | P |  | KEPST4 - Cable Pull, 5/14-5/16, Tel Interconnects | 45457 | 45461 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 2580 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2580 | [8 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303027A | 2580 | F21P1 Module Tool Interconnection DIF1-2 | 1769 | C |  | DIF pliot run machine gas line | 44992 | 44998 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2580 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 2580 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112033A | 2567.52 | F21P1 UPW | 96 | P0 |  | Lenovo Yoga 7I Laptop | 44554 | 44558 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang |  |  | Matt |  |  |  |  | 2567.52 | 1 | 0 | 0 | 0 | 0 | 2567.52 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2310189A | 2560 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2841 | C |  | Banner Industries Welding Equipment Pre Fab Construction | 45228 | 45230 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2560 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 2560 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402274A | 2545.92 | F21P1 WWT package (Installation and 2 batch tanks) | 3699 | C |  | WWT SUS Weld Pipes_20240227 (A Side) | 45351 | [7 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2545.92 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 2545.92 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407030A | 2540 | Tool Interconnection Project (Main Tool & Other Vendors) | 1163 | P |  | 102: P-TIC-PFA-TU-015: PFA 1/2" (12.7MM OD, 9.53MM ID) | 45496 | 45498 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 2540 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 2540 | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2401220A | 2533.05 | F21P1-0423_H_T&M Hardware_MICU | 3402 | C |  | Quick-Clamp High-Vacuum Fitting for Stainless Steel Tubing, Straight Reducer for 1-1/2" x 1" Tube | 45317 | 45321 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2508.8 | 0.99043 | 24.25 | 0 | 24.25 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 2508.8 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | CO Scope (adding/additional scope) | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C009 | USCSB2404095A | 2526 | F21P1 WWT package (Installation and 2 batch tanks) | 4082 | C |  | FAB A WWT and WWTD Observation (Change Order) | 45393 | 45397 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 2526 | 0 | 2526 | 2526 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 378.9 |  |  |  | 378.9 |  |  |  | 378.9 |  | 2526 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403248A | 2525 | F21P1-0404_H_labor for 50 tools_MICU | 3941 | C |  | Arc Flash sticker for HK Power system | 45377 | 45384 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2525 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2525 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401194A | 2521.67 | F21P1-0404_H_labor for 50 tools_MICU | 3379 | C |  | headlamp for Plastic system, Drill bit and lock shared for all system | 45315 | 45316 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2478.7 | 0.98296 | 42.97 | 0 | 42.97 | 0 | 2478.7 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2306104A | 2521.1 | F21P1 WWT package (Installation and 2 batch tanks) | 2137 | C |  | FAB bolts request #2 | 45099 | 45103 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2521.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 2521.1 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2310101A | 2520 | F21P1 UPW | 2763 | C |  | UPW-AnCor-UT2211B,3111B-ladder modify | 45216 | 45224 | [6 empty] | An-Cor Industrial Plastics, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2520 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 2520 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403111A | 2518.53 | Tool Interconnection Project (Main Tool & Other Vendors) | 927 | P |  | BPT 437SLTI: 3IN STR L/T CONN STEEL | 45377 | 45376 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2518.53 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2518.53 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC24C003 | USCSB2408121A | 2518.5 | F21P1 Lasertec Interconnection | 4732 | C |  | ME: KPMI03: CABLE PULL | 45531 | 45534 | [6 empty] | Netcom Cabling, Inc. | PR Approved | PO Approved | [14 empty] | 2518.5 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 2518.5 | -
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401018A | 2516 | F21P1-0404_H_labor for 50 tools_MICU | 3209 | C |  | replacement of USCSB2312206. Phone lockers for HK shared by all system | 45296 | 45297 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2516 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 2516 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2304021A | 2502.5 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1862 | C |  | SST316 EP 1" 90-degree elbows and SST316 1" Tees and 22 of each | 45024 | 45027 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2502.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2502.5 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403117A | 2500 | F21P1-0404_H_labor for 50 tools_MICU | 3819 | C |  | HK Electrical PM material request | 45363 | 45364 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2500 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 2500 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C003 | USCSB2307008A | 2500 | F21P1 UPW | 2181 | C |  | Remove Water and Chemical from Tanks(UPW Degan tank clean) | 45108 | 45140 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 2500 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406145A | 2500 | F21P1-0404_H_labor for 50 tools_MICU | 4383 | C |  | CED Wire cut charge for HK Power trade for 1 tool | 45471 | 45472 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2500 | 2500 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | M+L | USC23C045 | USCSB2309143A | 2500 | WWT Change Order (Piping) | 2614 | C |  | WWT T-260 (8) Epoxy Coating Anchors | 45191 | 45197 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1500 | 0.6 | 1000 | 0 | 1000 | 120 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1500 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 125 |  |  |  | 250 |  |  |  | 125 |  | 0 |  | - | 0 | 0 | 0 | 120
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C053 | USCSB2308062A | 2500 | AMAT Interconnection (TSMC) | 2360 | C |  | Labor for Rosendin | 45148 | 45151 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 2500 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409017A | 2494.82 | Tool Interconnection Project (Main Tool & Other Vendors) | 1221 | P |  | Ring for 1" Tube OD Quick-Clamp High-Vacuum Fitting | 45545 | 45551 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2494.82 | 2487.28 | 7.54 | 0 | [73 empty] | -
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401159A | 2493 | F21P1-0404_H_labor for 50 tools_MICU | 3344 | C |  | Electrolyte Gold, Replenishment solution | 45311 | 45315 | [6 empty] | Servomex Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2493 | 0 | 2493 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111032A | 2475.8 | F21P1 UPW | 43 | P0 |  | File Cabinet | 44516 | 44524 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 2475.8 | 1 | 0 | 0 | 0 | 0 | 2475.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403105A | 2468 | Tool Interconnection Project (Main Tool & Other Vendors) | 921 | P |  | SS-1613-1 FRONT FERRULE 1" | 45374 | 45376 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2468 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2468 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403006A | 2466 | Tool Interconnection Project (Main Tool & Other Vendors) | 833 | P |  | MANPOWER PAY FOR CCE | 45353 | 45363 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 2466 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2466 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203018A | 2462.88 | F21P1 UPW | 140 | P0 |  | Zen 55 inch desk for moldular | 44636 | 44643 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2462.88 | 1 | 0 | 0 | 0 | 0 | 2462.88 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405088A | 2456.68 | F21P1-0404_H_labor for 50 tools_MICU | 4108 | C |  | Duralable for tool hookup team | 45427 | 45448 | [6 empty] | Graphic Products, Inc. | PR Approved | PO Approved | [14 empty] | 2451.78 | 0.99801 | 4.9 | 0 | 4.9 | 0 | [56 empty] | 0 | [9 empty] | 2451.78 | [6 empty] | - |  |  | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC22C009 | USCSB2403066A | 2455 | F21P1 230kV MTR Oil and Drain Pipe work | 3771 | C |  | UPW-Harrington-U-bent for Brine RO tank | 45358 | 45358 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2255 | 0.91853 | 200 | 0 | 200 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 2255 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C006 | USCSB2308096A | 2451.75 | F21P1 Module Tool Interconnection EPI | 2393 | C |  | EPI: General use - U-Style Crimper & 1/0 U-Style Die | 45155 | 45160 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2451.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 2451.75 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2302049A | 2451 | F21P1 UPW | 1730 | C |  | Organo Freight and Forwarding Charges/Expenses | 44981 | 44984 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2451 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 2451 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311065A | 2450 | Tool Interconnection Project (Main Tool & Module) | 534 | P |  | CDA purifier material | 45252 | 45257 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2450 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 2450 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2403235A | 2450 | F21P1-0404_H_Hallway plate install_MICU | 3928 | C |  | Jeoufwu Foundation manufacture M0603 | 45374 | 45383 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 2450 | 0 | 2450 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403079A | 2434.27 | Tool Interconnection Project (Main Tool & Other Vendors) | 898 | P |  | 32625T57 Strut-Mount Vibration-Damping Routing Clamp with TPE Rubber Cushion, Zinc-Plated Steel, 1-1/8" ID | 45370 | 45370 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 2434.27 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1192.32 | 0 |  | 1241.95 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC24C005 | USCSB2405184A | 2432.19 | Chemical & WCCS B Side Project | 4212 | C |  | 3 house keeping pads 128"x48" PAD PREP, EPOXY AND YELLOW PERIMETOR PAINT | 45443 | 45448 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved | [14 empty] | 2432.19 | 1 | 0 | 2432.19 | -2432.19 | 0 | [73 empty] | 2432.19 |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Steel | Labor | USC21C009 | USCSB2403054A | 2430 | F21P1 WWT package (Installation and 2 batch tanks) | 3760 | C |  | WWT: Triazole Electrical Panel Anchoring | 45357 | 45356 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2430 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2430 |  | 0 |  |  |  |  | 364.5 |  |  |  | 364.5 |  |  |  | 364.5 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC24C005 | USCSB2404180A | 2428.27 | Chemical & WCCS B Side Project | 4161 | C |  | Amazon - Chemical Team | 45406 | 45406 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 2230.99 | 0.91876 | 197.28 | 0 | 197.28 | 0 | 2230.99 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2404068A | 2418.99 | F21P1-0404_H_labor for 50 tools_MICU | 4060 | C | -01 | zip lock bag, tool hookup team | 45388 | 2024/4/9 2024/4/11 | [5 empty] | V | Thomas Scientific Holdings LLC | PR Approved | PO Approved | R1: Revise ship-to address and instructions |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 2418.99 | 0 | 2418.99 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405130A | 2408.7 | WWT B side Project | 4158 | C |  | WWT RT&Bushing_20240521 (B Side) | 45434 | 45435 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2408.7 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2408.7 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401214A | 2407.2 | F21P1-0404_H_labor for 50 tools_MICU | 3397 | C |  | Galvanized Loose flat ring flange for HK exhaust | 45317 | 45317 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2407.2 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 2407.2 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2306008A | 2403.5 | F21P1 Module Tool Interconnection DIF1-2 | 2042 | C |  | SWAGELOK: DIF2-INTERCONNECT MATERIAL FOR 03 DETECTOR | 45080 | 45083 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2403.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 2403.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2409113A | 2402.58 | TSMC Fab 21 P1B Tool Hook Up | 4932 | C |  | label kit for BBP 37 and white circle label for QC, tool hookup team | 45562 | 45565 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2402.58 | 0 | 2402.58 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2409060A | 2401.72 | TSMC Fab 21 P1B Tool Hook Up | 4884 | C |  | Hand tool, Tower Manufacturing 30396501-08 Manual-Reset 20 AMP Inline GFCI Triple Tap Cord, Yellow/Black, tool hookup team | 45552 | 45566 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2401.72 | 0 | 2401.72 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2404132A | 2400.92 | F21P1 WWT package (Installation and 2 batch tanks) | 4116 | C |  | WWT B side Drain label | 45399 | 45400 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 2376.27 | 0.98973 | 24.65 | 0 | 24.65 | 2400.92 | [54 empty] | 0 |  | 0 |  |  |  |  | 360.138 |  |  |  | 360.138 |  |  | 2376.27 | 360.138 |  | 2400.92 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2311044A | 2400 | EBO21- Tool interconnection | 2899 | C |  | EBO: ZOCD-1: CDA CABINET INSTALL | 45239 | 45245 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2400 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 2400 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C032 | USCSB2309037A | 2400 | F21_AZQR_Hookup_ Interconnection | 2514 | C |  | QR: KAX01/KXAT02 – TOOL DEMO LABOR ONLY | 45178 | 45182 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2400 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 2400 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2401120A | 2399 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3307 | C |  | United Rentals train the trainer certification for boom, scissor, reach & whs forks | 45308 | 45308 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2399 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 2399 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2401164A | 2395.5 | F21P1-0404_H_labor for 50 tools_MICU | 3349 | C |  | Scissorlift Invoice and Controller Quote for James McCormick shared by all system | 45311 | 45313 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2395.5 | 0 | 2395.5 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304050A | 2393.6 | F21P1 WWT package (Installation and 2 batch tanks) | 1890 | C |  | Equalization Line Bolts/Gaskets | 45035 | 45043 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2372.22 | 0.99107 | 21.38 | 0 | 21.38 | 23.7222 | [33 empty] | 0 |  |  |  |  | 2372.22 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 23.7222
[5 empty] | Others |  |  | USC24C006 | USCSB2410005A | 2383 | WWT B side Project | 4952 | C |  | BMWC WWT - CCR CO-2(Piping rerouting and equipment tags changes to match the design) | 45566 | 45567 | [7 empty] | PR Approved | PO Approving | [14 empty] | 0 | 0 | 2383 | 0 | 2383 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408063A | 2375 | Tool Interconnection Project (Main Tool & Other Vendors) | 1206 | P |  | KPE604-S & KPE607-S CW Piping Material | 45533 | 45533 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2375 | 2375 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306047A | 2370 | Tool Interconnection Project (Main Tool & Module) | 331 | P |  | KPSP06 - PARTIAL MECHNICAL LABOR | 45100 | 45138 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2370 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 2370 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308022A | 2368 | Tool Interconnection Project (Main Tool & Module) | 372 | P |  | KPE603-S Trident Labor Pay | 45167 | 45199 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2368 | 0 | 2368 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2404086A | 2365.7 | F21P1-0404_H_labor for 50 tools_MICU | 4075 | C |  | Equipment Share GENIE GR-20 for HK | 45392 | 45394 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 2365.7 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 2365.7 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307075A | 2360 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2242 | C |  | Glendale 42 Crates Unpack | 45125 | 45135 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2360 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 2360 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  | Main Contract Scope | UPW | UPW | Electrical | Material | USC24C008 | USCSB2406098A | 2350 | UPW B Side Project | 4333 | C |  | UPW B Side Panel Materials | 45462 | 45467 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 2350 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 2350 |  |  |  |  | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402013A | 2332.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 739 | P |  | Perform interconnection on KEPRL2. | 45324 | 45355 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 2332.4 | 2595.47 | -263.07 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407080A | 2315 | TSMC Fab 21 P1B Tool Hook Up | 4496 | C |  | Label for Gas/Plastic/UPW system | 45487 | 45500 | [6 empty] | KANTEK TECHNOLOGY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2315 | 0 | 2315 | 0 | [73 empty] | - |  |  | 0
[5 empty] | Others |  |  | USC23C036 | USCSB2409107A | 2310.68 | F21P1 AMAT Interconnection | 4926 | C |  | AMAT_DIF_KDIGA5 KDIGA6 KDIGA7 KDIGA9_Eletrical materials | 45561 | 45566 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2310.68 | 0 | 2310.68 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402223A | 2308.5 | F21P1-0404_H_labor for 50 tools_MICU | 3650 | C |  | Hard Hat Chin Strap with Black Elastic Strap and Chin Cup shared by all hookup system | 45344 | 45348 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2056.5 | 0.89084 | 252 | 0 | 252 | 0 | 2056.5 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2312027A | 2300.44 | F21P1 WWT package (Installation and 2 batch tanks) | 3020 | C |  | Chemical Lab Cabinets for WWT lab in WRC | 45266 | 45267 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2300.44 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 2300.44 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | GF Agru Material | Material |  |  | WWT | Mechanical | Material | USC22C023 | USCSB2210022A | 2298.12 | AZ GF Agru Material | 1505 | C |  | GF PP&PVDF Material Organo | 44847 | 44852 | [6 empty] | Organo Technology CO., LTD | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 2298.12 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 2298.12 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403025A | 2292 | Tool Interconnection Project (Main Tool & Other Vendors) | 851 | P |  | Manpower Pay for CCE | 45358 | 45363 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 2292 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2292 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312162A | 2289.18 | F21P1-0404_H_labor for 50 tools_MICU | 3150 | C |  | Steel Passing Link Chain, lock, cutting machine, shared materials for all system, tool hook up team. | 45282 | 45287 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2081.18 | 0.90914 | 208 | 0 | 208 | 0 | 2081.18 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403196A | 2287 | F21P1-0404_H_labor for 50 tools_MICU | 3892 | C |  | Fuji Recording Chart,愛知 Circular Recording Chart, tool hookup team | 45370 | 45371 | [6 empty] | Richwell Instrument Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 2287 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 2287 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203017A | 2286.96 | F21P1 UPW | 139 | P0 |  | 55 inch computer desk for site modular | 44636 | 44643 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2286.96 | 1 | 0 | 0 | 0 | 0 | 2286.96 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC24C008 | USCSB2405044A | 2278.51 | UPW B Side Project | 4068 | C |  | Sticker | 45420 | 45427 | [6 empty] | StickerYou Inc. | PR Approved | PO Approved | [14 empty] | 2141.99 | 0.94008 | 136.52 | 0 | 136.52 | 0 | 2141.99 | [55 empty] | 0 | [16 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408112A | 2278.5 | TSMC Fab 21 P1B Tool Hook Up | 4726 | C |  | Mobile Storage Cabinet for HK Power trade | 45528 | 45531 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2278.5 | 2278.5 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403121A | 2275 | Tool Interconnection Project (Main Tool & Other Vendors) | 936 | P |  | Manpower Pay for CCE for Tool ID: KETRTE | 45378 | 45378 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 2275 | 0 | 2275 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2404223A | 2270.99 | F21P1-0404_H_labor for 50 tools_MICU | 4024 | C |  | Ferrules crimps for HK Power Luis | 45412 | 45426 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 2270.99 | 1 | 0 | 2270.99 | -2270.99 | 0 | [56 empty] | 0 | [16 empty] | 2270.99 |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2306103A | 2264.28 | F21P1 WWT package (Installation and 2 batch tanks) | 2136 | C |  | FAB bolts request #1 | 45099 | 45103 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2264.28 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 2264.28 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401167A | 2264 | F21P1-0404_H_labor for 50 tools_MICU | 3352 | C |  | Panduit Terminal for HK power trade | 1/21/2024 8/22/2024 | 2/14/2024 8/28/2024 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Yikang Wang | [11 empty] | 2264 | 1 | 0 | 2421.99 | -2421.99 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 2264 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304023A | 2259.02 | F21P1 WWT package (Installation and 2 batch tanks) | 1864 | C |  | Flanges for the Chem Lab connection from L10 to LB2 | 45027 | 45043 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2259.02 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 1710.68 | 490.74 | 57.6 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Site Expense |  |  | Others |  |  | USC22C008 | USCSB2403053A | 2256.7 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3759 | C |  | United Rentals Branch DK8/10 scissor lift operator certificates/Fall Pro Awareness for Equipment | 45357 | 45357 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2256.7 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 2256.7 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203012A | 2250.66 | F21P1 UPW | 136 | P0 |  | Power Strips surge protectors | 44650 | 44650 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2250.66 | 1 | 0 | 0 | 0 | 0 | 2250.66 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | Main Contract Scope | WWT | WWT | Civil | M+L | USC21C009 | USCSB2302030A | 2250 | F21P1 WWT package (Installation and 2 batch tanks) | 1711 | C |  | Spot prime and painting of 30 steel header supports | 44971 | 44985 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2250 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 2250 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403016A | 2250 | F21P1 Chemical & WCCS package | 3725 | C |  | CDS strut end caps | 45352 | 45356 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2250 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2100 |  |  |  |  | 150 | 150 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402147A | 2245.95 | F21P1-0404_H_labor for 50 tools_MICU | 3580 | C |  | contractor bags for HK Exhaust team | 2/15/2024 8/8/2024 | 2/20/2024 8/31/2024 | 175.95 | 2070 | V |  |  |  | U-Line Corporation | PR Approved | PO Approved | R1: Match the actual payment for credit card reconciliation |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2245.95 | 1 | 0 | 0 | 0 | 0 | 2245.95 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402237A | 2244 | F21P1 Chemical & WCCS package | 3663 | C |  | CDS 2" Pipe cush clamps | 45346 | 45349 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 44.88 | 0.02 | 2199.12 | 0 | 2199.12 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 44.88 | 2244 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402110A | 2244 | Tool Interconnection Project (Main Tool & Other Vendors) | 822 | P |  | Manpower Pay for Delta Wye | 45349 | 45353 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 2244 | 0 | 2244 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407024A | 2243 | Tool Interconnection Project (Main Tool & Other Vendors) | 1160 | P |  | 100ea BLN 73A-120 Dividers | 45492 | 45495 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 2243 | 1 | 0 | 2243 | -2243 | 0 | [73 empty] | 2243 |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2306003A | 2240.6 | F21_AZQR_Hookup_ Interconnection | 2038 | C |  | 瑭承實業有限公司: QR LAB - UNISTRUT MATERIALS | 45079 | 45079 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2240.6 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2240.6 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403013B | 2239.66 | F21P1-0404_H_labor for 50 tools_MICU | 3722 | C |  | tools for calibration for HK power system | 45352 | 2024/3/12 2024/3/19 2024/3/20 |  |  | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: change to amazon because account is still on hold B: Change to AMAZON |  | Yi En Wong | [11 empty] | 1823.42 | 0.81415 | 416.24 | 0 | 416.24 | 0 | 1823.42 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | Labor | USC23C045 | USCSB2310016A | 2239 | WWT Change Order (Piping) | 2679 | C |  | WWT Flange Level Gauge Platform Mod(MU)( T125AC/AD LG clash) | 45202 | 45206 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2239 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 2239 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2404093A | 2234.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 1039 | P |  | Michael Rodrigues - RS Payroll 1-7 May Cable pulls, 8395 inspections, tool walks. | 45406 | 45448 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2234.4 | 0 | 2234.4 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2312068A | 2228.4 | F21P1-0423_H_T&M Hardware_MICU | 3060 | C |  | Connector, KRWRS6, KMOPA4-C | 45272 | 45273 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2228.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 2228.4 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2310002A | 2226.34 | F21P1 Chemical & WCCS package | 2665 | C |  | VMB parts for Chemical team | 45202 | 45206 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2226.34 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2226.34 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2405099A | 2225 | F21P1 WWT package (Installation and 2 batch tanks) | 4118 | C |  | WWT 2" Backing Ring_20240515 (A&B Side) | 45428 | 45429 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2225 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 2225 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311070A | 2223.01 | Tool Interconnection Project (Main Tool & Module) | 538 | P |  | Manpower Labor for Tool KEMGL1 | 2023/11/27 2023/12/13 | 20224/1/24 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1: Needed Updated back-up paperwork. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2223.01 | 3171.27 | -948.26 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2404113A | 2214.53 | Tool Interconnection Project (Main Tool & Other Vendors) | 1057 | P |  | WIC. THHN 4 STR GRN MR COPPER BUILDING WIRE Cuts: QTY1 @ 2000 ft** IN STOCK AT IES PHOENIX **; 1QTY @ 2,000ft X 1070.516/m | 45412 | 45416 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 2214.53 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 2141.03 |  |  |  | 73.5 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409109A | 2211.32 | TSMC Fab 21 P1B Tool Hook Up | 4915 | C |  | PCW hand tool consumable for 297 tools | 45562 | 45563 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2211.32 | 0 | 2211.32 | 0 | [73 empty] | -
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2308035A | 2204 | F21P1-0404_H_Hallway plate install_MICU | 2335 | C |  | MIC - TSMC Tooling Foundations-AET-G-07 Rework | 45145 | 45145 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2093.8 | 0.95 | 110.2 | 0 | 110.2 | 0 | [40 empty] | 2093.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2302054A | 2200 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1735 | C |  | Recurring Fee (revised) | 44972 | 44984 | [6 empty] | Lee Collins Air Conditioning | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1606.45 | 0.7302 | 593.55 | 0 | 593.55 | 0 | [28 empty] | 0 |  |  |  | 550 | 0 |  |  |  |  | 550 |  | 0 | 0 | 0 | 0 |  | 506.45 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2304079A | 2200 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1917 | C |  | Cubicles for lobby- Glendale | 45043 | 45048 | [6 empty] | TCS Solutions, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2200 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 2200 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2312073A | 2194 | F21P1 Chemical & WCCS package | 3065 | C |  | CDS Electronic pressure recorder CR87P requested by Henry | 45273 | 45275 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2194 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 2194 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2307028A | 2190.8 | F21P1 UPW | 2200 | C |  | UPW sight glass ball valves | 45115 | 45114 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2190.8 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 2190.8 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406109A | 2184.47 | F21P1-0404_H_labor for 50 tools_MICU | 4349 | C |  | Per purchasing team request. initiate a new PR to write off this invoice. | 45464 | 45471 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 2184.47 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 2184.47 | [10 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402269A | 2180.85 | F21P1-0404_H_labor for 50 tools_MICU | 3694 | C | -02 | Bags and cleanroom tapes for HK Exhaust and PCW | 2024/2/28 2024/3/1 3/26/2024 | 3/22/2024 3/27/2024 3/28/2024 | 32.98 | 2147.87 |  |  |  |  | U-Line Corporation | PR Approved | PO Approved | PR R1:tax was not included R1: PR Amendment change tax R2: Change Tax Amount |  | Jen-Ping Tsai Yikang Wang | [11 empty] | 2180.85 | 1 | 0 | 0 | 0 | 0 | 2180.85 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2309019A | 2179.37 | F21P1 AMAT Interconnection | 2496 | C |  | Change Order for KESDA1 | 45176 | 45177 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2179.37 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 2179.37 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C007 | USCSB2310177A | 2177.91 | F21P1 Module Tool Interconnection PVD1-2 | 2830 | C |  | San Tan Fire KSMGS1 Hot N2 | 45226 | 45230 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 2177.91 | 0 | 2177.91 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2405111A | 2177 | F21P1 Chemical & WCCS package | 4141 | C |  | CDS L brackets requested by Alonso in 2023 | 45433 | 2024/5/22 2024/5/28 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2177 | 0 | 2177 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203013A | 2167.5 | F21P1 UPW | 137 | P0 |  | Desk for modular toward total needed | 44630 | 44643 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2167.5 | 1 | 0 | 0 | 0 | 0 | 2167.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C006 | USCSB2309083A | 2158.08 | F21P1 Module Tool Interconnection EPI | 2556 | C |  | RKC 4.5T-10/S90 | 45184 | 45192 | [6 empty] | Motion Automation Intelligence | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2158.08 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 2158.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311044A | 2151.06 | Tool Interconnection Project (Main Tool & Module) | 518 | P |  | Litho 2 KPE605-S XCDA/HCDA Material Please see quote in documents for material details. | 45246 | 45246 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2151.06 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 2151.06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | Organo |  |  |  | Others |  |  | USC24C013 | USCSB2406037A | 2150 | Organo USA - UPW Electrical | 4263 | C |  | WRC UPW Pump Revision - Permit | 45449 | 45450 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2150 | 0 | 2150 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2312082A | 2149.2 | F21P1 Chemical & WCCS package | 3074 | C |  | CDS 1-1/2"x2" 45 ELBOW 316LEP/304AP | 45274 | 45273 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2149.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 2149.2 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C006 | USCSB2410056A | 2145.65 | WWT B side Project | 4996 | C |  | WWT Stripper system label | 45569 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 2145.65 | 0 | 2145.65 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2305065A | 2132 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1987 | C |  | Preventive Maintenance on dock doors | 5/16/2023 8/19/2024 | 5/19/2023 8/24/2024 | -636 | 2768 |  |  |  |  | Raymond West Intralogistics Solutions | PR Approved | PO Approved | R1: The amount has been adjusted from $2,768 to $2,132 due to the expiration of the contract period. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2132 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 186 |  | 319 | 0 | 0 | 346 | 454 | 0 | 0 | 0 | 0 | 0 |  | 27 | 0 | 0 | 0 |  | 0 |  | 454 |  |  |  | 346 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2405070A | 2125.4 | F21P1 WWT package (Installation and 2 batch tanks) | 4090 | C |  | WWT Blind Flange 4&6_20240510 (A Side) | 45423 | 45425 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 2125.4 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 2125.4 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC24C005 | USCSB2404052A | 2119.1 | Chemical & WCCS B Side Project | 4046 | C |  | 電料補齊.1 20240403 | 45386 | 45387 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2119.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2119.1 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111058A | 2118.4 | F21P1 UPW | 59 | P0 |  | Office Desk | 44524 | 44624 | [6 empty] | American Furniture Warehouse | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | [7 empty] | 2118.4 | 1 | 0 | 0 | 0 | 0 | 2118.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405108A | 2109.44 | Tool Interconnection Project (Main Tool & Other Vendors) | 1106 | P |  | Interconnect Cable Pull for KCSCN2-Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45429 | 45432 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 2109.44 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 2109.44 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404055A | 2109.44 | Tool Interconnection Project (Main Tool & Other Vendors) | 1008 | P |  | Regular cable interconnect for KSCBH5,Pulling cables from L30 to L20 and L10, follow 8395 cable routing specifications | 45393 | 45393 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Sian-Ning Pei | [11 empty] | 2109.44 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2109.44 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406034A | 2109.44 | Tool Interconnection Project (Main Tool & Other Vendors) | 1140 | P |  | Interconnect Cable Pull for KCSCN4 | 45471 | 45474 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2109.44 | 0 | 2109.44 | 0 | [73 empty] | - |  |  | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2308038A | 2104 | F21P1-0404_H_Hallway plate install_MICU | 2336 | C |  | Added Support Legs, Larger Holes AET-G-14 | 45145 | 45145 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1998.8 | 0.95 | 105.2 | 0 | 105.2 | 0 | [40 empty] | 1998.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309017A | 2103.75 | F21P1 Chemical & WCCS package | 2494 | C |  | Flanges used for CDU exhaust drain. | 45175 | 45182 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2103.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 2103.75 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2410001A | 2102 | TSMC Fab 21 P1B Tool Hook Up | 4948 | C |  | Electrical Insulation tape Quotation request for HK Power for 200 tools | 45566 | 45566 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2102 | 0 | 2102 | 0
Base-Build | Chemical |  |  |  | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC24C005 | USCSB2408031A | 2100 | Chemical & WCCS B Side Project | 4626 | C |  | CDA/GN2 Particle testing Equipment Calibration (設備校正0806) | 45512 | 45512 | [6 empty] | Particle Measuring Systems, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2100 | 0 | 2100 | [74 empty] | -
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Material | USC24C005 | USCSB2407005A | 2100 | Chemical & WCCS B Side Project | 4407 | C |  | F21P1 Fab LB2 WWT Tank H2SO4 Header | 45474 | 45474 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | [14 empty] | 2100 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 2100 |  |  | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2311028A | 2099.16 | F21P1 WWT package (Installation and 2 batch tanks) | 2883 | C |  | WWT chemical storage in LB2 | 45237 | 45237 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2099.16 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 2099.16 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208016A | 2098.57 | F21P1 UPW | 215 | P0 |  | 3 drawer black personal desk files | 44798 | 44810 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2098.57 | 1 | 0 | 0 | 0 | 0 | 2098.57 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2309090A | 2098.5 | F21P1 Chemical & WCCS package | 2563 | C | -01 | Chemical box&box cover for location of support welding & hole location | 2023/9/15 2023/9/19 | 2023/9/19 2023/12/4 | 470.25 | 1628.25 |  |  | V |  | FusionHPX LLC | PR Approved | PO Approved | Revise quantity of order to add 1 more item |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2098.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2098.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2305018A | 2095 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1942 | C |  | Outlets for overflow warehouse | 45050 | 45056 | [6 empty] | RMJ Electrical Contractors Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2095 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 2095 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2405052A | 2094.51 | F21P1-0404_H_labor for 50 tools_MICU | 4058 | C |  | V-Belt K-30 for HK Exhaust trade for 20 tools | 45420 | 45429 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1771.33 | 0.8457 | 323.18 | 0 | 323.18 | 0 | 1771.33 | [55 empty] | 0 | [16 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403267A | 2091.3 | F21P1-0404_H_labor for 50 tools_MICU | 3960 | C |  | 3/8 in PE Tubing Coil for exhaust trade | 45378 | 45385 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1901.2 | 0.9091 | 190.1 | 0 | 190.1 | 0 | 1901.2 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402014A | 2090.24 | Tool Interconnection Project (Main Tool & Other Vendors) | 740 | P |  | KEPRL3 in house manpower-TSMC + ETC2 + KEPRL3 + Interconnect 2/8/2024, 2/9/2024, 2/12/2024 | 45324 | 45355 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 2090.24 | 3273.19 | -1182.95 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Site Expense | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2306041A | 2084.61 | F21P1 Chemical & WCCS package | 2075 | C |  | Scissor lift for Chemical welding | 45090 | 45210 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 2084.61 | 0 | 2084.61 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 2084.61 | [9 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2409120A | 2080.5 | TSMC Fab 21 P1B Tool Hook Up | 4938 | C |  | Glove Guard Extreme Cable Safe Hook, Yellow, 9 Inch HookGlove Guard Extreme Cable Safe Hook, Yellow, 9 Inch Hook | 45563 | 45566 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2080.5 | 0 | 2080.5 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403226A | 2078.3 | F21P1-0404_H_labor for 50 tools_MICU | 3921 | C |  | Electrician tools Power System order form Luis | 45373 | 45376 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1883.3 | 0.90617 | 195 | 0 | 195 | 0 | 1883.3 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403115A | 2070.8 | Tool Interconnection Project (Main Tool & Other Vendors) | 931 | P |  | SS-12-E FNPT ELBOW 3/4" | 45377 | 45378 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 2070.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2070.8 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC22C036 | USCSB2304020A | 2066.73 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1861 | C |  | PVC Reducers and Elbows | 45026 | 45026 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2066.73 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2066.73 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2405112A | 2064 | F21P1 AMAT Interconnection | 4142 | C |  | Action Scaffolding | 45433 | 45442 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2064 | 0 | 2064 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201010A | 2063.38 | F21P1 UPW | 104 | P0 |  | Laptop | 44579 | 44580 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2063.38 | 1 | 0 | 0 | 0 | 0 | 2063.38 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2312076A | 2063.23 | F21P1-0404_H_labor for 50 tools_MICU | 3068 | C |  | Home Depot tools for 永旗. New arrival trade new tools request | 45273 | 45276 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1899.84 | 0.92081 | 163.39 | 0 | 163.39 | 0 | 1899.84 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2204015A | 2057.4 | F21P1 UPW | 1364 | C |  | Added Order (Nagano Adapter) | 44679 | 44683 | [6 empty] | Ashcroft Inc. | PR Approved | PO Approved | USC2111018A的Change Order | 100% After shipment-Net 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 2057.4 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 2057.4 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312080A | 2050.01 | Tool Interconnection Project (Main Tool & Module) | 623 | P |  | Interconnect cable pull for KETRT4 (ETC3), Interconnect cable pull, Ewah considered & implemented suggestions during our initial installation of interconnect work. Includes interconnect rework. | 45283 | 45303 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 486.88 | 0.2375 | 1563.13 | 0 | 1563.13 | 0 | [45 empty] | 0 |  | 0 | 0 | 486.88 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2312094A | 2047.91 | F21P1-0423_H_T&M Hardware_MICU | 3085 | C |  | Quick-Clamp High-Vacuum Fitting for Stainless Steel Tubing, Straight Reducer for 1-1/2" x 1" Tube | 45274 | 45279 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2036.1 | 0.99423 | 11.81 | 0 | 11.81 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 2036.1 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402247A | 2042.83 | F21P1 WWT package (Installation and 2 batch tanks) | 3673 | C |  | WWT Hardware_20240223 (A Side) | 45347 | 45349 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2042.83 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1447.42 | 0 |  | 0 |  |  |  | 595.41 |  |  |  |  | 102.1415 |  |  |  | 102.1415 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2311100A | 2040 | F21P1 Chemical & WCCS package | 2951 | C |  | CDS M421C0201-54 missing needle valves replacement. | 45251 | 45258 | [6 empty] | JIM & STEVE INDUSTRIAL CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2040 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 | 2040 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 2040 | [5 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403047A | 2032.05 | Tool Interconnection Project (Main Tool & Other Vendors) | 873 | P |  | DAILY USE OF D/D KIT, D/D BITS, VAC/DUST EXTR, X-LINE LASER, CABLE CUTTER | 45363 | 45362 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2032.05 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 2032.05 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2308031A | 2024 | F21P1-0404_H_Hallway plate install_MICU | 2332 | C |  | AET-E-13 Rework and Added Supports | 45143 | 45143 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1922.8 | 0.95 | 101.2 | 0 | 101.2 | 0 | [40 empty] | 1922.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C053 | USCSB2312034A | 2020.78 | AMAT Interconnection (TSMC) | 3027 | C |  | Change Order total for KKDB04 | 45266 | 45267 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2020.78 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 2020.78 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2401061A | 2016.88 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3250 | C |  | Border States Electrical Work Material PreFab Area Open Statement Invoices | 45302 | 45303 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2016.88 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 2016.88 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403023A | 2016 | F21P1 Chemical & WCCS package | 3732 | C |  | CDS tools for flare | 45353 | 45357 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2016 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2016 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202004A | 2009.09 | F21P1 UPW | 113 | P0 |  | Desktop Computer | 44604 | 44609 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2009.09 | 1 | 0 | 0 | 0 | 0 | 2009.09 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C053 | USCSB2401238A | 2006.65 | AMAT Interconnection (TSMC) | 3419 | C |  | KESDA3.1 Tray Dividers, & Insulated Clamps | 45318 | 45324 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2006.65 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 2006.65 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2308033A | 2004 | F21P1-0404_H_Hallway plate install_MICU | 2333 | C |  | AET-F-05 Rework | 45145 | 45145 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1903.8 | 0.95 | 100.2 | 0 | 100.2 | 0 | [40 empty] | 1903.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC24B002 | USC2401045A | 2002 | Tool Interconnection Project (Main Tool & Other Vendors) | 667 | P |  | KECOT5 MANPOWER PAY FOR WGN STAR | 45311 | 45313 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 2002 | 0 | 2002 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2404191A | 2000 | F21P1-0404_H_labor for 50 tools_MICU | 4171 | C |  | Tray canle wire cut for HK Power system. Tool id KPE604-S | 45407 | 45407 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1750 | 0.875 | 250 | 1250 | -1000 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 500 |  |  | 0 |  | 1250 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C032 | USCSB2306107A | 2000 | F21_AZQR_Hookup_ Interconnection | 2140 | C |  | QR LAB: MECHANICAL LABOR KXAT01 & KXFX01 | 45100 | 45114 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 2000 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403124A | 1998.24 | F21P1-0404_H_labor for 50 tools_MICU | 3826 | C | -01 | tape for all systems | 45364 | 2024/3/13 2024/3/15 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | R1: Change Ship-to Address to Surprise WH |  | Yikang Wang | [11 empty] | 1996.4 | 0.99908 | 1.84 | 0 | 1.84 | 0 | [52 empty] | 0 | 0 | 0 |  | 1996.4 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202005A | 1998.22 | F21P1 UPW | 114 | P0 |  | Laptop | 44604 | 44609 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1998.22 | 1 | 0 | 0 | 0 | 0 | 1998.22 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203016A | 1993.55 | F21P1 UPW | 138 | P0 |  | 55 inch computer desk | 44636 | 44643 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1993.55 | 1 | 0 | 0 | 0 | 0 | 1993.55 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C006 | USCSB2312167A | 1989.6 | F21P1 Slurry package | 3155 | C |  | CDS MIC A side electrical materials | 45282 | 45282 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1989.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1989.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2306100A | 1989.35 | F21 TMAH System | 2133 | C |  | WWT-CCB-PVC | 45098 | 45114 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1989.35 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 1989.35 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse | Site Expense |  |  | Others |  |  | USC22C008 | USCSB2403039A | 1988.38 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3746 | C |  | United Rentals Branch DK8,30 foot 2wd Articulating Electric Boom Lift | 45356 | 45357 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1112.7 | 0.5596 | 875.68 | 0 | 875.68 | 0 | [52 empty] | 0 | 0 | 1112.7 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402250A | 1987.68 | F21P1 Chemical & WCCS package | 3676 | C |  | CDS sealing materials | 45349 | 45348 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1987.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1987.68 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C005 | USCSB2405037A | 1980 | Chemical & WCCS B Side Project | 4046 | C |  | CHEM_ panel design_20240506_ (12004) | 45419 | 45419 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | [14 empty] | 1980 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 1980 | 1980 | [7 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2307080A | 1980 | F21P1 Module Tool Interconnection DIF1-2 | 2246 | C |  | DIFF1: DOUBLE CASING CONNECTION FOR DIFF1, KDAPK2-4 | 45126 | 45126 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1980 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 1980 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2409095A | 1979.59 | WWT B side Project | 4905 | C |  | WWT shortage materials on the B side NaOH H2SO4, AWD O3 | 45560 | 45561 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1979.59 | 0 | 1979.59 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409031A | 1978.35 | TSMC Fab 21 P1B Tool Hook Up | 4798 | C |  | Cutting Band Saw Blade for HK Power Team for 200 tools | 45541 | 45545 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1708.5 | 0.8636 | 269.85 | 0 | 269.85 | 0 | 1708.5 | [72 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2312148A | 1974.7 | F21P1 Chemical & WCCS package | 3137 | C |  | CDS Materials for Lorry requested by Ben and John | 45280 | 45280 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1974.7 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1974.7 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2312055A | 1974.6 | F21P1-0404_H_labor for 50 tools_MICU | 3048 | C |  | Amazon order for James McCormick | 45268 | 45271 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1466 | 0.74243 | 508.6 | 0 | 508.6 | 0 | 1466 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Material | USC24C006 | USCSB2405152A | 1973.12 | WWT B side Project | 4181 | C |  | These cables will be installed for control system of WSR. | 45441 | 45442 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1973.12 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 1973.12 | [6 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Labor | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2308052A | 1972 | F21P1 Chemical & WCCS package | 2350 | C |  | Dual Contained Pipe testing(Pressure test tools for Lorry) | 45147 | 45152 | [6 empty] | M. Caputo Technical Services, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1972 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1972 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403270A | 1965 | F21P1 WWT package (Installation and 2 batch tanks) | 3963 | C |  | WWT PVC Glue & Primer_20240327 | 45379 | 45379 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1965 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 1965 |  |  |  |  | 294.75 |  |  |  | 294.75 |  |  |  | 294.75 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2402008A | 1963.5 | F21P1 Chemical & WCCS package | 3451 | C |  | CDS Sensor FLS-VM-400 | 45323 | 45327 | [6 empty] | AutomationDirect.com INC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1785 | 0.90909 | 178.5 | 0 | 178.5 | 0 | 1785 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 176.72 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2404174A | 1960.05 | Chemical & WCCS B Side Project | 4155 | C |  | CHEM_Waste System Fab L20 PVDF PIPE USED | 45405 | 45405 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1960.05 | 0 | 1960.05 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 1960.05 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407032A | 1958.08 | WWT B side Project | 4431 | C |  | Materials for B side LB 1 Drain | 45479 | 45481 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 1958.08 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 1958.08 |  |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303044A | 1956.36 | F21P1 WWT package (Installation and 2 batch tanks) | 1786 | C |  | Litho Drain Bolts and Gaskets | 44994 | 44998 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1956.36 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 1956.36 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311129A | 1955.13 | F21P1-0404_H_labor for 50 tools_MICU | 2979 | C |  | HK Hydraulic pipe bender for orientation/training | 45259 | 45260 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1955.13 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1057.69 |  |  | 897.44 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408147A | 1955 | TSMC Fab 21 P1B Tool Hook Up | 4763 | C |  | Label for GAS, CHEMICAL and PPL | 45534 | 9/5/2024 9/12/2024 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | PO R1: Revise responsible engineer and update the completion date | [13 empty] | 0 | 0 | 1955 | 0 | 1955 | 0 | [73 empty] | -
Base-Build | UPW | MISC Expense | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111007A | 1954.6 | F21P1 UPW | 27 | P0 |  | Cabinet | 44511 | 44512 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Ka In Wong Lane | Lan Yun Chang |  | X | Matt |  |  |  |  | 1954.6 | 1 | 0 | 0 | 0 | 0 | 1954.6 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2311024A | 1950.21 | F21P1 UPW | 2879 | C |  | UPW-GF-limitswitch | 45237 | 45237 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1950.21 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 1950.21 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403122A | 1950 | Tool Interconnection Project (Main Tool & Other Vendors) | 937 | P |  | Manpower Pay for CCE for Tool ID: KESTL6 | 45378 | 45378 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 1950 | 0 | 1950 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Safety | USC21C009 | USCSB2407016A | 1950 | F21P1 WWT package (Installation and 2 batch tanks) | 4417 | C |  | WWT - SCS Lorry to tunnel confined space rescue | 45475 | 45482 | [6 empty] | Safety Compliance Services, Inc | PR Approved | PO Approved | [14 empty] | 1950 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 | 1950 | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312060A | 1950 | Tool Interconnection Project (Main Tool & Module) | 606 | P |  | TSMC20 管路貼紙 【防水、撕不破】 【耐曬油墨】:Stickers for piping system 100 X 15 mm (4”X0.6”) | 45276 | 45278 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1950 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 1950 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C032 | USCSB2312117A | 1948.12 | F21_AZQR_Hookup_ Interconnection | 2968 | C |  | QR LABS: CHAD/FAD LAN TRAY MATERIALS | 2023/12/16 | 45443 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1948.12 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 1948.12 | [12 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2401241A | 1944.64 | F21P1 Module Tool Interconnection CVD | 3422 | C |  | KCANN1 CIP re-work | 45321 | 45322 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1944.64 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 1944.64 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2401249A | 1944.64 | F21P1 Module Tool Interconnection CVD | 3430 | C |  | KCANN2 re-work to fulfill CIP gasline heater jacket and AC boxes. | 45321 | 45322 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1944.64 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 1944.64 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201008A | 1942.99 | F21P1 UPW | 102 | P0 |  | Autodesk AECC License | 44579 | 44580 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1942.99 | 1 | 0 | 0 | 0 | 0 | 1942.99 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C019 | USCSB2405008A | 1942 | F21P1 Hitachi Interconnection | 4019 | C |  | ME: KPCD15: RMF MODIFICATIONS. | 45414 | 45420 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 1942 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 1942 | [6 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USC2404039A | 1940.58 | F21P1 AMAT Interconnection | 993 | P |  | wire and lug material | 45391 | 45392 | [6 empty] | Rexel USA, INC. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1940.58 | 1 | 0 | 0 | 0 | 0 | 1940.58 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2307118A | 1935.83 | EBO21- Tool interconnection | 2282 | C |  | ZCOAT-1: Interconnection material, Basket Trays, Basket Tray 90 Degree Kit | 45133 | 45142 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1935.83 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 1935.83 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201009A | 1933.77 | F21P1 UPW | 103 | P0 |  | Autodesk AECC License | 44579 | 44580 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1933.77 | 1 | 0 | 0 | 0 | 0 | 1933.77 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401072A | 1932 | Tool Interconnection Project (Main Tool & Other Vendors) | 692 | P |  | KESRT2 MANPOWER PAY for NETCOMN | 45316 | 45316 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 1932 | 0 | 1932 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403099A | 1928.71 | F21P1 WWT package (Installation and 2 batch tanks) | 3801 | C |  | WWT Hardware_20240308 (A Side) | 45360 | 45362 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 1928.71 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 652.66 | 636.45 |  | 0 |  |  |  | 639.6 | 96.4355 |  |  |  | 192.871 |  |  |  | 192.871 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C046 | USCSB2403152A | 1927.65 | F21P1 ATS Interconnection | 3851 | C | -01 | ATS CHILLER: NO TOOL ID: DAILY USE OF LADDERS, CHAINS, LOCKS, STORAGE CHEST, HEX KEY SET, & CASTER KIT W/ HARDWARE | 2024/3/14 2024/4/1 | 2024/3/21 2024/5/2 | -51.82 | 1979.47 |  |  |  |  | The Home Depot, Inc | PR Approved | PO Approved | R1: Ridgid storage chest was refunded. Ordered 2nd time with a discount. |  | Yikang Wang | [11 empty] | 1927.65 | 1 | 0 | 0 | 0 | 0 | 1927.65 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403034A | 1924.81 | Tool Interconnection Project (Main Tool & Other Vendors) | 860 | P |  | MANPOWER PAY FOR RS PAYROLL | 45359 | 45363 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 0 | 0 | 1924.81 | 0 | 1924.81 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | DCR Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C007 | USCSB2309177A | 1918.57 | F21P1 VOC package （Installation ) | 2646 | C |  | F21 P1 VOC Cable | 45197 | 45202 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1918.57 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 1918.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2407062A | 1917.44 | F21P1 AMHS Wiring Work Outline | 4459 | C |  | AMHS - Cleanroom Supplies | 45484 | 45488 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 1917.44 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1917.44 |  |  | - |  |  | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2308026A | 1914 | F21P1 UPW | 2327 | C |  | Damaged Instrument Sensors | 45142 | 45142 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1914 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1914 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408051A | 1912.35 | TSMC Fab 21 P1B Tool Hook Up | 4669 | C |  | Label kit for BBP 37, Gas and chemical system | 45514 | 45516 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 1912.35 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1912.35 |  |  | -
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C032 | USCSB2310013A | 1911.63 | F21_AZQR_Hookup_ Interconnection | 2676 | C |  | QR: KXAT01, KXAT02, KXFX01, KXPS01: T&M FOR ECONNECTION BOX TERMINATIONS | 2023/10/3 2024/8/5 | 2023/10/26 2024/8/5 | -1208.37 | 3120 | V |  |  |  | Delta Wye Electric, Inc. | PR Approved | PO Approved | R1: Updated amount to match invoice. Material was not included, so modified line#1 ($744.00 + $271.63 for material)/8 hrs. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1911.63 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 1911.63 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409035A | 1905.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1237 | P |  | CED S41010CT00: 1'' SS304 RIGID CONDUIT, 10' W/CO | 45553 | 45553 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1905.6 | 0 | 1905.6 | 0 | [73 empty] | -
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204003A | 1900.48 | F21P1 UPW | 150 | P0 |  | Lenovo Laptop, Dell Laptop | 44673 | 44676 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1900.48 | 1 | 0 | 0 | 0 | 0 | 1900.48 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical Lab | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC22C021 | USCSB2403115A | 1900 | F21P1 Chemical Lab setup | 3817 | C |  | 2 Hach Dissolved Oxygen Sensor Repair | 45363 | 45363 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1900 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 1900 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C029 | USCSB2403280A | 1900 | EBO21- Tool interconnection | 3973 | C |  | EBO: ZFP3-1: GEX EXHAUST REWORK | 45380 | 45383 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1900 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1900 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC24C006 | USCSB2405156A | 1899.49 | WWT B side Project | 4184 | C |  | WWT Container Covers_20240524 (B Side) | 45441 | 45441 | [6 empty] | Global Equipment Company Inc. | PR Approved | PO Approved | [14 empty] | 1899.49 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 1899.49 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311007A | 1888 | Tool Interconnection Project (Main Tool & Module) | 482 | P |  | KDSNB1 Cable Pull Labor Pay | 45232 | 45238 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1888 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 1888 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311024A | 1888 | Tool Interconnection Project (Main Tool & Module) | 498 | P |  | Manpower Pay for General Labor for Elsa Nieto/ Von Villas | 45239 | 45241 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1888 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1888 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403215A | 1883.78 | F21P1-0404_H_labor for 50 tools_MICU | 3910 | C |  | For tailer 15 office supplies, tool hookup team | 45372 | 45372 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1426.12 | 0.75705 | 457.66 | 0 | 457.66 | 0 | 1426.12 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311046A | 1883.38 | Tool Interconnection Project (Main Tool & Module) | 520 | P |  | Litho 2 Material Armaflex | 45246 | 45248 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1883.38 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 1883.38 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2306066A | 1882 | F21P1 Module Tool Interconnection CVD | 2099 | C |  | CVD2_MACH 1+，Interconnection material KCANN1~7, 7 tools, Male Fujikin 1/2" Diaphragm manual valve | 45093 | 45096 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1882 | 0 | 1882 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2402205A | 1879.74 | F21P1 AMAT Interconnection | 3632 | C |  | Hot Ground Wire | 45343 | 45350 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1879.74 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1879.74 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407010A | 1875.15 | WWT B side Project | 4411 | C |  | WWT Hardware #1 | 45475 | 45476 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1875.15 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 1875.15 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401104A | 1869.11 | F21P1-0404_H_labor for 50 tools_MICU | 3291 | C |  | cart for UPW 20 tools, cutting saw blade for GAS 50 tools, tape for PCW 5o tools, Tool hookup team | 45307 | 45310 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1837.3 | 0.98298 | 31.81 | 0 | 31.81 | 0 | 1837.3 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406072A | 1867.42 | F21P1-0404_H_labor for 50 tools_MICU | 4304 | C |  | P1B power tool request for Third, tool base is 50 tools | 45456 | 45459 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1514.25 | 0.81088 | 353.17 | 0 | 353.17 | 0 | 1514.25 | [72 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303100A | 1861.86 | F21P1 WWT package (Installation and 2 batch tanks) | 1837 | C |  | Litho adding Tee material | 45015 | 45019 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 1861.86 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1861.86 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Site Expense | The budget execution does not pertain to this project | Shared Cost | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2212020A | 1850 | F21P1 WWT package (Installation and 2 batch tanks) | 1593 | C |  | Grounding for generator and fuel cube | 44908 | 44909 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1850 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 1850 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2409079A | 1849.8 | WWT B side Project | 4871 | C |  | WWT shortage materials on the B side ACF-720BA~BD | 45555 | 45558 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1849.8 | 0 | 1849.8 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409049A | 1849.75 | Tool Interconnection Project (Main Tool & Other Vendors) | 1252 | P |  | 22PTL-088020: Milw M18 Cordless Wet/Dry Vacuum (Bare Tool)#0880-20 | 45556 | 45558 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1849.75 | 0 | 1849.75 | 0 | [73 empty] | -
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2311080A | 1847.66 | F21 TMAH System | 2933 | C |  | Tmah Hardware request #1(coated bolts not enough) | 45247 | 45248 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 1847.66 | 0 | 1847.66 | 1847.66 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 1847.66 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112026A | 1846.18 | F21P1 UPW | 89 | P0 |  | Laptop | 44548 | 44554 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang |  |  | Matt |  |  |  |  | 1846.18 | 1 | 0 | 0 | 0 | 0 | 1846.18 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C004 | USCSB2306020A | 1844 | F21P1 WWT package （USA EQ-FRP tank) | 2054 | C | -03 | WWT-Lab oven & scale | 2023/6/6 2024/1/13 2024/3/23 | 2023/7/17 2024/1/13 2024/2/21 2024/3/26 | 151.05 | 1692.95 |  |  |  |  | Global Equipment Company Inc. | PR Approved | PO Approved | PO R1:revise price R2: Quote Update R3: The Supplier increased price again… |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 1844 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 276.6 |  |  |  | 276.6 | 1844 |  |  | 276.6 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2401138A | 1842 | EBO21- Tool interconnection | 3323 | C |  | EBO: ZCENT-1: INSTALL CABLE TRAY - LB1 | 45310 | 45331 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1842 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 1842 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311018A | 1840.8 | Tool Interconnection Project (Main Tool & Module) | 491 | P |  | Labor Pull cable and 8395 Certification/Install seal tight flex conduit, cables from L30 to L10 and tie wraps. $59 x 8 hours = $472.00 $472 x 2 installers = $944.00 | 45238 | 45241 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1840.8 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1840.8 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C011 | USCSB2402048A | 1840.39 | F21 TMAH System | 3490 | C |  | WWT Leak Detector Accessory-Omron F03-20T | 45328 | 45328 | [6 empty] | Mouser Electronics | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1840.39 | 1 | 0 | 0 | 0 | 0 | 1840.39 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2406108A | 1839.08 | F21P1 AMAT Interconnection | 4343 | C |  | CVD Brycon Material | 45464 | 45484 | [6 empty] | Brycon Corporation | PR Approved | PO Approved | [14 empty] | 1839.08 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1839.08 |  |  | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402101A | 1836.25 | Tool Interconnection Project (Main Tool & Other Vendors) | 815 | P |  | Manpoer Pay for Delta Wye | 45346 | [7 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1836.25 | 0 | 1836.25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2305096A | 1836 | F21P1 UPW | 2017 | C |  | UPW test pump | 45066 | 45079 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1836 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 1836 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2404050A | 1834.8 | F21P1-0404_H_labor for 50 tools_MICU | 4044 | C |  | Impact driver tool for HK exhaust team | 45386 | 45391 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1143 | 0.62296 | 691.8 | 0 | 691.8 | 0 | 1143 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401106A | 1831 | F21P1-0404_H_labor for 50 tools_MICU | 3293 | C |  | One-Hole Lug Compression Connector for HK power trade | 45307 | 45307 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1831 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 128.17 | [5 empty] | 1702.83 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C036 | USCSB2401048A | 1830 | F21P1 AMAT Interconnection | 3238 | C |  | square Shark Cages | 45300 | 45302 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1830 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 1830 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402251A | 1828.24 | F21P1-0404_H_labor for 50 tools_MICU | 3677 | C |  | HK Electrical PM Luis Retiz's material request | 45349 | 45353 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 1828.24 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 648.76 |  | 1179.48 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | Main Contract Scope | UPW | UPW | Steel | Labor | USC21C003 | USCSB2403299A | 1828 | F21P1 UPW | 3991 | C |  | WRC L20 Additional Welding | 45381 | 45383 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 1828 | 0 | 1828 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2306058A | 1826.88 | F21P1-0404_H_Hallway plate install_MICU | 2092 | C |  | Hard barricade hardware | 45092 | 45099 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1826.88 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 1826.88 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC24C009 | USCSB2404168A | 1825 | F21P1 Nova Interconnection | 4150 | C |  | NOVA: KEPRM6-8: PFA CLEAR TUBE FOR SIGNAL CABLE. | 45405 | 45406 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 1825 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 1825 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2312099A | 1825 | F21P1 UPW | 3090 | C |  | UPW-Tomoe-part repair | 45275 | 45275 | [6 empty] | Tomoe USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1825 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1825 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Speed Gate | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Equipment ( Tank 等工程相關的設備) | USC21C002 | USCSB2105001A | 1825 | TSMC AZ Temp Office Speed Gate | 1272 | C |  | Speed gate opeing cover and install | 44324 | 44327 | [6 empty] | B&D Industries, Inc. | PR Approved | PO Approved |  | 100% by progress , T/T 30 Days | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang |  |  | Henry |  | N |  |  | 1825 | 1 | 0 | 0 | 0 | 0 | 1825 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2305047A | 1820.62 | F21P1 WWT package (Installation and 2 batch tanks) | 1972 | C |  | Stainless Steel Pipe in Lorry | 45057 | 45061 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1820.62 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1820.62 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312083A | 1813.98 | F21P1-0404_H_labor for 50 tools_MICU | 3075 | C |  | Terminals for Third. Alternative Vendor | 45274 | 45276 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1813.98 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1813.98 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2308058A | 1810.72 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2356 | C |  | Swagelok Hand Tools | 45147 | 45152 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1810.72 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 1810.72 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C004 | USCSB2403186A | 1804 | F21P1 WWT package （USA EQ-FRP tank) | 3883 | C | -01 | U-Line - MIMO - Move In/Move Out Team | 45370 | 3/21/2024 3/27/2024 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | R1: Change payment method |  | Yikang Wang | [11 empty] | 1791.9 | 0.99329 | 12.1 | 0 | 12.1 | 0 | 1791.9 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312060A | 1802.54 | F21P1-0404_H_labor for 50 tools_MICU | 3052 | C | -01 | Stackable Plastic Bin Box, shared materials with upw system | 2023/12/8 2023/12/18 | 2023/12/11 2023/12/18 | 265.85 | 1536.69 | V |  |  |  | McMaster-Carr Supply Company | PR Approved | PO Approved | PR R1: Shipping fee increased due to expedition |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1320.8 | 0.73274 | 481.74 | 0 | 481.74 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 1320.8 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USC2404054A | 1801.55 | F21P1 AMAT Interconnection | 1007 | P |  | 8,12,14 AWG ring terminal | 45393 | 45392 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1801.55 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1801.55 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203006A | 1800.86 | F21P1 UPW | 131 | P0 |  | Laptop | 44629 | 44635 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1800.86 | 1 | 0 | 0 | 0 | 0 | 1800.86 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311078A | 1800 | F21P1-0404_H_labor for 50 tools_MICU | 2932 | C |  | Magnum Hopper Bin for Trusval Chemical. KECOT5 KECOT1 KESTL3 | 45246 | 45248 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1800 | 0 | 1800 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312180A | 1800 | F21P1-0404_H_labor for 50 tools_MICU | 3167 | C |  | 1/4 " 凸緣螺母, shared material for gas system, tool hook up | 45287 | 45289 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1800 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1800 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C003 | USCSB2311036A | 1800 | F21P1 Module Tool Interconnection CVD | 2891 | C |  | Rebuild KCOXN4 Loa Lock Lines: -Orbital Weld VCR Micro Glands and Corresponding Male/Female Connector (MICU Provided) 3/8"Mal | 45238 | 45241 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1800 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1800 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402122A | 1794 | F21P1-0404_H_labor for 50 tools_MICU | 3559 | C |  | stackable bins, broom and dust pan combo for HK Exhaust. Cleanroom tapes shared by all HK system | 45336 | 45336 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1794 | 1 | 0 | 0 | 0 | 0 | 1794 | [48 empty] | 0 |  |  | 0 | 0 | 0 | [16 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2312033A | 1790.82 | F21P1 AMAT Interconnection | 3026 | C |  | Change Order KCEPA1 AC Cover Modifications & Insulated Cable Clamps | 45266 | 45269 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1790.82 | 0 | 1790.82 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404023A | 1771 | Tool Interconnection Project (Main Tool & Other Vendors) | 978 | P |  | Manpower Pay for Delta Wye for Tool IDs: KEBEL1 & KEMEL6 Time card 2.26.2024 | 45386 | 45387 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 1771 | 0 | 1771 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2312072A | 1767.6 | F21P1 AMAT Interconnection | 3064 | C |  | AMAT_ME_KKSV02_CGB 2" connector, 2" to 1" reduec washer | 45272 | 45273 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1767.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 1767.6 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402053A | 1766.75 | Tool Interconnection Project (Main Tool & Other Vendors) | 771 | P |  | Delta Wye KEMEL7 cable pull | 45330 | 45330 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1766.75 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 1766.75 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | The budget execution does not pertain to this project | 0 | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC22C013 | USCSB2401139A | 1763.38 | F21P1 QR Lab Security & CCTV | 3324 | C |  | Laydown Material - Grainger | 2024/1/19 2024/1/24 | 45330 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | PR R1:Total contains shipping cost, added 10% buffer |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 1763.38 | 0 | 1763.38 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403210A | 1761.71 | F21P1-0404_H_labor for 50 tools_MICU | 3905 | C |  | Additional 220 V outlets to complete the electrical requirements materials | 45372 | 45373 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 1685.64 | 0.95682 | 76.07 | 0 | 76.07 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1529.6 | [9 empty] | 156.04 |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409058A | 1756.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 1258 | P |  | COND EMT3 EMT Steel Material; hot-dip galvanized finish; 10FT; 3.5 Inch outer diameter; UL 797 Approval; ANSI C80.3 Applicable standard; 263 LB Per 100 Ft Weight; 3Inch trade size; 0.072 Inch wal thickness; plain and style | 45562 | 45562 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1756.4 | 0 | 1756.4 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401261A | 1750 | F21P1-0404_H_labor for 50 tools_MICU | 3441 | C |  | Pressure Recorder | 45322 | 45323 | [6 empty] | Richwell Instrument Co., Ltd. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1750 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 1750 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2312132A | 1746.8 | F21P1-0404_H_labor for 50 tools_MICU | 3121 | C |  | Flow/reg 356-ar/he-580 dual, gas 300 tools, tool hookup | 45279 | 45280 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1746.8 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1746.8 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309115A | 1745.58 | F21P1 Chemical & WCCS package | 2587 | C |  | FNDP Material request for YaHo work at Lorry FNDP. | 45189 | 45191 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1745.58 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 1326.41 | 419.17 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2306055A | 1742.14 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2089 | C |  | A1 Locksmith & Security Center | 45091 | 45113 | [6 empty] | A1 Locksmith & Security Center Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 1742.14 | 0 | 1742.14 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C003 | USCSB2404171A | 1737.6 | F21P1 UPW | 4152 | C |  | Chemical for commissioning flush | 45405 | 45405 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved | [14 empty] | 1737.6 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 1737.6 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202017A | 1737.58 | F21P1 UPW | 124 | P0 |  | Dell Laptop | 44614 | 44617 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1737.58 | 1 | 0 | 0 | 0 | 0 | 1737.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206012A | 1737.58 | F21P1 UPW | 179 | P0 |  | Dell Laptop | 44724 | 44764 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1737.58 | 1 | 0 | 0 | 0 | 0 | 1737.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311031A | 1731.13 | Tool Interconnection Project (Main Tool & Module) | 505 | P |  | FLEX LT4UAGRY: 4 UL LIQ-TITE, PER HUNDRED | 45241 | 45245 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1731.13 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 1731.13 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC22C012 | USCSB2403085A | 1730 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3788 | C |  | UPW-ORGANO BSGN valves | 45359 | 45358 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1730 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1730 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402038A | 1727.5 | F21P1 Chemical & WCCS package | 3481 | C |  | CDS Lorry FNDP parts | 45325 | 45327 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1727.5 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 1727.5 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2312086A | 1725 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3078 | C |  | Consolidated Electrical Distributors material for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45274 | 45275 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1725 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1725 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402047A | 1718.93 | F21P1 Chemical & WCCS package | 3489 | C |  | CDS BT union and gasket | 45328 | 45329 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1718.93 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 1460.43 | 0 |  | 0 |  |  |  | 258.5 | 257.84 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203008A | 1711.76 | F21P1 UPW | 133 | P0 |  | Tablet | 44629 | 44635 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1711.76 | 1 | 0 | 0 | 0 | 0 | 1711.76 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401048A | 1707.74 | Tool Interconnection Project (Main Tool & Other Vendors) | 670 | P |  | YAV2CL2NT14FX90 BURNDY 2 AWG FLEX 15.140/ea 1514.00 CU COMPRESSION TERMINAL | 45311 | 45314 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1707.74 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 1707.74 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2403195A | 1704.87 | F21P1-0404_H_labor for 50 tools_MICU | 3891 | C |  | Blade and band saw, tool hookup team | 45370 | 45370 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1704.87 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 1704.87 | [6 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Commissioning | USC21C005 | USCSB2310115A | 1700 | F21P1 Chemical & WCCS package | 2776 | C |  | CDS Commission PE tubes requested by Albert Tseng | 45218 | 45218 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1700 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 1700 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408034A | 1696.33 | TSMC Fab 21 P1B Tool Hook Up | 4654 | C | -01 | Label kit shared for UPW and PCW system, item 3, tool hookup team | 45512 | 8/13/2024 8/14/2024 | -117.68 | 1814.01 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Some items quantity changed between PO approved and Amazon order placed | [13 empty] | 1696.33 | 1 | 0 | 235.36 | -235.36 | 0 | [70 empty] | 1150.42 |  | 310.55 | 235.36
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2405082A | 1695.75 | F21P1-0404_H_labor for 50 tools_MICU | 4102 | C |  | HK Electrical PM Luis Retiz's material request | 45426 | 45428 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 1695.75 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 1695.75 | [8 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402039A | 1690 | Tool Interconnection Project (Main Tool & Other Vendors) | 762 | P |  | Electrical cable pull for KESTL4 | 45329 | [7 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 1690 | 294 | 1396 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2403168A | 1688.82 | Tool Hookup Material (UPW&Chemical) | 3866 | C |  | HK Chemical PVDF Materials Pipe | 45366 | 45366 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 1688.82 | 0 | 1688.82 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2401077A | 1683.6 | F21P1-0423_H_T&M Hardware_MICU | 3266 | C | -01 | Plastic_第四批短期需求用料[MIC代採購_T&M] | 2024/1/12 2024/2/2 | 2024/1/17 2024/2/2 |  | 1825.2 |  | V |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | Revision to replace with Stainless Steel Hose Connectors |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1683.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 1067.76 |  |  |  | 615.84 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405054A | 1680 | Tool Interconnection Project (Main Tool & Other Vendors) | 1095 | P |  | 4/10/2024 Scaffolding for KCOXN7 Scaffold Tag 111166 | 45427 | 45429 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 1680 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 1680 |  |  |  |  | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111055A | 1672.3 | F21P1 UPW | 56 | P0 |  | Metal 3 drawer filing cabinets | 44524 | 44544 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 1672.3 | 1 | 0 | 0 | 0 | 0 | 1672.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204009A | 1672.2 | F21P1 UPW | 156 | P0 |  | Sceptre 24IN & 7IN2 | 44673 | 44725 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1672.2 | 1 | 0 | 0 | 0 | 0 | 1672.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403113A | 1672 | Tool Interconnection Project (Main Tool & Other Vendors) | 929 | P |  | Manpower Pay for CCE on 2.28.2024 for Tool ID KESRT2 | 45377 | 45377 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 1672 | 0 | 1672 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2405087A | 1664.55 | F21P1 WWT package (Installation and 2 batch tanks) | 4107 | C |  | WWT B side Drain label - batch 2 | 45427 | 45427 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1664.55 | 0 | 1664.55 | 1664.55 | [56 empty] | 0 | [14 empty] | 1664.55 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Steel | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2309095A | 1663 | WWT Change Order (Piping) | 2568 | C |  | WWT (118) Tank Crossover Platform Brackets | 45185 | 45191 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1663 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 1663 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2402081A | 1662.96 | Tool Interconnection Project (Main Tool & Other Vendors) | 791 | P |  | Manpower Pay for Tool ID's KEMGT1 and KESRT5 for RS Payroll | 45344 | 45448 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1662.96 | 5760.87 | -4097.91 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC24C006 | USCSB2404113A | 1653.08 | WWT B side Project | 4098 | C |  | Megaunion 220V-400V變壓器 | 45397 | 45397 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1653.08 | 0 | 1653.08 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403194A | 1650 | F21P1-0404_H_labor for 50 tools_MICU | 3890 | C |  | Knockout Tool Kit-New PR for Power system | 45370 | 45370 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1499.99 | 0.90908 | 150.01 | 0 | 150.01 | 0 | 1499.99 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2307117A | 1650 | F21P1 Chemical & WCCS package | 2281 | C |  | Welder equipment (pipe saw) for Chemical welding. | 45133 | 45133 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 1650 | 0 | 1650 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1650 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405055A | 1647.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1096 | P |  | PFA-T2-030-500 500' COIL 1/8 X .030 TUBE | 45427 | 45427 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 1647.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 1647.6 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2308016A | 1646.57 | Tool Interconnection Project (Main Tool & Module) | 366 | P | -01 | 16A180 Circular Chart Recorder: Pressure, 0 to 200 psi, For 4 in Chart Size, 1 or 7 Day DICKSON PW474 Country of Origin USA | 2023/8/22 2023/9/5 | 2023/8/22 2023/9/5 | 50.85 | 1595.72 | V |  |  |  | WW Grainger Inc | PR Approved | PO Approved | R1:Correct charts were ordered. Original were picked up at the store but new once were shipped $43.92 tax $10.25, extra charge |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1592.4 | 0.9671 | 54.17 | 0 | 54.17 | 0 | [40 empty] | 0 | 1465.92 | 0 | 0 |  | 0 | 0 | 0 | 0 | 126.48 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC22C012 | USCSB2403032A | 1645 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3741 | C |  | UPW-train B valves from ORGANO | 45356 | 45358 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1645 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1645 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | Main Contract Scope | UPW | UPW | Electrical | QAQC | USC21C003 | USCSB2303051A | 1640 | F21P1 UPW | 1793 | C |  | TSMC F21P1 WRC UPW Special Inspections | 44999 | 45007 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1640 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 820 |  |  |  | 820 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2404161A | 1639.95 | WWT Change Order (Piping) | 4144 | C |  | WWT blower GIP gasket purchase | 45402 | 45401 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 1639.95 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 1639.95 | 245.9925 |  |  |  | 245.9925 |  |  |  | 245.9925 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202009A | 1639.11 | F21P1 UPW | 118 | P0 |  | Autodesk AECC License | 44604 | 44609 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1639.11 | 1 | 0 | 0 | 0 | 0 | 1639.11 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402079A | 1635.28 | F21P1 WWT package (Installation and 2 batch tanks) | 3521 | C |  | WWT SUS Pipes_20240207 (A Side) | 45330 | 45331 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1635.28 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 1635.28 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111053A | 1631.36 | F21P1 UPW | 54 | P0 |  | Office Chairs | 44523 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 1631.36 | 1 | 0 | 0 | 0 | 0 | 1631.36 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207011A | 1628.98 | F21P1 UPW | 191 | P0 |  | Dell Laptop | 44771 | 44784 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1628.98 | 1 | 0 | 0 | 0 | 0 | 1628.98 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402059A | 1628.51 | Tool Interconnection Project (Main Tool & Other Vendors) | 777 | P |  | TB 2941NM | 45335 | 45337 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1628.51 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 1628.51 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206009A | 1628.4 | F21P1 UPW | 176 | P0 |  | Home Office Ergo black mesh chairs for subs trailers | 44722 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1628.4 | 1 | 0 | 0 | 0 | 0 | 1628.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206006A | 1628.4 | F21P1 UPW | 174 | P0 |  | Ergo black mesh back office chairs for sub trailers | 44722 | 44736 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1628.4 | 1 | 0 | 0 | 0 | 0 | 1628.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208001A | 1628.4 | F21P1 UPW | 202 | P0 |  | Black mesh ergonomic office desk chairs | 44775 | 44784 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1628.4 | 1 | 0 | 0 | 0 | 0 | 1628.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401062A | 1619.6 | F21P1-0404_H_labor for 50 tools_MICU | 3251 | C |  | Locknut for power trade jeryih and third | 45302 | 45306 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1619.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 1619.6 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403005A | 1616.73 | F21P1 Chemical & WCCS package | 3713 | C |  | CDS 2" OD cush clamps EG | 45352 | 45356 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1616.7 | 0.99998 | 0.03 | 0 | 0.03 | 0 | [52 empty] | 0 | 0 | 1616.7 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C007 | USCSB2308073A | 1615 | F21P1 VOC package （Installation ) | 2371 | C |  | F21 P1 VOC 2 k-type wire order | 45153 | 45154 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1615 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 1615 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Civil | M+L | USC21C009 | USCSB2406136A | 1604 | F21P1 WWT package (Installation and 2 batch tanks) | 4375 | C |  | sand,prep,expoxy and yellow safety paint at one house keeping pad. | 45470 | 45472 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 1604 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 1604 |  |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203024A | 1602.72 | F21P1 UPW | 144 | P0 |  | 55 inch Zen Computer desk | 44650 | 44650 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1602.72 | 1 | 0 | 0 | 0 | 0 | 1602.72 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Site Expense |  |  | Others |  |  | USC23B002 | USC2308005A | 1600 | Tool Interconnection Project (Main Tool & Module) | 355 | P |  | Electric Scissor Lift, 19' Micro - Rent. Renting Lifts for cable pull, mechanical, and 8395 routing. | 45141 | 45154 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1600 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1600 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403150A | 1600 | F21P1-0404_H_labor for 50 tools_MICU | 3850 | C |  | Cable ties for HK Power trade | 45365 | 45366 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1600 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 1600 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207008A | 1599.58 | F21P1 UPW | 188 | P0 |  | 24in& 27in Monitor, Keyboard and Mouse | 44771 | 44784 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1599.58 | 1 | 0 | 0 | 0 | 0 | 1599.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Equipment | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207010A | 1596.2 | F21P1 UPW | 190 | P0 |  | Pallet Trucks, 2500KG,1220mm long forks,牙叉內 220mm,H-6710 | 44771 | 44798 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Shannon Pulcifer | Yi En Wong | [7 empty] | 1596.2 | 1 | 0 | 0 | 0 | 0 | 1596.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Southland | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C007 | USCSB2212022A | 1595 | F21P1 VOC package （Installation ) | 1595 | C |  | 2 months rental-Light tower | 44908 | 44909 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1595 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 1595 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2312143A | 1588.1 | F21P1-0404_H_labor for 50 tools_MICU | 3132 | C |  | 3M Chemical Sorbent Pad for UPW System, Tool hookup team | 45279 | 45280 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1175.66 | 0.74029 | 412.44 | 0 | 412.44 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 618.66 |  | 557 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | MIC - Material | Material |  |  | Others |  |  | USC22C016 | USCSB2301057A | 1586.56 | Asahi Valve and Positioner from Harrington |  | C |  | Gasket from Harrington | 44954 | 44957 | [23 empty] | 1586.56 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 1586.56 | [11 empty] | 0 |  | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Site Expense | USC21C011 | USCSB2312064A | 1583.25 | F21 TMAH System | 3056 | C |  | WWT_Testing tool | 45269 | 45271 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1583.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1583.25 |  | 0 |  |  |  |  | 237.4875 |  |  |  | 237.4875 |  |  |  | 237.49 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C006 | USCSB2312118A | 1582.89 | F21P1 Module Tool Interconnection EPI | 2969 | C |  | EPI: KCEPS1: COND CLAMPS, BUSHINGS, & CONNECTORS | 45276 | [7 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1: canceled order | [13 empty] | 1582.89 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 1582.89 | [12 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402095A | 1579.7 | F21P1 Chemical & WCCS package | 3535 | C |  | CDS HPM Punch materials | 45332 | 45337 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1579.7 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 1579.7 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2305016A | 1575.47 | Tool Interconnection Project (Main Tool & Module) | 283 | P |  | TOOL: KPE601-S QTY. (2) MSR-FSR ANALYTICAL TESTING &QAQC TESTS | 45077 | 45140 | [6 empty] | MSR FSR LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1575.47 | 0 | 1575.47 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404213A | 1564.04 | WWT B side Project | 3964 | C |  | WWT Fittings_ZeWei_20240426 (B Side) | 45412 | [7 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 1395.26 | 0.89209 | 168.78 | 0 | 168.78 | 153.4786 | [54 empty] | 0 |  | 0 | [5 empty] | 1395.26 | [8 empty] | 153.4786 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206002A | 1563.3 | F21P1 UPW | 170 | P0 |  | Office Ergonomic black mesh chairs for construction sub trailers | 44722 | 44736 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1563.3 | 1 | 0 | 0 | 0 | 0 | 1563.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206001A | 1563.3 | F21P1 UPW | 169 | P0 |  | Office Ergonomic black mesh chairs for construction sub trailers | 44722 | 44736 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1563.3 | 1 | 0 | 0 | 0 | 0 | 1563.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403064A | 1560 | F21P1-0404_H_labor for 50 tools_MICU | 3769 | C |  | Cable ties for HK PCW trade | 45357 | 45358 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1560 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 1560 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407079A | 1552.09 | TSMC Fab 21 P1B Tool Hook Up | 4495 | C |  | For welding machine extension cord, and office supplies, tool hookup team | 2024/7/14 2024/10/3 | 2024/7/15 2024/10/3 | -198.14 | 1750.23 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approving | PO R1: Per purchaning team request, amend to the final amount. | [13 empty] | 1552.09 | 1 | 0 | 0 | 0 | 0 | 1552.09 | [72 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402054A | 1552 | Tool Interconnection Project (Main Tool & Other Vendors) | 772 | P |  | KEMEL8 Cable Pull: - L30 - L30 Cable Pull, - L30 - L20 Cable Pull, - Total ~20 Cables | 45330 | 45330 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1552 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 1552 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201016A | 1550.4 | F21P1 UPW | 110 | P0 |  | Office Chairs | 44586 | 44600 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | James Baginskis | Yi En Wong | [7 empty] | 1550.4 | 1 | 0 | 0 | 0 | 0 | 1550.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2407166A | 1550 | F21P1 Module Tool Interconnection CVD | 4589 | C |  | CVD KCSCN2 Erect?scaffold to install pipe. Gather and transport materials from laydown yard to the loading deck. | 45503 | 45507 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 1550 | 1 | 0 | 0 | 0 | [71 empty] | 1550 |  |  | -
Base-Build | Chemical | Material | 0 | 0 | Chemical | Electrical | Material | USC21C009 | USCSB2312116B | 1550 | F21P1 WWT package (Installation and 2 batch tanks) | 3107 | C |  | CDS CED MIC A side 2 of 2 per Paul | 45276 | 45293 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1550 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 800 | 750 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2407169A | 1547.55 | F21P1-0404_H_Hallway plate install_MICU | 4592 | C |  | Mobile shelving for foundation | 45503 | 45505 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 1546.13 | 0.99908 | 1.42 | 0 | 1.42 | [71 empty] | 1546.13 |  |  | -
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2311065A | 1543.2 | F21P1 AMAT Interconnection | 2920 | C |  | Change Order total for KCENA1 | 45245 | 45246 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1543.2 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 1543.2 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2309150A | 1543.05 | F21P1 UPW | 2621 | C |  | UPW sight glass PVC-train B | 45192 | 45195 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1543.05 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 1543.05 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C006 | USCSB2407172A | 1540 | WWT B side Project | 4595 | C |  | WWT - P-780 AB blockage fix | 45504 | 45517 | [6 empty] | Phoenix Pumps, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1540 | 0 | 1540 | [74 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402254A | 1532 | F21P1 WWT package (Installation and 2 batch tanks) | 3680 | C |  | WWT materials-1 | 45349 | 45350 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 780 | 0.50914 | 752 | 0 | 752 | 1532 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 229.8 |  |  |  | 229.8 |  |  | 780 | 229.8 |  | 1532 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408038A | 1524.75 | TSMC Fab 21 P1B Tool Hook Up | 4630 | C |  | Pallet Truck for HK MIMO | 2024/8/9 2024/8/10 | 45516 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | PR R1:To inclide Shipping & handling | [13 empty] | 0 | 0 | 1524.75 | 0 | 1524.75 | [74 empty] | -
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208017A | 1520.37 | F21P1 UPW | 216 | P0 |  | Samsung 75 inch color tv for conference room 1, Nest security camers | 44799 | 44810 | [6 empty] | Costco Wholesale Corporation | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1520.37 | 1 | 0 | 0 | 0 | 0 | 1520.37 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Pipeline | Material |  |  | Water Line | Civil | M+L | USC21C010 | USCSB2309003A | 1520 | tsmc AZ sewer and water pipeline installation | 2481 | C |  | Modify Handrail Base Plates on Mezz 2 and 3 | 45170 | 45197 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1520 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 1520 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311068A | 1516.25 | Tool Interconnection Project (Main Tool & Module) | 536 | P |  | FLEX LT3UAGRY: 3 UL LIQ-TITE, PER 100 | 45253 | 45286 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1516.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 1516.25 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311069A | 1516.25 | Tool Interconnection Project (Main Tool & Module) | 537 | P |  | FLEX LT3UAGRY: 3 UL LIQ-TITE, PER 100 | 45253 | 45287 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1516.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 1516.25 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209011A | 1516.06 | F21P1 Chemical & WCCS package | 236 | P0 |  | Revu License | 44825 | 44826 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1516.06 | 1 | 0 | 0 | 0 | 0 | 1516.06 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407085A | 1515 | TSMC Fab 21 P1B Tool Hook Up | 4501 | C |  | For Gas trade TCBC105 刀刃 | 45489 | 45488 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved | [14 empty] | 1515 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 1515 | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Commissioning | USC21C009 | USCSB2402150A | 1510.55 | F21P1 WWT package (Installation and 2 batch tanks) | 3583 | C |  | WWT 7 Chemical - 2 | 45337 | 2024/3/5 2024/7/29 | 387.85 | 1122.7 |  |  |  |  | Midland Scientific, Inc. | PR Approved | PO Approved | R1: Add Freight fee per purchasing team Yikang. |  | Ta Wei Wang | [11 empty] | 1510.55 | 1 | 0 | 0 | 0 | 291.902 | 1510.55 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 291.902 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402034A | 1510.5 | F21P1-0404_H_labor for 50 tools_MICU | 3477 | C |  | UPG MALE SLEEVE, UPG COUPLING BODY, | 45325 | 45327 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1510.5 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 319 |  | 0 |  | 1191.5 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310188A | 1506.48 | F21P1-0404_H_labor for 50 tools_MICU | 2840 | C | -01 | Harting crimpers and extraction for Third | 45227 | 2023/11/2 2023/11/4 | [6 empty] | Mouser Electronics | PR Approved | PO Approved | R1: Ship-to Address Change |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1506.48 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 | 1506.48 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309096A | 1505.97 | F21P1-0404_H_labor for 50 tools_MICU | 2569 | C |  | Hand Tool - Mao Hsun | 45185 | 45198 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1505.97 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 1505.97 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405034A | 1503 | Tool Interconnection Project (Main Tool & Other Vendors) | 1092 | P |  | KPE601-S Cable Rerouting Labor | 45422 | 45422 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 1503 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 1503 | [10 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Civil | Labor | USC21C004 | USCSB2305117A | 1500 | F21P1 WWT package （USA EQ-FRP tank) | 2033 | C |  | Dosing Box Installation | 2023/5/31 2023/6/3 | 45079 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1500 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1500 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406002A | 1489.83 | Tool Interconnection Project (Main Tool & Other Vendors) | 1122 | P |  | KDMRS4- DNS SCREEN INTERCONNECTS- 5/1/2024 | 45450 | 45454 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 1489.83 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 1489.83 | [6 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407031A | 1489.62 | F21P1-0404_H_labor for 50 tools_MICU | 4430 | C |  | Tools for HK PCW for 100 tools | 45477 | 45477 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1261.9 | 0.84713 | 227.72 | 0 | 227.72 | 0 | 1261.9 | [72 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408150A | 1488 | TSMC Fab 21 P1B Tool Hook Up | 4765 | C |  | Extension Cords Request for HK PCW, PPL, Power, EXH | 45534 | 45540 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1488 | 1 | 0 | 1488 | -1488 | 0 | [73 empty] | 1488
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402156A | 1478 | F21P1-0404_H_labor for 50 tools_MICU | 3588 | C |  | office supplies for tool hookup department | 45338 | 45342 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1383.33 | 0.93595 | 94.67 | 0 | 94.67 | 0 | 1383.33 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C059 | USCSB2405025A | 1476.81 | F21P1 Foundation T&M | 4036 | C |  | 3 in 1 project Orbum 1CPDH WP 1GPLSTC HORZ DEV CVR | 45416 | 45421 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1476.81 | 1 | 0 | 1476.81 | -1476.81 | 0 | [56 empty] | 0 | [16 empty] | 1476.81 |  |  | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2402108A | 1473.34 | F21P1-0404_H_labor for 50 tools_MICU | 3547 | C |  | lock, chain, and hammer, tool hook up team shared for all systems' | 45333 | 45342 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1473.34 | 1 | 0 | 0 | 0 | 0 | 1473.34 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402036A | 1472.2 | F21P1-0404_H_labor for 50 tools_MICU | 3479 | C |  | Cleanroom paper shared by all hk systems | 45325 | 45327 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 736.1 | 0.5 | 736.1 | 0 | 736.1 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 736.1 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2312202A | 1472.2 | F21P1-0404_H_labor for 50 tools_MICU | 3188 | C |  | HK cleanroom printing paper shared by all system | 45290 | 45294 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1472.2 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 1472.2 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2403208A | 1472 | F21P1-0404_H_labor for 50 tools_MICU | 3903 | C |  | Additional 220 V outlets to complete the electrical requirements | 45372 | 45372 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1350 | 0.91712 | 122 | 0 | 122 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1350 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2404126A | 1464 | F21P1 Module Tool Interconnection CVD | 4111 | C |  | Reduction Tees | 45398 | 45399 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1464 | 0 | 1464 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2209003A | 1456 | F21P1 UPW | 228 | P0 |  | HDX tan folding tables 8ft, Lifetime tan folding tables 8 ft | 44805 | 44810 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1456 | 1 | 0 | 0 | 0 | 0 | 1456 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402240A | 1455.6 | F21P1 WWT package (Installation and 2 batch tanks) | 3666 | C |  | WWT Gasket_20240223 (A Side) | 45346 | 45350 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1455.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1455.6 |  | 0 |  |  |  |  | 218.34 |  |  |  | 218.34 |  |  |  | 218.34 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C059 | USCSB2405067A | 1454.42 | F21P1 Foundation T&M | 4087 | C |  | additional 3 in 1 project material HK Power system | 45423 | 45429 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1454.42 | 1 | 0 | 1454.42 | -1454.42 | 0 | [56 empty] | 0 | [16 empty] | 1454.42 |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2303028A | 1450 | F21P1 Module Tool Interconnection ETC1-3 | 1770 | C |  | QR-lab adaptor | 44992 | 45001 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1450 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 1450 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303043A | 1450 | F21P1 Module Tool Interconnection DIF1-2 | 1785 | C |  | DIF pliot run machine 1/2" gas line | 44994 | 44998 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1450 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 1450 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401260A | 1447 | F21P1-0404_H_labor for 50 tools_MICU | 3440 | C | -01 | Consumables for HK exhaust trade | 45322 | 2024/1/31 2024/2/1 | [5 empty] | V | U-Line Corporation | PR Approved | PO Approved | R1: Payment Term changed from NET 30 to Credit Card as the Uline account reaches credit limit |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1447 | 1 | 0 | 0 | 0 | 0 | 1447 | [47 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402152A | 1444 | F21P1-0404_H_labor for 50 tools_MICU | 3585 | C |  | Nut order for Luis | 45338 | 45338 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1444 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 1444 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2404121A | 1437.77 | F21P1 UPW | 4106 | C |  | SS Clamps to repair 14" SS Leaks | 45398 | 45401 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 1437.77 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 1437.77 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2404220A | 1433.95 | F21P1 WWT package (Installation and 2 batch tanks) | 3971 | C |  | WWT Clamps_20240429 (A Side) | 45412 | 45412 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 1433.95 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 1433.95 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409006A | 1433.38 | Tool Interconnection Project (Main Tool & Other Vendors) | 1213 | P |  | COND EMT3; EMT; PER HUNDRED | 45540 | 45541 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1433.38 | 1433.38 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404092A | 1428.39 | Tool Interconnection Project (Main Tool & Other Vendors) | 1044 | P |  | 65181 1/2"IDX3/4"OD KFLEX TUBING 50 | 45406 | 45412 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 1428.38 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 1428.38 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2404043A | 1427.19 | Tool Interconnection Project (Main Tool & Other Vendors) | 990 | P |  | Manpower Pay for RS Payroll for Tool ID: KETRTE for Laborer Mark Murray Timecards for 2.28 and 2.29.2024 | 45391 | 45425 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1427.19 | 0 | 1427.19 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403100A | 1424.69 | Tool Interconnection Project (Main Tool & Other Vendors) | 916 | P |  | Manpower Pay for Tool ID: KETRT9 for CGS for Installer Mark Murray | 45373 | 45376 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 1424.69 | 0 | 1424.69 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2401040A | 1416.5 | F21P1-0404_H_labor for 50 tools_MICU | 3230 | C |  | office supplies for tool hookup department | 45298 | 45299 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1122.7 | 0.79259 | 293.8 | 0 | 293.8 | 0 | 1122.7 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310043A | 1416 | Tool Interconnection Project (Main Tool & Module) | 461 | P |  | Manpower | 45218 | 45225 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | Initial amount revised from $300 to $1416. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1416 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1416 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401026A | 1416 | Tool Interconnection Project (Main Tool & Other Vendors) | 649 | P |  | LABOR | 45304 | 45308 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1416 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1416 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312005A | 1416 | Tool Interconnection Project (Main Tool & Module) | 557 | P |  | Cables need to be swapped from the conduit they were routed through due to vendor error. KDSNB1 | 45261 | 45264 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1416 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1416 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2401154A | 1414 | F21P1 WWT package (Installation and 2 batch tanks) | 3339 | C |  | WWT tools for MU | 45310 | 45310 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1414 | 1 | 0 | 0 | 0 | 0 | 1414 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USC2404116A | 1413.81 | F21P1 AMAT Interconnection | 1058 | P |  | 8,10,12 1c color code wire | 45412 | 45413 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1413.81 | 1 | 0 | 1413.81 | -1413.81 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | 1413.81 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2307094A | 1408.4 | F21P1 Chemical & WCCS package | 2260 | C |  | CPVC purchase | 45126 | 45126 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1408.4 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 1408.4 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2311125A | 1404.6 | F21P1 Chemical & WCCS package | 2976 | C |  | CDS Nippon Pillar connectors used for PFA tie in on CDU and Tank of B side. | 45259 | 45260 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1404.6 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 728.97 | 0 |  | 675.63 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310087A | 1400.57 | F21P1-0404_H_labor for 50 tools_MICU | 2748 | C |  | Hansen LABEL okland | 45212 | 45218 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1394.33 | 0.99554 | 6.24 | 0 | 6.24 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 1394.33 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2310184A | 1400 | F21P1 Chemical & WCCS package | 2836 | C |  | CDS Welder rental for Chemical welding. | 45227 | 45229 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1400 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 1400 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Site Expense | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2403069A | 1400 | F21P1 Chemical & WCCS package | 3774 | C |  | CDS Welder rental for Chemical welding.( RENTAL FROM 1-29-24 TO 2-26-24) | 45358 | 45362 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 1400 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 1400 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405051A | 1397.28 | Tool Interconnection Project (Main Tool & Other Vendors) | 1093 | P |  | Manpower Pay to CGS GLOBAL for Tool IDs: KESRT1 AND KESRT2 for Cable Pull and 8395 Rule on Time Card from 3.20.2024 for Mario Diaz, Eloy Pacheco, Miguek Argueta, and Shamarie Murphy | 45426 | 45427 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1397.28 | 0 | 1397.28 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112030A | 1395.75 | F21P1 UPW | 93 | P0 |  | AutoCAD License | 44553 | 44558 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang |  |  | Matt |  |  |  |  | 1395.75 | 1 | 0 | 0 | 0 | 0 | 1395.75 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2403202A | 1391.96 | F21P1 UPW | 3898 | C |  | 8800lb Dolly for MIMO - Move In/Move Out Team | 45371 | 45379 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1160.08 | 0.83341 | 231.88 | 0 | 231.88 | 0 | 1160.08 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2403019A | 1391.77 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3728 | C |  | Product/DOT 6502PZ PULL LINE DSPNG PAIL,240 FT STEEL FISHTAPE,CADDY CAT32HP 2IN CAT5 CABLE CLIP | 45353 | 45355 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 103.96 | 0.074696 | 1287.81 | 0 | 1287.81 | 0 | [52 empty] | 0 | 0 | 0 |  | 103.96 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401009A | 1385.55 | Tool Interconnection Project (Main Tool & Other Vendors) | 633 | P |  | KPD801-T Labor | 45301 | 45308 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1385.55 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 1385.55 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209012A | 1384.5 | F21P1 Chemical & WCCS package | 237 | P0 |  | 27in Monitor | 44825 | 44826 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1384.5 | 1 | 0 | 0 | 0 | 0 | 1384.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403245A | 1381.51 | F21P1-0404_H_labor for 50 tools_MICU | 3938 | C | -01 | Locks and vacuum filter for HK Exhaust trade | 45377 | 2024/3/27 2024/4/3 | -2189.62 | 3571.13 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Returning budget per purchasing request |  | Ta Wei Wang | [11 empty] | 1381.51 | 1 | 0 | 0 | 0 | 0 | 1381.51 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403164A | 1380.67 | F21P1-0404_H_labor for 50 tools_MICU | 3862 | C |  | M610 PRINTER - Handheld Label Maker for HK Power system | 45366 | 45370 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1375.33 | 0.99613 | 5.34 | 0 | 5.34 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 1375.33 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304032A | 1379.84 | F21P1 WWT package (Installation and 2 batch tanks) | 1872 | C |  | 780/120 Header Bolts | 45031 | 45034 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1379.84 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 1379.84 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C025 | USCSB2410036A | 1371.03 | Tool Hookup Material (UPW&Chemical) | 4979 | C |  | Urgent 23 DP Fillers_AMHS | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1371.03 | 0 | 1371.03 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406133A | 1370.06 | F21P1-0404_H_labor for 50 tools_MICU | 4372 | C |  | Amazon Loto PR for Power Luis Retiz for 100 LOTO for 7 tools | 45469 | 45469 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1218.51 | 0.88938 | 151.55 | 0 | 151.55 | 0 | 1218.51 | [72 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208007A | 1368.15 | F21P1 UPW | 208 | P0 |  | Zenstyle Computer Desk black 55 inch | 44785 | 44798 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1368.15 | 1 | 0 | 0 | 0 | 0 | 1368.15 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306048A | 1365 | Tool Interconnection Project (Main Tool & Module) | 332 | P |  | KPSP01 - MECHANICAL LABOR | 45100 | 45113 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1365 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1365 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306056A | 1365 | Tool Interconnection Project (Main Tool & Module) | 337 | P |  | MECHANICAL LABOR | 45106 | 45113 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1365 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1365 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2305003A | 1364.2 | Tool Interconnection Project (Main Tool & Module) | 272 | P |  | CVD2 Tool interconnection materials | 45063 | 45064 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1364.2 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 1364.2 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409018A | 1362.59 | TSMC Fab 21 P1B Tool Hook Up | 4787 | C |  | Extension Cords Request for HK PCW, PPL, Power, EXH | 45540 | 45539 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 1176.56 | 0.86347 | 186.03 | 0 | 186.03 | 0 | 1176.56 | [72 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401052A | 1360.14 | Tool Interconnection Project (Main Tool & Other Vendors) | 674 | P |  | KECOT5 MANPOWER PAY FOR E-OPS | 45311 | 45314 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1360.14 | 0 | 1360.14 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2301051A | 1360 | F21P1 UPW | 1668 | C |  | T1021C handrail replacement | 44953 | 44953 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1360 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 1360 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401080A | 1359.45 | F21P1 Chemical & WCCS package | 3269 | C |  | CDS Unions to replace all Union Box accessories of Lorry to HPM IPA and PFA to SUS. | 45303 | 45303 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1359.45 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1359.45 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2309004A | 1350 | F21P1 WWT package (Installation and 2 batch tanks) | 2482 | C |  | WWT Machine PP D63 12” PN10 pipe to PN6 | 45170 | 45175 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 1350 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312029A | 1350 | F21P1-0404_H_labor for 50 tools_MICU | 3022 | C |  | Fork terminal for Third. Top 100 tools | 45266 | 45271 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1350 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | MMI | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C004 | USCSB2212012A | 1350 | F21P1 WWT package （USA EQ-FRP tank) | 1585 | C |  | Flange Gaskets | 44902 | 44902 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 1350 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402260A | 1350 | F21P1-0404_H_labor for 50 tools_MICU | 3686 | C |  | Fork terminal for HK Power trade | 45350 | 45352 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 1350 | [6 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2311087A | 1350 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2939 | C |  | Bay Alarm Company CCTV System Relocation | 45247 | 45247 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 675 |  | 0 | [14 empty] | 0 | 675 | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408014A | 1350 | TSMC Fab 21 P1B Tool Hook Up | 4610 | C |  | Cleaning services for HK 3-plex | 45507 | 45517 | [6 empty] | Viking Facility Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1350 | 0 | 1350 | [74 empty] | -
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2402242A | 1349.61 | F21P1 AMAT Interconnection | 3668 | C |  | cable tray | 45346 | 45370 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1349.61 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1349.61 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402061A | 1347.9 | F21P1-0404_H_labor for 50 tools_MICU | 3503 | C |  | materials for all systems, tool hookup team 300 tools | 45329 | 45332 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1225.4 | 0.90912 | 122.5 | 0 | 122.5 | 0 | 1225.4 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2307033A | 1345.6 | F21P1 UPW | 2203 | C |  | UPW enclosure flange | 45118 | 45119 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1345.6 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 1345.6 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310158A | 1343.75 | F21P1-0404_H_labor for 50 tools_MICU | 2813 | C | -01 | QC stickers shared by different trades | 45223 | 2023/10/26 2023/11/1 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved | R1:Trade Term Correction Per Request |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 1343.75 | 0 | 1343.75 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC23C002 | USCSB2309060A | 1342 | F21P1-0404_H_Hallway plate install_MICU | 2535 | C |  | 50pcs small iron plates to AMHS | 45182 | 45189 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1342 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 1342 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403156A | 1339 | F21P1 Chemical & WCCS package | 3855 | C |  | CDS clamps for the T supports | 45366 | 45366 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1339 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1339 |  |  | 1339 | [5 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402046A | 1336.94 | Tool Interconnection Project (Main Tool & Other Vendors) | 766 | P |  | KETRT8 MANPOWER PAY FOR SAN TAN FIRE | 45329 | 45332 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1336.94 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 1336.94 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203023A | 1335.6 | F21P1 UPW | 143 | P0 |  | Zenstyle computer desk 55 inch. | 44650 | 44650 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1335.6 | 1 | 0 | 0 | 0 | 0 | 1335.6 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2309160A | 1334 | F21P1 UPW | 2630 | C |  | TW-UPW-Gaskets | 45195 | 45201 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1334 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 1334 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202010A | 1332.08 | F21P1 UPW | 119 | P0 |  | Air Quality Monitor | 44604 | 44617 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1332.08 | 1 | 0 | 0 | 0 | 0 | 1332.08 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24B002 | USC2410002A | 1331.88 | Tool Interconnection Project (Main Tool & Other Vendors) | 1264 | P |  | Quick-Clamp High-Vacuum Fitting, Wing Nut Clamp for 1" Tube OD | 45567 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1331.88 | 0 | 1331.88 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C006 | USCSB2312187A | 1331.45 | F21P1 Slurry package | 3174 | C |  | CDS Snoop and 1/2 Tee's | 45288 | 45293 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1331.45 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1331.45 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C053 | USCSB2401022A | 1331.2 | AMAT Interconnection (TSMC) | 3213 | C |  | Change Order for KCEPA1: power cables, PVC coated clamps, Tray dividers | 45296 | 45300 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 1331.2 | 0 | 1331.2 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207014A | 1330.13 | F21P1 UPW | 194 | P0 |  | 24in& 27in Monitor | 44771 | 44784 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1330.13 | 1 | 0 | 0 | 0 | 0 | 1330.13 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407048A | 1328.43 | F21P1-0404_H_labor for 50 tools_MICU | 4447 | C |  | Shelf for Plastic system, extension cord for welding machine | 2024/7/10 2024/9/26 | 2024/7/11 2024/9/26 | -145 | 1473.43 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: Per purchasing team request, this should change to the final amount. | [13 empty] | 1328.43 | 1 | 0 | 0 | 0 | 0 | 1328.43 | [72 empty] | - |  |  | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2308030A | 1327.4 | F21P1-0404_H_Hallway plate install_MICU | 2331 | C | -01 | Hard barricade bolt | 45143 | 2023/8/7 2023/8/8 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | R1:remark revised |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1327.4 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1327.4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201013A | 1324.8 | F21P1 UPW | 107 | P0 |  | Office Chairs | 44585 | 44600 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | James Baginskis | Yi En Wong | [7 empty] | 1324.8 | 1 | 0 | 0 | 0 | 0 | 1324.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2402153A | 1324.55 | F21P1 AMAT Interconnection | 3586 | C |  | Torque Wrench, Torque Wrench Set, Tamperproof tape | 45338 | 45342 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1324.55 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 1324.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401073A | 1319.26 | Tool Interconnection Project (Main Tool & Other Vendors) | 693 | P |  | KESRT2 MANPOWER PAY FOR RS PAYROLL | 45316 | 45322 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 965.6 | 0.73193 | 353.66 | 1697.12 | -1343.46 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 965.6 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303070A | 1317.58 | F21P1 WWT package (Installation and 2 batch tanks) | 1809 | C |  | Waterfall Bolts/Gaskets | 45001 | 45006 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1317.57 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [28 empty] | 0 |  |  |  | 1317.57 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2405003A | 1314.25 | F21P1 UPW | 3979 | C |  | BIM and Valves for MAU Bypass | 45413 | 45413 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 1314.25 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 1314.25 | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material |  |  | UPW | Mechanical | Material | USC24C008 | USCSB2407039A | 1313 | UPW B Side Project | 4438 | C |  | Valve Handles for B Area | 45482 | 45482 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved | [14 empty] | 1313 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 1313 |  |  | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403066A | 1311.3 | Tool Interconnection Project (Main Tool & Other Vendors) | 889 | P |  | 2CFY3 Strt Adapter,PFA, PTFE, ETF Manufacturer: PARGRIP Part Number: GAMS-1212 | 45366 | 45369 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1311.3 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1311.3 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402111A | 1311 | Tool Interconnection Project (Main Tool & Other Vendors) | 823 | P |  | Manpoer Pay for CGS for Tool ID's KEPOL7 and KEMGT1 | 45350 | 45376 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 1311 | 0 | 1311 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2308143A | 1310.1 | F21P1 Module Tool Interconnection CVD | 2438 | C |  | CVD2 Ball valve for interconnection KCANN1, KCANN3, KCANN4, KCANN7 | 45162 | 45163 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1310.1 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 1310.1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USC2112004A | 1309.6 | F21P1 Chemical & WCCS package | 72 | P |  | pressure regulating valve/Straight connector | 44533 | 44575 | [6 empty] | Flodraulic Group | PR Approved | PO Approved | NO CF/NO Vendor sheet | 100% delivery net 30 days | Yi En Wong | DAP MICU Phoenix Office | 1 year in operation or 1.5 years after delivery | Stephon Dean | Yi En Wong | N | 44588 | Henry |  | N | 5000 |  | 1309.6 | 1 | 0 | 0 | 0 | 0 | [5 empty] | 1309.6 | [22 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2308121A | 1301.75 | F21P1-0404_H_labor for 50 tools_MICU | 2418 | C |  | 15 Pound PVDF and PP Welding Rod Coil, 3mm,standard loose coil | 45157 | 45161 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1301.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 1301.75 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2303004A | 1300 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1746 | C |  | Block wall Repair | 44986 | 44999 | [6 empty] | Graylo Construction, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1300 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 1300 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2404083A | 1298.85 | F21P1 Module Tool Interconnection ETC1-3 | 3935 | C |  | WIRE 24WG 4C for MOULE CIP' UNITS | 45392 | 45456 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1298.85 | 1298.85 | 0 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312159A | 1296 | F21P1-0404_H_labor for 50 tools_MICU | 3148 | C |  | IDEAL 31601 1LB DUCT SEAL for power trade | 45281 | 45282 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1296 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 1296 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308018A | 1295.98 | F21P1 Chemical & WCCS package | 2320 | C | -01 | TGCM Duty Room items – white board and cabinets | 2023/8/4 2023/8/22 2024/3/8 | 2023/9/27 2024/3/8 | [6 empty] | Zoro Tools, Inc. | PR Approved | PO Approved | PR R1:Remove wardrobe locker item WO R1: Revise the amount to align with actual order |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1295.98 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1295.98 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405002A | 1292.9 | WWT B side Project | 3978 | C |  | WWT 2-1/2" & 4-5/8" Clamps (B Side)_20240429 | 45413 | 45413 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1292.9 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 1292.9 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407123A | 1290 | TSMC Fab 21 P1B Tool Hook Up | 4537 | C |  | welding label shared for all system, tool hookup team | 45493 | 45495 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1290 | 0 | 1290 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2303083A | 1289.86 | F21P1 Module Tool Interconnection DIF1-2 | 1820 | C |  | QR lab SWG adaptor | 45007 | 45008 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1289.86 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 1289.86 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2308017A | 1287 | Tool Interconnection Project (Main Tool & Module) | 367 | P |  | CR87P Supco Pressure 6" Chart 429.00 1,287.00 Recorder, 0-500PSI, LED, 110V | 45161 | 45167 | [6 empty] | MicroDAQ | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1287 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 1287 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2312069A | 1283.72 | F21P1-0423_H_T&M Hardware_MICU | 3061 | C |  | Tool hookup Plastic material, KRWRS6, KMOPA4-C | 45272 | 45274 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1283.72 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 806.8 | 0 | 476.92 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407102A | 1283.7 | TSMC Fab 21 P1B Tool Hook Up | 4517 | C |  | P1B Extension Ladder Request for HK Power Trade for 100 tools | 45490 | 45491 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1167 | 0.90909 | 116.7 | 0 | 116.7 | 0 | 1167 | [72 empty] | - |  |  | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2312137A | 1280 | F21P1 UPW | 3126 | C |  | UPW-ORGANO-flexible joints for ICW | 45279 | 45279 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1280 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1280 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402082A | 1265 | Tool Interconnection Project (Main Tool & Other Vendors) | 795 | P |  | Manpower Pay to CGS GLOBAL FOR TOOL ID: KESRT5 for Timecards on 2.15 and 2.17.2024 | 45344 | 45413 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1265 | 0 | 1265 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403100A | 1264.24 | F21P1 WWT package (Installation and 2 batch tanks) | 3802 | C |  | WWT PVC & PP Pipes_20240308 (A Side) | 45360 | 45362 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 1264.24 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1264.24 |  |  | 189.636 |  |  |  | 189.636 |  |  |  | 189.636 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2403022A | 1260 | F21P1 WWT package (Installation and 2 batch tanks) | 3731 | C |  | WWT - Replacement Coupling for P-350 AA/AB | 45353 | 45356 | [6 empty] | Phoenix Pumps, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1228.12 | 0.9747 | 31.88 | 0 | 31.88 | 36.8436 | 1228.12 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 36.8436
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2311052A | 1256.98 | Tool Interconnection Project (Main Tool & Module) | 524 | P |  | Armaflex 1-5/8 X 1/2 | 45248 | 45253 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1256.96 | 0.99998 | 0.02 | 0 | 0.02 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 1256.96 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C063 | USCSB2404119A | 1256.94 | F21P1-0423_H_T&M Hardware_MICU | 4104 | C |  | E2 Team_CV 三合一施作工具請MIC協助報價/採購 | 2024/4/16 2024/4/23 | 45404 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | PR R1:zero out first two items | [13 empty] | 1124.22 | 0.89441 | 132.72 | 0 | 132.72 | 0 | 1124.22 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403124A | 1254 | Tool Interconnection Project (Main Tool & Other Vendors) | 939 | P |  | Manpower Pay for CCE for Tool ID: KESTL2 | 45378 | 45379 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 1254 | 0 | 1254 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C060 | USCSB2404199A | 1250 | F21 CT Local Scrubber Interconnection | 3957 | C |  | PCA-CT: KCASA1, KCSCN2, KCOXA1, KCOXN8, KCOXN1-2, KCOXN5-6, KCSMA3, KCSCN3-4: WIRES | 45408 | 45413 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1250 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 1250 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2304071A | 1250 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1910 | C |  | Starlink upgrade at Glendale Warehouse | 45041 | 45044 | [6 empty] | GeoTech Enterprises LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1250 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 1250 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309039A | 1248 | Tool Interconnection Project (Main Tool & Module) | 428 | P |  | Four laborers for 8395 wiring and general mechanical labor for KPMU01 for the work that was completed on 09/29/2023. | 2023/9/27 2023/11/9 | 45240 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PR R1:the amount should be $1,248 instead of 400. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1248 | 0 | 1248 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111060A | 1247.81 | F21P1 UPW | 61 | P0 |  | Free standing refrigerator | 44524 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 1247.81 | 1 | 0 | 0 | 0 | 0 | 1247.81 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C025 | USCSB2310098A | 1246 | F21P1 Lam Interconnection | 2760 | C |  | Cable Tray Divider Supply | 45216 | 45218 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1246 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1246 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407037A | 1245 | F21P1-0404_H_labor for 50 tools_MICU | 4436 | C |  | B Side Power tower for HK Power for 100 tools | 45482 | 45483 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1245 | 1 | 0 | 0 | 0 | 0 | 1245 | [72 empty] | - |  |  | 0
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Material | USC24C005 | USCSB2407025A | 1238.15 | Chemical & WCCS B Side Project | 4424 | C |  | F21P1 B Side PFA - Nylon Line | 2024/7/3 2024/7/9 | 45484 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | PR R1:Add shipping & handling&10% buffer | [13 empty] | 1125.59 | 0.90909 | 112.56 | 0 | 112.56 | 0 | 1125.59 | [72 empty] | - |  |  | 0
Base-Build | UPW | Labor | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2404004A | 1237 | F21P1 UPW | 4001 | C |  | Temperature Indicator for Train B | 45384 | 45385 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1237 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1237 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2305033A | 1232.5 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1956 | C |  | KPAP01 S LIT 1 MMI | 45056 | 45159 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1232.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 1232.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2305032A | 1232.5 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1955 | C |  | KPAE01-S LIT 1 MMI | 45056 | 45159 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1232.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 1232.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403128A | 1230.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 943 | P |  | Manpower Pay for CCE for Tool ID: KEPOL2 | 45378 | 45379 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 1230.5 | 0 | 1230.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | MMI | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC21C005 | USCSB2308093A | 1228 | F21P1 Chemical & WCCS package | 2390 | C |  | L30 PDP Panel Move to clean room | 45155 | 45168 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1228 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1228 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408048A | 1227.78 | TSMC Fab 21 P1B Tool Hook Up | 4666 | C |  | pipe threading oil and cutting blade saw for HK PCW trade | 45514 | 45516 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 1078.16 | 0.87814 | 149.62 | 0 | 149.62 | 0 | 1078.16 | [72 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2307116A | 1224.85 | F21P1 WWT package (Installation and 2 batch tanks) | 2280 | C |  | WRC Bolt-PSS request (Double Order) | 45133 | 45133 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1224.84 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [36 empty] | 1224.84 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304014A | 1224.85 | F21P1 WWT package (Installation and 2 batch tanks) | 1855 | C |  | WRC Bolt-PSS request (100% paid by Jim) | 45023 | 45030 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1224.85 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 1224.85 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2305098A | 1224.7 | F21P1 UPW | 2019 | C |  | UPW sight glass | 45066 | 45079 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1224.7 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 1224.7 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401116A | 1218.75 | F21P1-0404_H_labor for 50 tools_MICU | 3303 | C |  | HK scope for welding training, Tool hookup team | 45308 | 45310 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 928.18 | 0.76158 | 290.57 | 0 | 290.57 | 0 | 928.18 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | Main Contract Scope | CDS | Chemical | Mechanical | Safety | USC21C005 | USCSB2308070A | 1218.08 | F21P1 Chemical & WCCS package | 2368 | C |  | Self-Retracting Lifeline for Chemical/TPC work. | 45150 | 45162 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 1218.08 | 0 | 1218.08 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312014A | 1217.11 | Tool Interconnection Project (Main Tool & Module) | 563 | P |  | workers for 3 days to install exhaust duct between L10 and LB1 (Robert Nelson) | 45262 | 45279 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 681.6 | 0.56002 | 535.51 | 0 | 535.51 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 681.6 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2212010A | 1216.4 | F21P1 WWT package (Installation and 2 batch tanks) | 1583 | C |  | WRC CCB camlocks | 44902 | 44909 | [6 empty] | CamlockDirect | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1216.4 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 1216.4 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404117A | 1216.08 | WWT B side Project | 4102 | C |  | WWT SUS 90Elbow_20240412 (B Side) | 45397 | 45397 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 1216.08 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 1216.08 | 182.412 |  |  |  | 182.412 |  |  |  | 182.412 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2308078A | 1216 | EBO21- Tool interconnection | 2375 | C |  | EBO: ZCOAT1 - Interconnection material Pedestal Clamps | 45153 | 45154 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1216 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 1216 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403080A | 1207 | F21P1-0404_H_labor for 50 tools_MICU | 3783 | C |  | Heavy duty clear trash bags for HK Power trades | 45358 | 45363 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1064.2 | 0.88169 | 142.8 | 0 | 142.8 | 0 | 1064.2 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403011A | 1207 | Tool Interconnection Project (Main Tool & Other Vendors) | 838 | P |  | KPI401-S Labor | 45356 | 45357 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1207 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1207 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | M+L | USC24C005 | USCSB2404134A | 1206.55 | Chemical & WCCS B Side Project | 4118 | C | -01 | CHEM_L30 SDS VMB/ piping supports 240415020001_ (QT04350562-1) | 45399 | 2024/4/17 2024/4/18 | -1386 | 2592.55 |  |  |  |  | Copper State Bolt & Nut Company | PR Approved | PO Approved | R1: Cancel Item No.2 as the spec cannot fulfill the requirements | [13 empty] | 1206.55 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 1206.55 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403014A | 1200 | Tool Interconnection Project (Main Tool & Other Vendors) | 841 | P |  | Welding of stainless steel MPT nipple 304 to 316 pipe x 8 | 45356 | 45358 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1200 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1200 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401033A | 1196 | F21P1-0404_H_labor for 50 tools_MICU | 3224 | C |  | HK Cable tie for Exhaust trade HL, Cleanroom tapes shared by all system | 45297 | 45300 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1196 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 1196 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2405062A | 1193.5 | F21P1-0404_H_labor for 50 tools_MICU | 4082 | C |  | Storage box for HK PPL trade for 100 tools | 45422 | 45425 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 1193.5 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 1193.5 | [10 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC24C006 | USCSB2404027A | 1193 | WWT B side Project | 4023 | C |  | WWT Center Ring 4x2_20240402 (B Side) | 45385 | 45387 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1193 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1193 |  |  | 178.95 |  |  |  | 178.95 |  |  |  | 178.95 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | DCR Scope | CDS | Chemical | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C005 | USCSB2310003A | 1190 | F21P1 Chemical & WCCS package | 2666 | C | -01 | VMB parts for Chemical team | 45202 | 2023/10/7 2023/10/11 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | PO R1:Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1190 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1190 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403027A | 1189.25 | F21P1 Chemical & WCCS package | 3736 | C |  | CDS 1/4" ball valve and snoop | 45353 | 45356 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1189.25 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1189.25 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403128A | 1182.55 | F21P1 Chemical & WCCS package | 3830 | C |  | CDS VCR, etc | 45364 | 45367 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1182.55 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1182.55 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC23C042 | USCSB2408165A | 1181.96 | F21P1 Chemical Safety Cabinet Installation | 4770 | C |  | REVISED VARTEAGA Invoice No. MICU-010 @ T^0M WORK_CDS L10_L20_L30 Cleanroom CPVC_SS_PFA Chemical System Tubes_ Batch 3/3 | 45535 | 45546 | [6 empty] | CRG International | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1181.96 | 1181.96 | 0 | 0 | [73 empty] | -
Base-Build | Slurry | Material | Main Contract Scope | SDS | Chemical | Mechanical | Material | USC21C006 | USCSB2307127A | 1180.5 | F21P1 Slurry package | 2290 | C | -01 | Slurry H2O2 VMB | 2023/7/27 2023/9/6 2023/9/6 | 2023/7/28 2023/9/6 | 826.35 | 354.15 |  |  |  |  | SEMITORR GROUP, LLC | PR Approved | PO Approved | PR R2: Qty :9 to 30 PR R1: Adjusting the amount from 9 to 30 based on request. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1180.5 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 314.8 | 42.42 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 823.28 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2405078A | 1179 | F21P1 AMAT Interconnection | 4098 | C |  | Replenish wire lugs used to complete P1A project | 45423 | 45433 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1179 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 1179 | [10 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403087A | 1176.12 | F21P1-0404_H_labor for 50 tools_MICU | 3790 | C |  | Loto PR for Power Luis Retiz | 45359 | 45389 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1023.11 | 0.8699 | 153.01 | 0 | 153.01 | 0 | 1023.11 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC24B002 | USC2401053A | 1176 | Tool Interconnection Project (Main Tool & Other Vendors) | 675 | P |  | KECOT5 MANPOWER PAY FOR WGN STAR | 45311 | 45314 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1176 | 0 | 1176 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401035A | 1175 | F21P1-0404_H_labor for 50 tools_MICU | 3226 | C |  | High Accuracy Digital Pressure Gauge, Gas and plastic system, Tool hookup team | 45297 | 45311 | [6 empty] | Richwell Instrument Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1175 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 1175 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203002A | 1170.18 | F21P1 UPW | 127 | P0 |  | Desk chairs | 44624 | 44643 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1170.18 | 1 | 0 | 0 | 0 | 0 | 1170.18 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408113A | 1163.8 | TSMC Fab 21 P1B Tool Hook Up | 4727 | C |  | Cordless impact driver and strap wrench for HK Power trade Third for 297 tools | 45528 | 45531 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 943.68 | 0.81086 | 220.12 | 0 | 220.12 | 0 | [72 empty] | 943.68 | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2402281A | 1163.64 | F21P1 Chemical & WCCS package | 3704 | C |  | CDS NZMB1-A25-NA breaker | 45351 | 45363 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1163.64 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1163.64 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401117A | 1156 | F21P1-0404_H_labor for 50 tools_MICU | 3304 | C |  | Cable tie and cleanroom tapes for HK Exhaust trade HL | 45308 | 45308 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1156 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 1156 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Labor | USC21C009 | USCSB2312195A | 1147.47 | F21P1 WWT package (Installation and 2 batch tanks) | 3182 | C | -01 | WWT tools for MU | 45289 | 2024/1/3 2024/1/8 | -119.53 | 1267 |  | V |  |  | Abbeon Cal Inc. | PR Approved | PO Approved | R1: Original item is out of stock so switch to another available product which is also qualified for user's requirements |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1147.47 | 1 | 0 | 0 | 0 | 0 | 1147.47 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401004A | 1146.4 | F21P1-0404_H_labor for 50 tools_MICU | 3196 | C |  | Stretch Wrap and Dry Wipe, for UPW system, tool hookup team | 45294 | 45295 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1146.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 728.87 |  | 0 | 0 | 0 |  | 0 | [11 empty] | 417.53 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical Lab | Material | The budget execution does not pertain to this project | Chemical Lab | Chemical | Mechanical | Material | USC22C021 | USCSB2307093A | 1144.39 | F21P1 Chemical Lab setup | 2259 | C |  | GC Lab Valve | 45127 | 45128 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1144.39 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1144.39 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2306005A | 1144.2 | F21_AZQR_Hookup_ Interconnection | 2039 | C |  | CED: PES/FAD - KXF/KXP WIRE XHHW 10/12 AWG INTERCONNECT MATERIALS | 45079 | 45082 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1144.2 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 1144.2 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | MIC - Material | Material |  |  | Others |  |  | USC22C016 | USCSB2310159A | 1142.44 | Asahi Valve and Positioner from Harrington |  | C |  | Gasket from Harrington for M5 | 45223 | 45225 | [23 empty] | 1142.44 | 1 | 0 | 0 | 0 | 0 | [46 empty] | 1142.44
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408110A | 1141.31 | TSMC Fab 21 P1B Tool Hook Up | 4724 | C |  | Consumables Hardware for HK Power trade Third | 45528 | 8/31/2024 9/5/2024 | -24.47 | 1165.78 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: Change Payment Method to Credit Card as Shipping Date is too late. | [13 empty] | 1141.31 | 1 | 0 | 0 | 0 | 0 | 1141.31 | [72 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2310054A | 1139.49 | Tool Interconnection Project (Main Tool & Module) | 471 | P |  | materials for KDSNB1 Flex LT2UAGRY (50) BPT 435SLTI (20) BPT 38614LTI (20 GSTRT GC1154-200ASMBL (20) WIRE THHN6STRGRN (20) BPT 2150 (20) BUR KA6U (8) | 45225 | 45227 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1139.49 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 1139.49 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403107A | 1137.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 923 | P |  | Manpower Pay for Tool ID: KEPOL1 for CCE | 45374 | 45377 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 1137.5 | 0 | 1137.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2404026A | 1136.74 | F21P1 UPW | 4022 | C |  | PP/EPDM PNU 627 DIA VLV 2: FLG | 45385 | 45385 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1136.74 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1136.74 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2208011A | 1136 | F21P1 UPW | 1448 | C |  | UPW MABAT SDI Filter Paper | 44796 | 44803 | [6 empty] | MABAT Chemical systems Ltd | PR Approved | PO Approved | related to USC2112005A (original forgets to purchase filter paper) | 100% before shipping | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 1136 | 1 | 0 | 0 | 0 | 0 | [17 empty] | 1136 | [10 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Electrical | Material | USC21C007 | USCSB2307110A | 1133 | F21P1 VOC package （Installation ) | 2274 | C |  | VOC 1 Ground wire | 45129 | 45132 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1133 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 1133 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207005A | 1129 | F21P1 UPW | 185 | P0 |  | Black ergominc mesh back office chairs | 44770 | 44778 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1129 | 1 | 0 | 0 | 0 | 0 | 1129 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408081A | 1125.21 | TSMC Fab 21 P1B Tool Hook Up | 4697 | C |  | office supplies for tool hookup department shared by all systems | 45520 | 45523 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 948.19 | 0.84268 | 177.02 | 0 | 177.02 | 0 | 948.19 | [72 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402016A | 1124.9 | F21P1-0404_H_labor for 50 tools_MICU | 3459 | C |  | Pallet jack and sweeping compound for James McCormick shared by all HK system | 45323 | 45323 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1011 | 0.89875 | 113.9 | 0 | 113.9 | 0 | 1011 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2405167A | 1124 | F21P1 AMAT Interconnection | 4195 | C |  | 200 2/0 AWG | 45441 | 45443 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 1124 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 1124 | [8 empty] | - |  |  | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2403206A | 1123.5 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3901 | C |  | Consolidated Electrical Distributors Inc,Taiwaan Vendor Electricl Upgrade | 45371 | 45377 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1123.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 749 | [14 empty] | 0 |  | 374.5 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310049A | 1123 | Tool Interconnection Project (Main Tool & Module) | 467 | P |  | KPE602-S Reservoir Mounting | 45220 | 45224 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1123 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 1123 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403094A | 1120 | F21P1 Chemical & WCCS package | 3796 | C |  | CDS green screws | 45360 | 45374 | [6 empty] | Valqua NGC, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 1120 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1120 |  |  | 1120 | [5 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402097A | 1120 | F21P1-0404_H_labor for 50 tools_MICU | 3537 | C |  | Lug for HK power trade | 45332 | 45335 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 714 | 0.6375 | 406 | 0 | 406 | 0 | 714 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2410012A | 1118.4 | TSMC Fab 21 P1B Tool Hook Up | 4957 | C |  | Safety PPE, Tool hookup team | 45566 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1118.4 | 0 | 1118.4 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404195A | 1115.18 | WWT B side Project | 4174 | C |  | WWT 1-2 Bolts_20240424 (A&B Side) | 45407 | 45407 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1115.18 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 1012.59 |  |  | 167.277 |  |  |  | 167.277 | 102.59 |  |  | 167.277 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409033A | 1109.21 | Tool Interconnection Project (Main Tool & Other Vendors) | 1235 | P |  | DVF-B160250LH ISO160/200/250 CLAMP ALUMINUM QTY(1)= 4CLAMPS | 45553 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1109.21 | 0 | 1109.21 | 0 | [73 empty] | -
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401107A | 1108.68 | F21P1-0404_H_labor for 50 tools_MICU | 3294 | C |  | brother tape replacement for HK daily QAQC | 45307 | 45307 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 957.24 | 0.86341 | 151.44 | 0 | 151.44 | 0 | 957.24 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403092A | 1107.8 | F21P1-0404_H_labor for 50 tools_MICU | 3794 | C |  | share material for upw system and storage usage | 45360 | 45363 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1041.8 | 0.94042 | 66 | 0 | 66 | 0 | 1041.8 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405030A | 1105.2 | WWT B side Project | 4039 | C |  | WWT 5_8 Bolt_20240506 (B Side) | 45419 | 45419 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1105.2 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 |  | 1105.2 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2406048A | 1104 | F21P1 Module Tool Interconnection ETC1-3 | 4281 | C |  | DRY ETC 3 | 45450 | 45455 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1104 | 0 | 1104 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209017A | 1102.64 | F21P1 Chemical & WCCS package | 242 | P0 |  | 27in Monitor | 44825 | 44826 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1102.64 | 1 | 0 | 0 | 0 | 0 | 1102.64 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2307059A | 1102.58 | F21P1 Chemical & WCCS package | 2226 | C |  | Argon for Chemical welding. Qty: 2. | 45121 | 45132 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1099.46 | 0.99717 | 3.12 | 0 | 3.12 | 0 | [39 empty] | 976.46 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 121.28 |  |  |  |  | 123 | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2307055A | 1102.58 | F21P1 Chemical & WCCS package | 2223 | C |  | Argon for Chemical welding. Qty: 2. | 45120 | 45132 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1102.58 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1102.58 | [8 empty] | 1102.58 | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309043A | 1100 | F21P1 Chemical & WCCS package | 2520 | C |  | NATURAL POLYPRO COVER WITH 1.257" THRU HOLE. | 45181 | 45181 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1100 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 1100 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408100A | 1100 | TSMC Fab 21 P1B Tool Hook Up | 4716 | C |  | Parts of Tube Facing Tool, Hardware for tool hookup team | 45526 | 45532 | [6 empty] | Potex Technologies Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1100 | 0 | 1100 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403112A | 1099.23 | F21P1-0404_H_labor for 50 tools_MICU | 3814 | C |  | share for all systems, tool hookup team | 45363 | 45364 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 929.98 | 0.84603 | 169.25 | 0 | 169.25 | 0 | 929.98 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310160A | 1097.99 | F21P1-0404_H_labor for 50 tools_MICU | 2814 | C |  | Tripod light & batteries | 45223 | 45230 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1097.99 | 0 | 1097.99 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402207A | 1097.66 | F21P1-0404_H_labor for 50 tools_MICU | 3634 | C |  | Manlift skates and jack for James M. shared by all HK system | 45344 | 45343 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 997.86 | 0.90908 | 99.8 | 0 | 99.8 | 0 | 997.86 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407138A | 1096 | TSMC Fab 21 P1B Tool Hook Up | 4551 | C |  | Duct seal for HK Power trade Third for 150 tools | 45497 | 45498 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1096 | 1096 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202007A | 1095.13 | F21P1 UPW | 116 | P0 |  | Monitor | 44604 | 44609 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1095.13 | 1 | 0 | 0 | 0 | 0 | 1095.13 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402212A | 1088.6 | F21P1 Chemical & WCCS package | 3639 | C |  | CDS 20amp breakers | 45344 | 45344 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1088.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1088.6 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207015A | 1085.85 | F21P1 UPW | 195 | P0 |  | 27in Monitor | 44771 | 44784 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1085.85 | 1 | 0 | 0 | 0 | 0 | 1085.85 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2403304A | 1082.49 | F21P1-0404_H_labor for 50 tools_MICU | 3996 | C |  | Insulating Roll Blanket,Clear,Class 1 for HK Power trade | 45381 | 2024/4/1 2024/7/24 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | R1: Revising the payment to credit card as it was charged back in April for urgent request |  | Yikang Wang | [11 empty] | 1082.49 | 1 | 0 | 0 | 0 | 0 | 1082.49 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311025A | 1080.5 | Tool Interconnection Project (Main Tool & Module) | 499 | P |  | ClickCopier Wide Format Printer-Purchasing the machine not leasing | 2023/11/9 2023/12/15 | 45302 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | PR R1:Vendor name change to Electrical Ops and amount changed from 3840 to 1080.50 |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1080.5 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 1080.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407035A | 1079.74 | WWT B side Project | 4434 | C |  | Sticker | 45482 | 45484 | [6 empty] | StickerYou Inc. | PR Approved | PO Approved | [14 empty] | 1050.79 | 0.97319 | 28.95 | 0 | 28.95 | 1079.74 | 1050.79 | [70 empty] | 1079.74 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402279A | 1073.32 | F21P1-0404_H_labor for 50 tools_MICU | 3703 | C |  | office supply, tool hookup team | 45351 | 45351 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 994.51 | 0.92657 | 78.81 | 0 | 78.81 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 994.51 | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2401213A | 1071.2 | F21P1-0404_H_labor for 50 tools_MICU | 3396 | C |  | Portable band saw blade for HK Power trade | 45317 | 45320 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1071.2 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 1071.2 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403165A | 1069.28 | F21P1-0404_H_labor for 50 tools_MICU | 3863 | C |  | 1/2 in. x 250 ft Polyethylene Tubing Coil in Natural Color for HK Exhaust team | 45366 | 45370 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 972.08 | 0.9091 | 97.2 | 0 | 97.2 | 0 | 972.08 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402162A | 1069.28 | F21P1-0404_H_labor for 50 tools_MICU | 3594 | C |  | Polyethylene Tubing Coil for HK Exhaust | 45339 | 45343 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 1069.28 | 0 | 1069.28 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403187A | 1065.8 | F21P1-0404_H_labor for 50 tools_MICU | 3884 | C |  | Shared for all system, tool hookup team | 45370 | 45372 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 785.97 | 0.73745 | 279.83 | 0 | 279.83 | 0 | 785.97 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310058A | 1062 | Tool Interconnection Project (Main Tool & Module) | 475 | P |  | KDCRS3 Cable Pull | 45227 | 45231 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1062 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1062 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402188A | 1060 | F21P1-0404_H_labor for 50 tools_MICU | 3617 | C |  | For gas system stores coupon in L40, tool hookup team | 45343 | 45343 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1060 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 1060 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2408083A | 1059.85 | F21P1 Module Tool Interconnection LIT2-3 | 4699 | C |  | Lit 3: No Tool ID: Material to Help Install Storage Cabinet | 45520 | 45532 | [6 empty] | Cutting Edge Mfg LLC | PR Approved | PO Approved | [14 empty] | 1059.85 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 1059.85 | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405057A | 1057.43 | WWT B side Project | 4062 | C |  | WWT 1-2 Bolts_20240508 (B Side) | 45421 | 45425 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 1057.43 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 |  |  |  | 1057.43 | [10 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402176A | 1055.59 | F21P1-0404_H_labor for 50 tools_MICU | 3605 | C |  | LATERAL FILE CABINET - 36" WIDE, 4 DRAWER, WHITE, cabinet dolly, tool hook up | 45342 | 45343 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 972 | 0.92081 | 83.59 | 0 | 83.59 | 0 | [52 empty] | 972 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204014A | 1055.52 | F21P1 UPW | 161 | P0 |  | 55 inch zenstyle computer desk | 44679 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1055.52 | 1 | 0 | 0 | 0 | 0 | 1055.52 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404037A | 1054.72 | Tool Interconnection Project (Main Tool & Other Vendors) | 992 | P |  | Interconnect cable pull, routing, and 8395 compliance for KUECN2 and 3. Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45387 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1054.72 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1054.72 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111059A | 1050.65 | F21P1 UPW | 60 | P0 |  | Water dispensers | 44524 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 1050.65 | 1 | 0 | 0 | 0 | 0 | 1050.65 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208008A | 1049.28 | F21P1 UPW | 209 | P0 |  | Black small 3 drawer file cabinets | 44789 | 44791 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1049.28 | 1 | 0 | 0 | 0 | 0 | 1049.28 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2306110A | 1046.87 | F21P1 UPW | 2143 | C |  | UPW skids cover replacement | 45100 | 20230/7/19 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1046.87 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 1046.87 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2306092A | 1038.11 | F21P1 Module Tool Interconnection DIF1-2 | 2125 | C |  | DIFF1: FLEX METAL CONDUITS, ALUM, TRD SZ 1 IN. | 45098 | 45106 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1038.11 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 1038.11 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV |  |  |  | Low Voltage | Electrical | M+L | USC21C008 | USCSB2409011A | 1037.99 | F21P1 CCTV & Security | 4781 | C |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 4/6 | 45539 | 45542 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 1037.99 | 1 | 0 | 1037.99 | -1037.99 | 0 | [73 empty] | 1037.99
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402157A | 1035.06 | F21P1 Chemical & WCCS package | 3589 | C |  | Quality Material | 45338 | 45339 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 963.11 | 0.93049 | 71.95 | 0 | 71.95 | 0 | 963.11 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1035.06 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401106A | 1033 | Tool Interconnection Project (Main Tool & Other Vendors) | 723 | P |  | BUR BTCGC1/0SS GROUND CLAMP | 45322 | 45322 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1033 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 1033 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403060A | 1032.72 | Tool Interconnection Project (Main Tool & Other Vendors) | 883 | P |  | Tube PFA 10x8x100M Roll | 45365 | 45364 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1032.72 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 1032.72 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111025A | 1031.69 | F21P1 UPW | 39 | P0 |  | Dell Laptop for Engineers | 44512 | 44524 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 1031.69 | 1 | 0 | 0 | 0 | 0 | 1031.69 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Site Expense | 0 | 0 | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC22C019 | USCSB2401162A | 1031.36 | AMC monitor 595T0 | 3347 | C |  | Laydown Materials - Zoro | 45311 | 45336 | [6 empty] | Zoro Tools, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 952 | 0.92305 | 79.36 | 0 | 79.36 | 0 | 952 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2308012A | 1031 | Tool Interconnection Project (Main Tool & Module) | 362 | P |  | P-G-EPDM-GSK-250: 10"EPDM | 45142 | 45147 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1031 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 1031 | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409030A | 1029.48 | TSMC Fab 21 P1B Tool Hook Up | 4797 | C |  | HK Exhaust hardware Request for 200 Tools | 45541 | 45545 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved | [14 empty] | 2.38 | 0.0023118 | 1027.1 | 614.67 | 412.43 | 0 | [73 empty] | 2.38
Base-Build | Barcode | Equipment | The budget execution does not pertain to this project | Barcode | Low Voltage | Electrical | Material | USC22C019 | USCSB2403020B | 1026 | AMC monitor 595T0 | 3729 | C |  | F21 Brcode system _ G-Bit | 45353 | 2024/3/5 2024/3/8 2024/3/11 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved |  | R1: Correcting the Supplier B: Correcting the Supplier | Yikang Wang | [11 empty] | 1026 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1026 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2309054A | 1021.72 | F21P1 Module Tool Interconnection DIF1-2 | 2530 | C |  | DIFF/EPI - CABLE TRAY DIVIDER | 45181 | 45184 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1021.72 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 1021.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407094A | 1020.25 | TSMC Fab 21 P1B Tool Hook Up | 4510 | C |  | Welding Inspection Tool Set | 2024/7/16 2024/8/7 | 2024/8/2 2024/8/7 | -122.5 | 1142.75 | V |  |  |  | G.A.L Gage, CO. | PR Approved | PO Approved | PR R1: Supplier offered discounts | [13 empty] | 1020.25 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 1020.25 | - |  |  | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2310103A | 1017.69 | F21P1 UPW | 2765 | C |  | UPW-NaHSO3 cover repair | 45216 | 45219 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1017.69 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 1017.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402245A | 1016.21 | F21P1 WWT package (Installation and 2 batch tanks) | 3671 | C |  | WWT Narrow flat washer_20240223 (A Side) | 45347 | 45349 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1016.21 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1016.21 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401038A | 1015.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 661 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45310 | 45309 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1015.19 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1015.19 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403078A | 1009.05 | F21P1-0404_H_labor for 50 tools_MICU | 3781 | C |  | TTI Molex battery cable lug for HK Power trade | 45358 | 45364 | [6 empty] | TTI, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 980 | 0.97121 | 29.05 | 0 | 29.05 | 0 | 980 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403003A | 1009.01 | Tool Interconnection Project (Main Tool & Other Vendors) | 830 | P |  | SPL012: 1-1/4X10 FT PVC S40 CLR PIPE STOCK SPEARS | 45353 | 45356 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1009.01 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1009.01 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2306124A | 1008 | F21P1 Chemical & WCCS package | 2157 | C | -01 | Pillar tools for flare | 2023/6/28 2023/6/30 | 2023/6/28 2023/6/30 | 232 | 776 | V |  |  |  | Nippon Pillar Corporation of America | PR Approved | PO Approved | Price quoted incorrectly |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1008 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 1008 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403087A | 1005 | Tool Interconnection Project (Main Tool & Other Vendors) | 904 | P |  | Manpower Pay for Tool ID: KEPRL5 for CGS | 2024/3/20 2024/3/26 | 45376 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | PR R1: Calucaltion error needed to be corrected |  | Ta Wei Wang | [11 empty] | 0 | 0 | 1005 | 0 | 1005 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2312040A | 1002.08 | F21P1 Module Tool Interconnection CVD | 3033 | C |  | KCSOA4 Material request for Seal-Tite conduit, supporting hardware, rigid EMT conduit, and grounding hardware | 45267 | 45269 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1002.08 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 1002.08 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2209005A | 1001.88 | F21P1 UPW | 230 | P0 |  | Zen style modern desk work station 55" black | 44806 | 44810 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mirielli Terres | Yi En Wong | [7 empty] | 1001.88 | 1 | 0 | 0 | 0 | 0 | 1001.88 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401076A | 1000 | Tool Interconnection Project (Main Tool & Other Vendors) | 696 | P |  | KKDB03: CUT & ROLL EDGE ON DUCTING PIPE | 45317 | 45323 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 500 | 0.5 | 500 | 0 | 500 | 0 | [48 empty] | 0 | 0 |  |  | 500 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Safety | USC24C006 | USCSB2409044A | 1000 | WWT B side Project | 4829 | C |  | WWT: SCS PR - Confined Space Safety Tank T-140AB | 45545 | 45547 | [6 empty] | Safety Compliance Services, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1000 | 0 | 1000 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403243A | 1000 | F21P1-0404_H_labor for 50 tools_MICU | 3936 | C |  | Switchboard Mat for HK power system | 45377 | 45376 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 1000 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Commissioning | USC21C009 | USCSB2403120A | 996.82 | F21P1 WWT package (Installation and 2 batch tanks) | 3822 | C |  | WWT 7 Chemical - 3 | 45364 | 45363 | [6 empty] | Midland Scientific, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 949.36 | 0.95239 | 47.46 | 0 | 47.46 | 996.82 | 949.36 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 149.523 |  |  |  | 149.523 |  |  |  | 149.523 |  | 996.82 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310061A | 996 | F21P1 Chemical & WCCS package | 2721 | C |  | 2” BA tube for Yaho work at Lorry FNDP | 45210 | 45211 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 996 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 996 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Mechanical | Material | USC24C005 | USCSB2407006A | 992 | Chemical & WCCS B Side Project | 4408 | C |  | F21P1 Fab HMP Mixing box | 45474 | 45475 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | [14 empty] | 992 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 992 |  |  | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409093A | 979.57 | TSMC Fab 21 P1B Tool Hook Up | 4903 | C |  | Hand tool for upw system, tool hookup team | 45560 | 45562 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 979.57 | 0 | 979.57 | 0 | [73 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310060A | 977.28 | F21P1 Chemical & WCCS package | 2720 | C | -01 | Material for YaHo at Lorry FNDP. | 45210 | 2023/10/12 2023/12/2 | 90.88 | 886.4 |  |  |  |  | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | PO R1:Per request by engineer to revise price |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 977.28 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 977.28 |  |  |  |  | 977.28 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303042A | 976.84 | F21P1 WWT package (Installation and 2 batch tanks) | 1784 | C |  | Bolts/Gaskets for 6.5 LB2 | 44994 | 44998 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 976.84 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 976.84 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | M+L | USC21C003 | USCSB2305075A | 975.1 | F21P1 UPW | 1996 | C |  | UPW skids cover replacement | 45063 | 45065 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 975.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 975.1 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS |  |  |  | AMHS |  |  | USC23C015 | USCSB2406064A | 973 | F21P1 AMHS Wiring Work Outline | 4297 | C |  | AMHS Power Tools for Panel Install | 45454 | 45454 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 875.35 | 0.89964 | 97.65 | 0 | 97.65 | 0 | 875.35 | [72 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2401245A | 972.32 | F21P1 Module Tool Interconnection CVD | 3426 | C |  | KDALS2 re-work to fulfill CIP signal cables | 45321 | 45322 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 972.32 | 0 | 972.32 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2401247A | 972.32 | F21P1 Module Tool Interconnection CVD | 3428 | C |  | KCSNA1 re-work to fulfill CIP signal cables | 45321 | 45322 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 972.32 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 972.32 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203020A | 970.73 | F21P1 UPW | 142 | P0 |  | AutoCAD License | 44637 | 44643 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 970.73 | 1 | 0 | 0 | 0 | 0 | 970.73 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2305073A | 970.32 | F21_AZQR_Hookup_ Interconnection | 1995 | C |  | QR - 6mm & 8mm PFA Tubing | 45062 | 45063 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 970.32 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 970.32 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312085A | 969.32 | F21P1-0404_H_labor for 50 tools_MICU | 3077 | C |  | Brother printer, share materials, tool hook up | 45274 | 45276 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 944.32 | 0.97421 | 25 | 0 | 25 | 0 | 944.32 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2403262A | 966.72 | F21P1 WWT package (Installation and 2 batch tanks) | 3955 | C | -01 | WWT WRC laboratory furniture_1 | 45378 | 2024/3/27 2024/04/18 | 179.98 | 1146.7 |  |  | V |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Cancelled purchase for GREATMEET Metal Storage Cabinet |  | Ta Wei Wang | [11 empty] | 862.36 | 0.89205 | 104.36 | 0 | 104.36 | 0 | 862.36 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 145.008 |  |  |  | 145.008 |  |  |  | 145.008 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403078A | 966 | Tool Interconnection Project (Main Tool & Other Vendors) | 897 | P |  | Manpower Pay for Tool ID KEMEL6 for Delta Wye | 45370 | 45369 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 966 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 966 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311029A | 965 | F21P1-0404_H_labor for 50 tools_MICU | 2884 | C | -01 | cleanroom backpack | 45237 | 2023/11/15 2023/11/26 | [6 empty] | S-TURBO D.I.Y. and HARDWARE CO., LTD. | PR Approved | PO Approved | PO R1: Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 965 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 965 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402019A | 963.02 | Tool Interconnection Project (Main Tool & Other Vendors) | 745 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45324 | 45327 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 963.01 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 921.69 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401098A | 963 | Tool Interconnection Project (Main Tool & Other Vendors) | 715 | P |  | FLEX LT3UAGRY | 45321 | 45321 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 963 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 921.69 |  | 41.31 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402015A | 961.95 | Tool Interconnection Project (Main Tool & Other Vendors) | 741 | P |  | FLEX LT3UAGRY | 45324 | 45327 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 961.95 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 920.63 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402021A | 956.96 | F21P1 Chemical & WCCS package | 3464 | C |  | CDS CDA fittings | 45324 | 45325 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 956.96 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 | 956.96 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208024A | 956.7 | F21P1 UPW | 223 | P0 |  | Box License | 44800 | 44810 | [6 empty] | Box, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 956.7 | 1 | 0 | 0 | 0 | 0 | 956.7 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C011 | USCSB2306139A | 954.36 | F21 TMAH System | 2172 | C | -01 | WWT-PVC blind flange 20” | 2023/6/30 2023/7/17 | 2023/7/13 2023/7/17 | 106.04 | 1060.4 | V |  |  |  | Pure Plastics, LLC | PR Approved | PO Approved | Discount given by vendor. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 954.36 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 954.36 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2310036A | 953.01 | Tool Interconnection Project (Main Tool & Module) | 456 | P |  | 5YE30: STAND NUT, STEEL, OVERALL W 1 3/8IN, PK25 | 45216 | 45219 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 953.01 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 953.01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403081A | 953 | F21P1-0404_H_labor for 50 tools_MICU | 3784 | C |  | P clamp for gas system, tool hookup team | 45358 | 45362 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 953 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 953 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Equipment | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USCSB2306082A | 950 | F21P1 UPW | 2115 | C |  | Forklift for the pipe crating project at the TSMC site | 45097 | 45103 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 950 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 950 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C027 | USCSB2410025A | 947.74 | CAP_E_F21P1 Autoshelf Installation 4 set | 4968 | C |  | DP Design Change_AMHS_2/7 batch | 45568 | [7 empty] | 0 | PR Approved | PO Processing | [14 empty] | 0 | 0 | 947.74 | 0 | 947.74 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310017A | 944 | Tool Interconnection Project (Main Tool & Module) | 449 | P |  | Labor Pull cable and 8395 Certification/Install seal tight flex conduit, cables from L30 to L10 and tie wraps. $59 x 8 hours = $472.00 $472 x 2 installers = $944.00 | 45206 | 45212 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 944 | 0 | 944 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402073A | 937.89 | Tool Interconnection Project (Main Tool & Other Vendors) | 789 | P |  | KETRT9 Trey in house. KETRT9 cable pull - L30-L20 Drop - L20-L10 Drop | 45339 | [7 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 937.89 | 1858.63 | -920.74 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2311084A | 937.39 | F21P1 AMAT Interconnection | 2937 | C |  | Change Order: KECOA1 AC Box Cover Plate Notch. | 45247 | 45246 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 937.39 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 937.39 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2311086A | 937.39 | F21P1 AMAT Interconnection | 2938 | C |  | Change Order: KESDA1 AC Box Cover Plate Notch. | 45247 | 45246 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 937.39 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 937.39 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2305095A | 935.14 | F21P1 UPW | 2016 | C |  | Eaton Broken | 45066 | 45070 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 935.14 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 935.14 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204012A | 933.6 | F21P1 UPW | 159 | P0 |  | Ergonomic Desk Chair Mesh Cavalier for Sub Trailers | 44678 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 933.6 | 1 | 0 | 0 | 0 | 0 | 933.6 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402186A | 932.84 | F21P1 Chemical & WCCS package | 3615 | C |  | CDS Monstair low b2b pc strut | 45343 | 45344 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 932.84 | 0 | 932.84 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 932.84 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2312203A | 930 | F21P1 UPW | 3189 | C | -01 | UPW-earthquake limiters | 45290 | 2024/1/16 2024/1/30 | -200 | 1130 |  | V |  |  | Harmony Rubber Industry Co., Ltd. | PR Approved | PO Approved | PR R1: Change trade terms and payment terms |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 930 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 930 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  |  |  | UPW | Mechanical | M+L | USC24C008 | USCSB2408161A | 930 | UPW B Side Project | 4767 | C |  | Damaged Valves on A Side, Replacement order through UMEC, TSMC issued PO | 45535 | 45540 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 930 | 0 | 930 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402282A | 925.53 | F21P1-0404_H_labor for 50 tools_MICU | 3705 | C |  | office supplies for tool hookup department | 45351 | 45351 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 848.77 | 0.91706 | 76.76 | 0 | 76.76 | 0 | 848.77 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2401226A | 923.69 | F21P1 Module Tool Interconnection ETC1-3 | 3408 | C |  | KECOT1 DAQ RS Payroll | 2024/1/26 2024/8/15 | 2024/1/27 2024/8/15 | -631.21 | 1554.9 |  |  | V |  | RS PAYROLL SERVICES | PR Approved | PO Approved | To release excess bugdet |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 923.69 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 923.69 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C007 | USCSB2308084A | 919.2 | F21P1 Module Tool Interconnection PVD1-2 | 2381 | C |  | BLINE BVT200YZN 2IN PIPE CLMPS for AMAT PVD1&2 DIMAX water hoses | 45154 | 45159 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 919.2 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 919.2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403153A | 917.81 | F21P1-0404_H_labor for 50 tools_MICU | 3852 | C |  | Connectors for HK Power trade | 45366 | 45370 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 917.81 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 917.81 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2312054A | 916.32 | F21P1 WWT package (Installation and 2 batch tanks) | 3047 | C |  | CDA line WRC L20 material revise | 45268 | 45267 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 916.32 | 1 | 0 | -58.53 | 58.53 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 235.68 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 45.816 |  |  |  | 91.632 | 680.64 |  |  | 91.632 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403096A | 912 | Tool Interconnection Project (Main Tool & Other Vendors) | 912 | P | -01 | KCOCN1-3/22/2024 labor Eliseo Perez, Luis Rojas, Xavier Niesen | 45372 | 2024/3/29 2024/6/14 | 25.92 | 886.08 |  |  |  | V | CGS Global Support, LLC | PR Approved | PO Approved | R1: Adjusting the amount due to the rate discrepancy-invoice with correct rate is provided. |  | Ta Wei Wang | [11 empty] | 912 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 912 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2403130A | 911.29 | Tool Interconnection Project (Main Tool & Other Vendors) | 945 | P |  | ABAA0158012 Armaflex 1-5/8 X 1/2; 522 FT X 1.7458 | 45379 | 45379 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 911.29 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 911.29 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401165A | 910.4 | F21P1 Chemical & WCCS package | 3350 | C |  | CDS ICP Mass CDA GN2 parts | 45311 | 45313 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 910.4 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 910.4 |  |  |  |  | 910.4 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402027A | 908.9 | F21P1 WWT package (Installation and 2 batch tanks) | 3470 | C |  | Tmah Resin filling | 45324 | 45324 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 908.9 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 908.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403114A | 905.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 930 | P |  | Manpower Pay for CCE on 3.6.2024 for Tool ID KETRT2 ETC 3 | 45377 | 45378 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 905.5 | 0 | 905.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403117A | 905.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 933 | P |  | Manpoer Pay for CCE for Tool ID: KEPOL8 | 45378 | 45378 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 905.5 | 0 | 905.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C016 | USCSB2403276A | 903.52 | F21P1 Mattson Interconnection | 3969 | C |  | MATTSON: KEPRM6-8: GROUND CONDUIT FROM L20-L10 FOR SIGNAL CABLING. | 45380 | [7 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 903.52 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 903.52 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405079A | 903.33 | Tool Interconnection Project (Main Tool & Other Vendors) | 1102 | P |  | Payment for Material: 1. Supply (6) 2-1/2’’x 2-1/2’’x1’’ 304 SS Tees 2. Supply (6) 1’’x3/4’’ 304 SS Reducers. | 45429 | 45433 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 903.33 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 903.33 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404068A | 901.49 | Tool Interconnection Project (Main Tool & Other Vendors) | 1022 | P |  | GSTRT G-582A-OS-1 10FT B2B SLOTTED DP STRUT | 45399 | 45404 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 901.49 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 581.49 | [9 empty] | 320 |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403211A | 900 | F21P1 Chemical & WCCS package | 3906 | C | -01 | CDS Circuit Lockout Kit | 45372 | 3/30/2024 4/4/2024 | -96.6 | 996.6 | V |  |  |  | Wesco Distribution, Inc. | PR Approved | PO Approved | R1: Quote Update |  | Yikang Wang | [11 empty] | 900 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 900 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2312019A | 898.67 | F21P1 WWT package (Installation and 2 batch tanks) | 3013 | C |  | WWT-lab tech-sink | 45265 | 45268 | [6 empty] | LabTech Supply Company Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 898.67 | 1 | 0 | 0 | 0 | 898.67 | [44 empty] | 898.67 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 134.8005 |  |  |  | 134.8005 |  |  |  | 134.8005 |  | 898.67 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2403177A | 898.04 | F21P1 WWT package (Installation and 2 batch tanks) | 3874 | C | -01 | WWT Cleaning Material | 45367 | 2024/3/18 2024/3/19 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | R1: Change to Store Pick up per Angela Hsu |  | Ta Wei Wang | [11 empty] | 791.69 | 0.88158 | 106.35 | 0 | 106.35 | 898.04 | 791.69 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 134.706 |  |  |  | 134.706 |  |  |  | 134.706 |  | 898.04 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Site Expense |  |  | Others |  |  | USC24B002 | USC2404013A | 897.31 | Tool Interconnection Project (Main Tool & Other Vendors) | 968 | P |  | Lifts rental for February 2x19'Micro 2/1-2/29/2024 | 45385 | 45385 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 897.31 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 897.31 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311066A | 895.63 | Tool Interconnection Project (Main Tool & Module) | 535 | P | -01 | manpower request for KDANT2. This will be for general labor for today to install Unistrut & cable tray at LB1 F.5/9. | 45252 | 2023/12/5 2024/1/30 | 415.25 | 480.38 | V |  |  |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | PR R1: Total Amount Change |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 895.62 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 895.62 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2404203A | 893.05 | F21P1 Module Tool Interconnection ETC1-3 | 4182 | C |  | DRY ETC MATERIAL ORDER FOR ETC 1,2,3 from Amazon | 2024/4/26 2024/9/26 | 2024/4/29 2024/9/26 | -101.2 | 994.25 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: Match to the actual expense (See packing slip) | [13 empty] | 893.05 | 1 | 0 | 0 | 0 | 0 | 893.05 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC23C045 | USCSB2311002A | 892 | WWT Change Order (Piping) | 2857 | C |  | T-125AC Replacement Top Manway (Include manway, hardware, and gasket) | 45231 | 45232 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 892 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 892 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311084A | 891.8 | Tool Interconnection Project (Main Tool & Module) | 551 | P |  | SS-16-VCR-P: VCR PLUG 1" | 45260 | 45264 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 891.8 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 891.8 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407018A | 886.18 | Tool Interconnection Project (Main Tool & Other Vendors) | 1155 | P |  | For use on upcoming CVD/PVD tools in P1B (Cable lables, Core Hole markings, Cable Tray designation). For use on CVD/PVD tools - this is used for interconnect cables, cable trays, core holes, and more | 45489 | 45498 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 886.18 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 886.18 |  |  | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405139A | 884 | Tool Interconnection Project (Main Tool & Other Vendors) | 1114 | P |  | 1KT H-2084 SECURITY CART - 48 X 24 X 69" | 45435 | 45443 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 803.64 | 0.9091 | 80.36 | 0 | 80.36 | 0 | [62 empty] | 803.64 | [10 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408103A | 883.32 | TSMC Fab 21 P1B Tool Hook Up | 4711 | C |  | Cleanroom paper shared by all hk systems | 45527 | 45531 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 883.32 | 883.32 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403007A | 883 | Tool Interconnection Project (Main Tool & Other Vendors) | 834 | P |  | MANPOWER PAY FOR CCE | 45353 | 45401 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | 0 | 883 | 0 | 883 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409051A | 882.41 | Tool Interconnection Project (Main Tool & Other Vendors) | 1253 | P |  | Wire: SOOW/SOW-6/4-Black -RCL "ONE CUT=200ft" **Cut Wire is NOT refundable** | 45560 | 45560 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 882.41 | 0 | 882.41 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402106A | 881.69 | F21P1-0404_H_labor for 50 tools_MICU | 3545 | C |  | Vacuum Hose,10 ft. L,Hose 1-1/2" Dia | 45332 | 45335 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 881.69 | 1 | 0 | 0 | 0 | 0 | 881.69 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2209019A | 879.6 | F21P1 UPW | 244 | P0 |  | Zenstyle desk 55 inch black | 44827 | 44839 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 879.6 | 1 | 0 | 0 | 0 | 0 | 879.6 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203025A | 879.5 | F21P1 UPW | 145 | P0 |  | Super Deal 55 inch modern desk | 44643 | 44670 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 879.5 | 1 | 0 | 0 | 0 | 0 | 879.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403236A | 875.51 | F21P1-0404_H_labor for 50 tools_MICU | 3929 | C |  | battery and Oxygen regulator, tool hookup | 45374 | 45376 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 803.36 | 0.91759 | 72.15 | 0 | 72.15 | 0 | 803.36 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402077A | 875 | F21P1 Chemical & WCCS package | 3519 | C |  | CDS M6 x 1 x 16 (5/8) Screws PP | 45330 | 45331 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 875 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 875 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401145A | 874.5 | F21P1-0404_H_labor for 50 tools_MICU | 3330 | C |  | divider box for 永旗 PPL, Cleanroom tapes shared by all system | 45310 | 45328 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 874.5 | 1 | 0 | 0 | 0 | 0 | 874.5 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | [16 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402012A | 874 | Tool Interconnection Project (Main Tool & Other Vendors) | 738 | P |  | Electrical cable pull for KEPOL8 and KEPOL2- L30 - L20 Cable drop. | 45324 | 45352 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 0 | 0 | 874 | 0 | 874 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404100A | 874 | Tool Interconnection Project (Main Tool & Other Vendors) | 1044 | P |  | Manpower Pay to CGS for Tool IDs: KEPOT1, KESRT1, KESRT2 for Time card on 3.4.2024 | 45407 | 45411 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 874 | 0 | 874 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404109A | 874 | Tool Interconnection Project (Main Tool & Other Vendors) | 1053 | P |  | Manpower Pay to CGS for Tool ID: KESTL6 for Timecard on 2.20.2024 for worker: ELOY PACHECO UBALDO FERREYA JR. | 45409 | 45411 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 874 | 0 | 874 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111022A | 868.79 | F21P1 UPW | 36 | P0 |  | Sony TV for Company owned house | 44512 | 44524 | [6 empty] | Costco Wholesale Corporation | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 868.79 | 1 | 0 | 0 | 0 | 0 | 868.79 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404018A | 861 | Tool Interconnection Project (Main Tool & Other Vendors) | 973 | P |  | Manpower Pay for CGS for Tool ID: KETRT2 Time cards 3.1,, and 3.4.2024 | 45385 | 45387 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 861 | 0 | 861 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | EUV Overhead Crane | Material |  |  | Others |  |  | USC24C002 | USCSB2403006A | 860.5 | [RM]F21 EUV Crane service contract | 3714 | C |  | Certex-Phoenix CX07-0130TT MlB4 EE2 93 93 X Four Leg Nylon bridle sling, SO116-FS20-Us 3/4 Stainless SPA Shackle US Made 6,00 | 45352 | 45357 | [6 empty] | Certex USA LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 860.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 860.5 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2303039A | 859.8 | F21P1 UPW | 1781 | C |  | UPW Pressure indicator | 44994 | 45014 | [6 empty] | Hwa Chi Technology Co., Ltd | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 859.8 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 859.8 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303045A | 856.92 | F21P1 WWT package (Installation and 2 batch tanks) | 1787 | C |  | Gaskets | 44995 | 44998 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 856.92 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 856.92 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Commissioning | USC24C006 | USCSB2404178A | 856.8 | WWT B side Project | 4159 | C |  | Safety Filter for LSR ACF | 45406 | 45405 | [6 empty] | ServAPure Company | PR Approved | PO Approved | [14 empty] | 856.8 | 1 | 0 | 0 | 0 | 856.8 | 856.8 | [53 empty] | 0 |  | 0 | [14 empty] | 856.8 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2301001A | 856.02 | F21P1 UPW | 1624 | C |  | UPW Copper Connector Bars for MCP | 44930 | 44937 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Chih-Hao Ting | Tiong Sheng Poh | [7 empty] | 856.02 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 856.02 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311026A | 855.17 | Tool Interconnection Project (Main Tool & Module) | 500 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45239 | 45239 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 855.18 | 1 | -0.01 | 0 | -0.01 | 0 | [43 empty] | 0 |  | 855.18 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403057A | 852 | Tool Interconnection Project (Main Tool & Other Vendors) | 878 | P |  | MANPOWER PAY FOR TOOL ID: KETRTA FOR RS PAYROLL | 45364 | 45412 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 852 | 0 | 852 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311021A | 850 | Tool Interconnection Project (Main Tool & Module) | 494 | P |  | Labor for level QC | 45238 | 45240 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 850 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 850 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C047 | USCSB2309028A | 850 | F21P1 HK Seismic Installation | 2505 | C |  | MIC-121-23 Metrios Seismic Anchoring | 45177 | 45177 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 850 | 0 | 850 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC23C045 | USCSB2403266A | 849.12 | WWT Change Order (Piping) | 3959 | C |  | WWT: (6) ANSI300 4" Flanges for LSR | 45378 | 45381 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 849.12 | 0 | 849.12 | 849.12 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 127.368 |  |  |  | 127.368 |  |  |  | 127.368 |  | 849.12 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402284A | 847.68 | F21P1-0404_H_labor for 50 tools_MICU | 3707 | C |  | Electrical tapes for HK Power Trade | 45351 | 45352 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 847.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 847.68 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403147A | 847.68 | F21P1-0404_H_labor for 50 tools_MICU | 3847 | C |  | Electrical tape for HK Power trade | 45365 | 45367 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 847.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 811.28 | [9 empty] | 36.4 |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312091A | 847.68 | F21P1-0404_H_labor for 50 tools_MICU | 3082 | C |  | cleanroom tapes shared by all hk trades | 45274 | 45275 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 847.68 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 847.68 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C029 | USCSB2305037A | 846 | EBO21- Tool interconnection | 1960 | C |  | Armaflex 3/8 x 1/2 | 45057 | 45071 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 846 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 846 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311023B | 842.03 | Tool Interconnection Project (Main Tool & Module) | 497 | P |  | LAM Interconnect cable pull for KESTL3 (ETC1) TSMC K/2.5 Lvl. L30 2 days | 45239 | 45280 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 842.03 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 842.03 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  | Main Contract Scope | UPW | UPW | Electrical | Material | USC24C008 | USCSB2406057A | 839.13 | UPW B Side Project | 4290 | C |  | Ashcroft PIA KM31 | 45454 | 45454 | [6 empty] | Ashcroft Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 839.13 | 0 | 839.13 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2404100A | 838.74 | F21P1 WWT package (Installation and 2 batch tanks) | 4087 | C |  | WWT Gasket_20240410 (A Side) | 45393 | 45394 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 838.74 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 838.74 | [12 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2402084A | 836.85 | F21P1 AMAT Interconnection | 3525 | C |  | KCUVA3 AC Cover Modificatons | 45339 | 45343 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 836.85 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 836.85 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311048A | 836.06 | Tool Interconnection Project (Main Tool & Module) | 521 | P |  | FLEX LT2UAGRY | 45247 | 45250 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 836.07 | 1 | -0.01 | 0 | -0.01 | 0 | [43 empty] | 0 |  | 836.07 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2311039A | 835.52 | Tool Interconnection Project (Main Tool & Module) | 513 | P |  | Water line insulation; ABAA0218100 Armaflex 2-1/8 X 1 ZZZY049 | 45245 | 45248 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 835.52 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 835.52 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC22C012 | USCSB2403015A | 830.76 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 3724 | C |  | UPW-GF valve for train B | 45352 | 45353 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 830.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 830.76 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | CCE | DCR Scope | WWT | WWT | Electrical | M+L | USC21C009 | USCSB2312107A | 826.65 | F21P1 WWT package (Installation and 2 batch tanks) | 3097 | C |  | WWT CCE Change Orders_CO64 | 45276 | 45278 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 785.32 | 0.95 | 41.33 | 0 | 41.33 | 0 | [45 empty] | 0 | 0 | 0 | 785.32 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2308152A | 816 | F21P1 AMAT Interconnection | 2447 | C |  | Change order for KSSBA3 REI Labor. | 45163 | 45163 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 816 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 816 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208006A | 814.2 | F21P1 UPW | 207 | P0 |  | Office Chair Black with Mesh | 44785 | 44791 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 814.2 | 1 | 0 | 0 | 0 | 0 | 814.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403058A | 812.04 | Tool Interconnection Project (Main Tool & Other Vendors) | 881 | P |  | 2CEX5 90° Elbow: 1 in x 1 in Fitting Pipe Size, Schedule 40, Female Socket x Female Socket, Clear | 45364 | 45363 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 812.04 | 1 | 0 | 0 | 0 | 0 | 812.04 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401092A | 810.98 | F21P1-0404_H_labor for 50 tools_MICU | 3280 | C |  | 6 additional Hot air welding gun requested by SC Chen | 45304 | 45303 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 638.28 | 0.78705 | 172.7 | 0 | 172.7 | 0 | 638.28 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310143A | 810 | F21P1-0404_H_labor for 50 tools_MICU | 2801 | C |  | Uline Pallet Truck lime | 45220 | 45225 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 810 | 0 | 810 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311016A | 809.5 | Tool Interconnection Project (Main Tool & Module) | 489 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45237 | 45240 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 809.5 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 809.5 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2404131A | 807.85 | F21P1 Module Tool Interconnection ETC1-3 | 4115 | C |  | DRY ETC 1,2,3 MISC TOOLS ZIP TIES, AIRIC WIRE FERRULE CONNECTORS, MILWAUKEE DEEP CUT BAND SAW,&PVC CLEAR POLYETHYLENE | 2024/4/17 2024/10/3 | 2024/4/26 2024/10/3 | -24.97 | 832.82 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approving | PO R1: Match to the actual expense | [13 empty] | 807.85 | 1 | 0 | 0 | 0 | 0 | 807.85 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2402183A | 806.91 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3612 | C |  | EUV Crane Project Code Materials | 45342 | 45343 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 806.91 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 353.76 |  | 0 | [9 empty] | 453.15 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207016A | 802.7 | F21P1 UPW | 196 | P0 |  | 24in Monitor | 44771 | 44784 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 802.7 | 1 | 0 | 0 | 0 | 0 | 802.7 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C006 | USCSB2407024A | 799 | WWT B side Project | 4423 | C |  | Storage containers for tools and materials for Fab A side | 45476 | 45476 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 799 | 0 | 799 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Commissioning | USC21C011 | USCSB2401244A | 798.45 | F21 TMAH System | 3425 | C |  | WWT-TMAH-LCMSMS-Nitrogen | 45321 | 45320 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 798.36 | 0.99989 | 0.09 | 0 | 0.09 | 0 | [48 empty] | 0 | 0 | 798.36 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403028A | 798 | Tool Interconnection Project (Main Tool & Other Vendors) | 854 | P |  | Manpower Pay for CCE | 45358 | 45363 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 0 | 0 | 798 | 0 | 798 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404104A | 797.7 | Tool Interconnection Project (Main Tool & Other Vendors) | 1054 | P |  | GSP44LG 1 SS S40 304L A312 WELD PIPE STOCK | 45408 | 45409 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 797.7 | 1 | 0 | -331.2 | 331.2 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 797.7 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2402026A | 791 | F21P1 WWT package (Installation and 2 batch tanks) | 3469 | C |  | WWT Cleaning Material | 45324 | 45324 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 791 | 1 | 0 | 0 | 0 | 0 | 791 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403129A | 789.76 | Tool Interconnection Project (Main Tool & Other Vendors) | 944 | P |  | 5434007 3/4" UNION BF HP PVDF FKM TYPE G 230PSI: CPN-P-TIC-PD-UN-022 | 45379 | 45379 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 789.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 789.76 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  |  |  | UPW | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C003 | USCSB2409003A | 788.6 | F21P1 UPW | 4773 | C |  | Horiba SILA Buffer Tank and PFA Tube | 45539 | 45540 | [6 empty] | HORIBA Instruments Incorporated | PR Approved | PO Approved | [14 empty] | 0 | 0 | 788.6 | 0 | 788.6 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306008A | 787.2 | Tool Interconnection Project (Main Tool & Module) | 293 | P |  | SS-6-HC-7-8: 3/8" HOSE BARB X FNPT CONNECTOR | 45080 | 45083 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 787.2 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 787.2 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2310094A | 782.66 | F21P1 AMAT Interconnection | 2755 | C | -01 | AMAT_ME_ Amazon_KKDB04, KKDD03, KKDB05, KKDD04_flexible duct, clamps | 45213 | 2023/10/20 2023/11/8 | -42.14 | 824.8 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | Amazon order amount was changed due to partial refund/return. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 782.66 | 0 | 782.66 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2308174A | 782.58 | F21P1 AMAT Interconnection | 2468 | C |  | Change Order for KCBDA1 | 45168 | 45168 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 782.58 | 0 | 782.58 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2308015A | 780 | Tool Interconnection Project (Main Tool & Module) | 365 | P |  | TEL interconnect Cable pull KESRT4 | 45160 | 45160 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 780 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 780 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309172A | 779.7 | F21P1 Chemical & WCCS package | 2641 | C |  | NFPA Diamond Signs for chemical tanks, HPM 20. | 45197 | 45202 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 779.7 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 779.7 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2211028A | 779.52 | F21P1 UPW | 1561 | C |  | UPW WRC Chemical room ball valves (1-1/2”) | 44884 | 44886 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 779.52 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 779.52 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2311108A | 778.45 | F21P1 Module Tool Interconnection CMP1 | 2959 | C |  | CMP: MKS1-4: INTERCONNECT MATERIALS - STRUT, CUSH CLAMPS, 90 UNISTRUT BRACKET SS, HEX NUT | 45253 | 45268 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 778.16 | 0.99963 | 0.29 | 0 | 0.29 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 778.16 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC22C036 | USCSB2305039B | 778.26 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1964 | C |  | Armaflex 7/8 x1/2 | 45057 | 45071 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 778.26 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 778.26 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409076A | 775.4 | TSMC Fab 21 P1B Tool Hook Up | 4869 | C |  | UNIVERSAL SORBENT PADS for upw system | 45554 | 45558 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 775.4 | 0 | 775.4 | 0 | [73 empty] | -
Base-Build | UPW |  |  |  | UPW | Mechanical | Equipment ( Tank 等工程相關的設備) | USC24C008 | USCSB2407096A | 774 | UPW B Side Project | 4511 | C |  | Anion Tower Materials_UPW | 45490 | 45491 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 774 | 620 | 154 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2403224A | 773.85 | F21P1 Module Tool Interconnection CVD | 3919 | C |  | AMAT CVD Bolts, Square Washers, Spring Nuts, & Flat washers | 45373 | 45377 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 773.85 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 773.85 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2409026A | 772.8 | Tool Interconnection Project (Main Tool & Other Vendors) | 1229 | P |  | 12316065ST 1/2 X .065 WALL SMLS 316 TUBIN | 45548 | 45548 | [6 empty] | Industrial Pipe & Valve Inc. | PR Approved | PO Approved |  | 100% by progress, T/T 30 days | Eddie |  |  | Chia-Yi Chang | Eddie |  |  | Henry |  | N |  |  | 0 | 0 | 772.8 | 0 | 772.8 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2308168A | 770.5 | F21P1 Module Tool Interconnection DIF1-2 | 2462 | C |  | DIFF2: KDALS1 - ELECTRIC WIRE CONNECTION MATERIALS | 45167 | 45170 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 770.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 770.5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401102A | 769.93 | F21P1-0404_H_labor for 50 tools_MICU | 3289 | C |  | Brother P-Touch PT- D610BT label maker, For plastic system, tool hook up team for 100 tools | 45305 | 45307 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 699.93 | 0.90908 | 70 | 0 | 70 | 0 | 699.93 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USCSB2406116A | 769.85 | F21P1 Chemical & WCCS package | 4356 | C |  | lay down box | 45467 | 45468 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 769.85 | 0 | 769.85 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403255A | 769.85 | F21P1 WWT package (Installation and 2 batch tanks) | 3948 | C |  | WWT Hardware_20240320 (A Side) | 45378 | 45378 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 769.85 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 769.85 |  | 0 |  |  |  |  | 115.4775 |  |  |  | 115.4775 |  |  |  | 115.48 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2308156A | 768.91 | F21_AZQR_Hookup_ Interconnection | 2450 | C |  | QR LABS: CHAD/FAD LABS - Lan Cable Tray | 45163 | 45164 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 768.91 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 682.3 | 0 | 0 | 0 |  |  | 0 | 86.61 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405036A | 768 | Tool Interconnection Project (Main Tool & Other Vendors) | 1078 | P |  | Manpower Pay to CGS Global for Tool ID: KESTT1 for Cable Tray Divider installation. Time Card on 3.15.2024 for Miguel Argueta and Mario Diaz | 45423 | 45426 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 768 | 0 | 768 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2309071A | 766.43 | F21P1 Module Tool Interconnection CMP1 | 2545 | C |  | AMAT_CMP_KMOPA2-C / KMOPA5-C / KMOPAB-C_cush clamps, strut channel, strut channel bracket, nut, washers | 45183 | 45191 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 706.84 | 0.92225 | 59.59 | 0 | 59.59 | 0 | [40 empty] | 0 | 0 | 0 | 706.84 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2310166A | 766.24 | F21P1 Module Tool Interconnection CVD | 2820 | C |  | Swagelok 90 Elbows | 45225 | 45225 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 766.24 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 | 766.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401156A | 765.68 | F21P1-0404_H_labor for 50 tools_MICU | 3341 | C | -01 | John was cornered by TSMC today to purchase hand tools asap. | 45310 | 45311 | -258.75 | 1024.43 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: PR amendment on this to reflect the actual cost. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 765.68 | 1 | 0 | 0 | 0 | 0 | 765.68 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2404024A | 765 | F21P1 UPW | 4020 | C |  | Butterfly Valves for Train B | 45385 | 45387 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 765 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 765 | [6 empty] | 688.5 |  | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208022A | 764.7 | F21P1 UPW | 221 | P0 |  | 24in Monitors | 44800 | 44826 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 764.7 | 1 | 0 | 0 | 0 | 0 | 764.7 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402175A | 764.2 | F21P1-0404_H_labor for 50 tools_MICU | 3604 | C | -01 | label, cabinet and magnet, tool hookup team | 2/20/2024 2/29/2024 8/22/2024 | 2/22/2024 3/1/2024 8/28/2024 | -206.21 | 970.41 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: change the quantity as request R2: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 764.2 | 1 | 0 | 0 | 0 | 0 | 764.2 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111035A | 764.12 | F21P1 UPW | 46 | P0 |  | Bulletin Boards | 44517 | 44524 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 764.12 | 1 | 0 | 0 | 0 | 0 | 764.12 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C006 | USCSB2308086A | 763.67 | F21P1 Module Tool Interconnection EPI | 2383 | C |  | EPI: KCEPS1 - UNITSTRUT & CONDUIT | 45154 | 45155 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 760.34 | 0.99564 | 3.33 | 0 | 3.33 | 0 | [40 empty] | 682.34 | 0 | 0 | 0 |  | 0 | 0 | 78 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111056A | 762.32 | F21P1 UPW | 57 | P0 |  | Double sided white boards | 44524 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 762.32 | 1 | 0 | 0 | 0 | 0 | 762.32 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | MIC - Material | Material |  |  | Others |  |  | USC22C016 | USCSB2301015A | 761.76 | Asahi Valve and Positioner from Harrington |  | C |  | Asahi valve from Harrington | 44936 | 44936 | [23 empty] | 761.76 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 761.76 | [8 empty] | 0 |  | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208020A | 758.03 | F21P1 UPW | 219 | P0 |  | Revu License | 44800 | 44820 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 758.03 | 1 | 0 | 0 | 0 | 0 | 758.03 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112029A | 758.03 | F21P1 UPW | 92 | P0 |  | Bluebeam Revu | 44553 | 44558 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang |  |  | Matt |  |  |  |  | 758.03 | 1 | 0 | 0 | 0 | 0 | 758.03 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208002A | 758.03 | F21P1 UPW | 203 | P0 |  | Bluebeam Revu | 44777 | 44784 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 758.03 | 1 | 0 | 0 | 0 | 0 | 758.03 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303035A | 757.58 | F21P1 WWT package (Installation and 2 batch tanks) | 1777 | C |  | Bushings for 6.5 LB2 | 44993 | 45008 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 757.58 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 757.58 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303069A | 756.73 | F21P1 WWT package (Installation and 2 batch tanks) | 1808 | C |  | Bolts/Gaskets | 45001 | 45006 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 756.73 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 756.73 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201011A | 755.55 | F21P1 UPW | 105 | P0 |  | Monitor | 44579 | 44580 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 755.55 | 1 | 0 | 0 | 0 | 0 | 755.55 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C011 | USCSB2406062A | 755.28 | F21 TMAH System | 4295 | C |  | F21 WWT industrial media converter | 45454 | 45454 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved | [14 empty] | 755.28 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 755.28 | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403162A | 755.16 | F21P1-0404_H_labor for 50 tools_MICU | 3861 | C |  | cleanroom tapes shared by all hk trades | 45366 | 45369 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 696 | 0.92166 | 59.16 | 0 | 59.16 | 0 | [52 empty] | 0 | 0 | 0 |  | 696 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311127A | 752.36 | F21P1-0404_H_labor for 50 tools_MICU | 2977 | C |  | Electrolyte Gold, Replenishment solution | 45259 | 45262 | [6 empty] | Servomex Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 752.36 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 752.36 |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401076A | 750.4 | F21P1-0404_H_labor for 50 tools_MICU | 3265 | C |  | Galvanized Steel Pail 1-1/4 Gallon Capacity, Shared for all system for materials carriage. | 45303 | 45307 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 750.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 750.4 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Triazole | Material | DCR Scope | WWT | WWT | Civil | Labor | USC22C022 | USCSB2312079A | 750 | F21P1 Triazole treatment system | 3071 | C |  | WWT - Remove Unused Triazole Pad in WRC between E14 and D14 | 45273 | 45274 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 750 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 750 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C003 | USCSB2401073A | 749.93 | F21P1 UPW | 3262 | C |  | UPW-Northernmedia-ACF gravels | 45303 | 45317 | [6 empty] | Northern Filter Media, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 749.93 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 749.93 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401168A | 748.7 | F21P1-0404_H_labor for 50 tools_MICU | 3353 | C |  | steel step drill bit set and 3-plane laser level kit for HK PCW trade | 45312 | 45313 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 748.7 | 1 | 0 | 0 | 0 | 0 | 748.7 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2211040A | 747.8 | F21P1 WWT package (Installation and 2 batch tanks) | 1573 | C |  | wastewater adapter | 44895 | 44897 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 747.8 | 0 | 747.8 | 747.8 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 112.17 |  |  |  | 112.17 |  |  |  | 112.17 |  | 747.8 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2307119A | 747.8 | F21 TMAH System | 2283 | C | -01 | WWT-PVC material | 45133 | 2023/7/26 2023/9/14 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Trade Terms Changed |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 747.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 747.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206011A | 744.29 | F21P1 UPW | 178 | P0 |  | AutoCAD | 44724 | 44736 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 744.29 | 1 | 0 | 0 | 0 | 0 | 744.29 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2210002A | 743.8 | F21P1 Chemical & WCCS package | 247 | P0 |  | 24in Monitor | 44835 | 44839 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 743.8 | 1 | 0 | 0 | 0 | 0 | 743.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2405010A | 740 | F21P1-0404_H_labor for 50 tools_MICU | 3984 | C |  | Washer nut and bolt for HK Power trade for 200 tools | 45415 | 45415 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 740 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 740 |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409039A | 740 | TSMC Fab 21 P1B Tool Hook Up | 4824 | C |  | Label for gas and plastic system, p1-b tool hookup team | 45542 | 45545 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 740 | 0 | 740 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404098A | 739.68 | Tool Interconnection Project (Main Tool & Other Vendors) | 1048 | P | -01 | Cleanroom Notebook, 5.5x8.5, College Rule | 45407 | 2024/4/26 2024/06/11 | 369.84 | 369.84 |  |  | V |  | Thomas Scientific Holdings LLC | PR Approved | PO Approved | R1: order was shipped as a double order so PO was adjusted to cover cost of both see second packing slip | [13 empty] | 739.68 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 739.68 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207009A | 732.65 | F21P1 UPW | 189 | P0 |  | 24in Monitor | 44771 | 44784 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 732.65 | 1 | 0 | 0 | 0 | 0 | 732.65 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2404128A | 731.5 | F21P1 Module Tool Interconnection ETC1-3 | 4113 | C |  | TOOL ID: KEPOL6 INSTALLATION OF CIP SENSORS TO DAQ AND TERMINICATIONS | 45398 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 731.5 | 0 | 731.5 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403044A | 731.28 | Tool Interconnection Project (Main Tool & Other Vendors) | 870 | P | -01 | 705 QC Solvent Cement PVC QT CLR Low VOC Med Bodied Fast Set MC/AC | 45363 | 2024/3/11 2024/3/12 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Change Location |  | Yikang Wang | [11 empty] | 731.28 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 731.28 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402178A | 728 | F21P1-0404_H_labor for 50 tools_MICU | 3607 | C | -01 | MILWAUKEE Drill for HK Power trade | 45342 | 2/21/2024 2/23/2024 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | R1: Change Delivery Method to Self Pickup per requested |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 728 | 1 | 0 | 0 | 0 | 0 | 728 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2312015A | 726.75 | F21P1 Module Tool Interconnection ETC1-3 | 3009 | C |  | ETC2，Interconnection material Cable Tray Divider | 45265 | 45267 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 726.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 726.75 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2402062A | 721 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3504 | C |  | Consolidated Electrical Distributors Fiber Optic Material for GWH OSC | 45329 | 45330 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 721 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 721 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C002 | USCSB2406123A | 720 | F21P1-0404_H_Hallway plate install_MICU | 4362 | C |  | Cleanroom tapes for foundation | 45468 | 45468 | [6 empty] | Xiang Sheng Hardware Enterprise Co., Ltd. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 720 | 0 | 720 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C032 | USCSB2309038A | 720 | F21_AZQR_Hookup_ Interconnection | 2515 | C |  | QR: KAX01/KXAT02 – CABLE INSTALLATION | 45178 | 45182 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 720 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 720 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312082A | 719.1 | Tool Interconnection Project (Main Tool & Module) | 625 | P |  | Interconnect cable pull for KECOL4 (ETC2) | 45283 | 45289 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 719.1 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 719.1 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401243A | 716.3 | F21P1-0404_H_labor for 50 tools_MICU | 3424 | C |  | hole saw for Tsmc training center, tool hookup team | 45321 | 45323 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 634.1 | 0.88524 | 82.2 | 0 | 82.2 | 0 | 634.1 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207004A | 715.36 | F21P1 UPW | 184 | P0 |  | large 72 inch locking file cabinet | 44770 | 44784 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 715.36 | 1 | 0 | 0 | 0 | 0 | 715.36 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408116A | 714.9 | TSMC Fab 21 P1B Tool Hook Up | 4729 | C |  | Label for GAS system, P1-B hookup team | 45531 | 45533 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 597.93 | 0.83638 | 116.97 | 0 | 116.97 | 0 | [72 empty] | 597.93 | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312157A | 714.04 | F21P1-0404_H_labor for 50 tools_MICU | 3146 | C |  | Vern and Lewis unincluded taxes and services fee | 45281 | 45300 | [6 empty] | Vern Lewis Welding Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 605.72 | 0.8483 | 108.32 | 0 | 108.32 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 605.72 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2304068A | 712.56 | F21_AZQR_Hookup_ Interconnection | 1907 | C |  | QR LABS Swagelok Adaptors #2 | 45038 | 45040 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 712.56 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 712.56 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402265A | 710 | F21P1-0404_H_labor for 50 tools_MICU | 3690 | C |  | Trailer related, tool hookup team | 45350 | 45351 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 613.41 | 0.86396 | 96.59 | 0 | 96.59 | 0 | 613.41 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310002A | 708.62 | Tool Interconnection Project (Main Tool & Module) | 436 | P |  | ARGON, REFRIGERATED LIQUID, 2.2 | 45202 | 45204 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 708.62 | 0 | 708.62 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312051A | 707.63 | Tool Interconnection Project (Main Tool & Module) | 597 | P |  | Cable Pull for KDPOT2. 2 manpower for 1 day 11/10/2023. (Robert Nelson) | 45273 | 45274 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 707.63 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 707.63 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2312178A | 706.55 | F21P1 WWT package (Installation and 2 batch tanks) | 3165 | C |  | Laminator Sheets&Mounting Tape | 45283 | 45287 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 623 | 0.88175 | 83.55 | 0 | 83.55 | 27.036 | 623 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 27.036
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408075A | 706.49 | TSMC Fab 21 P1B Tool Hook Up | 4691 | C |  | Handtools for HK Exhaust trade for 200 tools | 45520 | 45523 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 609.89 | 0.86327 | 96.6 | 0 | 96.6 | 0 | 609.89 | [72 empty] | -
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201007A | 705.89 | F21P1 UPW | 101 | P0 |  | 10.3" Tablet | 44579 | 44580 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 705.89 | 1 | 0 | 0 | 0 | 0 | 705.89 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C003 | USCSB2312194A | 705.84 | F21P1 UPW | 3181 | C |  | UPW-commissioning horse | 45289 | 45296 | [6 empty] | Bridgestone Hosepower, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 705.84 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 705.84 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2401057A | 703.29 | F21P1 WWT package (Installation and 2 batch tanks) | 3246 | C |  | WWT_pressure gauge | 45301 | 45303 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 703.29 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 703.29 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402040A | 703.04 | Tool Interconnection Project (Main Tool & Other Vendors) | 763 | P |  | Electrical cable pull for KEPOL8 and KEPOL2 - LAM Interconnections | 45329 | 45352 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 703.04 | 2436.9 | -1733.86 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405035A | 702 | Tool Interconnection Project (Main Tool & Other Vendors) | 1077 | P |  | PAY TO J.T. THORPE FOR TOOL ID: KETRTE ETC 3 ON 4.3.2024 SCAFFOLD WAS TAKEN DOWN THAT WAS USED ON TOOL ID: KETRTE | 45422 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 702 | 0 | 702 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2407153A | 702 | F21P1 Module Tool Interconnection ETC1-3 | 4562 | C |  | Tool: KETRTE Scaffolding requested by Trey Pubins | 45499 | 45504 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 702 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 702 |  |  |  |  | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C006 | USCSB2312120A | 701.55 | F21P1 Module Tool Interconnection EPI | 2975 | C |  | EPI: KCEPS1: CONNECTORS & BUSHINGS | 45276 | 45455 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 701.55 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 701.55 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2308008A | 700 | F21P1 Module Tool Interconnection CMP1 | 2311 | C |  | AMAT CMP，Interconnection material KMOPA2-C, KMOPA5-C, KMOPAB-C, 3/8'' PFA | 45140 | 45142 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 700 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 700 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material |  |  | Low Voltage | Mechanical |  | USC22C013 | USCSB2407134A | 700 | F21P1 QR Lab Security & CCTV | 4547 | C |  | F21 P1 VOC duct Label | 45496 | 45496 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | [14 empty] | 700 | 1 | 0 | 0 | 0 | 700 | [68 empty] | 700 |  |  |  |  | - | 700 |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USC2407033A | 699 | TSMC Fab 21 P1B Tool Hook Up | 1164 | P |  | QAQC Visual Testing Level I/II Course for Tool Hook-up | 45497 | 45510 | [6 empty] | WorldSpec NDT Training | PR Approved | PO Approved | [14 empty] | 699 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 699 |  |  | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401059A | 696 | F21P1-0404_H_labor for 50 tools_MICU | 3248 | C |  | Cleanroom tapes shared by all hk trades. Elias's request | 45302 | 45302 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 696 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 696 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2311064A | 695.36 | F21P1 Module Tool Interconnection CMP1 | 2919 | C |  | AMAT CMP，Interconnection material Primer, 1 3/8" cush clamp | 45245 | 45246 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 695.36 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 695.36 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204010A | 693.57 | F21P1 UPW | 157 | P0 |  | AutoCAD License | 44673 | 44676 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 693.57 | 1 | 0 | 0 | 0 | 0 | 693.57 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2405098A | 690.84 | F21P1 Module Tool Interconnection LIT2-3 | 4117 | C |  | Lit 3: KPPTT1, KPPTT2, and KPPTT3: Material: Flex Exhaust for Blower Box | 45428 | 45441 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 690.84 | 1 | 0 | 717.37 | -717.37 | 0 | [56 empty] | 0 | [5 empty] | 690.84 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309031A | 690 | Tool Interconnection Project (Main Tool & Module) | 420 | P |  | KPD801-T GREENBERRY EXHAUST LABOR | 45192 | 45197 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 655.5 | 0.95 | 34.5 | 0 | 34.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 655.5 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202013A | 689.95 | F21P1 UPW | 120 | P0 |  | Desks for modular | 44611 | 44643 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 689.95 | 1 | 0 | 0 | 0 | 0 | 689.95 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2312191A | 688.18 | F21P1-0404_H_labor for 50 tools_MICU | 3178 | C |  | brother label tape, for UPW and power system, tool hookup team | 45289 | 44929 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 579.18 | 0.84161 | 109 | 0 | 109 | 0 | 579.18 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312027A | 680.88 | Tool Interconnection Project (Main Tool & Module) | 576 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45266 | 45268 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 680.87 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 680.87 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C031 | USCSB2311052A | 680.19 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2907 | C |  | DP-B06 N2-NOZ 15A-2P Breaker | 45240 | 45239 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 680.19 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 680.19 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2306025A | 680.02 | F21P1 Chemical & WCCS package | 2060 | C |  | Argon for Chemical welding | 45084 | 45125 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 612.52 | 0.90074 | 67.5 | 0 | 67.5 | 0 | [33 empty] | 0 |  |  | 612.52 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 67.5 | [9 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C059 | USCSB2310167A | 680 | F21P1 Foundation T&M | 2821 | C | -01 | 3000 T-Bolts | 45225 | 2023/10/26 2023/11/03 | -1300 | 1980 | V |  |  |  | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | Negotiate new rate and change packaging |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 680 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 680 | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C047 | USCSB2308146A | 679.9 | F21P1 HK Seismic Installation | 2441 | C |  | Seismic bracket modification for ME dept. 1st batch | 45161 | 45161 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 679.9 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 679.9 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C047 | USCSB2308148A | 679.9 | F21P1 HK Seismic Installation | 2443 | C |  | Seismic bracket modification for ME dept. 2nd batch | 45161 | 45161 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 679.9 | 0 | 679.9 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2403075A | 678.66 | Tool Interconnection Project (Main Tool & Other Vendors) | 896 | P | -01 | 6 ft ladder | 45370 | 2024/3/19 2024/3/20 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | change remark based on revised PR |  | Yi En Wong | [11 empty] | 537.97 | 0.79269 | 140.69 | 0 | 140.69 | 0 | 537.97 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2405183A | 678.3 | Tool Interconnection Project (Main Tool & Other Vendors) | 1117 | P |  | STAINLESS MATERIAL | 45443 | 45446 | [6 empty] | Cliff’s Welding, Inc | PR Approved | PO Approved | [14 empty] | 678.3 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 678.3 |  |  | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408104A | 677.85 | TSMC Fab 21 P1B Tool Hook Up | 4712 | C |  | QAQC OFFICE RELATED SUPPLIES | 8/23/2024 8/29/2024 | 8/27/2024 8/29/2024 9/18/2024 | 8.08 | 669.77 |  |  | V | V | Amazon.com, Inc. | PR Approved | PO Approved | R1: BUSINESS PRICE R2: match with the actual spending | [13 empty] | 677.85 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 677.85 | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404099A | 676 | Tool Interconnection Project (Main Tool & Other Vendors) | 1049 | P |  | Manpower Pay to RS Payroll Servicies for Tool IDs: KEPOT1, KESRT1, KESRT2 for Time cards on 3.4.2024 | 45407 | 45408 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 676 | 0 | 676 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408049A | 672 | TSMC Fab 21 P1B Tool Hook Up | 4667 | C |  | Circular Saw Blade for HK PCW tools for 50 tools | 45514 | 45519 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 672 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 672 |  |  | -
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2304048A | 667 | F21P1 UPW | 1888 | C |  | UPW Tomoe angle adjuster | 45035 | 45043 | [6 empty] | Tomoe USA, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 667 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 667 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311081A | 665.67 | F21P1-0404_H_labor for 50 tools_MICU | 2934 | C |  | Turnlok Recept for Third. Tool id: ACM-B06, AMC-B03, AMC-B10, AIB-B02, APH-B11, AET-C13, ATF-B07, ATF-C15, ATF-E1 AE | 45247 | 45271 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 665.67 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 665.67 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2306009A | 663.36 | Tool Interconnection Project (Main Tool & Module) | 294 | P |  | ARMAFLEX 5/8 X 1/2 | 45080 | 45083 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 663.36 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 663.36 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306010A | 660 | Tool Interconnection Project (Main Tool & Module) | 295 | P |  | HOSE-MD1 ALUMIN. DUCT HOSE- 2INX10FT W/ TUBE | 45080 | 45128 | [6 empty] | FLEXICRAFT INDUSTRIES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 660 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 660 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C002 | USCSB2307104A | 660 | F21P1-0404_H_Hallway plate install_MICU | 2269 | C |  | Plastic head of hard barricade | 45129 | 45131 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 660 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 660 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Electrical | Material | USC23C045 | USCSB2407027A | 659.84 | WWT Change Order (Piping) | 4426 | C |  | A site LB2 VFD power cable re-pull | 45477 | 45476 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 659.84 | 659.84 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402018A | 659.4 | F21P1-0404_H_labor for 50 tools_MICU | 3461 | C |  | Material Request for the label.for 150 tools, tool hookup team | 45323 | 45323 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 376.02 | 0.57025 | 283.38 | 0 | 283.38 | 0 | 376.02 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C010 | USCSB2402196A | 652.3 | tsmc AZ sewer and water pipeline installation | 3623 | C |  | Laydown, Bins & Rack to organize bolts & elbows | 45343 | 45351 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 592.98 | 0.90906 | 59.32 | 0 | 59.32 | 0 | 592.98 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402189A | 652 | F21P1 Chemical & WCCS package | 3618 | C |  | CDS coax tube | 45343 | 45344 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 652 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 652 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2401023A | 651.98 | F21P1 AMAT Interconnection | 3214 | C |  | Cordless Cable Cutter | 45296 | 45301 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 651.98 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 651.98 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2312052A | 650 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3045 | C |  | Discount Saw Cut LLC Concrete core drilling in support of Taiwan Vendors | 45268 | 45300 | [6 empty] | DISCOUNT SAW CUT, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 650 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Site Expense | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402185A | 650 | F21P1 Chemical & WCCS package | 3614 | C |  | CDS Welder rental for Chemical welding. | 45343 | 45344 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 650 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C009 | USCSB2306076A | 650 | F21P1 WWT package (Installation and 2 batch tanks) | 2109 | C |  | WWT-CCB dry-run CO | 45093 | 45093 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 650 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Site Expense | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2403017A | 650 | F21P1 Chemical & WCCS package | 3726 | C |  | CDS Welder rental for Chemical welding.(RENTAL FROM 2-2-24 TO 3-1-24) | 45352 | 45357 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 650 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Site Expense | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402227A | 650 | F21P1 Chemical & WCCS package | 3654 | C |  | CDS Welder rental for Chemical welding(RENTAL FROM 1-4-24 TO 2-1-24) | 45345 | 45351 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 650 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2311049A | 650 | F21P1 Chemical & WCCS package | 2904 | C |  | CDS Welder rental for Chemical welding. | 45240 | 45240 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 650 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C003 | USCSB2307140A | 650 | F21P1 UPW | 2302 | C |  | UPW-CCB dry-run | 45136 | 45136 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 650 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Site Expense | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402187A | 650 | F21P1 Chemical & WCCS package | 3616 | C |  | CDS Welder rental for Chemical welding.(RENTAL FROM 11-7-23 TO 12-5-23) | 45343 | 45344 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [51 empty] | 650 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403114A | 649 | F21P1-0404_H_labor for 50 tools_MICU | 3816 | C |  | Warning sign 3-1/2 in. x 5 in. NEC Arc Flash Adhesive for HK power trade | 45363 | 45363 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 590 | 0.90909 | 59 | 0 | 59 | 0 | 590 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC |  |  |  | Low Voltage | Electrical | M+L | USC24C007 | USCSB2409013A | 648.03 | Low Voltage B Side Project | 4783 | C |  | F21 P1 VOC Electricity Change Order _CO#25_Batch 6/6 | 45539 | 45545 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | [14 empty] | 648.03 | 1 | 0 | 648.03 | -648.03 | 0 | [73 empty] | 648.03
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USC2404067A | 648 | F21P1 AMAT Interconnection | 1021 | P |  | insulation plug | 45398 | 45412 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved | [14 empty] | 648 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 648 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112027A | 647.12 | F21P1 UPW | 90 | P0 |  | Sceptre Monitor 24in | 44548 | 44554 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang |  |  | Matt |  |  |  |  | 647.12 | 1 | 0 | 0 | 0 | 0 | 647.12 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406027A | 644.49 | F21P1-0404_H_labor for 50 tools_MICU | 4253 | C |  | Cleanroom tape for HK shared by all system | 45448 | 45448 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 644.49 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 644.49 | [10 empty] | - |  |  | 0
[5 empty] | Others |  |  | USC24B002 | USC2410001A | 644.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 1263 | P |  | REDUCING UNION 1" SWG X 1/2" SWG | 45566 | 45567 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 644.4 | 0 | 644.4 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401074A | 644 | Tool Interconnection Project (Main Tool & Other Vendors) | 694 | P |  | KESRT2 MANPOWER PAY FOR CGS PAYROLL | 45316 | 45316 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 644 | 0 | 644 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2405043A | 642.05 | F21P1-0404_H_labor for 50 tools_MICU | 4051 | C |  | lock up the Scissorlift, Tool hookup team for 500 tools | 45420 | 45420 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 642.05 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 642.05 | [6 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208012A | 640.2 | F21P1 UPW | 212 | P0 |  | Black metal folding chairs for workers lunchroom at Fab and 8 foot folding tables | 44789 | 44798 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 640.2 | 1 | 0 | 0 | 0 | 0 | 640.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402018A | 636.84 | Tool Interconnection Project (Main Tool & Other Vendors) | 744 | P |  | FLEX LT3UAGRY | 45324 | 45327 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 636.84 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 595.52 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  |  |  | UPW | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C003 | USCSB2409001A | 634.55 | F21P1 UPW | 4771 | C |  | CIA Sensor | 45539 | 45540 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 634.55 | 0 | 634.55 | 0 | [73 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312048A | 632 | Tool Interconnection Project (Main Tool & Module) | 594 | P |  | KESDL1 cable pull in-house manpower EOPS | 45273 | 45278 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 632 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 632 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312049A | 632 | Tool Interconnection Project (Main Tool & Module) | 595 | P |  | KEPOL3- Interconnect cable pull for KEPOL3 (ETC1) | 45273 | 45275 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 632 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 632 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C011 | USCSB2402010A | 629.87 | F21 TMAH System | 3453 | C |  | HFC/ Tmah tools | 45323 | 45322 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 629.87 | 1 | 0 | 0 | 0 | 0 | 629.87 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404065A | 627 | Tool Interconnection Project (Main Tool & Other Vendors) | 1018 | P |  | Manpower Pay for CCE . Timecard for 1.30.2024 | 45398 | 45402 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 627 | 0 | 627 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207018A | 626.32 | F21P1 UPW | 198 | P0 |  | 24in Monitor | 44771 | 44784 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 626.32 | 1 | 0 | 0 | 0 | 0 | 626.32 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406154A | 625.95 | F21P1-0404_H_labor for 50 tools_MICU | 4401 | C |  | For GAS and Plastic system, 100 tools | 2024/6/30 2024/9/26 | 2024/7/1 2024/9/26 | -161.46 | 787.41 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: Per purchaning team request, amend to the final amount. | [13 empty] | 625.95 | 1 | 0 | 0 | 0 | 0 | 625.95 | [72 empty] | - |  |  | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2409035A | 624.97 | WWT B side Project | 4821 | C |  | WWT shortage of hardware materials on the B side and WRC | 45542 | 45545 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 624.97 | 0 | 624.97 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2406016A | 624.58 | Tool Interconnection Project (Main Tool & Other Vendors) | 1136 | P |  | FLEX LT2-1/2UAGRY 2-1/2 UL LIQ-TITE | 45464 | 45467 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 624.58 | 624.58 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111057A | 624.22 | F21P1 UPW | 58 | P0 |  | Mini fridges | 44524 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 624.22 | 1 | 0 | 0 | 0 | 0 | 624.22 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC22C020 | USCSB2401136A | 623.39 | F21P1 Penetration Pipe | 3321 | C |  | Laydown Material - Home Depot | 45309 | 45314 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 602.8 | 0.96697 | 20.59 | 0 | 20.59 | 0 | 602.8 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2210012A | 623.18 | F21P1 UPW | 255 | P0 |  | Rigid Shop Vacuum 16 gallon dry and wet/yellow jacket extension cords/vacumn filters | 44839 | 44848 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 623.18 | 1 | 0 | 0 | 0 | 0 | 623.18 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C001 | USCSB2310121A | 622.88 | TEL Main Tool Interconnection | 2781 | C |  | 25 cable tray dividers BLN 73A-120 (KCSCS5,KCSCS8,KDCRS3,KDSNB1) | 45218 | 45219 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 622.88 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 622.88 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2310185A | 621.84 | F21P1 WWT package (Installation and 2 batch tanks) | 2837 | C |  | WWT CDA SUS Socket Weld Fittings | 45227 | 45229 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 621.84 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 621.84 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403073A | 621.24 | Tool Interconnection Project (Main Tool & Other Vendors) | 894 | P |  | SS - 12 - E FNPT Elbow 3/4' | 45367 | 45367 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 621.24 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 621.24 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2401068A | 619.99 | F21P1-0404_H_labor for 50 tools_MICU | 3257 | C |  | office supplies for tool hookup department shared by all systems | 1/11/2024 8/22/2024 | 1/13/2024 8/28/2024 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 608.88 | 0.98208 | 11.11 | 0 | 11.11 | 0 | 608.88 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2303101A | 619.44 | F21P1 WWT package (Installation and 2 batch tanks) | 1838 | C |  | NFPA labels | 45015 | 45019 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 619.44 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 619.44 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401104A | 619.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 721 | P |  | PAN FSD748D #24 PP DIN 1W FRL PANDUIT FSD74-8-D COVERED SINGLE WIRE FERRULE | 45321 | 45321 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 619.17 | 0.99995 | 0.03 | 0 | 0.03 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 619.17 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403273A | 619.2 | F21P1-0404_H_labor for 50 tools_MICU | 3966 | C |  | Grounding Plug and Step Drill Set for exhaust | 45379 | 45385 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 619.2 | 0 | 619.2 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Civil | Material | USC24C005 | USCSB2407060A | 619.03 | Chemical & WCCS B Side Project | 4457 | C |  | CHEM_CDS project_Ladder and EXT code | 45484 | 45484 | [6 empty] | NEFCO Construction Supply LLC | PR Approved | PO Approved | [14 empty] | 619.03 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 619.03 |  |  | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401107A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 724 | P |  | FLEX LT3UAGRY | 45322 | 45322 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402017A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 743 | P |  | FLEX LT3UAGRY | 45324 | 45327 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401108A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 725 | P |  | FLEX LT3UAGRY | 45322 | 45322 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402020A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 746 | P |  | FLEX LT3UAGRY | 45324 | 45327 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401112A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 728 | P |  | FLEX LT3UAGRY | 45322 | 45322 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401113A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 729 | P |  | FLEX LT3UAGRY | 45322 | 45322 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401114A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 730 | P |  | FLEX LT3UAGRY | 45322 | 45322 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401110A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 727 | P |  | FLEX LT3UAGRY | 45322 | 45322 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401102A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 719 | P |  | FLEX LT3UAGRY | 45321 | 45321 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402057A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 775 | P |  | FLEX LT3UAGRY | 45332 | 45335 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402024A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 750 | P |  | FLEX LT3UAGRY | 45324 | 45327 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402023A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 749 | P |  | FLEX LT3UAGRY | 45324 | 45327 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402022A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 748 | P |  | FLEX LT3UAGRY | 45324 | 45327 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402021A | 618.12 | Tool Interconnection Project (Main Tool & Other Vendors) | 747 | P |  | FLEX LT3UAGRY | 45324 | 45327 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401101A | 618.11 | Tool Interconnection Project (Main Tool & Other Vendors) | 718 | P |  | FLEX LT3UAGRY | 45321 | 45321 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.11 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.31 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2309118A | 615.96 | F21_AZQR_Hookup_ Interconnection | 2590 | C | -02 | QR LABS: KXAT01, KXAT02, KXEX02 6 & 9-INCH BEND, BLINE 9 ZN-1204NB CLAMPS | 45189 | 2023/9/26 2023/9/30 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Supplier (John McDonald) contact on 9/29 6:27 AM to change completion date due to previous shipment negotiation. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 615.96 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 615.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402116A | 612.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 826 | P |  | BLINE 73A120 | 45351 | 45351 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 612.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 612.4 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2306034A | 612.35 | Tool Interconnection Project (Main Tool & Module) | 318 | P |  | DEMAND CHARgE CYLINDERS | 45087 | 45118 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 612.35 | 0 | 612.35 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2402030A | 610.3 | F21P1 AMAT Interconnection | 3473 | C |  | KCSMA6, KCASA4 Core Hole Sleeve Handoff | 45325 | 45328 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 610.3 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 610.3 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202016A | 608.04 | F21P1 UPW | 123 | P0 |  | 24in Monitor | 44614 | 44617 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 608.04 | 1 | 0 | 0 | 0 | 0 | 608.04 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C001 | USC2401055A | 607.7 | TEL Main Tool Interconnection | 677 | P |  | KECOT1 MANPOWER PAY FOR SAN TAN FIRE,LLC. | 45314 | 45314 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 607.7 | 0 | 607.7 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C004 | USCSB2403181A | 607.09 | F21P1 WWT package （USA EQ-FRP tank) | 3878 | C | -01 | Global Industrial - MIMO - Move In/Move Out Team | 45369 | 2024/3/20 2024/3/28 | [5 empty] | V | Global Equipment Company Inc. | PR Approved | PO Approved | R1: Listing Global Industrial Concerns on the PO |  | Ta Wei Wang | [11 empty] | 551.9 | 0.90909 | 55.19 | 0 | 55.19 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 551.9 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2210005A | 605.3 | F21P1 UPW | 250 | P0 |  | 24in Monitor | 2022/10/1 | 44859 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 605.3 | 1 | 0 | 0 | 0 | 0 | 605.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403121A | 603.68 | F21P1 WWT package (Installation and 2 batch tanks) | 3823 | C |  | WWT 5_Blind Flange_20240312 (A Side) | 45364 | 45365 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 603.68 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 603.68 |  |  |  |  | 90.552 |  |  |  | 90.552 |  |  |  | 90.55 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2310035A | 603.02 | Tool Interconnection Project (Main Tool & Module) | 455 | P |  | FLEX LT2UAGRY: 2 UL LIQ-TITE | 45216 | 45219 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 603.04 | 1 | -0.02 | 0 | -0.02 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 603.04 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C009 | USCSB2403040A | 601.82 | F21P1 WWT package (Installation and 2 batch tanks) | 3747 | C | -01 | WWT - Replacement guard for P-350 AB | 45356 | 2024/3/15 2024/3/21 | 85.02 | 516.8 | V |  |  |  | Phoenix Pumps, Inc. | PR Approved | PO Approved | R1: Change PR amount to add freight and credit card fee |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 601.82 | 1 | 0 | 0 | 0 | 0 | 601.82 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 90.273 |  |  |  | 90.273 |  |  |  | 90.273 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2306060A | 601 | F21P1-0404_H_Hallway plate install_MICU | 2094 | C |  | ADI-C-01 shift 3cm modification | 45092 | 45113 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 570.95 | 0.95 | 30.05 | 0 | 30.05 | 0 | [33 empty] | 0 | [6 empty] | 570.95 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407038A | 600.99 | F21P1-0404_H_labor for 50 tools_MICU | 4437 | C |  | B Side Insulating Roll Blanket for HK Power for 100 tools | 45482 | 45490 | -589.75 | 1190.74 |  |  |  |  | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved | [14 empty] | 0 | 0 | 600.99 | 0 | 600.99 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2301001A | 600 | F21P1 UPW | 260 | P |  | Non Woven Shoe Cover | 44932 | 44932 | [6 empty] | Super Starnix SDN BHD | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 600 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 600 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2307001A | 600 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2175 | C |  | Bay Alarm Company | 45108 | 45114 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 600 | 0 | 600 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401242A | 599.26 | F21P1 Chemical & WCCS package | 3423 | C |  | CDS Tee and Bulkhead. | 45321 | 45321 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 599.26 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 | 599.26 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401006A | 598.72 | F21P1-0404_H_labor for 50 tools_MICU | 3198 | C | -01 | T.W. Evans Cordage and Bucket, shared material for Gas and chemical system, tool hoop up team | 2024/1/3 2024/1/17 | 2024/1/4 2025/1/17 | -287.36 | 886.08 |  |  |  |  | The Home Depot, Inc | PR Approved | PO Approved | PO R1:Home depot out of stock, we can only purchase 1 quantity. |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 465.58 | 0.77763 | 133.14 | 0 | 133.14 | 0 | 465.58 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2402238A | 597.4 | F21P1 UPW | 3664 | C |  | UPW-Harrington-U bolts and tank gaskets | 45346 | 45349 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 597.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 597.4 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403044A | 596.81 | F21P1-0404_H_labor for 50 tools_MICU | 3751 | C |  | QAQC and office supply for trail 14, tool hookup team | 45357 | 45372 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 520.94 | 0.87287 | 75.87 | 0 | 75.87 | 0 | 520.94 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408002A | 596 | Tool Interconnection Project (Main Tool & Other Vendors) | 1173 | P | -01 | WA524T*1.5MM*20 Transparent table mat*1.5mm*20Y 交易條件:EXW | 45506 | 2024/8/2 2024/8/7 | [6 empty] | Xiang Sheng Hardware Enterprise Co., Ltd. | PR Approved | PO Approved | R1: Change Delivery Location and Payment Term | [13 empty] | 0 | 0 | 596 | 0 | 596 | [74 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407129A | 593.67 | TSMC Fab 21 P1B Tool Hook Up | 4543 | C |  | Double sided tape for HK exhaust team | 45493 | 45496 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 405 | 0.6822 | 188.67 | 0 | 188.67 | 0 | 405 | [72 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2210008A | 591.84 | F21P1 UPW | 252 | P0 |  | Two Rolling double sided whiteboards 72 x 40 for conference rooms. | 44838 | 44848 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 591.84 | 1 | 0 | 0 | 0 | 0 | 591.84 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USC2408003A | 591 | TSMC Fab 21 P1B Tool Hook Up | 1174 | P |  | Torque Wrenches | 45506 | 45520 | [6 empty] | Ceet Industries Inc DBA Trident Calibration Labs | PR Approved | PO Approved | [14 empty] | 0 | 0 | 591 | 0 | 591 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403293A | 591 | F21P1-0404_H_labor for 50 tools_MICU | 3985 | C |  | Nuts and bolts for pipe straps for HK PPL trade | 45381 | 45383 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 591 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [7 empty] | 591 | [6 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24B002 | USC2409057A | 590.56 | Tool Interconnection Project (Main Tool & Other Vendors) | 1260 | P |  | 1 1/4IN STR L/T CONN STEEL | 45562 | 45562 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 590.56 | 0 | 590.56 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311076A | 589.44 | Tool Interconnection Project (Main Tool & Module) | 544 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45258 | 45260 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 589.43 | 0.99998 | 0.01 | 0 | 0.01 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 589.43 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311075A | 589.43 | Tool Interconnection Project (Main Tool & Module) | 543 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45258 | 45261 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 589.42 | 0.99998 | 0.01 | 0 | 0.01 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 589.42 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C014 | USCSB2402166A | 583.22 | F21P1 Labor incentive program-MICU | 3597 | C |  | Laydown Material - U Line | 45339 | 45359 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 530.2 | 0.90909 | 53.02 | 0 | 53.02 | 0 | 530.2 | [51 empty] | 0 | 0 | 0 | [16 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311006A | 582.25 | Tool Interconnection Project (Main Tool & Module) | 481 | P |  | WIRE SO10/4 10/4 SOW-A SO TYPE; 250 FT; 250 LENGTH IN FT; COPPER CONDUCTOR MATERIAL; 600 V VOLTAGE RATING; -40 TO 60 DEG C TEMPERATURE RATING; 4 CONDUCTOR(S); EPDM RUBBER INSULATION MATERIAL; 10 AWG CONDUCTOR SIZE; COIL PACKAGE TYPE; 104 STRANDS STRANDING; BLACK JACKET COLOR | 45232 | 45234 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 582.25 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 582.25 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C006 | USCSB2309116A | 581.52 | F21P1 Module Tool Interconnection EPI | 2588 | C |  | EPI: KCEPS1: 4 UL LIQ TITE EG UNIVERSDAL CLAMP STEEL | 45189 | 45195 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 581.52 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 575.62 | 0 | 0 | 5.9 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401224A | 580 | F21P1-0404_H_labor for 50 tools_MICU | 3406 | C |  | Saw blade for gas system, tool hookup team | 45317 | 45367 | [6 empty] | Orbitalum North America | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 0 | 0 | 580 | 0 | 580 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Site Expense |  |  | Others |  |  | USC22C008 | USCSB2402257A | 579.06 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3683 | C |  | Grainger Work Table | 45349 | 45350 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 579.06 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 579.06 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401058A | 578.18 | Tool Interconnection Project (Main Tool & Other Vendors) | 680 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45314 | 45314 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401040A | 578.18 | Tool Interconnection Project (Main Tool & Other Vendors) | 663 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45310 | 45310 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401056A | 578.18 | Tool Interconnection Project (Main Tool & Other Vendors) | 678 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45314 | 45314 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401060A | 578.18 | Tool Interconnection Project (Main Tool & Other Vendors) | 681 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45314 | 45314 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401037A | 578.18 | Tool Interconnection Project (Main Tool & Other Vendors) | 660 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45309 | 45309 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401054A | 578.18 | Tool Interconnection Project (Main Tool & Other Vendors) | 676 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45314 | 45314 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2311062A | 578 | F21P1-0404_H_labor for 50 tools_MICU | 2917 | C | -01 | Hex for Tunyi. Tool id: ACM-B06 AMC-B03 AMC-B10 AIB-B02 APH-B11 AET-C13 ATF- | 45245 | 2023/12/11 2023/12/15 | -49.71 | 627.71 |  |  |  |  | Carson Sales Co Inc | PR Approved | PO Approved | PO R1: Tax Exempt |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 578 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 578 | [10 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C001 | USCSB2310109A | 574.62 | TEL Main Tool Interconnection | 2771 | C |  | DRY ETC2: KEPCH2 G.5/3, Conduit install | 45217 | 45220 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 574.62 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 | 574.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C009 | USC2312033A | 574.58 | F21P1 Module Tool Interconnection ETC1-3 | 580 | P |  | FLEX LT3UAGRY | 45267 | 45271 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 574.58 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 574.58 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303103A | 573.84 | F21P1 WWT package (Installation and 2 batch tanks) | 1840 | C |  | WWT SUS CDA TPC port | 45015 | 45023 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 546.78 | 0.95284 | 27.06 | 0 | 27.06 | 27.339 | [33 empty] | 0 |  |  | 546.78 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 27.339
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312069A | 573.54 | Tool Interconnection Project (Main Tool & Module) | 615 | P |  | FLEX LT3UAGRY | 45280 | 45280 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 573.54 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 573.54 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312068A | 573.54 | Tool Interconnection Project (Main Tool & Module) | 614 | P |  | FLEX LT3UAGRY | 45280 | 45281 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 573.54 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 573.54 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402110A | 571.86 | F21P1-0404_H_labor for 50 tools_MICU | 3548 | C |  | Chan and Cutter, shared for all system 300 tools | 45333 | 45335 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 518.81 | 0.90723 | 53.05 | 0 | 53.05 | 0 | 518.81 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403090A | 571.6 | F21P1-0404_H_labor for 50 tools_MICU | 3792 | C |  | Cable Gland 20 Pack PG19 Waterproof Adjustable 12-16mm Nylon Cable Glands Joints with Gaskets, Black(PG19) for HK Power trade | 45359 | 45362 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 519.6 | 0.90903 | 52 | 0 | 52 | 0 | 519.6 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2309087A | 569.74 | F21P1 Module Tool Interconnection ETC1-3 | 2560 | C |  | Change order – conduit install for signal cable routing from L20 to L10 KECOT2 | 45184 | 45199 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 569.74 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 569.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2403219A | 569.69 | F21P1 Module Tool Interconnection ETC1-3 | 3914 | C |  | Home Depot Order for 2 ladders and 4 combo locks for cages | 45372 | 45376 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 515.17 | 0.9043 | 54.52 | 0 | 54.52 | 0 | 515.17 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C009 | USCSB2402124A | 568.54 | F21P1 WWT package (Installation and 2 batch tanks) | 3561 | C | -01 | Sulfate Analyser SO4 reagents | 45336 | 2024/2/15 2024/02/26 2024/3/1 | 16 | 552.54 | V |  |  |  | Hach Company | PR Approved | PO Approved | R1: Change payment method to credit card R2: Adding Shippment Fee |  | Ta Wei Wang | [11 empty] | 568.54 | 1 | 0 | 0 | 0 | 0 | 568.54 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403110A | 565.65 | F21P1-0404_H_labor for 50 tools_MICU | 3812 | C |  | Marketech calibration request for quote timing and turnaround with CALHUB support and documentation conforming to ISO 9001 | 45363 | 45363 | [6 empty] | National Calibration Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 226.4 | 0.40025 | 339.25 | 0 | 339.25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 226.4 | [8 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2308048A | 565 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2346 | C |  | Techsouth Hand tool 02 | 45146 | 45147 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 565 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 565 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | CCE | DCR Scope | WWT | WWT | Electrical | Material | USC21C009 | USCSB2401066A | 564.88 | F21P1 WWT package (Installation and 2 batch tanks) | 3255 | C |  | WWT CCE Change Orders | 45302 | 45304 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 564.88 | 0 | 564.88 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 84.732 |  |  |  | 84.732 |  |  |  | 84.732 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403043A | 563.12 | F21P1-0404_H_labor for 50 tools_MICU | 3750 | C |  | Heavy duty Contractor's bags for HK Power trades | 45356 | 45358 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 563.12 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 563.12 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208025A | 562.8 | F21P1 UPW | 224 | P0 |  | 24in Monitor | 44800 | 44810 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 562.8 | 1 | 0 | 0 | 0 | 0 | 562.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402198A | 562 | F21P1 Chemical & WCCS package | 3625 | C |  | CDS 1" SS EP tube | 45343 | 45345 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 562 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 562 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2209016A | 561.2 | F21P1 Chemical & WCCS package | 241 | P0 |  | 24in Monitor | 44825 | 44826 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 561.2 | 1 | 0 | 0 | 0 | 0 | 561.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2402145A | 560 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3578 | C |  | Banner Industries Durabiti Tube Squaring .75 tall for 301 & 302 | 45337 | 45337 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 560 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 560 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2407065A | 558.11 | F21P1 AMAT Interconnection | 4483 | C |  | U- Bolts and Hex Nut Zinc for P1B Material | 45484 | 45496 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 558.11 | 1 | 0 | 528.5 | -528.5 | 0 | [70 empty] | 29.61 |  | 528.5 | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312165A | 557.61 | F21P1-0404_H_labor for 50 tools_MICU | 3153 | C |  | HK strut clamp for PPL trade | 45282 | 45288 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 557.61 | 0 | 557.61 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201012A | 553.8 | F21P1 UPW | 106 | P0 |  | Monitor | 44579 | 44580 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 553.8 | 1 | 0 | 0 | 0 | 0 | 553.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2401206A | 551.99 | F21P1 AMAT Interconnection | 3391 | C |  | Wesco Panduit | 45316 | 45317 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 551.99 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 551.99 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206015A | 551.01 | F21P1 UPW | 182 | P0 |  | AECC License | 44724 | 44764 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 551.01 | 1 | 0 | 0 | 0 | 0 | 551.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C007 | USCSB2408021A | 550 | F21P1 Module Tool Interconnection PVD1-2 | 4617 | C |  | Polyolefin heat shrink Fittings needed for cables that MIC provides for tool KCANN4,KCANN5,KCANN6,KCANN7 for CVD/LAM | 45510 | 45516 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 550 | 1 | 0 | 602.41 | -602.41 | [74 empty] | 550
[5 empty] | Others |  |  | USC24C015 | USCSB2409119A | 549 | TSMC Fab 21 P1B Tool Hook Up | 4937 | C |  | M18 FUEL 18V Lithium-Ion Brushless Cordless Deep Cut Band Saw with Two 5.0Ah Batteries, Charger, Hard Case, tool hookup tea, | 45563 | 45567 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approving | [14 empty] | 0 | 0 | 549 | 0 | 549 | 0
Non-TSMC Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C036 | USC2404040A | 548 | F21P1 AMAT Interconnection | 994 | P |  | heat gun | 45391 | 45392 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 548 | 1 | 0 | 0 | 0 | 0 | 548 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2404104A | 546.84 | F21P1-0404_H_labor for 50 tools_MICU | 4091 | C |  | Strectch wrap for HK power trade | 45395 | 45407 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 546.84 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 546.84 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Commissioning | USC21C005 | USCSB2312028A | 546.4 | F21P1 Chemical & WCCS package | 3021 | C |  | CDS commissioning 20L PE Tank/Bottle - Acid and alkali resistance requested by Steven Chiu. Qty: 20. | 45266 | 45290 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 546.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 546.4 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409094A | 546.19 | TSMC Fab 21 P1B Tool Hook Up | 4904 | C |  | Hand tool for upw system, tool hookup team | 45560 | 45562 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 546.19 | 0 | 546.19 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2401027A | 545.98 | F21_AZQR_Hookup_ Interconnection | 3218 | C |  | QR: FAD/CHAD LABS: INTERCON. MATERIAL LAN CABLE TRAY | 45296 | 45316 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 545.98 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 545.98 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2305077A | 544.38 | F21P1 UPW | 1998 | C |  | UPW AGRU check valves | 45063 | 45065 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 544.38 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 544.38 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401212A | 544.2 | F21P1-0404_H_labor for 50 tools_MICU | 3395 | C |  | Contractor drill bit for hk power, ppl, and exhaust trade | 45316 | 45316 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 494.7 | 0.90904 | 49.5 | 0 | 49.5 | 0 | 494.7 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203026A | 542.8 | F21P1 UPW | 146 | P0 |  | Cavalier Ergo Mesh Chairs | 44643 | 44670 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 542.8 | 1 | 0 | 0 | 0 | 0 | 542.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2312172A | 542.14 | F21P1 Module Tool Interconnection CVD | 3160 | C |  | CVD2_KCANN3_WIRE SO10/4 | 45283 | 45289 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 542.14 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 542.14 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24B002 | USC2410007A | 541.16 | Tool Interconnection Project (Main Tool & Other Vendors) | 1267 | P |  | 2-1/2 in. x 20 ft. DUAL-FLEX Locking Vacuum Hose Kit Accessory Shop Vac Attachment for RIDGID Wet Dry Vacuums | 45569 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 541.16 | 0 | 541.16 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406152A | 540 | F21P1-0404_H_labor for 50 tools_MICU | 4399 | C |  | Y terminals for HK Power P1B 40 tools | 45472 | 45475 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 540 | 540 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204004A | 538.63 | F21P1 UPW | 151 | P0 |  | 5 Port Switch, Netgear Router | 44673 | 44676 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 538.63 | 1 | 0 | 0 | 0 | 0 | 538.63 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310122A | 535 | F21P1 Chemical & WCCS package | 2782 | C |  | CDS Paint for W-TANK Scratch Repair | 45218 | 45224 | [6 empty] | Continental Coatings Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 535 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 535 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309135A | 535 | F21P1 Chemical & WCCS package | 2606 | C |  | Paint for Tank Scratch Repair | 45190 | 45194 | [6 empty] | Continental Coatings Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 535 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 535 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112013A | 534.26 | F21P1 UPW | 80 | P0 |  | 27" Sceptre Monitor | 44537 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 534.26 | 1 | 0 | 0 | 0 | 0 | 534.26 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2307139A | 533.43 | F21P1 Chemical & WCCS package | 2301 | C |  | TGCM Duty Room items – projector | 45136 | 45140 | [6 empty] | Office Depot Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 533.43 | 0 | 533.43 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 533.43 | [9 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309117A | 533 | F21P1 Chemical & WCCS package | 2589 | C |  | Tee and elbow for YaHo at Lorry FNDP. | 45189 | 45192 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 533 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 533 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C005 | USCSB2407146A | 532.55 | Chemical & WCCS B Side Project | 4556 | C |  | Chemical Team Cleanroom supplies | 45498 | 45499 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 532.55 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 532.55 | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2404011A | 531.44 | WWT B side Project | 4007 | C |  | WWT SS Fittings_20240401 (B Side) | 45384 | 45387 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 531.44 | 0 | 531.44 | 531.44 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 79.716 |  |  |  | 79.716 |  |  |  | 79.716 |  | 531.44 |  | - | 0 | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C025 | USCSB2303076A | 530.28 | AMHS TSMC Instrustructure and Branch Circuits | 1814 | C |  | Fitting and Reducing Union | 45003 | 45007 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 530.28 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [5 empty] | 530.28 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2312158A | 528 | F21P1 WWT package (Installation and 2 batch tanks) | 3147 | C |  | WWT-Gripper 2 in. Plastic Mechanical Test Plug | 45281 | 45280 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 528 | 1 | 0 | 0 | 0 | 0 | 528 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407020A | 527.36 | Tool Interconnection Project (Main Tool & Other Vendors) | 1157 | P |  | Labor 8395 Certification and cable pull | 45491 | 45492 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 527.36 | 0 | 527.36 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408109A | 527.2 | TSMC Fab 21 P1B Tool Hook Up | 4723 | C |  | safety equipment for tool hookup team | 45528 | 45532 | [6 empty] | Palo Verde First Aid-Fire-Safety-Shredding | PR Approved | PO Approved | [14 empty] | 0 | 0 | 527.2 | 0 | 527.2 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2404035A | 524.48 | F21P1-0404_H_labor for 50 tools_MICU | 4030 | C |  | SO 151205 PO for HK Power system | 45385 | 45385 | [6 empty] | National Calibration Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 524.48 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 524.48 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2311143A | 523.2 | F21P1 Module Tool Interconnection CVD | 2993 | C | -01 | KCWCN1 | 45260 | 2023/12/4 2023/12/6 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 523.2 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 523.2 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C040 | USCSB2401137A | 522.9 | TSMC F21 Clean Room Suit | 3322 | C |  | Laydown Material - Amazon | 45310 | 1/24/2024 9/13/2024 | -85.05 | 607.95 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PO R1: Adjusting the PR amount to align with the actual PO and close out this PO. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 522.9 | 1 | 0 | 0 | 0 | 0 | 522.9 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2409082A | 521.73 | F21P1 AMAT Interconnection | 4894 | C |  | P1B_AMAT_MATERIAL_CED | 45555 | 45560 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 521.73 | 0 | 521.73 | 0 | [73 empty] | -
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2311046A | 516.17 | EBO21- Tool interconnection | 2901 | C |  | EBO: ZCENT-1: CABLE TRAY | 45240 | 45246 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 516.17 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 516.17 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2403010A | 515.84 | F21P1 Chemical & WCCS package | 3718 | C |  | CDS Mini circuit breaker, QO, 15A, 2 pole, 240VAC, 22kA, bolt on mount | 45352 | 45363 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 515.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 515.84 |  |  |  |  | 515.84 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2310005A | 513.32 | Tool Interconnection Project (Main Tool & Module) | 438 | P | -01 | FLEX LT3UAGRY: 3 UL LIQ-TITE, PER 100 | 45203 | 2023/11/1 2023/11/13 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PO R1:Remark Information Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 513.32 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 513.32 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2310056A | 513.2 | Tool Interconnection Project (Main Tool & Module) | 473 | P |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45226 | 45230 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 513.19 | 0.99998 | 0.01 | 0 | 0.01 | 0 | [42 empty] | 0 | 0 |  | 513.19 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207006A | 512.33 | F21P1 UPW | 186 | P0 |  | AECC License | 44771 | 44784 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Chiehwen Chen | Yi En Wong | [7 empty] | 512.33 | 1 | 0 | 0 | 0 | 0 | 512.33 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407006A | 511.6 | Tool Interconnection Project (Main Tool & Other Vendors) | 1147 | P |  | Male Connector: 3/4" S300 to 3/4" NPT (DWG# PM-7018-1-1) | 45483 | 45486 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | [14 empty] | 511.6 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 511.6 |  |  | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2405145A | 511.49 | F21P1 Module Tool Interconnection DIF1-2 | 4169 | C |  | DIFF 1& 2 no tool ID#, monthly rental rate for Nitrogen ACCT68520233 09/20/2023-06/20/2024 | 2024/5/24 2024/5/30 | 45448 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | PR R1:We had adjusted off the safety & environmental fee for Oct thru Dec 2023 as we did for the other accounts. When we added the | [13 empty] | 188.31 | 0.36816 | 323.18 | 0 | 323.18 | 0 | [62 empty] | 188.31 | [10 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2401229A | 510.82 | Tool Hookup Material (UPW&Chemical) | 3411 | C |  | QR Lab Drain and UPW construction parts | 45317 | 45317 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 510.82 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 510.82 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401185A | 510.49 | F21P1-0404_H_labor for 50 tools_MICU | 3370 | C |  | storage equipment for plastic system | 45314 | 45314 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 510.49 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 510.49 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2409054A | 510.04 | WWT B side Project | 4850 | C |  | WWT shortage of hardware materials on the B side and WRC | 45549 | 45551 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 510.04 | 0 | 510.04 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409053A | 509.92 | Tool Interconnection Project (Main Tool & Other Vendors) | 1255 | P |  | SUS304: NW63 -> 4” | 45560 | 45561 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 509.92 | 0 | 509.92 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408033A | 509.58 | TSMC Fab 21 P1B Tool Hook Up | 4628 | C |  | USCSB2402019A issue over shipped amount | 45512 | 45513 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 509.58 | 1 | 0 | 0 | 0 | [69 empty] | 509.58 |  |  |  |  | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306018A | 506.4 | Tool Interconnection Project (Main Tool & Module) | 303 | P |  | LAM Interconnect Cable Management-Building LAM cables | 45084 | 45100 | [6 empty] | Motion Automation Intelligence | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 405.12 | 0.8 | 101.28 | 0 | 101.28 | 0 | [33 empty] | 0 |  |  |  |  | 101.28 |  | 101.28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 202.56 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311139A | 504.54 | F21P1-0404_H_labor for 50 tools_MICU | 2989 | C |  | Snoop, Liquid Leak Detector, 1 gal (3.8 L) Bottle, shared material for gas system | 45259 | 45264 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 504.54 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 504.54 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2210007A | 502.82 | F21P1 UPW | 251 | P0 |  | 55 inch Samsung flat screen TV UHD/one tv stand for new TV | 44838 | 44848 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 502.82 | 1 | 0 | 0 | 0 | 0 | 502.82 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408008A | 499.12 | TSMC Fab 21 P1B Tool Hook Up | 4605 | C |  | office supply and materials, tool hookup team | 2024/8/2 2024/9/25 | 2024/8/7 2024/9/25 | -230.57 | 729.69 | V | V |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: CHAIN PASS 2/0 ZNC125'CHAIN PASS 2/0 ZNC125' not receive and purchasing request to amend 154.93 refund. | [13 empty] | 499.12 | 1 | 0 | 0 | 0 |  | 499.12 | [72 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402171A | 498.73 | F21P1-0404_H_labor for 50 tools_MICU | 3601 | C |  | Milwaukee Fleece Dust Bags (3-Pack), Nashua Tape, Chain, tool hookup team | 45339 | 45351 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 438.88 | 0.88 | 59.85 | 0 | 59.85 | 0 | 438.88 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407173A | 496.08 | TSMC Fab 21 P1B Tool Hook Up | 4596 | C |  | Scissor lift for HK department start 05/02 | 45504 | 45503 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 496.08 | 0 | 496.08 | [74 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C011 | USCSB2403256A | 493.63 | F21 TMAH System | 3949 | C | -01 | WWT-Ammonia standards solution | 45378 | 2024/3/27 2024/3/28 | [5 empty] | V | Winn Marion Barber, LLC | PR Approved | PO Approved | R1: Removing Liquidated Damage per email discussion |  | Ta Wei Wang | [11 empty] | 493.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 74.0445 | 493.63 |  |  | 74.0445 |  |  |  | 74.0445 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409066A | 491.62 | TSMC Fab 21 P1B Tool Hook Up | 4861 | C |  | CLEANROOM TAPE - 1" X 36 YDS, CLEAR | 45553 | 45555 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 491.62 | 0 | 491.62 | 0 | [73 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402099A | 491.37 | F21P1 Chemical & WCCS package | 3539 | C |  | Chemical Team Material | 45332 | 45347 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 446.7 | 0.90909 | 44.67 | 0 | 44.67 | 0 | 446.7 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401081A | 491.05 | F21P1 Chemical & WCCS package | 3270 | C |  | CDS Reducing Union Adapter | 45303 | 45303 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 491.05 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 491.05 | [8 empty] | 491.05 | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2402285A | 490.83 | F21P1 Module Tool Interconnection ETC1-3 | 3708 | C |  | Change Order KEPOA1 | 45351 | 45352 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 490.83 | 0 | 490.83 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2401204A | 490.39 | F21P1 AMAT Interconnection | 3389 | C |  | AMAT Amazon order | 45316 | 45316 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 430.78 | 0.87844 | 59.61 | 0 | 59.61 | 0 | 430.78 | [46 empty] | 0 | 0 | 0 |  |  | 0 |  | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2312101A | 488.65 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3092 | C |  | Consolidated Electrical Distributors material for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45275 | 45275 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 488.65 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 488.65 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408125A | 487.92 | TSMC Fab 21 P1B Tool Hook Up | 4736 | C |  | keep PPE for the TOOL HOOK UP EHS Department. | 45532 | 45533 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 419.42 | 0.85961 | 68.5 | 0 | 68.5 | 0 | [72 empty] | 419.42 | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2401239A | 487.25 | F21P1 Module Tool Interconnection CVD | 3420 | C |  | CVD2_KCANN3_316L union Tee, 1/4 in. OD | 45321 | 45322 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 487.25 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  | 487.25 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2304082A | 486 | F21_AZQR_Hookup_ Interconnection | 1920 | C |  | QR HARRINGTON ICPMS PIPING | 45044 | 45047 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 486 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 486 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2305001A | 485.74 | Tool Interconnection Project (Main Tool & Module) | 270 | P |  | HVCR/VCR coupling connectors for CVD CIP. | 45063 | 45063 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | TSMC has agreed to be invoiced the full sum upon delivery. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 485.74 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 485.74 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112008A | 485.34 | F21P1 UPW | 76 | P0 |  | 24" Monitor | 44533 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 485.34 | 1 | 0 | 0 | 0 | 0 | 485.34 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112007A | 481.5 | F21P1 UPW | 75 | P0 |  | Office chairs | 44533 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 481.5 | 1 | 0 | 0 | 0 | 0 | 481.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407170A | 480.23 | TSMC Fab 21 P1B Tool Hook Up | 4593 | C |  | PPE for UPW system, tool hookup team | 45503 | 45506 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 479.79 | 0.99908 | 0.44 | 0 | 0.44 | [71 empty] | 479.79 |  |  | -
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2312009A | 480 | F21 TMAH System | 3004 | C |  | Helix bolts Tmah | 45261 | 45267 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 480 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 480 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401057A | 480 | Tool Interconnection Project (Main Tool & Other Vendors) | 679 | P | -01 | 2-1/2 VITON GSKT 1/8 THK 100 3.629 EA 362.90 3 DAYS ARO | 2024/1/23 2024/2/5 | 2024/1/23 2024/2/5 | 117.1 | 362.9 | V | V |  |  | Ferguson Enterprises, LLC | PR Approved | PO Approved | R1: Same Material, got sent the wrong size. description: 2-1/2 VITON GSKT 1/8 THK ORIGINAL ORDER # 1081114 CM379066 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 480 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  | 480 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310035A | 478.27 | F21P1-0404_H_labor for 50 tools_MICU | 2698 | C |  | Label | 45204 | 45211 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 478.27 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 478.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306041A | 477.7 | Tool Interconnection Project (Main Tool & Module) | 325 | P |  | BUR YA1CL2 1 AWG CU 1H LUG 1/4" STUD, BUR Y4C 4WG CU 1H LNG LUG 1/4" | 45090 | 45131 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 477.7 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 477.7 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2310014A | 477.41 | EBO21- Tool interconnection | 2677 | C |  | EBO: CDA CABINET – INT. MATERIAL 30M COIL 8M PFA TUBING | 45202 | 45226 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 477.41 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 477.41 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2306142A | 475.52 | F21P1 WWT package (Installation and 2 batch tanks) | 2174 | C |  | Duncan Bolt - unpaid invoice | 45107 | 45110 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 475.52 | 1 | 0 | 0 | 0 | 0 | [35 empty] | 475.52 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2306087A | 472.42 | F21P1 Module Tool Interconnection DIF1-2 | 2120 | C |  | DIFF1: TLC/VMB FOR DIFF1 | 45098 | 45146 | [6 empty] | Southwest Steel Sales, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 472.42 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 472.42 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2307143A | 471.75 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2305 | C |  | Harrington solvent cement PVC | 45136 | 45138 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 471.75 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 471.75 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Instrument | USC21C009 | USCSB2401231A | 468.86 | F21P1 WWT package (Installation and 2 batch tanks) | 3413 | C |  | WWT_pressure gauge QTY:2 | 45317 | 45317 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 468.86 | 0 | 468.86 | 468.86 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 70.329 |  |  |  | 70.329 |  |  |  | 70.329 |  | 468.86 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408145A | 466 | TSMC Fab 21 P1B Tool Hook Up | 4753 | C |  | Calibration | 45534 | 45535 | [6 empty] | Ceet Industries Inc DBA Trident Calibration Labs | PR Approved | PO Approved | [14 empty] | 0 | 0 | 466 | 0 | 466 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407059A | 462.95 | TSMC Fab 21 P1B Tool Hook Up | 4456 | C |  | P1B EEW PPE 3/8" Drive SAE Insulated Hex Head Sockets - Extra Long for 100 tools | 2024/7/11 2024/7/23 | 45498 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | pr r1:change vendor | [13 empty] | 462.1 | 0.99816 | 0.85 | 0 | 0.85 | 0 | [68 empty] | 462.1 |  |  |  |  | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204013A | 462.76 | F21P1 UPW | 160 | P0 |  | Floor Cord protector for meeting rooms in modular | 44679 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 462.76 | 1 | 0 | 0 | 0 | 0 | 462.76 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401092A | 460 | Tool Interconnection Project (Main Tool & Other Vendors) | 709 | P |  | Manpower Pay for CGS for Tool ID: KEPOL6 Timecard on 1.29.2024 Workers Rafael Osorio and Eloy Pacheco | 45321 | 45398 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 460 | 0 | 460 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309027A | 459.6 | Tool Interconnection Project (Main Tool & Module) | 416 | P |  | 3/8 PLTD CHAN NUT L/SPRG | 45191 | 45196 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 459.6 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 459.6 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309004A | 459.6 | Tool Interconnection Project (Main Tool & Module) | 399 | P |  | FNW7819Z0037 3/8" PLTD CHAN NUT L/SPRNG | 45176 | 45181 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 459.6 | 0 | 459.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409013A | 458 | Tool Interconnection Project (Main Tool & Other Vendors) | 1217 | P |  | Werner 10 ft. Fiberglass Step Ladder (14 ft. Reach Height) 300 lb. Load Capacity Type IA Duty Rating | 2024/9/7 2024/9/25 | 2024/9/12 2024/9/25 | 42.8 | 500.8 |  |  |  |  | The Home Depot, Inc | PR Approved | PO Approving | PR R1:Match to the actual expense (See order confirmation) | [13 empty] | 458 | 1 | 0 | 0 | 0 | 0 | 458 | [72 empty] | -
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2402191A | 457.11 | F21P1 WWT package (Installation and 2 batch tanks) | 3620 | C | -01 | (2) Steel Storage cabinets 72" with adjusteable drawers for storing Respitory Equipment and PPE. | 45343 | 2024/2/28 2024/3/22 | 31.41 | 425.7 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: PR amount change to add shipping |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 457.11 | 1 | 0 | 0 | 0 | 0 | 457.11 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111023A | 456.06 | F21P1 UPW | 37 | P0 |  | 24" Monitors for Employees | 44512 | 44524 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 456.06 | 1 | 0 | 0 | 0 | 0 | 456.06 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2303097A | 453 | F21P1 UPW | 1834 | C |  | Prominent backpressure valve | 45013 | 45014 | [6 empty] | Prominent Fluid Controls (Taiwan) Co. Ltd. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 453 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 453 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403102A | 452.21 | F21P1 Chemical & WCCS package | 3804 | C |  | CDS JJ Healy CO2 90 elbow | 45360 | 45362 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 452.21 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 452.21 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2403052A | 451.55 | F21P1-0404_H_labor for 50 tools_MICU | 3758 | C |  | BandSawBlade, Fiber Disc, Thread Sealant Tape, Tool hookup team | 45357 | 45362 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 451.55 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 451.55 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2401161A | 450.04 | F21P1-0404_H_labor for 50 tools_MICU | 3346 | C |  | Amazon office supplies for HK Alex's team | 45311 | 45317 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 401.88 | 0.89299 | 48.16 | 0 | 48.16 | 0 | 401.88 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C029 | USCSB2305029A | 450 | EBO21- Tool interconnection | 1952 | C |  | EBO-SUSS-ZASC5-Gas System 1/4" Valex Tube | 45052 | 45055 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 450 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 450 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Site Expense |  |  | Others |  |  | USC23B002 | USC2308006A | 450 | Tool Interconnection Project (Main Tool & Module) | 356 | P |  | Electric Scissor Lift, 20' Micro - Rent. Renting Lifts for cable pull, mechanical, and 8395 routing. | 45141 | 45154 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 450 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 450 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Site Expense |  |  | Others |  |  | USC24B002 | USC2404079A | 448.65 | Tool Interconnection Project (Main Tool & Other Vendors) | 1033 | P |  | 1394335 Electric Scissor Lift, 19' Micro-Rental. 3/28-4/25/2024 | 45405 | 45406 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved | [14 empty] | 448.65 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 448.65 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Site Expense |  |  | Others |  |  | USC24B002 | USC2404058A | 448.65 | Tool Interconnection Project (Main Tool & Other Vendors) | 1011 | P |  | 1394335 Electric Scissor Lift, 19' Micro-Rental.PHX-2923149-0020-Invoice. | 45394 | 45399 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 448.65 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 448.65 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409009A | 447 | Tool Interconnection Project (Main Tool & Other Vendors) | 1218 | P |  | 2AWG CU 1H LUG 3/8" STUD | 45540 | 45560 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 447 | 0 | 447 | 0 | [73 empty] | -
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C060 | USCSB2311107A | 444.29 | F21 CT Local Scrubber Interconnection | 2958 | C |  | PCA: SEE LIST OF TOOLS: INTERCONNECT MATERIAL SIGNAL CABLE | 45253 | 45258 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 444.29 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 444.29 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC22C025 | USCSB2410034A | 443.87 | Tool Hookup Material (UPW&Chemical) | 4977 | C |  | Urgent 7 DP Fillers_AMHS | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 443.87 | 0 | 443.87 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2312155A | 443.75 | F21P1 Module Tool Interconnection CVD | 3144 | C |  | KCANN3,KCAPN1,KCSCN5 SOOW 10-4 Power cable run from L30 to L20 | 45281 | 45281 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 443.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 443.75 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C009 | USCSB2306053A | 443.54 | F21P1 WWT package (Installation and 2 batch tanks) | 2087 | C |  | WWT NH4 analyzer (Chemical Only) | 45091 | 45113 | [6 empty] | Winn Marion Barber, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 443.54 | 0 | 443.54 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 66.531 |  |  |  | 66.531 |  |  |  | 66.531 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2310195A | 442.5 | F21P1 Chemical & WCCS package | 2846 | C |  | CDS HPM10 A Side DHL Drain cover PP plates requested | 45230 | 45231 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 442.5 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 442.5 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409062A | 442 | TSMC Fab 21 P1B Tool Hook Up | 4857 | C |  | Y terminals_Panduit_PV10-8F-D for HK Power for 20 tools | 45553 | 45553 | [6 empty] | Elliott Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 442 | 0 | 442 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2310102A | 441.08 | EBO21- Tool interconnection | 2764 | C |  | EBO: PVC CURTAIN - ALUM. MOUNTAIN PLATE | 45216 | 45219 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 440.97 | 0.99975 | 0.11 | 0 | 0.11 | 0 | [41 empty] | 0 | 0 | 0 | 440.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402132A | 437.7 | F21P1 Chemical & WCCS package | 3569 | C |  | CDS flare nut 1-1/4 | 45336 | 45337 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 437.7 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 437.7 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2402163A | 433.65 | F21P1 Module Tool Interconnection ETC1-3 | 3595 | C |  | DRY ETC3: KETRTC, KETRT6, KETRT9: AC CONNECTORS | 45339 | 45343 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 433.65 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 433.65 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Instrument | USC24C005 | USCSB2405102A | 430.99 | Chemical & WCCS B Side Project | 4133 | C |  | Chem. Adjustable chain Sling | 45429 | 45434 | [6 empty] | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved | [14 empty] | 430.99 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 430.99 | [10 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403005A | 430 | Tool Interconnection Project (Main Tool & Other Vendors) | 832 | P |  | MANPOWER PAY FOR CCE | 45353 | 45363 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 0 | 0 | 430 | 0 | 430 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407099A | 427.9 | TSMC Fab 21 P1B Tool Hook Up | 4514 | C |  | P1B Extension Ladder Request for HK PPL Trade for 100 tools | 45490 | 45491 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 389 | 0.90909 | 38.9 | 0 | 38.9 | 0 | 389 | [72 empty] | - |  |  | 0
Base-Build | Chemical | Material | DCR Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | QAQC | USC21C005 | USCSB2310170A | 426.9 | F21P1 Chemical & WCCS package | 2824 | C |  | CDS Lorry A CO2 Offsets CO parts | 45225 | 45229 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 414.1 | 0.97002 | 12.8 | 0 | 12.8 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 143.3 |  | 0 |  | 270.8 | [6 empty] | 12.8 | [5 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401024A | 425.5 | F21P1-0404_H_labor for 50 tools_MICU | 3215 | C |  | Male Connector, for plastic QA/QC testing, Tool hookup team | 45296 | 45300 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 425.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 425.5 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402211A | 424.18 | F21P1-0404_H_labor for 50 tools_MICU | 3638 | C |  | Cable tie for HK CYH PCW | 45344 | 45348 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 424.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 424.18 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406041A | 423.5 | Chemical & WCCS B Side Project | 4267 | C |  | F21P1 B Side material Harrington - PVC Conduit fitting for PP | 45449 | 45449 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 423.5 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 142 |  | 281.5 |  |  |  |  | - |  |  | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC24B002 | USC2403037A | 420 | Tool Interconnection Project (Main Tool & Other Vendors) | 863 | P |  | MANPOWER PAY FOR WGN-Star | 45359 | 45362 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 0 | 0 | 420 | 0 | 420 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404063A | 419.76 | Tool Interconnection Project (Main Tool & Other Vendors) | 1016 | P |  | BPT 247 3IN SET SCREW CPLG | 45398 | 45401 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 419.76 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 419.76 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2401093A | 419.36 | F21_AZQR_Hookup_ Interconnection | 3281 | C |  | QR LABS: KXPS/KXFX/KXSM: 1/4" VCR HARDWARE FOR CABLE TRAY | 45304 | 45308 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 419.36 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 419.36 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311011A | 419.03 | F21P1-0404_H_labor for 50 tools_MICU | 2866 | C |  | COND/EMT Universal Clamp for Third | 45232 | 45236 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 419.03 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 419.03 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310030A | 419.03 | F21P1-0404_H_labor for 50 tools_MICU | 2693 | C |  | Clamps | 45204 | 45211 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 419.03 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 419.03 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406139A | 418.92 | F21P1-0404_H_labor for 50 tools_MICU | 4378 | C |  | Anchor Strut Fasteners for Fall Protection Working at Heights per TSMC Requirements | 45470 | 2024/6/27 2024/6/29 | -41.89 | 460.81 |  |  |  |  | NEFCO Construction Supply LLC | PR Approved | PO Approved | PO R1:Removed unnecessary buffer | [13 empty] | 418.92 | 1 | 0 | 454.94 | -454.94 | 0 | [73 empty] | 418.92 |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403030A | 416.33 | F21P1-0404_H_labor for 50 tools_MICU | 3739 | C | -01 | extension ladder, tie-down straps, and locks for HK PPL | 3/5/2024 3/19/2024 8/22/2024 | 3/5/2024 4/5/2024 8/28/2024 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | R1: Matching the amount with the actual cost R2: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 416.33 | 1 | 0 | 0 | 0 | 0 | 416.33 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409051A | 415.9 | TSMC Fab 21 P1B Tool Hook Up | 4835 | C |  | Trash bag for tool hookup team | 45548 | 45551 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 366.5 | 0.88122 | 49.4 | 0 | 49.4 | 0 | 366.5 | [72 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408042A | 414.38 | Tool Interconnection Project (Main Tool & Other Vendors) | 1191 | P |  | Zip Tie Mount (1EA = 140 pack) | 45521 | 45525 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 289.71 | 0.69914 | 124.67 | 0 | 124.67 | 0 | 289.71 | [72 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2305038B | 414 | EBO21- Tool interconnection | 1962 | C |  | 3/8" HT PVC Pressure hose (8M) | 45057 | 2023/5/15 2023/6/16 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 414 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 372.6 | 0 | 0 | 0 | 0 |  | 0 | 0 | 41.4 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111064A | 412.66 | F21P1 UPW | 65 | P0 |  | L-shaped office desks | 44525 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 412.66 | 1 | 0 | 0 | 0 | 0 | 412.66 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC22C012 | USCSB2404045A | 410 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 4040 | C |  | pH Sensor Accessories & Control Net Adapters from Organo | 45386 | 45387 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 410 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 410 | [6 empty] | 410 |  | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2403184A | 409.68 | F21P1 WWT package (Installation and 2 batch tanks) | 3881 | C | -02 | WWT-lab tech-hood sash weight | 45370 | 2024/3/19 2024/3/27 2024/4/12 | 85.23 | 324.45 | V |  |  |  | LabTech Supply Company Inc | PR Approved | PO Approved | R2: The previous amount of $324.45 should sum up with the freight of $85.23, also change payment method R1: Change Total amount to add credit card fee |  | Ta Wei Wang | [11 empty] | 324.45 | 0.79196 | 85.23 | 0 | 85.23 | 409.68 | 324.45 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 61.452 |  |  |  | 61.452 |  |  |  | 61.452 |  | 409.68 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311002A | 408.89 | Tool Interconnection Project (Main Tool & Module) | 477 | P |  | EPI cable tray/cable pull material for EPI_KEXR01,KEXR01 | 45231 | 45238 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 408.84 | 0.99988 | 0.05 | 0 | 0.05 | 0 | [42 empty] | 0 | 0 |  | 0 | 408.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408090A | 408.52 | TSMC Fab 21 P1B Tool Hook Up | 4709 | C |  | office supplies | 45525 | 45535 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 329.49 | 0.80655 | 79.03 | 329.49 | -250.46 | 0 | [73 empty] | 329.49
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406005A | 407.4 | Chemical & WCCS B Side Project | 4234 | C |  | F21P1 WCCS PVDF ADPT | 45444 | 45446 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 407.4 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 407.4 | [8 empty] | - |  |  | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402120A | 406.87 | F21P1 Chemical & WCCS package | 3558 | C |  | Tools for chemical team | 45335 | 45336 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 326.15 | 0.80161 | 80.72 | 0 | 80.72 | 0 | 326.15 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402197A | 405 | F21P1 Chemical & WCCS package | 3624 | C |  | CDS 5/8 Screw sets | 45343 | 45344 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | B | [7 empty] | 405 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 405 | 405 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C007 | USCSB2401060A | 405 | F21P1 Module Tool Interconnection PVD1-2 | 3249 | C |  | PVD，Interconnection material 36" Zip Tie | 45302 | 45302 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 375 | 0.92593 | 30 | 0 | 30 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 375 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402069A | 404.7 | Tool Interconnection Project (Main Tool & Other Vendors) | 785 | P |  | Manpower Pay for RS Payroll for Michael Rodriquez | 45336 | 45377 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 404.7 | 0 | 404.7 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2402128A | 404.04 | F21P1 UPW | 3565 | C |  | FIQ Sensor Cable x2 for FIQCWS9034 | 45336 | 45337 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 404.04 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 404.04 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2405033A | 402.81 | F21P1-0404_H_labor for 50 tools_MICU | 4042 | C |  | Forklift for HK item 11329770 | 45419 | 45420 | [6 empty] | United Rentals | PR Approved | PO Approved | [14 empty] | 402.81 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 402.81 |  |  |  |  | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311028A | 401.9 | Tool Interconnection Project (Main Tool & Module) | 502 | P |  | FLEX LT2UAGRY: 2 UL LIQ-TITE, PER 100 | 45240 | 45244 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 401.9 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 340.68 | 0 | 0 | 61.22 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2312205A | 400 | F21P1-0404_H_labor for 50 tools_MICU | 3191 | C |  | thread sealing plumber's tape for PCW | 45290 | 45294 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 374 | 0.935 | 26 | 0 | 26 | 0 | 374 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2308128A | 398.09 | F21P1 Module Tool Interconnection ETC1-3 | 2425 | C |  | Change order – conduit install for signal cable routing from L20 to L10 KESRT4 | 45160 | 45160 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 389.02 | 0.97722 | 9.07 | 0 | 9.07 | 0 | [40 empty] | 0 | 389.02 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2308127A | 398.09 | F21P1 Module Tool Interconnection ETC1-3 | 2424 | C |  | Change order – conduit install for signal cable routing from L20 to L10 KECOT2 | 45160 | 45160 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 235.11 | 0.5906 | 162.98 | 0 | 162.98 | 0 | [40 empty] | 0 | 235.11 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401024A | 392.4 | Tool Interconnection Project (Main Tool & Other Vendors) | 647 | P |  | DIFF1: KIMIS1: CUSH CLAMPS FOR AIR & WATER HOSES | 45303 | 45304 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 392.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 392.4 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2312023A | 392 | F21P1 UPW | 3017 | C |  | DO Power Supply | 45265 | 45266 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 392 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 392 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2407083A | 390.96 | WWT B side Project | 4499 | C |  | Sticker | 45489 | 45492 | [6 empty] | StickerYou Inc. | PR Approved | PO Approved | [14 empty] | 356 | 0.91058 | 34.96 | 0 | 34.96 | 0 | 356 | [70 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2307095A | 390.4 | F21_AZQR_Hookup_ Interconnection | 2261 | C |  | QR LABS Swagelok Interconnect material for KXIM01-07 | 45127 | 45135 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 390.4 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 255.84 | 134.56 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406042A | 389.9 | Chemical & WCCS B Side Project | 4268 | C | -01 | F21P1 B Side material Amz - RS-232 Connector | 45449 | 2024/6/6 2024/6/18 | 0.9 | 389 |  | V |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Align with the actual purchase amount | [13 empty] | 389.9 | 1 | 0 | 0 | 0 | 0 | 389.9 | [72 empty] | - |  |  | 0
Base-Build | Base-Build | MIMO/Rigging | Main Contract Scope | CDS | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Labor | USC21C005 | USCSB2403298A | 388.25 | F21P1 Chemical & WCCS package | 3990 | C |  | Amazon - MIMO - Move In/Move Out Team | 45381 | 45383 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 347.3 | 0.89453 | 40.95 | 0 | 40.95 | 0 | 347.3 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USC2410009A | 386 | TSMC Fab 21 P1B Tool Hook Up | 1268 | P |  | Lock washer 防鬆華司,galvanzied 鍍鋅,3/8" | 45569 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 386 | 0 | 386 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USC2112001A | 383.92 | F21P1 Chemical & WCCS package | 69 | P |  | Ball Valve | 44531 | 44586 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | CF (Trade term check)) | Arrival (delivery) 100.00% NET 30days after shipping | Cherry Chang |  |  | Chih-Chien Hung | Cherry Chang | N |  | Henry |  | N | 5000 |  | 285.8 | 0.74443 | 98.12 | 0 | 98.12 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 285.8 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111054A | 382.06 | F21P1 UPW | 55 | P0 |  | Cork Boards | 44524 | 44554 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 382.06 | 1 | 0 | 0 | 0 | 0 | 382.06 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203004A | 380.09 | F21P1 UPW | 129 | P0 |  | Router | 44629 | 44635 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 380.09 | 1 | 0 | 0 | 0 | 0 | 380.09 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208011A | 379.56 | F21P1 UPW | 211 | P0 |  | Black Metal Chairs for Fab lunchroom | 44789 | 44798 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 379.56 | 1 | 0 | 0 | 0 | 0 | 379.56 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2209002A | 379.56 | F21P1 UPW | 227 | P0 |  | Black metal folding chairs | 44805 | 44810 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 379.56 | 1 | 0 | 0 | 0 | 0 | 379.56 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403125A | 379.26 | F21P1-0404_H_labor for 50 tools_MICU | 3827 | C |  | 3199 INSTRUMENTATION MISC 6" 24 hour 150 psi cicular chart recorder paper 60 pcs, tool hookup team | 45364 | 45365 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 379.26 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 379.26 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202014A | 379.01 | F21P1 UPW | 121 | P0 |  | Bluebeam Revu | 44614 | 44617 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204005A | 379.01 | F21P1 UPW | 152 | P0 |  | Revu License | 44673 | 44676 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2206010A | 379.01 | F21P1 UPW | 177 | P0 |  | Bluebeam Revu | 44724 | 44736 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207007A | 379.01 | F21P1 UPW | 187 | P0 |  | Bluebeam Revu | 44771 | 44784 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111020A | 379.01 | F21P1 UPW | 34 | P0 |  | Revu | 44512 | 44524 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203007A | 379.01 | F21P1 UPW | 132 | P0 |  | Bluebeam Revu | 44629 | 44635 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111021A | 379.01 | F21P1 UPW | 35 | P0 |  | Revu | 44512 | 44524 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207012A | 379.01 | F21P1 UPW | 192 | P0 |  | Bluebeam Revu | 44771 | 44784 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202015A | 379.01 | F21P1 UPW | 122 | P0 |  | Bluebeam Revu | 44614 | 44617 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2207017A | 379.01 | F21P1 UPW | 197 | P0 |  | Bluebeam Revu | 44771 | 44784 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403135A | 379 | F21P1-0404_H_labor for 50 tools_MICU | 3837 | C |  | 十字吊架 | 45365 | 45364 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 379 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 379 | [8 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2409115A | 378.84 | TSMC Fab 21 P1B Tool Hook Up | 4933 | C |  | MIC power team hand tool-consumable stretch wrap request for 200 tools | 45562 | 45566 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 378.84 | 0 | 378.84 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403189A | 376.93 | F21P1-0404_H_labor for 50 tools_MICU | 3886 | C |  | office supplies for tool hookup department | 45370 | 45370 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 338.6 | 0.89831 | 38.33 | 0 | 38.33 | 0 | 338.6 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2306007A | 372 | Tool Interconnection Project (Main Tool & Module) | 292 | P |  | TPVC.375X.625X100FT-REINFORCED .375ID X .625 OD X 100FT REINFORCED PVC TUBE | 45080 | 45100 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 372 | 1 | 0 | -44.8 | 44.8 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 372 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402056A | 371.92 | Tool Interconnection Project (Main Tool & Other Vendors) | 774 | P |  | CGS - KETRT8 - Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards | 45330 | 45332 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 0 | 0 | 371.92 | 0 | 371.92 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C007 | USCSB2307003A | 370 | F21P1 Module Tool Interconnection PVD1-2 | 2177 | C |  | CED (36IN CABLE TIE & INBOUND NSI) | 45108 | 45112 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 370 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 370 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2312138A | 367.56 | F21P1 UPW | 3127 | C |  | UPW-ORGANO-WRC BPV | 45279 | 45279 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 367.56 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 367.56 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401187A | 366 | F21P1-0404_H_labor for 50 tools_MICU | 3372 | C |  | Filing cabinet, speaker, and protector sheet for safety PPE shared by all trades | 45314 | 45314 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 355.84 | 0.97224 | 10.16 | 0 | 10.16 | 0 | 355.84 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2308045A | 364 | F21_AZQR_Hookup_ Interconnection | 2343 | C |  | QR Labs，Interconnection material FAD Lab tools, VCT Series Cable 600A 18 AWG 3C | 45146 | 45147 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 364 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 364 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208019A | 361.47 | F21P1 UPW | 218 | P0 |  | Revit License | 44800 | 44810 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 361.47 | 1 | 0 | 0 | 0 | 0 | 361.47 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312032A | 360.75 | Tool Interconnection Project (Main Tool & Module) | 579 | P | -01 | 1 E-OPS to pull cable for KCEPS3 | 2023/12/7 2024/1/6 | 2023/12/11 2024/3/7 | 194.25 | 166.5 |  |  | V |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | Revised for higher labor hours |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 360.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 360.75 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2403239A | 358.84 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3932 | C | -02 | Arizona/Albuquerque V&F Co./Swagelok Southwest Co,OSC Welding Supplies | 45377 | 2024/4/5 2024/4/8 2024/4/9 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: Change Shipping Address to Glendale R2: Change trade term from DDP to FOB |  | Ta Wei Wang | [11 empty] | 210.71 | 0.5872 | 148.13 | 0 | 148.13 | 0 | [52 empty] | 0 | 0 | 0 |  | 167.43 | [5 empty] | 43.28 | [8 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW |  |  |  | UPW | Mechanical | Equipment ( Tank 等工程相關的設備) | USC21C003 | USCSB2409002A | 355.94 | F21P1 UPW | 4772 | C |  | PIA KM31-584_Broken PIA instrument replacement | 45539 | 45540 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 355.94 | 355.94 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404009A | 354.78 | Tool Interconnection Project (Main Tool & Other Vendors) | 964 | P |  | 32625T56 Strut-Mount Vibration-Damping Routing Clamp with TPE Rubber Cushion, Steel, 1" ID, 1-7/16" Long | 45384 | 45384 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 354.78 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 354.78 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2404092A | 354 | F21P1 Module Tool Interconnection DIF1-2 | 4079 | C |  | Aluminum Clamps for Diffusion Tool ID#KDFAD1 | 45393 | 45397 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 354 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 354 | [10 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406138A | 353.76 | F21P1-0404_H_labor for 50 tools_MICU | 4377 | C |  | HK PCW tool request for 100 tools | 45470 | 45471 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 279.4 | 0.7898 | 74.36 | 0 | 74.36 | 0 | 279.4 | [72 empty] | - |  |  | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2404151A | 353.05 | F21P1 UPW | 4135 | C |  | PSAT L Bracket | 45401 | 45401 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 353.05 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 353.05 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C046 | USCSB2403103A | 352.99 | F21P1 ATS Interconnection | 3805 | C |  | PCA-ATS: DAILY USE TOOL: TELESCOPIC EXTENSION POLE & WERA TOOL-CHECK PLUS TOOL SET | 45360 | 45364 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 320.89 | 0.90906 | 32.1 | 0 | 32.1 | 0 | 320.89 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408079A | 352.76 | TSMC Fab 21 P1B Tool Hook Up | 4695 | C |  | Hex nut, bolt, and washer for HK power trade for 200 tools | 45520 | 45523 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 302.98 | 0.85888 | 49.78 | 11.96 | 37.82 | 0 | [72 empty] | 291.02 | 11.96
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401205A | 351.96 | F21P1-0404_H_labor for 50 tools_MICU | 3390 | C |  | scrubber mat for hk department shared by all system | 45316 | 45317 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 313.56 | 0.8909 | 38.4 | 0 | 38.4 | 0 | 313.56 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Site Expense | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2403093A | 350 | F21P1 Chemical & WCCS package | 3795 | C |  | CDS Welder rental for Chemical welding.(RENTAL FROM 2-27-24 To 3-8-24) | 45360 | 45363 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 350 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 350 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Commissioning | USC21C009 | USCSB2306044A | 350 | F21P1 WWT package (Installation and 2 batch tanks) | 2078 | C |  | WWT-CCB dry-run | 45090 | 45092 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 350 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 350 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409006A | 350 | TSMC Fab 21 P1B Tool Hook Up | 4776 | C |  | M200 Calibration | 45539 | 45539 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 350 | 350 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2304083A | 349.44 | F21_AZQR_Hookup_ Interconnection | 1921 | C |  | QR SWAGELOK ICPMS PIPING CONX | 2023/4/28 2023/5/16 | 45047 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | PR-R1:The quantity changed from 7 sets to 14 sets |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 349.44 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 349.44 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2304083B | 349.44 | F21_AZQR_Hookup_ Interconnection | 1922 | C |  | QR SWAGELOK ICPMS PIPING CONX | 45044 | 45302 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 349.44 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 349.44 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407139A | 349 | TSMC Fab 21 P1B Tool Hook Up | 4565 | C |  | FLOW/REG 356-AR/HE-580 DUAL for Gas trade | 45497 | 45506 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | [14 empty] | 349 | 1 | 0 | 0 | 0 | [73 empty] | 349 | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2312030A | 349 | F21P1 Chemical & WCCS package | 3023 | C |  | CDS 1/4 in. x 800 ft. Nylon Solid Braid Rope, White for JuWei PFA line work requested by Jay Huang. | 45266 | 45271 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 313.57 | 0.89848 | 35.43 | 0 | 35.43 | 0 | 313.57 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 34.9 | [9 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409016A | 349 | TSMC Fab 21 P1B Tool Hook Up | 4803 | C |  | Argon regulator for yaho, gas system | 45539 | 45551 | [6 empty] | Linde Gas & Equipment Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 349 | 349 | 0 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402225A | 348.9 | F21P1 WWT package (Installation and 2 batch tanks) | 3652 | C |  | WWT E2 missing SUS material | 45345 | 45345 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 348.9 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 348.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2210011A | 347.5 | F21P1 UPW | 254 | P0 |  | 3 drawer black file cabinet | 44838 | 44848 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 347.5 | 1 | 0 | 0 | 0 | 0 | 347.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2311073A | 347.2 | F21P1 Chemical & WCCS package | 2927 | C |  | CDS:adapters for Fab CDU drain port at B side. | 45246 | 45248 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 347.2 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 125 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 222.2 |  |  |  |  | 222.2 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403133A | 346.64 | Tool Interconnection Project (Main Tool & Other Vendors) | 948 | P |  | 5YE32 Corner Connector, 90 Degrees,Steel 40.00 EA 3.62 144.80 Manufacturer: APPROVED VENDOR Part Number: V321EG | 45380 | 45380 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | PR R1: per purchasing team, no longer need the shipping and must be zero out. |  | Kuan-Chung Su | [11 empty] | 346.64 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 346.64 |  |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2407132A | 346.5 | F21P1 Module Tool Interconnection ETC1-3 | 4545 | C |  | CED 350 BUNDY One-Hole Log Compression Connector: 6 AWG MAX Hole Size | 45496 | 45498 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 346.5 | 346.5 | 0 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2401207A | 345.72 | F21P1 Module Tool Interconnection ETC1-3 | 3392 | C |  | WELD PIPE for KEMEA3 | 45316 | 45329 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 345.72 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  | 345.72 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111019A | 345.28 | F21P1 UPW | 33 | P0 |  | Autodesk Revit | 44512 | 44524 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | 8 |  |  |  |  | 345.28 | 1 | 0 | 0 | 0 | 0 | 345.28 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Site Expense |  |  | Others |  |  | USC23B002 | USC2308007A | 345 | Tool Interconnection Project (Main Tool & Module) | 357 | P |  | Booties for MEC Micro 19's - Rent. Required for Lifts to complete cable pull, mechanical, and 8395 routing. | 45141 | 45154 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 345 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 345 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2403157A | 344.96 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3856 | C |  | OSC WELDING SUPPLIES Arizona/Albuquerque V&F Co./Swagelok Southwest Co | 45366 | 45370 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 344.96 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 344.96 | [8 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2310063A | 342.42 | F21P1 Module Tool Interconnection CVD | 2723 | C |  | AMAT CVD Interconnection material | 45210 | 45212 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 342.42 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 342.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304002A | 342.3 | F21P1 WWT package (Installation and 2 batch tanks) | 1843 | C |  | Sump pump/SUS bolt | 45017 | 45020 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 0 | 0 | 342.3 | 0 | 342.3 | 342.3 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 51.345 |  |  |  | 51.345 |  |  |  | 51.345 |  | 342.3 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | CO Scope (adding/additional scope) | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2305046A | 342.13 | F21P1 UPW | 1971 | C |  | ORGANO isolation valves | 45057 | 45061 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 342.13 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 342.13 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C014 | USCSB2305109A | 339.73 | F21P1 WH2SO4 | 2026 | C |  | Hardware for Dosing Boxes | 45070 | 45071 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 339.73 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 339.73 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C006 | USCSB2406111A | 339.4 | WWT B side Project | 4351 | C |  | WWT Cleaning Material | 45465 | 45467 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 329 | 0.96936 | 10.4 | 0 | 10.4 | 0 | 329 | [70 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402246A | 338.96 | F21P1-0404_H_labor for 50 tools_MICU | 3672 | C |  | SS stem and nut for CGA 580, TOOL HOOKUP TEAM | 45347 | 45350 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 338.96 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 338.96 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2401105A | 338.1 | Tool Interconnection Project (Main Tool & Other Vendors) | 722 | P |  | DOT DT75SB 3/4-3/4 MNTG BASE - BLACK 3/4 X 3/4IN ADHESIVE MOUNTING BASES - U.V. BLACK | 45322 | 45322 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 338.1 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 338.1 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2401210A | 337.85 | F21P1 AMAT Interconnection | 3394 | C |  | trim edge, spring nut, hex nut, washer, cleanroom tape. | 45316 | 45316 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 337.85 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 337.85 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304019A | 337 | F21P1 WWT package (Installation and 2 batch tanks) | 1860 | C |  | CCB Box Label | 45023 | 45027 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 312 | 0.92582 | 25 | 0 | 25 | 21.84 | [32 empty] | 312 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 10.11 |  | 0 |  | - | 0 | 0 | 0 | 21.84
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403062A | 332.34 | F21P1-0404_H_labor for 50 tools_MICU | 3767 | C |  | Office supplies for tool hookup ppep trade | 45357 | 45358 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 328.02 | 0.987 | 4.32 | 0 | 4.32 | 0 | 328.02 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405178A | 332 | F21P1-0404_H_labor for 50 tools_MICU | 4206 | C |  | PIPE P/E CLR PVC SCH40, FOR CHEMICAL tool hookup team | 45443 | 45443 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 332 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 332 | [8 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2311048A | 328.72 | F21P1 Chemical & WCCS package | 2903 | C |  | CDS blind flanges requested by Ben Chuang for pressure test. | 45240 | 45240 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 328.72 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 328.72 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2312134A | 328.27 | EBO21- Tool interconnection | 3123 | C |  | EBO: ZFP3-1: GEX INTERCONNECT MATERIAL | 45279 | 45281 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 328.27 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 328.27 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2309089A | 326.25 | F21P1 Module Tool Interconnection CMP1 | 2562 | C |  | CMP: MKS1-4: CUSHIONED CLAMPS | 45184 | 45287 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 326.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 326.25 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409034A | 324.53 | Tool Interconnection Project (Main Tool & Other Vendors) | 1236 | P |  | 6" ISO160 BLANK FERRULE (FLANGE) SS | 45553 | 45553 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 324.53 | 0 | 324.53 | 0 | [73 empty] | -
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401109A | 323.94 | F21P1-0404_H_labor for 50 tools_MICU | 3296 | C |  | office supplies for tool hookup department | 1/16/2024 8/22/2024 | 1/16/2024 8/28/2024 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 309.46 | 0.9553 | 14.48 | 0 | 14.48 | 0 | 309.46 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408018A | 323 | Tool Interconnection Project (Main Tool & Other Vendors) | 1187 | P |  | 3/4" 90 Degree Female NPT Elbow Fitting | 45519 | 45523 | [6 empty] | Industrial Pipe & Valve Inc. | PR Approved | PO Approved | [14 empty] | 323 | 1 | 0 | 323 | -323 | 0 | [73 empty] | 323
Hookup | Foundation | Material |  |  | Others |  |  | USC23C047 | USCSB2307013A | 322.5 | F21P1 HK Seismic Installation | 2185 | C |  | Seismic Sticker | 45113 | 45118 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 322.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 322.5 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401081A | 322 | Tool Interconnection Project (Main Tool & Other Vendors) | 701 | P |  | KPE601-S RL MECHANICAL HVAC LABOR PAY | 45317 | 45317 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 322 | 0 | 322 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC24C006 | USCSB2405140A | 320.67 | WWT B side Project | 4164 | C | -01 | 氨氮標準液 | 45435 | 2024/5/28 2024/5/29 | [6 empty] | Winn Marion Barber, LLC | PR Approved | PO Approved | R1: Modify Liquidation Damage to NA | [13 empty] | 320.67 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 320.67 | [8 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C046 | USCSB2404053A | 320.04 | F21P1 ATS Interconnection | 4047 | C |  | ATS: NO TOOL: CLEANROOM TAPE & NOTEBOOKS | 45387 | 45387 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 320.04 | 0 | 320.04 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C006 | USCSB2410009A | 320 | WWT B side Project | 4955 | C |  | WWT shortage of hardware materials on the B side | 45566 | 45567 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 320 | 0 | 320 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2402033A | 319.83 | F21P1 Module Tool Interconnection ETC1-3 | 3476 | C |  | Etch 2 CIP installation DAQ - DAQ installation tools | 45325 | 45327 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 283.43 | 0.88619 | 36.4 | 0 | 36.4 | 0 | 283.43 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404071A | 319.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 1025 | P |  | 23AB02Z 2 Hole 90° (1 7/8 x 2) Angle Bracket EG | 45400 | 45399 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 319.5 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 319.5 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2304038A | 318.7 | F21P1 UPW | 1878 | C |  | Seismic snubber YS-90EA | 45033 | 45043 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 318.7 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 318.7 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C063 | USCSB2312071A | 316 | F21P1-0423_H_T&M Hardware_MICU | 3063 | C |  | 400CL-005H 1/2" PIPE P/E CLR PVC SCH40, | 45272 | 45274 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 316 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 316 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2404118A | 314.66 | F21P1 Chemical & WCCS package | 4103 | C |  | Quality Material | 2024/4/15 2024/4/16 | 45401 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 278.25 | 0.88429 | 36.41 | 0 | 36.41 | 0 | 278.25 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312006A | 311.58 | Tool Interconnection Project (Main Tool & Module) | 558 | P |  | 1" x 1/4" BPE CON RDC 20 RA 316SS: MFG P/N S31-1x.25-PL-316 | 45261 | 45266 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 311.58 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 311.58 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | M+L | USC21C007 | USCSB2306113A | 311.1 | F21P1 VOC package （Installation ) | 2146 | C |  | VOC Electrical:TSMC-MIC VOC Pipe -VEX | 45101 | 45126 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 311.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 311.1 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2404108A | 310.96 | Tool Interconnection Project (Main Tool & Other Vendors) | 1052 | P |  | Manpower Pay to RS Payroll Services for Tool ID: KESTL6 for Timecard on 2.20.2024 for worker: Shamarriee Murphy | 45409 | 45411 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 310.96 | 0 | 310.96 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112006A | 309.48 | F21P1 UPW | 74 | P0 |  | Printer cart with storage | 44533 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 309.48 | 1 | 0 | 0 | 0 | 0 | 309.48 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C047 | USCSB2407160A | 308.25 | F21P1 HK Seismic Installation | 4584 | C |  | Hillman 12-mm x 1.75 Zinc-plated Steel Hex Nut (2-Count) | 45500 | 45503 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 308.25 | 0 | 308.25 | [74 empty] | -
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401047A | 307.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 669 | P |  | KECOT5 MANPOWER PAY FOR E-OPS | 45311 | 45314 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 307.5 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 307.5 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201014A | 304.92 | F21P1 UPW | 108 | P0 |  | Solid State Drive | 44650 | 44650 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | James Baginskis | Yi En Wong | [7 empty] | 304.92 | 1 | 0 | 0 | 0 | 0 | 304.92 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2201001A | 304.61 | F21P1 UPW | 97 | P0 |  | Office Chair | 44569 | 44572 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | [7 empty] | 304.61 | 1 | 0 | 0 | 0 | 0 | 304.61 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407003A | 304.01 | Tool Interconnection Project (Main Tool & Other Vendors) | 1144 | P |  | anchor bolt | 45475 | 45476 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 304.01 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 304.01 |  |  | - |  |  | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2409017A | 301.93 | F21P1 AMAT Interconnection | 4786 | C |  | AMAT_Purchase 4 sets of D-ring, Sliding beam clamp, D-ring anchor for Tool ID:KSWGA2,KDIGA8,KSCPA2,KSSBAH | 45539 | 45541 | [6 empty] | WW Grainger Inc (DBA Grainger) | PR Approved | PO Approved | [14 empty] | 0 | 0 | 301.93 | 274.48 | 27.45 | 0 | [73 empty] | -
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406040A | 300.12 | Chemical & WCCS B Side Project | 4266 | C |  | F21P1 B Side material Mcmaster-carr - SUS Y-Strainers | 45449 | 45449 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 300.12 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 300.12 | [10 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2409053A | 300 | F21P1 AMAT Interconnection | 4849 | C |  | P1A_AMAT_KCEPA3_CABLE WORK_Delta Wye | 45549 | 45561 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 300 | 0 | 300 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403139A | 297 | F21P1-0404_H_labor for 50 tools_MICU | 3840 | C |  | Multi-Voltage Rapid Battery Charger for HK Exhasut system | 45365 | 45366 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 198 | 0.66667 | 99 | 0 | 99 | 0 | 198 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402129A | 296 | F21P1 Chemical & WCCS package | 3566 | C |  | CDS plastic clamp | 45336 | 45337 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 296 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 296 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2401013A | 295.98 | F21P1 WWT package (Installation and 2 batch tanks) | 3204 | C |  | WWT tools and office supplies for MU | 45295 | 45295 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 260.4 | 0.87979 | 35.58 | 0 | 35.58 | 31.248 | 260.4 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 8.8794 |  |  |  | 8.8794 |  | 31.248 |  | - | 0 | 0 | 0 | 0
Base-Build | CCTV |  | The budget execution does not pertain to this project | 光阻櫃 | Low Voltage | Mechanical | M+L | USC22C013 | USCSB2406078A | 288.96 | F21P1 QR Lab Security & CCTV | 4310 | C |  | F21-P1_B-SIDE Photoresist cabinet exhaust hookup | 45457 | 45457 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 288.96 | 0 | 288.96 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405052A | 284 | Tool Interconnection Project (Main Tool & Other Vendors) | 1094 | P |  | Manpower Pay to RS PAYROLL for Tool IDs: KESRT1 AND KESRT2 for Cable Pull and 8395 Rule on Timecard for 3.20.2024 for James Thompson | 45426 | 45429 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 284 | 0 | 284 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2402236A | 284 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3662 | C |  | RS PAYROLL SERVICES, TIMECARD PAYMENT FOR ASSOCIATES | 45346 | 45349 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 284 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 284 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2401065A | 281.7 | F21P1-0404_H_labor for 50 tools_MICU | 3254 | C |  | Office supplies for tool hookup Alex's team | 45302 | 45302 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 220.65 | 0.78328 | 61.05 | 0 | 61.05 | 0 | 220.65 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405153A | 281.49 | F21P1-0404_H_labor for 50 tools_MICU | 4182 | C |  | Hex bolt and nut for HK PPL trade. New PR to replace USCSB2312151 | 45441 | 45442 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved | [14 empty] | 281.49 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 281.49 | [10 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USC2404051A | 279.3 | F21P1 AMAT Interconnection | 1004 | P | -01 | insulation tape | 2024/4/10 2024/5/6 | 2024/4/10 2024/5/8 | 110.38 | 168.92 |  | V | V |  | Independent Electric Supply, Inc. | PR Approved | PO Approved | R1: Adjusting the amount due to additional purchase on the PO and need to align with invoices. |  | Yi En Wong | [11 empty] | 279.3 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 279.3 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2405172A | 279.27 | F21P1 Module Tool Interconnection ETC1-3 | 4200 | C |  | 3/8" HEAT SHRINK TUBING 3:1 RATIO and HEAT- ALL SHRINNK TUBING HWT-0025 | 45442 | 45448 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 253.82 | 0.90887 | 25.45 | 0 | 25.45 | 0 | 253.82 | [72 empty] | - |  |  | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Office Supplies | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C005 | USC2210003A | 276.9 | F21P1 Chemical & WCCS package | 248 | P0 |  | 27in Monitor | 44835 | 44839 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 276.9 | 1 | 0 | 0 | 0 | 0 | 276.9 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112031A | 276.49 | F21P1 UPW | 94 | P0 |  | LG 34" Monitor | 44553 | 44558 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid (員工代墊款) | Credit card paid (員工代墊款) | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 276.49 | 1 | 0 | 0 | 0 | 0 | 276.49 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401050A | 276 | Tool Interconnection Project (Main Tool & Other Vendors) | 672 | P |  | KECOT5 MANPOWER PAY FOR CGS GLOBAL | 45311 | 45313 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 276 | 0 | 276 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Housekeeping | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Housekeeping | USC21C003 | USCSB2404085A | 275.37 | F21P1 UPW | 4074 | C |  | Home Depot - Cleaning and equipment maintenance | 45392 | 45398 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | 0 | [11 empty] | 248.35 | 0.90188 | 27.02 | 0 | 27.02 | 0 | 248.35 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 41.3055 |  |  |  | 41.3055 |  |  |  | 41.3055 |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2402064A | 274.97 | EBO21- Tool interconnection | 3506 | C |  | EBO: ZCOAT-1: RIGID UNISTRUT CLAMPS | 45329 | 45364 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 274.97 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 274.97 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2401026A | 274.68 | EBO21- Tool interconnection | 3217 | C |  | EBO: ZASC5-1: INTERCON. MATERIAL. CABLE TRAY | 45296 | 45303 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 274.68 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 274.68 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2312004A | 273.25 | Tool Interconnection Project (Main Tool & Module) | 556 | P |  | 1 X NITROGEN, COMPRESSED, 2.2 NITROGEN T MRO5505 | 45261 | 45265 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 273.25 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 273.25 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2306051A | 273.18 | Tool Interconnection Project (Main Tool & Module) | 334 | P |  | Nitrogen, Compressed, 2.2 Nitrogen T | 45105 | 45119 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 273.18 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 273.18 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403131A | 272.66 | F21P1-0404_H_labor for 50 tools_MICU | 3833 | C |  | Tipped hole cutters for stainless steel mild steel copper for HK Power trade JerYih | 45364 | 45364 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 236.8 | 0.86848 | 35.86 | 0 | 35.86 | 0 | 236.8 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403112A | 270 | Tool Interconnection Project (Main Tool & Other Vendors) | 928 | P |  | 5406007 25mmx3/4" Fitting Trans BF PipexT Tube Flare HP PVDF | 45377 | 45377 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 270 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 270 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409099A | 269.44 | TSMC Fab 21 P1B Tool Hook Up | 4907 | C |  | MIC power team hardware request RED WASH for 200 tools | 45561 | 45562 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 269.44 | 0 | 269.44 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2404070A | 268.38 | Tool Interconnection Project (Main Tool & Other Vendors) | 1024 | P |  | HS Extra Long Heavy Duty Zip Tie Straps (50 Pack) Thick 0.35 Inch Plastic Duct Zip Ties Heavy Duty 175 Pounds,Black Large Zip Ties 36 Inch for HVAC,Travel,Packaging,Vessel for TOOL ID#KDPOT8, KDPOT7, KDEPT3. | 45400 | 45399 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 201.9 | 0.75229 | 66.48 | 0 | 66.48 | 0 | 201.9 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2407018A | 265.5 | F21P1 Module Tool Interconnection ETC1-3 | 4419 | C |  | 8 AWG Max Wire Size | 45475 | 45485 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 265.5 | 265.5 | 0 | 0 | [73 empty] | - |  |  | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2410003A | 263.91 | TSMC Fab 21 P1B Tool Hook Up | 4950 | C |  | 60/40 Tin Lead Solder Wire for HK Power for 40 tools | 45566 | 45566 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 263.91 | 0 | 263.91 | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC22C017 | USCSB2401097A | 262.6 | AMHS MML Power Design | 3284 | C | -01 | QAQC | 1/13/2024 2/15/2024 | 1/16/2024 3/27/2024 | 14.88 | 247.72 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: Adjusting the amount to align with the credit card write off record. |  | Jen-Ping Tsai Yikang Wang |  |  |  | Jen-Ping Tsai | [7 empty] | 262.6 | 1 | 0 | 0 | 0 | 0 | 262.6 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2304076A | 261 | F21P1 Module Tool Interconnection DIF1-2 | 1914 | C |  | Tamper evident seal/label | 45043 | 45051 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 261 | 0 | 261 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407015A | 260 | F21P1-0404_H_labor for 50 tools_MICU | 4416 | C |  | 珠光不上膜白底黑字圓 | 45475 | 45475 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | [14 empty] | 260 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 260 |  |  |  |  | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403166A | 259.1 | F21P1-0404_H_labor for 50 tools_MICU | 3864 | C |  | 3-Port and 4-Port connectors for HK Power trade | 45366 | 45370 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 259.1 | 0 | 259.1 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation |  |  |  | Others |  |  | USC23C047 | USCSB2409019A | 258.9 | F21P1 HK Seismic Installation | 4788 | C |  | M12 Hex Nut*500, 1/2" nuts*2500 | 45540 | 45541 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 258.9 | 258.9 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402079A | 258.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 795 | P |  | SS-400-1-4 MALE CONNECTOR 1/4" SWG X 1/4" MNPT | 45344 | 45344 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 258.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 258.2 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2312057A | 258.13 | F21P1 Chemical & WCCS package | 3050 | C |  | CDS CED DFK Lorry HPM materials additional quote | 45268 | 45268 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 258.13 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 258.13 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2409059A | 257.5 | WWT B side Project | 4855 | C |  | WWT shortage materials on the B side NaOH | 45552 | 45552 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 257.5 | 0 | 257.5 | 0 | [73 empty] | -
Base-Build | Barcode |  | The budget execution does not pertain to this project | 0 | Low Voltage | Electrical | Material | USC22C001 | USCSB2405123A | 256.5 | F21 P1 Office and WH Security and CCTV | 4151 | C |  | F21 Barcode system _G-Bit | 45434 | 45435 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved | [14 empty] | 256.5 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 256.5 | [6 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2304067A | 253.08 | F21_AZQR_Hookup_ Interconnection | 1906 | C |  | QR Special Adaptors Harrington | 45038 | 45040 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 253.08 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 16.88 |  | 236.2 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2310062A | 252.2 | F21P1 Module Tool Interconnection CMP1 | 2722 | C |  | CMP Interconnection Material Tubing | 45210 | 45212 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 252.2 | 1 | 0 | -252.2 | 252.2 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 252.2 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | The budget execution does not pertain to this project | Shared Cost | UPW | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C009 | USCSB2404147A | 251.9 | F21P1 WWT package (Installation and 2 batch tanks) | 4131 | C |  | Amazon - UPW Clean up and equipment maintenance | 45401 | 45405 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 229 | 0.90909 | 22.9 | 0 | 22.9 | 0 | 229 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2409104A | 250 | F21P1-0404_H_labor for 50 tools_MICU | 4912 | C |  | Hardware 軟外塞增加 1000個 | 45561 | 45561 | [6 empty] | Jinsheng Industrial Co | PR Approved | PO Approved | [14 empty] | 250 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 250
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2208018A | 249.67 | F21P1 UPW | 217 | P0 |  | VIZ PRO Dry Erase Whiteboard Non Magnetic pack of 2 5x3' | 44800 | 44810 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 249.67 | 1 | 0 | 0 | 0 | 0 | 249.67 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USC2402074A | 248.88 | F21P1 Module Tool Interconnection DIF1-2 | 790 | P |  | HS Extra Long Heavy Duty Zip Tie Straps (50 Pack) | 45342 | 45343 | [6 empty] | Amazon | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 201.9 | 0.81123 | 46.98 | 0 | 46.98 | 0 | 201.9 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403116A | 247.46 | Tool Interconnection Project (Main Tool & Other Vendors) | 932 | P |  | SPL012 1-1/4X10 FT PVC S40 CLR PIPE | 45378 | 45377 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 247.46 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 247.46 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2409058A | 246.2 | WWT B side Project | 4854 | C |  | WWT shortage materials on the B side NaOH | 45552 | 45552 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 246.2 | 0 | 246.2 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2402093A | 245.76 | F21P1 WWT package (Installation and 2 batch tanks) | 3533 | C |  | WWT SUS Pipes_20240208 (A Side) | 45331 | 45335 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 245.76 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  | 245.76 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Material | USC24C006 | USCSB2405091A | 244.89 | WWT B side Project | 4111 | C |  | The electrical pipe installation for power and control of WSR. | 45427 | 45427 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 244.89 | 1 | 0 | 0 | 0 | 244.89 | [56 empty] | 0 | [14 empty] | 244.89 |  | 244.89 | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401027A | 243.08 | Tool Interconnection Project (Main Tool & Other Vendors) | 650 | P |  | Cut and modify all AC covers on KECOT5 for power/signal cables per TEL spec. | 45304 | 45308 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 243.08 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 243.08 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401028A | 243.08 | Tool Interconnection Project (Main Tool & Other Vendors) | 651 | P |  | Cut and modify all AC covers on KECOT1 for power/signal cables per TEL spec. | 45304 | 45308 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 236 | 0.97087 | 7.08 | 0 | 7.08 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 236 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401029A | 243.08 | Tool Interconnection Project (Main Tool & Other Vendors) | 652 | P |  | Cut and modify all AC covers on KECOT2 for power/signal cables per TEL spec. | 45304 | 45307 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 243.08 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 243.08 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2308114A | 242.25 | F21P1 Chemical & WCCS package | 2411 | C |  | 1/2" union Qty 5/1/4" gasket Qty 50 For Chemical welding | 45157 | 45159 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 242.05 | 0.99917 | 0.2 | 0 | 0.2 | 0 | [40 empty] | 242.05 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Labor | USC21C005 | USCSB2403068A | 241.24 | F21P1 Chemical & WCCS package | 3773 | C | -01 | CDS NZM1-XTVD DOOR COUPLING ROTARY HDL LOCK | 45358 | 2024/3/9 2024/3/22 | [6 empty] | RS AMERICAS, INC | PR Approved | PO Approved | PO R1:Payment Term Change |  | Yikang Wang |  |  |  | 0 | [7 empty] | 241.24 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 241.24 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404062A | 240.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 1015 | P |  | BPT 247 3IN SET SCREW CPLG | 45398 | 45400 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 240.2 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 240.2 | [12 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402139A | 237.6 | F21P1-0404_H_labor for 50 tools_MICU | 3574 | C |  | Office supplies for HK PPEP team | 45337 | 45342 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 211.21 | 0.88893 | 26.39 | 0 | 26.39 | 0 | 211.21 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2304027A | 235.2 | F21P1 WWT package (Installation and 2 batch tanks) | 1867 | C |  | NFPA labels | 45028 | 45030 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 235.2 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 235.2 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2410019A | 235 | TSMC Fab 21 P1B Tool Hook Up | 4962 | C |  | Safety PPE, Tool hookup team | 45567 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 235 | 0 | 235 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407075A | 234.9 | TSMC Fab 21 P1B Tool Hook Up | 4491 | C |  | Mfr. No.XC5585-CB Cleanbuild Construction Cleanroom Notebook, 5.5x8.5, College Rule Shared by all HK system | 45486 | 45488 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 154.8 | 0.659 | 80.1 | 154.8 | -74.7 | 0 | [73 empty] | 154.8 |  |  | 0
Base-Build | Chemical | Material | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308017A | 234.78 | F21P1 Chemical & WCCS package | 2319 | C |  | TGCM Duty Room items – screen | 45142 | 45142 | [6 empty] | Office Depot Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 234.78 | 0 | 234.78 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 234.78 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2403146A | 234.76 | F21P1 Module Tool Interconnection DIF1-2 | 3846 | C |  | 5 in. x 60 in. Non-insulated Flexible SS-Flex 800 Stainless Steel Hose Silver For KDSRK1 | 2024/3/14 2024/8/12 | 2024/3/14 2024/8/12 | -31.46 | 266.22 | V |  |  |  | The Home Depot, Inc | PR Approved | PO Approved | PR R1: Price Variation of $31.46 which created an excess in the original PO |  | Ta Wei Wang | [11 empty] | 234.76 | 1 | 0 | 0 | 0 | 0 | 234.76 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C006 | USCSB2307002A | 233.76 | F21P1 Module Tool Interconnection EPI | 2176 | C | -01 | Glands and unions for AMAT EPI interconnect materials | 45108 | 2023/8/2 2023/8/15 | -1103.4 | 1337.16 |  | V |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: Change of material requirement by TSMC |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 233.76 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 233.76 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2311128A | 233.4 | F21P1 Chemical & WCCS package | 2978 | C |  | CDS Lorry Exhaust. Elbow 3/4" Super 300 Type | 45259 | 45260 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 233.4 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 233.4 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405104A | 231.64 | F21P1-0404_H_labor for 50 tools_MICU | 4135 | C | -01 | Cleanroom order for HK EHS | 2024/5/17 2024/5/25 | 45435 | -182.04 | 413.68 |  |  |  |  | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 231.64 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 231.64 | [10 empty] | - |  |  | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2409122A | 231.49 | TSMC Fab 21 P1B Tool Hook Up | 4940 | C |  | Label printer shared for all system | 45563 | 45567 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approving | [14 empty] | 0 | 0 | 231.49 | 0 | 231.49 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2311045A | 230.06 | F21_AZQR_Hookup_ Interconnection | 2900 | C |  | QR: KXMS01: EDGE TRIM | 11/9/2023 9/24/2024 | 11/16/2023 9/26/2024 | -0.03 | 230.09 |  |  |  |  | McMaster-Carr Supply Company | PR Approved | PO Approved | R1: Returning the rest of the funds back to the account. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 230.06 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 230.06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2309105A | 230 | F21P1 Module Tool Interconnection DIF1-2 | 2577 | C |  | DIFF1: 19 TOOLS: REGULATOR FOR THE N2 TESTING | 45188 | 45195 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 230 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 230 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2205002A | 228.74 | F21P1 UPW | 167 | P0 |  | Construction site modular office supplies | 44699 | 44820 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 228.74 | 1 | 0 | 0 | 0 | 0 | 228.74 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2307025A | 225.6 | F21_AZQR_Hookup_ Interconnection | 2197 | C |  | QR LAB: VNTC-PVC/NYLON INSULATION - PVC JACKET -18 AWG | 45114 | 45127 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 225.6 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 225.6 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2309031A | 225.39 | F21P1 Module Tool Interconnection DIF1-2 | 2508 | C | -01 | DIFF1: 19 TOOLS FOR THE N2 TESTING | 45177 | 45182 | -37.5 | 262.89 |  | V |  |  | Linde Gas and Equipment Inc | PR Approved | PO Approved | PO R1:Invoiced did not include cylinder Rental |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 225.39 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 225.39 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311049A | 224.63 | Tool Interconnection Project (Main Tool & Module) | 522 | P | -01 | Cable tray divider | 45247 | 2023/11/20 2023/11/21 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Supplier Request to change completion date |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 224.63 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 40.91 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 183.72 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C006 | USCSB2309066A | 224.24 | F21P1 Module Tool Interconnection EPI | 2541 | C |  | EPI: KEXR01 KCEPS1 KCEPS3 CABLE TRAY DIVIDER | 45182 | 2023/9/15 2024/8/10 | -0.04 | 224.28 |  |  |  |  | Independent Electric Supply, Inc. | PR Approved | PO Approved | PO R1:Updated amount to match the invoice & to close PO. Credited $.04. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 224.24 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 224.24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409073A | 224.15 | TSMC Fab 21 P1B Tool Hook Up | 4866 | C |  | Office Supples for HK shared by Hank's 4 systems | 45554 | 2024/9/23 2024/9/30 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | R1: Revise to change Payment Term to NET 30 | [13 empty] | 0 | 0 | 224.15 | 0 | 224.15 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409103A | 222.13 | TSMC Fab 21 P1B Tool Hook Up | 4911 | C |  | MIC power team hand tool padlock and chain request for 200 tools | 45561 | 45562 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 222.13 | 0 | 222.13 | 0 | [73 empty] | -
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111065A | 220.78 | F21P1 UPW | 66 | P0 |  | Office chair | 44525 | 44543 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang |  |  | Matt |  |  |  |  | 220.78 | 1 | 0 | 0 | 0 | 0 | 220.78 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403252A | 220.4 | F21P1-0404_H_labor for 50 tools_MICU | 3945 | C |  | Cable ties for HK Power trade | 45378 | 45387 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 220.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 220.4 |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408101A | 219.75 | TSMC Fab 21 P1B Tool Hook Up | 4709 | C |  | Pressure washer, hose, and sump pump for HK MIMO | 45526 | 45531 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 209.69 | 0.95422 | 10.06 | 0 | 10.06 | 0 | [72 empty] | 209.69 | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402090A | 219.35 | Tool Interconnection Project (Main Tool & Other Vendors) | 805 | P |  | BPT 437SLTI | 45345 | 45346 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402089A | 219.35 | Tool Interconnection Project (Main Tool & Other Vendors) | 804 | P |  | BPT 437SLTI | 45344 | 45346 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402083A | 219.35 | Tool Interconnection Project (Main Tool & Other Vendors) | 798 | P |  | BPT 437SLTI | 45344 | 45344 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402085A | 219.35 | Tool Interconnection Project (Main Tool & Other Vendors) | 800 | P |  | BPT 437SLTI | 45344 | 45344 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402091A | 219.35 | Tool Interconnection Project (Main Tool & Other Vendors) | 806 | P |  | BPT 437SLTI | 45345 | 45346 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402086A | 219.35 | Tool Interconnection Project (Main Tool & Other Vendors) | 801 | P |  | BPT 437SLTI | 45344 | 45344 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402088A | 219.35 | Tool Interconnection Project (Main Tool & Other Vendors) | 803 | P |  | BPT 437SLTI | 45344 | 45344 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2403052A | 218.17 | Tool Interconnection Project (Main Tool & Other Vendors) | 876 | P |  | BRADY***B30C-2250-569-GN: FACTORY SHIP LEAD TIME: 4-5 WEEKS PLUS FREIGHT | 45363 | 45364 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 218.17 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 218.17 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409063A | 218 | TSMC Fab 21 P1B Tool Hook Up | 4858 | C |  | 6-Tier Commercial Grade Heavy Duty Steel Wire Shelving | 45553 | 45554 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 218 | 0 | 218 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407029A | 217.31 | F21P1-0404_H_labor for 50 tools_MICU | 4428 | C |  | Pressure washer, hose, and sump pump for HK MIMO | 45477 | 45478 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 217.31 | 0 | 217.31 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409069A | 216.72 | TSMC Fab 21 P1B Tool Hook Up | 4882 | C |  | Cleanroom notebooks shared by all hk systems | 45554 | 45559 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 216.72 | 0 | 216.72 | 0 | [73 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC24C006 | USCSB2405174A | 216 | WWT B side Project | 4202 | C |  | WWT PVC PP Unions_20240529 (B Side) | 45442 | 45447 | [6 empty] | Delpha Plastics Co., Ltd. | PR Approved | PO Approved | [14 empty] | 216 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 216 |  |  |  |  | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405037A | 215.84 | Tool Interconnection Project (Main Tool & Other Vendors) | 1079 | P |  | Manpower Pay to RS Payroll Services for Tool ID: KEPRL5 for Cable Pull and 8395 Rule on Time Card from 3.8.2024 for Michael Rodriquez | 45423 | 45425 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 215.84 | 0 | 215.84 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2403203A | 214.5 | F21P1 WWT package (Installation and 2 batch tanks) | 3899 | C |  | WWT WRC laboratory furniture_2 | 45371 | 45376 | [6 empty] | Ramo Trading & Consulting Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 185.25 | 0.86364 | 29.25 | 0 | 29.25 | 0 | 185.25 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 32.175 |  |  |  | 32.175 |  |  |  | 32.175 |  | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407078A | 211.84 | TSMC Fab 21 P1B Tool Hook Up | 4494 | C |  | For UPW system pe-fab area | 2024/7/14 2024/10/3 | 2024/7/15 2024/10/3 | -21.1 | 232.94 | V |  |  |  | Amazon.com, Inc. | PR Approved | PO Approving | PO R1: Per purchaning team request, amend to the final amount. | [13 empty] | 211.84 | 1 | 0 | 0 | 0 | 0 | 211.84 | [72 empty] | - |  |  | 0
Base-Build | Base-Build | Site Expense | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2403300A | 211.75 | F21P1 UPW | 3992 | C |  | LB2 Train-A Anchor Tank Safety Supplies | 45381 | 45393 | [6 empty] | Safety Solutions & Supply | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 211.75 | 0 | 211.75 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406134A | 211.7 | F21P1-0404_H_labor for 50 tools_MICU | 4373 | C |  | Grainger Loto PR for Power Luis Retiz for 100 LOTO for 7 tools | 45469 | 45470 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | [14 empty] | 211.7 | 1 | 0 | 15.12 | -15.12 | 0 | [72 empty] | 211.7 | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408005A | 210.94 | TSMC Fab 21 P1B Tool Hook Up | 4603 | C |  | Wire Brush for HK PPL Prefab | 45506 | 45506 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 153.12 | 0.72589 | 57.82 | 0 | 57.82 |  | 153.12 | [72 empty] | -
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2306075A | 210.6 | F21 TMAH System | 2108 | C |  | WWT ICW-4” SUS flange | 45093 | 2023/6/16 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 210.6 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 210.6 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2309109A | 208 | F21P1 Module Tool Interconnection CMP1 | 2581 | C | -01 | CMP: KMPRE1: 76MM/1P PEDESTAL CLAMPS | 45188 | 2023/9/26 2023/10/4 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved | PO R1:Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 208 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 208 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2312168A | 208 | F21P1 Module Tool Interconnection CMP1 | 3156 | C |  | CMP: MKS1: INTERCONNECT MATERIAL PEDESTAL CLAMPS | 45282 | 45287 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 208 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 208 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312003A | 207.58 | Tool Interconnection Project (Main Tool & Module) | 555 | P |  | FLEX LT2UAGRY 2 UL LIQ-TITE FLEXIBLE TYPE; 50 FT; UL APPROVAL; 2 INCH TRADE SIZE; UA/LA STYLE; GRAY JACKET COLOR; STEEL CORE MATERIA | 45261 | 45264 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 207.58 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 207.58 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C006 | USCSB2403025A | 207.14 | F21P1 Slurry package | 3734 | C |  | Chem PVDF Fittings_20240229 | 45353 | 45356 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 207.14 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 207.14 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204015A | 206.33 | F21P1 UPW | 162 | P0 |  | Compact refrigerator for sub contractors trailer | 44679 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 206.33 | 1 | 0 | 0 | 0 | 0 | 206.33 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2202008A | 206.33 | F21P1 UPW | 117 | P0 |  | Portable Monitor | 44604 | 44609 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 206.33 | 1 | 0 | 0 | 0 | 0 | 206.33 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2402161A | 205.5 | F21P1 AMAT Interconnection | 3593 | C |  | CED WIRE, KKSS03 Metrology | 45338 | 45342 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 205.5 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 205.5 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402177A | 204.7 | F21P1-0404_H_labor for 50 tools_MICU | 3606 | C |  | Multi-Tap Connector; 10-250 AWG-kcmil; 2-Port; 600 VAC; 3/16 In.for HK Power trade | 45342 | 45343 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 204.7 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 204.7 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408056A | 204 | Tool Interconnection Project (Main Tool & Other Vendors) | 1202 | P |  | Admin Fee | 45526 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 204 | 0 | 204 | 0 | [73 empty] | -
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2312067A | 204 | F21P1 UPW | 3059 | C | -01 | UPW-Horiba adaptor | 2023/12/9 2023/12/15 | 2023/12/12 2023/12/15 | 2 | 202 | V |  |  |  | HORIBA Taiwan, Inc. | PR Approved | PO Approved | PR R1: Unit rate round up to $34 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 204 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 204 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24C015 | USCSB2409116A | 203.19 | TSMC Fab 21 P1B Tool Hook Up | 4934 | C |  | MIC power team hardware request 4 AWG ?’’ terminal for 200 tools | 45562 | 45565 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 203.19 | 0 | 203.19 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2405110A | 201.76 | F21P1 AMAT Interconnection | 4140 | C |  | Mateiral Storage | 45430 | 45443 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 187.97 | 0.93165 | 13.79 | 0 | 13.79 | 0 | 187.97 | [72 empty] | - |  |  | 0
Non-TSMC | Organo |  |  |  | Others |  |  | USC24C013 | USCSB2407045A | 200 | Organo USA - UPW Electrical | 4444 | C |  | MCP Fan Cover | 45483 | 45484 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 200 | 200 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2403227A | 199.12 | F21P1 WWT package (Installation and 2 batch tanks) | 3922 | C |  | S-11545 Draw ULINE - Cord Bags – 20X24X4 Clear 250/Per Carton | 45373 | 45376 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 197.26 | 0.99066 | 1.86 | 0 | 1.86 | 199.12 | 197.26 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 29.868 |  |  |  | 29.868 |  |  |  | 29.868 |  | 199.12 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403126A | 197.76 | Tool Interconnection Project (Main Tool & Other Vendors) | 941 | P |  | Routing PFA chiller lines in L30 for KSECN3 | 45378 | 45379 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 197.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 197.76 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2309158A | 196.75 | F21P1 Chemical & WCCS package | 2629 | C |  | MILWAUKEE Portable Shop Vacuum. | 45195 | 45195 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 196.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 196.75 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403080A | 195.96 | Tool Interconnection Project (Main Tool & Other Vendors) | 899 | P |  | Manpower Pay for CGS Tool ID KEMEL4 | 45370 | 45377 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 195.96 | 0 | 195.96 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402023A | 195.83 | F21P1 Chemical & WCCS package | 3466 | C |  | CDS cush clamp, screw | 45324 | 45324 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 195.83 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 195.83 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409024A | 194.74 | Tool Interconnection Project (Main Tool & Other Vendors) | 1227 | P |  | Brady M21-750-499 Signs, Labels & Markers Make-Your-Own Sign, Label & Marker Blanks Continuous Tape Cartridges for Printers | 45547 | 45547 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 173.2 | 0.88939 | 21.54 | 0 | 21.54 | 0 | 173.2 | [72 empty] | -
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111068A | 194.39 | F21P1 UPW | 68 | P0 |  | Drone for F21 Project. | 44530 | 44533 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Debit card paid (員工代墊款) | Debit card paid (員工代墊款) | Lan Yun Chang |  |  | Ka In Wong Lane | Lan Yun Chang |  |  | Matt |  |  |  |  | 194.39 | 1 | 0 | 0 | 0 | 0 | 194.39 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2306111A | 193.99 | F21P1 UPW | 2144 | C |  | UPW-PP-HP-Zewei | 45100 | 45105 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 193.99 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 193.99 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2306007A | 193.57 | F21_AZQR_Hookup_ Interconnection | 2041 | C |  | CED: QR LABS - CABLE TRAY FIXTURE - FAD LALBS | 45080 | 45082 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 193.57 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 193.57 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2402058A | 191.79 | F21P1 Module Tool Interconnection ETC1-3 | 3500 | C |  | CIP ETCH3 - CIP Tools ETCH3 | 45329 | 45331 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 174.13 | 0.90792 | 17.66 | 0 | 17.66 | 0 | 174.13 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2210010A | 191.12 | F21P1 UPW | 253 | P0 |  | Black 3 drawer file cabinet | 44838 | 44848 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 191.12 | 1 | 0 | 0 | 0 | 0 | 191.12 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401031A | 189.1 | F21P1-0404_H_labor for 50 tools_MICU | 3222 | C |  | Braided Steel security cable and brass combination padlock. shared by all system/trades | 45297 | 45300 | [6 empty] | Harbor Freight Tools USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 118.63 | 0.62734 | 70.47 | 0 | 70.47 | 0 | 118.63 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402118A | 187.5 | F21P1-0404_H_labor for 50 tools_MICU | 3556 | C |  | office supplies for tool hookup department | 45335 | 45337 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 183.14 | 0.97675 | 4.36 | 0 | 4.36 | 0 | 183.14 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312084A | 183.67 | F21P1-0404_H_labor for 50 tools_MICU | 3076 | C |  | 2" OD STRUT CLAMP for Tunyi PPL top 100 tools. | 45274 | 45275 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 183.67 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 183.67 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC21C011 | USCSB2410057A | 181.85 | F21 TMAH System | 4997 | C |  | 5191-8121 vials and 5191-8151 caps for LS_MS/MS TMAH room device | 45569 | [8 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 181.85 | 0 | 181.85 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2309108A | 181.6 | F21P1 Module Tool Interconnection CMP1 | 2580 | C | -01 | CMP: MKS1-4: 1” inch cush clamp for CMP | 45188 | 45195 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1:Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 181.6 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 181.6 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403129A | 181.51 | F21P1-0404_H_labor for 50 tools_MICU | 3831 | C |  | Office supplies for HK PPEP team | 45364 | 45364 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 164.19 | 0.90458 | 17.32 | 0 | 17.32 | 0 | 164.19 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MIMO/Rigging |  |  | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC23C059 | USCSB2401140A | 180.32 | F21P1 Foundation T&M | 3325 | C |  | Laydown Material - Global Industrial | 45310 | 45397 | [6 empty] | Global Equipment Company Inc. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 150.94 | 0.83707 | 29.38 | 0 | 29.38 | 0 | 150.94 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409043A | 179.9 | TSMC Fab 21 P1B Tool Hook Up | 4825 | C |  | HK Power trade hardware requested_Metal Wall plate | 45545 | 45545 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 179.9 | 1 | 0 | 179.9 | -179.9 | 0 | [73 empty] | 179.9
Base-Build | VOC | Material | CO Scope (adding/additional scope) | Low Voltage | Low Voltage | Mechanical | Material | USC21C007 | USCSB2308024A | 179.52 | F21P1 VOC package （Installation ) | 2325 | C |  | 4” and 6” FNW gaskets | 45142 | 45142 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 179.52 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 179.52 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Material | USC21C011 | USCSB2405053A | 177.55 | F21 TMAH System | 4059 | C |  | 5191-8121 vials and 5191-8151 caps for LS_MS/MS TMAH room device | 45420 | 2024/5/9 2024/9/10 | [6 empty] | Agilent Technologies, Inc. | PR Approved | PO Approved | po r1:quote number changed | [13 empty] | 0 | 0 | 177.55 | 0 | 177.55 | 177.55 | [56 empty] | 0 | [14 empty] | 177.55 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403241A | 176.9 | F21P1 Chemical & WCCS package | 3934 | C | -01 | CDS CO2 system warning signs | 45377 | 2024/3/27 2024/3/30 | 7.06 | 169.84 | V |  |  |  | Compliance Signs, LLC | PR Approved | PO Approved | R1: Due to the additional shipping fee as per purchasing team David. |  | Ta Wei Wang | [11 empty] | 176.9 | 1 | 0 | 0 | 0 | 0 | 176.9 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 176.9 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405038A | 176 | Tool Interconnection Project (Main Tool & Other Vendors) | 1080 | P |  | Manpower Pay to CGS GLOBAL for Tool ID: KEPRL5 for Cable Pull and 8395 Rule on Time Card from 3.8.2024 for Monica Dabdoub | 45423 | 45429 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 176 | 0 | 176 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2403065A | 175.39 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3770 | C |  | U-LINE-Bump cap white, Ice Wraparounds-Clear,Uline Safety Glass Wipes | 45357 | 45358 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 175.39 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 175.39 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2312121A | 175.14 | F21P1 Module Tool Interconnection DIF1-2 | 3112 |  |  | DIFF2: KDALS1: CONNECTORS | 2024/6/12 | 45457 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 175.14 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 175.14 | [12 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408097A | 174.95 | TSMC Fab 21 P1B Tool Hook Up | 4713 | C |  | Hand tool for GAS system, Tool HK team | 45526 | 45539 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 156.91 | 0.89688 | 18.04 | 0 | 18.04 | 0 | 156.91 | [72 empty] | -
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2310019A | 173.73 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2682 | C |  | Pillar hand tool_0828 requirement | 45203 | 45206 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 173.73 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 173.73 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2308167A | 173.63 | F21P1 Module Tool Interconnection CVD | 2461 | C |  | Change order – conduit install for signal cable routing from L20 to L10 for KCOXN4 | 45167 | 45168 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 173.62 | 0.99994 | 0.01 | 0 | 0.01 | 0 | [40 empty] | 0 | 173.62 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2305017A | 173.22 | Tool Interconnection Project (Main Tool & Module) | 284 | P |  | WORM GEAR SCREW CLAMP, HOSECLAMP | 45077 | 45133 | [6 empty] | FLEXICRAFT INDUSTRIES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 173.22 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 108 |  | 0 | 65.22 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111050A | 172.65 | F21P1 UPW | 51 | P0 |  | Webcam for meeting rooms | 44523 | 44533 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 172.65 | 1 | 0 | 0 | 0 | 0 | 172.65 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2402044A | 171.89 | F21P1 Module Tool Interconnection ETC1-3 | 3486 | C |  | ETCH 2 CIP installation - ETCH 2 CIP installation TOOLS. | 45328 | 45328 | [6 empty] | Harbor Freight Tools USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 171.89 | 0 | 171.89 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C011 | USCSB2403057A | 170.64 | F21 TMAH System | 3762 | C | -01 | WWT-Ammonia-High concentration standards solution | 45357 | 2024/3/6 2024/3/27 | [6 empty] | Winn Marion Barber, LLC | PR Approved | PO Approved | R1: Remark 10 and 20 discussion with supplier |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 170.64 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 25.596 | 170.64 |  |  | 25.596 |  |  |  | 25.596 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2312031A | 167.07 | F21P1 Chemical & WCCS package | 3024 | C |  | CDS #36 Rosary cord twine for JuWei PFA line work requested by Jay Huang. | 45266 | 45273 | [6 empty] | The Fish Net Company, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 161.75 | 0.96816 | 5.32 | 0 | 5.32 | 0 | 161.75 | [44 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2312038A | 166.01 | F21P1 Module Tool Interconnection CVD | 3031 | C |  | KCSNA1 Material Request for Seal-Tite conduit and supporting hardware | 45267 | 45269 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 166 | 0.99994 | 0.01 | 0 | 0.01 | 0 | [45 empty] | 0 | 0 | 0 | 166 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409018A | 157.74 | Tool Interconnection Project (Main Tool & Other Vendors) | 1222 | P |  | Gardner Bender HWT-0025 Heavy-Wall Heat Shrink Tube, 7/8" | 45546 | 45547 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 141.16 | 0.89489 | 16.58 | 0 | 16.58 | 0 | 141.16 | [72 empty] | -
Base-Build | Chemical | Material | CO Scope (adding/additional scope) | CDS | Chemical | Mechanical | Site Expense | USC21C005 | USCSB2308020A | 154.99 | F21P1 Chemical & WCCS package | 2322 | C |  | TGCM Duty Room items – Microwave | 45142 | 45142 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 154.99 | 0 | 154.99 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 154.99 | [9 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C046 | USCSB2404188A | 154.8 | F21P1 ATS Interconnection | 4168 | C |  | ATS: NO TOOL: CLEANROOM NOTEBOOKS | 45407 | 45411 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 154.8 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 154.8 | [12 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C053 | USCSB2408019A | 154.35 | AMAT Interconnection (TSMC) | 4615 | C |  | DIFF - P1B MATERIALS - 1" conduit mounting clamps | 45509 | 45513 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 154.35 | 1 | 0 | 154.35 | -154.35 | [74 empty] | 154.35
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2402127A | 152.72 | F21P1 WWT package (Installation and 2 batch tanks) | 3564 | C |  | Cabinet door in TM room | 45336 | 45337 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 152.72 | 0 | 152.72 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 22.908 |  |  |  | 22.908 |  |  |  | 22.908 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2401098A | 150 | F21P1 UPW | 3285 | C |  | UPW-GF-electrolyte solution | 45304 | 45307 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 150 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 150 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405177A | 150 | F21P1-0404_H_labor for 50 tools_MICU | 4205 | C |  | 珠光不上膜空白綠色圓標-20mm | 45443 | 45443 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 150 | 0 | 150 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402193A | 149.94 | F21P1 Chemical & WCCS package | 3621 | C |  | CDS 1" 90 elbow | 45343 | 45344 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 149.94 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 149.94 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402052A | 148.48 | F21P1-0404_H_labor for 50 tools_MICU | 3494 | C |  | cable lugs for hk power trade | 45328 | 45329 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 148.48 | 1 | 0 | 0 | 0 | 0 | 148.48 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Commissioning | USC21C005 | USCSB2310191A | 147.64 | F21P1 Chemical & WCCS package | 2843 | C |  | CDS Nippon Pillar Fittings for commission flushing | 45230 | 45231 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 147.64 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 96.31 |  |  |  |  | 51.33 |  |  |  |  | 51.33 |  |  |  |  | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403098A | 147.3 | F21P1-0404_H_labor for 50 tools_MICU | 3800 | C |  | Night Vison Optical Monocular Camping/Hunting Handheld Telescope Water Proof and Anti-Fog for HK Exhaust trade | 45360 | 45363 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 133.92 | 0.90916 | 13.38 | 0 | 13.38 | 0 | 133.92 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401050A | 147.3 | F21P1-0404_H_labor for 50 tools_MICU | 3240 | C |  | Bucket: 3/4 gal Capacity, 7 in Overall Wd, 5 in Overall Ht, Galvanized Steel, Graduated, shared materials for Gas system | 45300 | 45301 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 147.3 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 147.3 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402239A | 146.67 | F21P1 Chemical & WCCS package | 3665 | C |  | CDS Ring Terminals | 45346 | 45349 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 121.67 | 0.82955 | 25 | 0 | 25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 121.67 |  |  | 24.93 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2311130A | 145.34 | F21P1 Module Tool Interconnection ETC1-3 | 2980 | C |  | Unistrut for conduit installation KEMEL1 | 45259 | 45264 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 145.34 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 145.34 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401184A | 145 | F21P1-0404_H_labor for 50 tools_MICU | 3369 | C |  | office supplies for tool hookup department | 45314 | 45315 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 132.86 | 0.91628 | 12.14 | 0 | 12.14 | 0 | 132.86 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Electrical | Material | USC21C011 | USCSB2403251A | 144.77 | F21 TMAH System | 3944 | C | -02 | Additional wiring material for Ammonia analyzer_WWT | 45377 | 3/30/2024 4/3/2024 4/5/2024 | -14.48 | 159.25 |  |  |  |  | WW Grainger Inc | PR Approved | PO Approved | R1: Remove Item Buffer R2: Change Payment Method |  | Yikang Wang | [11 empty] | 144.77 | 1 | 0 | 0 | 0 | 144.77 | 144.77 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 21.7155 |  |  |  | 21.7155 |  |  |  | 21.7155 |  | 144.77 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402252A | 144 | F21P1-0404_H_labor for 50 tools_MICU | 3678 | C |  | HK Electrical PM Luis Retiz's material request | 45349 | 45353 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 144 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 144 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Material | USC21C003 | USCSB2402258A | 144 | F21P1 UPW | 3684 | C |  | Foxboro A1U Enclosure Sample | 45349 | 45352 | [6 empty] | Black Label Services Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 144 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 144 | [10 empty] | 144 |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C009 | USCSB2403250A | 143.58 | F21P1 Module Tool Interconnection ETC1-3 | 3943 | C |  | CUSH TUBE STRUT CLMP CUSH TUBE STRUT CLMP | 45377 | 45378 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 143.58 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 143.58 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407152A | 142.89 | TSMC Fab 21 P1B Tool Hook Up | 4561 | C |  | Gloves for HK PCW trade CYH for 200 tools | 45499 | 45499 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 124.7 | 0.8727 | 18.19 | 0 | 18.19 | 0 | 124.7 | [72 empty] | - |  |  | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2401049A | 142 | F21P1-0404_H_labor for 50 tools_MICU | 3239 | C |  | office supplies for tool hookup department | 45300 | 45302 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 129.52 | 0.91211 | 12.48 | 0 | 12.48 | 0 | 129.52 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24B002 | USC2410006A | 140.27 | Tool Interconnection Project (Main Tool & Other Vendors) | 1266 | P |  | SELTERM 25pcs 2 AWG 5/16" Stud Marine Grade Tinned Copper Battery Cable Lugs, 2 Gauge Ring Terminals, UL Wire Lugs Electrical Battery Cable Ends, Tinned Copper Lugs Battery Terminal Connectors | 45569 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 140.27 | 0 | 140.27 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403140A | 140 | F21P1 Chemical & WCCS package | 3841 | C |  | CDS plastic clamp tube OD 1 | 45365 | 45367 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 140 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 140 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC24B002 | USC2401023A | 140 | Tool Interconnection Project (Main Tool & Other Vendors) | 646 | P |  | Perform interconnection on KECOL3.12/11/2024 | 45303 | 45307 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 140 | 0 | 140 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Site Expense |  |  | Others |  |  | USC23C007 | USC2404106A | 138.89 | F21P1 Module Tool Interconnection PVD1-2 | 1056 | P |  | label printer | 45408 | 45411 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 135.08 | 0.97257 | 3.81 | 0 | 3.81 | 0 | 135.08 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2403253A | 138.82 | F21P1 Module Tool Interconnection ETC1-3 | 3946 | C |  | RYOBI BAND SAW FOR DRY ETC | 45378 | 45378 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 129.61 | 0.93366 | 9.21 | 0 | 9.21 | 0 | 129.61 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2401202A | 138 | F21P1-0404_H_labor for 50 tools_MICU | 3387 | C |  | office supplies for tool hookup department | 45316 | 45316 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 125.94 | 0.91261 | 12.06 | 0 | 12.06 | 0 | 125.94 | [46 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403063A | 138 | F21P1-0404_H_labor for 50 tools_MICU | 3768 | C |  | 4 in. Crimped Wire Wheel for HK PPL trade | 45357 | 45357 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 121.6 | 0.88116 | 16.4 | 0 | 16.4 | 0 | 121.6 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2211032A | 136 | F21P1 UPW | 1565 | C |  | UPW Mark-up RO skids limit switch | 44888 | 44894 | [6 empty] | Azbil North America, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 136 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 136 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2304008A | 136 | F21P1 WWT package (Installation and 2 batch tanks) | 1849 | C |  | Gasket for WRC mini line | 45022 | 45026 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 136 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 136 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2405093A | 132.02 | Chemical & WCCS B Side Project | 4113 | C |  | CHEM_ puch list for A side_John | 45428 | 45428 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 132.02 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 132.02 |  |  | 132.02 | [7 empty] | - |  |  | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C009 | USC2402071A | 131.58 | F21P1 Module Tool Interconnection ETC1-3 | 787 | P |  | BRADY M210 HANDHELD LABEL MAKER | 45337 | 45358 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 110.64 | 0.84086 | 20.94 | 0 | 20.94 | 0 | 110.64 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204008A | 130.56 | F21P1 UPW | 155 | P0 |  | X-Change Pro | 44673 | 44764 | [6 empty] | Digital River, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 130.56 | 1 | 0 | 0 | 0 | 0 | 130.56 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402076A | 130 | F21P1 Chemical & WCCS package | 3518 | C |  | CDS M6 x 1 x 16 (5/8) Screws | 45330 | 45331 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 130 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 130 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2403204A | 129.36 | F21P1 WWT package (Installation and 2 batch tanks) | 3900 | C |  | WWT WRC laboratory furniture_3 | 45371 | 45385 | [6 empty] | Mega Depot, LLC | PR Approved | PO Approved | [14 empty] | 117.6 | 0.90909 | 11.76 | 0 | 11.76 | 10.584 | 117.6 | [51 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 19.404 |  |  |  | 19.404 |  |  |  | 19.404 |  | 0 |  | - | 0 | 0 | 0 | 10.584
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402032A | 129.01 | Tool Interconnection Project (Main Tool & Other Vendors) | 756 | P |  | 784R30 Plastic Welding Rod Manufacturer: USA INDUSTRIALS Part Number: BULK-WR-PVDF-1 | 45328 | 45328 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 129.01 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 129.01 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2311056A | 127.43 | F21P1 UPW | 2911 | C |  | UPW-test kits | 45241 | 45245 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 127.43 | 0 | 127.43 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311063A | 126.61 | Tool Interconnection Project (Main Tool & Module) | 532 | P | -01 | Strut Channel Nut With Spring, 13/16" High Channel, Steel, 3/8"-16 Thread Size, 1" Long, packs of 1 | 45251 | 2023/11/23 2023/12/2 | 11.21 | 137.82 |  |  |  |  | McMaster-Carr Supply Company | PR Approved | PO Approved | PO R1:Supplier Credit Shipping Charge |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 126.61 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 126.61 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408126A | 125.38 | TSMC Fab 21 P1B Tool Hook Up | 4737 | C |  | Waterproof tarp for HK | 45532 | 45533 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 97.98 | 0.78146 | 27.4 | 0 | 27.4 | 0 | [72 empty] | 97.98 | -
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2403098A | 125.33 | Tool Interconnection Project (Main Tool & Other Vendors) | 914 | P |  | Anti Static Clear PVC Backpack Cleanroom Engineer Tool Bag for Computer Tools Working Daypack | 45373 | 45373 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 113.94 | 0.90912 | 11.39 | 0 | 11.39 | 0 | 113.94 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Electrical | Material | USC21C005 | USCSB2404009A | 125 | F21P1 Chemical & WCCS package | 4005 | C |  | Request for Quote_Please Purchase a Breaker_CED_20240325 | 45384 | 45385 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 125 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 125 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2403053A | 124.77 | Tool Interconnection Project (Main Tool & Other Vendors) | 877 | P |  | C Spanner Tool Adjustable Hook Wrench Nut Wrench-Square head, 95-165mm | 45363 | 45363 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 124.77 | 1 | 0 | 0 | 0 | 0 | 124.77 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401049A | 124.25 | Tool Interconnection Project (Main Tool & Other Vendors) | 671 | P |  | Cable pull KETRTE 12/6/2023 | 45311 | 45313 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 124.25 | 0 | 124.25 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409044A | 123.78 | Tool Interconnection Project (Main Tool & Other Vendors) | 1247 | P |  | 5LJ49: TONGUE & GROOVE PLIER: FLAT, GROOVE JOINT, 5 1/2 IN MAX JAW OPENING | 45555 | 45558 | [6 empty] | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved | [14 empty] | 0 | 0 | 123.78 | 0 | 123.78 | 0 | [73 empty] | -
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2312182A | 123.29 | F21P1-0404_H_labor for 50 tools_MICU | 3169 | C |  | office supplies for tool hookup department | 12/27/2023 8/8/2024 | 12/28/2023 8/28/2024 | 13.33 | 109.96 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: change price |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 123.29 | 1 | 0 | 0 | 0 | 0 | 123.29 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2307124A | 123.25 | F21_AZQR_Hookup_ Interconnection | 2287 | C |  | KXMS01: Locking Receptacle Mfr. Model L18-30R | 45134 | 45142 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 123.25 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 123.25 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2403018A | 120.34 | F21P1 WWT package (Installation and 2 batch tanks) | 3727 | C |  | WWT Threaded Plug_20240229 (A Side) | 45353 | 45355 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 120.34 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 120.34 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Speed Gate | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C001 | USC2107008A | 119.93 | tsmc AZ Temporary Office Physical Security | 9 | P0 |  | Metal gate壓邊條及配件 | 44384 | 44399 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | Debit card paid (員工代墊款) | T/T 0 day (貨款員工代墊) | Cherry Chang |  |  | Chao Chia | Cherry Chang |  |  | Henry |  |  |  |  | 119.93 | 1 | 0 | 0 | 0 | 0 | 119.93 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204007A | 119.45 | F21P1 UPW | 154 | P0 |  | Netgear Switch | 44673 | 44676 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 119.45 | 1 | 0 | 0 | 0 | 0 | 119.45 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2401147A | 119.21 | F21P1 Module Tool Interconnection ETC1-3 | 3332 | C |  | KEPRL7 DAQ | 45310 | 45346 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 119.21 | 60336.07 | -60216.86 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2303034A | 119.2 | F21P1 WWT package (Installation and 2 batch tanks) | 1776 | C |  | TEM LAB PP 90 Elbows Fittings | 44993 | 45007 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 119.2 | 0 | 119.2 | 119.2 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 17.88 |  |  |  | 17.88 |  |  |  | 17.88 |  | 119.2 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C009 | USCSB2312045A | 119.04 | F21P1 WWT package (Installation and 2 batch tanks) | 3038 | C |  | WWT _7/8 washer extra | 45267 | 45267 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 119.04 | 0 | 119.04 | 119.04 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 17.856 |  |  |  | 17.856 |  |  |  | 17.856 |  | 119.04 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C036 | USCSB2405076A | 117.3 | F21P1 AMAT Interconnection | 4096 | C |  | Voltage Testing Pen | 5/11/2024 9/25/2024 | 5/15/2024 9/26/2024 | -14.52 | 131.82 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1: Match to the actual expense (See packing slip) | [13 empty] | 117.3 | 1 | 0 | 0 | 0 | 0 | 117.3 | [55 empty] | 0 | [16 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2308107A | 116.71 | F21P1 Module Tool Interconnection CVD | 2404 | C |  | Change order – conduit install for signal cable routing from L20 to L10 KCANN2 | 45157 | 45156 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 116.71 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 116.71 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2403292A | 115.48 | F21P1 AMAT Interconnection | 3984 | C |  | Hydraulic Crimping & Tinned Copper Wire Lugs Kit | 45381 | 45383 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 91.98 | 0.7965 | 23.5 | 0 | 23.5 | 0 | 91.98 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403116A | 115.28 | F21P1-0404_H_labor for 50 tools_MICU | 3818 | C |  | HK Electrical PM material request | 45363 | 45364 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 103.6 | 0.89868 | 11.68 | 0 | 11.68 | 0 | 103.6 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2401096A | 112.91 | EBO21- Tool interconnection | 3283 | C |  | EBO: ZMERIT1: ARMAFLEX 3/8"*1/2" INSULATION FOR THE CHILLER HOSES | 45304 | 45309 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 112.91 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 112.91 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2403008A | 112.45 | F21_AZQR_Hookup_ Interconnection | 3716 | C |  | QR LABS: CHAD LABS: SS CUSHION CLAMPS | 45352 | [7 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 112.45 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 112.45 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2402142A | 111.54 | F21P1 Module Tool Interconnection ETC1-3 | 3575 | C |  | ETC Brady M210 Handheld label maker | 45337 | 45350 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 101.4 | 0.90909 | 10.14 | 0 | 10.14 | 0 | 101.4 | [48 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2402213A | 111 | F21P1 Chemical & WCCS package | 3640 | C |  | CDS SMC pressure gauges | 45344 | 45344 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 111 | 0 | 111 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 111 | [9 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2407147A | 110.79 | TSMC Fab 21 P1B Tool Hook Up | 4557 | C |  | FLOW/REG 356-AR/HE-580 DUAL for Gas trade | 45498 | 45499 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 102.36 | 0.92391 | 8.43 | 0 | 8.43 | 0 | [68 empty] | 102.36 |  |  |  |  | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2408107A | 110.78 | F21P1 Module Tool Interconnection ETC1-3 | 4722 | C |  | Amazon.com Order for DRY ETC | 45528 | 45539 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 53.35 | 0.48159 | 57.43 | 0 | 57.43 | 0 | 53.35 | [72 empty] | -
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Mechanical | Site Expense | USC21C009 | USCSB2401025A | 110.05 | F21P1 WWT package (Installation and 2 batch tanks) | 3216 | C |  | WWT office supplies for PSS support doc. | 45296 | 45300 | [6 empty] | Walmart Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 107.85 | 0.98001 | 2.2 | 0 | 2.2 | 0.9304 | 107.85 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 5.5025 |  |  |  | 11.005 |  |  |  | 16.5075 |  | 0 |  | - | 0 | 0 | 0 | 0.9304
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409056A | 109.96 | Tool Interconnection Project (Main Tool & Other Vendors) | 1257 | P |  | 30 ft. Looped End Steel Cable with Resettable Outdoor Combination Lock (Bundle Pack) | 45562 | 45562 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 109.96 | 0 | 109.96 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405107A | 109.9 | F21P1-0404_H_labor for 50 tools_MICU | 4138 | C |  | Lock for tool box | 45430 | 45434 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 74.9 | 0.68153 | 35 | 0 | 35 | 0 | 74.9 | [72 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2404069A | 109.5 | F21P1-0404_H_labor for 50 tools_MICU | 4061 | C |  | Plug Lockout Box for all sysem, tool hookup team | 45389 | 45390 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 96.8 | 0.88402 | 12.7 | 0 | 12.7 | 0 | 96.8 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403172A | 108.78 | F21P1 Chemical & WCCS package | 3869 | C |  | CDS electrical tape and tool | 45367 | 45370 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 107.48 | 0.98805 | 1.3 | 0 | 1.3 | 0 | 107.48 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2404067A | 108.2 | F21P1-0404_H_labor for 50 tools_MICU | 4059 | C |  | For scissorlift safety, so people do not steal our lifts again. The other is for Pressure Testing. | 45388 | 45390 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 108.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 108.2 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2310203A | 108 | F21P1 Module Tool Interconnection CMP1 | 2854 | C |  | CMP: MSK1-4: INTERCONNECTION MATERIAL 3/8" EP PIPE | 45230 | 45233 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 108 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 108 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Software | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2111024A | 107.36 | F21P1 UPW | 38 | P0 |  | PDF-XChange Pro | 44512 | 44524 | [6 empty] | Digital River, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang |  |  | Matt |  |  |  |  | 107.36 | 1 | 0 | 0 | 0 | 0 | 107.36 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403289A | 106.7 | F21P1-0404_H_labor for 50 tools_MICU | 3981 | C |  | X STRAP Standard Power PIU Work | 45381 | 45383 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 92.15 | 0.86364 | 14.55 | 0 | 14.55 | 0 | 92.15 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403111A | 106.69 | F21P1-0404_H_labor for 50 tools_MICU | 3813 | C |  | Industrial tapes for HK Power trade | 45363 | 45363 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 106.69 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 106.69 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C006 | USCSB2405154A | 105.86 | WWT B side Project | 4183 | C |  | WWT WRC laboratory furniture_Sensor | 45441 | 45441 | [6 empty] | Mega Depot, LLC | PR Approved | PO Approved | [14 empty] | 105.28 | 0.99452 | 0.58 | 0 | 0.58 | 0 | 105.28 | [70 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204018A | 104.51 | F21P1 UPW | 165 | P0 |  | set of 4 hand soap | 44679 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 104.51 | 1 | 0 | 0 | 0 | 0 | 104.51 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24B002 | USC2410005A | 104.5 | Tool Interconnection Project (Main Tool & Other Vendors) | 1265 | P |  | Falltech 7445 Strut Anchor | 45568 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 104.5 | 0 | 104.5 | 0
Base-Build | VOC | Labor | 0 | 0 | Low Voltage | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C009 | USCSB2404084A | 104.16 | F21P1 WWT package (Installation and 2 batch tanks) | 4073 | C |  | Zoro - Clean and equipment maintenance | 45392 | 45391 | [6 empty] | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 94.69 | 0.90908 | 9.47 | 0 | 9.47 | 0 | [52 empty] | 0 | 0 | 0 |  | 94.69 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402004A | 103.65 | Tool Interconnection Project (Main Tool & Other Vendors) | 733 | P |  | C406-010 1" 90 Elbow S CLR PVC SCH40 | 45323 | 45323 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 103.65 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 103.65 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2308027A | 103.41 | EBO21- Tool interconnection | 2328 | C |  | EBO: ZASC5，Interconnection material Flange Nut, Washer, Cube nut, Hex screw, Self tapping screw | 45142 | 45156 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 103.41 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 17.19 | 86.22 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311064A | 99.75 | Tool Interconnection Project (Main Tool & Module) | 533 | P | -01 | BLINE 9ZN-1204NB CABLE TRAY CLAMP | 45252 | 2023/11/23 2023/12/5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1: Remark Information Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 99.75 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 99.75 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2401109A | 98.98 | Tool Interconnection Project (Main Tool & Other Vendors) | 726 | P |  | Skywalker Cable Caddy, Cable Holder (Max Weight 100 lbs.)Skywalker Cable Caddy, Cable Holder (Max Weight 100 lbs.) | 45322 | 45322 | [6 empty] | Amazon | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 89.08 | 0.89998 | 9.9 | 0 | 9.9 | 0 | 89.08 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409061A | 98.98 | TSMC Fab 21 P1B Tool Hook Up | 4856 | C |  | HK PCW hand tool-consumable request_ Battery Pack for 100 tools | 45553 | 45553 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 89.98 | 0.90907 | 9 | 0 | 9 | 0 | 89.98 | [72 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403001A | 98.9 | F21P1-0404_H_labor for 50 tools_MICU | 3709 | C |  | Cable Gland Lokman 20 Pack PG9 Plastic Waterproof Adjustable 4-8mm Cable Glands Joints with Gasket, Black (PG9) for HK Power | 45352 | 45352 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 77 | 0.77856 | 21.9 | 0 | 21.9 | 0 | 77 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408065A | 98.2 | Tool Interconnection Project (Main Tool & Other Vendors) | 1207 | P |  | IS4CT9G 1 SS 304 150# THRD 90 ELL | 45534 | 45535 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 98.2 | 1 | 0 | 98.2 | -98.2 | 0 | [73 empty] | 98.2
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407036A | 97.5 | F21P1-0404_H_labor for 50 tools_MICU | 4435 | C |  | B Side ELECTRICAL RUBBER GLOVE INFLATION TOOL for HK Power for 100 tools | 45482 | 45502 | [6 empty] | JM Test Systems, LLC | PR Approved | PO Approved | [14 empty] | 82.5 | 0.84615 | 15 | 0 | 15 | 0 | 82.5 | [72 empty] | - |  |  | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2404120A | 97.18 | F21P1-0404_H_labor for 50 tools_MICU | 4105 | C |  | Tool for HK PPL trade Tunyi. For 50 tools | 45398 | 45407 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 88.34 | 0.90903 | 8.84 | 0 | 8.84 | 0 | 88.34 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2312081A | 97.15 | Tool Hookup Material (UPW&Chemical) | 3073 | C |  | F21 EBO PVC MET UNION ADPT | 45273 | 45275 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 97.15 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 97.15 | [12 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2305115A | 94.4 | EBO21- Tool interconnection | 2031 | C |  | EBO - SWAGELOK INTERCONNECT MATERIALS FOR ZASC5-1 | 45077 | 45079 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 94.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 94.4 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2401064A | 94.38 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3253 | C |  | Consolidated Electrical Distributors material for electrical work in OSC/Prefab to support TSMC & Taiwan Vendors | 45302 | 45303 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 94.38 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 94.38 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2406153A | 94.13 | F21P1 AMAT Interconnection | 4400 | C |  | These will be for P1B signoff documents and for staff to carry extra copies with them. | 45472 | 45475 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 49.47 | 0.52555 | 44.66 | 0 | 44.66 | 0 | 49.47 | [72 empty] | - |  |  | 0
Hookup | Hookup | Site Expense |  |  | Others |  |  | USC23C055 | USCSB2403305A | 94.02 | F21P1-0404_H_labor for 50 tools_MICU | 3997 | C | -01 | Electrical insulating gloves for HK Power trade | 45381 | 2024/4/1 2024/4/2 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved | R1: Change payment method to US2 Credit Card |  | Ta Wei Wang | [11 empty] | 94.02 | 1 | 0 | 0 | 0 | 0 | 94.02 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409101A | 93.97 | TSMC Fab 21 P1B Tool Hook Up | 4909 | C |  | HK Power trade Hardware_Request 9/18 for 200 tools | 45561 | 45562 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 93.97 | 0 | 93.97 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2408099A | 93.47 | F21P1 Module Tool Interconnection ETC1-3 | 4715 | C |  | AMAZON | 45526 | 45539 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 84.98 | 0.90917 | 8.49 | 0 | 8.49 | 0 | 84.98 | [72 empty] | -
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2112032A | 93.15 | F21P1 UPW | 95 | P0 |  | Dell G15 Laptop | 44554 | 44558 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang |  |  | Matt |  |  |  |  | 93.15 | 1 | 0 | 0 | 0 | 0 | 93.15 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402148A | 89.62 | F21P1 Chemical & WCCS package | 3581 | C |  | CDS Sealing Compound Powder, Qty 2 | 45337 | 45337 | [6 empty] | Walmart Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 0 | 0 | 89.62 | 0 | 89.62 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204016A | 86.87 | F21P1 UPW | 163 | P0 |  | Multi purpose paper 11 x 17 | 44679 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 86.87 | 1 | 0 | 0 | 0 | 0 | 86.87 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2402071A | 86.56 | EBO21- Tool interconnection | 3513 | C |  | EBO: ZMERIT & ZASC5-1: FEMALE CONNECTORS | 45330 | 45330 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 86.56 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  | 86.56 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2402113A | 86.56 | EBO21- Tool interconnection | 3551 | C |  | EBO: ZMERIT: FEMALE CONNECTORS | 45335 | 45335 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 86.56 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 86.56 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C006 | USCSB2312122A | 86.06 | F21P1 Module Tool Interconnection EPI | 2971 | C |  | EPI: KCEPS1: LIQ-TITE, BUSHINGS, & CONNECTORS | 45276 | [7 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1: canceled order | [13 empty] | 86.06 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 86.06 | [12 empty] | - |  |  | 0
Base-Build | WWT |  |  |  | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C006 | USCSB2408069A | 85.74 | WWT B side Project | 4685 | C |  | WWT Tent 9 WMS Barcode Paper Label | 45519 | 45519 | [6 empty] | Barcodes LLC | PR Approved | PO Approved | [14 empty] | 85.74 | 1 | 0 | 91.22 | -91.22 | 0 | [73 empty] | 85.74
Base-Build | Chemical |  | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC24C005 | USCSB2406022A | 85.43 | Chemical & WCCS B Side Project | 4248 | C |  | 1-1/2 SS 304L 法蘭洗孔 | 45447 | 45448 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 85.43 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 85.43 | [6 empty] | - |  |  | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403003A | 85.3 | F21P1-0404_H_labor for 50 tools_MICU | 3711 | C |  | HK Electrical PM Conn and Bush INS | 45352 | 45352 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 85.29 | 0.99988 | 0.01 | 0 | 0.01 | 0 | [52 empty] | 0 | 0 | 0 |  | 85.29 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2308098A | 82.4 | F21P1 Chemical & WCCS package | 2395 | C |  | Unions to Correct MIC Taiwan M4 cabinets | 45155 | 45157 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 82.4 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 82.4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2209020A | 80 | F21P1 UPW | 245 | P0 |  | microwave 1.1 chrome and black hamilton beach | 44832 | 44848 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 80 | 1 | 0 | 0 | 0 | 0 | 80 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | Main Contract Scope | WWT | WWT | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C011 | USCSB2404200B | 78.5 | F21 TMAH System | 4018 | C |  | WWT-ammonia 1000 ppm standards solution for stripper | 45408 | 45433 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved | [14 empty] | 58.5 | 0.74522 | 20 | 0 | 20 | 14.625 | [62 empty] | 58.5 | [8 empty] | 14.625 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2402094A | 78.25 | Tool Interconnection Project (Main Tool & Other Vendors) | 808 | P |  | 4NKN6 SHRINK TUBING 100 FT. | 45345 | 45346 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 78.25 | 0 | 78.25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Speed Gate | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C002 | USC2107005A | 78.17 | TSMC AZ Temp Office Speed Gate | 6 | P0 |  | Adopter and mount for speed gate | 44384 | 44399 | [6 empty] | Staples Inc. | PR Approved | PO Approved | Debit card paid (員工代墊款) | T/T 0 day (貨款員工代墊) | Cherry Chang |  |  | Chao Chia | Cherry Chang |  |  | Henry |  |  |  |  | 78.17 | 1 | 0 | 0 | 0 | 0 | 78.17 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405138A | 77.9 | Tool Interconnection Project (Main Tool & Other Vendors) | 1113 | P |  | SUIN 1'' 3 Ring Binder -1 inch View Binders with Round Ring Binders, Large 200 Sheet Capacity, Fit 8.5" x 11" US Letter Size Paper, 12 Pack White (1-inch) | 45435 | 45443 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 77.9 | 0 | 77.9 | 0 | [73 empty] | - |  |  | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Mechanical | Material | USC21C011 | USCSB2306119A | 76.67 | F21 TMAH System | 2152 | C |  | WRC Ammonia nitrogen CO -2 | 45104 | 45104 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 76.67 | 0 | 76.67 | 76.67 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 76.67 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2308104A | 76.59 | F21P1 Module Tool Interconnection CVD | 2401 | C |  | Change order – conduit install for signal cable routing from L20 to L10 for KCANN1 and KCANN2 | 45156 | 45156 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 76.59 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 76.59 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408025A | 75.81 | TSMC Fab 21 P1B Tool Hook Up | 4620 | C |  | Receptacle tester and power extension for HK Power 3-in-1 QA/QCfor 300 tools | 45511 | 45511 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 65.68 | 0.86638 | 10.13 | 0 | 10.13 |  | 65.68 | [72 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C006 | USCSB2403046A | 75.18 | F21P1 Slurry package | 3753 | C |  | Chem Gasket_20240305 | 45357 | 45362 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 75.18 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 75.18 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203027A | 74.91 | F21P1 UPW | 147 | P0 |  | Sarood Laptop stand in adjustable size | 44643 | 44670 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 74.91 | 1 | 0 | 0 | 0 | 0 | 74.91 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2309093A | 73.59 | F21P1 UPW | 2566 | C |  | UPW-PVDF valve handle | 45185 | 45192 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 73.59 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 24.53 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 49.06 | [10 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2303095A | 73.4 | F21P1 UPW | 1832 | C |  | DG tower pressure gauge | 45013 | 45016 | [6 empty] | Hwa Chi Technology Co., Ltd | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 73.4 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 73.4 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2308134A | 72.25 | F21P1 Chemical & WCCS package | 2429 | C |  | Unions For Chemical welding. | 45161 | 45161 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 72.25 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 72.25 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2312026A | 68.97 | F21P1 Module Tool Interconnection CVD | 3019 | C |  | Hex Head Bolt, Washer, Strut Channel Nut | 45265 | 45268 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 68.97 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 68.97 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | Main Contract Scope | UPW | UPW | Mechanical | Material | USC21C003 | USCSB2401072A | 66.5 | F21P1 UPW | 3261 | C | -01 | UPW-Harrington-Sight glass Orings | 45303 | 2024/1/12 2024/1/16 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: trade term changes from DDP to FOB |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 66.5 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 66.5 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Equipment | Main Contract Scope | WWT | WWT | Electrical | Instrument | USC21C011 | USCSB2404063A | 65 | F21 TMAH System | 4055 | C | -01 | Cast Iron Conduit box for TATUNG MOTOR WH0202FEJ SN14063611 in STRIPPER PAD | 45388 | 2024/4/29 2024/4/30 | [6 empty] | Tatung Company | PR Approved | PO Approved | R1: Change payment method to prepayment |  | 0 | [11 empty] | 65 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 65 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2401251A | 64.96 | F21P1-0404_H_labor for 50 tools_MICU | 3432 | C |  | Aluminum foil duct for exhaust | 45322 | 45322 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 64.96 | 1 | 0 | 0 | 0 | 0 | 64.96 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2309166A | 64.69 | EBO21- Tool interconnection | 2635 | C |  | EBO: CDA Cabinet – NO TOOL ID: Interconnection material - U-bolt | 45196 | 45202 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 64.69 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 64.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406135A | 63.38 | F21P1-0404_H_labor for 50 tools_MICU | 4374 | C |  | Hex Panel Nut and Shims/ for 5 tools/ tool hookup team | 2024/6/26 2024/6/28 | 45472 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | PR R1:change shipping cost to usd $10. | [13 empty] | 63.36 | 0.99968 | 0.02 | 0 | 0.02 | 0 | [68 empty] | 63.36 |  |  |  |  | - |  |  | 0
[5 empty] | Others |  |  | USC24C008 | USCSB2410006A | 60.57 | UPW B Side Project | 4953 | C |  | Limit Switch for SB-P Valve_UPW | 45566 | 45566 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 0 | 0 | 60.57 | 0 | 60.57 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C009 | USC2402002A | 60.5 | F21P1 Module Tool Interconnection ETC1-3 | 732 | P |  | Stock Code: SPVCGY.1250 WHSE:CE0001. DESC.:0125 Thick Gray PVC Sheet (Per Piece) 48"x48" (Covers for A/C Boxes) | 45323 | 45324 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 55 | 0.90909 | 5.5 | 0 | 5.5 | 0 | [48 empty] | 0 | 0 |  | 55 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2310127A | 57.4 | F21_AZQR_Hookup_ Interconnection | 2786 | C |  | QR: NO TOOL ID: SPECIAL ADAPTERS - PVDF Reducer 2” to 1-1/4” | 45219 | 45227 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 57.4 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 57.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2204017A | 56.46 | F21P1 UPW | 164 | P0 |  | hand soap package of 4 | 44679 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 56.46 | 1 | 0 | 0 | 0 | 0 | 56.46 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC24B002 | USC2403074A | 56.07 | Tool Interconnection Project (Main Tool & Other Vendors) | 895 | P |  | Sellstrom Advantage Series Face Shield - Clear Window with Aluminum Binding - Comfortable Ratcheting Headgear, ANSI Z87.1+ (S30110) | 45367 | 45369 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 50.47 | 0.90012 | 5.6 | 0 | 5.6 | 0 | 50.47 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | Main Contract Scope | WWT | WWT | Electrical | Material | USC21C011 | USCSB2402101A | 54.52 | F21 TMAH System | 3541 | C |  | TMAH MS/HS receptacle | 45332 | 45335 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 54.52 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 54.52 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C007 | USCSB2310112A | 54.18 | F21P1 Module Tool Interconnection PVD1-2 | 2773 | C |  | Tamper Evident Tape Red | 45217 | 45220 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 54.18 | 0 | 54.18 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2205001A | 52.93 | F21P1 UPW | 166 | P0 |  | paper for copier | 44692 | 44764 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 52.93 | 1 | 0 | 0 | 0 | 0 | 52.93 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403042A | 49.49 | F21P1-0404_H_labor for 50 tools_MICU | 3749 | C |  | Cooper Wiring Devices CS8269 Recp Single 50A 250V 2P3W H/L BK for HK Power trade | 45356 | 45357 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 44.78 | 0.90483 | 4.71 | 0 | 4.71 | 0 | 44.78 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409021A | 46.18 | TSMC Fab 21 P1B Tool Hook Up | 4837 | C |  | safety | 45540 | 45558 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 46.18 | 0 | 46.18 | 0 | [73 empty] | -
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Instrument | USC21C005 | USCSB2308181A | 45.52 | F21P1 Chemical & WCCS package | 2474 | C | -01 | Connectors for Chemical team to conduct pressure test. | 45169 | 2023/9/1 2023/9/6 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1:Responsible Engineer |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 45.52 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 45.52 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312024A | 44.67 | Tool Interconnection Project (Main Tool & Module) | 573 | P |  | Liquid Tite for EPI for the tool ID#KECPS3 | 45265 | 45267 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 44.67 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 44.67 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
[5 empty] | Others |  |  | USC24B002 | USC2409059A | 41.78 | Tool Interconnection Project (Main Tool & Other Vendors) | 1262 | P |  | M10 ISO flanges Double Wall Clamp Double Claw Clamps Vacuum Fittings Aluminium Semiconductor ISO160-ISO250 (4 Pack) | 45563 | 45562 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 41.78 | 0 | 41.78 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401086A | 40.69 | F21P1-0404_H_labor for 50 tools_MICU | 3275 | C |  | Padlocks order for HK James M | 45303 | 45306 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 36.99 | 0.90907 | 3.7 | 0 | 3.7 | 0 | 36.99 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2406083A | 40.23 | F21P1-0404_H_labor for 50 tools_MICU | 4325 | C |  | Twist drill bits for HK PPL Trade | 45457 | 45469 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 33.28 | 0.82724 | 6.95 | 0 | 6.95 | 0 | 33.28 | [72 empty] | - |  |  | 0
Base-Build | VOC | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C007 | USCSB2309007A | 40 | F21P1 VOC package （Installation ) | 2485 | C |  | VOC system signal wire termination | 45170 | 45174 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 40 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 40 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MISC Expense | The budget execution does not pertain to this project | Shared Cost | Base-Build | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC21C003 | USC2203003A | 37.99 | F21P1 UPW | 128 | P0 |  | Switch | 44629 | 44635 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 37.99 | 1 | 0 | 0 | 0 | 0 | 37.99 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2409096A | 37.39 | TSMC Fab 21 P1B Tool Hook Up | 4906 | C |  | Steel Padlock for HK MIMO | 45560 | 45565 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 37.39 | 0 | 37.39 | 0 | [73 empty] | -
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2401099A | 36.98 | F21P1 AMAT Interconnection | 3286 | C | -01 | AMAT_ME_KKDB04/KKSV02/KKSS03/KPCD16_6x14" flexible duct | 45304 | 2024/1/16 2024/1/25 | -5.8 | 42.78 |  | V | V |  | Amazon.com, Inc. | PR Approved | PO Approved | Amazon order amount to return "10% buffer" |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 36.98 | 1 | 0 | 0 | 0 | 0 | 36.98 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401056A | 36.95 | F21P1 Chemical & WCCS package | 3245 | C |  | WCCS Cutter | 45301 | 45306 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 36.95 | 1 | 0 | 0 | 0 | 0 | 36.95 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2310012A | 36.19 | F21_AZQR_Hookup_ Interconnection | 2675 | C |  | QR: CHAD/FAD LAN CABLE TRAY – INT. MATERIALS | 45202 | 45223 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36.19 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 36.19 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2311121A | 36.12 | F21_AZQR_Hookup_ Interconnection | 2972 | C |  | QR: KXFX01, KXPS01: INTERCONNECT MATERIAL - 3 CONDUCTORS, 2 AWG WIRE | 45259 | 45265 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 36.12 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 36.12 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2406087A | 33.74 | F21P1 AMAT Interconnection | 4339 | C |  | KCENA4 Heat Shrinks | 45458 | 45483 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 33.74 | 1 | 0 | 0 | 0 | 0 | 33.74 | [72 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C001 | USCSB2407100A | 32.5 | TEL Main Tool Interconnection | 4515 | C |  | Tools for all Dry ETC Tools | 2024/7/17 2024/9/23 | 2024/7/23 2024/9/23 | -5.86 | 38.36 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | PR R1: Match to the actual expense (See packing slip) | [13 empty] | 32.5 | 1 | 0 | 0 | 0 | 0 | 32.5 | [72 empty] | - |  |  | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USC2404048A | 32.04 | F21P1 AMAT Interconnection | 1001 | P |  | 8AWG ring terminal | 45392 | 45392 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 21.36 | 0.66667 | 10.68 | 0 | 10.68 | 0 | 21.36 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USC2408004A | 32 | TSMC Fab 21 P1B Tool Hook Up | 1175 | P |  | Glove testing for 1000VT Welding gloves | 45506 | [8 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 32 | 0 | 32 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404072A | 31.95 | Tool Interconnection Project (Main Tool & Other Vendors) | 1026 | P |  | 23AB02Z 2 Hole 90° (1 7/8 x 2) Angle Bracket EG | 45400 | 45399 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 31.95 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 31.95 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | Main Contract Scope | UPW | UPW | Electrical | Commissioning | USC21C003 | USCSB2311083A | 31 | F21P1 UPW | 2936 | C |  | UPW_Sulfuric Acid 96% | 45247 | 45248 | [6 empty] | Thomas Scientific Holdings LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 31 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 31 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407040A | 30.79 | F21P1-0404_H_labor for 50 tools_MICU | 4439 | C |  | P1B Self Adhesive Cable Zip Tie for HK Power fot 300 tools | 45482 | 45483 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 26.99 | 0.87658 | 3.8 | 0 | 3.8 | 0 | 26.99 | [72 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312025A | 29.78 | Tool Interconnection Project (Main Tool & Module) | 574 | P |  | EPI，Interconnection material Liquid tite 4 feet For KECPS3 | 45265 | 45267 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 29.78 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 29.78 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2403191A | 29.69 | F21P1 Chemical & WCCS package | 3888 | C | -02 | CDS Punch list SS screws | 3/19/2024 3/29/2024 | 2024/3/20 2024/4/2 | 6.92 | 22.77 |  |  |  |  | The Home Depot, Inc | PR Approved | PO Approved | R1: Change Delivery Location |  | Yikang Wang | [11 empty] | 0 | 0 | 29.69 | 0 | 29.69 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  |  | 29.69 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2309107A | 29.34 | F21P1 Module Tool Interconnection CMP1 | 2579 | C |  | CMP: MKS1-4: CLEAR PRIMER DIO3 LINES | 45188 | 45194 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 29.34 | 0 | 29.34 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  |  |  | Chemical | Others (commissioning, QAQC, Safety, Outsourcing, etc) | Site Expense | USC24C005 | USCSB2407090A | 27.5 | Chemical & WCCS B Side Project | 4506 | C |  | Chemical Scope | 45489 | 45489 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 19.99 | 0.72691 | 7.51 | 0 | 7.51 | 0 | 19.99 | [72 empty] | - |  |  | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402045A | 27.24 | F21P1 Chemical & WCCS package | 3487 | C |  | CDS 1/2 GROUNDING PIGTAIL | 45328 | 45328 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 27.24 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 27.24 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2402235A | 26.79 | F21P1 Module Tool Interconnection ETC1-3 | 3661 | C |  | DRY ETC 1,2 AND 3 Hex Washer Drill Point Screw | 45346 | 45350 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 23.93 | 0.89324 | 2.86 | 0 | 2.86 | 0 | 23.93 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C006 | USCSB2312119A | 26.4 | F21P1 Module Tool Interconnection EPI | 2970 | C |  | EPI: KCEPS1: PIPE CLAMPS | 45276 | [7 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1: canceled order | [13 empty] | 26.4 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 26.4 | [12 empty] | - |  |  | 0
Base-Build | WWT |  |  |  | WWT | Mechanical | Material | USC24C006 | USCSB2409085A | 25.63 | WWT B side Project | 4897 | C |  | WWT shortage of hardware materials on the B side sump pump at TIMA | 45556 | 45561 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 25.63 | 0 | 25.63 | 0 | [73 empty] | -
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2310196A | 25.62 | EBO21- Tool interconnection | 2847 | C |  | EBO: CDA CABINET: INTERCONNECT MATERIAL FEMALE CONNECTOR | 45230 | 45231 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 25.62 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 25.62 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2405007A | 25.2 | F21P1 Module Tool Interconnection CMP1 | 4018 | C |  | CMP: KMRPE4: CAP 3/4" SWG | 45414 | 45419 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 25.2 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 25.2 | [10 empty] | - |  |  | 0
Base-Build | Speed Gate | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C002 | USC2107006A | 20.97 | TSMC AZ Temp Office Speed Gate | 7 | P0 |  | Adaptor for speed gate and bults for mounting | 44384 | 44399 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | Debit card paid (員工代墊款) | T/T 0 day (貨款員工代墊) | Cherry Chang |  |  | Chao Chia | Cherry Chang |  |  | Henry |  |  |  |  | 20.97 | 1 | 0 | 0 | 0 | 0 | 20.97 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC24B002 | USC2404076A | 18.17 | Tool Interconnection Project (Main Tool & Other Vendors) | 1030 | P |  | HT-PVC 大小頭 (SxS) 40Ax25A | 45402 | 45406 | [6 empty] | Supertung Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 18.17 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 18.17 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2402215A | 17.82 | F21P1 Chemical & WCCS package | 3642 | C |  | CDS 5/8 Hex nut, EG | 45344 | 45344 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 17.82 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 17.82 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Speed Gate | Material | Main Contract Scope | Low Voltage | Low Voltage | Electrical | Material | USC21C001 | USC2107007A | 16.22 | tsmc AZ Temporary Office Physical Security | 8 | P0 |  | Furniture D (Metal gate壓邊條及配件) | 44384 | 44399 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Debit card paid (員工代墊款) | T/T 0 day (貨款員工代墊) | Cherry Chang |  |  | Chao Chia | Cherry Chang |  |  | Henry |  |  |  |  | 16.22 | 1 | 0 | 0 | 0 | 0 | 16.22 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2402125A | 15.98 | F21P1 AMAT Interconnection | 3562 | C |  | Hex Head Bolt for AMAT Change Order completion | 45336 | 45342 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 15.98 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 15.98 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C007 | USCSB2310111A | 11.87 | F21P1 Module Tool Interconnection PVD1-2 | 2772 | C |  | Tamperproof Tube marker | 45217 | 45220 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 11.87 | 0 | 11.87 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Material | USC21C005 | USCSB2401055A | 11.22 | F21P1 Chemical & WCCS package | 3244 | C |  | WCCS weld tube cap 2" | 45301 | 45303 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 11.22 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 11.22 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2404217A | 10.43 | F21P1 Module Tool Interconnection CMP1 | 3968 | C |  | CMP: KMOPA5: 3/8" FITTINGS | 45412 | 45412 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 10.43 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 10.43 | [12 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | Main Contract Scope | CDS | Chemical | Mechanical | Safety | USC21C005 | USCSB2401044A | 9.99 | F21P1 Chemical & WCCS package | 3234 | C |  | WCCS Thread locker | 45300 | 45300 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 8.89 | 0.88989 | 1.1 | 0 | 1.1 | 0 | 8.89 | [44 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2305093A | 0 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2014 | C | -01 | KPE601-S LIT 2 Streimers Exhaust-Revised Labor Pricing | 45066 | 2023/9/19 2023/9/22 | -21245.1 | 21245.1 |  |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | R1:PO USC23B002 Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C004 | USC2202001A | 0 | F21P1 WWT package （USA EQ-FRP tank) | 111 | P |  | Sludge Hopper | 44595 | x | -683732.16 | 683732.16 | [5 empty] | PR Approved | PO Approved | *與Henry確認，此單退回刪除，2022/4/16 PR異動完成 *此單先Hold，因廠商欲改付款條件，所以我方再在台灣找其他廠商詢價。 | 取消 | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | N |  |  |  | N |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USC2111026A | 0 | F21P1 UPW | 40 | P | -01 | Total Organic Carbon analyzers and ICR. | 2021/11/13 2021/12/16 | 2021/11/19 2021/12/20 | -379239 | 379239 |  | V | V |  | Veolia WTS Analytical Instruments, Inc. | PR Approved | PO Approved |  | 90% Received, 10% 60 days after acceptance, net 30 days | York Yeh | DDP Office | 2 year limited warranty | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2306035A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 2070 | C |  | DIF: PFA TUBING FOR DOUBLE CASING CONNECTION ONLY ITEM 1 AND 2 ARE REQIRED FOR PURCHASE. | 2023/6/10 2023/6/21 2024/8/6 | 2023/7/20 2024/8/7 | -7832.92 | 7832.92 |  |  | V |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | PR R1:The amount is lower from $21K to $7K & only the first 2 materials,not the whole order and cancelled subsequently | PR R1:The amount is lower from $21K to $7K & only the first 2 materials,not the whole order. | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USC2112010A | 0 | F21P1 Chemical & WCCS package | 78 | P | -01 | Valve housing | 44537 | 44559 | -799175.66 | 799175.66 |  |  |  |  | Pure Plastics, LLC | PR Approved | PO Approved | 5/18 異動為0(另開新單) | 20% after receipt of signed submittal. 25% after receipt of material. 50% after completion. before storage. 5% after commission. (Net 45days.) | York Yeh |  |  | Stephon Dean | York Yeh | N | 44207 | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | AMHS | Equipment |  |  | AMHS |  |  | USC23C015 | USCSB2306073A | 0 | F21P1 AMHS Wiring Work Outline | 2106 | C | -01 | TSMC F21 AMHS Panel redesign | 2023/6/16 2023/8/9 | 2023/6/22 2023/8/9 | -127860 | 127860 |  |  |  |  | Third Enterprise | PR Approved | PO Approved | This PO need to be zero out per PM's instruction./TSMC will buy it from the vendor directly. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Barcode | Equipment | 0 | Low Voltage | Low Voltage | 0 | 0 | USC21C012 | USC2111011A | 0 | F21 Barcode RFID System | 30 | P | -01 | Warning light | 2021/11/9 2022/1/11 | 2021/11/19 2022/1/13 | -6704.73 | 6704.73 | V |  |  |  | ONRION LLC | PR Approved | PO Approved | 1/13因付款條件&廠商問題異動結案。 | PR取消 | York Yeh |  |  | Hsiang Cheng Lee | York Yeh | N |  | Martin |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USC2111017A | 0 | F21P1 UPW | 31 | P |  | vortex flow meters | 2021/11/11 2023/4/3 | x | -23824 | 23824 | [5 empty] | PR Approved | PO Approved | *USC2112028A取代 *Already returned to PM side Have been unable to confirm instruments, will need to make new PR after confirmation. NO CF | PR取消 | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | MIC - Material | Equipment |  |  | Others |  |  | USC23C010 | USCSB2301028A | 0 | Holon-Mitsubishi Breaker |  | C |  | Mitsubishi Breaker | 44973 | 44974 | [23 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2306006A | 0 | F21_AZQR_Hookup_ Interconnection | 2040 | C |  | IDEAL VACUUM: QR LABS - NPT TO NW/KF FLANGE | 45079 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | 0 |  | WWT | 0 | 0 | USC24C006 | USCSB2409020A | 0 | WWT B side Project | 4789 | C |  | Payment for HuaYi's Lien | 2024/9/5 2024/9/18 | 45545 | [6 empty] | Sullins, Johnston, Rohrbach & Magers | PR Approved | PO Approved | PR R1: Go this PR to APN per Debby. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C004 | USC2110019A | 0 | F21P1 WWT package （USA EQ-FRP tank) | 22 | P | -01 | Strippers, absorbers, and ducts | 44492 | 44508 | -2486170.38 | 2486170.38 |  |  | V |  |  | PR Approved | PO Approved | 因專案代號有誤，申請異動結案。 | PR取消 | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | x | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Slurry | Material | 0 | 0 | Chemical | 0 | 0 | USC21C006 | USC2111062A | 0 | F21P1 Slurry package | 63 | P |  | Ball Valve, Diaphragm Valve | 44524 | x | -42157.38 | 42157.38 | [5 empty] | PR Approved | PO Approved | 專案申請退回 | PR取消 | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USC2111002A | 0 | F21P1 UPW | 25 | P |  | SDI analyzer | 2021/11/4 2021/12/2 | x | -29344 | 29344 | [5 empty] | PR Approved | PO Approved | 12/2 Will purchased in other PR 11/9專案回覆待確認中(CF & Supplier's sheet) | PR取消 | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C008 | USCSB2305102A | 0 | F21P1 Module Tool Interconnection LIT2-3 | 2023 | C |  | KPE602-S EUV_ASML_NXE3600D | 45069 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2305091A | 0 | F21P1 Chemical & WCCS package | 2012 | C | -01 | Tunnel to Lorry transition Pipe Routing Design Change | 45065 | 2023/6/2 2023/12/29 | -8280 | 8280 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Equipment | 0 | 0 | WWT | 0 | 0 | USC21C011 | USC2110018A | 0 | F21 TMAH System | 21 | P | -03 | Supply Tank | 2021/10/23 2021/11/03 2021/12/29 2022/5/17 | 2021/10/28 2021/11/05 2022/01/05 2022/05/27 | -266570 | 266570 | V | V |  |  | Belco Manufacturing Co., Inc. | PR Approved | PO Approved | R1:異動簽核中因為取消運費 R2:FRP coating upgrade due to engineering design calculation R3:5/27 異動為0,因交期無法滿足cancel | Based on T&C 001 Prepayments 25 % T/T 45天 all submittals approved 002 before shipment 70 % T/T 45天 receipt of materials 20%, ready to ship status 50% 003 Final payment 5 % T/T 45天 commissioning -- with 60 days cap from shipping day | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | 44508 | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C004 | USCSB2306021A | 0 | F21P1 WWT package （USA EQ-FRP tank) | 2055 | C | -02 | WWT - Lab glassware | 2023/6/6 2023/12/5 | 2023/7/28 2023/7/29 2023/12/5 | -2777.15 | 2777.15 | V |  |  |  | Laboratory Sales and Service | PR Approved | PO Approved | R1: Correction (ITEM 019 QTY to 0) |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C009 | USC2110024A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 23 | P | -02 | Strippers, absorbers, and ducts | 2021/10/27 2021/11/04 2022/5/17 | 2021/11/2 2021/11/05 2022/05/27 | -2365209 | 2365209 |  |  |  |  | Belco Manufacturing Co., Inc. | PR Approved | PO Approved | 取代專案代號錯誤的USC2110019A。 異動簽核中因為取消運費 5/27異動為0,因交期無法滿足,cancel | Based on T&C 001 Prepayments 25 % T/T 45天 all submittals approved 002 before shipment 70 % T/T 45天 receipt of materials 20%, ready to ship status 50% 003 Final payment 5 % T/T 45天 commissioning -- with 60 days cap from shipping day | York Yeh |  |  | Rui Ma | York Yeh | N | 44508 | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | 0 | Shared Cost | Base-Build | 0 | 0 | USC21C003 | USC2204002A | 0 | F21P1 UPW | 149 | P |  | 2019 Polaris Gas, Green 4 seater | 44656 | x | -17318.84 | 17318.84 | [5 empty] | PR Approved | PO Approved | PO已退回，因廠商通知此車已被買走 | PO取消 | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USC2111001A | 0 | F21P1 UPW | 24 | P |  | Pressure Switch、 sensor、transmitter | 2021/11/3 2021/12/2 | x | -92188.79 | 92188.79 | [5 empty] | PR Approved | PO Approved | 12/2 Will purchased in other PR (USC2111018) 11/9專案回覆待確認中(CF&Supplier's sheet) | PR取消 | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Speed Gate | Equipment | 0 | 0 | Low Voltage | 0 | 0 | USC21C008 | USC2109006A | 0 | F21P1 CCTV & Security | 14 | P | -01 | Speed Gate | 44443 | 44461 | -30500 | 30500 |  |  |  |  | Gunnebo Entrance Control, Inc. | PR Approved | PO Approved | 11/18 因廠商無UR 認證,故cancel此單,並另找廠商 | PR取消 | Cherry Chang |  |  | Chih-Chien Hung | Cherry Chang | N |  | Martin |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408129A | 0 | TSMC Fab 21 P1B Tool Hook Up | 4740 | C |  | 10 Scissor Lifts rentals for HK for 8 months | 2024/8/29 2024/9/13 | [8 empty] | PR Approved | PO Approved | PR R1: Previous PO can cover till a later time | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408130A | 0 | TSMC Fab 21 P1B Tool Hook Up | 4741 | C |  | 6 Scissor Lifts rentals for HK for 8 months | 2024/8/29 2024/9/13 | [8 empty] | PR Approved | PO Approved | PR R1: Previous PO can cover till a later time | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2407162A | 0 | F21P1 Module Tool Interconnection CVD | 4585 | C |  | For use on the CVD/LAM tools - Heat shrink tubing needed for use on cables that MIC provides for the tools. | 2024/7/27 2024/8/9 | [8 empty] | PR Approved | PO Approved | PR R1:Duplicate PR, use USCSB2408021 instead of this one | [13 empty] | 0 | 1 | 0 | 0 | 0 | [74 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408131A | 0 | TSMC Fab 21 P1B Tool Hook Up | 4742 | C |  | Truck STKBD rentals for HK for 8 months | 2024/8/29 2024/9/13 | [8 empty] | PR Approved | PO Approved | PR R1: Previous PO can cover till a later time | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USC2108008A | 0 | F21P1 UPW | 11 | P | -02 | tank,FRP | 44427 | 2021/8/27 2021/9/29 | -2617784 | 2617784 | V |  | V |  | B&D Plastics, LLC | PR Approved | PO Approved | 10/14專案通知因原vendor無法配合T&C,故取消此訂單,將另找新供應商 Rev01US$2,595,884 (異動追加USD$22,000) | PR取消 | Cherry Chang | - | - | Chia-Yi Chang | Cherry Chang | N |  | Matt |  |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | 0 |  | WWT | 0 | 0 | USC24C006 | USCSB2407157A | 0 | WWT B side Project | 4582 | C |  | T&M to have GJX involve in A+B side punch fixed(2024/07/01~2024/09/30) | 2024/7/27 2024/8/6 | 45505 | [7 empty] | PR Approved | PO Approved | PR R1:As per Jim& Serena to cancel this PR USCSB2407157 for Gejinsin and create a new PR : USCSB2408020 for Daxin(達鑫). | [13 empty] | 0 | 1 | 0 | 0 | 0 | [74 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC24C015 | USCSB2408135A | 0 | TSMC Fab 21 P1B Tool Hook Up | 4768 | C |  | 20' Office for HK for 8 months | 2024/8/29 2024/9/13 | [8 empty] | PR Approved | PO Approved | PR R1: Previous PO can cover till a later time | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USC2108007A | 0 | F21P1 UPW | 10 | P | -02 | tank,FRP | 44426 | 2021/8/27 2021/9/29 | -4096024 | 4096024 | V | V | V |  | Augusta Fiberglass Coating,Inc. | PR Approved | PO Approved | 10/12專案通知因原vendor無法配合T&C,故取消此訂單,將另找新供應商 Revo1 USD3,551,511(追加USD544,513) | PR取消 | Cherry Chang | - | - | Chia-Yi Chang | Cherry Chang | N |  | Matt |  |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Material | 0 | 0 | Chemical | 0 | 0 | USC21C006 | USC2111067A | 0 | F21P1 Slurry package | 67 | P |  | pressure regulating valve | 44530 | x | -43646 | 43646 | [5 empty] | PR Approved | PO Approved | 專案申請退回 | PR取消 | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Equipment | 0 | 0 | Chemical | 0 | 0 | USC21C006 | USC2112003A | 0 | F21P1 Slurry package | 71 | P | -02 | Power Panels | 2021/12/2 2021/12/29 2022/4/24 | 2021/12/13 2022/01/21 2022/05/04 | -24944 | 24944 | V |  |  |  | Kelso-Burnett Co. | PR Approved | PO Approved | PO:USCSB2204006A取代 Adding cost for additonal 12 months of warranty, please provide final quotation. | 90% by received, Net 30days; 10% by acceptance, Net 30days(after acceptance in 60days). | York Yeh |  |  | Stephon Dean | York Yeh | N |  | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C036 | USCSB2306065A | 0 | F21P1 AMAT Interconnection | 2098 | C | -01 | AMAT WIRE FOR POWER TRANSFORMER CONNECTION | 2023/6/16 2023/8/10 | 2023/7/10 2023/12/5 | -42180 | 42180 |  |  |  | V | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PO R1: Order is cancelled due to duplicate with USCSB2308053A |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C006 | USCSB2306034A | 0 | F21P1 Module Tool Interconnection EPI | 2069 | C |  | CEU/RK4.5T-10/S90 | 2023/6/9 2023/10/31 | x | [7 empty] | PR Approved | PO Approved | PR R1:Unresponsive supplier. Replaced with Motion Intelligence Automation USCSB2309083A per purchaser. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309161A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2631 | C |  | Hardware for Tun Yi Pumping Line | 2023/9/26 2023/10/10 | x | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved | Cancel due to wrong currency; Replace with USCSB2310051 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2305090A | 0 | F21P1 Chemical & WCCS package | 2011 | C | -01 | F21P1-U-CDS-LB2-MIC-HARDER-R6 | 45065 | 2023/6/2 2023/12/29 | -5520 | 5520 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2312206A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3192 | C |  | Phone Locker 16 door (4h*4w) 4 dial combination lock for Hook up | 2023/12/31 2024/1/5 | [8 empty] | PR Approved | PO Approved | PR R1:Australian vendor |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | 0 | CDS | Chemical | 0 | 0 | USC21C006 | USCSB2312146A | 0 | F21P1 Slurry package | 3135 | C |  | CDS H20 Caustic electrical work T&M | 2023/12/20 2024/3/27 | [8 empty] | PR Approved | PO Approved | PR R1:As per PM:Johnny Wan to cancel the PR. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312151A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3140 | C | -01 | Hex bolt and nut for Pumping Line trade | 2023/12/21 2024/3/30 | 2023/12/27 2024/4/5 | -281.49 | 281.49 |  |  |  |  | Carson Sales Co Inc | PR Approved | PO Approved | R1: zero out (but this is a mistake that need to be fixed) |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C025 | USCSB2301042A | 0 | AMHS TSMC Instrustructure and Branch Circuits | 1659 | C | -01 | Tubing hook up for AMHS GEX and PV | 2023/1/10 2024/6/15 | 2023/1/25 2024/6/18 | -70000 | 70000 |  |  | V |  | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Cancellation of scope as requested by PM | 100% by progress-Net 30 days-After acceptance | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C025 | USCSB2301043A | 0 | AMHS TSMC Instrustructure and Branch Circuits | 1660 | C |  | Reducing Assembly | 2023/1/20 2024/6/13 | 2023/2/2 2023/7/4 | -55756 | 55756 |  |  |  |  | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | R1: As per Martin to cancel the PSS PR. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | TMAH | Material | 0 | 0 | WWT | 0 | 0 | USC21C011 | USCSB2312186A | 0 | F21 TMAH System | 3173 | C |  | TMAH Addition and WRC Pads | 2023/12/28 2024/1/5 | [7 empty] | Degan Construction LLC | PR Approved | PO Approved | PR R1:Scope Change |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312189A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3176 | C |  | Grainger invoice report, shared material, tool hook up team | 45288 | [8 empty] | PR Approved | PO Approved | PR R1:zero out per Yi-Kang request. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2301058A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1674 | C |  | Lab spectraphotometer | 2023/1/28 2023/10/20 | x | [7 empty] | PR Approved | PO Approved | PR R1Replaced with USCSB2306019 |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C025 | USCSB2301061A | 0 | AMHS TSMC Instrustructure and Branch Circuits | 1677 | C |  | AHMS DP 600 amp ABB | 2023/1/28 2023/2/3 | x | -1150585 | 1150585 |  |  |  |  | Main Electric Supply Co, LLC | PR Approved | PO Approved | PM Instruction Supplier cannot meet schedule |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2401019A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3210 | C |  | HK Maohsun Equipment Rental for 3 months | 2024/1/5 2024/8/7 | [8 empty] | PR Approved | PO Approved | PR R1:Zeroing out this PR per request from Ning and Yikang. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2301022A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1644 | C |  | CO for WWT CDA cooper tube and fittings | 2023/1/11 2023/12/2 | [8 empty] | PR Approved | PO Approved | PR R1:Purchaser's request: Wrong packaging, please void this PR |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Equipment | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2401032A | 0 | F21P1 Chemical & WCCS package | 3223 | C |  | CDS Lorry A 18 Tanks | 2024/1/6 2024/1/23 | [7 empty] | DFK Tech, LLC | PR Approved | PO Approved | PR R1:Renew quotation and change budget code, so cancel the PR. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2302003A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1684 | C |  | Camera and access control for Surprise warehouse | 2023/2/2 2023/2/8 | x | -29200 | 29200 | [5 empty] | PR Approved | PO Approved | Incorrect project code, it should be USC23C001 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403082A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 901 | P |  | KDCRS4-Field Supervisor Ubaldo Ferreyra Jr | 2024/3/19 2024/8/15 | 2024/3/21 2024/8/16 | -2576 | 2576 |  |  | V |  | CGS Global Support, LLC | PR Approved | PO Approved | R1 ; Closing of order to release excess budget. |  | Tiong Sheng Poh | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | 0 | 0 | UPW | 0 | 0 | USC21C003 | USCSB2401082A | 0 | F21P1 UPW | 3271 | C |  | UPW-HKPs epoxy | 2024/1/12 2024/1/23 | [8 empty] | PR Approved | PO Approved | PR R1: Renew the quotation and scope, so cancel this PR, |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2302020A | 0 | F21P1 UPW | 1701 | C |  | Tank Diamond labels | 2023/2/9 2023/3/1 | x | -4874.6 | 4874.6 | [5 empty] | PR Approved | PO Approved | Supplier unable to accept payment methods. This will be resubmitted through a distributor of the supplier. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC21C003 | USCSB2308133A | 0 | F21P1 UPW | 2428 | C |  | WWT Lab Furniture Installation | 45161 | x | [7 empty] | PR Approved | PO Approved | PR Returned - use mic general labor |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2401095A | 0 | F21P1 Module Tool Interconnection ETC1-3 | 3282 | C |  | DAQ KECOT5 Install E-sensors and route cables/PFA tubing to Prime Controls supplied AC box. | 2024/1/13 2024/8/22 | 2024/3/8 2024/8/22 | -777.45 | 777.45 |  |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC24B002 | USC2403067A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 890 | P |  | welding for 3 flanges for tools KDPOT9 (2) & KDANT8 & should only 3hrs. | 3/15/2024 8/10/2024 | 3/26/2024 8/22/2024 | -448 | 448 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | R1: PO never was used. Needs to be deleted |  | Yikang Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2312127A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3117 | C |  | AZ F21 Pumping Line hardware for Tunyi | 2023/12/16 2024/3/31 | [8 empty] | PR Approved | PO Approved | PR R1: zero out |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2301017A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1639 | C |  | CCB DCR pipe materials | 2023/1/10 2023/2/2 | x | -13467.49 | 13467.49 | [5 empty] | PR Approved | PO Approved | This PR has been cancelled by PM |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | 0 |  | Base-Build | 0 | 0 | USC23C040 | USCSB2309052A | 0 | TSMC F21 Clean Room Suit | 2528 | C |  | Sunrise Phoenix housekeeping services | 45181 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2212035A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1607 | C |  | CO MIC BIM Support | 44915 | x | -358560 | 358560 |  | V |  |  |  | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2311101A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2952 | C |  | 100 tools hard wares demand | 2023/11/21 2023/12/1 | X | [7 empty] | PR Approved | PO Approved | PR R1:canceled order |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C001 | USCSB2309047A | 0 | TEL Main Tool Interconnection | 2524 | C | -01 | KPOCT8-T UMEC ADD ON | 2023/9/12 2023/9/28 | 2023/9/22 2023/10/2 | -2013.45 | 2013.45 |  |  |  | V | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Labor | 0 | Low Voltage | Low Voltage | 0 | 0 | USC21C013 | USCSB2311105A | 0 | F21P1 AMC THC Monitoring System | 2956 | C | -02 | FAB B VOC Electrical Permit and CA service | 2023/11/23 2023/12/14 | 2023/11/30 2023/12/5 2023/12/28 | -57905 | 57905 |  |  |  |  | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | R2: As per WanChun,the scope of this work order needs to revise it. So close this PR, and create a new PR. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2311115A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2966 | C | -01 | Border States Electrical Work Material PreFab Area | 2023/11/28 2023/12/13 | 2023/11/28 2023/12/14 | -1780.67 | 1780.67 |  |  |  | V | Border State Industries, Inc. | PR Approved | PO Approved | PO R1:Since our work order was not acknowledged by Border States yet because of the account hold, we will cancel our order directly |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | 5G | Material | 0 | 0 | Low Voltage | 0 | 0 | USC22C010 | USCSB2311131A | 0 | F21 P1 LSC CMS and DPM 5G System | 2981 | C |  | F21 CMS & DPM IMP Engineering | 2023/11/29 2023/12/5 | X | [7 empty] | PR Approved | PO Approved | PR R1:cancelled the PO |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | 0 | Chemical | 0 | 0 | USC23C054 | USCSB2309033A | 0 | UPW Change Order | 2510 | C |  | F21 P1 Harder CDS Change Order | 2023/9/8 2023/11/15 | [8 empty] | PR Approved | PO Approved | PR R1: PR to be cancel. / The work with Harder changed to T&M. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2311145A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 2995 | C | -01 | CDA line WRC L20 material | 2023/11/30 2023/12/8 | 2023/11/30 2023/12/8 | -874.32 | 874.32 |  |  |  |  | WW Grainger Inc | PR Approved | PO Approved | PO R1:As per responsible engineer to cancel the PR |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312004A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2999 | C |  | Connector, KRWRS6, KMOPA4-C | 2023/12/1 2023/12/12 | X | [7 empty] | PR Approved | PO Approved | PR R1:Using the wrong budget/ project code. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2312008A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3003 | C |  | Tool hookup Plastic material, KRWRS6, KMOPA4-C | 2023/12/1 2023/12/12 | X | [7 empty] | PR Approved | PO Approved | PR R1:Using the wrong budget/ project code. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2312093A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3084 | C |  | HK Yaho engineer assistants. | 2023/12/14 2024/1/9 | [8 empty] | PR Approved | PO Approved | PR R1:need to clarify scope |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USC2404066A | 0 | F21P1 AMAT Interconnection | 1019 | P | -01 | tw trade manager fee for company | 45398 | 2024/4/23 2024/5/6 | -176000 | 176000 |  |  |  |  | THIRD ENTERPRISE CO., LTD | PR Approved | PO Approved | PO R1: Vendor requests this order to be released to its company in the U.S., so this order will be zero out | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2309027A | 0 | F21P1 Chemical & WCCS package | 2504 | C | -01 | Boxes for bridge/HPM/clean room of CDS system. | 2023/9/8 2023/9/21 | 2023/9/13 2023/9/21 | -78434.46 | 78434.46 | V | V | V | V | Professional Plastics Inc | PR Approved | PO Approved | This PR will be modified to change the amount and add items, so need cancel this PR and create a new one. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2309025A | 0 | F21P1 Chemical & WCCS package | 2502 | C | -01 | 441002-EWO-091-Bridge IPA UB relocation Bim track 36 Proposal | 2023/9/8 2023/12/12 | 2023/10/1 2023/12/30 | -39033 | 39033 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO 100% |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2309024A | 0 | F21P1 Chemical & WCCS package | 2501 | C | -01 | 441002-EWO-054-Lorry A & B CDA/GN2 Cap removal and re-install | 2023/9/8 2023/12/12 | 2023/9/12 2023/12/30 | -32883 | 32883 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO 100% |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | 0 | Low Voltage | Low Voltage | 0 | 0 | USC21C013 | USCSB2212048A | 0 | F21P1 AMC THC Monitoring System | 1619 | C | -01 | Dual-Stage Pressure Regulator | 2022/12/29 2023/3/2 | 2023/1/3 2023/3/3 | -22552.6 | 22552.6 |  | V |  |  | Matheson Tri-Gac Inc. | PR Approved | PO Approved | Item changes that cannot be added on this PR; need to void this one and create a new PR |  | Yuanyuan Liang |  |  | Rui Ma | Yuanyuan Liang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309014A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2492 | C | -01 | TW E2 Hookup GF Welding Machine part 2 | 2023/9/6 2023/9/22 | 2023/9/14 2023/9/22 | -138090.06 | 138090.06 |  |  |  |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | R1:The original PO is for rent, and now MICU would like to issue a new PO for purchase. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23C003 | USCSB2309011A | 0 | F21P1 Module Tool Interconnection CVD | 2489 | C |  | Change Order: install under RMF Chamber Junction Boxes for Tool KCBDA1 | 2023/9/2 2023/9/12 | x | [7 empty] | PR Approved | PO Approved | PR R1: needed to correct quantity |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2309006A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 2484 | C |  | Mini-Electronic Kit with Threaded Tips & blower | 2023/9/1 2023/9/9 | x | [7 empty] | PR Approved | PO Approved | Return - No Purchase |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2401110A | 0 | F21P1 Module Tool Interconnection CVD | 3297 | C | -01 | Single& Dual Vent Line Scope | 45308 | 2024/1/26 2024/2/22 | -100000 | 100000 |  |  |  |  | YAHO System Technology Co., Ltd. | PR Approved | PO Approved | PO R1:Change Vendor to YAHO USA |  | Yikang Wang (Ta Wei Wang) |  |  |  | Yikang Wang (Ta Wei Wang) | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Material | 0 | 0 | Low Voltage | 0 | 0 | USC21C013 | USCSB2302028A | 0 | F21P1 AMC THC Monitoring System | 1709 | C | -01 | Electrician from Hua Yi | 2023/2/11 2023/12/28 | 2023/4/17 2024/1/1 | -103000 | 103000 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | Redundant job scope |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C005 | USCSB2401124A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 3311 | C | -01 | Labor and Material Quote for 16 tools | 45309 | 1/20/2024 2/22/2024 | -20552.68 | 20552.68 |  |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: PR was submitted under Main Tool so this order is cancelled |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C006 | USCSB2308081A | 0 | F21P1 Module Tool Interconnection EPI | 2378 | C |  | EPI: KCEPS1 – CABLE PULLS | 45153 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Equipment |  |  | AMHS |  |  | USC22C031 | USCSB2401262A | 0 | CAP_E_F21P1 AMHS MML Seismic Foundation | 3442 | C | -01 | I-Line USE PLUG-IN NFB 15A 2-Pole AC breaker | 45322 | 2024/4/1 2024/6/18 | -603 | 603 | V | V |  |  | Third Enterprise | PR Approved | PO Approved | R1: As per engineer Tzuhao to cancel this PR. |  | Ta Wei Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C014 | USCSB2402002A | 0 | F21P1 AMHS Power Panel | 3445 | C | -01 | He Dain(和電) Manpower for Hookup Interconnection | 2024/2/1 2024/3/8 | 2024/2/28 2024/3/11 | -740520 | 740520 |  |  |  | V | He Dain Automation Equipment Co.,Ltd. | PR Approved | PO Approved | PO R1: As per Martin to cancel the PR. (Change to Sinfo Engineering) |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2402003A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3446 | C |  | 100% DI Water Cleanroom wipes for HK shared by all trades | 2024/2/1 2024/2/29 | [8 empty] | PR Approved | PO Approved | PR R1:need dry wipes instead |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | Leak Panel | Material |  |  | Others |  |  | USC23C013 | USCSB2303024A | 0 | Hookup Leak Panel for AZQR&EBO | 1766 | C | -01 | QR Leak Panel | 2023/3/4 2024/5/13 | 2023/4/18 2024/5/13 | -2112800 | 2112800 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | Descope order |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2402035A | 0 | F21P1 Chemical & WCCS package | 3478 | C | -01 | CDS LB2 SS parts | 2024/2/3 2024/2/6 2024/2/27 | 2024/2/9 2024/2/28 | -7721.5 | 7721.5 |  |  |  | V | Propersys Corp | PR Approved | PO Approved | PR R1:As per TJ to updated the quote (remove item 3、4 and 7 ) PO R1: Duplication Order |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C006 | USCSB2308083A | 0 | F21P1 Module Tool Interconnection EPI | 2380 | C |  | EPI: KEXR01 – CABLE PULLS | 45153 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2402059A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3501 | C |  | cable lugs for hk power trade | 2024/2/7 2024/2/10 | [8 empty] | PR Approved | PO Approved | PR R1:zero out |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C006 | USCSB2308082A | 0 | F21P1 Module Tool Interconnection EPI | 2379 | C |  | EPI: KCEPS3 – CABLE PULLS | 45153 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2308079A | 0 | EBO21- Tool interconnection | 2376 | C |  | EBO: ZMERIT1 - Galvanized Steel for F76mmPedestal/1P Raised Floor | 2023/8/15 2024/8/2 | 2023/8/15 2024/8/7 | -496 | 496 |  |  |  | V | TCELC CO., LTD | PR Approved | PO Approved | R1: VOID - PER PM change scope and PURCHASING |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | 0 | UPW | 0 | 0 | USC21C003 | USCSB2308117A | 0 | F21P1 UPW | 2414 | C |  | TOC Replacement Parts | 45157 | 2023/8/23 2023/9/26 | -10965 | 10965 |  |  |  |  | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC24B002 | USC2402058A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 776 | P |  | I welder for 7 hrs. to weld 4 4" exhaust adapters and 3 6 inch exhaust adapters for tool ID# (KDANT1, KDPOT3, KDANT5, KDANTA | 2024/2/12 2024/8/22 | 2024/2/23 2024/8/22 | -448 | 448 |  |  |  | V | Westerwood Global USA Corporation | PR Approved | PO Approved | PR R1: PO never was used. Needs to be deleted |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C004 | USCSB2306021C | 0 | F21P1 WWT package （USA EQ-FRP tank) | 2057 | C |  | WWT - Lab glassware | 45083 | 45135 | [6 empty] | Laboratory Sales and Service | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C008 | USCSB2402098A | 0 | F21P1 Module Tool Interconnection LIT2-3 | 3538 | C |  | Lit 3: KPAN01-T: Grounding Box and Wiring Installation | 2/10/2024 8/28/2024 | 2/22/2024 8/29/2024 | -3850 | 3850 |  |  |  |  | Advanced Technical Solutions, LLC | PR Approved | PO Approved | R1: Advanced Technical Solutions did not do the work |  | Yikang Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C008 | USCSB2402100A | 0 | F21P1 Module Tool Interconnection LIT2-3 | 3540 | C |  | Lit 3: KPAP01-T: Grounding Box and Wiring Installation | 2/10/2024 8/28/2024 | 2/22/2024 8/29/204 | -3850 | 3850 |  |  |  |  | Advanced Technical Solutions, LLC | PR Approved | PO Approved | R1: Advanced Technical Solutions did not do the work |  | Yikang Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Southland | 0 | AMC THC | Low Voltage | 0 | 0 | USC21C007 | USCSB2308068A | 0 | F21P1 VOC package （Installation ) | 2366 | C | -01 | VOC 3 and VOC 2 railing removal | 45149 | 2023/9/15 2023/9/20 | -4512.09 | 4512.09 |  |  |  |  | Southland Industries | PR Approved | PO Approved | R1:Cancel, per responsible engineer. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402044A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 764 | P |  | Electrical cable pull for KESRT5 | 2/7/2024 8/10/2024 | 2/28/2024 8/22/2024 | -4759.56 | 4759.56 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402037A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 760 | P |  | Rafael Osorio and Eloy Pacheco Electrical cable pull for KEBEL2. ETCH 1 INTERCONNECTS. CGS. | 2024/2/7 2024/8/12 | 2024/2/6 2024/8/13 | -276 | 276 |  |  |  | V | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2402154A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3587 | C |  | Electric Scissor Lift skyjack/Packaging & Crating unit/Palletizing tire cover for Skyjack 3219/new sales tax | 2024/2/16 2024/3/21 | [8 empty] | PR Approved | PO Approved | PR R1:Purchasing used orginal PR submitted |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C014 | USCSB2401258A | 0 | F21P1 AMHS Power Panel | 3438 | C |  | Chi-Yang manpower for interconnection(Feb-May) and AMHS(June-Oct) | 2024/1/31 2024/3/8 | [7 empty] | Marketech International Corp. | PR Approved | PO Approved | PR R1:As per Martin to cancel the PR. |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C014 | USC2402098A | 0 | F21P1 AMHS Power Panel | 812 | P |  | manpower - general labors | 2024/2/23 2024/4/27 | [7 empty] | 0 | PR Approved | PO Approved | PR R1:please close this PR. Was never in use | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2401230A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 3412 | C |  | Narrow size washers | 2024/1/26 2024/1/29 | [8 empty] | PR Approved | PO Approved | PR R1:cancel this PR | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402105A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 817 | P |  | Cable pull KESRT2 | 2024/2/27 2024/8/14 | 2024/2/26 2024/8/16 | -527.73 | 527.73 |  |  | V |  | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2302041A | 0 | F21P1 Chemical & WCCS package | 1722 | C | -01 | L20 VMB Design Change | 2023/2/18 2023/12/12 | 2023/2/22 2024/1/4 | -109807 | 109807 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | Scope is completed and therefore no requirement |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2401144A | 0 | F21P1 Module Tool Interconnection ETC1-3 | 3329 | C |  | KESDM2 DAQ | 1/19/2024 8/15/2024 | 2/24/2024 8/28/2024 | -103.66 | 103.66 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2401150A | 0 | F21P1 Module Tool Interconnection ETC1-3 | 3335 | C |  | KECOL4 DAQ Install E-sensors and route cables/PFA tubing to Prime Controls supplied AC box. | 2024/1/19 2024/8/14 | 2024/3/7 2024/8/16 | -350.74 | 350.74 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | PO R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C009 | USCSB2401151A | 0 | F21P1 Module Tool Interconnection ETC1-3 | 3336 | C |  | KEPCH2 DAQ | 1/19/2024 8/15/2024 | 2/24/2024 8/28/2024 | -103.66 | 103.66 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403017A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 844 | P |  | Interconnect power and signal KESTL6 | 2024/3/6 2024/8/12 | 2024/3/6 2024/8/13 | -805 | 805 |  |  |  | V | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2401166A | 0 | F21P1 Module Tool Interconnection CVD | 3351 | C |  | WELD PIPE for KEMEA3 | 2024/1/20 2024/1/25 | [7 empty] | 0 | PR Approved | PO Approved | PR R1:wrong account code |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2302051A | 0 | F21P1-0404_H_Hallway plate install_MICU | 1732 | C | -01 | Type B and Type E foundations installation | 2023/2/25 2023/4/22 | 2023/3/17 2023/4/27 | -10650000 | 10650000 |  |  |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | PO cancelled by engineer due to scope change |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2302052A | 0 | F21P1-0404_H_Hallway plate install_MICU | 1733 | C |  | Type A, Type C and Type D foundations installation | 2023/2/25 2023/4/29 | x | -12424568 | 12424568 | [5 empty] | PR Approved | PO Approved | Return requested by Martin due to Scope Change |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Labor | 0 | 0 | Low Voltage | 0 | 0 | USC21C013 | USCSB2302053A | 0 | F21P1 AMC THC Monitoring System | 1734 | C |  | Crating Service and Delivery | 2023/2/25 2023/4/29 | x | -2374 | 2374 | [5 empty] | PR Approved | PO Approved | The invoice for this PR has already been paid via APN. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2302059A | 0 | F21P1 Chemical & WCCS package | 1740 | C | -01 | 14652 - H10A at X1,7 module clash with square duct | 2023/2/28 2023/12/11 | 2023/3/15 2023/1/4 | -6080 | 6080 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Work done before turning T&M, Paid in Orginal PO |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403002A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 829 | P |  | Mechanical Interconnect - Labor KCSCS3, KEPSL5, KEPSL3, KEPSL1, KDCCS1 KEPSL4, KDCRS4, KDCCS2, KDCCS3, KCSCSA, KEBCL1, KRWRS7, KCSCS9, KCSCS7, KEPSL6 KEPSS1, KCSCSB, KCSCSC, KCSCS6, KEPSL2 | 2024/3/2 2024/8/12 | 2024/3/6 2024/8/13 | -147000 | 147000 |  |  |  | V | Trusval Technology CO., LTD. | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2403001A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 828 | P |  | Electrical cable pull for KESDL2 and KESTL2. | 45352 | 2024/3/1 2024/8/14 | -646.88 | 646.88 |  |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Kuan-Chung Su | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2401197A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 3382 | C |  | Southwestern Scale Company EUV Crane Maintenance Mennen Annual Inspection | 2024/1/25 2024/3/6 | [8 empty] | PR Approved | PO Approved | PR R1:Cancelled, went with a different vendor |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC24B002 | USC2402114A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 824 | P |  | 1 welder, to weld, 6 exhaust flanges- KDANT3, KDANT7, KDANT6, KDPOTJ, KDEPT5 (2) | 2024/2/29 2024/3/7 2024/8/10 | 3/9/2024 8/22/2024 | -448 | 448 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | PR R1:whole amount needed to be calculated R2: PO never was used. Needs to be deleted |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2302060A | 0 | F21P1 Chemical & WCCS package | 1741 | C | -01 | About Bridge to L20 HPM | 2023/2/28 2023/12/12 | 2023/3/15 2024/1/4 | -6160 | 6160 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Work done before turning T&M, Paid in Orginal PO |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2302061A | 0 | F21P1 Chemical & WCCS package | 1742 | C | -01 | EWO-018 Lorry A,B E. room hanger re-work proposal | 2023/2/28 2023/12/11 | 2023/3/21 2024/1/4 | -102991 | 102991 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Work done before turning T&M, Paid in Orginal PO |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | 0 | CDS | Chemical | 0 | 0 | USC21C006 | USCSB2401221A | 0 | F21P1 Slurry package | 3403 | C |  | CDS B side support L20 | 2024/1/26 2024/3/28 | [8 empty] | PR Approved | PO Approved | PR R1:As per PM:Johnny Wan to cancel the PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Labor | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2212015A | 0 | F21P1 UPW | 1588 | C |  | UPW LB2 & X1-Y Line Redesign and Network & Com | 44904 | x | [7 empty] | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2212011A | 0 | F21P1 UPW | 1584 | C | -01 | UPW-MMF-Anthracite procurement | 44902 | 44935 | -6080 | 6080 |  | V |  |  | Northern Filter Media, Inc. | PR Approved | PO Approved | Cannot revise description and cannot add new item, so we can only cancel this PO and get a new one, which is super redundant and a waste of time |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2402206A | 0 | F21P1 AMAT Interconnection | 3633 | C | -01 | E-OPS Installers for 3 Months | 2024/2/21 2024/4/18 | 2024/2/28 2024/4/26 | -189281.69 | 189281.69 |  |  |  |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | R1: Canceled order |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C006 | USCSB2310033A | 0 | F21P1 Module Tool Interconnection EPI | 2696 | C |  | KCENA1 & KCEPA1 EPI Pump Fore Line Adapter Modification Proposal | 2023/10/5 2023/11/15 | x | [7 empty] | PR Approved | PO Approved | PR R1: canceled order |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | 0 | 0 | Base-Build | 0 | 0 | USC21C009 | USCSB2110015A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1304 | C | -01 | Outsourcing Service Master Scheduler | 2021/10/14 2022/7/19 | 2021/10/22 2022/7/27 | -52500 | 52500 |  |  |  |  | World Wide Professional Solutions, LLC | PR Approved | PO Approved | 7/27 manpower shortage ,change odrder to 0 | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N |  | Henry |  | N |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C003 | USCSB2310015A | 0 | F21P1 Module Tool Interconnection CVD | 2678 | C |  | CVD2: KCANN1/KCANN2: Load Lock Gasline Weldments | 10/3/2023 8/15/2024 | 10/12/2023 8/22/2024 | -4043 | 4043 |  |  |  |  | Trident Mechanical Services | PR Approved | PO Approved | R1: VOID - PER PM. NO LONGER NEEDED IT. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | 0 | 0 | Base-Build | 0 | 0 | USC21C009 | USCSB2110014A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1303 | C | -01 | Outsourcing Service QA/QC Manager | 2021/10/14 2022/3/9 | 2021/10/22 2022/3/11 | -281604 | 281604 |  |  | V |  | World Wide Professional Solutions, LLC | PR Approved | PO Approved | MICU 3/11提出， 執行異動結案。 | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N |  | Henry |  | N |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | 0 | 0 | Base-Build | 0 | 0 | USC21C009 | USCSB2110009A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1298 | C | -01 | Outsourcing Service | 2021/10/12 2022/3/9 | 2021/10/18 2022/3/11 | -329604 | 329604 |  |  | V |  | World Wide Professional Solutions, LLC | PR Approved | PO Approved | MICU 3/11提出， 執行異動結案。 | 100% by Progress-T/T 30 day (Monthly payment) | Cherry Chang |  |  | Rui Ma | Cherry Chang | N |  | Henry |  | N |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2109013A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1287 | C | -01 | WWT Tank Inspection | 2021/9/21 2021/11/02 | 2021/9/28 2021/11/4 | -191946 | 191946 |  |  | V |  | Technical Inspections Group | PR Approved | PO Approved | MICU 10/27提出， 執行異動結案。 | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | x | Henry |  | N |  |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | [26 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2109011A | 0 | F21P1 UPW | 1285 | C | -01 | UPW Tank Inspection | 2021/9/21 2021/11/2 | 2021/9/30 2021/11/4 | -119244 | 119244 |  |  | V |  | Technical Inspections Group | PR Approved | PO Approved | MICU 10/27提出， 執行異動結案 | PR取消 | York Yeh | DDP | 1year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | York Yeh | N | x | Matt |  | N |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Slurry | Equipment | 0 | 0 | Chemical | 0 | 0 | USC21C006 | USCSB2109006A | 0 | F21P1 Slurry package | 1280 | C | -01 | Slurry Mechanical Instrument Air | 2021/9/4 2023/12/11 | 2021/9/14 2023/12/13 | -1258610 | 1258610 |  | V |  |  | Prime Mechanical, Inc. | PR Approved | PO Approved | PO R1:arrcording to PM indication :Close Out PO | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Slurry |  | Henry |  | Y |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2209008A | 0 | F21P1 UPW | 1461 | C |  | UPW Resin temporary storage | 44814 | 44831 | [7 empty] | PR Approved | PO Approved | Returned, paid storage fee for Hankyu Hanshin (Membrane storage) |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | MMI | 0 | 0 | Base-Build | 0 | 0 | USC22C013 | USCSB2309141A | 0 | F21P1 QR Lab Security & CCTV | 2612 | C | -01 | Provide generator rental for temporary power staged outside of Fab building on West side. | 2023/9/22 2023/12/7 | 2023/9/29 2023/12/7 | -119203 | 119203 |  |  |  | V | Milling Machinery, Inc. | PR Approved | PO Approved | Revise project code,so need to cancel this PR,and issue a new PR for this PR. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | 0 | Shared Cost | Base-Build | 0 | 0 | USC21C003 | USCSB2112004A | 0 | F21P1 UPW | 1316 | C |  | Shane's Grading & Paving | 2021/12/14 2022/2/5 | x | -170335 | 170335 | [5 empty] | PR Approved | PO Approved | 1/18 MICU weekly neeting ask for cancelation *Already returned to PM side | PR取消 | York Yeh |  |  | Shannon Pulcifer | York Yeh | N |  | Matt |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | 0 | Low Voltage | Low Voltage | 0 | 0 | USC21C013 | USCSB2209030A | 0 | F21P1 AMC THC Monitoring System | 1482 | C | -01 | AMC Gas Cylinders | 44832 | 2022/10/8 2022/12/2 | -10942.4 | 10942.4 |  | V |  |  | Matheson Tri-Gac Inc. | PR Approved | PO Approved | Desciption cannot be changed, so close this and open new one because of new scope and quotation | 100% by received-Net 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | 光阻櫃 | Equipment | Main Contract Scope | Low Voltage | Low Voltage | Mechanical | Equipment ( Tank 等工程相關的設備) | USC22C012 | USCSB2210003A | 0 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1487 | C | -01 | 宇承_光阻推車&推酸車 | 2022/10/1 2023/4/1 | 2022/10/3 2023/4/4 | -10302 | 10302 |  |  |  | V | Yu Cheng Kid Enterprise Co., | PR Approved | PO Approved | Cancelling this PR due to the rush of manufacture Combine this overtime pay into USCSB2210002A | 100% by received-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310053A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2713 | C | -01 | flowmeter vern | 2023/10/10 2024/3/8 | 2023/11/4 2024/3/28 | -3636.44 | 3636.44 |  |  |  |  | Vern Lewis Welding Supply, Inc. | PR Approved | PO Approved | R1: duplicate. zero out |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309130A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2601 | C | -01 | E2 TW Profit - Trusval | 2023/9/21 2023/12/28 | 2023/10/2 2023/12/28 | -1113900 | 1113900 |  |  |  | V | Trusval Technology CO., LTD. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2310065A | 0 | F21P1 Chemical & WCCS package | 2725 | C | -01 | Hardware for Chemical YaoHong work at Lorry FNDP, CDA at L20. | 2023/10/11 2023/11/14 | 2023/10/13 2023/11/14 | -77013 | 77013 |  |  |  |  | JUWEI ENGINEERING CO LTD | PR Approved | PO Approved | R1: Will change to another supplier per request |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309128A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2599 | C | -01 | E2 TW Profit - GENIIDEAS | 2023/9/21 2023/12/28 | 2023/10/3 2023/12/28 | -294000 | 294000 |  |  |  | V | GENII IDEAS Co., Ltd. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409031A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1233 | P |  | Vantech 3-Bar White Aluminum Bolt-On Ladder Rack System Ford Transit 2015-current Model H1753W | 2024/9/16 2024/9/19 | [8 empty] | PR Approved | PO Approved | PR R1:Orders related to our company's car accessory, such as this ladder rack, go through HR department for purchase by APN | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309127A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2598 | C | -01 | E2 TW Profit - Chuan Ta | 2023/9/21 2023/12/28 | 2023/10/4 2023/12/28 | -418000 | 418000 |  |  |  | V | Chuan Ta Technology Corp. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Labor | 0 | 0 | WWT | 0 | 0 | USC21C014 | USCSB2111002A | 0 | F21P1 WH2SO4 | 1306 | C | -01 | W-H2SO4 Electrical Work | 44509 | 2021/11/15 2023/6/8 | -583750 | 583750 |  |  |  | v | Climatec, LLC | PR Approved | PO Approved | Termination with Climatec | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Henry |  | Y | 5005 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2201003A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1320 | C | -01 | Equipment install supervision | 2022/1/14 2023/03/23 | 2022/1/20 2023/03/23 | -800000 | 800000 |  |  |  | V | Marketech International Corp. | PR Approved | PO Approved | tsmc F21P1 MIC 出差人力 Reorganized M4 WO (03/24/2023) | 100% by progress, T/T 45 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT |  |  |  | Y |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | CCTV | Labor | 0 | Low Voltage | Low Voltage | 0 | 0 | USC21C008 | USCSB2212006A | 0 | F21P1 CCTV & Security | 1579 | C | -01 | Power Cable | 2022/12/2 2023/12/27 | 2022/12/14 2023/12/27 | -147000 | 147000 |  |  |  | V | Alvarado Electric LLC. | PR Approved | PO Approved | R1: Canceled Scope and already PO to other sub |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2309184A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2652 | C |  | Mobile Bar and Pipe Rack | 45198 | 2023/10/4 2023/11/14 | 0 | [5 empty] | Uline | PR Approved | PO Approved | PO R1:Supplier Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | 0 | 0 | Base-Build | 0 | 0 | USC21C009 | USCSB2207014A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1429 | C | -01 | Electrical Superintendent | 2022/7/12 2022/7/22 | 2022/7/18 2022/7/24 | -99600 | 99600 |  | V |  |  | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 取消 | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2207013A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1428 | C | -02 | Internet for Glendale warehouse | 2022/7/9 2022/7/30 2022/11/2 | 2022/7/19 2022/8/5 2022/11/3 | -59394.6 | 59394.6 |  | V |  |  | Level 3 Communications, LLC, A Lumen Technologies Company | PR Approved | PO Approved | Rev01-add the router to the current order Rev02-change to another company (Transpak) | 100% by progress/distributed monthly-net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309154A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2625 | C | -01 | E2 TW Profit - Yaho | 2023/9/26 2023/12/28 | 2023/10/4 2023/12/28 | -1516000 | 1516000 |  |  |  | V | YAHO System Technology Co., Ltd. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2208018A | 0 | F21P1 UPW | 1454 | C | -01 | Horiba Conductivity/Resistivity Meter | 44804 | 44810 | -53532 | 53532 | V |  |  |  | HORIBA Taiwan, Inc. | PR Approved | PO Approved | JPY 6,691,500; ERP不能直接更改幣值，因需重開而異動為0 | 100% by shipment-after acceptance-net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC | EDG | Equipment |  |  | Others |  |  | USC22C003 | USCSB2206006A | 0 | TSMC Fab21 Project Phase 1 EDG Package | 1397 | C | -01 | TSMC Fuel Oil System Long Lead Items | 2022/6/3 2022/9/30 | 2022/6/22 2022/10/10 | -857319 | 857319 |  | V |  |  | W.D. Manor Mechanical Contractors, Inc. | PR Approved | PO Approved | We send PO to WD Manor in the beginning for EDG mechanical work. However, their delivery date cannot meet our requirement. After meeting with Fu Energy, we decide to transfer the whole scope to Sundt. | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC21C004 | USCSB2209003A | 0 | F21P1 WWT package （USA EQ-FRP tank) | 1456 | C |  | WRC Chemical Room Chemical Resistant Coating | 44806 | x | -300000 | 300000 | [5 empty] | PR Approved | PO Approved | Scope changed |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Labor | 0 | 0 | Base-Build | 0 | 0 | USC21C009 | USCSB2205010A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1374 | C |  | Modular Pipe Support Assembly Design change order | 44691 | x | -11000 | 11000 | [5 empty] | PR Approved | PO Approved | 因Item Description錯誤且無法異動修改，已請專案刪除結案(USCSB2205014A取代) | 取消PR | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2309183A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 2651 | C |  | DIFF 1: 25 Tools Swagelok for N2 bottle | 2023/9/29 2024/8/5 | 2023/10/3 2024/8/5 | -89.08 | 89.08 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: VOID - Material never ordered. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2309184B | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2653 | C |  | Mobile Bar and Pipe Rack | 9/29/2023 8/22/2024 | 11/16/2023 8/24/2024 | -10400 | 10400 |  |  |  | V | U-Line Corporation | PR Approved | PO Approved | B PR R1: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | 0 | 0 | Chemical | 0 | 0 | USC21C005 | USCSB2201004A | 0 | F21P1 Chemical & WCCS package | 1321 | C | -01 | CDS Equipment | 2022/1/14 2023/3/23 | 2022/1/24 2023/3/23 | -3000000 | 3000000 |  |  |  | V | Marketech International Corp. | PR Approved | PO Approved | tsmc F21P1 MIC 設備費用 Quotation clarifying Reorganize M4 WO (03/24/2023) | 100% by progress, T/T 45 days (after acceptance) | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | N | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2309190A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2658 | C |  | Andys Air Conditioning Installation Glendale and Surprise | 2023/9/29 2023/10/21 | x | [7 empty] | PR Approved | PO Approved | PR R1: cancel this PR |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2203014A | 0 | F21P1 UPW | 1349 | C |  | Mechanical | 44644 | 44650 | -47706 | 47706 | [5 empty] | PR Approved | PO Approved | 報價單調整，重新開請購單USCSB2204001A | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | 0 | Chemical | 0 | 0 | USC21C005 | USCSB2203010A | 0 | F21P1 Chemical & WCCS package | 1345 | C | -01 | Mechanical CDS Field Work | 2022/3/17 2023/3/23 | 2022/3/21 2023/3/24 | -1150000 | 1150000 |  |  |  | V | Marketech International Corp. | PR Approved | PO Approved | Reorganize M4 WO (03/24/2023) | 90% by progress, T/T 30 days. 10% after acceptance or 90 days after shipping which ever is early. | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | CHEM | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309193A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2661 | C | -01 | E2 TW Profit - Uangyih | 2023/9/29 2023/12/28 | 2023/10/3 2023/12/28 | -252000 | 252000 |  |  |  | V | Uangyih-Tech Industrial Co., LTD | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309194A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2662 | C | -01 | E2 TW Profit - Huengluei | 2023/9/29 2023/12/28 | 2023/10/3 2023/12/28 | -661520 | 661520 |  |  |  | V | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C005 | USCSB2309147A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 2618 | C | -01 | DIFF1: 25 TOOLS : T&M N2 DIFFUSION LINES | 45192 | 45210 | -333633 | 333633 |  |  |  |  | Greenberry Industrial | PR Approved | PO Approved | PO R1: VOID - PER TYLER SMITH No longer using subcontractor |  | Yikang Wang (Lemar J Edwards) |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | CCTV | CCE | 0 | 0 | Low Voltage | 0 | 0 | USC21C008 | USCSB2202006A | 0 | F21P1 CCTV & Security | 1331 | C | -01 | MIC TURNSTILES ON DUNLAP AVENUE | 44604 | 44609 | -12062.22 | 12062.22 | V | V |  |  | Commercial Comm and Electric Inc | PR Approved | PO Approved | 取消此單並用BPG，PM忘記在2月已有開給CCE，但SCOPE已變，所以交由BPG處理 | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N? | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2310004A | 0 | F21P1 Chemical & WCCS package | 2667 | C | -01 | Leveling Foot to support W-IPA WLS at the correct elevations. | 45202 | 2023/10/6 2023/11/7 | -405.2 | 405.2 |  |  |  |  | WW Grainger Inc | PR Approved | PO Approved | Cancelled the PO |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C026 | USCSB2210029A | 0 | F21P1-0423_H_Unistrut Support Frame_MICU | 1512 | C | -01 | MISC BOM-3 CLAMPS | 2022/10/19 2022/11/16 | 2022/10/24 2022/11/16 | -4772888.51 | 4772888.51 | V | V |  |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Price changed & item number changed, but PR cannot revise, so close this and open new one Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310082A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2742 | C |  | Tool Hookup L40 Warehouse | 45212 | 2023/10/19 2023/11/14 | [6 empty] | Uline | PR Approved | PO Approved | PO R1:Supplier Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | GF Agru Material | Material | 0 |  | WWT | 0 | 0 | USC22C023 | USCSB2210031A | 0 | AZ GF Agru Material | 1514 | C |  | Harrington-8" PVDF STUB END | 2022/10/19 2022/12/1 | x | -23440 | 23440 | [5 empty] | PR Approved | PO Approved | scope change to open PO |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309074A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2548 | C | -01 | E2 TW Profit - TUN YI | 2023/9/14 2023/12/28 | 2023/9/28 2023/12/28 | -808220 | 808220 |  |  |  | V | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved | R1: TW Company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC23C045 | USCSB2311006A | 0 | WWT Change Order (Piping) | 2861 | C |  | (20) Epoxy kit to complete agitator installation | 2023/11/1 2023/11/3 2023/11/28 | X | [7 empty] | PR Approved | PO Approved | PR R2: Request to be canceled by Grant PR R1:add freight charge |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C006 | USCSB2309085A | 0 | F21P1 Module Tool Interconnection EPI | 2558 | C | -01 | cabel trays | 2023/9/15 2023/11/20 | 2023/9/20 2023/11/20 | -2347.34 | 2347.34 |  |  |  | V | Graybar Electric Company, Inc. | PR Approved | PO Approved | PO R1:canceled order (as confirmed by engineering team) |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309078A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2553 | C | -01 | E2 TW Profit - CHI YI HSIN | 2023/9/14 2023/12/28 | 2023/9/29 2023/12/28 | -721600 | 721600 |  |  |  | V | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2405133A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1110 | P |  | 1394335 Electric Scissor Lift, 19' Micro-Rental. Rental date 4/25-5/23/2024. PHX-2923149-0023-Invoice | 2024/5/22 2024/6/5 | 2024/5/23 2024/7/4 | -448.65 | 448.65 |  |  |  |  | EquipmentShare.com INC | PR Approved | PO Approved | R1: This PO is canceled. Shannon Pulcifer will pay for this invoice since the they have been using the lift. See attached email. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309077B | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2552 | C | -01 | E2 TW Profit - Da Yi Cheng | 2023/9/14 2023/12/28 | 2023/10/26 2023/12/28 | -838500 | 838500 |  |  |  | V | DA YI CHENG Technology Co., Ltd. | PR Approved | PO Approved | Zero out USCSB2309077A and Change to another supplier in USCSB2309077B R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309077A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2551 | C | -01 | E2 TW Profit - Third | 2023/9/14 2023/9/26 | 2023/9/28 2023/10/25 | -838500 | 838500 |  |  |  |  | Third Enterprise | PR Approved | PO Approved | R1: Will change to another supplier per request. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309076A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2550 | C | -01 | E2 TW Profit - LI JEI | 2023/9/14 2023/12/28 | 2023/9/28 2023/12/28 | -1080000 | 1080000 |  |  |  | V | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309075A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2549 | C | -01 | E2 TW Profit - Mao Hsun | 2023/9/14 2023/12/28 | 2023/9/28 2023/12/28 | -456000 | 456000 |  |  |  | V | SWIFT ENGINEERING CO., LTD. | PR Approved | PO Approved | R1: TW Company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2212002A | 0 | F21P1 UPW | 1575 | C |  | UPW 4C Wire | 44896 | x | [7 empty] | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2310088A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2749 | C | -01 | Galv. st Duct revision of USCSB2310007 | 2023/10/14 2023/10/27 | 2023/10/19 2023/12/29 | -104813.23 | 104813.23 |  |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | Duplicate USCSB2310007A |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Labor | 0 | 0 | Low Voltage | 0 | 0 | USC21C006 | USCSB2309070A | 0 | F21P1 Slurry package | 2544 | C |  | F21 P1 VOC Support _Labor | 45183 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | 0 | 0 | Low Voltage | 0 | 0 | USC21C006 | USCSB2309069A | 0 | F21P1 Slurry package | 2543 | C |  | F21 P1 VOC Support _material | 2023/9/14 2023/9/16 | x | [7 empty] | PR Approved | PO Approved | Cancelled per request by Angelan Hsu via dated 9/15/2023 |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2309065A | 0 | F21P1 Chemical & WCCS package | 2540 | C | -01 | H20A Spec Change from Plastic to Stainless in Solvent room | 2023/9/13 2023/12/11 | 2023/9/21 2023/12/11 | -76164 | 76164 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per Johnny to cancel PO :Work done before turning T&M, Paid in Original PO 60%, should only pay material and design fee |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2309064A | 0 | F21P1 Chemical & WCCS package | 2539 | C | -01 | L20 HPM Bridge Rework | 2023/9/13 2023/12/12 | 2023/10/11 2024/1/4 | -120000 | 120000 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO 80% |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2309063A | 0 | F21P1 Chemical & WCCS package | 2538 | C | -01 | Lorry A/B RU&CCBTU to tanks piping re-work due to design change REV 2 | 2023/9/13 2023/12/12 | 2023/10/1 2023/12/30 | -115200 | 115200 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO 100% |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2309062A | 0 | F21P1 Chemical & WCCS package | 2537 | C | -01 | L20 HPM Transition to Fab pipe redesign rev2 | 2023/9/13 2023/12/12 | 2023/10/10 2024/1/4 | -35142 | 35142 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Paid in Original PO 50%, MICU only agree to pay design & material |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | 0 | 0 | WWT | 0 | 0 | USC23C045 | USCSB2311068A | 0 | WWT Change Order (Piping) | 2922 | C |  | WWT-misc support-HYC | 2023/11/16 2024/3/1 | 45262 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PR R1:The Supplier is suspended. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2405039A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1081 | P |  | Manpower Pay to CGS GLOBAL for Tool ID: KEMGL3 for Cable Pull and 8395 Rule on Time Card from 3.21.2024 for Luis Rosas, Daniel Calderon, Xavier Niesen, Raul Acuna, and Eliseo Perez | 5/11/2024 8/28/2024 | 5/14/2024 8/28/2024 | -1318.2 | 1318.2 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: Case Closed | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [16 empty] | - |  |  | 0
Others | AMHS | Labor |  |  | AMHS |  |  | USC22C031 | USCSB2310204A | 0 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2855 | C | -01 | AMHS Hole Framing and Cover Removal | 2023/10/31 2023/11/29 | 2023/11/10 2023/12/29 | -28028 | 28028 |  |  |  | V | Milling Machinery, Inc. | PR Approved | PO Approved | Cancelled as scope is covered in another order. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310186A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2838 | C |  | MC Cable for Third | 2023/10/28 2023/11/7 | x | [7 empty] | PR Approved | PO Approved | PR R1:zero out USCSB2310186 |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Material |  |  | Others |  |  | USC22C008 | USCSB2211030A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1563 | C |  | Portable Cleanroom Material - Copper State | 2022/11/22 2023/2/2 | x | -967.46 | 967.46 | [5 empty] | PR Approved | PO Approved | go through APN (non-material) for card purchase |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | 0 | 0 | Chemical | 0 | 0 | USC21C005 | USCSB2211017A | 0 | F21P1 Chemical & WCCS package | 1551 | C | -01 | Protego-Flame Arrestors | 2022/11/12 2023/1/12 | 2022/11/30 2023/1/18 | -134500 | 134500 |  |  |  | V | BERMINGHAM CONTROLS, INC. | PR Approved | PO Approved | Cancelled, used Catrol |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC22C005 | USCSB2210048A | 0 | Tool Hookup Material (UPW&Chemical) | 1530 | C |  | HK UPW material (20k) | 2022/10/26 2023/3/28 | x | -824533.51 | 824533.51 | [5 empty] | PR Approved | PO Approved | scope changed, void this PR |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2409008A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1215 | P |  | Position sensor, 0-6000 mm, Profinet, M4, Linearity 0,02% | 2024/9/5 2024/9/10 | [8 empty] | PR Approved | PO Approved | PR R1:Replace PR # USC2409016 | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C055 | USCSB2310097A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2758 | C | -02 | Uline security cart | 45216 | 2023/10/26 2024/1/13 2024/1/26 | -56160 | 56160 |  |  |  |  | U-Line Corporation | PR Approved | PO Approved | PO R2:change supplier from ULINE to Thomas Scientific PO R1:Negotiated Unit Rate |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USCSB2309121A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2593 | C | -01 | E2 TW Profit - Jer Yih | 2023/9/20 2023/12/28 | 2023/10/3 2023/12/28 | -893000 | 893000 |  |  |  | V | Jer-Yih Electrical Engineering Ltd. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408059A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1205 | P |  | PAY TO DELTA WYE FOR 6 TOOL: CABLE PULL | 2024/8/27 2024/9/7 | [8 empty] | PR Approved | PO Approved | PR R1:Per request to cancel, and will create a lumpsum P1B bulk order in another PO for Delta Wye including these TOOL | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Base-Build | WWT | CCE | 0 | 0 | WWT | 0 | 0 | USC21C004 | USCSB2210049A | 0 | F21P1 WWT package （USA EQ-FRP tank) | 1531 | C |  | CCE Redesign Change Order | 44860 | x | -916925 | 916925 | [5 empty] | PR Approved | PO Approved | Under wrong project |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408055A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1201 | P |  | Labor for Tool KSCBH9 (8395 Certificated 5 techs X 8hrs 40hrs X 3days = 120hrs X $85/hrs | 2024/8/22 2024/9/21 | 45530 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | PR R1: Cancelled*Modified Quote Tools included in PR# USC2409042 | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408053A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1200 | P |  | Labor for Tool KSCTT2 (8395 Certificated 5 techs X 8hrs 40hrs X 3days = 120hrs X $85/hrs | 2024/8/22 2024/9/21 | 45530 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | PR R1: Cancelled*Modified Quote Tools included in PR# USC2409042 | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408044A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1193 | P |  | HMT-24030020: KEPSL7 INTERNAL CONNECT HOOK UP | 2024/8/20 2024/9/24 2024/9/25 2024/9/25 | [8 empty] | PR Approved | PO Approved | PR R4:VOID. New quotation issued. PR R3ERP updated tool ids: line 026 - KEPSLB, line 030 - KEPSS2, line 033 - KCSCSH, line 034 - KEBCT5 PR R2ERP Help updated tool IDS: Line 26 - KEPSLB, Line 30 - KEPSS2, Line 33 - KCSCSH, Line 34 - KEBCT5. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2408013A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1184 | P |  | WIRE TCXH2/4G | 2024/8/10 2024/8/23 | [8 empty] | PR Approved | PO Approved | PR R1: Close this PR, create a new PR USC2408057 instead. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | -
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2310136A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2793 | C | -01 | Yaho Hex nut, square nute, washer | 45219 | 2023/11/1 2023/11/7 | -178286 | 178286 |  |  |  |  | YAHO System Technology Inc. | PR Approved | PO Approved | PO R1:Supplier Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | 0 | 0 | WWT | 0 | 0 | USC21C004 | USCSB2210054A | 0 | F21P1 WWT package （USA EQ-FRP tank) | 1536 | C |  | Distribution Panels | 2022/10/29 2022/11/10 | x | -4963.2 | 4963.2 | [5 empty] | PR Approved | PO Approved | Under wrong project |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2309113A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 2585 | C | -01 | E2 TW Profit - Laien Parts | 2023/9/19 2023/12/28 | 2023/10/3 2023/12/28 | -232000 | 232000 |  |  |  | V | Laien Parts Technology Co., Ltd. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407032A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1165 | P |  | QAQC Visual Testing Level I/II Course fro Tool Hook-up | 2024/7/24 2024/7/25 | [8 empty] | PR Approved | PO Approved | PR R1: PO needs to be deleted, it was submitted under the wrong Project Code | [13 empty] | 0 | 1 | 0 | 0 | 0 | [74 empty] | -
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC23C045 | USCSB2309106A | 0 | WWT Change Order (Piping) | 2578 | C | -01 | WWT -unitstrut_Southwest Fastener | 2023/9/19 2023/10/4 | 2023/9/21 2023/12/5 | -799.57 | 799.57 |  |  |  | V | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | Order included in WO#USCSB2311025A |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407010A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1149 | P |  | 451 PFA Tubing 3/8X1/4X200M | 2024/7/10 2024/7/17 | [8 empty] | PR Approved | PO Approved | PR R1: Cancel Order. Purchasing team will look for other suppliers | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC24B002 | USC2407007A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 1148 | P |  | DRY ETC- ITEM# 93 TUBE SIZE 6.35X4.35X200M | 2024/7/10 2024/7/17 | [8 empty] | PR Approved | PO Approved | PR R1: canceled | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | Housekeeping | 0 | 0 | Base-Build | 0 | 0 | USC21C011 | USCSB2303050A | 0 | F21 TMAH System | 1792 | C | -01 | F21 General Labor and Housekeeping Service | 2023/3/14 2023/4/17 | 2023/3/15 2023/4/17 | -300000 | 300000 |  |  |  |  | BHTC Arizona, LLC | PR Approved | PO Approved | BHTC's performance is not good, cancelled and shifted to HuaYi |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2402216A | 0 | F21P1 Chemical & WCCS package | 3643 | C |  | CDS electrial materials | 2024/2/22 2024/2/27 | [8 empty] | PR Approved | PO Approved | PR R1:As per Purchasing team, replaced by other order. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2305087A | 0 | F21P1 Chemical & WCCS package | 2008 | C | -01 | 4mm PFA Pulls | 2023/5/19 2023/12/11 | 2023/6/20 2023/12/29 | -35407 | 35407 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC21C003 | USCSB2405109A | 0 | F21P1 UPW | 4139 | C | -01 | WWT B Side Battery Recharge 2 | 5/18/2024 6/4/2024 | 2024/5/21 2024/6/5 | -9800 | 9800 |  |  |  | V | Gruber Industries | PR Approved | PO Approved | R1: As per engineer Chihhao to revise the quote, so cancel this PR, and add new PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310011A | 0 | Tool Interconnection Project (Main Tool & Module) | 444 | P |  | Click Copers Monthly rental | 45204 | x | [7 empty] | PR Approved | PO Approved | PR R1 :No PR Email, No Supporting Documents/Wrong |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310010A | 0 | Tool Interconnection Project (Main Tool & Module) | 443 | P |  | Click Copers Monthly rental | 45204 | x | [7 empty] | PR Approved | PO Approved | PR R1: Information mismatch./Wrong project. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310009A | 0 | Tool Interconnection Project (Main Tool & Module) | 442 | P |  | Click Copers Monthly rental | 45204 | x | [7 empty] | PR Approved | PO Approved | PR R1: No PR Email, No Supporting Documents/Wrong project |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310008A | 0 | Tool Interconnection Project (Main Tool & Module) | 441 | P |  | Click Copers Monthly rental | 45204 | x | [7 empty] | PR Approved | PO Approved | PR R1:Information mismatch. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310007A | 0 | Tool Interconnection Project (Main Tool & Module) | 440 | P |  | Click Copers Monthly rental | 45204 | x | [7 empty] | PR Approved | PO Approved | PR R1: No PR Email, No Supporting Documents/Wrong project |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310006A | 0 | Tool Interconnection Project (Main Tool & Module) | 439 | P |  | Click Copers Monthly rental | 45203 | x | [7 empty] | PR Approved | PO Approved | PR R1: No PR Email, No Supporting Documents/Wrong project |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Labor |  |  | Others |  |  | USC23C055 | USC2310004A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 437 | P |  | General Labor | 2023/10/4 2023/11/14 | [8 empty] | PR Approved | PO Approved | PR R1:Return by Purchaser./ Outdated request. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2405108A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 4158 | C |  | Mobile Storage Container Combo Office for HK | 45430 | [8 empty] | PR Approved | PO Approved | PR R1: Zero out. Change vendor | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | Housekeeping | 0 |  | Base-Build | 0 | 0 | USC23C002 | USC2309044A | 0 | F21P1-0404_H_Hallway plate install_MICU | 433 | P | -01 | Manpower Pay for 7 General Labor, 1 fork lift, and 2 carpenters | 45196 | 2023/10/17 2024/2/27 | -34400 | 34400 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PO R1:Contract changed to RS Payroll |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 2704 | -2704 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310013A | 0 | Tool Interconnection Project (Main Tool & Module) | 446 | P |  | Click Copers Monthly rental | 45204 | x | [7 empty] | PR Approved | PO Approved | PR R1 :No PR Email, No Supporting Documents/Wrong |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Others | AMHS | Material |  |  | AMHS |  |  | USC22C025 | USC2309043A | 0 | AMHS TSMC Instrustructure and Branch Circuits | 431 | P |  | Manpower Pay for AMHS Infrastructure and Branch Circuits | 45196 | 2023/10/28 2024/01/24 | -6000 | 6000 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PO R1:change supplier name from Hua Yi to RSPS |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USC2309038A | 0 | F21P1 Chemical & WCCS package | 426 | P | -01 | Manpower Pay Qty, 1 Pipe Fitter | 45196 | 2023/10/17 2024/3/7 | -36800 | 36800 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PO R1:Change of Contractor to RS Payroll |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309035A | 0 | Tool Interconnection Project (Main Tool & Module) | 423 | P |  | KPE602-T HYC ELECTRICAL/MECHANICAL | 2023/9/23 2024/8/30 | 2023/11/11 2024/9/5 | -90000 | 90000 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: Case Closed |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | 0 | CDS | Chemical | 0 | 0 | USC24C005 | USCSB2405133A | 0 | Chemical & WCCS B Side Project | 4161 | C |  | (MA0240028A)TSMC F21P1_B HPM 20 UPW 配管(SDS) | 2024/5/23 2024/6/22 | [8 empty] | PR Approved | PO Approved | PR R1:As per Johnny wan return this PR,and find alternative supplier. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23B002 | USC2309026A | 0 | Tool Interconnection Project (Main Tool & Module) | 415 | P |  | 18-8 Stainless Steel Hex Head Screw, 3/8"-16 Thread Size, 1" Long, packs of 25 | 2023/9/22 2023/11/8 | x | [7 empty] | PR Approved | PO Approved | Return due to incorrect PR items PR R1: Canceling the PR as there's currently no need per request. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309025A | 0 | Tool Interconnection Project (Main Tool & Module) | 414 | P |  | 90 Degree Angle Fitting | 2023/9/22 2023/11/8 | x | [7 empty] | PR Approved | PO Approved | PR R1: Canceling the PR as there's currently no need per request. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23B002 | USC2309024A | 0 | Tool Interconnection Project (Main Tool & Module) | 413 | P |  | 3/8-16 X3 ALL THRAD ROD 18-8 STAINLESS | 2023/9/22 2023/11/8 | x | [7 empty] | PR Approved | PO Approved | PR R1: Canceling the PR as there's currently no need per request. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2305005A | 0 | F21P1 AMAT Interconnection | 1929 | C |  | AMAT Interconnect Mechanical | 2023/5/3 2023/6/10 | x | -208944 | 208944 | [5 empty] | PR Approved | PO Approved | Cancelled to substitute with another contractor and same work scope. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310012A | 0 | Tool Interconnection Project (Main Tool & Module) | 445 | P |  | Click Copers Monthly rental | 45204 | x | [7 empty] | PR Approved | PO Approved | PR R1 :No PR Email, No Supporting Documents/Wrong |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | CDS | Chemical | 0 | 0 | USC24C005 | USCSB2405085A | 0 | Chemical & WCCS B Side Project | 4105 | C | -01 | CHEM_ Ryan Herco Flow Solutions_ PVDV+CPVC+PP | 5/14/2024 5/31/2024 | 2024/5/17 2024/6/5 | -108633.48 | 108633.48 |  |  |  |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | R1: Due to quote revised item context and quote number ,so as per engineer Janie to cancel the PR,and create new PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [8 empty] | 54316.74 |  |  |  | 54316.74 |  |  |  | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311020A | 0 | Tool Interconnection Project (Main Tool & Module) | 493 | P |  | MECHANICAL LABOR | 2023/11/8 2024/1/4 2024/8/14 | 2024/1/11 2024/8/15 | -1710.92 | 1710.92 | V |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1:Vendor name change from MICU Manpower/Hua Yi Constraction to RS Payroll Services and the amount changed from $7680 to $1710.. R2 : Order is closed to re-allocate funding sources. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2307043A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2212 | C | -01 | American Fence Company | 2023/7/11 2023/8/1 | 2023/7/27 2023/8/4 | -44137.08 | 44137.08 |  |  |  | V | American Fence Company of Arizona, Inc. | PR Approved | PO Approved | R1:Getting materials through Hua Yi Construction |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC22C036 | USCSB2304063A | 0 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1902 | C |  | KPE601-S TRIDENT MECHANICAL | 2023/4/22 2023/5/11 | x | -161673.85 | 161673.85 | [5 empty] | PR Approved | PO Approved | The budget number is incorrect/ Need to recalculate again. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | 0 | 0 | Chemical | 0 | 0 | USC24C005 | USCSB2404226A | 0 | Chemical & WCCS B Side Project | 3976 | C | -01 | P1B區Chemical SP2人力支援SP1施工 (SUS 12人/3月，CPVC 11人/1.5月) | 2024/4/30 2024/6/13 | 2024/5/8 2024/6/13 | -375221 | 375221 |  |  |  | V | Trusval Technology CO., LTD. | PR Approved | PO Approved | R1: As per PM Johnny to cancel this PR ,due to 2次配人力仍由TSMC所調配，相關費用會由TSMC直接與MIC對接，不需要透過信紘. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  |  | 150088.4 |  |  |  | 112566.3 |  |  |  | 112566.3 |  | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311013A | 0 | Tool Interconnection Project (Main Tool & Module) | 486 | P |  | Labor for level QC | 45233 | 2023/11/8 2024/8/6 | -3881.96 | 3881.96 |  |  |  | V | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | R1: VOID - Replaced with PO#USC2311079A |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Labor |  |  | Others |  |  | USC22C008 | USCSB2304070A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1909 | C | -01 | Starlink installation at TransPak warehouse for OSC | 2023/4/25 2023/05/09 | 2023/4/28 2023/05/10 | -4761 | 4761 |  | V |  |  | GeoTech Enterprises LLC | PR Approved | PO Approved | Cannot add new item, so cancel this PO to generate a new one |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | PSS | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2307046A | 0 | F21P1 Chemical & WCCS package | 2215 | C | -01 | Revised to remove labor cost for piping installed in room 38 & 39 H2O2. | 2023/7/12 2024/6/14 | 2023/8/25 2024/6/14 | -6444.96 | 6444.96 |  |  |  | V | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | This is a Change Order and corresponds to WO#USCSB2301045A to settle for wrong material order. Revision is to cancel scope as requested by PM. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | PSS | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2307045A | 0 | F21P1 Chemical & WCCS package | 2214 | C | -01 | Reroute drain lines per MIC (Ben) Sketches dated 5/18/23 | 2023/7/12 2024/6/14 | 2023/7/21 2024/6/14 | -21100.2 | 21100.2 |  |  |  | V | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | This is a Change Order and corresponds to WO#USCSB2301045A. Design change to reroute and rectify design error. Revision is to cancel scope as requested by PM. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2307044A | 0 | F21P1 Chemical & WCCS package | 2213 | C | -01 | MIC CDS HPM-FAB | 2023/7/12 2023/12/12 | 2023/9/14 2023/12/29 | -30723 | 30723 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2310057A | 0 | Tool Interconnection Project (Main Tool & Module) | 474 | P |  | Uline Utility Cart with Pneumatic Wheels - 45 x 25 x 37", Black | 2023/10/27 2024/3/29 | [8 empty] | PR Approved | PO Approved | PR R1: Zeroing out this PR per Purchaser and Michelle's request. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | 0 | Chemical | 0 | 0 | USC21C005 | USC2310055A | 0 | F21P1 Chemical & WCCS package | 472 | P |  | Manpower Pay for Mike Zipp 1 Pipe Fitter, 3 general labor, and 1 orbital welder. | 10/26/2023 8/24/2024 | 11/3/2023 8/29/2024 | -40000 | 40000 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: As per Hua Yi to close out the PO. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C005 | USC2310014A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 447 | P |  | Manpower Pay for General Labor for Shannon Pulcifer | 2023/10/5 2023/11/14 | [8 empty] | PR Approved | PO Approved | PR R1: Wrong project code. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | PSS | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2307042A | 0 | F21P1 Chemical & WCCS package | 2211 | C | -01 | Additional Scope for Chemical Drain transferred from Harder in Fab and Lorry | 7/11/2023 3/6/2024 | 8/7/2023 3/6/2024 | -276782.06 | 276782.06 |  |  |  |  | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | R1: As per PM:Johnny Wan,due to the engineering for the chemical system drain has been transferred from PSS to UMEC. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2310053A | 0 | Tool Interconnection Project (Main Tool & Module) | 470 | P |  | Manpower | 2023/10/26 2023/11/9 2024/8/12 | 2023/11/9 2023/11/13 2024/8/20 | -448 | 448 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: No longer needed PO. Close PO |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2307038A | 0 | F21P1 Chemical & WCCS package | 2207 | C | -01 | L20 GN2 Rework for EMT | 2023/7/11 2023/12/11 | 2023/7/20 2323/12/11 | -105634 | 105634 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Work done before turning T&M, Paid in Orginal PO 60% |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310038A | 0 | Tool Interconnection Project (Main Tool & Module) | 458 | P | -01 | ALL MEP INTERCONNECTION SOW | 45216 | 2023/10/25 2024/3/7 | -138802 | 138802 |  |  |  | V | Greenberry Industrial | PR Approved | PO Approved | Cancel request by Responsible Engineer as order "not delivered" |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310029A | 0 | Tool Interconnection Project (Main Tool & Module) | 454 | P |  | labor of KPE605-S cable pull | 2023/10/13 2023/11/14 | x | [7 empty] | PR Approved | PO Approved | PR R1: Order cancelled and replaced with another vendor. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2310024A | 0 | Tool Interconnection Project (Main Tool & Module) | 453 | P |  | ClickCopier Wide Format Printer-Purchasing the machine not leasing | 2023/10/12 2024/1/25 | X | [7 empty] | PR Approved | PO Approved | PR R1:This order was entered in error and needs to be VOIDED/DELETED per request. (Please see attached email thread.) |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310023A | 0 | Tool Interconnection Project (Main Tool & Module) | 452 | P |  | Manpower Pay for General Labor for Elsa Nieto/ Von Villas | 2023/10/12 2023/11/14 | x | [7 empty] | PR Approved | PO Approved | PR R1: Wrong project code. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2310020A | 0 | Tool Interconnection Project (Main Tool & Module) | 450 | P |  | Labor for level QC | 45210 | x | [7 empty] | PR Approved | PO Approved | Cancelled PR R1: Cancelled: by Kyle Came/needs to zero out |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC22C036 | USCSB2305006A | 0 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1930 | C |  | KPE602-S Trident | 2023/5/3 2023/5/4 2023/5/11 2023/5/25 | x | -161673.85 | 161673.85 | [5 empty] | PR Approved | PO Approved | R3:Budget isn't correct/ Need to be revised. R2:VOID PR Request USCSB2305006per Scott Weary. Budget numbers are being corrected to be correct. R1:Adjustment due to Tool KPE601-1 &Tool KPE602-2S are the same. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2307015A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2187 | C |  | Bay Alarm Company | 2023/7/6 2023/7/7 | x | [7 empty] | PR Approved | PO Approved | PR R1:This PR needs to be cancel/ APN |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC22C036 | USCSB2305008A | 0 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1932 | C |  | EUV interconnect cable tie | 2023/5/3 2023/8/1 | x | -9050 | 9050 | [5 empty] | PR Approved | PO Approved | PR R1:Supply is purchased online |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2407053A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 4452 | C |  | Material for P1B to bulk order Tubing | 2024/7/10 2024/7/24 | [8 empty] | PR Approved | PO Approved | PR R1:order canceled Steven wants a different vendor | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Base-Build | Site Expense | 0 | Shared Cost | Base-Build | 0 | 0 | USC21C003 | USC2301002A | 0 | F21P1 UPW | 261 | P |  | 2022 Polaris PRO XD Crew Diesel | 44932 | x | [7 empty] | PR Approved | PO Approved | Requested by Wanyu |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | 0 |  | Chemical | 0 | 0 | USC24C005 | USCSB2407002A | 0 | Chemical & WCCS B Side Project | 4404 | C |  | CED 化學系統線0627 | 2024/7/1 2024/7/4 | 45475 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1:As per engineer Johnny Wan to cancel the PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | WWT |  | 0 |  | WWT | 0 | 0 | USC24C006 | USCSB2407007A | 0 | WWT B side Project | 4409 | C |  | WWT Inventory Management System_2 year | 2024/7/1 2024/7/18 | [8 empty] | PR Approved | PO Approved | PR R1: Due to it can use the company's system,so as per purchasing team to cancel the PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT |  | 0 |  | WWT | 0 | 0 | USC24C006 | USCSB2407009A | 0 | WWT B side Project | 4410 | C |  | A+B side sump pump L10(labor + material) | 2024/7/2 2024/7/9 | [8 empty] | PR Approved | PO Approved | PR R1: AS per engineer Jim to cancel this order, WWT decide to have another vendor working on it. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USCSB2305051A | 0 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1976 | C |  | KPAP01-S LIT 1 UMEC | 2023/5/12 2024/9/9 | 2023/5/17 2024/9/17 | -87904.5 | 87904.5 | V |  |  |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | PO R1: Case Closed. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | 0 |  | WWT | 0 | 0 | USC24C006 | USCSB2407023A | 0 | WWT B side Project | 4452 | C |  | Materials for gasket on Fab B side | 2024/7/3 2024/7/4 | [8 empty] | PR Approved | PO Approved | PR R1:Duplicate one, return to cancel per engineer Jim. | [13 empty] | 0 | 1 | 0 | 0 | 0 | [74 empty] | -
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2407034A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 4433 | C |  | B Side EEW PPE for HK Power for 100 tools | 2024/7/9 2024/7/13 | [8 empty] | PR Approved | PO Approved | PR R1:change project code | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2305072A | 0 | F21_AZQR_Hookup_ Interconnection | 1994 | C |  | QR - NPT to NW/KF flange | 2023/5/16 2023/6/15 | x | -1258.11 | 1258.11 | [5 empty] | PR Approved | PO Approved | Identical to USCSB2305031 |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | 0 |  | WWT | 0 | 0 | USC24C006 | USCSB2407066A | 0 | WWT B side Project | 4484 | C |  | Chemical dump ( 1 month) | 2024/7/11 2024/7/24 | [8 empty] | PR Approved | PO Approved | PR R1:Cancelled per PM Andy confirmation | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C007 | USCSB2305009A | 0 | F21P1 Module Tool Interconnection PVD1-2 | 1933 | C |  | TSMC AZ F21 DI MAX | 45049 | 2023/5/6 2023/6/17 | -94680 | 94680 |  |  |  |  | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved | R1:Vendor formed a US-based company and requested for new entity to be trading counterparty |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT |  | 0 |  | WWT | 0 | 0 | USC24C006 | USCSB2407076A | 0 | WWT B side Project | 4492 | C |  | 美國WWT-P1A WRC PVC配管工程(2024/07/01~2024/09/30) | 2024/7/13 2024/7/23 | [8 empty] | PR Approved | PO Approved | PR R1: As per Engineer Jim to cancel this PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2305082A | 0 | F21P1 Chemical & WCCS package | 2003 | C | -01 | Lorry B RM 16 high zone clear PVC re-work due to clash with AAS duct main | 2023/5/19 2023/12/11 | 2023/5/24 2023/12/29 | -7920 | 7920 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | 0 | Shared Cost | Base-Build | 0 | 0 | USC21C003 | USC2208014A | 0 | F21P1 UPW | 213 | P |  | Extinguishers, Installation | 44793 | x | [7 empty] | PR Approved | PO Approved | PR Return - Identical to USC2208004A |  | Yi En Wong |  |  | Mirielli Terres | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | 0 |  | Chemical | 0 | 0 | USC24C005 | USCSB2407091A | 0 | Chemical & WCCS B Side Project | 4507 | C | -01 | CED 化學系統L10 Breaker | 45489 | 2024/7/17 2024/7/22 | -28545 | 28545 |  |  | V |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | WO R1: Confirmed by Mars the items have already been ordered in USCSB2407061A, so this order needs to be cancelled | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2305083A | 0 | F21P1 Chemical & WCCS package | 2004 | C | -01 | Lorry A & B sump pit piping re-work due to concrete pit elevation issue | 2023/5/19 2023/12/11 | 2023/6/2 2023/12/29 | -13032 | 13032 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2305084A | 0 | F21P1 Chemical & WCCS package | 2005 | C | -01 | LB2 NaOH system cpvc damage | 2023/5/19 2023/12/11 | 2023/5/24 2023/12/29 | -5520 | 5520 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2305085A | 0 | F21P1 Chemical & WCCS package | 2006 | C | -01 | Lorry B Room 40 Sump Pump missing PVDF spool to sump pit | 2023/5/19 2023/12/11 | 2023/5/24 2023/12/29 | -1187 | 1187 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2305086A | 0 | F21P1 Chemical & WCCS package | 2007 | C | -01 | Bridge pull box removal request by MIC | 2023/5/19 2023/12/11 | 2023/5/24 2023/12/29 | -3510 | 3510 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23B002 | USC2305007A | 0 | Tool Interconnection Project (Main Tool & Module) | 276 | P |  | SERV***TCXH2/4G | 2023/5/24 2023/7/22 | x | -23020 | 23020 | [5 empty] | PR Approved | PO Approved | PR R1:PM found a better pricing. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC22C036 | USC2305011A | 0 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 278 | P |  | KPAP01 ONSIGHT LIVE ELECTRICAL INTERCONNECT 2023/05/26` | 45073 | x | [7 empty] | PR Approved | PO Approved | PR R1: Void due to duplicate PR |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2305012A | 0 | Tool Interconnection Project (Main Tool & Module) | 279 | P |  | KPAP01 ONSIGHT LIVE ELECTRICAL INTERCONNECT 2023/05/26` | 45073 | x | [7 empty] | PR Approved | PO Approved | PR R1: Void due to duplicate PR |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23B002 | USC2305015A | 0 | Tool Interconnection Project (Main Tool & Module) | 282 | P |  | KPE601-S GAVALIN INSULATION INSTALLING 10-15' OF INSULATE DUCT INSULATION. | 2023/5/31 2023/6/23 | x | -160000 | 160000 | [5 empty] | PR Approved | PO Approved | Price went from $1,600.00 to $3,200.00. Originally 1 day and three workers. Ended up being 2 days with 3 workers to complete |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2309014A | 0 | Tool Interconnection Project (Main Tool & Module) | 405 | P |  | LAM Interconnect cable pull for KESTL1 (ETC1) | 2023/9/15 2024/8/14 | 2023/10/16 2024/8/15 | -4320 | 4320 |  |  | V |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1:Order is cancelled to release surplus budget. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309012A | 0 | Tool Interconnection Project (Main Tool & Module) | 404 | P |  | LAM Interconnect cable pull for KECOT2 (ETC2 | 2023/9/15 2024/8/15 | 45184 | [7 empty] | PR Approved | PO Approved | PR R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2309006A | 0 | Tool Interconnection Project (Main Tool & Module) | 401 | P |  | KPE602-S LIT 2 LABOR PAY | 9/7/2023 8/27/2024 | 10/5/2023 8/29/2024 | -5151 | 5151 |  |  |  |  | Trident Mechanical Services | PR Approved | PO Approved | R1: Case Closed |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2308045A | 0 | Tool Interconnection Project (Main Tool & Module) | 395 | P |  | 1N960 Barricade Tape, Red/Black, 1000 FT X 3 IN | 45169 | x | [7 empty] | PR Approved | PO Approved | PR NOT EXISTING IN SYSTEM PR Invalid |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | W-H2SO4 |  | 0 | WWT | WWT | 0 | 0 | USC21C014 | USCSB2405175A | 0 | F21P1 WH2SO4 | 4203 | C |  | WSR tool | 2024/5/30 2024/7/4 | [8 empty] | PR Approved | PO Approved | PR R1:As per engineer Jim to cancel the PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [71 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Chemical |  | 0 | 0 | Chemical | 0 | 0 | USC24C005 | USCSB2405187A | 0 | Chemical & WCCS B Side Project | 4230 | C | -01 | (MA0240031A)TSMC F21P1_B HPM Material quotation | 45443 | 2024/6/4 2024/6/18 | -437475.16 | 437475.16 | V |  |  |  | MornstAir Inc. | PR Approved | PO Approved | R1: As per purchasing team David to revise the vendor to Chern shuo,so close this PR and add new PR for this order. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C032 | USCSB2305031A | 0 | F21_AZQR_Hookup_ Interconnection | 1954 | C |  | QR - NPT to NW/KF flange | 45056 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23B002 | USC2307011A | 0 | Tool Interconnection Project (Main Tool & Module) | 345 | P |  | FORD TRANSIT-350 15 PASSENGER VAN | 45135 | 2023/8/16 2023/09/07 | -50000 | 50000 |  |  |  |  | MCVT Motors Inc dba Camelback Ford Lincoln | PR Approved | PO Approved | R1:The original van was sold to others and we will need to purchase from another vendor. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C025 | USCSB2305034A | 0 | F21P1 Lam Interconnection | 1957 | C |  | Wire lugs/Terminals | 45056 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23B002 | USC2306044A | 0 | Tool Interconnection Project (Main Tool & Module) | 328 | P |  | KPOCT5 LIT3 CUTTING EDGE MANUFACTURING | 45094 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C029 | USCSB2305038A | 0 | EBO21- Tool interconnection | 1961 | C | -01 | 3/8" HT PVC Pressure hose (8M) | 45057 | 2023/5/16 2023/6/17 | -414 | 414 |  |  |  |  | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved | Vendor requested change to a US subsidiary for US transactions. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC22C036 | USCSB2305039A | 0 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1963 | C |  | Armaflex 7/8 x1/2 | 45057 | 45070 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306017A | 0 | Tool Interconnection Project (Main Tool & Module) | 302 | P |  | Interconnect Material (5 Tools-KPE602-S,KPE60303.KPE604-S,KPE605-S, & KPE606-S) | 45084 | x | [7 empty] | PR Approved | PO Approved | Stop and Cancelled per email from Joel Chen |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2306016A | 0 | Tool Interconnection Project (Main Tool & Module) | 301 | P |  | Kable Kontrol Black Zip Ties | 45084 | x | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical |  | 0 | CDS | Chemical | 0 | 0 | USC24C005 | USCSB2406082A | 0 | Chemical & WCCS B Side Project | 4319 | C |  | FAB Chemical Observation - LSW | 45457 | [8 empty] | PR Approved | PO Approved | PR R1:Change the budget code. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  |  | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2306011A | 0 | Tool Interconnection Project (Main Tool & Module) | 296 | P |  | KPAP01 ONSIGHT LIVE ELECTRICAL INTERCONNECT | 45083 | x | [7 empty] | PR Approved | PO Approved | Voided per email June 11, 2023 8:33 PM from Ian |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23B002 | USC2305018A | 0 | Tool Interconnection Project (Main Tool & Module) | 285 | P |  | 18AWG 3C SHIELD 100F- MULTI-CONDUCTOR CABLES | 2023/5/31 2023/6/10 | x | -1901.23 | 1901.23 | [5 empty] | PR Approved | PO Approved | Revise project budget code from Project B to Project C |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311019A | 0 | Tool Interconnection Project (Main Tool & Module) | 492 | P |  | 1 welder welding flanges onto exhaust adapters. Total of 4 flanges | 2023/11/8 2024/8/15 | 2023/11/17 2024/8/15 | -840 | 840 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1. Budget was not used and so released. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311022A | 0 | Tool Interconnection Project (Main Tool & Module) | 495 | P |  | MECHANICAL LABOR | 2023/11/9 2024/8/14 | 2023/12/12 2024/8/15 | -1046.25 | 1046.25 |  |  | V |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | R1 - Release excess budget to user team. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2402217A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 3644 | C | -01 | WWT LSR SUS material | 2024/2/22 2024/3/1 | 2024/2/24 2024/3/9 | -4915.2 | 4915.2 |  |  |  |  | Ferguson Enterprises, LLC | PR Approved | PO Approved | Incorrect order placed |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC23C045 | USCSB2403175A | 0 | WWT Change Order (Piping) | 3872 | C |  | YAHO T&M A side work from 11/2023-05/2024 | 2024/3/16 2024/3/26 | [8 empty] | PR Approved | PO Approved | PR R1: Due to budget issue,so need to change the budget code and cancel this PR. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2403095A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 3797 | C |  | WWT Fab LB2 Missing Rack Column 6 | 2024/3/9 2024/3/13 | [8 empty] | PR Approved | PO Approved | PR R1: As per engineer Manuel to change the vendor and cancel this PR. |  | 0 |  |  |  | 0 | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401079A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 699 | P |  | Electrical cable pull for KESTL4 | 1/26/2024 8/10/2024 | 2/28/2024 8/20/2024 | -3806.76 | 3806.76 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2403109A | 0 | F21P1 Chemical & WCCS package | 3811 | C |  | CDS CO2 Swivel Adapter | 2024/3/12 2024/3/19 | 45365 | [6 empty] | Aidant Fire Protection | PR Approved | PO Approved | PR R1: As per Jeremiah Healy and Harvey Pinder to cancel the PR. |  | Tiong Sheng Poh | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2403126A | 0 | F21P1-0404_H_Hallway plate install_MICU | 3828 | C |  | 3rd MMI tile alignment T&M | 2024/3/13 2024/3/15 | [7 empty] | 0 | PR Approved | PO Approved | PR R1:Change project code | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C004 | USCSB2308007A | 0 | F21P1 Module Tool Interconnection CMP1 | 2310 | C |  | PFA reducers for AMAT CMP KMOPA2-C, KMOPA5-C, KMOPAB-C | 2023/8/2 2023/8/9 | x | [7 empty] | PR Approved | PO Approved | RETURN & CANCEL R1:no Longer need product |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | 0 | Low Voltage | Low Voltage | 0 | 0 | USC21C013 | USCSB2303085A | 0 | F21P1 AMC THC Monitoring System | 1822 | C | -01 | Gas cylinders | 2023/3/23 2023/4/14 | 2023/3/30 2023/4/14 | -19845.6 | 19845.6 |  |  |  | V | Matheson Tri-Gac Inc. | PR Approved | PO Approved | Cancelled because of lead time |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C003 | USCSB2303092A | 0 | F21P1 Module Tool Interconnection CVD | 1829 | C |  | gas line pipe and manual valve | 2023/3/24 2023/8/1 | x | -31180 | 31180 | [5 empty] | PR Approved | PO Approved | PR R1:Per purchaser's request, this PR had been replaced with USC2305002, USC2305003 and USC2305004 to cut 50% cost of purchase. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403173A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3870 | C | -01 | CONNECTOR and ADAPTOR | 45367 | 2024/3/18 2024/3/20 | -137.14 | 137.14 |  |  |  | V | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: The purchase was completed but not complied with the purchasing policy; Engineering team purchased via personal credit card |  | Kuan-Chung Su | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2307138A | 0 | F21P1 Chemical & WCCS package | 2300 | C | -01 | Sump pits and sump pump processing | 2023/7/29 2023/12/12 | 2023/8/3 2023/12/29 | -11319 | 11319 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403079A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3782 | C |  | PG19 Cable gland for HK Power | 2024/3/7 2024/3/12 | [8 empty] | PR Approved | PO Approved | PR R1:user request | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2307137A | 0 | F21P1 Chemical & WCCS package | 2299 | C | -01 | H20A CDA GN2 changes and additions | 2023/7/29 2023/12/12 | 2023/8/3 2023/12/29 | -123398 | 123398 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401051A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 673 | P |  | Cable pull KETRTE 12/6/2023-CGS | 1/20/2024 8/11/2024 | 1/23/2024 8/21/2024 | -645.72 | 645.72 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | 0 | 0 | WWT | 0 | 0 | USC21C004 | USCSB2303102A | 0 | F21P1 WWT package （USA EQ-FRP tank) | 1839 | C |  | Triazole FRP tanks | 2023/3/30 2023/4/22 | x | -290349.47 | 290349.47 | [5 empty] | PR Approved | PO Approved | Cancelling this PR based on PM's request |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C036 | USCSB2403225A | 0 | F21P1 AMAT Interconnection | 3920 | C |  | THHN Insulated Metallic Cable | 2024/3/22 2024/4/13 | [8 empty] | PR Approved | PO Approved | PR R1:Pr no longer needed |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403231A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3924 | C |  | 20' & 40' storage containers for HK Power team | 2024/3/22 2024/8/22 | [8 empty] | PR Approved | PO Approved | PR R1:Close | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Equipment | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2303104A | 0 | F21P1 UPW | 1841 | C | -01 | UPW Panel design change (Fuse holder) | 2023/3/30 2023/4/8 | 2023/4/3 2023/4/10 | -41131.38 | 41131.38 |  |  |  |  | Radwell International LLC | PR Approved | PO Approved | UPW Plan C Fuse Holder, TSMC additional PO requested 2023/04/10 Cancelled by TSMC |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2403234A | 0 | F21P1 Module Tool Interconnection ETC1-3 | 3927 | C |  | Modcule CIP Create ad installed E- Sensors at DAQ Box on 7 tools | 2024/3/23 2024/9/17 | 2024/3/29 2024/9/17 | -7367.23 | 7367.23 | V |  |  |  | Commercial Comm and Electric Inc | PR Approved | PO Approved | PO R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Tiong Sheng Poh | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC24B002 | USC2401030A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 653 | P |  | 1 welder for 1 day/8 hrs. for welding flanges onto 4" exhaust adapters (7 total) for TOOL ID#- KDANTA, KDPOT4, KDPOT5, KDEPT1 (2), KDEPT4 (2) | 1/16/2024 8/13/2024 | 1/22/2024 8/21/2024 | -448 | 448 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | R1: PO never was used. Needs to be deleted |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403089A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3791 | C |  | Cable Tray Clamps for HK Power trade | 2024/3/8 2024/3/13 | 45364 | [7 empty] | PR Approved | PO Approved | PR R1:Change QTY to 10000 | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401090A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 707 | P | -01 | Lit 2: KPE604-S: RF Cable Tray Mesh Cover Installation | 45321 | 2024/1/31 2024/5/11 | -5080.32 | 5080.32 |  |  | V | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | PR R1: No longer use CCE |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311023A | 0 | Tool Interconnection Project (Main Tool & Module) | 496 | P | -03 | Labor | 2023/11/9 2023/11/20 2023/12/11 | 2023/11/11 2023/11/21 2023/12/14 2023/12/18 | -3840 | 3840 | V |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PO R3:Supplier Change PO R1:Unit Price Change per Cost Book PO R2: Price Change per Actual Work Timecard |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Equipment |  |  | Others |  |  | USC23C063 | USCSB2402271A | 0 | F21P1-0423_H_T&M Hardware_MICU | 3696 | C | -01 | For Plastic system storage | 2/28/2024 4/2/2024 | 2/29/2024 4/6/2024 | -10909.18 | 10909.18 |  |  |  |  | U-Line Corporation | PR Approved | PO Approved | R1: per purchasing team request, change to new PR: USCSB2404003 |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2402220A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 3647 | C | -01 | WWT LSR Small SUS material | 2024/2/22 2024/3/5 | 2024/2/27 2024/3/5 | -25804 | 25804 |  |  |  |  | Ferguson Enterprises, LLC | PR Approved | PO Approved | R1: As per engineer Cindy Fan to cancel the order and will issue another order in lieu. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402010A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 737 | P |  | Electrical cable pull for KESDL2 and KESTL2. | 2/2/2024 8/10/2024 | 3/4/2024 8/20/2024 | -805 | 805 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402009A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 736 | P |  | KEPOL4 + ETC1 + Main Tool + Interconnect 1/30-1/31/2024 | 45324 | 2024/3/21 2024/814 | -2944 | 2944 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | PR R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Kuan-Chung Su | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2402008A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 735 | P |  | KESTL6 in house manpower labor for Interconnection power and signal | 45324 | 2024/3/7 2024/8/14 | -286.12 | 286.12 |  |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1:CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | 0 |  | Base-Build | 0 | 0 | USC23C056 | USCSB2308047A | 0 | Fab LB2 Trench Cleaning | 2345 | C | -01 | FAB Building LB2 Trench Clean | 2023/8/8 2024/3/15 | 2023/8/16 2024/3/19 | -142659.2 | 142659.2 |  |  |  |  | Handy Technology Corp. | PR Approved | PO Approved | PR R1: Handy Tech had been expelled from TSMC site last year and this PO might already billed to another PO due to T&M contract. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | UPW | Material | 0 | UPW | UPW | 0 | 0 | USC21C003 | USCSB2303056A | 0 | F21P1 UPW | 1796 | C |  | UPW EQ labels | 2023/3/15 2023/4/21 | x | -10440.67 | 10440.67 | [5 empty] | PR Approved | PO Approved | Order cancelled and replaced with another vendor |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C005 | USCSB2308043A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 2341 | C |  | DIFF1: 16 TOOLS – LABOR/MATERIAL FOR GALVANIZED DUCTS/ELBOWS BLOWER BOX | 2023/8/8 2023/12/5 | [8 empty] | PR Approved | PO Approved | PR R1:RESUBMIT AS STREIMER IN POS UNDER USC23B002 |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2308041A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 2339 | C |  | DIFF1: Orientation Cost for 8395 – 2 HRS & OSIP Orientation – 8 HRS | 2023/8/8 2023/8/24 | x | [7 empty] | PR Approved | PO Approved | Voided per email dated 8/8 from Rosa Brual. Training cost will not be reimbursed. R1:MICU does not cover 8395 & OSIP orientation |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2303064A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1803 | C |  | WWT Lab funiture | 2023/3/16 2023/4/12 | x | -40316.43 | 40316.43 | [5 empty] | PR Approved | PO Approved | To adjust for new items and lower labor cost |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401091A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 708 | P | -01 | Lit 2: KPE605-S: RF Cable Tray Mesh Cover Installation | 45321 | 2024/1/31 2024/5/11 | -5080.32 | 5080.32 |  |  | V | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | PR R1: No longer use CCE |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403013A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3721 | C | -01 | tools for calibration for HK power system | 45352 | 2024/3/13 2024/3/20 | -2239.66 | 2239.66 |  |  |  |  | Border State Industries, Inc. | PR Approved | PO Approved | PO R1:change to amazon because account is still on hold |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Material |  |  | Others |  |  | USC23C047 | USCSB2308029A | 0 | F21P1 HK Seismic Installation | 2330 | C |  | QR,EBO seismic installation | 2023/8/5 2024/6/7 | 2023/8/11 2024/7/4 | -70953.81 | 70953.81 |  |  |  |  | Greenberry Industrial | PR Approved | PO Approved | R1: Work area constraint affect quote |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401094A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 711 | P | -01 | KPE607-S RF Cable Tray Mesh Cover Installation | 2024/1/30 2024/5/13 | 2024/2/1 2024/5/13 | -5080.32 | 5080.32 |  |  | V | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | PR R1: No longer use CCE |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC21C011 | USCSB2403041A | 0 | F21 TMAH System | 3748 | C | -01 | WWT - LSR(i) Scope | 2024/3/5 2024/4/27 | 2024/3/16 2024/5/7 | -247423 | 247423 |  |  |  |  | BMWC Constructors, INC. | PR Approved | PO Approved | R1: As per engineer Jim to cancel the PR. |  | Yikang Wang |  |  |  | 0 | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401093A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 710 | P | -01 | KPE606-S Labor | 2024/1/30 2024/5/13 | 2024/2/1 2024/5/13 | -5080.32 | 5080.32 |  |  | V | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | PR R1: No longer use CCE |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup | Material |  |  | Others |  |  | USC23C055 | USCSB2403058A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3763 | C |  | Red and blue cable tie for high pressure hose for HK PCW trade | 2024/3/6 2024/8/22 | [8 empty] | PR Approved | PO Approved | PR R1:Close | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C005 | USCSB2303067A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 1806 | C |  | QR lab cable tray | 2023/3/16 2023/3/24 | x | -15058.8 | 15058.8 | [5 empty] | PR Approved | PO Approved | APEX cannot complete this order/Giving the scope to CED |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403072A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3776 | C |  | desk mats in the laydown area for materials and tools to prevent damage to the floor shared by all HK systen | 2024/3/7 2024/3/13 | [8 empty] | PR Approved | PO Approved | PR R1: change vendor zero out | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC24B002 | USC2401020A | 0 | Tool Interconnection Project (Main Tool & Other Vendors) | 644 | P |  | Interconnect cable pull for KETRT4 (ETC3), Includes initial interconnect cable pull, Ewah considered & implemented suggestions during our initial installation of interconnect work. Includes interconnect rework. RS 11/29-12/1 | 2024/1/12 2024/8/12 | 2024/1/17 2024/8/12 | -2280.52 | 2280.52 |  |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC23C045 | USCSB2403268A | 0 | WWT Change Order (Piping) | 3961 | C |  | B side remaining pipe MU can't supply . | 2024/3/28 2024/3/30 | [8 empty] | PR Approved | PO Approved | PR R1:Need to change the budget code, so need to cancel this PR |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | 0 | 0 | Base-Build | 0 | 0 | USC23C045 | USCSB2403269A | 0 | WWT Change Order (Piping) | 3962 | C |  | welding machine 6300 fix part. | 2024/3/28 2024/4/23 | [8 empty] | PR Approved | PO Approved | PR R1: As per Jim to cancel the PR. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Equipment | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2304040A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 1880 | C |  | WWT lab quality analyzer | 2023/4/17 2023/6/14 | x | -6555 | 6555 | [5 empty] | PR Approved | PO Approved | Cancelling this PR per Kate Wu's request, this item will be added to the quote of another vendor. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | Hot DI | Material | 0 | 0 | Chemical | 0 | 0 | USC23C012 | USCSB2307086A | 0 | F21P1 Hot DI Machine Hookup | 2252 | C | -01 | Hot DI long lead parts from Taiwan | 45135 | 2023/7/28 2023/7/29 | -5680.5 | 5680.5 |  | V |  |  | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | R1: Change item 8 size, cancel this PR, and submit a new PR. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Labor | 0 | 0 | Chemical | 0 | 0 | USC21C005 | USC2311080A | 0 | F21P1 Chemical & WCCS package | 548 | P |  | manpower - electricians | 2023/11/29 2024/4/27 | [8 empty] | PR Approved | PO Approved | PR R1:New PR was created USCSB2404034 |  | 0 | [11 empty] | 0 | 1 | 0 | 50152.53 | -50152.53 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 750 | [9 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2311078A | 0 | Tool Interconnection Project (Main Tool & Module) | 546 | P | -01 | E-OPS Manpower for cable pull (Robert Nelson) | 45258 | 2023/12/5 2024/2/7 | -3297.75 | 3297.75 |  |  |  |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | PO R1:The PO is incorrect and need to be issued again according to E-OPS. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Material | 0 | 0 | Chemical | 0 | 0 | USC24C005 | USCSB2404115A | 0 | Chemical & WCCS B Side Project | 4100 | C |  | [PFD] CABLE TRAY FLOOR L10 | 2024/4/15 2024/4/19 | [8 empty] | PR Approved | PO Approved | PR R1:Per request from contractor via 4/17 email and confirmed with Johnny Wan, withdrawing it | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2404123A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 4108 | C |  | A business trip to TSMC in the US | 2024/4/16 2024/5/3 | [8 empty] | PR Approved | PO Approved | PR R1:wrong requisition, should be UPW's scope under USC21C003, please cancel this and will re-issue | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Labor | 0 | 0 | WWT | 0 | 0 | USC21C009 | USCSB2404140A | 0 | F21P1 WWT package (Installation and 2 batch tanks) | 4124 | C | -01 | WWT - RO Membrane Installation LB2 P1 A side | 2024/4/18 2024/4/26 | 2024/4/19 2024/4/26 | -13950.95 | 13950.95 |  |  |  | V | Marquis Construction Services LLC | PR Approved | PO Approved | Request to cancel by engineering team | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Hookup | Warehouse |  |  |  | Others |  |  | USC22C008 | USCSB2404144A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 4128 | C | -01 | M0495 Foundation manufacture | 2024/4/18 2024/5/28 | 2024/4/25 2024/5/29 | -3733 | 3733 |  |  | V | V | Milling Machinery, Inc. | PR Approved | PO Approved | PR R1: Zero out the PR to release the budget per instructed | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | VOC | Material | 0 | VOC | Low Voltage | 0 | 0 | USC22C013 | USCSB2404152A | 0 | F21P1 QR Lab Security & CCTV | 3949 | C |  | VOC duct flange insulation | 2024/4/19 2024/7/9 | [8 empty] | PR Approved | PO Approved | PR R1:Replaced by Petrochem USCSB2407020A | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [12 empty] | 24852 |  |  |  | - |  | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23C036 | USCSB2307069A | 0 | F21P1 AMAT Interconnection | 2236 | C | -01 | Subject install Cable tray dividers and insulated cable clamps to meet NEC Electrical code on took KCBDA1 | 2023/7/15 2023/8/10 | 2023/7/21 2023/8/11 | -2500 | 2500 |  |  |  | V | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Hookup |  |  |  | Others |  |  | USC23C055 | USCSB2403274A | 0 | F21P1-0404_H_labor for 50 tools_MICU | 3967 | C | -01 | Office supplies for tool hookup department | 45379 | 45387 | -905.81 | 905.81 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | R1:Zero out. go through HR |  | Ta Wei Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Warehouse | Equipment |  |  | Others |  |  | USC22C008 | USCSB2304042A | 0 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1882 | C |  | Cubicle Partitions for Tool Team | 2023/4/18 2023/4/28 | x | -15000 | 15000 | [5 empty] | PR Approved | PO Approved | Change of source of funding from Subcontract budget to USH |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2311032A | 0 | Tool Interconnection Project (Main Tool & Module) | 506 | P | -01 | KPI401-S (LIT 1) - Cable Pulls & Tray Install - HYC | 45244 | 45247 | -50000 | 50000 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: HYC demobilizing, installed tray but did not and will not install the cabling |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2311030A | 0 | Tool Interconnection Project (Main Tool & Module) | 504 | P |  | 1 welder for 6, 4"flanges, and 4 6" flanges to be welded onto adapters | 45240 | 2023/11/28 2024/8/14 | -448 | 448 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | PR R1: PO was never used. Needs to be deleted |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | 0 | 0 | Base-Build | 0 | 0 | USC21C006 | USCSB2404193A | 0 | F21P1 Slurry package | 4172 | C |  | Trailer 40 Access Control System Installation | 45407 | [7 empty] | Bay Alarm Company | PR Approved | PO Approved | PR R1: As Per Eric to cancel this PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | 0 | 0 | Base-Build | 0 | 0 | USC21C006 | USCSB2404194A | 0 | F21P1 Slurry package | 4173 | C |  | Trailer 40 Electrified Lock Work | 45407 | [7 empty] | Bay Alarm Company | PR Approved | PO Approved | PR R1: As Per Eric to cancel this PR. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | MIMO/Rigging |  |  | Others |  |  | USC22C036 | USCSB2304062A | 0 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1901 | C |  | KPE601-S MMI RIGGING AND DELIVERY | 2023/4/22 2023/8/1 | 45054 | -24500 | 24500 |  |  |  |  | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C011 | USCSB2404200A | 0 | F21 TMAH System | 4179 | C | -01 | WWT-ammonia 1000 ppm standards solution for stripper | 45408 | 2024/4/26 2024/5/17 | -147.3 | 147.3 |  |  |  |  | Midland Scientific, Inc. | PR Approved | PO Approved | R1: Change supplier | [13 empty] | 136.02 | 1 | -136.02 | 0 | -136.02 | 0 | 136.02 | [53 empty] | 0 |  | 0 | [12 empty] | 22.1 |  | 0 |  | - | 0 | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC24C006 | USCSB2404205A | 0 | WWT B side Project | 3962 | C | -01 | WWT PP PN10 D140 Pipes_20240425 (B Side) | 2024/4/27 2024/5/15 | 2024/4/30 2024/5/15 | -21853.2 | 21853.2 | V |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Items: As per engineer Cindy to cancel this PR | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0
Interconnection | interconnection | Material |  |  | Others |  |  | USC23C005 | USC2311085A | 0 | F21P1 Module Tool Interconnection DIF1-2 | 552 | P |  | For the PO renewal of Daniel Dircio, in the Project Coordinator (Tool Interconnect) position Project Coordinator. 6 month PO | 2023/11/30 2023/12/8 | X | [7 empty] | PR Approved | PO Approved | PR R1:the project code was incorrect |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C003 | USCSB2404094A | 0 | F21P1 Module Tool Interconnection CVD | 4081 | C | -01 | Ball valves KCOLA1 KCOLA2 KCOLA3 | 45393 | 2024/4/11 2024/4/16 | -2589 | 2589 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | PO R1:PC no longer wants |  | Ta Wei Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23B002 | USC2312001A | 0 | Tool Interconnection Project (Main Tool & Module) | 553 | P |  | ELECTROLYTE_GOLD: Potassium Hydroxide Solution 100ml | 2023/12/1 2023/12/11 | X | [7 empty] | PR Approved | PO Approved | PR R1 :VOID - Tool HookUp already submitted the same quote. Ok to void per TL. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23B002 | USC2312007A | 0 | Tool Interconnection Project (Main Tool & Module) | 559 | P |  | Manpower | 2023/12/2 2024/8/12 | 2023/12/4 2024/8/13 | -4134 | 4134 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: PO was created but never used. Needs to be deleted |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection |  |  |  | Others |  |  | USC23C016 | USCSB2403277A | 0 | F21P1 Mattson Interconnection | 3970 | C |  | MATTSON: KEPRM6-8: PFA CLEAR TUBE FOR SIGNAL CABLE. | 2024/3/29 2024/4/23 | [8 empty] | PR Approved | PO Approved | PR R1 :INCORRECT PROJECT CODE, S/B USC24C009 | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312084A | 0 | Tool Interconnection Project (Main Tool & Module) | 627 | P |  | Interconnect cable pull for KECOL4 (ETC2) | 2023/12/23 2024/8/12 | 2024/1/2 2024/8/12 | -441.6 | 441.6 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312083A | 0 | Tool Interconnection Project (Main Tool & Module) | 626 | P |  | Interconnect cable pull for KECOL4 (ETC2) | 2023/12/23 2024/8/14 | 2023/12/30 2024/8/16 | -532.8 | 532.8 |  |  | V |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | R1 :Case closed to release excess amount budgeted for the order.. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312081A | 0 | Tool Interconnection Project (Main Tool & Module) | 624 | P |  | Interconnect cable pull for KETRT4 (ETC3), Includes initial interconnect cable pull, Ewah considered & implemented suggestions during our initial installation of interconnect work. Includes interconnect rework. CGS 11/29-12/1 and 12/4-12/21. | 2023/12/23 2024/8/15 | 2024/1/20 2024/8/15 | -13454.31 | 13454.31 |  |  | V |  | CGS Global Support, LLC | PR Approved | PO Approved | R1 : Order cancelled to release allocated budget. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Material |  |  | Others |  |  | USC23C004 | USCSB2307114A | 0 | F21P1 Module Tool Interconnection CMP1 | 2278 | C | -01 | SINGLE TILE BARRICADE for CMP | 45133 | 2023/8/7 2023/8/31 | -3225.24 | 3225.24 |  |  |  |  | Metzfab Industries | PR Approved | PO Approved | R1:Superceded and replaced by USCSB2308156A |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2304010A | 0 | F21P1-0404_H_Hallway plate install_MICU | 1851 | C |  | DUV foundation installation | 2023/4/6 2023/5/11 | 45033 | [7 empty] | PR Approved | PO Approved | There is a change of supplier for this work. This PR needs to be cancelled. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection |  |  |  | Others |  |  | USC23C009 | USCSB2404016A | 0 | F21P1 Module Tool Interconnection ETC1-3 | 4012 | C |  | CCE DAQ E-SENSOR(S) INSTALLATION | 2024/4/2 2024/8/29 | [8 empty] | PR Approved | PO Approved | PR R1:Case Closed | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312059A | 0 | Tool Interconnection Project (Main Tool & Module) | 605 | P |  | KETRT7- Cut out 7 holes. Install 7 gromets and terminate 7 cables to AC box | 2023/12/16 2024/8/12 | 2023/12/18 2024/8/13 | -286 | 286 |  |  |  | V | San Tan Fire, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312058A | 0 | Tool Interconnection Project (Main Tool & Module) | 604 | P |  | LAM Interconnect cable pull for KESTL7 (ETC1) TSMC M.4/3.5 Lvl. L30 | 2023/12/15 2024/8/12 | 2023/12/15 2024/8/12 | -255.6 | 255.6 | V |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | Chemical | Harder | 0 | CDS | Chemical | 0 | 0 | USC21C005 | USCSB2307111A | 0 | F21P1 Chemical & WCCS package | 2275 | C |  | Lorry room 40 CCBTU#1 to room 41 Tank B piping design change | 2023/7/24 2023/8/2 | x | [6 empty] | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | PO Returned for Cancellation, per PM R1:Johnny Wan say this PO need to be cancel |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Hookup | Foundation | Labor |  |  | Others |  |  | USC23C002 | USCSB2304012A | 0 | F21P1-0404_H_Hallway plate install_MICU | 1853 | C |  | X-B3-EUV foundation installation | 2023/4/6 2023/5/11 | 45041 | [7 empty] | PR Approved | PO Approved | There is a change of supplier for this work. This PR needs to be cancelled. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2312050A | 0 | Tool Interconnection Project (Main Tool & Module) | 596 | P |  | Manpower Pay for KEMGL1 for WGN-star | 12/13/2023 8/27/2024 | 12/14/2023 8/29/2024 | -168 | 168 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | R1: Case Closed |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment |  |  | Others |  |  | USC23B002 | USC2312043A | 0 | Tool Interconnection Project (Main Tool & Module) | 590 | P |  | Rachel Smith - Installer | 12/12/2023 8/12/2024 | 12/19/2023 8/21/2024 | -732.5 | 732.5 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: PO never was used. Needs to be deleted |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | AMC THC | Equipment | 0 | Low Voltage | Low Voltage | 0 | 0 | USC21C013 | USCSB2404039A | 0 | F21P1 AMC THC Monitoring System | 4034 | C |  | F21 P1 WRC Building Flow meters & Temp installation engineering of stack | 2024/4/3 2024/4/5 | [8 empty] | PR Approved | PO Approved | PR R1:Per PM's request to cancel this order as the vendor needs to update the quote. |  | Ta Wei Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Outsourcing |  |  | Others |  |  | USC23B002 | USC2312035A | 0 | Tool Interconnection Project (Main Tool & Module) | 582 | P |  | workers for 3 days to install exhaust duct between L10 and LB1 for the TOOL KDPOT1 | 2023/12/8 2024/8/22 | 2023/12/8 2024/8/22 | -104 | 104 |  |  |  | V | Westerwood Global USA Corporation | PR Approved | PO Approved | PR R1: PO never was used. Need to be deleted |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312022A | 0 | Tool Interconnection Project (Main Tool & Module) | 571 | P |  | Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards KETRT7 | 2023/12/5 2024/8/14 | 2023/12/8 2024/8/15 | -6854 | 6854 |  |  | V |  | CGS Global Support, LLC | PR Approved | PO Approved | R1 : order is cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Interconnection | Interconnection | Labor |  |  | Others |  |  | USC23B002 | USC2312008A | 0 | Tool Interconnection Project (Main Tool & Module) | 560 | P |  | Manpower | 12/2/2023 8/12/2024 | 12/7/2023 8/20/2024 | -3312 | 3312 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: PO was created but never used. Needs to be deleted |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0
Base-Build | WWT | Material | 0 | 0 | WWT | 0 | 0 | USC21C004 | USCSB2306021B | 0 | F21P1 WWT package （USA EQ-FRP tank) | 2056 | C |  | WWT - Lab glassware (LS-1030070 FILTER SYSTEM, FRITTED GLASS) | 45083 | 45145 | [6 empty] | Laboratory Sales and Service | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 0 | 0 | 0

## pc_overview
TSMC 新工 | Type | Type2 | Project Number | Project Name | Item | Type22 | PO # | Rev | PO Description | PR Date | PO Date | Amount | Change Order | Original | Price Change --Reason for change 1 價格異動 2 項目異動 3 數量異動 4業主變更 | Item Change | Quantity Change | Client Request | Vendor/Subcontractor | PR 狀況備註 | PO 狀況備註 | Remark M2 | Remark Elaine | Payment Term | Incoterms | Warranty | 請購人 | 採購人 | OCIP Enrollment | PO Signed Back | PM | Budget Item | GMP | Form 5000 or 5005 | Lien Filed | Accumulated AP (Paid) | AP % | Balance Before Open Invoice | Open Invoice | Balance | Total Plan | Debit and Credit Card/ Previous | 102021 Real | 112021 Real | 122021 Real | 012022 Real | 022022 Real Urgent Payment | 022022 Real Regular | 032022 | 042022 | 052022 20th payment | 052022 5th payment | 062022 20th payment | 062022 5th payment | 072022 20th payment | 072022 5th payment | 082022 20th payment | 082022 5th payment | 092022 20th payment | 092022 5th payment | 102022 20th payment | 102022 5th payment | 112022 20th payment | 112022 5th payment | 122022 20th payment | 122022 5th payment | 012023 20th payment | 012023 5th payment | 022023 20th payment | 022023 5th payment | 032023 20th payment | 032023 5th payment | 042023 20th payment | 042023 5th payment | 052023 20th payment | 052023 5th payment | 062023 20th payment | 062023 5th payment | 072023 20th payment | 072023 5th payment | 082023 20th payment | 082023 5th payment | 092023 20th payment | 092023 5th payment | 102023 20th payment | 102023 5th payment | 112023 20th payment | 112023 5th payment | 122023 20th payment | 122023 5th payment | 012024 20th Payment | 012024 5th Payment | 022024 20th Payment | 022024 5th Payment | 032024 20th Payment | 032024 5th Payment | 042024 20th Plan | 042024 20th Payment | 042024 5th Plan | 042024 5th Paymen | 052024 20th Plan | 052024 20th Payment | 052024 5th Plan | 052024 5th Payment | 062024 20th Plan | 062024 20th Payment | 062024 5th Plan | 062024 5th Payment | 072024 20th Plan | 072024 20th Payment | 072024 5th Plan | 072024 5th Payment | 082024 Plan | 082024 20th Payment | 082024 5th Payment | 092024 Plan | 092024 20th Payment | 102024 Plan | 112024 Plan | 122024 Plan
Hookup | Warehouse |  | USC24C017 | MIC Glendale Warehouse Management | 1 | C | US2SB2409001A |  | Transpak Operational Invoice March-July | 45560 | 45572 | 2793603.82 | [6 empty] | Transpak, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2793603.82 | 0 | 2793603.82 | 0 | [73 empty] | - |  | -
Hookup | Warehouse |  | USC24C017 | MIC Glendale Warehouse Management | 2 | C | US2SB2409002A |  | Transpak Intrastate Transportation from August to December 2024 | 45562 | 45657 | 850000 | [6 empty] | Transpak, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 850000 | 0 | 850000 | 0 | [73 empty] | - |  | -
|  |  | USC24C017 | MIC Glendale Warehouse Management | 3 | C | US2SB2409003A |  | Uline | 45563 | 45565 | 4040 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4040 | 0 | 4040 | 0 | [75 empty] | -
|  |  | USC24C017 | MIC Glendale Warehouse Management | 4 | C | US2SB2410001A |  | Transpak Operational expense Aug-Dec 2024 | 45569 | 45575 | 3150000 | [6 empty] | Transpak, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3150000 | 0 | 3150000 | 0 | [75 empty] | -
|  |  | USC24C017 | MIC Glendale Warehouse Management | 5 | C | US2SB2410003A |  | Cable Tray Cleaning Project - Staffing | 45571 | 45575 | 23400 | [6 empty] | Masis Staffing Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23400 | 0 | 23400 | 0 | [75 empty] | -
|  |  | USC24C017 | MIC Glendale Warehouse Management | 6 | C | US2SB2410004A |  | 24/7 Security Service till 12/31/2024 | 45571 | 45575 | 110000 | [6 empty] | Allied Universal Security Services | PR Approved | PO Approved | [14 empty] | 0 | 0 | 110000 | 0 | 110000 | 0 | [75 empty] | -
|  |  | USC24C017 | MIC Glendale Warehouse Management | 7 | C | US2SB2410005A |  | Truck, Containers and Demurrage for Round-the-World Interstate Transportaion | 45574 |  | 1000000 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 1000000 | 0 | 1000000 | 0
|  |  | USC24C017 | MIC Glendale Warehouse Management | 8 | C | US2SB2410006A |  | Replenishment of PCW Filter for Glendale | 45576 |  | 4400 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 4400 | 0 | 4400 | 0
|  |  | USC24C017 | MIC Glendale Warehouse Management | 9 | C | US2SB2410007A |  | Transpak Cycle Count Project | 45576 | 45581 | 23555.3 | [6 empty] | Transpak, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 23555.3 | 0 | 23555.3 | 0
|  |  | USC24C017 | MIC Glendale Warehouse Management | 10 | C | US2SB2410008A |  | Masis Staffing Services | 45576 |  | 27979.97 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 27979.97 | 0 | 27979.97 | 0
|  |  | USC24C017 | MIC Glendale Warehouse Management | 11 | C | US2SB2410009A |  | WMS Hardware for Glendale Warehouse | 45580 |  | 79662.29 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 79662.29 | 0 | 79662.29 | 0
|  |  | USC24C017 | MIC Glendale Warehouse Management | 12 | C | US2SB2410010A |  | Enhance CCTV Coverage for Racks and Prefabs | 45580 |  | 19880 | [7 empty] | PR Approving | PR Applying | [14 empty] | 0 | 0 | 19880 | 0 | 19880 | 0
Base-Build | WWT |  | USC24C006 | WWT B side Project | 1 | C | US8SB2408001A |  | Electrical Hazards Training required for people working with or around electricity | 45518 | 45518 | 3975 | [6 empty] | LC LIND, LLC | PR Approved | PO Approved | [14 empty] | 3975 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 3975 | - |  | -
Base-Build | Speed Gate | Equipment | USC21C002 | TSMC AZ Temp Office Speed Gate | 14 | P0 | USC2107005A |  | Adopter and mount for speed gate | 44384 | 44399 | 78.17 | [6 empty] | Staples Inc. | PR Approved | PO Approved | Debit card paid (員工代墊款) | T/T 0 day (貨款員工代墊) | Cherry Chang |  |  | Chao Chia | Cherry Chang | NA |  | Henry |  | NA | NA |  | 78.17 | 1 | 0 | 0 | 0 | 0 | 78.17 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Speed Gate | Equipment | USC21C002 | TSMC AZ Temp Office Speed Gate | 15 | P0 | USC2107006A |  | Adaptor for speed gate and bults for mounting | 44384 | 44399 | 20.97 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | Debit card paid (員工代墊款) | T/T 0 day (貨款員工代墊) | Cherry Chang |  |  | Chao Chia | Cherry Chang | NA |  | Henry |  | NA | NA |  | 20.97 | 1 | 0 | 0 | 0 | 0 | 20.97 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Speed Gate | Material | USC21C001 | tsmc AZ Temporary Office Physical Security | 16 | P0 | USC2107007A |  | Furniture D (Metal gate壓邊條及配件) | 44384 | 44399 | 16.22 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Debit card paid (員工代墊款) | T/T 0 day (貨款員工代墊) | Cherry Chang |  |  | Chao Chia | Cherry Chang | NA |  | Henry |  | NA | NA |  | 16.22 | 1 | 0 | 0 | 0 | 0 | 16.22 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Speed Gate | Material | USC21C001 | tsmc AZ Temporary Office Physical Security | 17 | P0 | USC2107008A |  | Metal gate壓邊條及配件 | 44384 | 44399 | 119.93 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | Debit card paid (員工代墊款) | T/T 0 day (貨款員工代墊) | Cherry Chang |  |  | Chao Chia | Cherry Chang | NA |  | Henry |  | NA | NA |  | 119.93 | 1 | 0 | 0 | 0 | 0 | 119.93 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 18 | P | USC2108007A | -02 | tank,FRP | 44426 | 2021/8/27 2021/9/29 | 0 | -4096024 | 4096024 | V | V | V |  | Augusta Fiberglass Coating,Inc. | PR Approved | PO Approved | 10/12專案通知因原vendor無法配合T&C,故取消此訂單,將另找新供應商 Revo1 USD3,551,511(追加USD544,513) | PR取消 | Cherry Chang | - | - | Chia-Yi Chang | Cherry Chang | N |  | Matt |  | NA | NA |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 19 | P | USC2108008A | -02 | tank,FRP | 44427 | 2021/8/27 2021/9/29 | 0 | -2617784 | 2617784 | V |  | V |  | B&D Plastics, LLC | PR Approved | PO Approved | 10/14專案通知因原vendor無法配合T&C,故取消此訂單,將另找新供應商 Rev01US$2,595,884 (異動追加USD$22,000) | PR取消 | Cherry Chang | - | - | Chia-Yi Chang | Cherry Chang | N |  | Matt |  | NA | NA |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 20 | P | USC2109002A |  | tank,FRP | 44441 | 44449 | 1733380.86 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | 44491 | Henry |  | N | 5000 |  | 1733380.512 | 1 | 0.348 | 0 | 0.348 | 0 |  |  |  |  | 185254.72 |  | 18468.9 |  | 258067.11 |  | 189095.6655 |  | 215557.25 |  | 35447.54 |  |  |  | 442551.84 |  | 137921.28 |  |  |  | 55868.3865 |  |  |  | 0 | 156894.82 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 38253 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 21 | P | USC2109003A | -01 | Tank | 2021/9/4 2021/9/17 | 2021/9/13 2021/9/28 | 4120988.48 | 43208.01 | 4077780.47 | V |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | 44474 | Henry |  | N | 5000 |  | 4120988.4786 | 1 | 0.0014 | 0 | 0.0014 | 0 | [6 empty] | 305045.36 |  | 237956.17 |  | 437432.646 |  | 377511.99 |  | 458362.76 |  |  |  | 789001.51 |  | 320081.8436 |  |  |  | 524527.049 |  |  |  | 330555.71 |  |  |  |  | 0 | 255584.11 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 84929.33 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Speed Gate | Equipment | USC21C008 | F21P1 CCTV & Security | 22 | P | USC2109006A | -01 | Speed Gate | 44443 | 44461 | 0 | -30500 | 30500 |  |  |  |  | Gunnebo Entrance Control, Inc. | PR Approved | PO Approved | 11/18 因廠商無UR 認證,故cancel此單,並另找廠商 | PR取消 | Cherry Chang |  |  | Chih-Chien Hung | Cherry Chang | N |  | Martin |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 23 | P | USC2109012A | -01 | Diaphragm Valve | 2021/9/14 2021/11/13 | 2021/9/17 2021/11/13 | 379521.12 | -113568.82 | 493089.94 |  |  | V |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | Design change 11/22 收到採購會辦,業主變更設計(隔膜閥數量變少364>264) | 90% After Received-T/T 30days, 10% T/T 30 days (60days after acceptance) | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | N |  | Henry |  | N | 5000 |  | 379521.12 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 251576.5 |  |  |  |  | 53190.46 | [10 empty] | 74754.16 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 24 | P | USC2109014A |  | FIRST 22 CS TANKS | 44463 | 44477 | 4470815 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved | 追加WO:USCSB2202007(CS Tank changed order work) | 25 % upon submittal approval, 20% upon material purchase, 50% upon ready to ship, and 5% after delivered 60 days (NET-30 days). | Cherry Chang |  |  | Rui Ma | Cherry Chang | Y | 44482 | Henry |  | N | 5000 |  | 4470815 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 300151.72 | 232324.8 | 232828.66 |  | 313396.54 |  |  | 416886.5 | 739882.6 |  | 548302.62 |  | 826752 |  | 289892.87 |  | 341815.88 |  |  |  | 228580.81 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 25 | P | USC2109015A | -01 | tank,FRP | 2021/9/26 2021/11/5 | 2021/10/1 2021/11/16 | 305828 | 49948 | 255880 | V | V |  |  | HORIBA Instruments Incorporated | PR Approved | PO Approved | 11/10專案回覆待確認運費是否MICU負擔 11/16PO異動簽核中 | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | Cherry Chang | DDP | 24 months warranty after received. | Chia-Yi Chang | Cherry Chang | N |  | Matt |  | N | 5000 |  | 305828 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 305828 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 26 | P | USC2109019A | -01 | WASTE Tank (Last 5 tanks) | 2021/9/29 2021/11/4 | 2021/10/6 2021/11/5 | 42455.71 | 10875.14 | 53330.85 |  | V |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | 異動簽核中因為取消3個桶槽 | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | 2021/10/22 2021/11/16 11/9/2021 | Henry |  | N | 5000 |  | 0 | 0 | 42455.71 | 0 | 42455.71 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 6368.3565 |  |  |  | 6368.3565 |  |  |  | 6368.3565 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 27 | P | USC2110005A |  | UPW FRP Tank | 44481 | 44484 | 4000000 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | 取代USC210800A (Augusta Fiberglass Coating,Inc.) | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days) | Cherry Chang | EX-WORK/工廠價 | 1year after the acceptance is completed and transferred to the owner | Chia-Yi Chang | Cherry Chang | N | 44491 | Matt |  | N | 5000 |  | 3999999.9135 | 1 | 0.0865 | 0 | 0.0865 | 0 |  |  |  |  | 412671.45 |  | 232597 |  | 668190.35 |  | 384435.0585 |  | 556676.42 |  | 260321.426 |  |  |  | 567506.31 |  | 79695.219 |  |  |  | 507793.08 |  |  |  | 0 | 258517.22 |  |  |  | 0 | 71596.38 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 28 | P | USC2110015A | -01 | UPW FRP PP Lining Tanks | 2021/10/19 2021/11/18 | 2021/10/26 2021/11/22 | 2724480 | 160200 | 2564280 |  | V |  |  | An-Cor Industrial Plastics, Inc. | PR Approved | PO Approved | 新增附屬安全設備 11/22 收到異動會辦(防墜落系統&EXPORY施工) | Based on T&C | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | N | 44529 | Matt |  | N | 5000 |  | 2724480 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 885456 |  | 340560 |  |  | 296759 |  |  |  |  | 170879.5 |  |  |  | 230879.5 |  |  | 70439.75 |  |  |  |  | 0 |  | 295131.75 |  |  | 85439.75 | 170879.5 |  |  | 178055.25 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Equipment | USC21C011 | F21 TMAH System | 29 | P | USC2110018A | -03 | Supply Tank | 2021/10/23 2021/11/03 2021/12/29 2022/5/17 | 2021/10/28 2021/11/05 2022/01/05 2022/05/27 | 0 | -266570 | 266570 | V | V |  |  | Belco Manufacturing Co., Inc. | PR Approved | PO Approved | R1:異動簽核中因為取消運費 R2:FRP coating upgrade due to engineering design calculation R3:5/27 異動為0,因交期無法滿足cancel | Based on T&C 001 Prepayments 25 % T/T 45天 all submittals approved 002 before shipment 70 % T/T 45天 receipt of materials 20%, ready to ship status 50% 003 Final payment 5 % T/T 45天 commissioning -- with 60 days cap from shipping day | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | 44508 | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 30 | P | USC2110019A | -01 | Strippers, absorbers, and ducts | 44492 | 44508 | 0 | -2486170.38 | 2486170.38 |  |  | V |  |  | PR Approved | PO Approved | 因專案代號有誤，申請異動結案。 | PR取消 | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | x | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 31 | P | USC2110024A | -02 | Strippers, absorbers, and ducts | 2021/10/27 2021/11/04 2022/5/17 | 2021/11/2 2021/11/05 2022/05/27 | 0 | -2365209 | 2365209 |  |  |  |  | Belco Manufacturing Co., Inc. | PR Approved | PO Approved | 取代專案代號錯誤的USC2110019A。 異動簽核中因為取消運費 5/27異動為0,因交期無法滿足,cancel | Based on T&C 001 Prepayments 25 % T/T 45天 all submittals approved 002 before shipment 70 % T/T 45天 receipt of materials 20%, ready to ship status 50% 003 Final payment 5 % T/T 45天 commissioning -- with 60 days cap from shipping day | York Yeh |  |  | Rui Ma | York Yeh | N | 44508 | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 32 | P | USC2111001A |  | Pressure Switch、 sensor、transmitter | 2021/11/3 2021/12/2 | x | 0 | -92188.79 | 92188.79 | [5 empty] | PR Approved | PO Approved | 12/2 Will purchased in other PR (USC2111018) 11/9專案回覆待確認中(CF&Supplier's sheet) | PR取消 | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 33 | P | USC2111002A |  | SDI analyzer | 2021/11/4 2021/12/2 | x | 0 | -29344 | 29344 | [5 empty] | PR Approved | PO Approved | 12/2 Will purchased in other PR 11/9專案回覆待確認中(CF & Supplier's sheet) | PR取消 | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 34 | P | USC2111003A | -01 | Conductivity Meter | 44504 | 2021/12/2 2022/10/14 | 109847.32 | -171227.2 | 281074.52 |  | v |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | 10/14 change quantity because of late delivery Will be changed and replaced partially by USCSB2209011A, USCSB2210006A, USCSB2210007A 12/3 採購單成立 11/9專案回覆待確認中(CF & Supplier's sheet) | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Chia-Yi Chang | York Yeh | N | 44539 | Matt |  | N | 5000 |  | 100398.95 | 0.91399 | 9448.37 | 0 | 9448.37 | 0 | [28 empty] | 0 |  |  |  |  | 28448.4 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 57834.71 | 0 | 0 |  | 5058.87 |  | 625.52 | [12 empty] | 0 | 8431.45 | - | 0 | - | 0 | 0
Base-Build | UPW | Site Expense | USC21C003 | F21P1 UPW | 35 | P0 | USC2111007A |  | Cabinet | 44511 | 44512 | 1954.6 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Ka In Wong Lane | Lan Yun Chang | NA | X | Matt |  | NA |  |  | 1954.6 | 1 | 0 | 0 | 0 | 0 | 1954.6 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 36 | P | USC2111009A |  | I LINE PANEL,Mains Panel | 44509 | 44515 | 93800 | [6 empty] | OEG ISG - Integrated Systems Group | PR Approved | PO Approved |  | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh | DDP | 24 months warranty after received | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 93800 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 93800 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Barcode | Material | USC21C012 | F21 Barcode RFID System | 37 | P | USC2111010A |  | Barcode 系統網路設備 | 44509 | 44517 | 198808.09 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Hsiang Cheng Lee | York Yeh | N | 44520 | Martin |  | ? | 5000 |  | 198808.09 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 198808.09 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Barcode | Equipment | USC21C012 | F21 Barcode RFID System | 38 | P | USC2111011A | -01 | Warning light | 2021/11/9 2022/1/11 | 2021/11/19 2022/1/13 | 0 | -6704.73 | 6704.73 | V |  |  |  | ONRION LLC | PR Approved | PO Approved | 1/13因付款條件&廠商問題異動結案。 | PR取消 | York Yeh |  |  | Hsiang Cheng Lee | York Yeh | N |  | Martin |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 39 | P | USC2111017A |  | vortex flow meters | 2021/11/11 2023/4/3 | x | 0 | -23824 | 23824 | [5 empty] | PR Approved | PO Approved | *USC2112028A取代 *Already returned to PM side Have been unable to confirm instruments, will need to make new PR after confirmation. NO CF | PR取消 | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 40 | P | USC2111018A | -01 | pressure transmitter | 44511 | 44546 | 94829.03 | 1920.24 | 92908.79 |  |  |  |  | Ashcroft Inc. | PR Approved | PO Approved | 5/27採購異動(規格變05/06item) | 100% up front. | York Yeh | FOB- Stratford, CT | 2 years | Sterling Ellis | York Yeh | N | 44566 | Matt |  | N | 5000 |  | 94829.03 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 60000 | [11 empty] | 12580.79 |  | 22248.24 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Site Expense | USC21C003 | F21P1 UPW | 41 | P0 | USC2111019A |  | Autodesk Revit | 44512 | 44524 | 345.28 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | 8 |  | NA |  |  | 345.28 | 1 | 0 | 0 | 0 | 0 | 345.28 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 42 | P0 | USC2111020A |  | Revu | 44512 | 44524 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 43 | P0 | USC2111021A |  | Revu | 44512 | 44524 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 44 | P0 | USC2111022A |  | Sony TV for Company owned house | 44512 | 44524 | 868.79 | [6 empty] | Costco Wholesale Corporation | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 868.79 | 1 | 0 | 0 | 0 | 0 | 868.79 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 45 | P0 | USC2111023A |  | 24" Monitors for Employees | 44512 | 44524 | 456.06 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 456.06 | 1 | 0 | 0 | 0 | 0 | 456.06 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 46 | P0 | USC2111024A |  | PDF-XChange Pro | 44512 | 44524 | 107.36 | [6 empty] | Digital River, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 107.36 | 1 | 0 | 0 | 0 | 0 | 107.36 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 47 | P0 | USC2111025A |  | Dell Laptop for Engineers | 44512 | 44524 | 1031.69 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 1031.69 | 1 | 0 | 0 | 0 | 0 | 1031.69 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 48 | P | USC2111026A | -01 | Total Organic Carbon analyzers and ICR. | 2021/11/13 2021/12/16 | 2021/11/19 2021/12/20 | 0 | -379239 | 379239 |  | V | V |  | Veolia WTS Analytical Instruments, Inc. | PR Approved | PO Approved |  | 90% Received, 10% 60 days after acceptance, net 30 days | York Yeh | DDP Office | 2 year limited warranty | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 49 | P | USC2111027A |  | dissolved oxygen analyzers, Silica Analyzers | 44513 | 44519 | 249454.5 | [6 empty] | Hach Company | PR Approved | PO Approved |  | 90% Received, 10% 60 days after acceptance, net 30 days | York Yeh | DDP Office | 2 year limited warranty | Chia-Yi Chang | York Yeh | N | 44540 | Matt |  | N | 5000 |  | 249454.5 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 124727.25 | [12 empty] | 119433.33 |  |  |  |  | 5293.92 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Barcode | Material | USC21C012 | F21 Barcode RFID System | 50 | P | USC2111028A |  | alarm,wall-mounted | 44516 | 44551 | 33250 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | Cherry Chang |  |  | Hsiang Cheng Lee | Cherry Chang | N | 44565 | Martin |  | N | 5000 |  | 33250 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 33250 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 51 | P0 | USC2111032A |  | File Cabinet | 44516 | 44524 | 2475.8 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 2475.8 | 1 | 0 | 0 | 0 | 0 | 2475.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 52 | P | USC2111033A |  | Flanged Heater | 44517 | 44543 | 75000 | [6 empty] | Wattco Inc. | PR Approved | PO Approved | 12/10 (無supplier's sheet) | 70% in advance, 30% before shipping. | York Yeh | EXW | 1 year | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | 5000 |  | 75000 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 52500 |  |  | 22500 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 53 | P | USC2111034A |  | Hydrogen Peroxide Analyzer | 44517 | 44543 | 23801.52 | [6 empty] | Precision Integrated Systems, LLC | PR Approved | PO Approved | (無CF &Supplier's sheet) 12/13 採購單簽核 | 90% by received, Net 30days; 10% by acceptance, Net 30days(after acceptance in 60days). | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | N |  | Matt |  | N | 5000 |  | 23701.52 | 0.9958 | 100 | 0 | 100 | 0 | [6 empty] | 21331.37 | 2370.15 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 54 | P0 | USC2111035A |  | Bulletin Boards | 44517 | 44524 | 764.12 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 764.12 | 1 | 0 | 0 | 0 | 0 | 764.12 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 55 | P | USC2111038A | -01 | electromagnetic flowmeter,pressure transmitter | 2021/11/19 2021/12/11 | 2021/11/24 2021/12/14 | 133903.8 | -159.6 | 134063.4 |  |  | V |  | Azbil North America, Inc. | PR Approved | PO Approved |  | 90% Received, 10% 60 days after acceptance, net 30 days | York Yeh | DDP Office | 2 year limited warranty | Chia-Yi Chang | York Yeh | N |  | Matt |  | N | 5000 |  | 133903.8 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 133903.8 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 56 | P | USC2111047A |  | power panels for Chemical system | 44523 | 44532 | 21112 | [6 empty] | OEG ISG - Integrated Systems Group | PR Approved | PO Approved | 專案回覆待確認中(CF)，trade term 修改DAP 12/3 採購單成立 | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 21112 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 21112 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 57 | P | USC2111048A | -01 | Power Panels | 2021/11/23 2021/12/29 | 2021/12/9 2022/01/21 | 47296.04 | 2033.9 | 45262.14 | V |  | V |  | Kelso-Burnett Co. | PR Approved | PO Approved | Rev02-change in quantity and additional year warranty Rev01-Adding cost for warranty, additonal 12 months of warranty, please provide final quotation. | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 0 | 0 | 47296.04 | 0 | 47296.04 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 58 | P | USC2111049A |  | Valves for WCCS | 44523 | 44532 | 277255.58 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | 專案回覆待確認中(CF)，trade term 修改DAP 12/3 採購單成立 | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh | DAP | 1 year from ship date | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 277255.58 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 232839.32 | [19 empty] | 0 |  |  |  |  | 0 | 2115.06 | 23265.66 | 19035.54 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 59 | P0 | USC2111050A |  | Webcam for meeting rooms | 44523 | 44533 | 172.65 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 172.65 | 1 | 0 | 0 | 0 | 0 | 172.65 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 60 | P | USC2111051A |  | Ball Valve | 44523 | 44588 | 31860 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | CF (Trade term check)) | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh | FOB -- ship 4 weeks after receipt of order and we would invoice at that time |  | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 31860 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 31860 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 61 | P | USC2111052A |  | Valves for SDS | 44523 | 44532 | 69874.42 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | scope Changed after reviewing rev02-6/17 scope changed (material raised up ) from 2467383 to 2485140.6 | 90% by received (Net 30 days), 10% after acceptance in 60 days (Net 30 days) | York Yeh |  |  | Chia-Yi Chang | York Yeh | N |  | Henry |  | N | 5000 |  | 69874.42 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 62702.68 |  | 754.92 |  | 5661.9 | [15 empty] | 754.92 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 62 | P0 | USC2111053A |  | Office Chairs | 44523 | 44543 | 1631.36 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 1631.36 | 1 | 0 | 0 | 0 | 0 | 1631.36 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 63 | P0 | USC2111054A |  | Cork Boards | 44524 | 44554 | 382.06 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 382.06 | 1 | 0 | 0 | 0 | 0 | 382.06 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 64 | P0 | USC2111055A |  | Metal 3 drawer filing cabinets | 44524 | 44544 | 1672.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 1672.3 | 1 | 0 | 0 | 0 | 0 | 1672.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 65 | P0 | USC2111056A |  | Double sided white boards | 44524 | 44543 | 762.32 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 762.32 | 1 | 0 | 0 | 0 | 0 | 762.32 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 66 | P0 | USC2111057A |  | Mini fridges | 44524 | 44543 | 624.22 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 624.22 | 1 | 0 | 0 | 0 | 0 | 624.22 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 67 | P0 | USC2111058A |  | Office Desk | 44524 | 44624 | 2118.4 | [6 empty] | American Furniture Warehouse | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | [7 empty] | 2118.4 | 1 | 0 | 0 | 0 | 0 | 2118.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 68 | P0 | USC2111059A |  | Water dispensers | 44524 | 44543 | 1050.65 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 1050.65 | 1 | 0 | 0 | 0 | 0 | 1050.65 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 69 | P0 | USC2111060A |  | Free standing refrigerator | 44524 | 44543 | 1247.81 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 1247.81 | 1 | 0 | 0 | 0 | 0 | 1247.81 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 70 | P | USC2111061A |  | Ball Valve | 44524 | 44586 | 10252.19 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | CF (Trade term check)) | Arrival (delivery) 100.00% NET 30days after shipping | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 10252.19 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 0 |  |  |  | 0 |  |  | 10252.19 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 71 | P | USC2111062A |  | Ball Valve, Diaphragm Valve | 44524 | x | 0 | -42157.38 | 42157.38 | [5 empty] | PR Approved | PO Approved | 專案申請退回 | PR取消 | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 72 | P | USC2111063A | -01 | Supply Tank | 44525 | 44531 | 1251211.84 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved | remark修改 | 25% by submittal approved, 20% by material purchased, 50% ready to ship, 5% after final acceptance, T/T 30 days) | York Yeh |  |  | Rui Ma | York Yeh | N | 44553 | Henry |  | N | 5000 |  | 1242913.35 | 0.99337 | 8298.49 | 0 | 8298.49 | 12429.1335 | [18 empty] | 558632.7 |  | 223233.27 |  |  | 360135.6 |  |  |  |  | 76669.03 |  |  | 24242.75 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 12429.1335
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 73 | P0 | USC2111064A |  | L-shaped office desks | 44525 | 44543 | 412.66 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 412.66 | 1 | 0 | 0 | 0 | 0 | 412.66 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 74 | P0 | USC2111065A |  | Office chair | 44525 | 44543 | 220.78 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 220.78 | 1 | 0 | 0 | 0 | 0 | 220.78 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 75 | P | USC2111067A |  | pressure regulating valve | 44530 | x | 0 | -43646 | 43646 | [5 empty] | PR Approved | PO Approved | 專案申請退回 | PR取消 | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 76 | P0 | USC2111068A |  | Drone for F21 Project. | 44530 | 44533 | 194.39 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Debit card paid (員工代墊款) | Debit card paid (員工代墊款) | Lan Yun Chang |  |  | Ka In Wong Lane | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 194.39 | 1 | 0 | 0 | 0 | 0 | 194.39 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 77 | P | USC2112001A |  | Ball Valve | 44531 | 44586 | 383.92 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | CF (Trade term check)) | Arrival (delivery) 100.00% NET 30days after shipping | Cherry Chang |  |  | Chih-Chien Hung | Cherry Chang | N |  | Henry |  | N | 5000 |  | 285.8 | 0.74443 | 98.12 | 0 | 98.12 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 285.8 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 78 | P | USC2112002A |  | Ball Valve | 44531 | 44586 | 23872.51 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | CF (Trade term check)) | Arrival (delivery) 100.00% NET 30days after shipping | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 23872.52 | 1 | -0.01 | 0 | -0.01 | 0 | [28 empty] | 0 | 2929.2 |  |  |  | 0 |  |  | 20943.32 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 79 | P | USC2112003A | -02 | Power Panels | 2021/12/2 2021/12/29 2022/4/24 | 2021/12/13 2022/01/21 2022/05/04 | 0 | -24944 | 24944 | V |  |  |  | Kelso-Burnett Co. | PR Approved | PO Approved | PO:USCSB2204006A取代 Adding cost for additonal 12 months of warranty, please provide final quotation. | 90% by received, Net 30days; 10% by acceptance, Net 30days(after acceptance in 60days). | York Yeh |  |  | Stephon Dean | York Yeh | N |  | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 80 | P | USC2112004A |  | pressure regulating valve/Straight connector | 44533 | 44575 | 1309.6 | [6 empty] | Flodraulic Group | PR Approved | PO Approved | NO CF/NO Vendor sheet | 100% delivery net 30 days | Yi En Wong | DAP MICU Phoenix Office | 1 year in operation or 1.5 years after delivery | Stephon Dean | Yi En Wong | N | 44588 | Henry |  | N | 5000 |  | 1309.6 | 1 | 0 | 0 | 0 | 0 | [5 empty] | 1309.6 | [22 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 81 | P | USC2112005A |  | SDI analyzer | 44533 | 44539 | 30764 | [6 empty] | MABAT Chemical systems Ltd | PR Approved | PO Approved |  | 100% before shipping | York Yeh | DAP | 12 months from startup, or 18 months from delivery (whichever is earliest). | Chia-Yi Chang | York Yeh | N | 44546 | Matt |  | N | 5000 |  | 30764 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 30764 | [23 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 82 | P0 | USC2112006A |  | Printer cart with storage | 44533 | 44543 | 309.48 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 309.48 | 1 | 0 | 0 | 0 | 0 | 309.48 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 83 | P0 | USC2112007A |  | Office chairs | 44533 | 44543 | 481.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 481.5 | 1 | 0 | 0 | 0 | 0 | 481.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 84 | P0 | USC2112008A |  | 24" Monitor | 44533 | 44543 | 485.34 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 485.34 | 1 | 0 | 0 | 0 | 0 | 485.34 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 85 | P0 | USC2112009A |  | Dell Laptop/Nest Wifi Router and AP | 44533 | 44543 | 3137.42 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 3137.42 | 1 | 0 | 0 | 0 | 0 | 3137.42 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 86 | P | USC2112010A | -01 | Valve housing | 44537 | 44559 | 0 | -799175.66 | 799175.66 |  |  |  |  | Pure Plastics, LLC | PR Approved | PO Approved | 5/18 異動為0(另開新單) | 20% after receipt of signed submittal. 25% after receipt of material. 50% after completion. before storage. 5% after commission. (Net 45days.) | York Yeh |  |  | Stephon Dean | York Yeh | N | 44207 | Henry |  | N | 5000 |  | 0 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 87 | P | USC2112011A |  | Straight Union Reducer | 44537 | 44572 | 5678.1 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | CF (Trade term check)) | 90% by shipment,and last 10% invoice within 60 days of receiving the goods, All invoices are NET 30. | Cherry Chang | FOB Osaka port | 24 months | Chih-Chien Hung | Cherry Chang | N |  | Henry | Fittings | N | 5000 |  | 5678.1 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 5678.1 | [17 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 88 | P0 | USC2112013A |  | 27" Sceptre Monitor | 44537 | 44543 | 534.26 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 534.26 | 1 | 0 | 0 | 0 | 0 | 534.26 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 89 | P | USC2112014A |  | VMBs for slurry, Valve housing | 44538 | 44581 | 151360 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | 10/4/2022 close this account for USCSB2209032A, we only paid $45,408 NO VENDOR SHEET | 30%, 30%, 30%, 10% progress payment after acceptance net 30 days. | York Yeh |  |  | Stephon Dean | York Yeh | N |  | Henry |  | N |  |  | 67813.84 | 0.44803 | 83546.16 | 0 | 83546.16 | 0 | [6 empty] | 45408 | [21 empty] | 0 |  |  |  | 22405.84 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 90 | P | USC2112015A |  | Sleeve | 44539 | 44572 | 3282.49 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | CF (Trade term check)) | 90% by shipment, and last 10% invoice within 60 days of receiving the goods. All invoices are NET 30. | York Yeh | FOB Osaka port | 24 months | Chih-Chien Hung | York Yeh | N |  | Henry | Fittings | N | 5000 |  | 3282.49 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 3282.49 | [17 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 91 | P | USC2112016A |  | Chemical Resistant Tubing | 44539 | 44546 | 96000 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 90% by received, Net 30days; 10% by acceptance, Net 30days(after acceptance in 60days). | York Yeh |  |  | Chih-Chien Hung | York Yeh | N |  | Henry |  | N | 5000 |  | 96000 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 96000 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 92 | P | USC2112017A |  | Ball Valve | 44541 | 44566 | 8448 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | NO CF | 100% by delivery (Net 30 days) | Cherry Chang |  | twelve (12) months following delivery | Stephon Dean | Cherry Chang | N | 44571 | Henry |  | N | 5000 |  | 8448 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 4048 | 176 | [5 empty] | 4224 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 93 | P | USC2112018A |  | Ball Valve | 44541 | 44566 | 4068 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | NO CF | 100% by delivery (Net 30 days) | Cherry Chang |  | twelve (12) months following delivery | Stephon Dean | Cherry Chang | N |  | Henry |  | N | 5000 |  | 4068 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 0 |  | 4068 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 94 | P | USC2112019A | -01 | Copper, free chlorine, and turbidity analyzers. | 2021/12/14 2022/2/1 | 2021/12/28 2022/2/9 | 112714.39 | 3456.84 | 109257.55 | V |  |  |  | Hach Company | PR Approved | PO Approved | 12% price increase | 90% by received, Net 30days; 10% by acceptance, Net 30days(after acceptance in 60days). | York Yeh | DDP | 2 year limited warranty | Rui Ma | York Yeh | N |  | Henry |  | N | 5000 |  | 103659.72 | 0.91967 | 9054.67 | 0 | 9054.67 | 8292.7776 | [7 empty] | 56357 | [17 empty] | 47302.72 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 4508.5756 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 8292.7776
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 95 | P | USC2112023A |  | Bellows Valve | 44547 | 44571 | 6420 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | confirmed ok | 100% by delivery (Net 30 days) | Cherry Chang | FOB | twelve (12) months following delivery | Chih-Chien Hung | Cherry Chang | N |  | Henry |  | N | 5000 |  | 6420 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 535 | 0 |  | 5885 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 96 | P | USC2112025A |  | General hoses | 44548 | 44572 | 77500 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | NO CF | 90% by shipment, and last 10% invoice within 60 days of receiving the goods. All invoices are NET 30. | York Yeh | FOB Osaka port, for the tubing, the trade term is DDP Phoenix and for fittings, the trade term is FOB Japan. | 24 months | Chih-Chien Hung | York Yeh | N |  | Martin | PFA Tube | N | 5000 |  | 77500 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 77500 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 97 | P0 | USC2112026A |  | Laptop | 44548 | 44554 | 1846.18 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 1846.18 | 1 | 0 | 0 | 0 | 0 | 1846.18 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 98 | P0 | USC2112027A |  | Sceptre Monitor 24in | 44548 | 44554 | 647.12 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 647.12 | 1 | 0 | 0 | 0 | 0 | 647.12 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 99 | P | USC2112028A |  | vortex flowmeter | 44552 | 44571 | 25074.45 | [6 empty] | Oval Corporation of America | PR Approved | PO Approved | NO CF/NO Vendor sheet | 90% by received (Net 30 days) , 10% after acceptance in 60 days (Net 30 days). | York Yeh | EXW from Oval Houston Office | 24 months after shipping | Sterling Ellis | York Yeh | N |  | Matt |  | N | 5000 |  | 25074.45 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 25074.45 | [18 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 100 | P0 | USC2112029A |  | Bluebeam Revu | 44553 | 44558 | 758.03 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 758.03 | 1 | 0 | 0 | 0 | 0 | 758.03 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 101 | P0 | USC2112030A |  | AutoCAD License | 44553 | 44558 | 1395.75 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 1395.75 | 1 | 0 | 0 | 0 | 0 | 1395.75 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 102 | P0 | USC2112031A |  | LG 34" Monitor | 44553 | 44558 | 276.49 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid (員工代墊款) | Credit card paid (員工代墊款) | Lan Yun Chang |  |  | Chia-Yi Chang | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 276.49 | 1 | 0 | 0 | 0 | 0 | 276.49 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 103 | P0 | USC2112032A |  | Dell G15 Laptop | 44554 | 44558 | 93.15 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 93.15 | 1 | 0 | 0 | 0 | 0 | 93.15 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 104 | P0 | USC2112033A |  | Lenovo Yoga 7I Laptop | 44554 | 44558 | 2567.52 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Lan Yun Chang |  |  | Eric Lin | Lan Yun Chang | NA |  | Matt |  | NA |  |  | 2567.52 | 1 | 0 | 0 | 0 | 0 | 2567.52 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 105 | P0 | USC2201001A |  | Office Chair | 44569 | 44572 | 304.61 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Lan Yun Chang |  |  | James Baginskis | Lan Yun Chang | NA | [6 empty] | 304.61 | 1 | 0 | 0 | 0 | 0 | 304.61 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Barcode | Equipment | USC21C012 | F21 Barcode RFID System | 106 | P | USC2201003A |  | warning light (flashing type) | 44572 | 44580 | 9380.8 | [6 empty] | ADAMS International LLC | PR Approved | PO Approved |  | 100% Prepayment. | York Yeh |  |  | Hsiang Cheng Lee | York Yeh | N | 44581 | Martin |  |  | 5000 |  | 9380.8 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 9380.8 |  |  | 冲销 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 107 | P | USC2201005A |  | Sleeve,PFA,1"(PFA tube, Pipe Label) | 44575 | 44588 | 1000000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | tsmc F21P1 MIC 設備費用 | 100% by progress, T/T 45 days, after acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | N |  |  |  |  | NA |  | 0 | 0 | 1000000 | 0 | 1000000 | 1000000 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 1000000
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 108 | P | USC2201006A | -01 | Ball Valve, pressure regulating, Diaphragm Valve | 2022/1/18 2022/2/8 2022/3/31 | 2022/2/10 2022/3/31 | 108438.09 | 20599.84 | 87838.25 | V |  |  |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | Rev01:PVDF價格上漲，3個物件漲30%; Original:廠商報價時效性過，因此於請購異動增加價格 | Arrival (delivery) 100.00% NET 30days after shipping | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | N |  |  |  |  | 5000 |  | 108437.73 | 1 | 0.36 | 0 | 0.36 | 0 | [14 empty] | 13484.44 | [9 empty] | 35850.03 | 59103.26 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 109 | P0 | USC2201007A |  | 10.3" Tablet | 44579 | 44580 | 705.89 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 705.89 | 1 | 0 | 0 | 0 | 0 | 705.89 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 110 | P0 | USC2201008A |  | Autodesk AECC License | 44579 | 44580 | 1942.99 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1942.99 | 1 | 0 | 0 | 0 | 0 | 1942.99 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 111 | P0 | USC2201009A |  | Autodesk AECC License | 44579 | 44580 | 1933.77 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1933.77 | 1 | 0 | 0 | 0 | 0 | 1933.77 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 112 | P0 | USC2201010A |  | Laptop | 44579 | 44580 | 2063.38 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2063.38 | 1 | 0 | 0 | 0 | 0 | 2063.38 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 113 | P0 | USC2201011A |  | Monitor | 44579 | 44580 | 755.55 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 755.55 | 1 | 0 | 0 | 0 | 0 | 755.55 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 114 | P0 | USC2201012A |  | Monitor | 44579 | 44580 | 553.8 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 553.8 | 1 | 0 | 0 | 0 | 0 | 553.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 115 | P0 | USC2201013A |  | Office Chairs | 44585 | 44600 | 1324.8 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | James Baginskis | Yi En Wong | [7 empty] | 1324.8 | 1 | 0 | 0 | 0 | 0 | 1324.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 116 | P0 | USC2201014A |  | Solid State Drive | 44650 | 44650 | 304.92 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | James Baginskis | Yi En Wong | [7 empty] | 304.92 | 1 | 0 | 0 | 0 | 0 | 304.92 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Barcode | Material | USC21C012 | F21 Barcode RFID System | 117 | P | USC2201015A |  | 19" rack cabinet | 44586 | 44617 | 43061.4 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  | 1% 10th Prox, Net 15th Prox, Free Shipping-After Acceptance-Invoice Received | Yi En Wong |  |  | Hsiang Cheng Lee | Yi En Wong | N | [6 empty] | 43061.4 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 43061.4 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 118 | P0 | USC2201016A |  | Office Chairs | 44586 | 44600 | 1550.4 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | James Baginskis | Yi En Wong | [7 empty] | 1550.4 | 1 | 0 | 0 | 0 | 0 | 1550.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 119 | P | USC2202001A |  | Sludge Hopper | 44595 | x | 0 | -683732.16 | 683732.16 | [5 empty] | PR Approved | PO Approved | *與Henry確認，此單退回刪除，2022/4/16 PR異動完成 *此單先Hold，因廠商欲改付款條件，所以我方再在台灣找其他廠商詢價。 | 取消 | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | N |  |  |  | N |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C003 | F21P1 UPW | 120 | P | USC2202002A |  | Smartsheet Dynamic view Pro-rated license | 44603 | 44608 | 6213.7 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved | Fixed Assets (Software:Dynamic View) | Fixed Assets (Software:Dynamic View) | Yi En Wong |  |  | Eric Lin | Yi En Wong | N |  |  |  | N |  |  | 6213.7 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 6213.7 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 121 | P0 | USC2202004A |  | Desktop Computer | 44604 | 44609 | 2009.09 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2009.09 | 1 | 0 | 0 | 0 | 0 | 2009.09 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 122 | P0 | USC2202005A |  | Laptop | 44604 | 44609 | 1998.22 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1998.22 | 1 | 0 | 0 | 0 | 0 | 1998.22 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 123 | P0 | USC2202006A |  | Autodesk AECC License | 44604 | 44609 | 3554.47 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3554.47 | 1 | 0 | 0 | 0 | 0 | 3554.47 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 124 | P0 | USC2202007A |  | Monitor | 44604 | 44609 | 1095.13 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1095.13 | 1 | 0 | 0 | 0 | 0 | 1095.13 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 125 | P0 | USC2202008A |  | Portable Monitor | 44604 | 44609 | 206.33 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 206.33 | 1 | 0 | 0 | 0 | 0 | 206.33 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 126 | P0 | USC2202009A |  | Autodesk AECC License | 44604 | 44609 | 1639.11 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1639.11 | 1 | 0 | 0 | 0 | 0 | 1639.11 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 127 | P0 | USC2202010A |  | Air Quality Monitor | 44604 | 44617 | 1332.08 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1332.08 | 1 | 0 | 0 | 0 | 0 | 1332.08 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 128 | P0 | USC2202013A |  | Desks for modular | 44611 | 44643 | 689.95 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 689.95 | 1 | 0 | 0 | 0 | 0 | 689.95 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 129 | P0 | USC2202014A |  | Bluebeam Revu | 44614 | 44617 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 130 | P0 | USC2202015A |  | Bluebeam Revu | 44614 | 44617 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 131 | P0 | USC2202016A |  | 24in Monitor | 44614 | 44617 | 608.04 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 608.04 | 1 | 0 | 0 | 0 | 0 | 608.04 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 132 | P0 | USC2202017A |  | Dell Laptop | 44614 | 44617 | 1737.58 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1737.58 | 1 | 0 | 0 | 0 | 0 | 1737.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 133 | P0 | USC2202018A |  | Lenovo Laptop | 44614 | 44635 | 2850.58 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2850.58 | 1 | 0 | 0 | 0 | 0 | 2850.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 134 | P | USC2203001A |  | Short Reducer | 44623 | 44627 | 4429.5 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  | 100% delivery-Net 30 days-after acceptance | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | N | [6 empty] | 4429.5 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 3239 |  | 831.5 | [17 empty] | 0 |  |  |  |  | 0 |  |  | 359 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 135 | P0 | USC2203002A |  | Desk chairs | 44624 | 44643 | 1170.18 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1170.18 | 1 | 0 | 0 | 0 | 0 | 1170.18 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 136 | P0 | USC2203003A |  | Switch | 44629 | 44635 | 37.99 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 37.99 | 1 | 0 | 0 | 0 | 0 | 37.99 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 137 | P0 | USC2203004A |  | Router | 44629 | 44635 | 380.09 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 380.09 | 1 | 0 | 0 | 0 | 0 | 380.09 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 138 | P0 | USC2203005A |  | Laptop | 44629 | 44635 | 2850.58 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2850.58 | 1 | 0 | 0 | 0 | 0 | 2850.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 139 | P0 | USC2203006A |  | Laptop | 44629 | 44635 | 1800.86 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1800.86 | 1 | 0 | 0 | 0 | 0 | 1800.86 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 140 | P0 | USC2203007A |  | Bluebeam Revu | 44629 | 44635 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 141 | P0 | USC2203008A |  | Tablet | 44629 | 44635 | 1711.76 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1711.76 | 1 | 0 | 0 | 0 | 0 | 1711.76 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 142 | P0 | USC2203010A |  | Laptop | 44629 | 44643 | 2850.58 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2850.58 | 1 | 0 | 0 | 0 | 0 | 2850.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 143 | P0 | USC2203011A |  | Laptop | 44629 | 44643 | 2850.58 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2850.58 | 1 | 0 | 0 | 0 | 0 | 2850.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 144 | P0 | USC2203012A |  | Power Strips surge protectors | 44650 | 44650 | 2250.66 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2250.66 | 1 | 0 | 0 | 0 | 0 | 2250.66 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 145 | P0 | USC2203013A |  | Desk for modular toward total needed | 44630 | 44643 | 2167.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2167.5 | 1 | 0 | 0 | 0 | 0 | 2167.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 146 | P0 | USC2203016A |  | 55 inch computer desk | 44636 | 44643 | 1993.55 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1993.55 | 1 | 0 | 0 | 0 | 0 | 1993.55 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 147 | P0 | USC2203017A |  | 55 inch computer desk for site modular | 44636 | 44643 | 2286.96 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2286.96 | 1 | 0 | 0 | 0 | 0 | 2286.96 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 148 | P0 | USC2203018A |  | Zen 55 inch desk for moldular | 44636 | 44643 | 2462.88 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2462.88 | 1 | 0 | 0 | 0 | 0 | 2462.88 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC21C003 | F21P1 UPW | 149 | P | USC2203019A |  | Switch 48 Port、PoE Switch 48 Port、Transceiver Module | 44637 | 44657 | 10665.88 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 95% by received-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 10665.88 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 10665.88 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 150 | P0 | USC2203020A |  | AutoCAD License | 44637 | 44643 | 970.73 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 970.73 | 1 | 0 | 0 | 0 | 0 | 970.73 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 151 | P0 | USC2203023A |  | Zenstyle computer desk 55 inch. | 44650 | 44650 | 1335.6 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1335.6 | 1 | 0 | 0 | 0 | 0 | 1335.6 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 152 | P0 | USC2203024A |  | 55 inch Zen Computer desk | 44650 | 44650 | 1602.72 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1602.72 | 1 | 0 | 0 | 0 | 0 | 1602.72 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 153 | P0 | USC2203025A |  | Super Deal 55 inch modern desk | 44643 | 44670 | 879.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 879.5 | 1 | 0 | 0 | 0 | 0 | 879.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 154 | P0 | USC2203026A |  | Cavalier Ergo Mesh Chairs | 44643 | 44670 | 542.8 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 542.8 | 1 | 0 | 0 | 0 | 0 | 542.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 155 | P0 | USC2203027A |  | Sarood Laptop stand in adjustable size | 44643 | 44670 | 74.91 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 74.91 | 1 | 0 | 0 | 0 | 0 | 74.91 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Site Expense | USC21C003 | F21P1 UPW | 156 | P | USC2204001A |  | 2022 Polaris PRO XD Crew Diesel Com 21 902D PROXD, EPS | 44656 | 44664 | 25719.01 | [6 empty] | Iron City Polaris | PR Approved | PO Approved |  | 100% T/T 0 days (no deposit, all should be paid before delivery) | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 0 | 0 | 25719.01 | 0 | 25719.01 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 157 | P | USC2204002A |  | 2019 Polaris Gas, Green 4 seater | 44656 | x | 0 | -17318.84 | 17318.84 | [5 empty] | PR Approved | PO Approved | PO已退回，因廠商通知此車已被買走 | PO取消 | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 158 | P0 | USC2204003A |  | Lenovo Laptop, Dell Laptop | 44673 | 44676 | 1900.48 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1900.48 | 1 | 0 | 0 | 0 | 0 | 1900.48 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 159 | P0 | USC2204004A |  | 5 Port Switch, Netgear Router | 44673 | 44676 | 538.63 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 538.63 | 1 | 0 | 0 | 0 | 0 | 538.63 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 160 | P0 | USC2204005A |  | Revu License | 44673 | 44676 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 161 | P0 | USC2204006A |  | Lenovo Laptop | 44673 | 44764 | 2770.88 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2770.88 | 1 | 0 | 0 | 0 | 0 | 2770.88 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 162 | P0 | USC2204007A |  | Netgear Switch | 44673 | 44676 | 119.45 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 119.45 | 1 | 0 | 0 | 0 | 0 | 119.45 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 163 | P0 | USC2204008A |  | X-Change Pro | 44673 | 44764 | 130.56 | [6 empty] | Digital River, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 130.56 | 1 | 0 | 0 | 0 | 0 | 130.56 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 164 | P0 | USC2204009A |  | Sceptre 24IN & 7IN2 | 44673 | 44725 | 1672.2 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1672.2 | 1 | 0 | 0 | 0 | 0 | 1672.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 165 | P0 | USC2204010A |  | AutoCAD License | 44673 | 44676 | 693.57 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 693.57 | 1 | 0 | 0 | 0 | 0 | 693.57 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C006 | F21P1 Slurry package | 166 | P | USC2204011A |  | Diaphragm Valve | 44678 | 44679 | 159571.38 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | USC2109012A-1的Change order，因交期長達1年，再次數量異動增加111pcs成原廠商為我們保留的量(375 pcs) | 90% After received-T/T 30days-after acceptance; 10% after final acceptance-T/T 30days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 159571.38 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 159571.38 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 167 | P0 | USC2204012A |  | Ergonomic Desk Chair Mesh Cavalier for Sub Trailers | 44678 | 44764 | 933.6 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 933.6 | 1 | 0 | 0 | 0 | 0 | 933.6 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 168 | P0 | USC2204013A |  | Floor Cord protector for meeting rooms in modular | 44679 | 44764 | 462.76 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 462.76 | 1 | 0 | 0 | 0 | 0 | 462.76 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 169 | P0 | USC2204014A |  | 55 inch zenstyle computer desk | 44679 | 44764 | 1055.52 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1055.52 | 1 | 0 | 0 | 0 | 0 | 1055.52 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 170 | P0 | USC2204015A |  | Compact refrigerator for sub contractors trailer | 44679 | 44764 | 206.33 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 206.33 | 1 | 0 | 0 | 0 | 0 | 206.33 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 171 | P0 | USC2204016A |  | Multi purpose paper 11 x 17 | 44679 | 44764 | 86.87 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 86.87 | 1 | 0 | 0 | 0 | 0 | 86.87 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 172 | P0 | USC2204017A |  | hand soap package of 4 | 44679 | 44764 | 56.46 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 56.46 | 1 | 0 | 0 | 0 | 0 | 56.46 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 173 | P0 | USC2204018A |  | set of 4 hand soap | 44679 | 44764 | 104.51 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 104.51 | 1 | 0 | 0 | 0 | 0 | 104.51 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 174 | P0 | USC2205001A |  | paper for copier | 44692 | 44764 | 52.93 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 52.93 | 1 | 0 | 0 | 0 | 0 | 52.93 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 175 | P0 | USC2205002A |  | Construction site modular office supplies | 44699 | 44820 | 228.74 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 228.74 | 1 | 0 | 0 | 0 | 0 | 228.74 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 176 | P | USC2205007A |  | 2022 Polaris Pro XD Crew Diesel Com 21, Model D22P4ED4B4 Construction site #2 Polaris | 44709 | 44719 | 26856.34 | [6 empty] | Iron City Polaris | PR Approved | PO Approved |  | 100% T/T 0 day (no deposit, all should be paid before delivery) | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 26856.34 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 26856.34 | [18 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 177 | P0 | USC2206001A |  | Office Ergonomic black mesh chairs for construction sub trailers | 44722 | 44736 | 1563.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1563.3 | 1 | 0 | 0 | 0 | 0 | 1563.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 178 | P0 | USC2206002A |  | Office Ergonomic black mesh chairs for construction sub trailers | 44722 | 44736 | 1563.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1563.3 | 1 | 0 | 0 | 0 | 0 | 1563.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 179 | P0 | USC2206003A |  | Zenstyle black 55 inch computer desk for sub trailers construction | 44722 | 44736 | 2606.1 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2606.1 | 1 | 0 | 0 | 0 | 0 | 2606.1 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 180 | P0 | USC2206004A |  | Zenstyle black 55 inch computer desk for sub trailers construction | 44722 | 44736 | 2606.1 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2606.1 | 1 | 0 | 0 | 0 | 0 | 2606.1 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 181 | P0 | USC2206005A |  | Amazon Zenstyle Black 55 inch desk trailers for subs | 44722 | 44764 | 2726.76 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2726.76 | 1 | 0 | 0 | 0 | 0 | 2726.76 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 182 | P0 | USC2206006A |  | Ergo black mesh back office chairs for sub trailers | 44722 | 44736 | 1628.4 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1628.4 | 1 | 0 | 0 | 0 | 0 | 1628.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 183 | P0 | USC2206008A |  | Zenstyle Computer Desk 55 inch sub trailers | 44722 | 44764 | 2638.8 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2638.8 | 1 | 0 | 0 | 0 | 0 | 2638.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 184 | P0 | USC2206009A |  | Home Office Ergo black mesh chairs for subs trailers | 44722 | 44764 | 1628.4 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1628.4 | 1 | 0 | 0 | 0 | 0 | 1628.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 185 | P0 | USC2206010A |  | Bluebeam Revu | 44724 | 44736 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 186 | P0 | USC2206011A |  | AutoCAD | 44724 | 44736 | 744.29 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 744.29 | 1 | 0 | 0 | 0 | 0 | 744.29 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 187 | P0 | USC2206012A |  | Dell Laptop | 44724 | 44764 | 1737.58 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1737.58 | 1 | 0 | 0 | 0 | 0 | 1737.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 188 | P0 | USC2206013A |  | Dell Laptop | 44724 | 44764 | 2606.37 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2606.37 | 1 | 0 | 0 | 0 | 0 | 2606.37 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 189 | P0 | USC2206014A |  | Dell Laptop | 44724 | 44764 | 2606.37 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2606.37 | 1 | 0 | 0 | 0 | 0 | 2606.37 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 190 | P0 | USC2206015A |  | AECC License | 44724 | 44764 | 551.01 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 551.01 | 1 | 0 | 0 | 0 | 0 | 551.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 191 | P | USC2207003A |  | ESD Jumpsuit With Hood, Sticky Mat, Nitrile Disposable Glove & Face Mask, ESD Safety Shoe… | 44764 | 44768 | 1359840 | [6 empty] | Super Starnix SDN BHD | PR Approved | PO Approved |  | 15% Prepayment; 85% after cargo received-Net 30 days-After acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 1359840 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 203976 | [11 empty] | 214965 |  | 59500 | 12876.65 |  |  |  | 437099.75 | 18600 |  | 177272.6 |  |  |  | 0 | 209525 | 0 | 26025 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 192 | P0 | USC2207004A |  | large 72 inch locking file cabinet | 44770 | 44784 | 715.36 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 715.36 | 1 | 0 | 0 | 0 | 0 | 715.36 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 193 | P0 | USC2207005A |  | Black ergominc mesh back office chairs | 44770 | 44778 | 1129 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1129 | 1 | 0 | 0 | 0 | 0 | 1129 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 194 | P0 | USC2207006A |  | AECC License | 44771 | 44784 | 512.33 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Chiehwen Chen | Yi En Wong | [7 empty] | 512.33 | 1 | 0 | 0 | 0 | 0 | 512.33 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 195 | P0 | USC2207007A |  | Bluebeam Revu | 44771 | 44784 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 196 | P0 | USC2207008A |  | 24in& 27in Monitor, Keyboard and Mouse | 44771 | 44784 | 1599.58 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1599.58 | 1 | 0 | 0 | 0 | 0 | 1599.58 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 197 | P0 | USC2207009A |  | 24in Monitor | 44771 | 44784 | 732.65 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 732.65 | 1 | 0 | 0 | 0 | 0 | 732.65 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 198 | P0 | USC2207010A |  | Pallet Trucks, 2500KG,1220mm long forks,牙叉內 220mm,H-6710 | 44771 | 44798 | 1596.2 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Shannon Pulcifer | Yi En Wong | [7 empty] | 1596.2 | 1 | 0 | 0 | 0 | 0 | 1596.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 199 | P0 | USC2207011A |  | Dell Laptop | 44771 | 44784 | 1628.98 | [6 empty] | Best Buy Co., Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1628.98 | 1 | 0 | 0 | 0 | 0 | 1628.98 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 200 | P0 | USC2207012A |  | Bluebeam Revu | 44771 | 44784 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 201 | P0 | USC2207013A |  | Lenovo Laptop | 44771 | 44784 | 5772.65 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 5772.65 | 1 | 0 | 0 | 0 | 0 | 5772.65 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 202 | P0 | USC2207014A |  | 24in& 27in Monitor | 44771 | 44784 | 1330.13 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1330.13 | 1 | 0 | 0 | 0 | 0 | 1330.13 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 203 | P0 | USC2207015A |  | 27in Monitor | 44771 | 44784 | 1085.85 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1085.85 | 1 | 0 | 0 | 0 | 0 | 1085.85 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 204 | P0 | USC2207016A |  | 24in Monitor | 44771 | 44784 | 802.7 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 802.7 | 1 | 0 | 0 | 0 | 0 | 802.7 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 205 | P0 | USC2207017A |  | Bluebeam Revu | 44771 | 44784 | 379.01 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 379.01 | 1 | 0 | 0 | 0 | 0 | 379.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 206 | P0 | USC2207018A |  | 24in Monitor | 44771 | 44784 | 626.32 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 626.32 | 1 | 0 | 0 | 0 | 0 | 626.32 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 207 | P0 | USC2207019A |  | Lenovo Laptop | 44771 | 44784 | 2978.04 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2978.04 | 1 | 0 | 0 | 0 | 0 | 2978.04 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 208 | P0 | USC2207020A |  | Lenovo Laptop | 44771 | 44784 | 2978.04 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2978.04 | 1 | 0 | 0 | 0 | 0 | 2978.04 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 209 | P | USC2207021A |  | Painting | 44772 | 44776 | 250000 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | Y | [6 empty] | 250000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 39932.73 |  | 210067.27 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 210 | P0 | USC2208001A |  | Black mesh ergonomic office desk chairs | 44775 | 44784 | 1628.4 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1628.4 | 1 | 0 | 0 | 0 | 0 | 1628.4 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 211 | P0 | USC2208002A |  | Bluebeam Revu | 44777 | 44784 | 758.03 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 758.03 | 1 | 0 | 0 | 0 | 0 | 758.03 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 212 | P0 | USC2208003A |  | Lenovo Laptop | 44777 | 44784 | 3236.97 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3236.97 | 1 | 0 | 0 | 0 | 0 | 3236.97 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 213 | P | USC2208004A |  | Fire extinguishers, Inspection | 44778 | 44790 | 12122.25 | [6 empty] | Cintas Corporation | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 12122.25 | 1 | 0 | 0 | 0 | 0 | [15 empty] | 12122.25 | [12 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC21C005 | F21P1 Chemical & WCCS package | 214 | P | USC2208005A |  | Scaffold | 44779 | 44783 | 2000000 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved | USCSB2205005A Extension order | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 2000000 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 2000000 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 215 | P0 | USC2208006A |  | Office Chair Black with Mesh | 44785 | 44791 | 814.2 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 814.2 | 1 | 0 | 0 | 0 | 0 | 814.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 216 | P0 | USC2208007A |  | Zenstyle Computer Desk black 55 inch | 44785 | 44798 | 1368.15 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1368.15 | 1 | 0 | 0 | 0 | 0 | 1368.15 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 217 | P0 | USC2208008A |  | Black small 3 drawer file cabinets | 44789 | 44791 | 1049.28 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1049.28 | 1 | 0 | 0 | 0 | 0 | 1049.28 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 218 | P | USC2208009A |  | AECC License | 44785 | 44805 | 82057.95 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved |  | T/T 0 Day (paid by wire transfer) | Yi En Wong |  |  | Chiehwen Chen | Yi En Wong | [7 empty] | 0 | 0 | 82057.95 | 0 | 82057.95 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 219 | P0 | USC2208011A |  | Black Metal Chairs for Fab lunchroom | 44789 | 44798 | 379.56 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 379.56 | 1 | 0 | 0 | 0 | 0 | 379.56 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 220 | P0 | USC2208012A |  | Black metal folding chairs for workers lunchroom at Fab and 8 foot folding tables | 44789 | 44798 | 640.2 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 640.2 | 1 | 0 | 0 | 0 | 0 | 640.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 221 | P | USC2208014A |  | Extinguishers, Installation | 44793 | x | 0 | [7 empty] | PR Approved | PO Approved | PR Return - Identical to USC2208004A |  | Yi En Wong |  |  | Mirielli Terres | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 222 | P0 | USC2208015A |  | 55 inch black zenstyle computer desk | 44796 | 44798 | 2736.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2736.3 | 1 | 0 | 0 | 0 | 0 | 2736.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 223 | P0 | USC2208016A |  | 3 drawer black personal desk files | 44798 | 44810 | 2098.57 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 2098.57 | 1 | 0 | 0 | 0 | 0 | 2098.57 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 224 | P0 | USC2208017A |  | Samsung 75 inch color tv for conference room 1, Nest security camers | 44799 | 44810 | 1520.37 | [6 empty] | Costco Wholesale Corporation | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1520.37 | 1 | 0 | 0 | 0 | 0 | 1520.37 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 225 | P0 | USC2208018A |  | VIZ PRO Dry Erase Whiteboard Non Magnetic pack of 2 5x3' | 44800 | 44810 | 249.67 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 249.67 | 1 | 0 | 0 | 0 | 0 | 249.67 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 226 | P0 | USC2208019A |  | Revit License | 44800 | 44810 | 361.47 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 361.47 | 1 | 0 | 0 | 0 | 0 | 361.47 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 227 | P0 | USC2208020A |  | Revu License | 44800 | 44820 | 758.03 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 758.03 | 1 | 0 | 0 | 0 | 0 | 758.03 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 228 | P0 | USC2208021A |  | Lenovo Laptop | 44800 | 44810 | 3285.55 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3285.55 | 1 | 0 | 0 | 0 | 0 | 3285.55 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 229 | P0 | USC2208022A |  | 24in Monitors | 44800 | 44826 | 764.7 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 764.7 | 1 | 0 | 0 | 0 | 0 | 764.7 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 230 | P0 | USC2208023A |  | Lenovo Laptop | 44800 | 44810 | 3418.27 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3418.27 | 1 | 0 | 0 | 0 | 0 | 3418.27 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 231 | P0 | USC2208024A |  | Box License | 44800 | 44810 | 956.7 | [6 empty] | Box, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 956.7 | 1 | 0 | 0 | 0 | 0 | 956.7 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 232 | P0 | USC2208025A |  | 24in Monitor | 44800 | 44810 | 562.8 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 562.8 | 1 | 0 | 0 | 0 | 0 | 562.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 233 | P0 | USC2208026A |  | Dell BIM Laptop | 44800 | 44820 | 3798.35 | [6 empty] | Dell Technologies | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3798.35 | 1 | 0 | 0 | 0 | 0 | 3798.35 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 234 | P0 | USC2208027A |  | Iphones, Ipads | 44800 | 44820 | 3170.1 | [6 empty] | T-Mobile USA Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3170.1 | 1 | 0 | 0 | 0 | 0 | 3170.1 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 235 | P0 | USC2209002A |  | Black metal folding chairs | 44805 | 44810 | 379.56 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 379.56 | 1 | 0 | 0 | 0 | 0 | 379.56 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 236 | P0 | USC2209003A |  | HDX tan folding tables 8ft, Lifetime tan folding tables 8 ft | 44805 | 44810 | 1456 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 1456 | 1 | 0 | 0 | 0 | 0 | 1456 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Equipment | USC21C003 | F21P1 UPW | 237 | P | USC2209004A |  | Cushman Hauler Pro-X Elite 2023 Battery operated type is trail green color hood | 44806 | 44816 | 21031.43 | [6 empty] | Pohle NV Center, Inc. | PR Approved | PO Approved | Golf Cart with written approval | 100% Prepayment-Net 30 days | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 0 | 0 | 21031.43 | 0 | 21031.43 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 238 | P0 | USC2209005A |  | Zen style modern desk work station 55" black | 44806 | 44810 | 1001.88 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mirielli Terres | Yi En Wong | [7 empty] | 1001.88 | 1 | 0 | 0 | 0 | 0 | 1001.88 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 239 | P | USC2209006A |  | portable fans 48" 120V/1PH 12 foot power cord | 44806 | 44818 | 10396 | [6 empty] | Delta T, LLC dba Big Ass Fans | PR Approved | PO Approved |  | 100% by shipping-Net 30 days-After Acceptance | Yi En Wong |  |  | Mirielli Terres | Yi En Wong | [7 empty] | 10396 | 1 | 0 | 0 | 0 | 0 | [17 empty] | 10396 | [10 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 240 | P0 | USC2209007A |  | AECC License | 44825 | 44826 | 19396.88 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 19396.88 | 1 | 0 | 0 | 0 | 0 | 19396.88 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 241 | P0 | USC2209008A |  | AutoCAD | 44825 | 44826 | 12074.01 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 12074.01 | 1 | 0 | 0 | 0 | 0 | 12074.01 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 242 | P0 | USC2209009A |  | AECC License | 44835 | 44839 | 9643.39 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Chiehwen Chen | Yi En Wong | [7 empty] | 9643.39 | 1 | 0 | 0 | 0 | 0 | 9643.39 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 243 | P0 | USC2209010A |  | Dell Laptop | 44825 | 44826 | 8177.29 | [6 empty] | Dell Technologies | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 8177.29 | 1 | 0 | 0 | 0 | 0 | 8177.29 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 244 | P0 | USC2209011A |  | Revu License | 44825 | 44826 | 1516.06 | [6 empty] | Bluebeam, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1516.06 | 1 | 0 | 0 | 0 | 0 | 1516.06 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 245 | P0 | USC2209012A |  | 27in Monitor | 44825 | 44826 | 1384.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1384.5 | 1 | 0 | 0 | 0 | 0 | 1384.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 246 | P0 | USC2209013A |  | Lenovo Laptop | 44825 | 44826 | 3511.5 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3511.5 | 1 | 0 | 0 | 0 | 0 | 3511.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 247 | P0 | USC2209014A |  | Dell Laptop | 44825 | 44826 | 8214.22 | [6 empty] | Dell Technologies | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 8214.22 | 1 | 0 | 0 | 0 | 0 | 8214.22 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 248 | P0 | USC2209015A |  | Lenovo Laptop | 44825 | 44826 | 2973.28 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2973.28 | 1 | 0 | 0 | 0 | 0 | 2973.28 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 249 | P0 | USC2209016A |  | 24in Monitor | 44825 | 44826 | 561.2 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 561.2 | 1 | 0 | 0 | 0 | 0 | 561.2 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 250 | P0 | USC2209017A |  | 27in Monitor | 44825 | 44826 | 1102.64 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 1102.64 | 1 | 0 | 0 | 0 | 0 | 1102.64 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 251 | P0 | USC2209018A |  | Lenovo Laptop | 44825 | 44826 | 2973.28 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 2973.28 | 1 | 0 | 0 | 0 | 0 | 2973.28 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 252 | P0 | USC2209019A |  | Zenstyle desk 55 inch black | 44827 | 44839 | 879.6 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 879.6 | 1 | 0 | 0 | 0 | 0 | 879.6 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 253 | P0 | USC2209020A |  | microwave 1.1 chrome and black hamilton beach | 44832 | 44848 | 80 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Credit card paid | Credit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 80 | 1 | 0 | 0 | 0 | 0 | 80 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 254 | P0 | USC2210001A |  | Dell Laptop/Dell 27in Monitor | 44835 | 44848 | 17880.48 | [6 empty] | Dell Technologies | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 17880.48 | 1 | 0 | 0 | 0 | 0 | 17880.48 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 255 | P0 | USC2210002A |  | 24in Monitor | 44835 | 44839 | 743.8 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 743.8 | 1 | 0 | 0 | 0 | 0 | 743.8 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 256 | P0 | USC2210003A |  | 27in Monitor | 44835 | 44839 | 276.9 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 276.9 | 1 | 0 | 0 | 0 | 0 | 276.9 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 257 | P0 | USC2210004A |  | AECC License | 44835 | 44839 | 3528.33 | [6 empty] | Autodesk, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3528.33 | 1 | 0 | 0 | 0 | 0 | 3528.33 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 258 | P0 | USC2210005A |  | 24in Monitor | 2022/10/1 | 44859 | 605.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 605.3 | 1 | 0 | 0 | 0 | 0 | 605.3 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 259 | P0 | USC2210007A |  | 55 inch Samsung flat screen TV UHD/one tv stand for new TV | 44838 | 44848 | 502.82 | [6 empty] | Walmart Inc | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 502.82 | 1 | 0 | 0 | 0 | 0 | 502.82 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 260 | P0 | USC2210008A |  | Two Rolling double sided whiteboards 72 x 40 for conference rooms. | 44838 | 44848 | 591.84 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 591.84 | 1 | 0 | 0 | 0 | 0 | 591.84 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 261 | P0 | USC2210010A |  | Black 3 drawer file cabinet | 44838 | 44848 | 191.12 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 191.12 | 1 | 0 | 0 | 0 | 0 | 191.12 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 262 | P0 | USC2210011A |  | 3 drawer black file cabinet | 44838 | 44848 | 347.5 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 347.5 | 1 | 0 | 0 | 0 | 0 | 347.5 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 263 | P0 | USC2210012A |  | Rigid Shop Vacuum 16 gallon dry and wet/yellow jacket extension cords/vacumn filters | 44839 | 44848 | 623.18 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Mary Stockton | Yi En Wong | [7 empty] | 623.18 | 1 | 0 | 0 | 0 | 0 | 623.18 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 264 | P | USC2210013A |  | CM Services | 44841 | 44845 | 1000000 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 518549.47 | 0.51855 | 481450.53 | 0 | 481450.53 | 0 | [18 empty] | 244960.27 |  | 52417 |  |  |  | 51594 |  | 64422 |  | 0 |  |  |  | 11058 | 0 |  |  | 8242 | 17767.4 | 8242 |  | 9438 | 0 | 16484 | 0 |  | 0 | 8481.2 | 0 | 9737 | 9737 |  | 5969.6 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 265 | P0 | USC2210014A |  | Lenovo Laptop | 44842 | 44859 | 3355.7 | [6 empty] | Lenovo Group Ltd | PR Approved | PO Approved | Debit card paid | Debit card paid | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 3355.7 | 1 | 0 | 0 | 0 | 0 | 3355.7 | [27 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 266 | P | USC2210016A |  | WRC Chem Room Epoxy/Installation of FRP Membrane | 44854 | 44855 | 2150304 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 2150304 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 645091.2 |  |  |  | 884205.13 |  |  |  | 114059.18 |  | 506948.49 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 267 | P | USC2210017A |  | WRC Chem Room Epoxy | 44854 | 44855 | 16201 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 16201 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 15391 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 810 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 268 | P | USC2301001A |  | Non Woven Shoe Cover | 44932 | 44932 | 600 | [6 empty] | Super Starnix SDN BHD | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 600 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 600 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 269 | P | USC2301002A |  | 2022 Polaris PRO XD Crew Diesel | 44932 | x | 0 | [7 empty] | PR Approved | PO Approved | Requested by Wanyu |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 270 | P | USC2301003A |  | Superintendent (Tool Hook Up) | 44943 | 44952 | 292800 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 292800 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 66971.06 |  | 70052 |  | 35941.12 |  | 72095.43 |  | 47740.39 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 271 | P | USC2301004A |  | Kelly Outsourcing | 44943 | 44958 | 896185 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 896185 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 462989.74 |  | 304510.25 |  | 128685.01 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C005 | F21P1 Chemical & WCCS package | 272 | P | USC2301005A |  | Kelly Outsourcing | 44943 | 44958 | 896185 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 882540.55 | 0.98477 | 13644.45 | 0 | 13644.45 | 0 | [28 empty] | 286159.06 |  | 472960.48 |  | 123421.01 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC21C005 | F21P1 Chemical & WCCS package | 273 | P | USC2301007A |  | 2023 Pro XD Mid- Size Crew | 44944 | 44960 | 87026.68 | [6 empty] | Iron City Polaris | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 87026.68 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 87026.68 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C006 | F21P1 Slurry package | 274 | P | USC2301008A |  | General Laborer and Housekeeping Services/Superintendent Services | 44953 | 44959 | 500000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 489760 | 0.97952 | 10240 | 0 | 10240 | 0 | [25 empty] | 168622.5 | 65322.5 | 148015 | 67055 | 40745 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC21C003 | F21P1 UPW | 275 | P | USC2303001A |  | Liberty Scaffolding | 44993 | 44999 | 479076.14 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 479076.14 | 0 | 479076.14 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC21C005 | F21P1 Chemical & WCCS package | 276 | P | USC2303002A |  | Scaffolding | 44993 | 44999 | 1000000 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 1000000 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | Base-Build | Labor | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 277 | P | USC2303003A |  | General Laborer and Housekeeping Services /Superintendent Services | 44999 | 45000 | 500000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 469122.5 | 0.93824 | 30877.5 | 0 | 30877.5 | 0 | [28 empty] | 0 |  |  |  | 260757.5 | 94647.5 | 113217.5 | 500 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 278 | P | USC2305001A |  | HVCR/VCR coupling connectors for CVD CIP. | 45063 | 45063 | 485.74 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | TSMC has agreed to be invoiced the full sum upon delivery. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 485.74 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 485.74 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 279 | P | USC2305002A |  | CVD2 Tool interconnection materials | 45063 | 45068 | 11450 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11450 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 11450 | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 280 | P | USC2305003A |  | CVD2 Tool interconnection materials | 45063 | 45064 | 1364.2 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1364.2 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 1364.2 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 281 | P | USC2305004A |  | CVD2 Tool interconnection materials | 45063 | 45064 | 3679.5 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3672.53 | 0.99811 | 6.97 | 0 | 6.97 | 0 | [33 empty] | 0 |  |  | 3672.53 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 282 | P | USC2305005A |  | Printer and label to label cables | 45063 | 45084 | 9701.79 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9701.79 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 2968.8 |  | 6732.99 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 283 | P | USC2305006A | -01 | CVD2 Material-UHP Bourdon Tube Pressure Gauge | 45063 | 2023/6/14 2023/06/23 | 21710 | -2012 | 23722 |  |  |  |  | Motion Automation Intelligence | PR Approved | PO Approved | Better pricing sourced lower pricing |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21710 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 21710 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 284 | P | USC2305007A |  | SERV***TCXH2/4G | 2023/5/24 2023/7/22 | x | 0 | -23020 | 23020 | [5 empty] | PR Approved | PO Approved | PR R1:PM found a better pricing. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 285 | P | USC2305009A |  | Cables for LAM-Labor-Labor takes place at 23040 N. 11Th Ave Suite 100 - total 173 cabels | 45071 | 45120 | 26000 | [6 empty] | Kaleidescope Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 26000 | 0 | 26000 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 286 | P | USC2305011A |  | KPAP01 ONSIGHT LIVE ELECTRICAL INTERCONNECT 2023/05/26` | 45073 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Void due to duplicate PR |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 287 | P | USC2305012A |  | KPAP01 ONSIGHT LIVE ELECTRICAL INTERCONNECT 2023/05/26` | 45073 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Void due to duplicate PR |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 288 | P | USC2305013A |  | ZIP TIE | 45073 | 45084 | 293968.24 | [6 empty] | KunShan Doodle Electromechanical Science Technology Co.,Ltd. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 293968.24 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 44095.24 |  |  | 102888.88 |  |  | 0 | 146984.12 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 289 | P | USC2305014A |  | KPAP01 ONSIGHT LIVE ELECTRICAL INTERCONNECT | 45077 | 45090 | 49000 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 45500 | 0.92857 | 3500 | 0 | 3500 | 0 | [33 empty] | 0 |  |  | 35000 |  |  | 10500 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 290 | P | USC2305015A |  | KPE601-S GAVALIN INSULATION INSTALLING 10-15' OF INSULATE DUCT INSULATION. | 2023/5/31 2023/6/23 | x | 0 | -160000 | 160000 | [5 empty] | PR Approved | PO Approved | Price went from $1,600.00 to $3,200.00. Originally 1 day and three workers. Ended up being 2 days with 3 workers to complete |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 291 | P | USC2305016A |  | TOOL: KPE601-S QTY. (2) MSR-FSR ANALYTICAL TESTING &QAQC TESTS | 45077 | 45140 | 1575.47 | [6 empty] | MSR FSR LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1575.47 | 0 | 1575.47 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 292 | P | USC2305017A |  | WORM GEAR SCREW CLAMP, HOSECLAMP | 45077 | 45133 | 173.22 | [6 empty] | FLEXICRAFT INDUSTRIES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 173.22 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 108 |  | 0 | 65.22 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 293 | P | USC2305018A |  | 18AWG 3C SHIELD 100F- MULTI-CONDUCTOR CABLES | 2023/5/31 2023/6/10 | x | 0 | -1901.23 | 1901.23 | [5 empty] | PR Approved | PO Approved | Revise project budget code from Project B to Project C |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 294 | P | USC2306001A |  | Travis Hand -Project Coordinator (6 month) | 45079 | 45083 | 99600 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 87991.12 | 0.88344 | 11608.88 | -44.8 | 11653.68 | 0 | [33 empty] | 0 |  |  | 11855.72 |  | 14715.4 |  | 16600 | 0 | 12450 | 0 |  | 0 | 16600 | 0 | 15770 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 295 | P | USC2306002A |  | Daniel Gregoire-Superintendent (6 month), Tyler Smith-Project Coordinator (6 month) | 45079 | 45083 | 199200 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 179572.47 | 0.90147 | 19627.53 | 0 | 19627.53 | 0 | [33 empty] | 0 | 30927.28 |  | 33332.45 |  | 31185 |  | 36424.25 | 0 | 15097.77 | 0 |  | 0 | 11855.72 | 0 | 20750 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 296 | P | USC2306003A |  | Josue Daniel Dircio-Project Coordinator (6 month) | 45079 | 45084 | 99600 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 99568.24 | 0.99968 | 31.76 | 0 | 31.76 | 0 | [33 empty] | 0 | 11441.88 |  | 16860 |  | 17035 |  | 17398.38 | 0 | 20624.2 | 0 |  | 0 | 1708.78 | 0 | 14500 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 297 | P | USC2306004A |  | Joseph Turley-Project Coordinator, Clayton Thurber-Superintendent , Marco Galvan Jr-Project Coordinator (6 month) | 45079 | 45084 | 298800 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 276801.08 | 0.92638 | 21998.92 | 0 | 21998.92 | 0 | [33 empty] | 0 | 66852.76 |  | 51489.88 |  | 42823.36 |  | 33296 | 0 | 31625 | 0 |  | 0 | 20583.8 | 0 | 30130.28 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 298 | P | USC2306005A |  | Cody Seery-Project Coordinator (6 month) | 45079 | 45084 | 99600 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 99395 | 0.99794 | 205 | 0 | 205 | 0 | [33 empty] | 0 |  |  | 16600 |  | 8300 |  | 16600 | 0 | 16600 | 0 |  | 0 | 16600 | 0 | 24695 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 299 | P | USC2306006A |  | Roberto Almanza-Superintendent (6 month) | 45079 | 45084 | 99600 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 99600 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 31209.76 |  | 16679 |  | 16790 |  | 15978.9 | 0 | 16730 | 0 |  | 0 | 2212.34 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 300 | P | USC2306007A |  | TPVC.375X.625X100FT-REINFORCED .375ID X .625 OD X 100FT REINFORCED PVC TUBE | 45080 | 45100 | 372 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 372 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 372 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 301 | P | USC2306008A |  | SS-6-HC-7-8: 3/8" HOSE BARB X FNPT CONNECTOR | 45080 | 45083 | 787.2 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 787.2 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 787.2 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 302 | P | USC2306009A |  | ARMAFLEX 5/8 X 1/2 | 45080 | 45083 | 663.36 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 663.36 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 663.36 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 303 | P | USC2306010A |  | HOSE-MD1 ALUMIN. DUCT HOSE- 2INX10FT W/ TUBE | 45080 | 45128 | 660 | [6 empty] | FLEXICRAFT INDUSTRIES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 660 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 660 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 304 | P | USC2306011A |  | KPAP01 ONSIGHT LIVE ELECTRICAL INTERCONNECT | 45083 | x | 0 | [7 empty] | PR Approved | PO Approved | Voided per email June 11, 2023 8:33 PM from Ian |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 305 | P | USC2306012A |  | KPOCT5 LIT 3 FOR STREIMER- LABOR | 45083 | 45084 | 41566.5 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11546.25 | 0.27778 | 30020.25 | 0 | 30020.25 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1385.55 | 0 | 0 |  |  | 0 | 0 | 0 |  | 10160.7 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 306 | P | USC2306013A |  | KPOCT5 LIT3 HUA YI CONSTRUCTION-LABOR | 45083 | 45091 | 36400 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 34580 | 0.95 | 1820 | 0 | 1820 | 0 | [33 empty] | 0 | [6 empty] | 34580 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C001 | TEL Main Tool Interconnection | 307 | P | USC2306014A |  | KPOCT5 LIT 3 UMEC-LABOR | 45083 | 45091 | 36534 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36534 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 34854.33 |  |  | 0 | 0 | 0 | 0 |  | 1679.67 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 308 | P | USC2306015A |  | KPOCT5 LIT3- MMI LABOR | 45083 | 45093 | 9360 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 9360 | 0 | 9360 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 309 | P | USC2306016A |  | Kable Kontrol Black Zip Ties | 45084 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 310 | P | USC2306017A |  | Interconnect Material (5 Tools-KPE602-S,KPE60303.KPE604-S,KPE605-S, & KPE606-S) | 45084 | x | 0 | [7 empty] | PR Approved | PO Approved | Stop and Cancelled per email from Joel Chen |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 311 | P | USC2306018A |  | LAM Interconnect Cable Management-Building LAM cables | 45084 | 45100 | 506.4 | [6 empty] | Motion Automation Intelligence | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 405.12 | 0.8 | 101.28 | 0 | 101.28 | 0 | [33 empty] | 0 |  |  |  |  | 101.28 |  | 101.28 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 202.56 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 312 | P | USC2306019A |  | KPAE01-S UMEC-LABOR | 45085 | 45100 | 195711.79 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 195711.79 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 20957.86 | 40893.01 |  |  |  | 0 | 0 | 0 | 0 |  | 133860.92 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 313 | P | USC2306020A |  | KPOCT5-S UMEC LABOR | 45085 | 45100 | 90663.8 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 90663.8 | 0 | 90663.8 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 314 | P | USC2306021A |  | KPD901-S UMEC- LABOR | 45085 | 45100 | 141128.35 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 141128.35 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2225.53 |  |  |  |  | 0 | 0 | 0 | 0 |  | 138902.82 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 315 | P | USC2306022A |  | KPAP01 S UMEC- LABOR | 45085 | 45100 | 237806.89 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 237806.89 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 108894.37 | 80451.19 |  |  |  | 0 | 0 | 0 | 0 |  | 48461.33 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 316 | P | USC2306023A |  | KPAN01-S UMEC LABOR | 45085 | 45100 | 195711.79 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 195711.79 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2225.53 | 18432.02 |  |  |  | 0 | 0 | 0 | 0 |  | 175054.24 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 317 | P | USC2306024A |  | KPI401-T UMEC - LABOR | 45085 | 45100 | 104862.83 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 104862.83 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2225.53 |  |  |  |  | 0 | 0 | 0 | 0 |  | 102637.3 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 318 | P | USC2306025A |  | KPE601-T UMEC LABOR | 45085 | 45100 | 82545.8 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 8338.76 | 13034.1 |  |  |  | 0 | 0 | 0 | 0 |  | 61172.94 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 319 | P | USC2306026A |  | KPOCS1 LIT 3 SCREEN UMEC - LABOR Piping installation system. | 45085 | 45100 | 82545.8 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 82545.8 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 320 | P | USC2306027A |  | KPOCS1 LIT 3 SCREEN ALVARADO - LABOR | 45085 | 45096 | 17610 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 17600 | 0.99943 | 10 | 0 | 10 | 0 | [33 empty] | 0 | 17600 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 321 | P | USC2306028A |  | Labeling for waterlines, gas pipes, and exhaust-all functional areas. | 45085 | 45113 | 14955.18 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 14955.18 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 13384.22 | 0 | 0 | 0 |  | 0 | 1570.96 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 322 | P | USC2306029A |  | KPAE01 ONSIGHT LIVE ELECTRICAL INTERCONNECT | 45086 | 45096 | 49000 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 49000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 49000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 323 | P | USC2306030A |  | KPE601-T LIT3 VERO VERIA CORP | 45086 | 45117 | 3077.6 | [6 empty] | VERO VERIA CORPORATION | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3077.6 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 3077.6 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 324 | P | USC2306032A |  | KPE602-S TRIDENT MECHANICAL - LABOR | 45087 | 45139 | 596273 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 596273 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 498221 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 98052 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 325 | P | USC2306033A | -01 | Lugs for LAM Cable - cable manufacturing for LAM | 2023/6/10 2023/8/2 | 2023/6/23 2023/08/09 | 7953.5 | -716 | 8669.5 |  |  |  |  | Motion Automation Intelligence | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7953.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 1448 | 0 |  | 0 | 0 | 2212.5 | 0 | 0 |  |  | 0 | 0 | 4293 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 326 | P | USC2306034A |  | DEMAND CHARgE CYLINDERS | 45087 | 45118 | 612.35 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 612.35 | 0 | 612.35 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 327 | P | USC2306035A |  | KPAE01-T ALVARADO ELECTRIC - LABOR | 45087 | 45129 | 24780 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12060 | 0.48668 | 12720 | 0 | 12720 | 0 | [33 empty] | 0 | [5 empty] | 12060 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 328 | P | USC2306036A |  | KPAN01-T ALVARADO ELECTRIC-L | 45087 | 45131 | 24780 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7860 | 0.31719 | 16920 | 0 | 16920 | 0 | [33 empty] | 0 | [5 empty] | 7860 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 329 | P | USC2306037A |  | KPD801-T ALVARADO ELECTRIC - LABOR | 45087 | 45131 | 24780 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12240 | 0.49395 | 12540 | 0 | 12540 | 0 | [33 empty] | 0 | [5 empty] | 12240 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 330 | P | USC2306038A |  | KPOCT5 -S GRAINER | 45090 | 45126 | 2901.96 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2901.96 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2901.96 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 331 | P | USC2306039A |  | WIC. THHN 4 STR GRN MR COPPER BUILDING WIRE COILED & NR COPPER WIRE COILED | 45090 | 45178 | 4877.95 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4877.94 | 1 | 0.01 | 0 | 0.01 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 4877.94 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 332 | P | USC2306040A |  | ENCLOSURE JUNCTION BOX, GROUNDING CONNECTOR | 45090 | 45181 | 3314.22 | [6 empty] | RS AMERICAS, INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3314.22 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 1438.52 | 0 | 0 | 498.72 |  | 0 | 0 | 0 | 1376.98 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 333 | P | USC2306041A |  | BUR YA1CL2 1 AWG CU 1H LUG 1/4" STUD, BUR Y4C 4WG CU 1H LNG LUG 1/4" | 45090 | 45131 | 477.7 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 477.7 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 477.7 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 334 | P | USC2306042A |  | ELECTRICAL TRADE FOR KPSP05 & KPSP06 | 45091 | 45135 | 15060 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 15060 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 15060 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 335 | P | USC2306043A |  | KPE603-S EXHAUST INSTALLATION - STREIMERS | 45094 | 45096 | 21245.1 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16903.71 | 0.79565 | 4341.39 | 0 | 4341.39 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 2771.1 | 0 | 0 |  |  | 14132.61 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 336 | P | USC2306044A |  | KPOCT5 LIT3 CUTTING EDGE MANUFACTURING | 45094 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 337 | P | USC2306045A | -01 | VIEGA FITTING INTERCONNECT MATERIALS | 45094 | 2023/7/17 2023/07/26 | 127257.61 | [6 empty] | Hajoca Corporation DBA Hughes Supply Deer Valley | PR Approved | PO Approved | WO R1:Adjust delivery date |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 127257.58 | 1 | 0.03 | 0 | 0.03 | 0 | [33 empty] | 0 | [5 empty] | 127053.03 | 204.55 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 338 | P | USC2306046A |  | KPE602-S RL MECHANICAL LABOR PAY | 45098 | 45114 | 3200 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3200 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 3200 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 339 | P | USC2306047A |  | KPSP06 - PARTIAL MECHNICAL LABOR | 45100 | 45138 | 2370 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2370 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 2370 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 340 | P | USC2306048A |  | KPSP01 - MECHANICAL LABOR | 45100 | 45113 | 1365 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1365 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1365 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 341 | P | USC2306049A |  | KPE601-S TRIDENT MECHANICAL SERVICES LABOR PAY | 45105 | 45171 | 539509.11 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 539509.11 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 345890.11 | 0 | 0 | 0 | 0 |  | 0 | 99008.73 | 0 | 0 | 0 |  |  | 76198 | 0 | 0 |  | 0 | [7 empty] | 18412.27 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 342 | P | USC2306051A |  | Nitrogen, Compressed, 2.2 Nitrogen T | 45105 | 45119 | 273.18 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 273.18 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 273.18 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 343 | P | USC2306054A |  | KPE601-T STREIMERS EXHAUST LABOR PAY | 45105 | 45135 | 66506.4 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 40641.78 | 0.6111 | 25864.62 | 0 | 25864.62 | 0 | [39 empty] | 38794.38 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 1847.4 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 344 | P | USC2306055A |  | KPOV04 Onsite Live Labor Pay | 45105 | 45132 | 21000 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 21000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 345 | P | USC2306056A |  | MECHANICAL LABOR | 45106 | 45113 | 1365 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1365 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1365 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 346 | P | USC2307002A |  | KPE601-S RL MECHANICAL HVAC LABOR PAY | 45115 | 45131 | 3200 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3200 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 3200 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 347 | P | USC2307003A |  | Mechanical labor cost and materials KDSTS2, KDCRS3 | 45118 | 45138 | 120960 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 111649.32 | 0.92303 | 9310.68 | 0 | 9310.68 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 9529.97 | 0 | 0 | 0 |  |  | 0 | 102119.35 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 348 | P | USC2307004A |  | Mechanical Interconnect Labor and materials KDSNB1 | 45118 | 45138 | 60480 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 50849.99 | 0.84077 | 9630.01 | 0 | 9630.01 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 50849.99 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 349 | P | USC2307005A |  | Run power and signal cables accordingly, Get TSMC & EE’s to sign off to make sure everything is safe/qualified per TSMC standard. | 45118 | 45127 | 3840 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3445 | 0.89714 | 395 | 0 | 395 | 0 | [40 empty] | 3445 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 350 | P | USC2307006A |  | 400CL-015H-20 1-1/2" PIPE P/E CLR PVC SCH40 20'LENGTH | 45119 | 45124 | 12765.4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12765.4 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 12765.4 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 351 | P | USC2307007A |  | Electrical cable pull for KECOT2-Labor | 45128 | 45132 | 5200 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5200 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 5200 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 352 | P | USC2307008A |  | Labor Cable Pull KDSTS2/KDCRS3/KCSCS5 | 45129 | 45132 | 14040 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2600 | 0.18519 | 11440 | 0 | 11440 | 0 | [40 empty] | 2600 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 353 | P | USC2307011A |  | FORD TRANSIT-350 15 PASSENGER VAN | 45135 | 2023/8/16 2023/09/07 | 0 | -50000 | 50000 |  |  |  |  | MCVT Motors Inc dba Camelback Ford Lincoln | PR Approved | PO Approved | R1:The original van was sold to others and we will need to purchase from another vendor. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 354 | P | USC2307011B |  | FORD TRANSIT-350 15 PASSENGER VAN | 45135 | 45175 | 44097.4 | [6 empty] | One Stop Auto Mall LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 44097.4 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 44097.4 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 355 | P | USC2307012A |  | KPAN01-S Onsight Live- Proposal no # | 45136 | 45169 | 50750 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 50750 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 50750 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 356 | P | USC2307013A |  | KPAN01-T UMEC LABOR PAY | 45136 | 45140 | 36534 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36534 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 23464.05 |  |  | 0 | 0 | 0 | 0 |  | 13069.95 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 357 | P | USC2307014A |  | KPAN01-S UMEC LABOR PAY | 45136 | 45152 | 195711.79 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 195711.79 | 0 | 195711.79 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 358 | P | USC2307015A | -01 | KPE601-T STREIMERS LABOR PAY | 2023/7/29 2024/2/1 | 2023/8/15 2024/2/1 | 31710.63 | -34795.77 | 66506.4 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | To adjust for actual completion of work |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31710.63 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 31710.63 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 359 | P | USC2308001A |  | kpap01-s rl mechanical labor pay | 45139 | 45148 | 2730 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2730 | 0 | 2730 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 360 | P | USC2308002A |  | KPE601-t Hua Yi Construction Labor Pay | 45140 | 45149 | 20800 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 20800 | 0 | 20800 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 361 | P | USC2308003A | -01 | KPAE01 STREIMER EXHAUST LABOR PAY | 2023/8/2 2024/2/1 | 2023/8/11 2024/2/1 | 45417.4 | -15546.8 | 60964.2 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | To adjust for actual completion of work |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 45417.4 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 45417.4 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 362 | P | USC2308004A |  | KPI401-S University Medical Engineering Contractor Labor Pay | 45140 | 45199 | 104862.83 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 104862.83 | 0 | 104862.83 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Site Expense | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 363 | P | USC2308005A |  | Electric Scissor Lift, 19' Micro - Rent. Renting Lifts for cable pull, mechanical, and 8395 routing. | 45141 | 45154 | 1600 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1600 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1600 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Site Expense | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 364 | P | USC2308006A |  | Electric Scissor Lift, 20' Micro - Rent. Renting Lifts for cable pull, mechanical, and 8395 routing. | 45141 | 45154 | 450 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 450 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 450 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Site Expense | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 365 | P | USC2308007A |  | Booties for MEC Micro 19's - Rent. Required for Lifts to complete cable pull, mechanical, and 8395 routing. | 45141 | 45154 | 345 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 345 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 345 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 366 | P | USC2308008A |  | KPD801-S UMEC UNIVESITY MECHICAL ENGINEERING CONTRACTORS LABOR PAY | 45141 | 45218 | 141128.35 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 141128.35 | 0 | 141128.35 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 367 | P | USC2308009A |  | KPD801-T ONSIGHT LIVE LABOR PAY | 45141 | 45149 | 49000 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 49000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 34300 | 0 | 0 | 0 | 14700 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 368 | P | USC2308010A |  | KPOCT3 UNIVERSITY MECHANICAL & ENGINEERING CONTRACTORS LABOR PAY | 45141 | 45153 | 36534 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36534 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 36534 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 369 | P | USC2308011A |  | KPOCT3-S LIT 3 hua Ti Construction | 45141 | 45149 | 36400 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 36400 | 0 | 36400 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 370 | P | USC2308012A |  | P-G-EPDM-GSK-250: 10"EPDM | 45142 | 45147 | 1031 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1031 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 1031 | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 371 | P | USC2308013A |  | TEL interconnect Cable pull KECOT2 | 45154 | 45162 | 8496 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8496 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 8496 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 372 | P | USC2308014A |  | TEL Interconnect cable pull for KESRT4 (ETC1) | 45155 | 45162 | 9440 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9440 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 9440 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 373 | P | USC2308015A |  | TEL interconnect Cable pull KESRT4 | 45160 | 45160 | 780 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 780 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 780 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 374 | P | USC2308016A | -01 | 16A180 Circular Chart Recorder: Pressure, 0 to 200 psi, For 4 in Chart Size, 1 or 7 Day DICKSON PW474 Country of Origin USA | 2023/8/22 2023/9/5 | 2023/8/22 2023/9/5 | 1646.57 | 50.85 | 1595.72 | V |  |  |  | WW Grainger Inc | PR Approved | PO Approved | R1:Correct charts were ordered. Original were picked up at the store but new once were shipped $43.92 tax $10.25, extra charge |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1592.4 | 0.9671 | 54.17 | 0 | 54.17 | 0 | [40 empty] | 0 | 1465.92 | 0 | 0 |  | 0 | 0 | 0 | 0 | 126.48 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 375 | P | USC2308017A |  | CR87P Supco Pressure 6" Chart 429.00 1,287.00 Recorder, 0-500PSI, LED, 110V | 45161 | 45167 | 1287 | [6 empty] | MicroDAQ | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1287 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 1287 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 376 | P | USC2308018A |  | 2-1/2 SS S10 304L A312 WELD PIPE (FERGUSON WILL PAY FOR THE FREIGHT) | 45163 | 45180 | 16204.5 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16204.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 16204.5 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 377 | P | USC2308019A |  | KPAE01-T ONSIGHT LIVE LABOR PAY | 45166 | 45174 | 53032 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 53032 | 0 | 53032 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 378 | P | USC2308020A |  | KPAE01-T UMEC LABOR PAY | 45166 | 45174 | 82545.8 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 82545.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 379 | P | USC2308021A |  | KPAE01-S UMEC LABOR PAY | 45166 | 45174 | 87904.5 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 85101.38 | 0.96811 | 2803.12 | 0 | 2803.12 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 85101.38 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 380 | P | USC2308022A |  | KPE603-S Trident Labor Pay | 45167 | 45199 | 2368 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2368 | 0 | 2368 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 381 | P | USC2308023A | -01 | KPE602-S TRIDENT MECHANICAL - MATERIAL PAY | 2023/8/29 2024/1/29 | 2023/9/26 2024/1/29 | 41750 | -935 | 42685 | V |  |  |  | Trident Mechanical Services | PR Approved | PO Approved | Final amount to be paid for completed work |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 41750 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 41750 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 382 | P | USC2308024A |  | KPE601-S Trident Labor Pay | 45167 | 45184 | 16900 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16900 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 16900 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 383 | P | USC2308025A |  | KPE601-S RL MECHANICAL LABOR PAY | 45167 | 45169 | 2800 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2800 | 0 | 2800 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 384 | P | USC2308026A | -01 | KPOV04 STREIMER EXHAUST LABOR | 2023/8/29 2024/2/1 | 2023/10/6 2024/2/1 | 7112.49 | -9514.11 | 16626.6 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | Final amount to be paid for completed work |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7112.49 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 7112.49 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 385 | P | USC2308027A |  | KPAE01-S STREIMER LABOR PAY | 45167 | 45203 | 60964.2 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 60964.2 | 0 | 60964.2 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 386 | P | USC2308028A |  | Cable ties KEPRL6 | 45167 | 45176 | 6120 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6120 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 6120 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 387 | P | USC2308029A |  | KPAE01-T GREENBERRY LABOR PAY | 45167 | 45176 | 7315 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6949.25 | 0.95 | 365.75 | 0 | 365.75 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 6949.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 388 | P | USC2308030A |  | KPAP01-T UMEC LABOR PAY | 45167 | 45199 | 82545.8 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 82545.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 389 | P | USC2308031A |  | KPAP01-S STREIMERS LABOR PAY | 45167 | 45176 | 66506.4 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 66506.4 | 0 | 66506.4 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 390 | P | USC2308032A |  | KPAP01-S UMEC LABOR PAY | 45167 | 45176 | 87904.5 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 87904.5 | 0 | 87904.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 391 | P | USC2308033A |  | KPAN01-T UMEC LABOR PAY | 45168 | 45176 | 82545.8 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82545.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 82545.8 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 392 | P | USC2308034A |  | KPAN01-S UMEC LABOR PAY | 45168 | 45199 | 87904.5 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 87904.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 87904.5 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 393 | P | USC2308035A |  | KPAN01-T GREENBERRY LABOR PAY | 45168 | 45177 | 6645 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6312.75 | 0.95 | 332.25 | 0 | 332.25 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 6312.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 394 | P | USC2308036A |  | KPAN02-S UMEC LABOR PAY | 45168 | 45198 | 87904.5 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 87904.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 87904.5 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 395 | P | USC2308037A |  | KPI401-S UMEC LABOR PAY | 45168 | 45199 | 87904.5 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 87904.5 | 0 | 87904.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 396 | P | USC2308038A |  | KPI401-T ONSIGHTLIGHT LABOR | 45168 | 45191 | 42000 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 42000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 42000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 397 | P | USC2308039A |  | KPD801-T LABOR PAY | 45168 | 45177 | 82545.8 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 72102.83 | 0.87349 | 10442.97 | 0 | 10442.97 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 72102.83 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 398 | P | USC2308040A |  | KPD801-S UMEC LABOR PAY | 45168 | 45201 | 82357.7 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 82357.7 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 82357.7 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 399 | P | USC2308041A |  | KPD801-T GREENBERRY LABOR PAY | 45168 | 45188 | 7315 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6949.25 | 0.95 | 365.75 | 0 | 365.75 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 6949.25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 400 | P | USC2308042A |  | KPOCT4-T UMEC LABOR PAY | 45168 | 45180 | 82663.8 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 54397.65 | 0.65806 | 28266.15 | 0 | 28266.15 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 54397.65 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 401 | P | USC2308043A |  | KPOCT5-T GREENBERRY LABOR PAY | 45168 | 45177 | 7592 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7212.4 | 0.95 | 379.6 | 0 | 379.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7212.4 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 402 | P | USC2308044A |  | KPOCT9-T UMEC LABOR PAY | 45168 | 45177 | 82663.8 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 82663.8 | 0 | 82663.8 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 403 | P | USC2308045A |  | 1N960 Barricade Tape, Red/Black, 1000 FT X 3 IN | 45169 | x | 0 | [7 empty] | PR Approved | PO Approved | PR NOT EXISTING IN SYSTEM PR Invalid |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 404 | P | USC2309001A |  | KPE602-S TRIDENT MATERIAL PAY | 45170 | 45178 | 107408.38 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 107408.38 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 107408.38 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 405 | P | USC2309002A |  | KPE603-S MANPOWER LABOR PAY | 45170 | 45244 | 180180 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 153153 | 0.85 | 27027 | 0 | 27027 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 153153 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 406 | P | USC2309003A |  | 92240A911 18-8 SS HEX HEAD SCREW 3/8"-16 THREAD SIZE, 1" LONG, PACKS OF 25 | 45176 | 45180 | 3507.19 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3507.19 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 3507.19 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 407 | P | USC2309004A |  | FNW7819Z0037 3/8" PLTD CHAN NUT L/SPRNG | 45176 | 45181 | 459.6 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 459.6 | 0 | 459.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 408 | P | USC2309005A |  | KPE601-T HYC LABOR PAY | 45176 | 45180 | 78000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 78000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 78000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 409 | P | USC2309006A |  | KPE602-S LIT 2 LABOR PAY | 9/7/2023 8/27/2024 | 10/5/2023 8/29/2024 | 0 | -5151 | 5151 |  |  |  |  | Trident Mechanical Services | PR Approved | PO Approved | R1: Case Closed |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 410 | P | USC2309008A |  | LAM Interconnect cable pull for KEMEL1 (ETC3) | 45181 | 45199 | 4896 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3751.75 | 0.76629 | 1144.25 | 0 | 1144.25 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3751.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 411 | P | USC2309009A |  | Electrical cable pull for KESRT4-TEL | 45182 | 45204 | 8437.5 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8437.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 8437.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 412 | P | USC2309012A |  | LAM Interconnect cable pull for KECOT2 (ETC2 | 2023/9/15 2024/8/15 | 45184 | 0 | [7 empty] | PR Approved | PO Approved | PR R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 413 | P | USC2309014A |  | LAM Interconnect cable pull for KESTL1 (ETC1) | 2023/9/15 2024/8/14 | 2023/10/16 2024/8/15 | 0 | -4320 | 4320 |  |  | V |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1:Order is cancelled to release surplus budget. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Site Expense | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 414 | P | USC2309015A |  | Electric Scissor Lift, 19' Micro | 45185 | 45191 | 13609.61 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 13048.81 | 0.95879 | 560.8 | 0 | 560.8 | 0 | [40 empty] | 2299.35 | 0 | 2299.35 | 0 | 2299.35 | 0 | 2299.35 | 0 | 1047.31 | 0 | 2804.1 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 415 | P | USC2309016A |  | cable rework for 8395 | 45185 | 45303 | 70000 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 70000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 70000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 416 | P | USC2309017A |  | install ACC 10" duct insulation | 45185 | 45205 | 8425 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8003.75 | 0.95 | 421.25 | 0 | 421.25 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 8003.75 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 417 | P | USC2309018A |  | install ACC 10" duct insulation | 45185 | 45205 | 8210 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7799.5 | 0.95 | 410.5 | 0 | 410.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7799.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 418 | P | USC2309019A |  | install ACC 10" duct insulation | 45185 | 45202 | 8210 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7799.5 | 0.95 | 410.5 | 0 | 410.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7799.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 419 | P | USC2309021A |  | labor for install PCW&ACC insulation | 45191 | 45209 | 16780 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 15941 | 0.95 | 839 | 0 | 839 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 15941 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 420 | P | USC2309022A |  | CHNL BTB 14GA 120IN | 45191 | 45201 | 6773.79 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 6773.79 | 0 | 6773.79 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 421 | P | USC2309024A |  | 3/8-16 X3 ALL THRAD ROD 18-8 STAINLESS | 2023/9/22 2023/11/8 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Canceling the PR as there's currently no need per request. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 422 | P | USC2309025A |  | 90 Degree Angle Fitting | 2023/9/22 2023/11/8 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Canceling the PR as there's currently no need per request. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 423 | P | USC2309026A |  | 18-8 Stainless Steel Hex Head Screw, 3/8"-16 Thread Size, 1" Long, packs of 25 | 2023/9/22 2023/11/8 | x | 0 | [7 empty] | PR Approved | PO Approved | Return due to incorrect PR items PR R1: Canceling the PR as there's currently no need per request. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 424 | P | USC2309027A |  | 3/8 PLTD CHAN NUT L/SPRG | 45191 | 45196 | 459.6 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 459.6 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 459.6 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 425 | P | USC2309028A |  | labor for cable pull | 45191 | 45201 | 322290 | [6 empty] | Corbins, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 322290 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 322290 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 426 | P | USC2309029A |  | Electrical cable pull for KECOT2. TEL Interconnect cable pull for KECOT2 (ETC2) | 45192 | 45198 | 5959 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5959 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 5959 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 427 | P | USC2309030A |  | Labor for KPAP01-T Exhaust | 45192 | 45205 | 5980 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5681 | 0.95 | 299 | 0 | 299 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 5681 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 428 | P | USC2309031A |  | KPD801-T GREENBERRY EXHAUST LABOR | 45192 | 45197 | 690 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 655.5 | 0.95 | 34.5 | 0 | 34.5 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 655.5 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 429 | P | USC2309032A |  | KPE602-T GREENBERRY EXHAUST LABOR | 45192 | 45205 | 5980 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5681 | 0.95 | 299 | 0 | 299 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 5681 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 430 | P | USC2309033A |  | Build and qualify gas line | 45192 | 45239 | 60000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 60000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 60000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 431 | P | USC2309035A |  | KPE602-T HYC ELECTRICAL/MECHANICAL | 2023/9/23 2024/8/30 | 2023/11/11 2024/9/5 | 0 | -90000 | 90000 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: Case Closed |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 432 | P | USC2309036A | -01 | Build water line, insulation jacket and QC test | 45192 | 2023/10/3 2023/11/7 | 154500 | -132000 | 286500 |  |  |  |  | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | PO R1: Negotiated lower contract sum |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 154500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 154500 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 433 | P | USC2309037A |  | Manpower Pay for General Labor for Kate Wu | 45195 | 45216 | 38400 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 38400 | 0 | 38400 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 434 | P | USC2309038A | -01 | Manpower Pay Qty, 1 Pipe Fitter | 45196 | 2023/10/17 2024/3/7 | 0 | -36800 | 36800 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PO R1:Change of Contractor to RS Payroll |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 435 | P | USC2309038B |  | Manpower Pay Qty, 1 Pipe Fitter | 45196 | 45358 | 44000 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 44000 | 0 | 44000 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 436 | P | USC2309039A |  | Four laborers for 8395 wiring and general mechanical labor for KPMU01 for the work that was completed on 09/29/2023. | 2023/9/27 2023/11/9 | 45240 | 1248 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PR R1:the amount should be $1,248 instead of 400. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1248 | 0 | 1248 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 437 | P | USC2309041A |  | Manpower Pay for General Labor for Elsa Nieto | 45196 | 45215 | 124800 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 124800 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 124800 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 438 | P | USC2309042A |  | KPOCT4-T GREENBERRY EXHAUST INSTALLATION | 45196 | 45205 | 7592 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7212.4 | 0.95 | 379.6 | 0 | 379.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 7212.4 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Material | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 439 | P | USC2309043A |  | Manpower Pay for AMHS Infrastructure and Branch Circuits | 45196 | 2023/10/28 2024/01/24 | 0 | -6000 | 6000 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PO R1:change supplier name from Hua Yi to RSPS |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | AMHS | Labor | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 440 | P | USC2309043B |  | Manpower Pay for AMHS Infrastructure and Branch Circuits | 45196 | 45315 | 6000 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2155.56 | 0.35926 | 3844.44 | 0 | 3844.44 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 2155.56 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 441 | P | USC2309044A | -01 | Manpower Pay for 7 General Labor, 1 fork lift, and 2 carpenters | 45196 | 2023/10/17 2024/2/27 | 0 | -34400 | 34400 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PO R1:Contract changed to RS Payroll |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Base-Build | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 442 | P | USC2309044B |  | Manpower Pay for 7 General Labor, 1 fork lift, and 2 carpenters | 45196 | 45355 | 40000 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | Contract changed from Hua Yi to RS Payroll |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 40000 | 0 | 40000 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 443 | P | USC2310001A |  | labor for 8395 cable routing rework | 45202 | 45230 | 39480 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 32200 | 0.8156 | 7280 | 0 | 7280 | 0 | [40 empty] | 0 | 0 | 32200 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 444 | P | USC2310002A |  | ARGON, REFRIGERATED LIQUID, 2.2 | 45202 | 45204 | 708.62 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 708.62 | 0 | 708.62 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 445 | P | USC2310004A |  | General Labor | 2023/10/4 2023/11/14 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Return by Purchaser./ Outdated request. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 446 | P | USC2310005A | -01 | FLEX LT3UAGRY: 3 UL LIQ-TITE, PER 100 | 45203 | 2023/11/1 2023/11/13 | 513.32 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PO R1:Remark Information Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 513.32 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 513.32 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 447 | P | USC2310006A |  | Click Copers Monthly rental | 45203 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: No PR Email, No Supporting Documents/Wrong project |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 448 | P | USC2310007A |  | Click Copers Monthly rental | 45204 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: No PR Email, No Supporting Documents/Wrong project |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 449 | P | USC2310008A |  | Click Copers Monthly rental | 45204 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Information mismatch. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 450 | P | USC2310009A |  | Click Copers Monthly rental | 45204 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: No PR Email, No Supporting Documents/Wrong project |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 451 | P | USC2310010A |  | Click Copers Monthly rental | 45204 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Information mismatch./Wrong project. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 452 | P | USC2310011A |  | Click Copers Monthly rental | 45204 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1 :No PR Email, No Supporting Documents/Wrong |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 453 | P | USC2310012A |  | Click Copers Monthly rental | 45204 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1 :No PR Email, No Supporting Documents/Wrong |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 454 | P | USC2310013A |  | Click Copers Monthly rental | 45204 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1 :No PR Email, No Supporting Documents/Wrong |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 455 | P | USC2310014A |  | Manpower Pay for General Labor for Shannon Pulcifer | 2023/10/5 2023/11/14 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Wrong project code. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 456 | P | USC2310016A |  | labor for install cabinet anchor | 45204 | 45226 | 7470 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7470 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7470 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 457 | P | USC2310017A |  | Labor Pull cable and 8395 Certification/Install seal tight flex conduit, cables from L30 to L10 and tie wraps. $59 x 8 hours = $472.00 $472 x 2 installers = $944.00 | 45206 | 45212 | 944 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 944 | 0 | 944 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 458 | P | USC2310020A |  | Labor for level QC | 45210 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled PR R1: Cancelled: by Kyle Came/needs to zero out |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 459 | P | USC2310022A |  | Labor | 45211 | 45308 | 30843 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 30843 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 30843 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 460 | P | USC2310023A |  | Manpower Pay for General Labor for Elsa Nieto/ Von Villas | 2023/10/12 2023/11/14 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Wrong project code. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 461 | P | USC2310024A |  | ClickCopier Wide Format Printer-Purchasing the machine not leasing | 2023/10/12 2024/1/25 | X | 0 | [7 empty] | PR Approved | PO Approved | PR R1:This order was entered in error and needs to be VOIDED/DELETED per request. (Please see attached email thread.) |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 462 | P | USC2310029A |  | labor of KPE605-S cable pull | 2023/10/13 2023/11/14 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Order cancelled and replaced with another vendor. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 463 | P | USC2310035A |  | FLEX LT2UAGRY: 2 UL LIQ-TITE | 45216 | 45219 | 603.02 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 603.04 | 1 | -0.02 | 0 | -0.02 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 603.04 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 464 | P | USC2310036A |  | 5YE30: STAND NUT, STEEL, OVERALL W 1 3/8IN, PK25 | 45216 | 45219 | 953.01 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 953.01 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 953.01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 465 | P | USC2310037A | -01 | ELECTRICAL CABLE PULL | 45216 | 2023/10/25 2023/11/03 | 6890 | 650 | 6240 |  |  |  |  | OE Electric | PR Approved | PO Approved | R1: The original PO amount was lower, but the invoice charged, the PM agreed upon. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6890 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 6890 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 466 | P | USC2310038A | -01 | ALL MEP INTERCONNECTION SOW | 45216 | 2023/10/25 2024/3/7 | 0 | -138802 | 138802 |  |  |  | V | Greenberry Industrial | PR Approved | PO Approved | Cancel request by Responsible Engineer as order "not delivered" |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 467 | P | USC2310039A |  | Labor - Cable pull and chemical sus line install | 45217 | 45237 | 102000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 102000 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 102000 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 468 | P | USC2310041A |  | INTERCONNECTION CABLE PULL FOR KEPCH2.G.5-L30 ELECTRICAL LABOR. 4 PEOPLE FOR 3 DAYS. For the work that was completed starting 2023/10/23 | 45218 | 45251 | 4917.27 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4917.27 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 4917.27 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 469 | P | USC2310043A |  | Manpower | 45218 | 45225 | 1416 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | Initial amount revised from $300 to $1416. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1416 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1416 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 470 | P | USC2310044A |  | labor Invoice for Netcome | 45219 | 45224 | 19455 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 19455 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 19455 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 471 | P | USC2310045A |  | Six 40' storage containers | 45220 | 45228 | 25650 | [6 empty] | Adaptive Shelters, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 25650 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 25650 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 472 | P | USC2310046A |  | Work Post TM Reconciliation | 2023/10/21 2023/11/4 | 45307 | 5151 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved | PR R1: THIS IS ORIGINAL BETWEEN TONY LEE AND TRIDENT |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 5151 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 5151 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 473 | P | USC2310047A |  | Work Post TM Reconciliation | 2023/10/21 2023/11/4 | 45307 | 53298 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved | PR R1: THIS IS ORIGINAL BETWEEN TONY LEE AND TRIDENT |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 53298 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 53298 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 474 | P | USC2310048A |  | kpe602S temp cda line build COR | 45220 | 45224 | 7242 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7242 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 7242 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 475 | P | USC2310049A |  | KPE602-S Reservoir Mounting | 45220 | 45224 | 1123 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1123 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 1123 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 476 | P | USC2310050A |  | KPOCS3-S GREENBERRY EXHAUST | 45224 | 45241 | 24782 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 23542.9 | 0.95 | 1239.1 | 0 | 1239.1 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 23542.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 477 | P | USC2310052A |  | Manpower | 45225 | 45273 | 5108 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2923.89 | 0.57241 | 2184.11 | 0 | 2184.11 | 0 | [43 empty] | 0 |  | 0 | 0 | 2923.89 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 478 | P | USC2310053A |  | Manpower | 2023/10/26 2023/11/9 2024/8/12 | 2023/11/9 2023/11/13 2024/8/20 | 0 | -448 | 448 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: No longer needed PO. Close PO |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 479 | P | USC2310054A |  | materials for KDSNB1 Flex LT2UAGRY (50) BPT 435SLTI (20) BPT 38614LTI (20 GSTRT GC1154-200ASMBL (20) WIRE THHN6STRGRN (20) BPT 2150 (20) BUR KA6U (8) | 45225 | 45227 | 1139.49 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1139.49 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 1139.49 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 480 | P | USC2310055A |  | Manpower Pay for Mike Zipp 1 Pipe Fitter, 3 general labor, and 1 orbital welder. | 10/26/2023 8/24/2024 | 11/3/2023 8/29/2024 | 0 | -40000 | 40000 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: As per Hua Yi to close out the PO. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 481 | P | USC2310056A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45226 | 45230 | 513.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 513.19 | 0.99998 | 0.01 | 0 | 0.01 | 0 | [42 empty] | 0 | 0 |  | 513.19 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 482 | P | USC2310057A |  | Uline Utility Cart with Pneumatic Wheels - 45 x 25 x 37", Black | 2023/10/27 2024/3/29 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Zeroing out this PR per Purchaser and Michelle's request. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 483 | P | USC2310058A |  | KDCRS3 Cable Pull | 45227 | 45231 | 1062 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1062 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1062 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 484 | P | USC2311001A |  | Install 45 power and 11 signals; cable pulls from l30 to l20, l20 to l20, and 8395 organization: WBS:Power-Power,Signal | 45231 | 45240 | 45000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 45000 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 485 | P | USC2311002A |  | EPI cable tray/cable pull material for EPI_KEXR01,KEXR01 | 45231 | 45238 | 408.89 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 408.84 | 0.99988 | 0.05 | 0 | 0.05 | 0 | [42 empty] | 0 | 0 |  | 0 | 408.84 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 486 | P | USC2311003A |  | KDSNB1 Mechanical Work 12 working days | 45232 | 45245 | 56376.12 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 49053.01 | 0.8701 | 7323.11 | 0 | 7323.11 | 0 | [42 empty] | 0 | 0 |  | 0 | 49053.01 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 487 | P | USC2311004A |  | KDCRS3 Mechanical Work. 12 days | 45232 | 45245 | 56376.12 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 55076.49 | 0.97695 | 1299.63 | 0 | 1299.63 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 28048.35 |  | 0 | 27028.14 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 488 | P | USC2311005A |  | Labor - Cable Installation for KCSNA1 | 45232 | 45239 | 7552 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7552 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7552 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 489 | P | USC2311006A |  | WIRE SO10/4 10/4 SOW-A SO TYPE; 250 FT; 250 LENGTH IN FT; COPPER CONDUCTOR MATERIAL; 600 V VOLTAGE RATING; -40 TO 60 DEG C TEMPERATURE RATING; 4 CONDUCTOR(S); EPDM RUBBER INSULATION MATERIAL; 10 AWG CONDUCTOR SIZE; COIL PACKAGE TYPE; 104 STRANDS STRANDING; BLACK JACKET COLOR | 45232 | 45234 | 582.25 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 582.25 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 582.25 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 490 | P | USC2311007A |  | KDSNB1 Cable Pull Labor Pay | 45232 | 45238 | 1888 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1888 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 1888 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 491 | P | USC2311009A |  | accessory material | 45233 | 45250 | 9200 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9200 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 9200 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 492 | P | USC2311011A |  | KPAP02-S Stainless Material for XCHA Line | 45233 | 45237 | 3342.53 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3342.41 | 0.99996 | 0.12 | 0 | 0.12 | 0 | [42 empty] | 0 | 0 |  | 0 | 3342.41 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 493 | P | USC2311012A |  | Cable pull for KDSTS1 | 45233 | 45237 | 3776 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3304 | 0.875 | 472 | 0 | 472 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 3304 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 494 | P | USC2311013A |  | Labor for level QC | 45233 | 2023/11/8 2024/8/6 | 0 | -3881.96 | 3881.96 |  |  |  | V | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | R1: VOID - Replaced with PO#USC2311079A |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 495 | P | USC2311014A |  | MECHANICAL LABOR | 45234 | 45238 | 3776 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3776 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 496 | P | USC2311015A |  | Labor | 45234 | 45239 | 3776 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2475 | 0.65546 | 1301 | 0 | 1301 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 2475 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 497 | P | USC2311016A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45237 | 45240 | 809.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 809.5 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 809.5 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 498 | P | USC2311017A |  | labor for install cabinet anchor | 45237 | 45245 | 310000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 310000 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 62000 | 0 |  | 0 |  |  |  | 148800 |  |  |  | 12400 | [5 empty] | 86800 | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 499 | P | USC2311018A |  | Labor Pull cable and 8395 Certification/Install seal tight flex conduit, cables from L30 to L10 and tie wraps. $59 x 8 hours = $472.00 $472 x 2 installers = $944.00 | 45238 | 45241 | 1840.8 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1840.8 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1840.8 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 500 | P | USC2311019A |  | 1 welder welding flanges onto exhaust adapters. Total of 4 flanges | 2023/11/8 2024/8/15 | 2023/11/17 2024/8/15 | 0 | -840 | 840 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1. Budget was not used and so released. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 501 | P | USC2311020A |  | MECHANICAL LABOR | 2023/11/8 2024/1/4 2024/8/14 | 2024/1/11 2024/8/15 | 0 | -1710.92 | 1710.92 | V |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1:Vendor name change from MICU Manpower/Hua Yi Constraction to RS Payroll Services and the amount changed from $7680 to $1710.. R2 : Order is closed to re-allocate funding sources. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 502 | P | USC2311021A |  | Labor for level QC | 45238 | 45240 | 850 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 850 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 850 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 503 | P | USC2311022A |  | MECHANICAL LABOR | 2023/11/9 2024/8/14 | 2023/12/12 2024/8/15 | 0 | -1046.25 | 1046.25 |  |  | V |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | R1 - Release excess budget to user team. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 504 | P | USC2311023A | -03 | Labor | 2023/11/9 2023/11/20 2023/12/11 | 2023/11/11 2023/11/21 2023/12/14 2023/12/18 | 0 | -3840 | 3840 | V |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | PO R3:Supplier Change PO R1:Unit Price Change per Cost Book PO R2: Price Change per Actual Work Timecard |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 505 | P | USC2311023B |  | LAM Interconnect cable pull for KESTL3 (ETC1) TSMC K/2.5 Lvl. L30 2 days | 45239 | 45280 | 842.03 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 842.03 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 842.03 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 506 | P | USC2311024A |  | Manpower Pay for General Labor for Elsa Nieto/ Von Villas | 45239 | 45241 | 1888 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1888 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1888 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 507 | P | USC2311025A |  | ClickCopier Wide Format Printer-Purchasing the machine not leasing | 2023/11/9 2023/12/15 | 45302 | 1080.5 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | PR R1:Vendor name change to Electrical Ops and amount changed from 3840 to 1080.50 |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1080.5 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 1080.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 508 | P | USC2311026A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45239 | 45239 | 855.17 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 855.18 | 1 | -0.01 | 0 | -0.01 | 0 | [43 empty] | 0 |  | 855.18 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 509 | P | USC2311027A |  | KPAN02-T HYC LABOR | 45239 | 45253 | 81000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 81000 | 0 | 81000 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 510 | P | USC2311028A |  | FLEX LT2UAGRY: 2 UL LIQ-TITE, PER 100 | 45240 | 45244 | 401.9 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 401.9 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 340.68 | 0 | 0 | 61.22 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 511 | P | USC2311029A |  | KPE603-T HYC LABOR | 45240 | 45247 | 90000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 90000 | 0 | 90000 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 512 | P | USC2311030A |  | 1 welder for 6, 4"flanges, and 4 6" flanges to be welded onto adapters | 45240 | 2023/11/28 2024/8/14 | 0 | -448 | 448 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | PR R1: PO was never used. Needs to be deleted |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 513 | P | USC2311031A |  | FLEX LT4UAGRY: 4 UL LIQ-TITE, PER HUNDRED | 45241 | 45245 | 1731.13 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1731.13 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 1731.13 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 514 | P | USC2311032A | -01 | KPI401-S (LIT 1) - Cable Pulls & Tray Install - HYC | 45244 | 45247 | 0 | -50000 | 50000 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: HYC demobilizing, installed tray but did not and will not install the cabling |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 515 | P | USC2311033A |  | KPI401-S (LIT 1) - CA Exhaust Insulation Labor - Greenberry | 45244 | 45247 | 10497 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9972.15 | 0.95 | 524.85 | 0 | 524.85 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 9972.15 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 516 | P | USC2311034A |  | KPD801-S (LIT 1) - CA Exhaust Insulation Labor - Greenberry | 45244 | 45247 | 10497 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 9972.15 | 0.95 | 524.85 | 0 | 524.85 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 9972.15 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 517 | P | USC2311035A |  | Manpower Labor for Tool KECOT1 | 45244 | 45314 | 7708.99 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4227.22 | 0.54835 | 3481.77 | 0 | 3481.77 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3402.5 | 824.72 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 518 | P | USC2311036A |  | Labor to route qty (20) hoses, no connection points. II. Labor to routte and connect qty (2) hoses THC Sub-Fab cabinet. III. Furnish unistrut, clamps and zip ties as required. IV. Furnish Supervision and general conditions. | 45244 | 45253 | 9588 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9588 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 9588 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 519 | P | USC2311037A |  | Manpower Labor for Tool KECOT5 | 45245 | 45330 | 7937.09 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1770.16 | 0.22302 | 6166.93 | 0 | 6166.93 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1770.16 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Scaffolding | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 520 | P | USC2311038A |  | Action Equipment & Scaffold Co. Invoice Payment | 45245 | 45247 | 4440 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 4440 | 0 | 4440 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 521 | P | USC2311039A |  | Water line insulation; ABAA0218100 Armaflex 2-1/8 X 1 ZZZY049 | 45245 | 45248 | 835.52 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 835.52 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 835.52 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 522 | P | USC2311040A |  | I. Labor to route qty (18) hoses, no connection points. II. Labor to routte and connect qty (2) hoses THC Sub-Fab cabinet. III. Furnish unistrut, clamps and zip ties as required. IV. Furnish Supervision and general conditions. | 45245 | 45250 | 8651 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8218.45 | 0.95 | 432.55 | 0 | 432.55 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 8218.45 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 523 | P | USC2311041A |  | Pay for San Tan for Tool KDSTL1 | 45245 | 45247 | 2832 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2832 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 2832 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 524 | P | USC2311042A |  | Pay for San Tan for Tool KRWRS1 | 45246 | 45247 | 2832 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2832 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 2832 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 525 | P | USC2311043A |  | Pay for San Tan for Tool KRWRS4 | 45246 | 45247 | 2832 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2832 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 2832 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 526 | P | USC2311044A |  | Litho 2 KPE605-S XCDA/HCDA Material Please see quote in documents for material details. | 45246 | 45246 | 2151.06 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2151.06 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 2151.06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Scaffolding | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 527 | P | USC2311045A |  | Pay for Action Equip & Scaffold | 45246 | 45248 | 4395 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 4395 | 0 | 4395 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 528 | P | USC2311046A |  | Litho 2 Material Armaflex | 45246 | 45248 | 1883.38 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1883.38 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 1883.38 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 529 | P | USC2311048A |  | FLEX LT2UAGRY | 45247 | 45250 | 836.06 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 836.07 | 1 | -0.01 | 0 | -0.01 | 0 | [43 empty] | 0 |  | 836.07 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 530 | P | USC2311049A | -01 | Cable tray divider | 45247 | 2023/11/20 2023/11/21 | 224.63 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1: Supplier Request to change completion date |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 224.63 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 40.91 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 183.72 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 531 | P | USC2311051A |  | P-NF-1/2: NUT, FEMALE, HTC | 45248 | 45253 | 7511.92 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6200.91 | 0.82548 | 1311.01 | 0 | 1311.01 | 0 | [43 empty] | 0 |  | 0 | 0 | 5416.74 | 0 | 0 |  |  | 0 | 784.17 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 532 | P | USC2311052A |  | Armaflex 1-5/8 X 1/2 | 45248 | 45253 | 1256.98 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1256.96 | 0.99998 | 0.02 | 0 | 0.02 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 1256.96 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 533 | P | USC2311053A |  | Manpower pay for SanTan Tool ID KEPRL7 | 45248 | 45253 | 7552 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3923.5 | 0.51953 | 3628.5 | 0 | 3628.5 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 3923.5 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 534 | P | USC2311054A |  | Cooling water material. CW Pipe, CW Valves, Cushion Clamps | 45248 | 45258 | 28976.95 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 28976.95 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 28864.81 |  |  | 0 | 112.14 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 535 | P | USC2311057A |  | SANTAN PAY FOR KEPST1 | 45251 | 45252 | 3776 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3776 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 536 | P | USC2311059A |  | SANTAN PAY FOR KEPST2 | 45251 | 45252 | 3776 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3776 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 537 | P | USC2311060A |  | SANTAN PAY FOR KEBCT1 | 45251 | 45253 | 3776 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 3776 | 0 | 3776 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 538 | P | USC2311061A |  | SANTAN PAY FOR KEBCT2 | 45251 | 45252 | 3776 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 3776 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 539 | P | USC2311062A |  | FLEX LT3UAGRY | 45251 | 45258 | 10469.57 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 10469.59 | 1 | -0.02 | 0 | -0.02 | 0 | [43 empty] | 0 |  | 10469.59 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 540 | P | USC2311063A | -01 | Strut Channel Nut With Spring, 13/16" High Channel, Steel, 3/8"-16 Thread Size, 1" Long, packs of 1 | 45251 | 2023/11/23 2023/12/2 | 126.61 | 11.21 | 137.82 |  |  |  |  | McMaster-Carr Supply Company | PR Approved | PO Approved | PO R1:Supplier Credit Shipping Charge |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 126.61 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 126.61 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 541 | P | USC2311064A | -01 | BLINE 9ZN-1204NB CABLE TRAY CLAMP | 45252 | 2023/11/23 2023/12/5 | 99.75 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PR R1: Remark Information Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 99.75 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 99.75 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 542 | P | USC2311065A |  | CDA purifier material | 45252 | 45257 | 2450 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2450 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 2450 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 543 | P | USC2311066A | -01 | manpower request for KDANT2. This will be for general labor for today to install Unistrut & cable tray at LB1 F.5/9. | 45252 | 2023/12/5 2024/1/30 | 895.63 | 415.25 | 480.38 | V |  |  |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | PR R1: Total Amount Change |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 895.62 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 895.62 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 544 | P | USC2311068A |  | FLEX LT3UAGRY: 3 UL LIQ-TITE, PER 100 | 45253 | 45286 | 1516.25 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1516.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 1516.25 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 545 | P | USC2311069A |  | FLEX LT3UAGRY: 3 UL LIQ-TITE, PER 100 | 45253 | 45287 | 1516.25 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1516.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 1516.25 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 546 | P | USC2311070A |  | Manpower Labor for Tool KEMGL1 | 2023/11/27 2023/12/13 | 20224/1/24 | 2223.01 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1: Needed Updated back-up paperwork. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2223.01 | 0 | 2223.01 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 547 | P | USC2311071A |  | PVC Piping | 45257 | 45268 | 104729 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 104729 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 104729 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 548 | P | USC2311072A |  | PVC Piping | 45258 | 45272 | 127719 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 127719 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 127719 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 549 | P | USC2311073A |  | Unistrut clamps and zip ties | 45258 | 45266 | 8651 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8218.45 | 0.95 | 432.55 | 0 | 432.55 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 8218.45 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 550 | P | USC2311074A |  | 13/16 x 10' PRE-GALV BACK TO BACK HALF SLOT STRUT | 45258 | 45259 | 3647.98 | [6 empty] | TRI STAR INDUSTRIAL LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3647.98 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 3622.66 | 25.32 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 551 | P | USC2311075A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45258 | 45261 | 589.43 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 589.42 | 0.99998 | 0.01 | 0 | 0.01 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 589.42 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 552 | P | USC2311076A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45258 | 45260 | 589.44 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 589.43 | 0.99998 | 0.01 | 0 | 0.01 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 589.43 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 553 | P | USC2311077A |  | WIRE THHN6STRGRN | 45258 | 45259 | 3856.85 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3816.94 | 0.98965 | 39.91 | 0 | 39.91 | 0 | [43 empty] | 0 |  | 3816.94 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 554 | P | USC2311078A | -01 | E-OPS Manpower for cable pull (Robert Nelson) | 45258 | 2023/12/5 2024/2/7 | 0 | -3297.75 | 3297.75 |  |  |  |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | PO R1:The PO is incorrect and need to be issued again according to E-OPS. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 555 | P | USC2311079A |  | 6" FLEXIBLE DUCT (MD-13) | 45259 | 45261 | 3881.96 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3881.96 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 3881.96 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 556 | P | USC2311080A |  | manpower - electricians | 2023/11/29 2024/4/27 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:New PR was created USCSB2404034 |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 750 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 557 | P | USC2311081A |  | KETRT8 - Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards. | 45259 | 45331 | 11394.53 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 10595.16 | 0.92985 | 799.37 | 0 | 799.37 | 0 | [49 empty] | 0 |  |  | 1614.06 | 0 | 0 |  | 8981.1 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 558 | P | USC2311083A |  | KPSP01: CABLE PULL | 2023/11/30 2023/12/19 | 45286 | 13572 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved | PR R1: Uploaded revised invoice 38242 for $3,456. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 13572 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 13572 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 559 | P | USC2311084A |  | SS-16-VCR-P: VCR PLUG 1" | 45260 | 45264 | 891.8 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 891.8 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 891.8 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 560 | P | USC2311085A |  | For the PO renewal of Daniel Dircio, in the Project Coordinator (Tool Interconnect) position Project Coordinator. 6 month PO | 2023/11/30 2023/12/8 | X | 0 | [7 empty] | PR Approved | PO Approved | PR R1:the project code was incorrect |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 561 | P | USC2312001A |  | ELECTROLYTE_GOLD: Potassium Hydroxide Solution 100ml | 2023/12/1 2023/12/11 | X | 0 | [7 empty] | PR Approved | PO Approved | PR R1 :VOID - Tool HookUp already submitted the same quote. Ok to void per TL. |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 562 | P | USC2312002A |  | Grounding Box and Wiring | 45261 | 45279 | 3850 | [6 empty] | Advanced Technical Solutions, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3850 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 3850 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 563 | P | USC2312003A |  | FLEX LT2UAGRY 2 UL LIQ-TITE FLEXIBLE TYPE; 50 FT; UL APPROVAL; 2 INCH TRADE SIZE; UA/LA STYLE; GRAY JACKET COLOR; STEEL CORE MATERIA | 45261 | 45264 | 207.58 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 207.58 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 207.58 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 564 | P | USC2312004A |  | 1 X NITROGEN, COMPRESSED, 2.2 NITROGEN T MRO5505 | 45261 | 45265 | 273.25 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 273.25 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 273.25 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 565 | P | USC2312005A |  | Cables need to be swapped from the conduit they were routed through due to vendor error. KDSNB1 | 45261 | 45264 | 1416 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1416 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 1416 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 566 | P | USC2312006A |  | 1" x 1/4" BPE CON RDC 20 RA 316SS: MFG P/N S31-1x.25-PL-316 | 45261 | 45266 | 311.58 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 311.58 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 311.58 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 567 | P | USC2312007A |  | Manpower | 2023/12/2 2024/8/12 | 2023/12/4 2024/8/13 | 0 | -4134 | 4134 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: PO was created but never used. Needs to be deleted |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 568 | P | USC2312008A |  | Manpower | 12/2/2023 8/12/2024 | 12/7/2023 8/20/2024 | 0 | -3312 | 3312 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: PO was created but never used. Needs to be deleted |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 569 | P | USC2312011A |  | Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards.Istall conduit and cable tray dividers. KCWCN1 | 45262 | 45268 | 5487 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 5487 | 0 | 5487 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 570 | P | USC2312012A |  | KPAN02-S LIT 1 UMEC | 45262 | 45266 | 99953.6 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 99953.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 99953.6 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 571 | P | USC2312014A |  | workers for 3 days to install exhaust duct between L10 and LB1 (Robert Nelson) | 45262 | 45279 | 1217.11 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 681.6 | 0.56002 | 535.51 | 0 | 535.51 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 681.6 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 572 | P | USC2312015A |  | KPAP02-S LIT 1 UMEC | 45262 | 45266 | 99334.7 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 99334.7 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 99334.7 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 573 | P | USC2312016A |  | PPW: MANPOWER: 2 PEOPLE 12/07-12/15 & MILEAGE. | 45262 | 45400 | 3562.22 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 3562.22 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 3562.22 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 574 | P | USC2312017A |  | Build ASML EUV Gas Line and QC | 45264 | 45268 | 60000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 60000 | 0 | 60000 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 575 | P | USC2312018A |  | Build ASML EUV Gas Line & QC | 45264 | 45268 | 60000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 60000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 60000 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 576 | P | USC2312019A | -01 | KST-70R Tube | 45265 | 2023/12/8 2023/12/15 | 11110.46 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved | Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11110.46 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 11110.46 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 577 | P | USC2312020A |  | Build ASML EUV Gas Line and QC | 45265 | 45269 | 60000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 60000 | 0 | 60000 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 578 | P | USC2312021A |  | Build ASML EUV Gas Line and QC | 45265 | 45268 | 60000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 60000 | 0 | 60000 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 579 | P | USC2312022A |  | Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards KETRT7 | 2023/12/5 2024/8/14 | 2023/12/8 2024/8/15 | 0 | -6854 | 6854 |  |  | V |  | CGS Global Support, LLC | PR Approved | PO Approved | R1 : order is cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 580 | P | USC2312023A |  | Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards KETRT7 | 45265 | 45268 | 5572.37 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5572.37 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 5572.37 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 581 | P | USC2312024A |  | Liquid Tite for EPI for the tool ID#KECPS3 | 45265 | 45267 | 44.67 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 44.67 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 44.67 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 582 | P | USC2312025A |  | EPI，Interconnection material Liquid tite 4 feet For KECPS3 | 45265 | 45267 | 29.78 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 29.78 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 29.78 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 583 | P | USC2312026A |  | KDSTS2 Mechanical Work and material | 45265 | 45268 | 57600 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 57031.6 | 0.99013 | 568.4 | 0 | 568.4 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 44696.32 |  | 0 | 12335.28 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 584 | P | USC2312027A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45266 | 45268 | 680.88 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 680.87 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 680.87 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 585 | P | USC2312028A |  | LABOR & MATERIAL FOR GALVANIZED DUCT/ELBOWS FOR BLOWER BOX IN LB1. INSTALLATION OF H-BAR IN L10. | 45266 | 45268 | 133012.8 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 113911.63 | 0.8564 | 19101.17 | 0 | 19101.17 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 4064.28 | 3694.8 | 21605.34 | 0 |  | 0 |  | 43182.99 |  | 41364.22 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 586 | P | USC2312029A |  | KST-70R Tube | 45266 | 45270 | 7406.93 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 7406.93 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 7406.93 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 587 | P | USC2312032A | -01 | 1 E-OPS to pull cable for KCEPS3 | 2023/12/7 2024/1/6 | 2023/12/11 2024/3/7 | 360.75 | 194.25 | 166.5 |  |  | V |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | Revised for higher labor hours |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 360.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 360.75 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 588 | P | USC2312033A |  | FLEX LT3UAGRY | 45267 | 45271 | 574.58 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 574.58 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 574.58 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 589 | P | USC2312034A |  | PVC MALE ADPT N80 2.5" SXMT SPEA MFG P/N 836-025 | 45268 | 45272 | 6637.11 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 6637.04 | 0.99999 | 0.07 | 0 | 0.07 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 6383.74 | 253.3 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 590 | P | USC2312035A |  | workers for 3 days to install exhaust duct between L10 and LB1 for the TOOL KDPOT1 | 2023/12/8 2024/8/22 | 2023/12/8 2024/8/22 | 0 | -104 | 104 |  |  |  | V | Westerwood Global USA Corporation | PR Approved | PO Approved | PR R1: PO never was used. Need to be deleted |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 591 | P | USC2312036A |  | For the PO renewal of Daniel Dircio, in the Project Coordinator (Tool Interconnect) position. 6 month PO for the amount of 99,600.00 | 45268 | 45273 | 99600 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 40778.6 | 0.40942 | 58821.4 | 0 | 58821.4 | 0 | [45 empty] | 0 | 0 | 0 | 40778.6 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 592 | P | USC2312037A | -01 | KPOCS2 Exhaust Hookup | 2023/12/8 2024/3/26 | 2023/12/12 2024/3/27 | 45921.75 | 4355.25 | 41566.5 | V |  |  | V | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PR R1: Updated amount for KPOCS2 billing issue. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 45921.75 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 45921.75 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 593 | P | USC2312038A | -01 | KPAN01-S LIT 1 Streimers | 45269 | 2023/12/14 2024/1/31 | 58449.14 | -8057.26 | 66506.4 |  |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PR R1: Total amount change after 100% completion |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 58449.14 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 58449.14 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 594 | P | USC2312039A |  | KPAN02-S LIT 1 STREIMERS | 45269 | 45274 | 66506.4 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 13901.69 | 0.20903 | 52604.71 | 0 | 52604.71 | 0 | [45 empty] | 0 | 0 | 2771.1 | 0 | 0 |  |  | 11130.59 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 595 | P | USC2312040A |  | KPAP02-S LIT 1 STREIMERS | 45269 | 45275 | 66506.4 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11084.4 | 0.16667 | 55422 | 0 | 55422 | 0 | [45 empty] | 0 | 0 | 1847.4 | 0 | 0 |  |  | 9237 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 596 | P | USC2312041A |  | Installer Lead - Robert Nelson | 45271 | 45272 | 4352.46 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4352.46 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 4352.46 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 597 | P | USC2312042A |  | KPE603-S Cabinets | 45271 | 45275 | 53160 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 41730.6 | 0.785 | 11429.4 | 0 | 11429.4 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 10632 | 0 | 0 |  | 0 |  | 18911.67 | [11 empty] | 12186.93 | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 598 | P | USC2312043A |  | Rachel Smith - Installer | 12/12/2023 8/12/2024 | 12/19/2023 8/21/2024 | 0 | -732.5 | 732.5 |  |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: PO never was used. Needs to be deleted |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 599 | P | USC2312045A | -01 | KPE604-S Build ASML EUV Water Line & QC | 2023/12/12 2024/1/9 | 2023/12/15 2024/1/9 | 618000 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | Revision of Trade term from DDP to ExW |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 196240.24 | 0.31754 | 421759.76 | 0 | 421759.76 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 182532.16 | [5 empty] | 13708.08 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 600 | P | USC2312046A |  | KESRT1 in-house manpower EOPS | 45273 | 45303 | 3567.88 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3567.88 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 895.63 | 2672.25 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 601 | P | USC2312047A |  | 12/6/2023-12/20/2023 KESRT2 cable pull in-house manpower EOPS | 45273 | 45306 | 6365 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 6365 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 6365 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 602 | P | USC2312048A |  | KESDL1 cable pull in-house manpower EOPS | 45273 | 45278 | 632 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 632 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 632 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 603 | P | USC2312049A |  | KEPOL3- Interconnect cable pull for KEPOL3 (ETC1) | 45273 | 45275 | 632 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 632 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 632 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 604 | P | USC2312050A |  | Manpower Pay for KEMGL1 for WGN-star | 12/13/2023 8/27/2024 | 12/14/2023 8/29/2024 | 0 | -168 | 168 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | R1: Case Closed |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 605 | P | USC2312051A |  | Cable Pull for KDPOT2. 2 manpower for 1 day 11/10/2023. (Robert Nelson) | 45273 | 45274 | 707.63 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 707.63 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 707.63 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 606 | P | USC2312052A |  | KPOCS3-S Labor | 45274 | 45275 | 19372 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 18403.4 | 0.95 | 968.6 | 0 | 968.6 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 18403.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 607 | P | USC2312053A |  | KPOCT1 Labor | 45274 | 45274 | 9066 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 9066 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 9066 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 608 | P | USC2312054A |  | Manpower Pay for KEPOT1 for RS PAYROLL | 45274 | 45362 | 3428 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 0 | 0 | 3428 | 0 | 3428 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 609 | P | USC2312055A |  | KPE603-S T&M Installation for pipes (SS, PVC, PVDF, PP) Ball Valves, Pipe insulation, Cut Beam | 45274 | 45279 | 308225.43 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 308225.43 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 308225.43 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 610 | P | USC2312056A |  | Manpower Pay for KESTT1 for DELTA WYE | 45274 | 45352 | 14219 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 14219 | 0 | 14219 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 611 | P | USC2312057A |  | Perform interconnection on KEPCH1 | 45274 | 45318 | 2874.08 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 2551.57 | 0.88779 | 322.51 | 0 | 322.51 | 0 | [47 empty] | 0 | 0 | 1667.08 |  |  | 0 | 0 | 0 |  | 884.49 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 612 | P | USC2312058A |  | LAM Interconnect cable pull for KESTL7 (ETC1) TSMC M.4/3.5 Lvl. L30 | 2023/12/15 2024/8/12 | 2023/12/15 2024/8/12 | 0 | -255.6 | 255.6 | V |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 613 | P | USC2312059A |  | KETRT7- Cut out 7 holes. Install 7 gromets and terminate 7 cables to AC box | 2023/12/16 2024/8/12 | 2023/12/18 2024/8/13 | 0 | -286 | 286 |  |  |  | V | San Tan Fire, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 614 | P | USC2312060A |  | TSMC20 管路貼紙 【防水、撕不破】 【耐曬油墨】:Stickers for piping system 100 X 15 mm (4”X0.6”) | 45276 | 45278 | 1950 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1950 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 1950 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 615 | P | USC2312061A |  | Manpower Pay for KDSTS1 with BRAHMA GROUP | 2023/12/16 2023/12/20 | 45314 | 101870.2 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | PR R1: because we are anticipating them working OT so we took the day |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 92114.55 | 0.90423 | 9755.65 | 0 | 9755.65 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 | 62984.26 |  | 29130.29 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 616 | P | USC2312062A |  | Project Coordinator, Robert Almanza, Tool Interconnect, 6 month contract at $16,600 | 45276 | 45280 | 99600 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 43701.7 | 0.43877 | 55898.3 | 0 | 55898.3 | 0 | [45 empty] | 0 | 16786.02 | 12805.68 | 14110 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 617 | P | USC2312063A | -01 | Manpower Pay for KDSTS4 with BRAHMA GROUP | 45276 | 2023/12/18 2024/2/27 | 101870.02 | 91683 | 10187.02 | V |  |  |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | PR R1: 10x Price change in scope. Subcontractor agreed in 18 cents different |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 93705.81 | 0.91986 | 8164.21 | 0 | 8164.21 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 49318.76 | 0 | 44387.05 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 618 | P | USC2312064A |  | Pay for San Tan for Tools KEBCT1, KEBCT2, KEPST1, KEPST2 | 45279 | 45290 | 27991.24 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27991.24 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  | 27991.24 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 619 | P | USC2312065A |  | Labor for KCAOA4 - EMT conduit and liquid tie conduit, run wire between L10, L20, L30 | 45279 | 45279 | 7808 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 7808 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 7808 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 620 | P | USC2312066A |  | KPD801-S Labor | 45280 | 45287 | 15510 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 14734.5 | 0.95 | 775.5 | 0 | 775.5 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 14734.5 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 621 | P | USC2312067A |  | RP350 BATRY PRESS TOOL NO JAWS 4-PCS RP350 STOCK CHANDLER | 45280 | 45280 | 10451.37 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10451.37 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 10451.37 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 622 | P | USC2312068A |  | FLEX LT3UAGRY | 45280 | 45281 | 573.54 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 573.54 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 573.54 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 623 | P | USC2312069A |  | FLEX LT3UAGRY | 45280 | 45280 | 573.54 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 573.54 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 573.54 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 624 | P | USC2312072A |  | KPAP02-T Interconnect Labor | 45281 | 45288 | 105000 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 105000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 105000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 625 | P | USC2312074A |  | KPI401-S INTERCONNECT LABOR | 45282 | 45287 | 42000 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 42000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 42000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 626 | P | USC2312075A |  | KPAP02-S INTERCONNECT LABOR | 45282 | 45287 | 45000 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 45000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 627 | P | USC2312076A | -01 | KPAN02-S INTERCONNECT LABOR | 45282 | 2023/12/28 2024/1/4 | 45000 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | R1: Remark Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 45000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 628 | P | USC2312077A |  | KPAP01-S Labor | 45282 | 45287 | 3511 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3335.45 | 0.95 | 175.55 | 0 | 175.55 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 3335.45 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 629 | P | USC2312078A |  | KPAN02-S Labor | 45282 | 45288 | 20260 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20260 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 20260 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 630 | P | USC2312079A |  | KPOCS1 & KPOCS3 Labor Lit 3 Streimers Install | 45282 | 45287 | 11084.4 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1847.4 | 0.16667 | 9237 | 0 | 9237 | 0 | [45 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 1847.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 631 | P | USC2312080A |  | Interconnect cable pull for KETRT4 (ETC3), Interconnect cable pull, Ewah considered & implemented suggestions during our initial installation of interconnect work. Includes interconnect rework. | 45283 | 45303 | 2050.01 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 486.88 | 0.2375 | 1563.13 | 0 | 1563.13 | 0 | [45 empty] | 0 |  | 0 | 0 | 486.88 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 632 | P | USC2312081A |  | Interconnect cable pull for KETRT4 (ETC3), Includes initial interconnect cable pull, Ewah considered & implemented suggestions during our initial installation of interconnect work. Includes interconnect rework. CGS 11/29-12/1 and 12/4-12/21. | 2023/12/23 2024/8/15 | 2024/1/20 2024/8/15 | 0 | -13454.31 | 13454.31 |  |  | V |  | CGS Global Support, LLC | PR Approved | PO Approved | R1 : Order cancelled to release allocated budget. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 633 | P | USC2312082A |  | Interconnect cable pull for KECOL4 (ETC2) | 45283 | 45289 | 719.1 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 719.1 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 719.1 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 634 | P | USC2312083A |  | Interconnect cable pull for KECOL4 (ETC2) | 2023/12/23 2024/8/14 | 2023/12/30 2024/8/16 | 0 | -532.8 | 532.8 |  |  | V |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | R1 :Case closed to release excess amount budgeted for the order.. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23B002 | Tool Interconnection Project (Main Tool & Module) | 635 | P | USC2312084A |  | Interconnect cable pull for KECOL4 (ETC2) | 2023/12/23 2024/8/12 | 2024/1/2 2024/8/12 | 0 | -441.6 | 441.6 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 636 | P | USC2401004A |  | KPD801-S Labor | 45300 | 45307 | 54219.71 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 54219.71 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 54219.71 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 637 | P | USC2401005A |  | KPOCS1 Exhaust Install Labor | 45300 | 45311 | 90929.86 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 90929.86 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 90929.86 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 638 | P | USC2401006A |  | KPI401-S Labor | 45300 | 45310 | 62713.51 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 62713.51 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 62713.51 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 639 | P | USC2401007A |  | SAN TAN FIRE, LLC. MANPOWER PAY | 45300 | 45307 | 4314.67 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4314.67 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 4314.67 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 640 | P | USC2401008A |  | KPOCT4 Labor | 45301 | 45308 | 3787.17 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3787.17 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 3787.17 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 641 | P | USC2401009A |  | KPD801-T Labor | 45301 | 45308 | 1385.55 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1385.55 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 1385.55 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 642 | P | USC2401010A |  | KPAN01-T Labor | 45301 | 45307 | 4616.65 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4616.65 | 1 | 0 | 89040 | -89040 | 0 | [45 empty] | 0 |  | 0 | 0 | 4616.65 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 643 | P | USC2401011A |  | Armaflex 1-1/8 X 1/2; 900ft X 1.3220 | 45301 | 45309 | 5650.12 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 5650.12 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 5650.12 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 644 | P | USC2401012A |  | SS-QTM4A-B-6PM: SS QT BODY QC 3/8" MNPT | 45302 | 45310 | 5647.6 |  |  |  | USCSB2401172A |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5647.6 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  | 4740.2 | 0 | 0 | 907.4 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 645 | P | USC2401013A |  | 1 1/4" S/10S LR 90 A/SA 403 WP 304/L-W | 45302 | 45323 | 16183.32 | [6 empty] | Industrial Pipe and Valve Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 16183.32 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 16183.32 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 646 | P | USC2401014A |  | P-NF-1/2: NUT, FEMALE, HTC | 45302 | 45309 | 22487.1 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 18649.05 | 0.82932 | 3838.05 | 0 | 3838.05 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 18649.05 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 647 | P | USC2401015A |  | KPOV05 Exhaust Piping Labor | 45302 | 45309 | 21947 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 21947 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 648 | P | USC2401016A |  | KPAN02-T Labor | 45302 | 45309 | 89040 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 89040 | 0 | 89040 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 649 | P | USC2401017A |  | KPE603-T Labor | 45302 | 45309 | 102986 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 102986 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 102986 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 650 | P | USC2401018A |  | KPOCT1 Labor | 45302 | 45311 | 34510 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 34510 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 34510 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 651 | P | USC2401019A |  | MANPOWER PAY FOR CCE | 45303 | 45337 | 21474 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 21474 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 21474 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 652 | P | USC2401020A |  | Interconnect cable pull for KETRT4 (ETC3), Includes initial interconnect cable pull, Ewah considered & implemented suggestions during our initial installation of interconnect work. Includes interconnect rework. RS 11/29-12/1 | 2024/1/12 2024/8/12 | 2024/1/17 2024/8/12 | 0 | -2280.52 | 2280.52 |  |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 653 | P | USC2401022A |  | KETRT8- 11/15-12/20/2023 Cable pulls for power & signal interconnect. Cable rework for Ewah suggestions that were considered and implemented during our initial cable pulls. | 45303 | 45309 | 21451.81 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 21451.81 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 21451.81 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 654 | P | USC2401023A |  | Perform interconnection on KECOL3.12/11/2024 | 45303 | 45307 | 140 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 140 | 0 | 140 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 655 | P | USC2401024A |  | DIFF1: KIMIS1: CUSH CLAMPS FOR AIR & WATER HOSES | 45303 | 45304 | 392.4 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 392.4 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 392.4 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 656 | P | USC2401025A |  | LABOR | 45304 | 45308 | 3776 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3776 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 3776 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 657 | P | USC2401026A |  | LABOR | 45304 | 45308 | 1416 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1416 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1416 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 658 | P | USC2401027A |  | Cut and modify all AC covers on KECOT5 for power/signal cables per TEL spec. | 45304 | 45308 | 243.08 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 243.08 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 243.08 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 659 | P | USC2401028A |  | Cut and modify all AC covers on KECOT1 for power/signal cables per TEL spec. | 45304 | 45308 | 243.08 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 236 | 0.97087 | 7.08 | 0 | 7.08 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 236 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 660 | P | USC2401029A |  | Cut and modify all AC covers on KECOT2 for power/signal cables per TEL spec. | 45304 | 45307 | 243.08 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 243.08 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 243.08 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 661 | P | USC2401030A |  | 1 welder for 1 day/8 hrs. for welding flanges onto 4" exhaust adapters (7 total) for TOOL ID#- KDANTA, KDPOT4, KDPOT5, KDEPT1 (2), KDEPT4 (2) | 1/16/2024 8/13/2024 | 1/22/2024 8/21/2024 | 0 | -448 | 448 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | R1: PO never was used. Needs to be deleted |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 662 | P | USC2401031A |  | KPOCS2-S | 45308 | 45309 | 106205 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 106205 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 106205 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 663 | P | USC2401032A |  | KPD802-T Labor | 45308 | 45311 | 108729 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 108729 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 108729 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 664 | P | USC2401033A |  | KPOCS2 Labor | 45308 | 45309 | 10141 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 10141 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 10141 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 665 | P | USC2401034A |  | Installers from SantanFire to conduct & complete interconnection work on KUECN1 | 45308 | 45308 | 3889.28 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3889.28 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 3889.28 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 666 | P | USC2401035A |  | Installers from SantanFire to conduct & complete interconnection work on KSHMU1 | 45309 | 45309 | 13612.48 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 13612.48 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 13612.48 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 667 | P | USC2401036A |  | Installers from SantanFire to conduct & complete interconnection work on KCSCN5 | 45309 | 45309 | 13612.48 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 13612.48 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 13612.48 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 668 | P | USC2401037A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45309 | 45309 | 578.18 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 669 | P | USC2401038A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45310 | 45309 | 1015.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 1015.19 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 1015.19 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 670 | P | USC2401039A |  | KPI401-S Nov 2023 Invoice for Labor | 45310 | 45314 | 14103.03 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 14103.03 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 |  |  | 0 | 14103.03 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 671 | P | USC2401040A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45310 | 45310 | 578.18 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 672 | P | USC2401042A |  | KPAP01-S Nov 2023 Invoice for Labor | 45311 | 45315 | 5746.06 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 5746.06 | 0 | 5746.06 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 673 | P | USC2401043A |  | KPAN01-S Nov 2023 Invoice for Labor | 45311 | 45316 | 21016.44 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21016.44 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 21016.44 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 674 | P | USC2401044A |  | KPAE01-S Nov 2023 Invoice for Labor | 45311 | 45314 | 11619.89 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10062.94 | 0.86601 | 1556.95 | 0 | 1556.95 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 10062.94 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 675 | P | USC2401045A |  | KECOT5 MANPOWER PAY FOR WGN STAR | 45311 | 45313 | 2002 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 2002 | 0 | 2002 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 676 | P | USC2401046A |  | KPE601-S RF Cable Tray Mesh Cover Installation | 45311 | 45314 | 5080.32 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 5080.32 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 5080.32 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 677 | P | USC2401047A |  | KECOT5 MANPOWER PAY FOR E-OPS | 45311 | 45314 | 307.5 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 307.5 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 307.5 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 678 | P | USC2401048A |  | YAV2CL2NT14FX90 BURNDY 2 AWG FLEX 15.140/ea 1514.00 CU COMPRESSION TERMINAL | 45311 | 45314 | 1707.74 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1707.74 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 1707.74 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 679 | P | USC2401049A |  | Cable pull KETRTE 12/6/2023 | 45311 | 45313 | 124.25 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 124.25 | 0 | 124.25 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 680 | P | USC2401050A |  | KECOT5 MANPOWER PAY FOR CGS GLOBAL | 45311 | 45313 | 276 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 276 | 0 | 276 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 681 | P | USC2401051A |  | Cable pull KETRTE 12/6/2023-CGS | 1/20/2024 8/11/2024 | 1/23/2024 8/21/2024 | 0 | -645.72 | 645.72 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 682 | P | USC2401052A |  | KECOT5 MANPOWER PAY FOR E-OPS | 45311 | 45314 | 1360.14 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1360.14 | 0 | 1360.14 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 683 | P | USC2401053A |  | KECOT5 MANPOWER PAY FOR WGN STAR | 45311 | 45314 | 1176 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1176 | 0 | 1176 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 684 | P | USC2401054A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45314 | 45314 | 578.18 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C001 | TEL Main Tool Interconnection | 685 | P | USC2401055A |  | KECOT1 MANPOWER PAY FOR SAN TAN FIRE,LLC. | 45314 | 45314 | 607.7 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 607.7 | 0 | 607.7 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 686 | P | USC2401056A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45314 | 45314 | 578.18 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 687 | P | USC2401057A | -01 | 2-1/2 VITON GSKT 1/8 THK 100 3.629 EA 362.90 3 DAYS ARO | 2024/1/23 2024/2/5 | 2024/1/23 2024/2/5 | 480 | 117.1 | 362.9 | V | V |  |  | Ferguson Enterprises, LLC | PR Approved | PO Approved | R1: Same Material, got sent the wrong size. description: 2-1/2 VITON GSKT 1/8 THK ORIGINAL ORDER # 1081114 CM379066 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 480 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  | 480 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 688 | P | USC2401058A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45314 | 45314 | 578.18 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 689 | P | USC2401060A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45314 | 45314 | 578.18 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 578.18 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 578.18 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 690 | P | USC2401061A |  | KPE603-S Labor | 45314 | 45316 | 7825 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7825 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 7825 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 691 | P | USC2401063A | -01 | Manpower to pull cable for KDANT4 1/22/2024-1/26/2024 ( RSPS ) | 2024/1/25 2024/3/14 | 2024/2/7 2024/3/14 | 3997.78 | 92.7 | 3905.08 | V |  |  |  | RS PAYROLL SERVICES | PR Approved | PO Approved | PO R1: PR needed to be adjusted to Match Invoices From RSPS |  | Tiong Sheng Poh | [11 empty] | 3997.74 | 0.99999 | 0.04 | 0 | 0.04 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 3997.74 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 692 | P | USC2401064A |  | A crew of 4 with a supervisor budget estimate working 10 hr shifts 4 days to complete triple containment hookups, pipe supports, and pressure testing per (1) Tool on T & M (approx. 16 tools total) & Materials (Tool Trailer, Tool Pick-up, Pipe Bender) | 45316 | 45328 | 352148.48 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 76037.27 | 0.21592 | 276111.21 | 0 | 276111.21 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 40567.38 | 0 | 0 |  | 0 |  |  |  | 35469.89 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 693 | P | USC2401065A |  | KPE603-S Labor | 45316 | 45317 | 7825 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7825 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 7825 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 694 | P | USC2401066A |  | KPE605-S Labor | 45316 | 45317 | 7825 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7825 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 7825 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 695 | P | USC2401067A |  | KPE606-S Labor | 45316 | 45317 | 7825 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7825 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 7825 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 696 | P | USC2401068A |  | KPE607-S Labor | 45316 | 45317 | 7825 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 7825 | 0 | 7825 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 697 | P | USC2401069A |  | KPE602-S Labor | 45316 | 45325 | 3800 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3800 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 3800 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 698 | P | USC2401070A |  | Labor and materials for KDSNB1 | 45316 | 45317 | 101870.2 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 96947.38 | 0.95168 | 4922.82 | 0 | 4922.82 | 0 | [47 empty] | 0 | 0 | 0 | 92169.02 |  | 0 | 4778.36 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 699 | P | USC2401071A |  | Labor and materials for KDSTS2 | 45316 | 45320 | 50935.1 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 48587.9 | 0.95392 | 2347.2 | 0 | 2347.2 | 0 | [47 empty] | 0 | 0 | 0 | 16431.99 |  | 0 | 32155.91 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 700 | P | USC2401072A |  | KESRT2 MANPOWER PAY for NETCOMN | 45316 | 45316 | 1932 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 0 | 0 | 1932 | 0 | 1932 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 701 | P | USC2401073A |  | KESRT2 MANPOWER PAY FOR RS PAYROLL | 45316 | 45322 | 1319.26 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 965.6 | 0.73193 | 353.66 | 0 | 353.66 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 965.6 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 702 | P | USC2401074A |  | KESRT2 MANPOWER PAY FOR CGS PAYROLL | 45316 | 45316 | 644 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 644 | 0 | 644 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 703 | P | USC2401075A |  | KRKRS1 AND KRWRS4 MANPOWER PAY BRAHMA GROUP, INC. | 45316 | 45318 | 61122.12 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 56938.57 | 0.93155 | 4183.55 | 0 | 4183.55 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 56938.57 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 704 | P | USC2401076A |  | KKDB03: CUT & ROLL EDGE ON DUCTING PIPE | 45317 | 45323 | 1000 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 500 | 0.5 | 500 | 0 | 500 | 0 | [48 empty] | 0 | 0 |  |  | 500 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 705 | P | USC2401077A |  | Nitrogen, Compressed, 2.2 Nitrogen T | 45317 | 45316 | 10895.74 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 10895.74 | 1 | 0 | 0 | 0 | 0 | [47 empty] | 0 | 0 | 0 | 10895.74 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 706 | P | USC2401078A |  | Cable pull KETRT1. - L30 to L20 Power/Signal - L30 to L10 Signals - L20 to L20 Power/Signal - L30 to L20 Chiller Hoses (QTY 2) - Install Signal Wrap - 8395 | 45317 | 45348 | 8797.97 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5965.27 | 0.67803 | 2832.7 | 0 | 2832.7 | 0 | [52 empty] | 0 | 0 | 0 |  | 5965.27 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 707 | P | USC2401079A |  | Electrical cable pull for KESTL4 | 1/26/2024 8/10/2024 | 2/28/2024 8/20/2024 | 0 | -3806.76 | 3806.76 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 708 | P | USC2401080A |  | MECHANICAL LABOR | 45317 | 45318 | 2622 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 2622 | 0 | 2622 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 709 | P | USC2401081A |  | KPE601-S RL MECHANICAL HVAC LABOR PAY | 45317 | 45317 | 322 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 322 | 0 | 322 | 0 | [47 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 710 | P | USC2401082A |  | Lit 2: KPE602-S: Labor: RF Cable Tray Mesh Cover Installation | 45318 | 45322 | 5080.32 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5080.32 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 5080.32 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 711 | P | USC2401083A | -01 | ME: KKDB03: 10" Exhaust Ducting Installation | 2024/1/27 2024/4/6 | 2024/2/1 2024/4/10 | 20316.7 | 16361.8 | 3954.9 |  |  | V |  | BRAHMA GROUP, INC. | PR Approved | PO Approved | R1: Addtl' hrs/days added. Broken down from preparing, install, & rental/materials. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20316.7 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 20316.7 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 712 | P | USC2401086A |  | KCSOA1 regular interconnect for cable pull | 45321 | 45322 | 7778.56 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 7778.56 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 7778.56 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 713 | P | USC2401087A |  | KCANN3 regular interconnect and cable pull | 45321 | 45322 | 7778.56 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 7778.56 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 7778.56 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 714 | P | USC2401089A |  | Lit 2: KPE603-S: RF Cable Tray Mesh Cover Installation | 45321 | 45322 | 5080.32 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5080.32 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 5080.32 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 715 | P | USC2401090A | -01 | Lit 2: KPE604-S: RF Cable Tray Mesh Cover Installation | 45321 | 2024/1/31 2024/5/11 | 0 | -5080.32 | 5080.32 |  |  | V | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | PR R1: No longer use CCE |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 716 | P | USC2401091A | -01 | Lit 2: KPE605-S: RF Cable Tray Mesh Cover Installation | 45321 | 2024/1/31 2024/5/11 | 0 | -5080.32 | 5080.32 |  |  | V | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | PR R1: No longer use CCE |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 717 | P | USC2401092A |  | Manpower Pay for CGS for Tool ID: KEPOL6 Timecard on 1.29.2024 Workers Rafael Osorio and Eloy Pacheco | 45321 | 45398 | 460 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 460 | 0 | 460 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 718 | P | USC2401093A | -01 | KPE606-S Labor | 2024/1/30 2024/5/13 | 2024/2/1 2024/5/13 | 0 | -5080.32 | 5080.32 |  |  | V | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | PR R1: No longer use CCE |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 719 | P | USC2401094A | -01 | KPE607-S RF Cable Tray Mesh Cover Installation | 2024/1/30 2024/5/13 | 2024/2/1 2024/5/13 | 0 | -5080.32 | 5080.32 |  |  | V | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | PR R1: No longer use CCE |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 720 | P | USC2401095A |  | KPE605-S Labor | 45321 | 45325 | 90000 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 90000 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 90000 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 721 | P | USC2401096A |  | KPE606-S Labor | 45321 | 45325 | 180000 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 180000 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 180000 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 722 | P | USC2401097A |  | KPE603-S Labor | 45321 | 45323 | 12700.8 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12700.8 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 12700.8 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 723 | P | USC2401098A |  | FLEX LT3UAGRY | 45321 | 45321 | 963 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 963 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 921.69 |  | 41.31 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 724 | P | USC2401099A |  | KPE603-S Labor | 45321 | 45324 | 33868.8 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 33868.8 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 33868.8 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 725 | P | USC2401100A |  | KPD802-S Labor | 45321 | 45323 | 46994 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 46994 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 46994 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 726 | P | USC2401101A |  | FLEX LT3UAGRY | 45321 | 45321 | 618.11 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.11 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.31 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 727 | P | USC2401102A |  | FLEX LT3UAGRY | 45321 | 45321 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 728 | P | USC2401103A |  | KPSOT1 Vex Duct Material | 45321 | 45323 | 66377 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 66377 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 66377 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 729 | P | USC2401104A |  | PAN FSD748D #24 PP DIN 1W FRL PANDUIT FSD74-8-D COVERED SINGLE WIRE FERRULE | 45321 | 45321 | 619.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 619.17 | 0.99995 | 0.03 | 0 | 0.03 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 619.17 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 730 | P | USC2401105A |  | DOT DT75SB 3/4-3/4 MNTG BASE - BLACK 3/4 X 3/4IN ADHESIVE MOUNTING BASES - U.V. BLACK | 45322 | 45322 | 338.1 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 338.1 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 338.1 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 731 | P | USC2401106A |  | BUR BTCGC1/0SS GROUND CLAMP | 45322 | 45322 | 1033 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 1033 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 1033 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 732 | P | USC2401107A |  | FLEX LT3UAGRY | 45322 | 45322 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 733 | P | USC2401108A |  | FLEX LT3UAGRY | 45322 | 45322 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 734 | P | USC2401109A |  | Skywalker Cable Caddy, Cable Holder (Max Weight 100 lbs.)Skywalker Cable Caddy, Cable Holder (Max Weight 100 lbs.) | 45322 | 45322 | 98.98 | [6 empty] | Amazon | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 89.08 | 0.89998 | 9.9 | 0 | 9.9 | 0 | 89.08 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 735 | P | USC2401110A |  | FLEX LT3UAGRY | 45322 | 45322 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 736 | P | USC2401112A |  | FLEX LT3UAGRY | 45322 | 45322 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 737 | P | USC2401113A |  | FLEX LT3UAGRY | 45322 | 45322 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 738 | P | USC2401114A |  | FLEX LT3UAGRY | 45322 | 45322 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 739 | P | USC2401115A |  | ULINE H-2084 48"X24"X69" SECURITY CART | 45322 | 45323 | 3273.2 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 2740 | 0.8371 | 533.2 | 0 | 533.2 | 0 | 2740 | [47 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 740 | P | USC2402002A |  | Stock Code: SPVCGY.1250 WHSE:CE0001. DESC.:0125 Thick Gray PVC Sheet (Per Piece) 48"x48" (Covers for A/C Boxes) | 45323 | 45324 | 60.5 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 55 | 0.90909 | 5.5 | 0 | 5.5 | 0 | [48 empty] | 0 | 0 |  | 55 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 741 | P | USC2402004A |  | C406-010 1" 90 Elbow S CLR PVC SCH40 | 45323 | 45323 | 103.65 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 103.65 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 103.65 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 742 | P | USC2402006A |  | 92240A911; 18-8 Stainless Steel Hex Head Screw, 3/8"-16 Thread Size, 1" Long, Packs of 25 | 45323 | 45323 | 3507.19 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3507.19 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 3507.19 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 743 | P | USC2402008A |  | KESTL6 in house manpower labor for Interconnection power and signal | 45324 | 2024/3/7 2024/8/14 | 0 | -286.12 | 286.12 |  |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1:CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 744 | P | USC2402009A |  | KEPOL4 + ETC1 + Main Tool + Interconnect 1/30-1/31/2024 | 45324 | 2024/3/21 2024/814 | 0 | -2944 | 2944 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | PR R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Kuan-Chung Su | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 745 | P | USC2402010A |  | Electrical cable pull for KESDL2 and KESTL2. | 2/2/2024 8/10/2024 | 3/4/2024 8/20/2024 | 0 | -805 | 805 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 746 | P | USC2402012A |  | Electrical cable pull for KEPOL8 and KEPOL2- L30 - L20 Cable drop. | 45324 | 45352 | 874 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 0 | 0 | 874 | 0 | 874 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 747 | P | USC2402013A |  | Perform interconnection on KEPRL2. | 45324 | 45355 | 2332.4 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 2332.4 | 0 | 2332.4 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 748 | P | USC2402014A |  | KEPRL3 in house manpower-TSMC + ETC2 + KEPRL3 + Interconnect 2/8/2024, 2/9/2024, 2/12/2024 | 45324 | 45355 | 2090.24 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 2090.24 | 0 | 2090.24 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 749 | P | USC2402015A |  | FLEX LT3UAGRY | 45324 | 45327 | 961.95 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 961.95 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 920.63 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 750 | P | USC2402016A |  | KPE602-S & KPE603-S Labor | 45324 | 45327 | 3497 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 3497 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 3497 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 751 | P | USC2402017A |  | FLEX LT3UAGRY | 45324 | 45327 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 752 | P | USC2402018A |  | FLEX LT3UAGRY | 45324 | 45327 | 636.84 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 636.84 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 595.52 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 753 | P | USC2402019A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45324 | 45327 | 963.02 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 963.01 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 921.69 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 754 | P | USC2402020A |  | FLEX LT3UAGRY | 45324 | 45327 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 755 | P | USC2402021A |  | FLEX LT3UAGRY | 45324 | 45327 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 756 | P | USC2402022A |  | FLEX LT3UAGRY | 45324 | 45327 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 757 | P | USC2402023A |  | FLEX LT3UAGRY | 45324 | 45327 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 758 | P | USC2402024A |  | FLEX LT3UAGRY | 45324 | 45327 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 759 | P | USC2402025A |  | KPOV06 Exhaust Piping Labor | 45325 | 45331 | 21947 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 760 | P | USC2402026A |  | KPOV07 Exhaust Piping Labor | 45325 | 45331 | 21947 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 761 | P | USC2402027A |  | KPOV08 Exhaust Piping Labor | 45325 | 45331 | 21947 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 762 | P | USC2402028A |  | KPAN03-T Labor | 45325 | 45336 | 83728 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 83728 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 83728 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 763 | P | USC2402029A |  | KPOCT6 Labor | 45325 | 45336 | 60289 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 60289 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 60289 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 764 | P | USC2402032A |  | 784R30 Plastic Welding Rod Manufacturer: USA INDUSTRIALS Part Number: BULK-WR-PVDF-1 | 45328 | 45328 | 129.01 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 129.01 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 | 129.01 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 765 | P | USC2402033A |  | KETRTB L30-L20 cable drop, L20-L10 cable drop, routing cables and 8395 | 45328 | 45330 | 34669.29 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 34669.29 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 34669.29 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 766 | P | USC2402034A |  | WET cable pull brycone manpower support for one month T&M KDCRS5 KDHBS1, KDMRS2, KDSNS1, KDMRS1, KDMRS4, KCSCS3, KEPSL5, KEPSL3, KEPSL1, KDCCS1 KEPSL4, KDCRS4, KDCCS2, KDCCS3, KCSCSA, KEBCL1, KEBCT3 | 45328 | 45337 | 150616.48 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 95549.21 | 0.63439 | 55067.27 | 0 | 55067.27 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 95549.21 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 767 | P | USC2402035A |  | KETRTE and KETRTC labor-cable pull, L30-L20 cable drop, routing cables and 8395 | 45329 | 45330 | 7808.95 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 7808.95 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 7808.95 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 768 | P | USC2402037A |  | Rafael Osorio and Eloy Pacheco Electrical cable pull for KEBEL2. ETCH 1 INTERCONNECTS. CGS. | 2024/2/7 2024/8/12 | 2024/2/6 2024/8/13 | 0 | -276 | 276 |  |  |  | V | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yi En Wong | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 769 | P | USC2402038A |  | KETRT4 San Tan Fire Manpower Pay | 45329 | 45332 | 5712.38 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 5712.38 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5712.38 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 770 | P | USC2402039A |  | Electrical cable pull for KESTL4 | 45329 |  | 1690 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 1690 | 0 | 1690 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 771 | P | USC2402040A |  | Electrical cable pull for KEPOL8 and KEPOL2 - LAM Interconnections | 45329 | 45352 | 703.04 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 703.04 | 0 | 703.04 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 772 | P | USC2402044A |  | Electrical cable pull for KESRT5 | 2/7/2024 8/10/2024 | 2/28/2024 8/22/2024 | 0 | -4759.56 | 4759.56 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 773 | P | USC2402045A |  | Electrical cable pull for KESRT5 | 45329 |  | 4918.44 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 4918.44 | 0 | 4918.44 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 774 | P | USC2402046A |  | KETRT8 MANPOWER PAY FOR SAN TAN FIRE | 45329 | 45332 | 1336.94 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1336.94 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 1336.94 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 775 | P | USC2402047A |  | KETRT4 MANPOWER PAY FOR CCE | 45329 | 45337 | 10584 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 10584 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 10584 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 776 | P | USC2402048A |  | 01/29: PREPARE TO INSTALL DUCT WORK. | 45329 | 45331 | 19203.58 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 19203.58 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 19203.58 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 777 | P | USC2402049A |  | KETRT8 MANPOWER PAY FOR CCE | 45329 | 45337 | 13113 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 13113 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 13113 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 778 | P | USC2402050A |  | 2/5/2024: KPSP11: 3" FLEX HOSE INSTALLATION | 45329 | 45366 | 51570.94 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 51570.94 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 51570.94 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 779 | P | USC2402053A |  | Delta Wye KEMEL7 cable pull | 45330 | 45330 | 1766.75 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1766.75 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 1766.75 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 780 | P | USC2402054A |  | KEMEL8 Cable Pull: - L30 - L30 Cable Pull, - L30 - L20 Cable Pull, - Total ~20 Cables | 45330 | 45330 | 1552 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 1552 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 1552 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 781 | P | USC2402055A |  | BRADY***B30C-1125-595-YL | 45330 | 45331 | 3093.7 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 3093.7 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 3093.7 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 782 | P | USC2402056A |  | CGS - KETRT8 - Pull all power and signal cables from main tool module to power box and all relevant equipment. 8395 per TSMC standards | 45330 | 45332 | 371.92 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 0 | 0 | 371.92 | 0 | 371.92 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 783 | P | USC2402057A |  | FLEX LT3UAGRY | 45332 | 45335 | 618.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 618.12 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 576.8 |  | 41.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 784 | P | USC2402058A |  | I welder for 7 hrs. to weld 4 4" exhaust adapters and 3 6 inch exhaust adapters for tool ID# (KDANT1, KDPOT3, KDANT5, KDANTA | 2024/2/12 2024/8/22 | 2024/2/23 2024/8/22 | 0 | -448 | 448 |  |  |  | V | Westerwood Global USA Corporation | PR Approved | PO Approved | PR R1: PO never was used. Needs to be deleted |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 785 | P | USC2402059A |  | TB 2941NM | 45335 | 45337 | 1628.51 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai | [11 empty] | 1628.51 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 1628.51 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 786 | P | USC2402060A |  | Manpower pay to RS Payroll Services for Tool ID: KEPRL1 for Timecards 2.15, 2.16, 2.19, and 2.20.2024 | 45336 | 45392 | 3606.8 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 3606.8 | 0 | 3606.8 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 787 | P | USC2402061A |  | Pulling cables from L30 to L20 and L10 using ladders, scissor lifts, scaffolding, and hand tools. KCSOA5, KCANN3, KCAPN1, KSCTT1, KSHMU1 2/13-3/82024. | 45336 | 45379 | 9288.8 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2257.92 | 0.24308 | 7030.88 | 0 | 7030.88 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2257.92 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 788 | P | USC2402062A |  | KPOV14, KKSS01, KPSP08: CABLE PULL | 45336 | 45338 | 16774 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 14858 | 0.88578 | 1916 | 0 | 1916 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 14858 | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 789 | P | USC2402064A |  | Tool ID KEBCT1, Perform cable pull to all relevant units per cable lists and 8395 per TSMC spec. | 45336 | 45338 | 5833.92 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 5833.92 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5833.92 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 790 | P | USC2402065A |  | Tool ID KEPST1, Perform cable pull to all relevant units per cable lists and 8395 per TSMC spec. | 45336 | 45337 | 5833.92 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5833.92 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5833.92 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 791 | P | USC2402066A |  | Tool ID KEPST2, Perform cable pull to all relevant units per cable lists and 8395 per TSMC spec. | 45336 | 45337 | 5833.92 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5833.92 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5833.92 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 792 | P | USC2402067A |  | Tool ID KEBCT2, Perform cable pull to all relevant units per cable lists and 8395 per TSMC spec. | 45336 | 45337 | 5833.92 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 5833.92 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 5833.92 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 793 | P | USC2402069A |  | Manpower Pay for RS Payroll for Michael Rodriquez | 45336 | 45377 | 404.7 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 404.7 | 0 | 404.7 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 794 | P | USC2402070A |  | KPSP10: CABLE PULL | 45336 | 45337 | 3832 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 3832 | 1 | 0 | 0 | 0 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 3832 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 795 | P | USC2402071A |  | BRADY M210 HANDHELD LABEL MAKER | 45337 | 45358 | 131.58 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 110.64 | 0.84086 | 20.94 | 0 | 20.94 | 0 | 110.64 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 796 | P | USC2402072A |  | manpower - general labors | 2024/2/16 2024/4/25 |  | 3620.25 | [7 empty] | PR Approved | PO Processing | PR R1:Uploading supporting documents |  | 0 | [11 empty] | 0 | 0 | 3620.25 | 0 | 3620.25 | 0 | [49 empty] | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 797 | P | USC2402073A |  | KETRT9 Trey in house. KETRT9 cable pull - L30-L20 Drop - L20-L10 Drop | 45339 |  | 937.89 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 937.89 | 0 | 937.89 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 798 | P | USC2402074A |  | HS Extra Long Heavy Duty Zip Tie Straps (50 Pack) | 45342 | 45343 | 248.88 | [6 empty] | Amazon | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 201.9 | 0.81123 | 46.98 | 0 | 46.98 | 0 | 201.9 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 799 | P | USC2402075A |  | Regular interconnect cable pull for PVD2 KSCBH1. Pull cables from L30 to L20, routing cables in cable trays/ conduits, following 8395 routing procedures. | 45343 | 45345 | 9723 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9723 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 9723 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 800 | P | USC2402076A |  | Pulling interconnect cabling on KSCTT1 from L30 to L20 and L10. Pulling cables from L30 to L20 and L10, using cable tray and conduit, and following the 8395 cable routing specifications. | 45343 | 45345 | 8437.76 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8437.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 8437.76 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 801 | P | USC2402077A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45343 | 45344 | 3563.78 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3563.78 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3563.78 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 802 | P | USC2402078A |  | Interconnect cable pull for ETC1 KESRT1 10/25, 10/26, 10/27, 11/8, and 11/9 2023 | 45343 | 45345 | 5422.1 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5422.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 5422.1 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 803 | P | USC2402079A |  | SS-400-1-4 MALE CONNECTOR 1/4" SWG X 1/4" MNPT | 45344 | 45344 | 258.2 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 258.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 258.2 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 791 | P | USC2402081A |  | Manpower Pay for Tool ID's KEMGT1 and KESRT5 for RS Payroll | 45344 | 45448 | 1662.96 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1662.96 | 0 | 1662.96 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 795 | P | USC2402082A |  | Manpower Pay to CGS GLOBAL FOR TOOL ID: KESRT5 for Timecards on 2.15 and 2.17.2024 | 45344 | 2024/5/1 2024/10/11 | 0 | -1265 | 1265 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 806 | P | USC2402083A |  | BPT 437SLTI | 45344 | 45344 | 219.35 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 807 | P | USC2402084A |  | 02/16/2024: KKDB02-1: 10" DUCT INSTALL | 45344 | 45362 | 14524.22 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 14524.22 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 14524.22 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 808 | P | USC2402085A |  | BPT 437SLTI | 45344 | 45344 | 219.35 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 809 | P | USC2402086A |  | BPT 437SLTI | 45344 | 45344 | 219.35 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 810 | P | USC2402087A |  | KPOCT7 Labor | 45344 | 45357 | 60289 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 60289 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 60289 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 811 | P | USC2402088A |  | BPT 437SLTI | 45344 | 45344 | 219.35 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 812 | P | USC2402089A |  | BPT 437SLTI | 45344 | 45346 | 219.35 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 813 | P | USC2402090A |  | BPT 437SLTI | 45345 | 45346 | 219.35 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 814 | P | USC2402091A |  | BPT 437SLTI | 45345 | 45346 | 219.35 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 219.35 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 219.35 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 815 | P | USC2402092A |  | Double contained plastic line and chiller power line from module to tool in L30 for KSECN3 | 45345 | 45349 | 10103.72 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 10103.72 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 10103.72 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 816 | P | USC2402094A |  | 4NKN6 SHRINK TUBING 100 FT. | 45345 | 45346 | 78.25 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 0 | 0 | 78.25 | 0 | 78.25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 817 | P | USC2402095A |  | Regular interconnect cable pull for PVD2 KCTEN1. Pull cables from L30 to L20, routing cables in cable trays/ conduits, following 8395 routing procedures. | 45345 | 45348 | 6328.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 6328.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 818 | P | USC2402096A |  | Regular interconnect cable pull for PVD2 KSCBH2. Pull cables from L30 to L20, routing cables in cable trays/ conduits, following 8395 routing procedures. | 45345 | 45348 | 6328.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 6328.32 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 819 | P | USC2402097A |  | Regular cable interconnect for KCOXN7. Pull cables from L30 to L20 and L10, following NEC code and TSMC 8395 routing specifications. | 45345 | 45348 | 6328.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Jen-Ping Tsai |  |  |  | Jen-Ping Tsai | [7 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 6328.32 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C014 | F21P1 AMHS Power Panel | 820 | P | USC2402098A |  | manpower - general labors | 2024/2/23 2024/4/27 |  | 0 | [6 empty] | 0 | PR Approved | PO Approved | PR R1:please close this PR. Was never in use | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 821 | P | USC2402099A |  | F21P1-KPE602-S Labor: Removal and addition of GAS Pipelines | 45346 | 45348 | 23000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 23000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 23000 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 822 | P | USC2402100A |  | KPE601-S and KPE602-S Labor: H2/AR_VENT_S-gland Damage modifications | 45346 | 45348 | 31000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 31000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 31000 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 823 | P | USC2402101A |  | Manpoer Pay for Delta Wye | 45346 |  | 1836.25 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1836.25 | 0 | 1836.25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 824 | P | USC2402103A |  | KETRT1 labor-cable pull. - RMF L30-L20 Signal Pull - L20 8395 | 45349 | 45348 | 4861.6 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4861.6 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 4861.6 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 825 | P | USC2402105A |  | Cable pull KESRT2 | 2024/2/27 2024/8/14 | 2024/2/26 2024/8/16 | 0 | -527.73 | 527.73 |  |  | V |  | RS PAYROLL SERVICES | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 826 | P | USC2402106A |  | Interconnection cable pull for KDSET1, KDCRS5, KDMRS3, KDCRS1, KDHBS1, KDMRS2, KDSNS1, KDMRS1, KDMRS4, KCSCS3, KEPSL5, KEPSL3 KEPSL1, KDCCS1, KEPSL4, KDCRS4, KDCCS2, KDCCS3, KCSCSA, KEBCT3, KRWRS7, KCSCS9 KCSCS7, KEPSL6, KEPSS1, KCSCSB, KCSCSC KEPST4, KCSCS6, KEPSL2 | 45349 | 45357 | 464666.96 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 432000.56 | 0.9297 | 32666.4 | 0 | 32666.4 | 0 | [52 empty] | 0 | 0 | 54666.96 |  | 0 | [5 empty] | 377333.6 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 827 | P | USC2402107A |  | LIBRATON 2PCs Pipe Cutter Replacement Blade for Pipe Cutter for Cutting Pipes of Aluminum, Copper, PVC, Thin Stainless Steel Tube | 45349 | 45350 | 3031.5 | [6 empty] | Amazon | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2752.05 | 0.90782 | 279.45 | 0 | 279.45 | 0 | 2752.05 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 828 | P | USC2402108A |  | Manpoer Pay for Delta Wye | 45349 | 45351 | 11675.5 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11675.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 11675.5 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 829 | P | USC2402109A |  | Manpoer Pay for Delta Wye | 45349 | 45353 | 9078 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 9078 | 0 | 9078 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 830 | P | USC2402110A |  | Manpower Pay for Delta Wye | 45349 | 45353 | 2244 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 2244 | 0 | 2244 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 831 | P | USC2402111A |  | Manpoer Pay for CGS for Tool ID's KEPOL7 and KEMGT1 | 45350 | 45376 | 1311 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 1311 | 0 | 1311 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 832 | P | USC2402114A |  | 1 welder, to weld, 6 exhaust flanges- KDANT3, KDANT7, KDANT6, KDPOTJ, KDEPT5 (2) | 2024/2/29 2024/3/7 2024/8/10 | 3/9/2024 8/22/2024 | 0 | -448 | 448 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | PR R1:whole amount needed to be calculated R2: PO never was used. Needs to be deleted |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 833 | P | USC2402115A |  | GSTRT GC112-300ASMBL COND CLAMP RGD COND CLP 3IN 12GA EG STEEL | 45351 | 45352 | 3925.19 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3925.19 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3925.19 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 834 | P | USC2402116A |  | BLINE 73A120 | 45351 | 45351 | 612.4 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 612.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 612.4 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 835 | P | USC2402117A |  | TransPak February partial operation fee | 45351 | 45352 | 1000000 | [6 empty] | Transpak, Inc. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [50 empty] | 1000000 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 836 | P | USC2403001A |  | Electrical cable pull for KESDL2 and KESTL2. | 45352 | 2024/3/1 2024/8/14 | 0 | -646.88 | 646.88 |  |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved | PR R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Kuan-Chung Su | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 837 | P | USC2403002A |  | Mechanical Interconnect - Labor KCSCS3, KEPSL5, KEPSL3, KEPSL1, KDCCS1 KEPSL4, KDCRS4, KDCCS2, KDCCS3, KCSCSA, KEBCL1, KRWRS7, KCSCS9, KCSCS7, KEPSL6 KEPSS1, KCSCSB, KCSCSC, KCSCS6, KEPSL2 | 2024/3/2 2024/8/12 | 2024/3/6 2024/8/13 | 0 | -147000 | 147000 |  |  |  | V | Trusval Technology CO., LTD. | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 838 | P | USC2403003A |  | SPL012: 1-1/4X10 FT PVC S40 CLR PIPE STOCK SPEARS | 45353 | 45356 | 1009.01 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1009.01 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1009.01 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 839 | P | USC2403004A | -01 | MANPOWER: PINNACLE PEAK WAREHOUSE | 45353 | 2024/3/15 2024/3/29 | 12828 | 4348 | 8480 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: Manpower Adjusted from -3/04-03/22/24 with 1 HR OT. |  | Ta Wei Wang | [11 empty] | 0 | 0 | 12828 | 0 | 12828 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 840 | P | USC2403005A |  | MANPOWER PAY FOR CCE | 45353 | 45363 | 430 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 0 | 0 | 430 | 0 | 430 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 841 | P | USC2403006A |  | MANPOWER PAY FOR CCE | 45353 | 45363 | 2466 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 2466 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2466 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 842 | P | USC2403007A |  | MANPOWER PAY FOR CCE | 45353 | 45401 | 883 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | 0 |  |  |  | 0 | [7 empty] | 0 | 0 | 883 | 0 | 883 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 843 | P | USC2403008A |  | MANPOWER PAY FOR CCE | 45353 | 45363 | 10440 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 10440 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 10440 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 844 | P | USC2403009A |  | KPOV09 Exhaust Piping Labor | 45355 | 45359 | 21947 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 845 | P | USC2403010A |  | KPAN02-S, KPAP02-S CABLE TRAY LABOR | 45356 | 45356 | 4935.6 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 4935.6 | 0 | 4935.6 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 846 | P | USC2403011A |  | KPI401-S Labor | 45356 | 45357 | 1207 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1207 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1207 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 847 | P | USC2403012A |  | KPE606-S BTS Precision Tube Cutting Labor | 45356 | 45359 | 3000 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 3000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 848 | P | USC2403013A |  | ZLMS01: CABLE PULLS | 45356 | 45364 | 3788 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 3788 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3788 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 849 | P | USC2403014A |  | Welding of stainless steel MPT nipple 304 to 316 pipe x 8 | 45356 | 45358 | 1200 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1200 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1200 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 850 | P | USC2403015A |  | KCSCS3 Pressure test | 45356 | 45356 | 4062.32 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4062.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 4062.32 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 851 | P | USC2403016A |  | KCSCS1 Pressure test | 45356 | 45359 | 8142.5 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8142.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 8142.5 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 852 | P | USC2403017A |  | Interconnect power and signal KESTL6 | 2024/3/6 2024/8/12 | 2024/3/6 2024/8/13 | 0 | -805 | 805 |  |  |  | V | CGS Global Support, LLC | PR Approved | PO Approved | R1: CASE CLOSED, RECLAIMED BACK TO BUDGET |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 853 | P | USC2403018A |  | KDSTL1 Interconnects-LAM IC KDSTL1- LAM IC KDSTL1- Labor | 45358 | 45362 | 58620.79 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 58620.79 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 58620.79 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 854 | P | USC2403019A |  | DNS SCREEN IC KDSTS6-KDSTS6 INTERCONNECT WET-labor is completed 1/20-2/12/2024 | 45358 | 45362 | 133199.33 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 133199.33 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 133199.33 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 855 | P | USC2403021A | -01 | 5401010 l” PIPE P/E HP PVDF 230PSI 16.4’ LGTH SOLD IN BAGS OF 3 | 2024/3/7 2024/4/21 | 2024/3/13 2024/5/2 | 246302.33 | 1367.94 | 244934.39 |  |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Updated quantity amount (original amnt 300) by 21 for line 3. Extra were shipped and PM decided to keep the extra 21 pieces. |  | Yikang Wang |  |  |  | 0 | [7 empty] | 246302.33 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 75640.95 |  | 170661.38 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 856 | P | USC2403022A |  | KPCD01: CABLE PULL | 45358 | 45364 | 32055 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 32055 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 32055 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 857 | P | USC2403023A |  | KKDB06: EXAHUST INSTALL ADDTL DAYS | 45358 | 45362 | 7896 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 7896 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7896 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 858 | P | USC2403024A |  | KPOV10 Exhaust Piping Labor | 45358 | 45362 | 21947 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 21947 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 859 | P | USC2403025A |  | Manpower Pay for CCE | 45358 | 45363 | 2292 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 2292 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2292 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 860 | P | USC2403026A |  | KPOCT2 Vex, Power, and Mechanical Labor | 45358 | 45363 | 61727 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 61727 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 61727 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 861 | P | USC2403027A |  | Precision Cuts KPE-604-S BTS | 45358 | 45358 | 3000 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | Ta Wei Wang | [7 empty] | 3000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 3000 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 862 | P | USC2403028A |  | Manpower Pay for CCE | 45358 | 45363 | 798 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 0 | 0 | 798 | 0 | 798 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 863 | P | USC2403029A |  | Manpower Pay for CCE | 45358 | 45363 | 5394 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 5394 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 5394 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 864 | P | USC2403030A |  | KPCD04: CABLE PULL | 2024/3/7 2024/3/16 | 45369 | 47000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 47000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 47000 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 865 | P | USC2403031A |  | U1AT375-062 TUBING-CUT STOCK 451 HPJ 3/8IN | 45359 | 45363 | 48991.25 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 48991.25 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 44811.25 | 4180 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 866 | P | USC2403032A |  | KPAP02-S PVC Rework Labor | 45359 | 45358 | 4593 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4593 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 4593 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 867 | P | USC2403033A |  | SUS304 10" DUCT(1.2M) | 45359 | 45372 | 7425.1 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 7425.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [13 empty] | 7425.1 | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 868 | P | USC2403034A |  | MANPOWER PAY FOR RS PAYROLL | 2024/3/8 2024/10/11 | 2024/3/12 2024/10/11 | 0 | -1924.81 | 1924.81 |  |  |  | V | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 869 | P | USC2403035A |  | Power Cable Materials from WESCO for KSMGA1, KSMGA2, KSHMA3, KEEBA1, KEPAA1 | 45359 | 45364 | 24658.73 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 24130.01 | 0.97856 | 528.72 | 0 | 528.72 | 0 | [52 empty] | 0 | 820.52 | 268.17 |  | 5889.33 |  | 8419.48 |  |  |  | 8732.51 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 870 | P | USC2403036A |  | MANPOWER PAY FOR CGS | 2024/3/8 2024/10/11 | 2024/3/11 2024/10/11 | 0 | -2622 | 2622 |  |  |  | V | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | 0 | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 871 | P | USC2403037A |  | MANPOWER PAY FOR WGN-Star | 45359 | 45362 | 420 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Ta Wei Wang |  |  |  | 0 | [7 empty] | 0 | 0 | 420 | 0 | 420 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 872 | P | USC2403038A |  | KDSNB2 IC-SHIB INTERCONNECTS 1/31-3/2/2024 | 45360 | 45363 | 120204.4 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 120204.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 120204.4 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 873 | P | USC2403039A |  | KDSTS8 IC- DNS SCREEN INTERCONNECTS - 2/6-3/2/2024 | 45360 | 45363 | 183566.91 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 183566.91 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 183566.91 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 874 | P | USC2403040A |  | KDSTS5 IC - DNS SCREEN INTERCONNECTS - 2/2-3/4/2024. | 45360 | 45363 | 104305.57 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | 0 | [7 empty] | 104305.57 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 104305.57 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 875 | P | USC2403041A |  | KDSTS9 IC - DNS SCREEN INTERCONNECTS - 2/13-3/4/2024. | 45360 | 45364 | 107845.96 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | 0 | [7 empty] | 107845.96 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 107845.96 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 876 | P | USC2403042A |  | KDCRS2 - DNS SCREEN INTERCONNECTS - 1/26-3/5/2024 | 45363 | 45363 | 146354.59 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 146194.22 | 0.9989 | 160.37 | 0 | 160.37 | 0 | [52 empty] | 0 | 0 | 146194.22 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 877 | P | USC2403043A |  | KDCRS3 - DNS SCREEN INTERCONNECTS - 1/18-3/5/2024 | 45363 | 45363 | 131555.19 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 131555.19 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 131555.19 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 878 | P | USC2403044A | -01 | 705 QC Solvent Cement PVC QT CLR Low VOC Med Bodied Fast Set MC/AC | 45363 | 2024/3/11 2024/3/12 | 731.28 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1: Change Location |  | Yikang Wang | [11 empty] | 731.28 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 731.28 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 879 | P | USC2403045A |  | BPT 437SLTI 3IN STR L/T CONN STEEL 3IN MALL LTI CONNECTOR | 45363 | 45363 | 8245.12 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 8245.11 | 1 | 0.01 | 0 | 0.01 | 0 | [52 empty] | 0 | 0 | 0 |  | 8245.11 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 870 | P | USC2403046A |  | Manpower Pay for CGS for Tool ID: KETRTA Time cards on 3.8, 3.11, and 3.13.2924 | 45363 | 45412 | 3024 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3024 | 0 | 3024 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 881 | P | USC2403047A |  | DAILY USE OF D/D KIT, D/D BITS, VAC/DUST EXTR, X-LINE LASER, CABLE CUTTER | 45363 | 45362 | 2032.05 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2032.05 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 2032.05 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 882 | P | USC2403050A |  | KPPTT1 VEX, Power, and Mechanical Labor | 45363 | 45364 | 118335 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 118335 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 118335 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 883 | P | USC2403051A |  | KPE605-T Vex Signal, Power, and Mechanical Install | 45363 | 45364 | 112574 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 112574 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 112574 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 884 | P | USC2403052A |  | BRADY***B30C-2250-569-GN: FACTORY SHIP LEAD TIME: 4-5 WEEKS PLUS FREIGHT | 45363 | 45364 | 218.17 | [6 empty] | Wesco Distribution, Inc. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 218.17 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 218.17 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 885 | P | USC2403053A |  | C Spanner Tool Adjustable Hook Wrench Nut Wrench-Square head, 95-165mm | 45363 | 45363 | 124.77 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 124.77 | 1 | 0 | 0 | 0 | 0 | 124.77 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 886 | P | USC2403055A |  | KPAN03-S PVDF 3/4" Piping Labor | 45364 | 45365 | 40711 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 40711 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 40711 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 887 | P | USC2403056A |  | KPAN03-S Cable Pull Labor | 45364 | 45365 | 45000 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 45000 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 878 | P | USC2403057A |  | MANPOWER PAY FOR TOOL ID: KETRTA FOR RS PAYROLL | 45364 | 45412 | 852 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 852 | 0 | 852 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 889 | P | USC2403058A |  | 2CEX5 90° Elbow: 1 in x 1 in Fitting Pipe Size, Schedule 40, Female Socket x Female Socket, Clear | 45364 | 45363 | 812.04 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 812.04 | 1 | 0 | 0 | 0 | 0 | 812.04 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 890 | P | USC2403059A |  | KST-70R TUBE (SIGNAL CABLE WRAPS) | 45364 | 45369 | 7406.93 | [6 empty] | MISUMI USA, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 7406.93 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 7406.93 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 891 | P | USC2403060A |  | Tube PFA 10x8x100M Roll | 45365 | 45364 | 1032.72 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1032.72 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 1032.72 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 892 | P | USC2403061A |  | KPOV11 Exhaust Piping Labor | 45365 | 45370 | 21947 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 21947 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 893 | P | USC2403062A |  | KPOV12 Exhaust Piping Labor | 45365 | 45370 | 21947 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 21947 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 21947 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 894 | P | USC2403063A |  | KDSTS3 - DNS SCREEN INTERCONNECTS - 2/1-3/6/2024 | 45366 | 45369 | 162207.42 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 162207.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 162207.42 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 895 | P | USC2403064A |  | KDCRS5 - DNS SCREEN INTERCONNECTS - 2/13-3/7/2024 | 45366 | 45370 | 147328.47 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 147328.47 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 147328.47 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 896 | P | USC2403065A |  | PFA-T10M-1M-30M 30m COIL 10M PFA Tubing | 45366 | 45365 | 3300.36 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 3300.36 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 3300.36 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 897 | P | USC2403066A |  | 2CFY3 Strt Adapter,PFA, PTFE, ETF Manufacturer: PARGRIP Part Number: GAMS-1212 | 45366 | 45369 | 1311.3 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1311.3 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 1311.3 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Outsourcing | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 898 | P | USC2403067A |  | welding for 3 flanges for tools KDPOT9 (2) & KDANT8 & should only 3hrs. | 3/15/2024 8/10/2024 | 3/26/2024 8/22/2024 | 0 | -448 | 448 |  |  |  |  | Westerwood Global USA Corporation | PR Approved | PO Approved | R1: PO never was used. Needs to be deleted |  | Yikang Wang | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 899 | P | USC2403068A |  | Michael Rodriguez 3/18-3/29 | 45367 | 45387 | 4316.8 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 4316.8 | 0 | 4316.8 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 886 | P | USC2403069A |  | Manpower pay for CGS Global for Tooll ID: KETRTE for time cards on 3.14, 3.15, 3.18, and 3.19.2024 | 45367 | 45426 | 4941.12 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4941.12 | 0 | 4941.12 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 901 | P | USC2403071A |  | Armando Pisqueria 3/18-3/22/2024 | 45367 | 45387 | 3124 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 1241 | 0.39725 | 1883 | 0 | 1883 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 1241 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 902 | P | USC2403073A |  | SS - 12 - E FNPT Elbow 3/4' | 45367 | 45367 | 621.24 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 621.24 | 1 | 0 | -174.5 | 174.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 621.24 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 903 | P | USC2403074A |  | Sellstrom Advantage Series Face Shield - Clear Window with Aluminum Binding - Comfortable Ratcheting Headgear, ANSI Z87.1+ (S30110) | 45367 | 45369 | 56.07 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 50.47 | 0.90012 | 5.6 | 0 | 5.6 | 0 | 50.47 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 904 | P | USC2403075A | -01 | 6 ft ladder | 45370 | 2024/3/19 2024/3/20 | 678.66 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | change remark based on revised PR |  | Yi En Wong | [11 empty] | 537.97 | 0.79269 | 140.69 | 0 | 140.69 | 0 | 537.97 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 905 | P | USC2403078A |  | Manpower Pay for Tool ID KEMEL6 for Delta Wye | 45370 | 45369 | 966 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 966 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 966 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 906 | P | USC2403079A |  | 32625T57 Strut-Mount Vibration-Damping Routing Clamp with TPE Rubber Cushion, Zinc-Plated Steel, 1-1/8" ID | 45370 | 45370 | 2434.27 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 2434.27 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 1192.32 | 0 |  | 1241.95 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 907 | P | USC2403080A |  | Manpower Pay for CGS Tool ID KEMEL4 | 45370 | 2024/3/26 2024/10/11 | 0 | -195.96 | 195.96 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 908 | P | USC2403081A |  | 9863001 Rental SP 110-S (V3) 20mm-110mm 1 IR welding tool | 45370 | 45371 | 13176.6 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6329.49 | 0.48036 | 6847.11 | 0 | 6847.11 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2137.18 |  | 4192.31 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 909 | P | USC2403082A |  | KDCRS4-Field Supervisor Ubaldo Ferreyra Jr | 2024/3/19 2024/8/15 | 2024/3/21 2024/8/16 | 0 | -2576 | 2576 |  |  | V |  | CGS Global Support, LLC | PR Approved | PO Approved | R1 ; Closing of order to release excess budget. |  | Tiong Sheng Poh | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 897 | P | USC2403083A |  | Manpower for Tool ID KETRT6 for RS Payroll | 45370 | 45457 | 2732.58 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2732.58 | 0 | 2732.58 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 911 | P | USC2403086A |  | 1" PVDF 90° Elbow | 45371 | 45377 | 156124.5 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 156124.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 156124.5 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 912 | P | USC2403087A |  | Manpower Pay for Tool ID: KEPRL5 for CGS | 2024/3/20 2024/3/26 | 45376 | 1005 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | PR R1: Calucaltion error needed to be corrected |  | Ta Wei Wang | [11 empty] | 0 | 0 | 1005 | 0 | 1005 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 913 | P | USC2403088A |  | U1AT1000-062 TUBING-CUT STOCK 451 HPJ 1IN | 45372 | 45377 | 75095 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 75095 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 49285 | [5 empty] | 25810 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 914 | P | USC2403089A |  | 212304PS10 2-1/2 S10 304L WLD PIPE === 60FT STOCK BALANCE 1 WEEK | 45372 | 45376 | 22900.81 | [6 empty] | Industrial Pipe and Valve Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 22900.81 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 22900.81 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 915 | P | USC2403091A |  | TEL INTERCONNECTS-KDSET1 2/27-3/15/2024 | 45372 | 45377 | 28234.54 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 28234.54 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 28234.54 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 916 | P | USC2403092A |  | KRWRS1&4-DNS SCREEN INTERCONNECTS-labor 2/17-3/15/2024 | 45372 | 45376 | 79137.11 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 79137.11 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 79137.11 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 917 | P | USC2403093A |  | KEBCT2-TEL INTERCONNECTS-labor 3/11/2024 | 45372 | 45372 | 3275.69 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 3275.69 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3275.69 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 918 | P | USC2403094A |  | KEPST2 -TEL INTERCONNECTS - Labor 3/2-3/15/2024 | 45372 | 45377 | 16213.05 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 16213.05 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 16213.05 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 919 | P | USC2403095A |  | KEBCT1-TEL INTERCONNECTS - Labor 3/13/2024 | 45372 | 45377 | 6073.77 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 6073.77 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6073.77 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 920 | P | USC2403096A | -01 | KCOCN1-3/22/2024 labor Eliseo Perez, Luis Rojas, Xavier Niesen | 45372 | 2024/3/29 2024/6/14 | 912 | 25.92 | 886.08 |  |  |  | V | CGS Global Support, LLC | PR Approved | PO Approved | R1: Adjusting the amount due to the rate discrepancy-invoice with correct rate is provided. |  | Ta Wei Wang | [11 empty] | 912 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 912 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 921 | P | USC2403097A |  | ABAA0158012 Armaflex 1-5/8 X 1/2 | 45373 | 45372 | 4713.66 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 4713.59 | 0.99999 | 0.07 | 0 | 0.07 | 0 | [52 empty] | 0 | 0 | 0 |  | 4713.59 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 922 | P | USC2403098A |  | Anti Static Clear PVC Backpack Cleanroom Engineer Tool Bag for Computer Tools Working Daypack | 45373 | 45373 | 125.33 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 113.94 | 0.90912 | 11.39 | 0 | 11.39 | 0 | 113.94 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 923 | P | USC2403099A |  | Manpower Pay for Tool ID: KETRT9 for Delta Wye | 45373 | 45381 | 15744.5 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 15744.5 | 0 | 15744.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 924 | P | USC2403100A |  | Manpower Pay for Tool ID: KETRT9 for CGS for Installer Mark Murray | 45373 | 45376 | 1424.69 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 1424.69 | 0 | 1424.69 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 925 | P | USC2403101A |  | Manpower Pay for Tool ID: KEMGT1 for CGS | 45373 | 45379 | 5175 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 5175 | 0 | 5175 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 911 | P | USC2403102A |  | Eliseo Perez - 3/25-4/30/2024 | 45374 | 45435 | 12312 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 12312 | 0 | 12312 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 927 | P | USC2403103A |  | DNS SCREEN INTERCONNECTS-KRWRS5-3/8-313/2024 | 45374 | 45377 | 27790.98 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 27790.98 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 27790.98 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 928 | P | USC2403104A |  | KRWRS2-DNS SCREEN INTERCONNECTS - 3/8-3/15/2024. | 45374 | 45378 | 22163.91 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 22163.91 | 1 | 0 | 227866.5 | -227866.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 22163.91 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 929 | P | USC2403105A |  | SS-1613-1 FRONT FERRULE 1" | 45374 | 45376 | 2468 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 2468 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2468 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 930 | P | USC2403106A |  | Manpower Pay for Tool ID: KESRT5 for CCE | 45374 | 45402 | 3565.25 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | 0 | [11 empty] | 0 | 0 | 3565.25 | 0 | 3565.25 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 931 | P | USC2403107A |  | Manpower Pay for Tool ID: KEPOL1 for CCE | 45374 | 45377 | 1137.5 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 1137.5 | 0 | 1137.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 932 | P | USC2403108A |  | KPE604-S CW and Gas Piping Labor | 45377 | 45392 | 303822 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 303822 | 0 | 303822 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 303822 | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 933 | P | USC2403109A |  | KPE606-S CW and Gas Piping Installation | 45377 | 45392 | 303822 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 303822 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [13 empty] | 303822 | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 934 | P | USC2403110A |  | KPE607-S CW and Gas Piping Labor | 45377 | 45392 | 303822 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 303822 | 0 | 303822 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 935 | P | USC2403111A |  | BPT 437SLTI: 3IN STR L/T CONN STEEL | 45377 | 45376 | 2518.53 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2518.53 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2518.53 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 936 | P | USC2403112A |  | 5406007 25mmx3/4" Fitting Trans BF PipexT Tube Flare HP PVDF | 45377 | 45377 | 270 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 270 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 270 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 937 | P | USC2403113A |  | Manpower Pay for CCE on 2.28.2024 for Tool ID KESRT2 | 45377 | 45377 | 1672 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 1672 | 0 | 1672 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 938 | P | USC2403114A |  | Manpower Pay for CCE on 3.6.2024 for Tool ID KETRT2 ETC 3 | 45377 | 45378 | 905.5 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 905.5 | 0 | 905.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 939 | P | USC2403115A |  | SS-12-E FNPT ELBOW 3/4" | 45377 | 45378 | 2070.8 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 2070.8 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 2070.8 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 940 | P | USC2403116A |  | SPL012 1-1/4X10 FT PVC S40 CLR PIPE | 45378 | 45377 | 247.46 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 247.46 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 247.46 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 941 | P | USC2403117A |  | Manpoer Pay for CCE for Tool ID: KEPOL8 | 45378 | 45378 | 905.5 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 0 | 0 | 905.5 | 0 | 905.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 942 | P | USC2403119A |  | KDBCS1 DNS CREEN INTERCONNECTS 2/17-3/23/2024 | 45378 | 45380 | 119641.38 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 119641.38 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 119641.38 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 943 | P | USC2403120A |  | KDSTSA DNS SCREEN INTERCONNECTS 2/12-3/21/2024 | 45378 | 45380 | 247415.57 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 247415.57 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 247415.57 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 944 | P | USC2403121A |  | Manpower Pay for CCE for Tool ID: KETRTE | 45378 | 45378 | 2275 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 2275 | 0 | 2275 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 945 | P | USC2403122A |  | Manpower Pay for CCE for Tool ID: KESTL6 | 45378 | 45378 | 1950 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 0 | 0 | 1950 | 0 | 1950 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 946 | P | USC2403123A |  | Regular interconnect cable pull on KCTOA1 for L30, L20, and L10 | 45378 | 45380 | 8437.76 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 8437.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 8437.76 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 947 | P | USC2403124A |  | Manpower Pay for CCE for Tool ID: KESTL2 | 45378 | 45379 | 1254 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 1254 | 0 | 1254 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 948 | P | USC2403125A |  | Regular interconnect cable pull for KCOCN1 on L30, L20, and L10 | 45378 | 45379 | 6328.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6328.32 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 949 | P | USC2403126A |  | Routing PFA chiller lines in L30 for KSECN3 | 45378 | 45379 | 197.76 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 197.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 197.76 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 950 | P | USC2403127A |  | 30XT36 Ring Terminal,Bare,6 AWG,6 AWG,PK10 | 45378 | 45379 | 3591.01 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 3591.01 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 3591.01 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 951 | P | USC2403128A |  | Manpower Pay for CCE for Tool ID: KEPOL2 | 45378 | 45379 | 1230.5 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 0 | 0 | 1230.5 | 0 | 1230.5 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 952 | P | USC2403129A |  | 5434007 3/4" UNION BF HP PVDF FKM TYPE G 230PSI: CPN-P-TIC-PD-UN-022 | 45379 | 45379 | 789.76 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 789.76 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 789.76 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 953 | P | USC2403130A |  | ABAA0158012 Armaflex 1-5/8 X 1/2; 522 FT X 1.7458 | 45379 | 45379 | 911.29 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 911.29 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 911.29 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 954 | P | USC2403131A |  | KDHBS1-DNS SCREEN INTERCONNECTS, 2/23-3/19/2024 | 45379 | 45384 | 126684.25 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 126684.25 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 126684.25 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 955 | P | USC2403132A |  | 5402010 1” 90 ELBOW SWP EXT LEG BF HP CPN-P-TIC-I-PD-EB-025 PVDF 230PSI | 45379 | 45383 | 78701.1 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 78701.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 78701.1 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 956 | P | USC2403133A |  | 5YE32 Corner Connector, 90 Degrees,Steel 40.00 EA 3.62 144.80 Manufacturer: APPROVED VENDOR Part Number: V321EG | 45380 | 45380 | 346.64 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | PR R1: per purchasing team, no longer need the shipping and must be zero out. |  | Kuan-Chung Su | [11 empty] | 346.64 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [11 empty] | 346.64 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 957 | P | USC2403134A |  | U1AT750-062 TUBING-CUT STOCK 451 HPJ 3/4IN | 45380 | 45383 | 37140 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 37140 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 37140 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 958 | P | USC2403135A |  | BLINE 73A120 for DRY ETC | 45380 | 45381 | 3827.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 3827.5 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 3827.5 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 944 | P | USC2403136A |  | Michael Rodriguez 4/2-4/30/2024 - 21 days x 8hrs. | 45380 | 45435 | 9384.48 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9384.48 | 0 | 9384.48 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 945 | P | USC2403137A |  | Xavier Niesen 4/1-4/30/2024 | 45380 | 45435 | 5712 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5712 | 0 | 5712 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 961 | P | USC2403138A |  | KDSTS2 Mechanical work | 45380 | 45384 | 31904.41 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 31904.41 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 31904.41 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 962 | P | USC2403139A |  | Manpoer Pay for Delta Wye for Tool ID: KETRTA ETC 3 | 45381 | 45385 | 31732 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 31732 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 31732 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 963 | P | USC2403140A |  | Manpoer Pay for Delta Wye for Tool ID: KETRTE ETC 3 | 45381 | 45383 | 14318.75 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 14318.75 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 14318.75 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 964 | P | USC2404001A |  | KDMRS2-DNS SCREEN INTERCONNECTS 3/19-3/20/2024 | 45384 | 45391 | 10913.84 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 10913.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 10913.84 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 965 | P | USC2404002A |  | KDCRS4-DNS SCREEN INTERCONNECTS 3/19-3/20/2024 | 45384 | 45388 | 117344.42 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 117344.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 117344.42 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 966 | P | USC2404003A |  | KDMRS1-DNS SCREEN INTERCONNECTS 3/5-3/26/2024 | 45384 | 45386 | 21164.63 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 21164.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 21164.63 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 967 | P | USC2404004A |  | KEPSL1-LAM INETRCONNECTS 3/5-3/26/2024 | 45384 | 45385 | 31687.42 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 31687.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 31687.42 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 968 | P | USC2404005A |  | KRWRS3 DNS SCREEN INETRCONNE 3/13-3/27/2024CTS | 45384 | 45388 | 54585.17 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 54585.17 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 54585.17 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 969 | P | USC2404006A |  | KDCCS2-DNS SCREEN INTERCONNECTS 3/6-3/26/2024 | 45384 | 45387 | 121499.59 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 121499.59 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 121499.59 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 970 | P | USC2404007A |  | KDCCS3- DNS SCREEN INTERCONNECTS 3/8-3/27/2024 | 45384 | 45387 | 97601.09 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 97601.09 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 97601.09 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 971 | P | USC2404008A |  | KCSCS7-DNS SCREEN INTERCONNECTS 3/11-3/26/2024 | 45384 | 45387 | 24111.63 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 24111.63 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 24111.63 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 972 | P | USC2404009A |  | 32625T56 Strut-Mount Vibration-Damping Routing Clamp with TPE Rubber Cushion, Steel, 1" ID, 1-7/16" Long | 45384 | 45384 | 354.78 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 354.78 | 1 | 0 | 278408 | -278408 | 0 | [52 empty] | 0 | 0 | 0 |  | 354.78 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 973 | P | USC2404010A |  | WIRE SO10/4 10/4 SOW-A SO TYPE; 250 FT; 250 LENGTH IN FT; COPPER CONDUCTOR MATERIAL; 600 V VOLTAGE RATING; -40 TO 60 DEG C TEMPERATURE RATING; 4 CONDUCTOR(S); EPDM RUBBER INSULATION MATERIAL; 10 AWG CONDUCTOR SIZE; COIL PACKAGE TYPE; 104 STRANDS STRANDING; BLACK JACKET COLOR | 45385 | 45385 | 2963.08 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 2963.07 | 1 | 0.01 | 0 | 0.01 | 0 | [52 empty] | 0 | 0 | 0 |  | 2963.07 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 974 | P | USC2404011A |  | KPE604-S Inventory Labor | 45385 | 45393 | 278408 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 278408 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [9 empty] | 278408 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 975 | P | USC2404012A |  | Connecting PFA chiller lines to chillers and tool, pressure testing lines for KSECN3 3/22-3/23/2024. | 45385 | 45386 | 9775.61 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 9775.61 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 9775.61 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Site Expense | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 976 | P | USC2404013A |  | Lifts rental for February 2x19'Micro 2/1-2/29/2024 | 45385 | 45385 | 897.31 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 897.31 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 897.31 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 977 | P | USC2404014A |  | KPE605-S Cable Support Labor | 45385 | 45386 | 39282 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 39282 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [5 empty] | 39282 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 978 | P | USC2404015A |  | KPE607-S Inventory Labor | 45385 | 45393 | 278408 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 278408 | 0 | 278408 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 979 | P | USC2404016A |  | Manpower Pay for RS Payroll for Tool ID: KEMGT1 Time cards 22.13, 2.14, 2.22,2.23, 2.24, 2.26, and 2.28.2024 | 45385 | 45387 | 10704.11 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 0 | 0 | 10704.11 | 0 | 10704.11 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 980 | P | USC2404017A |  | Manpower Pay for Delta Wye for Tool ID: KETRT2 Time cards 3.1, 3.4, 3.5, 3.7, 3.8, 3.11, and 3.16.2024 | 45385 | 45388 | 20169 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 20169 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 20169 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 981 | P | USC2404018A |  | Manpower Pay for CGS for Tool ID: KETRT2 Time cards 3.1,, and 3.4.2024 | 45385 | 45387 | 861 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 861 | 0 | 861 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 982 | P | USC2404019A |  | KPE604-S EUV ASML Cabinet Connection Support Labor | 45386 | 45393 | 99495 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 99495 | 0 | 99495 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 983 | P | USC2404020A |  | KPAN02-T Cable Grounding Installation Labor | 45386 | 45387 | 6993 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 6993 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 984 | P | USC2404021A |  | KPAP02-T Cable Grounding Installation Labor | 45386 | 45387 | 6993 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 6993 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 985 | P | USC2404022A |  | KPE602-T Cable Grounding Installation Labor | 45386 | 45387 | 6993 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 6993 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 986 | P | USC2404023A |  | Manpower Pay for Delta Wye for Tool IDs: KEBEL1 & KEMEL6 Time card 2.26.2024 | 45386 | 45387 | 1771 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 0 | 0 | 1771 | 0 | 1771 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 987 | P | USC2404024A |  | KDSNS1-DNS SCREEN INTERCONNECTS 3/4-3/28/2024 | 45386 | 45387 | 70701.4 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 70701.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 70701.4 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 988 | P | USC2404025A |  | KRWRS6-DNS SCREEN INTERCONNECTS 2/22-3/28/2024 | 45386 | 45387 | 53692.42 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 53692.42 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 53692.42 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 989 | P | USC2404026A |  | KDCRS1-DNS SCREEN INTERCONNECTS 3/7-3/28/2024 | 45386 | 45387 | 151273.59 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 151273.59 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 151273.59 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 990 | P | USC2404027A |  | KRWRS7-DNS SCREEN INTERCONNECTS 3/13-3/28/2024 | 45386 | 45387 | 54177.84 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 54177.84 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 54177.84 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 991 | P | USC2404028A |  | KDCCS1-DNS SCREEN INTERCONNECTS 3/7-3/28-2024 | 45386 | 45387 | 125117.32 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 125117.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 125117.32 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 992 | P | USC2404029A |  | 1304P 1 SCH 10 304L WLD PIPE === 100FT STOCK BALANCE 1 WEEK | 45386 | 45387 | 5723.6 | [6 empty] | Industrial Pipe and Valve Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 5612.98 | 0.98067 | 110.62 | 0 | 110.62 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 5612.98 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 993 | P | USC2404030A |  | DOT MB381 MACHINE BOLT | 45387 | 45390 | 6454.1 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6454.1 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 5729.72 |  | 724.38 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 994 | P | USC2404031A |  | Interconnect cable pull, routing, and 8395 compliance for KCSAO5. Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45392 | 7910.4 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 995 | P | USC2404032A |  | Interconnect cable pull, routing, and 8395 compliance for KCSOA3.Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45392 | 7910.4 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 996 | P | USC2404033A |  | Interconnect cable pull, routing, and 8395 compliance for KSCBH5,6,7,8. Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45393 | 10547.2 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 10547.2 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 10547.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 997 | P | USC2404034A |  | Interconnect cable pull, routing, and 8395 compliance for KCOXN8. Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45394 | 7910.4 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 998 | P | USC2404035A |  | Interconnect cable pull, routing, and 8395 compliance for KCTEN1. Pull cables from L30 to L20 and L10, follow 8395 specifications, route ca | 45387 | 45394 | 7910.4 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 999 | P | USC2404036A |  | Interconnect cable pull, routing, and 8395 compliance for KCTOA1.Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45394 | 7910.4 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 7910.4 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1000 | P | USC2404037A |  | Interconnect cable pull, routing, and 8395 compliance for KUECN2 and 3. Pull cables from L30 to L20 and L10, follow 8395 specifications, route cables and place conduits and dividers. | 45387 | 45387 | 1054.72 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su | [11 empty] | 1054.72 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1054.72 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 1001 | P | USC2404039A |  | wire and lug material | 45391 | 45392 | 1940.58 | [6 empty] | Rexel USA, INC. | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1940.58 | 1 | 0 | 0 | 0 | 0 | 1940.58 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment | USC23C036 | F21P1 AMAT Interconnection | 1002 | P | USC2404040A |  | heat gun | 45391 | 45392 | 548 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yikang Wang | [11 empty] | 548 | 1 | 0 | 0 | 0 | 0 | 548 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1003 | P | USC2404041A |  | MANPOWER: PINNACLE PEAK WAREHOUSE | 45391 | 45399 | 8160 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8160 | 0 | 8160 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1004 | P | USC2404042A |  | Manpower Pay for Delta Wye for Tool ID: KETRTD Timecards for 3.26, 3.27,3.28, 3.29, 4.1, & 4.2.2024 | 45391 | 45393 | 23602 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 23602 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 23602 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 990 | P | USC2404043A |  | Manpower Pay for RS Payroll for Tool ID: KETRTE for Laborer Mark Murray Timecards for 2.28 and 2.29.2024 | 45391 | 45425 | 1427.19 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1427.19 | 0 | 1427.19 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 1006 | P | USC2404044A |  | 2,4,6,8,10,12 AWG wire | 45391 | 45399 | 83827.14 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | 0 | [11 empty] | 83827.14 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 8589.5 |  | 75237.64 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 1007 | P | USC2404045A |  | 2,4,6,8,10,12 AWG lug | 45391 | 45393 | 16889.74 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 16889.74 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 10754.54 |  | 4371.58 | [12 empty] | 0 |  | 1763.62 | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1008 | P | USC2404047A |  | Interconnect Cable Pull for KCSCN1 Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45392 | 45393 | 6328.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Sian-Ning Pei | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6328.32 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 1009 | P | USC2404048A |  | 8AWG ring terminal | 45392 | 45392 | 32.04 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 21.36 | 0.66667 | 10.68 | 0 | 10.68 | 0 | 21.36 | [51 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1010 | P | USC2404049A |  | Interconnect Cable Pull for KCOXN6. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45392 | 45393 | 6328.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Sian-Ning Pei | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6328.32 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1011 | P | USC2404050A |  | Interconnect Cable Pull for KCOXN2. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45392 | 45392 | 6328.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 6328.32 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 1012 | P | USC2404051A | -01 | insulation tape | 2024/4/10 2024/5/6 | 2024/4/10 2024/5/8 | 279.3 | 110.38 | 168.92 |  | V | V |  | Independent Electric Supply, Inc. | PR Approved | PO Approved | R1: Adjusting the amount due to additional purchase on the PO and need to align with invoices. |  | Yi En Wong | [11 empty] | 279.3 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 279.3 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1013 | P | USC2404052A |  | Interconnect Cable Pull for KCOXN1. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45392 | 45392 | 6328.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Ta Wei Wang | [11 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  |  |  | 6328.32 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1014 | P | USC2404053A |  | Fabricating cables at MICU office for KCOXN1,2,6, and KCSCN1. Pulling cable from reels out to specified lengths, cutting and stripping cables for terminals, terminating cables, and labeliing for use in cable pulls. | 45392 | 45393 | 4218.88 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh | [11 empty] | 4218.88 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 4218.88 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 1015 | P | USC2404054A |  | 8,12,14 AWG ring terminal | 45393 | 45392 | 1801.55 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong | [11 empty] | 1801.55 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 1801.55 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1016 | P | USC2404055A |  | Regular cable interconnect for KSCBH5,Pulling cables from L30 to L20 and L10, follow 8395 cable routing specifications | 45393 | 45393 | 2109.44 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Sian-Ning Pei | [11 empty] | 2109.44 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 |  | 2109.44 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1017 | P | USC2404056A |  | KDSET1 - TEL INTERCONNECTS 1/29/24-3/8/24 | 45393 | 45394 | 8240 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 8240 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 8240 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1018 | P | USC2404057A |  | PFA-T12-062-50 3/4" PFA TUBING 062 WALL, 50' | 45394 | 45399 | 7402.59 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | 0 | [11 empty] | 7402.59 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 0 |  | 7402.59 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Site Expense | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1019 | P | USC2404058A |  | 1394335 Electric Scissor Lift, 19' Micro-Rental.PHX-2923149-0020-Invoice. | 45394 | 45399 | 448.65 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved |  |  | 0 | [11 empty] | 448.65 | 1 | 0 | 0 | 0 | 0 | [52 empty] | 0 | 0 | 448.65 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1020 | P | USC2404059A |  | KSCBH4 Route and pull Cables install core hole sleeves/tray dividers | 45394 | 45399 | 15886.72 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 15886.72 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 15886.72 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1021 | P | USC2404060A |  | KCOXN3 Pull and route cables, install core hole sleeves/Tray dividers. | 45394 | 45399 | 38826.88 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 38826.88 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 38826.88 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1022 | P | USC2404061A |  | Manpower Pay for RS Payroll Services . Timecards for 1.30, 2.26, 2.27, 2.28, 2.29, 3.1, and 3.4.2024 | 45398 | 45399 | 9332.47 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9332.47 | 176000 | -166667.53 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1023 | P | USC2404062A |  | BPT 247 3IN SET SCREW CPLG | 45398 | 45400 | 240.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 240.2 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 240.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1024 | P | USC2404063A |  | BPT 247 3IN SET SCREW CPLG | 45398 | 45401 | 419.76 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 419.76 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 419.76 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1025 | P | USC2404064A |  | ABAA0158012 Armaflex 1-5/8 X 1/2 | 45398 | 45400 | 5774.42 | [6 empty] | Bay Insulation | PR Approved | PO Approved | [14 empty] | 5774.42 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 5774.42 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1026 | P | USC2404065A |  | Manpower Pay for CCE . Timecard for 1.30.2024 | 45398 | 45402 | 627 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 627 | 0 | 627 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 1027 | P | USC2404066A | -01 | tw trade manager fee for company | 45398 | 2024/4/23 2024/5/6 | 0 | -176000 | 176000 |  |  |  |  | THIRD ENTERPRISE CO., LTD | PR Approved | PO Approved | PO R1: Vendor requests this order to be released to its company in the U.S., so this order will be zero out | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 1012 | P | USC2404066B | -01 | tw trade manager fee for company | 2024/4/16 2024/5/22 2024/8/23 | 2024/5/9 2024/6/27 2024/8/30 | 176000 | -407 | 176407 |  |  |  |  | AUCAN INC | PR Approved | PO Approved | PR R1: Adjusting the PR amount per request from purchaser to align with the latest quotation. PR R2: Adjusting the PR amount to meet the actual final payment amount. | [13 empty] | 0 | 0 | 176000 | 0 | 176000 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 1029 | P | USC2404067A |  | insulation plug | 45398 | 45412 | 648 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved | [14 empty] | 648 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 648 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1030 | P | USC2404068A |  | GSTRT G-582A-OS-1 10FT B2B SLOTTED DP STRUT | 45399 | 45404 | 901.49 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 901.49 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 581.49 | [9 empty] | 320 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1031 | P | USC2404069A |  | 3353.005 +NRT+ SYGEF BCF PLUS UNION 1/2" NON-CANCELABLE, NON-RETURNABLE MFG P/N 735.528.626 | 45399 | 45401 | 22525.5 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 22525.5 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 19677.3 |  | 2848.2 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1032 | P | USC2404070A |  | HS Extra Long Heavy Duty Zip Tie Straps (50 Pack) Thick 0.35 Inch Plastic Duct Zip Ties Heavy Duty 175 Pounds,Black Large Zip Ties 36 Inch for HVAC,Travel,Packaging,Vessel for TOOL ID#KDPOT8, KDPOT7, KDEPT3. | 45400 | 45399 | 268.38 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 201.9 | 0.75229 | 66.48 | 0 | 66.48 | 0 | 201.9 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1033 | P | USC2404071A |  | 23AB02Z 2 Hole 90° (1 7/8 x 2) Angle Bracket EG | 45400 | 45399 | 319.5 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 319.5 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 319.5 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1034 | P | USC2404072A |  | 23AB02Z 2 Hole 90° (1 7/8 x 2) Angle Bracket EG | 45400 | 45399 | 31.95 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 31.95 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 31.95 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1035 | P | USC2404073A |  | Manpower Pay for Delta Wye Tools KETRTA and KETRTD for Time cards on 4.11, 4.12, and 4.15,2024 | 45401 | 45404 | 9914 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 9914 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 9914 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1036 | P | USC2404074A |  | Manpower Pay for Delta Wye Tool ID: KEMGH2 for Time cards on 4.2, 4.3, 4.4, 4.5, and 4.10.2024 | 45401 | 45407 | 7073.5 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 7073.5 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 7073.5 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1037 | P | USC2404075A |  | Manpower Pay for Delta Wye Tool ID:KESRT5 Time cards on 4.3, 4.4, 4.5, 4.8,4.9 and 4.10.2024 | 2024/4/20 2024/4/23 | 45407 | 22386.5 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | PR R1: Corrected work hours for 3 employees on three different days | [13 empty] | 22386.5 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 22386.5 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1038 | P | USC2404076A |  | HT-PVC 大小頭 (SxS) 40Ax25A | 45402 | 45406 | 18.17 | [6 empty] | Supertung Industrial Co., Ltd. | PR Approved | PO Approved | [14 empty] | 18.17 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 18.17 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1039 | P | USC2404077A |  | Manpower Pay for CCE Tool ID: KEMGT1 Timecards 2.28 and 2.28.2024 | 45402 | 45406 | 3615.7 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3615.7 | 0 | 3615.7 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1040 | P | USC2404078A |  | 800-015 1-1/2" PIPE P/E PVC SCH80 CPN-P-TIC-PV-S8PI-042 | 45405 | 45407 | 23969.51 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 23969.51 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 14473.26 |  | 7142.85 |  | 2353.4 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Site Expense | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1041 | P | USC2404079A |  | 1394335 Electric Scissor Lift, 19' Micro-Rental. 3/28-4/25/2024 | 45405 | 45406 | 448.65 | [6 empty] | EquipmentShare.com INC | PR Approved | PO Approved | [14 empty] | 448.65 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 448.65 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1042 | P | USC2404080A |  | KDMRS1 Internal Connect hook up. | 45406 | 45407 | 25000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 25000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 25000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1043 | P | USC2404081A |  | KDMRS2 Internal Connect hook up | 45406 | 45407 | 30000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 30000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 30000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1044 | P | USC2404082A |  | KDMRS3 Internal Connect hook up. | 45406 | 45407 | 34000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 34000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 34000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1045 | P | USC2404083A |  | SP-S835015SS 1-1/2 PVC FEM ADAPTER SOCXSSFPT SCH 3-5 DAYS ARO; 75 X $290.933 | 45406 | 45408 | 38234.64 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 38234.64 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 37624.01 | [5 empty] | 610.63 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1046 | P | USC2404084A |  | KEBCT1 Internal Connect hook up. | 45406 | 45407 | 26000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 26000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 26000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1047 | P | USC2404085A |  | KEPST1 Internal Connect hook up. | 45406 | 45406 | 22000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 22000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 22000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1048 | P | USC2404087A |  | KEPST2 Internal Connect hook up. | 45406 | 45406 | 22000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 22000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 22000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1049 | P | USC2404088A |  | KEBCT3 Internal Connect hook up. | 45406 | 45406 | 38000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 38000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 38000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1050 | P | USC2404089A |  | KDSET1 Internal Connect hook up | 45406 | 45406 | 36000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 36000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 36000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1051 | P | USC2404090A |  | KDMRS4 Internal Connect hook up. | 45406 | 45406 | 34000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 34000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [9 empty] | 34000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1052 | P | USC2404092A |  | 65181 1/2"IDX3/4"OD KFLEX TUBING 50 | 45406 | 45412 | 1428.39 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 1428.38 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 1428.38 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1039 | P | USC2404093A |  | Michael Rodrigues - RS Payroll 1-7 May Cable pulls, 8395 inspections, tool walks. | 45406 | 45448 | 2234.4 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2234.4 | 0 | 2234.4 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1038 | P | USC2404094A |  | Xavier | 45406 | 45420 | 14560 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 14560 | 0 | 14560 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1055 | P | USC2404097A |  | Manpower pay to RS Payroll Services for Tool ID: KEPRL3 for Timecards 2.6, 2.8, 2.9, 2.12, and 3.7.2024 | 45407 | 45408 | 3711.96 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3711.96 | 0 | 3711.96 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1056 | P | USC2404098A | -01 | Cleanroom Notebook, 5.5x8.5, College Rule | 45407 | 2024/4/26 2024/06/11 | 739.68 | 369.84 | 369.84 |  |  | V |  | Thomas Scientific Holdings LLC | PR Approved | PO Approved | R1: order was shipped as a double order so PO was adjusted to cover cost of both see second packing slip | [13 empty] | 739.68 | 1 | 0 | -331.2 | 331.2 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 739.68 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1057 | P | USC2404099A |  | Manpower Pay to RS Payroll Servicies for Tool IDs: KEPOT1, KESRT1, KESRT2 for Time cards on 3.4.2024 | 45407 | 45408 | 676 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 676 | 0 | 676 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1044 | P | USC2404100A |  | Manpower Pay to CGS for Tool IDs: KEPOT1, KESRT1, KESRT2 for Time card on 3.4.2024 | 45407 | 45411 | 874 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 874 | 0 | 874 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1059 | P | USC2404101A |  | Interconnect Cable Pull for KCOXN7. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45408 | 45412 | 10547.2 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 10547.2 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 10547.2 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1060 | P | USC2404102A |  | Interconnect Cable Pull for KCTEN2. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45408 | 45412 | 10547.2 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 10547.2 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 10547.2 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1061 | P | USC2404103A |  | Interconnect Cable Pull for KCTOA2. Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45408 | 45411 | 10547.2 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 10547.2 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  |  |  | 10547.2 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1062 | P | USC2404104A |  | GSP44LG 1 SS S40 304L A312 WELD PIPE STOCK | 45408 | 45409 | 797.7 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 797.7 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 797.7 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 1063 | P | USC2404105A |  | KSSBA5,KSSBA4,KSHMA2,KSHMA3 DI-max hard pipe install | 45408 | 45413 | 12000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 12000 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 12000 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Site Expense | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 1064 | P | USC2404106A |  | label printer | 45408 | 45411 | 138.89 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 135.08 | 0.97257 | 3.81 | 0 | 3.81 | 0 | 135.08 | [53 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1051 | P | USC2404107A |  | KPAN03-T Cable Grounding Installation Labor | 45409 | 45411 | 6993 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 6993 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1052 | P | USC2404108A |  | Manpower Pay to RS Payroll Services for Tool ID: KESTL6 for Timecard on 2.20.2024 for worker: Shamarriee Murphy | 45409 | 45411 | 310.96 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 310.96 | 0 | 310.96 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1053 | P | USC2404109A |  | Manpower Pay to CGS for Tool ID: KESTL6 for Timecard on 2.20.2024 for worker: ELOY PACHECO UBALDO FERREYA JR. | 45409 | 45411 | 874 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 874 | 0 | 874 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1054 | P | USC2404110A |  | KPE606-T Grounding Box Installation Labor | 45412 | 45413 | 6993 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 6993 | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1055 | P | USC2404111A |  | KPE607-T Cable Grounding Installation Labor | 45412 | 45413 | 6993 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6993 | 0 | 6993 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1056 | P | USC2404112A |  | KPE604-T Cable Grounding Installation Labor | 45412 | 45413 | 6993 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [13 empty] | 6993 | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1057 | P | USC2404113A |  | WIC. THHN 4 STR GRN MR COPPER BUILDING WIRE Cuts: QTY1 @ 2000 ft** IN STOCK AT IES PHOENIX **; 1QTY @ 2,000ft X 1070.516/m | 45412 | 45416 | 2214.53 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 2214.53 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 |  | 2141.03 |  |  |  | 73.5 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 1058 | P | USC2404116A |  | 8,10,12 1c color code wire | 45412 | 45413 | 1413.81 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 1413.81 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [14 empty] | 0 |  | 1413.81 | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1059 | P | USC2405001A |  | KPE603-T Grounding Box Installation Labor | 45414 | 45415 | 6993 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 6993 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1060 | P | USC2405002A |  | KPE605-T Grounding Box Installation Labor | 45414 | 45415 | 6993 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 6993 | 1 | 0 | 0 | 0 | 0 | [54 empty] | 0 |  | 0 | [5 empty] | 6993 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1061 | P | USC2405003A |  | 鐵氟龍軟管(1/4"） 6.35*4.35 (透)-DAIKlN | 45415 | 45421 | 40860 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved | [14 empty] | 40860 | 1 | 0 | 1216 | -1216 | 0 | [54 empty] | 0 |  | 0 | [11 empty] | 40860 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Scaffolding | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1063 | P | USC2405004A |  | KCSOA6/Scaffold Tag 111966/3-11-2024 | 45416 | 45419 | 18654 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 18654 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 18654 |  |  |  |  | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1064 | P | USC2405005A |  | KEBCT3- TEL INTERCONECTS-4/1-4/9/2024 | 45416 | 45422 | 54720.12 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 54720.12 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 54720.12 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1065 | P | USC2405006A |  | KCSCS6-DNS SCREEN INTERCONNECTS-4/15-4/16/2024 | 45416 | 45422 | 8420.79 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 8420.79 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 8420.79 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1067 | P | USC2405008A |  | KDMRS4-DNS SCREEN INTERCONNECTS-3/27-4/2/2024 | 45416 | 45420 | 40084.8 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 40083.8 | 0.99998 | 1 | 0 | 1 | 0 | [56 empty] | 0 | [5 empty] | 40083.8 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1068 | P | USC2405009A |  | KDMRS3-DNS SCREEN INTERCONNECTS 3/21, 3/27-3/28, 4/15-2024 | 45416 | 45421 | 28833.72 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 28833.72 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 28833.72 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1077 | P | USC2405018A |  | MANPOWER: PINNACLE PEAK WAREHOUSES: 04/23-05/31/24 REG HRS | 2024/5/7 2024/9/12 | 2024/5/8 2024/9/12 | 25636.83 | 8068.83 | 17568 |  |  |  | V | CGS Global Support, LLC | PR Approved | PO Approved | PR R1: Addtl' 179 REG HRS & 16.50 OT HRS combined for Ernesto Limon from 06/09-07/07. | [13 empty] | 0 | 0 | 25636.83 | 0 | 25636.83 | 0 | [56 empty] | 0 | [16 empty] | - |  | 8828.73 |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1078 | P | USC2405019A |  | Manpower Pay to Brahma Group for Tool ID: KEMEL2 Daililies for 3.28, 4.2, 4.3, 4.4, and 4.16.2024 | 45419 | 45426 | 15523.92 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 15523.92 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 15523.92 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1080 | P | USC2405021A |  | KEPSS1-DNS SCREEN INTERCONNECTS | 45419 | 45420 | 13588.66 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 13588.66 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 13588.66 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1082 | P | USC2405023A |  | KDMRS2 - rework | 45419 | 45419 | 8185.36 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 8185.36 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 8185.36 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1083 | P | USC2405024A |  | KDSTSA - rework | 45419 | 45421 | 42334.21 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 42334.21 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 42334.21 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1085 | P | USC2405026A |  | KRWRS2 - rework-DNS SCREEN INTERCONNECTS | 45419 | 45419 | 16764.53 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 16764.53 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 16764.53 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1086 | P | USC2405027A |  | KDSTS9 - rework - DNS SCREEN INTERCONNECTS | 45419 | 45419 | 14022.11 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 14022.11 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 14022.11 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1088 | P | USC2405029A |  | KDCRS1-rework - DNS SCREEN INTERCONNECTS | 45419 | 45420 | 11300.93 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 11300.93 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 11300.93 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1089 | P | USC2405030A |  | KEPST2 - rework - DNS SCREEN INTERCONNECTS | 45419 | 45419 | 4549.05 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 4549.05 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 4549.05 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1090 | P | USC2405032A |  | KEPST1-TEL INTERCONNECTS | 45419 | 45419 | 20403.36 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 20403.36 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 20403.36 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1091 | P | USC2405033A |  | MANPOWER: PINNACLE PEAK WAREHOUSES: 05/06-05/31/2024 REG HRS | 45420 | 2024/5/10 2024/8/2 | 9296.25 | -249.75 | 9546 |  |  |  |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | PO R1: Updated the correct reg. & OT hrs to match the invoice. | [13 empty] | 9296.25 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 9296.25 |  |  |  |  | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1092 | P | USC2405034A |  | KPE601-S Cable Rerouting Labor | 45422 | 45422 | 1503 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 1503 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 1503 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1077 | P | USC2405035A |  | PAY TO J.T. THORPE FOR TOOL ID: KETRTE ETC 3 ON 4.3.2024 SCAFFOLD WAS TAKEN DOWN THAT WAS USED ON TOOL ID: KETRTE | 45422 |  | 702 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 702 | 0 | 702 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1078 | P | USC2405036A |  | Manpower Pay to CGS Global for Tool ID: KESTT1 for Cable Tray Divider installation. Time Card on 3.15.2024 for Miguel Argueta and Mario Diaz | 45423 | 45426 | 768 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 768 | 0 | 768 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1079 | P | USC2405037A |  | Manpower Pay to RS Payroll Services for Tool ID: KEPRL5 for Cable Pull and 8395 Rule on Time Card from 3.8.2024 for Michael Rodriquez | 45423 | 45425 | 215.84 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 215.84 | 0 | 215.84 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1080 | P | USC2405038A |  | Manpower Pay to CGS GLOBAL for Tool ID: KEPRL5 for Cable Pull and 8395 Rule on Time Card from 3.8.2024 for Monica Dabdoub | 45423 | 45429 | 176 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 176 | 0 | 176 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1081 | P | USC2405039A |  | Manpower Pay to CGS GLOBAL for Tool ID: KEMGL3 for Cable Pull and 8395 Rule on Time Card from 3.21.2024 for Luis Rosas, Daniel Calderon, Xavier Niesen, Raul Acuna, and Eliseo Perez | 5/11/2024 8/28/2024 | 5/14/2024 8/28/2024 | 0 | -1318.2 | 1318.2 |  |  |  |  | CGS Global Support, LLC | PR Approved | PO Approved | R1: Case Closed | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1082 | P | USC2405040A |  | KRWRS1 - rework-DNS SCREEN INTERCONNECTS 4/11/2024 | 45426 | 45427 | 4176.24 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 4176.24 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 4176.24 | [8 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1083 | P | USC2405041A |  | KDCCS3 - rework DNS SCREEN INTERCONNECTS 4/4-4/6 | 45426 | 45427 | 25292.6 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 25292.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 25292.6 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1084 | P | USC2405042A |  | KDSTS6-rework DNS SCREEN INTERCONNECTS | 45426 | 45427 | 16050.64 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 16050.64 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 16050.64 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1085 | P | USC2405043A |  | KEPST4-TEL INTERCONNECTS | 45426 | 45432 | 77987.27 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 77987.27 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 77987.27 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1086 | P | USC2405044A |  | KDSTS8-DNS SCREEN INTERCONNECTS | 45426 | 45427 | 6218.06 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 6218.06 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 6218.06 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1087 | P | USC2405045A |  | KDSNB1- SHIB INTERCONNECTS | 45426 | 45426 | 19357.3 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 19357.3 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 19357.3 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1088 | P | USC2405046A |  | KDCRS5-DNS SCREEN INTERCONNECTS | 45426 | 45432 | 59338.94 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 59338.94 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 59338.94 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1089 | P | USC2405047A |  | KDCRS4 - DNS SCREEN INTERCONNECT | 45426 | 45429 | 104094.82 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 104094.82 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 104094.82 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1090 | P | USC2405048A |  | KDCCS2-DNS SCREEN INTERCONNECTS | 45426 | 45426 | 17350.06 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 17350.06 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 17350.06 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1091 | P | USC2405049A |  | KDCCS1-DNS SCREEN INTERCONNECTS | 45426 | 45429 | 90194.58 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 90194.58 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 90194.58 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1092 | P | USC2405050A |  | KRWRS5 / KRWRS4 / KRWRS2 / KDHBS1 / KRWRS7 / KDBCS1 / KRWRS6 / KCSCSB / KRWRS3 / KDSNS1 / KDCRS1 / KDCCS2 / KCSCSA / KRWRS1 / KDSTSA / KDCRS4 / KDCCS3 / KCSCS7 / KDCCS1 / KCSCS9 / KEPSS1 / KEPST4- DNS SCREEN INTERCONNECTS-Line Labeling | 45426 | 45428 | 594870.95 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 594870.95 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [7 empty] | 594870.95 | [8 empty] | - |  | - |  | 0
Interconnection | Interconnection | Labor | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1093 | P | USC2405051A |  | Manpower Pay to CGS GLOBAL for Tool IDs: KESRT1 AND KESRT2 for Cable Pull and 8395 Rule on Time Card from 3.20.2024 for Mario Diaz, Eloy Pacheco, Miguek Argueta, and Shamarie Murphy | 45426 | 45427 | 1397.28 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1397.28 | 0 | 1397.28 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1094 | P | USC2405052A |  | Manpower Pay to RS PAYROLL for Tool IDs: KESRT1 AND KESRT2 for Cable Pull and 8395 Rule on Timecard for 3.20.2024 for James Thompson | 45426 | 45429 | 284 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 0 | 0 | 284 | 0 | 284 | 0 | [56 empty] | 0 | [16 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1095 | P | USC2405053A |  | DNS SCREEN INTERCONNECTS 3/28-4/9/2024 | 45426 | 45434 | 148095.51 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 148095.51 | 1 | 0 | 0 | 0 | 0 | [62 empty] | 148095.51 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1095 | P | USC2405054A |  | 4/10/2024 Scaffolding for KCOXN7 Scaffold Tag 111166 | 45427 | 45429 | 1680 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 1680 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 1680 |  |  |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1096 | P | USC2405055A |  | PFA-T2-030-500 500' COIL 1/8 X .030 TUBE | 45427 | 45427 | 1647.6 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 1647.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 1647.6 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1097 | P | USC2405056A |  | KSECN2-CIP Work with PFA lines - for PFA line modifications and line testing. | 45427 | 45429 | 11530 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 11530 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [11 empty] | 11530 |  |  |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1098 | P | USC2405057A |  | KUECN3 -fixing a leak and replacing a 90-degree elbow. Identifying leaking fitting, re-terminating leaking fitting for QC, replacing fitting with missing compression rings. | 45428 | 45434 | 4416.6 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 4416.6 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 4416.6 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1099 | P | USC2405058A |  | KSECN3 connecting plastic chiller lines, certifying clear PVC double containment. Pulling and connecting PFA lines for chillers and double containment line for chemical drain. | 45428 | 45435 | 15499.28 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 15499.28 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 15499.28 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1100 | P | USC2405059A |  | KUECN1 - fixing a leak - Identifying leaking fitting, re-terminating fitting for QC. | 45428 | 45434 | 4088.17 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 4088.17 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 4088.17 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1101 | P | USC2405060A |  | KUECN2 - pressure test. Pressure testing, removing caps and installing ferrals and connected line, restoring lines to tool and labeling | 45428 | 45435 | 13572.57 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 13572.57 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [9 empty] | 13572.57 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1102 | P | USC2405079A |  | Payment for Material: 1. Supply (6) 2-1/2’’x 2-1/2’’x1’’ 304 SS Tees 2. Supply (6) 1’’x3/4’’ 304 SS Reducers. | 45429 | 45433 | 903.33 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 903.33 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 903.33 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1103 | P | USC2405082A |  | Payment for Materials: 1. Supply fittings 1’’ and above per BOM for KPE606-S | 45429 | 45435 | 16564 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 16564 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [13 empty] | 16564 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1104 | P | USC2405091A |  | KPE606-S Exhaust Installation Labor | 45429 | 45435 | 9806 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 9806 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [13 empty] | 9806 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1105 | P | USC2405107A |  | Interconnect Cable Pull for KCSCN4-Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45429 | 45435 | 7910.4 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 7910.4 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 7910.4 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1106 | P | USC2405108A |  | Interconnect Cable Pull for KCSCN2-Pull power and signal cables from L30 to L20 and L10, follow 8395 routing and zip tie rules. | 45429 | 45432 | 2109.44 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 2109.44 | 1 | 0 | 0 | 0 | 0 | [56 empty] | 0 | [5 empty] | 2109.44 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1108 | P | USC2405131A |  | LABOR & MATERIAL FOR GALVANIZED DUCT/ELBOWS FOR BLOWER BOX IN LB1.INSTALLATION OF H-BAR IN L10 FOR KDFAD1 | 45432 | 45435 | 28265.23 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | [14 empty] | 28265.23 | 1 | 0 | 0 | 0 | 0 | [60 empty] | 28265.23 | [12 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1109 | P | USC2405132A |  | Cable Pull KCSCS4 | 45434 | 45443 | 7204 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 7204 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 7204 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1110 | P | USC2405133A |  | 1394335 Electric Scissor Lift, 19' Micro-Rental. Rental date 4/25-5/23/2024. PHX-2923149-0023-Invoice | 2024/5/22 2024/6/5 | 2024/5/23 2024/7/4 | 0 | -448.65 | 448.65 |  |  |  |  | EquipmentShare.com INC | PR Approved | PO Approved | R1: This PO is canceled. Shannon Pulcifer will pay for this invoice since the they have been using the lift. See attached email. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1111 | P | USC2405134A |  | Quote 0877- KSCTT1 8395 Certification and cable pull and admin fee | 45434 | 45437 | 48583.04 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 48583.04 | 0 | 48583.04 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1112 | P | USC2405136A |  | KPE606-T VEX Signal, Power, and Mechanical Installation Labor | 45435 | 45455 | 112574 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 112574 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 112574 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1113 | P | USC2405138A |  | SUIN 1'' 3 Ring Binder -1 inch View Binders with Round Ring Binders, Large 200 Sheet Capacity, Fit 8.5" x 11" US Letter Size Paper, 12 Pack White (1-inch) | 45435 | 45443 | 77.9 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 77.9 | 0 | 77.9 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1114 | P | USC2405139A |  | 1KT H-2084 SECURITY CART - 48 X 24 X 69" | 45435 | 45443 | 884 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 803.64 | 0.9091 | 80.36 | 0 | 80.36 | 0 | [62 empty] | 803.64 | [10 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1115 | P | USC2405140A |  | FLEX LT3UAGRY 3 UL LIQ-TITE FLEXIBLE TYPE; HOT DIP GALVANIZED FINISH; 25 FT; UL APPROVAL; 80 DEG C TEMPERATURE RATING; 3 INCH TRADE SIZE; UA/LA STYLE; PVC JACKET MATERIAL; GRAY JACKET COLOR; STEEL CORE MATERIAL | 45436 | 45441 | 3824.19 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 3824.19 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 3824.19 |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1116 | P | USC2405141A |  | KCSCN5 4/18/24 Scaffold Tag 111733 | 45436 | 45443 | 17198 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 17198 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 17198 |  |  | - |  | - |  | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1117 | P | USC2405183A |  | STAINLESS MATERIAL | 45443 | 45446 | 678.3 | [6 empty] | Cliff’s Welding, Inc | PR Approved | PO Approved | [14 empty] | 678.3 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 678.3 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1118 | P | USC2405184A |  | 8395 Certification Cable Pull KCSCN4 4techs x 8hrs = 32hrs 32hrs x 3 days = 96hrs | 45443 | 45448 | 6328.32 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 6328.32 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 6328.32 | [8 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1121 | P | USC2406001A |  | KPE604-T VEX, Signal, Power, and Mechanical Installation Labor | 45450 | 45455 | 116237 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 116237 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 116237 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1122 | P | USC2406002A |  | KDMRS4- DNS SCREEN INTERCONNECTS- 5/1/2024 | 45450 | 45454 | 1489.83 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 1489.83 | 1 | 0 | 4414 | -4414 | 0 | [66 empty] | 1489.83 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1123 | P | USC2406003A |  | KDCRS4 - rework (change order)-DNS SCREEN INTERCONNECTS-5/1-5/10/24 | 45450 | 45461 | 63121.6 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 63121.6 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 63121.6 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1124 | P | USC2406004A |  | KDCRS1-rework - DNS SCREEN INTERCONNECTS-4/30/24 | 45450 | 45456 | 7962.62 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 7962.62 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 7962.62 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1125 | P | USC2406005A |  | KDSTSA - rework (change order)-DNS SCREEN INTERCONNECTS-5/2-5/16/2024. | 45450 | 45458 | 37947.91 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 37947.91 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 37947.91 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1126 | P | USC2406006A |  | KEPST4-TEL INTERCONNECTS-5/1-5/3/2024 | 45450 | 45458 | 27842.6 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 27842.6 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 27842.6 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1128 | P | USC2406008A |  | KRWRS4 - rework (change order)-DNS SCREEN INTERCONNECTS-5/1 and 5/3/2024. | 45450 | 45453 | 3272.32 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 3272.32 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 3272.32 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1130 | P | USC2406009A |  | Change Order EUV Reservoir Boxes Installation Labor | 45457 | 45460 | 4414 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4414 | 0 | 4414 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1131 | P | USC2406010A |  | Aluminum perforated sheet staggered hole | 45457 | 45460 | 9200 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9200 | 624.58 | 8575.42 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1132 | P | USC2406011A |  | KEPST4 - Cable Pull, 5/14-5/16, Tel Interconnects | 45457 | 45461 | 2580 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 2580 | 1 | 0 | 0 | 0 | 0 | [64 empty] | 2580 | [8 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1132 | P | USC2406012A |  | KDMRS4-Change order-DNS SCREEN INTERCONNECTS-5/18/2024 and 6/5/2024 | 45458 | 45462 | 9753.4 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 9753.4 | 1 | 0 | 0 | 0 | 0 | [66 empty] | 9753.4 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1133 | P | USC2406013A |  | KDBCS1 - rework (change order)-DNS SCREEN INTERCONNECTS-5/1-5/8/2024 | 45461 | 45462 | 16215.26 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 16215.26 | 1 | 0 | 6315.37 | -6315.37 | 0 | [66 empty] | 16215.26 | [6 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1134 | P | USC2406014A |  | KRWRS1 - rework (change order)-DNS SCREEN INTERCONNECTS-5/1, 5/6, and 5/8/2024 | 45461 | 45465 | 8521.44 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 8521.44 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 8521.44 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1135 | P | USC2406015A |  | KUECN5/6/7 PFA Install - Route (2) PFA lines on (3) separate tools. Pressure test all (6) lines after routing is completed. | 45462 | 45471 | 7672 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7672 | 0 | 7672 | 0 | [73 empty] | - |  | 7672 |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1136 | P | USC2406016A |  | FLEX LT2-1/2UAGRY 2-1/2 UL LIQ-TITE | 45464 | 45467 | 624.58 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 624.58 | 0 | 624.58 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1137 | P | USC2406017A |  | KPAE02-S Exhaust Installation | 45465 | 45471 | 29214 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29214 | 0 | 29214 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1138 | P | USC2406018A |  | SS012316S10WPE 1/2 10S 316 WELD PIPE | 45465 | 45470 | 10292.29 | [6 empty] | Industrial Pipe and Valve Inc. | PR Approved | PO Approved | [14 empty] | 10292.29 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 10292.29 |  |  |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1139 | P | USC2406033A |  | WIRE SOOW2/4C 558089 | 45471 | 45476 | 6315.37 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6315.37 | 0 | 6315.37 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1140 | P | USC2406034A |  | Interconnect Cable Pull for KCSCN4 | 45471 | 45474 | 2109.44 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2109.44 | 0 | 2109.44 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1141 | P | USC2406035A |  | Man-Power Pay to re-work (change Order)-DNS SCREEn Interconnects. 5/1 thru 5/10/2024 | 45472 | 45475 | 63121.6 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 63121.6 | 0 | 63121.6 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1142 | P | USC2406036A |  | Man-Power Pay Install Finish (Change Order)-2+ days no work waiting on permits. 5/1, 5/2, and 5/3/2024 | 45472 | 45476 | 27842.6 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 27842.6 | 0 | 27842.6 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1143 | P | USC2406038A |  | Manpower pay for Tool: KDSTSA for Brahma Work Performed- ITT rework on 5/2, 5/3, 5/8, 5/14, 5/14, 5/16/2024 | 45472 | 45476 | 37947.91 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 37947.91 | 0 | 37947.91 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1144 | P | USC2407003A |  | anchor bolt | 45475 | 45476 | 304.01 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 304.01 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 304.01 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1145 | P | USC2407004A |  | KPAE02-S PVC Pipe Installation Labor | 45482 | 45489 | 57776 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 57776 | 0 | 57776 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1146 | P | USC2407005A |  | Lit 1,2,&3 Connex Move Labor | 45482 | 45486 | 4013.5 | [6 empty] | Southwest Industrial Rigging | PR Approved | PO Approved | [14 empty] | 2041.27 | 0.5086 | 1972.23 | 0 | 1972.23 | 0 | [70 empty] | 2041.27 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1147 | P | USC2407006A |  | Male Connector: 3/4" S300 to 3/4" NPT (DWG# PM-7018-1-1) | 45483 | 45486 | 511.6 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved | [14 empty] | 511.6 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 511.6 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1148 | P | USC2407007A |  | DRY ETC- ITEM# 93 TUBE SIZE 6.35X4.35X200M | 2024/7/10 2024/7/17 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: canceled | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1149 | P | USC2407010A |  | 451 PFA Tubing 3/8X1/4X200M | 2024/7/10 2024/7/17 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Cancel Order. Purchasing team will look for other suppliers | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1150 | P | USC2407012A |  | KPAE02-S Pressure Testing Labor | 7/12/2024 9/28/2024 | 7/13/2024 10/8/2024 | 0 | -9859 | 9859 |  |  |  |  | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1151 | P | USC2407013A |  | KPAE02-S Insulation Labor | 45486 | 45490 | 21637 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21637 | 0 | 21637 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1152 | P | USC2407014A |  | KPAE02-S Cable Routing Labor | 45486 | 45490 | 29170 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29170 | 0 | 29170 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1153 | P | USC2407015A |  | KPD803-S PVC Piping Labor | 45486 | 45492 | 149656 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 149656 | 0 | 149656 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1154 | P | USC2407017A |  | KPAN05-S PVC Piping Labor | 45489 | 45492 | 229088 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 229088 | 0 | 229088 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1155 | P | USC2407018A |  | For use on upcoming CVD/PVD tools in P1B (Cable lables, Core Hole markings, Cable Tray designation). For use on CVD/PVD tools - this is used for interconnect cables, cable trays, core holes, and more | 45489 | 45498 | 886.18 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 886.18 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 886.18 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1156 | P | USC2407019A |  | KPAN06-S PVC Piping Labor | 45489 | 45492 | 229088 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 229088 | 0 | 229088 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1157 | P | USC2407020A |  | Labor 8395 Certification and cable pull | 45491 | 45492 | 527.36 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 527.36 | 0 | 527.36 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1158 | P | USC2407022A |  | WET ETC 451 PFA #106 (TUBE SIZE) 1X7/8X200M | 45491 | 45496 | 169083.9 | [6 empty] | PILLAR America, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 169083.9 | 200161.88 | -31077.98 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1159 | P | USC2407023A |  | Labor for Electrical cable pull for tool ID# KDFAD1 | 45492 | 45495 | 33621.98 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved | [14 empty] | 33621.98 | 1 | 0 | 0 | 0 | 0 | [68 empty] | 33621.98 |  |  |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1160 | P | USC2407024A |  | 100ea BLN 73A-120 Dividers | 45492 | 45495 | 2243 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 2243 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 2243 |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1161 | P | USC2407025A |  | C406-010: 1" 90 ELBOW S CLR PVC SCH40 | 45493 | 45499 | 316773.25 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 99557.09 | 0.31429 | 217216.16 | 0 | 217216.16 | 0 | [70 empty] | 89726.19 |  |  | 9830.9 |  | 217216.16 |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1162 | P | USC2407029A |  | 1/2-13 x 10' All Thread Rod Zinc | 45496 | 45499 | 14782.56 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 14782.59 | 1 | -0.03 | 0 | -0.03 | 0 | [70 empty] | 14635.8 |  | 146.79 | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1163 | P | USC2407030A |  | 102: P-TIC-PFA-TU-015: PFA 1/2" (12.7MM OD, 9.53MM ID) | 45496 | 45498 | 2540 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 2540 | 1 | 0 | 0 | 0 | 0 | [72 empty] | 2540 | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1164 | P | USC2407031A |  | 17: M-TIC-16L-TU-015: 1/2"*0.49" 304LSMLS Tube AP 4M/PC | 45496 | 45510 | 200161.88 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 200161.88 | 0 | 200161.88 | #N/A | [73 empty] | - |  | - |  | #N/A
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1165 | P | USC2407032A |  | QAQC Visual Testing Level I/II Course fro Tool Hook-up | 2024/7/24 2024/7/25 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: PO needs to be deleted, it was submitted under the wrong Project Code | [13 empty] | 0 | 1 | 0 | 0 | 0 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1164 | P | USC2407033A |  | QAQC Visual Testing Level I/II Course for Tool Hook-up | 45497 | 45510 | 699 | [6 empty] | WorldSpec NDT Training | PR Approved | PO Approved | [14 empty] | 699 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 699 |  |  | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1165 | P | USC2407034A |  | SS-QTM4A-B-6PM SS QT BODY QC 3/8" MNPT M-TIC-MNPT-009 | 45498 | 45504 | 5018.08 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 5018.08 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 3772.08 |  |  | 1246 |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1166 | P | USC2407035A |  | KPE602-S, KPE603-S, KPE605-S, and KPE607-S EUV Cable Rerouting Labor | 45498 | 45500 | 6012 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6012 | 0 | 6012 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1167 | P | USC2407037A |  | KPE605-S CW Whip Connection Support Labor | 45499 | 45502 | 9134 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 9134 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 9134 |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1168 | P | USC2407038A |  | KPI402-S PVC Piping Labor | 45499 | 45503 | 152632 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 152632 | 42873.61 | 109758.39 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1171 | P | USC2407039A |  | TIG Welding Certification and Training for Took Hook-Up through MSR-FSR for 27 welders | 45503 | 45504 | 4740 | [6 empty] | MSR FSR LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4740 | 1456.85 | 3283.15 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1172 | P | USC2408001A |  | KPE606-T Scaffolding Labor | 45506 | 45510 | 13126 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | [14 empty] | 13126 | 1 | 0 | 24000 | -24000 | #N/A | [70 empty] | 13126 |  |  | - |  | - |  | #N/A
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1173 | P | USC2408002A | -01 | WA524T*1.5MM*20 Transparent table mat*1.5mm*20Y 交易條件:EXW | 45506 | 2024/8/2 2024/8/7 | 596 | [6 empty] | Xiang Sheng Hardware Enterprise Co., Ltd. | PR Approved | PO Approved | R1: Change Delivery Location and Payment Term | [13 empty] | 0 | 0 | 596 | 33432.41 | -32836.41 | #N/A | [73 empty] | - |  | - |  | #N/A
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1174 | P | USC2408003A |  | Torque Wrenches | 45506 | 45520 | 591 | [6 empty] | Ceet Industries Inc DBA Trident Calibration Labs | PR Approved | PO Approved | [14 empty] | 0 | 0 | 591 | 9040.71 | -8449.71 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1175 | P | USC2408004A |  | Glove testing for 1000VT Welding gloves | 45506 |  | 32 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 32 | 0 | 32 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1177 | P | USC2408005A |  | 2 MALL INS BUSH | 45507 | 45518 | 42546.14 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 42546.14 | 0 | 42546.14 | 0 | [73 empty] | - |  | -
Base-Build | WWT |  | USC24C006 | WWT B side Project | 1178 | P | USC2408006A |  | Mobile Computers, Zebra TC22, WiFi 6, SE4710, 6 Display, 6GB64GB, 16MP RFC, 5MP FFC, 2Pin Back IO, Standard Battery, NFC, Bluetooth, USBC, GMS, NA | 45510 | 45512 | 2605.34 | [6 empty] | Barcodes LLC | PR Approved | PO Approved | [14 empty] | 938 | 0.36003 | 1667.34 | 0 | 1667.34 | 0 | [73 empty] | 938 |  | 10
Hookup | Hookup |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1176 | P | USC2408007A |  | Swagelok M200 Orbital Welding System Training | 45511 | 45518 | 40800 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 40800 | 0 | 40800 | 0 | [73 empty] | - |  | - |  | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1180 | P | USC2408009A |  | 10" SUS304 Dust 1.2M | 45513 | 45524 | 33432.41 | -43953.1 | 77385.51 |  |  |  | V | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | PO R1: Per request, place order only for Quote MICU-07-11-099 | [13 empty] | 0 | 0 | 33432.41 | 0 | 33432.41 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1181 | P | USC2408010A |  | 1-IN INSUL GRND BUSH | 2024/8/9 2024/9/24 | 2024/8/14 2024/9/24 | 12547.34 | -42.49 | 12504.85 |  |  |  |  | Independent Electric Supply, Inc. | PR Approved | PO Approved | PR R1: Supplier send extra #24 PP DIN 1W FRL materials, PM decide to keep them | [13 empty] | 2934.75 | 0.23389 | 9612.59 | 0 | 9612.59 | 0 | [73 empty] | 2934.75 |  | 571.83
Base-Build | General Condition |  | USC24C010 | General Conditions B Side Project | 1177 | P | USC2408011A |  | 15-HPM L30 V Line 及FAB L10 L LINE配合氣化課拆庫板 (MICU) | 45513 | 45524 | 1484981.27 | [6 empty] | United Integrated Services (USA) Corp | PR Approved | PO Approved | [14 empty] | 1484981.27 | 1 | 0 | 0 | 0 | #N/A | [70 empty] | 1000000 |  |  | 484981.27 |  | - |  | #N/A
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1183 | P | USC2408012A |  | KIHIB2: EXHAUST, SIGNAL & POWER CABLE INSTALL | 45514 | 45531 | 18958.46 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 18958.46 | 1299.17 | 17659.29 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1184 | P | USC2408013A |  | WIRE TCXH2/4G | 2024/8/10 2024/8/23 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: Close this PR, create a new PR USC2408057 instead. | [13 empty] | 0 | 1 | 0 | 9173.32 | -9173.32 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1185 | P | USC2408015A |  | INT--ETCH/WET/CVD/PVD/ME--CGS(Mar.&Apr.) | 45518 | 45523 | 76701.42 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 76701.42 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 76701.42 |  |  | - |  | -
Base-Build | General Condition |  | USC24C010 | General Conditions B Side Project | 1186 | P | USC2408016A |  | Base build-CGS 3&4 opening invoices | 45518 | 45524 | 137766.06 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | [14 empty] | 137766.06 | 1 | 0 | 0 | 0 | 0 | [70 empty] | 137766.06 |  |  | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1187 | P | USC2408018A |  | 3/4" 90 Degree Female NPT Elbow Fitting | 45519 | 45523 | 323 | [6 empty] | Industrial Pipe & Valve Inc. | PR Approved | PO Approved | [14 empty] | 323 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 323 |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1188 | P | USC2408023A |  | 3 CABLE PULL LEAD FOR 1 MONTH | 45520 | 45525 | 32760 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 32760 | 0 | 32760 | 0 | [73 empty] | - |  | 15632.56
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1189 | P | USC2408034A |  | ISO-KF Weld Stub Flange, NW25, 1.0in. Tube OD, 0.5in. Length 304 S. S | 45520 | 45523 | 25810.2 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 24619.8 | 0.95388 | 1190.4 | 0 | 1190.4 | 0 | [73 empty] | 24619.8 |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1190 | P | USC2408041A |  | 10/4 VNTC CABLE | 45520 | 45523 | 9174.16 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 9174.16 | 0 | 9174.16 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1191 | P | USC2408042A |  | Zip Tie Mount (1EA = 140 pack) | 45521 | 45525 | 414.38 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 289.71 | 0.69914 | 124.67 | 29103 | -28978.33 | 0 | 289.71 | [72 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1192 | P | USC2408043A |  | KEPST4 Conduit and Wire Pull | 45521 | 45532 | 85235.57 | [6 empty] | BRAHMA GROUP, INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 85235.57 | 0 | 85235.57 | 0 | [73 empty] | - |  | 85235.57
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1193 | P | USC2408044A |  | HMT-24030020: KEPSL7 INTERNAL CONNECT HOOK UP | 2024/8/20 2024/9/24 2024/9/25 2024/9/25 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R4:VOID. New quotation issued. PR R3ERP updated tool ids: line 026 - KEPSLB, line 030 - KEPSS2, line 033 - KCSCSH, line 034 - KEBCT5 PR R2ERP Help updated tool IDS: Line 26 - KEPSLB, Line 30 - KEPSS2, Line 33 - KCSCSH, Line 34 - KEBCT5. | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1194 | P | USC2408045A |  | KPAN05-T Exhaust Labor | 45524 | 45528 | 113968 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 113968 | 0 | 113968 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1195 | P | USC2408046A |  | KPAE02-T Exhaust Labor | 45524 | 45528 | 79560 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 79560 | 0 | 79560 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1196 | P | USC2408048A |  | KPAN06-T Exhaust Labor | 45524 | 45531 | 113968 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 113968 | 0 | 113968 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1197 | P | USC2408049A |  | Rework aquired for KKDB02, cables are running through popout that is in direct conflict with another tools foundation | 45525 | 45526 | 29103 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 29103 | 20168.8 | 8934.2 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1198 | P | USC2408050A |  | P1A_SUS 6" exhaust for 30' RHC line_KDTNK1_KDSRK6_KDCUK1_KDCUK2_KDCUK3 | 45525 | 45532 | 25722.48 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | [14 empty] | 25722.46 | 1 | 0.02 | 7004 | -7003.98 | 0 | [72 empty] | 25722.46 | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1199 | P | USC2408051A |  | KPOCTK Exhaust Labor | 45525 |  | 67091 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 67091 | 0 | 67091 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1200 | P | USC2408053A |  | Labor for Tool KSCTT2 (8395 Certificated 5 techs X 8hrs 40hrs X 3days = 120hrs X $85/hrs | 2024/8/22 2024/9/21 | 45530 | 0 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | PR R1: Cancelled*Modified Quote Tools included in PR# USC2409042 | [13 empty] | 0 | 1 | 0 | 2375 | -2375 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1201 | P | USC2408055A |  | Labor for Tool KSCBH9 (8395 Certificated 5 techs X 8hrs 40hrs X 3days = 120hrs X $85/hrs | 2024/8/22 2024/9/21 | 45530 | 0 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | PR R1: Cancelled*Modified Quote Tools included in PR# USC2409042 | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1202 | P | USC2408056A |  | Admin Fee | 45526 |  | 204 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 204 | 70557 | -70353 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1203 | P | USC2408057A |  | WIRE TCXH2/4G | 45527 | 45531 | 20168.8 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 20168.8 | 26259 | -6090.2 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1204 | P | USC2408058A |  | Labor for Multiple Tool Cabling | 45528 | 45530 | 7004 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7004 | 70557 | -63553 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1205 | P | USC2408059A |  | PAY TO DELTA WYE FOR 6 TOOL: CABLE PULL | 2024/8/27 2024/9/7 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Per request to cancel, and will create a lumpsum P1B bulk order in another PO for Delta Wye including these TOOL | [13 empty] | 0 | 1 | 0 | 1785.06 | -1785.06 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1206 | P | USC2408063A |  | KPE604-S & KPE607-S CW Piping Material | 45533 | 45533 | 2375 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2375 | 2458.13 | -83.13 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1207 | P | USC2408065A |  | IS4CT9G 1 SS 304 150# THRD 90 ELL | 45534 | 45535 | 98.2 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 98.2 | 1 | 0 | 1433.38 | -1433.38 | 0 | [73 empty] | 98.2 |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1208 | P | USC2409001A |  | KPE607-S CW PIPING TIG WELDING EXRA COSTS REV1: TIG WELDING | 45539 | 45545 | 70557 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 70557 | 3000 | 67557 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1209 | P | USC2409002A |  | KPE606-S: CW PIPING REWORK CLASHES: L30 | 45539 | 45547 | 26259 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 26259 | 0 | 26259 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1210 | P | USC2409003A |  | KPE604-S: CW PIPING TIG WELDING EXTRA COSTS REV1: TIG WELDING | 45539 | 45545 | 70557 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 70557 | 447 | 70110 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1211 | P | USC2409004A |  | Equipment SP-110 v3 | 45539 | 45541 | 13834.26 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 13834.26 | 0 | 13834.26 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1212 | P | USC2409005A |  | RELOCATE CONEX BOXES | 45539 | 45540 | 4738 | [6 empty] | Southwest Industrial Rigging | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4738 | 0 | 4738 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1213 | P | USC2409006A |  | COND EMT3; EMT; PER HUNDRED | 45540 | 45541 | 1433.38 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1433.38 | 154683.25 | -153249.87 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1214 | P | USC2409007A |  | PRECISION CUTS KPE607-S BTS | 45540 | 45541 | 3000 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3000 | 22652.2 | -19652.2 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1215 | P | USC2409008A |  | Position sensor, 0-6000 mm, Profinet, M4, Linearity 0,02% | 2024/9/5 2024/9/10 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Replace PR # USC2409016 | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1218 | P | USC2409009A |  | 2AWG CU 1H LUG 3/8" STUD | 45540 | 45560 | 447 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 447 | 0 | 447 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1216 | P | USC2409010A |  | 2304PIPE: 2 304 WELD PIPE S10 A312 | 45541 | 45541 | 2839.47 | [6 empty] | Industrial Pipe & Valve Inc. | PR Approved | PO Approved | [14 empty] | 1614.47 | 0.56858 | 1225 | 0 | 1225 | 0 | [73 empty] | 1614.47 |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1217 | P | USC2409013A |  | Werner 10 ft. Fiberglass Step Ladder (14 ft. Reach Height) 300 lb. Load Capacity Type IA Duty Rating | 2024/9/7 2024/9/25 | 2024/9/12 2024/9/25 | 458 | 42.8 | 500.8 |  |  |  |  | The Home Depot, Inc | PR Approved | PO Approving | PR R1:Match to the actual expense (See order confirmation) | [13 empty] | 458 | 1 | 0 | 33402 | -33402 | 0 | 458 | [72 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1218 | P | USC2409014A |  | DRY_ETCH_P1A WORK_LABOR_DEC 2023 TO JUN 2024_DELTA WYE | 45542 | 45546 | 154683.25 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 154683.25 | 0 | 154683.25 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1219 | P | USC2409015A |  | Dry Etch P1B Delta Wye Lump Sum Contract | 45542 | 45548 | 1220000 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1220000 | 0 | 1220000 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1220 | P | USC2409016A |  | Position sensor, 0-6000 mm, Profinet, M4, Linearity 0,02% | 45542 | 45545 | 2749.27 | [6 empty] | Mennens Cleanroom Cranes B.V. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2749.27 | 44100 | -41350.73 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1221 | P | USC2409017A |  | Ring for 1" Tube OD Quick-Clamp High-Vacuum Fitting | 45545 | 45551 | 2494.82 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 2494.82 | 0 | 2494.82 | 0 | [73 empty] | - |  | 1107.08
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1222 | P | USC2409018A |  | Gardner Bender HWT-0025 Heavy-Wall Heat Shrink Tube, 7/8" | 45546 | 45547 | 157.74 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 141.16 | 0.89489 | 16.58 | 21524 | -21507.42 | 0 | 141.16 | [72 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1223 | P | USC2409020A |  | KPAN03-T: LUMP SUM REWORK SCOPE | 45546 | 45549 | 33402 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 33402 | 0 | 33402 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1224 | P | USC2409021A |  | KIHIB2: EXHAUST, SIGNAL & POWER CABLE INSTALL | 2024/9/11 2024/10/10 | 2024/9/16 2024/10/10 | 0 | -2210375.61 | 2210375.61 |  |  |  |  | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 1 | 0 | 3415.13 | -3415.13 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1225 | P | USC2409022A |  | Pipe removal and added construction 3/8" *4/1/4" X3/8" *6 (KCANN2) | 45547 |  | 92440.86 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 92440.86 | 7972.13 | 84468.73 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1226 | P | USC2409023A |  | Labor multiple tool 3/6/2024-5/6/2024 Mechanical Interconnect - Labor KCSCS3, KEPSL5, KEPSL3, KEPSL1, KDCCS1,KEPSL4, KDCRS4, KDCCS2, KDCCS3, KCSCSA, KEBCL1, KRWRS7, KCSCS9, KCSCS7, KEPSL6, KEPSS1, KCSCSB, KCSCSC, KCSCS6, KEPSL2 | 45547 | 45552 | 147000 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved | [14 empty] | 147000 | 1 | 0 | 0 | 0 | 0 | [73 empty] | 147000 |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1227 | P | USC2409024A |  | Brady M21-750-499 Signs, Labels & Markers Make-Your-Own Sign, Label & Marker Blanks Continuous Tape Cartridges for Printers | 45547 | 45547 | 194.74 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 173.2 | 0.88939 | 21.54 | 0 | 21.54 | 0 | 173.2 | [72 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1228 | P | USC2409025A |  | WIRE 6-04TC-VN #6AWG/4C All Insulated ‘per 1000’ | 45548 | 45551 | 21524 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21524 | 0 | 21524 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection | Material | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1229 | P | USC2409026A |  | 12316065ST 1/2 X .065 WALL SMLS 316 TUBIN | 45548 | 45548 | 772.8 | [6 empty] | Industrial Pipe & Valve Inc. | PR Approved | PO Approved |  | 100% by progress, T/T 30 days | Eddie |  |  | Chia-Yi Chang | Eddie | NA |  | Henry |  | N | NA |  | 0 | 0 | 772.8 | 0 | 772.8 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 772.8 | 0 | 0
Interconnection | Interconnection | Equipment | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1230 | P | USC2409027A |  | 400CL-012H 1-1/4" PIPE P/E CLR PVC SCH40 CPN-P-TIC-CPV-PI-035 | 45548 | 45551 | 3359.73 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 50% down payment, 50% after acceptance, T/T 7 days. | Eddie |  |  | Chia-Yi Chang | Eddie | NA |  | Henry |  | N | NA |  | 0 | 0 | 3359.73 | 0 | 3359.73 | 0 |  | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1231 | P | USC2409028A |  | Low Voltage Electrician (8)Hrs per day=total of (105)working days X(2) headcount (1680) totalt man Hrs. | 2024/9/14 2024/9/17 | 45561 | 138255 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved | PR R1:Updated "Description Title" on New Quote. New Upload | [13 empty] | 0 | 0 | 138255 | 1905.6 | 136349.4 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1232 | P | USC2409030A |  | Fire Retardant Snap Tubing 50m Grey | 45549 | 45554 | 18366.75 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 18366.75 | 0 | 18366.75 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1233 | P | USC2409031A |  | Vantech 3-Bar White Aluminum Bolt-On Ladder Rack System Ford Transit 2015-current Model H1753W | 2024/9/16 2024/9/19 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Orders related to our company's car accessory, such as this ladder rack, go through HR department for purchase by APN | [13 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1234 | P | USC2409032A |  | F21 Dif. ADD O3 LOCAL DETECTOR *10set: 機型-1台1EA偵測器 - 共10台 | 45553 | 45555 | 133287 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 133287 | 997501 | -864214 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1235 | P | USC2409033A |  | DVF-B160250LH ISO160/200/250 CLAMP ALUMINUM QTY(1)= 4CLAMPS | 45553 |  | 1109.21 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1109.21 | 0 | 1109.21 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1236 | P | USC2409034A |  | 6" ISO160 BLANK FERRULE (FLANGE) SS | 45553 | 45553 | 324.53 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 324.53 | 102060 | -101735.47 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1237 | P | USC2409035A |  | CED S41010CT00: 1'' SS304 RIGID CONDUIT, 10' W/CO | 45553 | 45553 | 1905.6 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1905.6 | 0 | 1905.6 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1238 | P | USC2409036A |  | SINGLE-LAYER TUBING / CONSTRUCTION LABOR (5PPL2DAYS) | 45553 |  | 644335 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 644335 | 0 | 644335 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1239 | P | USC2409037A |  | KDZRTA: TOOLS BLAST CONDUIT INSTALLATION | 45553 |  | 432705.6 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 432705.6 | 0 | 432705.6 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1240 | P | USC2409039A |  | KPAE02-S Full Scope | 45554 | 45556 | 5053720 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 5053720 | 4568 | 5049152 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1241 | P | USC2409040A |  | Interconnection RS Payroll from Feb 2024 to Jun 2024 | 45554 | 45562 | 217997.65 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 217997.65 | 1 | 0 | 3000 | -3000 | 0 | [73 empty] | 217997.65 |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1245 | P | USC2409042A |  | P1B_KCANN4_CVD2_N/20.5_LAM | 45555 | 45559 | 1191034.88 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1191034.88 | 0 | 1191034.88 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1246 | P | USC2409043A |  | RENTAL OF A IR 63 FOR 2 TOOLS FOR 45 DAYS | 45555 | 45560 | 15750 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15750 | 0 | 15750 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1247 | P | USC2409044A |  | 5LJ49: TONGUE & GROOVE PLIER: FLAT, GROOVE JOINT, 5 1/2 IN MAX JAW OPENING | 45555 | 45558 | 123.78 | [6 empty] | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved | [14 empty] | 0 | 0 | 123.78 | 882.41 | -758.63 | 0 | [73 empty] | - |  | 123.78
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1248 | P | USC2409045A |  | KPCD (14, 24, 25, 27-333) TOOLS: INSTALL/ROUTE CABLES | 45556 | 45566 | 158784 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 158784 | 0 | 158784 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1249 | P | USC2409046A |  | KPE607-S Ball Valves | 45556 | 45559 | 4568 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4568 | 0 | 4568 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1250 | P | USC2409047A |  | KPOCS4 & KPOCS5 SS Flat Flange Cuts | 45556 | 45559 | 3000 | [6 empty] | CS Industrial Services LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3000 | 0 | 3000 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1251 | P | USC2409048A |  | 8" SUS304 Elbow 90° | 45556 | 45560 | 10214 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 10214 | 0 | 10214 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1252 | P | USC2409049A |  | 22PTL-088020: Milw M18 Cordless Wet/Dry Vacuum (Bare Tool)#0880-20 | 45556 | 45558 | 1849.75 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1849.75 | 590.56 | 1259.19 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1253 | P | USC2409051A |  | Wire: SOOW/SOW-6/4-Black -RCL "ONE CUT=200ft" **Cut Wire is NOT refundable** | 45560 | 45560 | 882.41 | [6 empty] | Crescent Electric Supply Co | PR Approved | PO Approved | [14 empty] | 0 | 0 | 882.41 | 1756.4 | -873.99 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1254 | P | USC2409052A |  | KEPSL7 INTERNAL CONNECT HOOK UP | 45560 | 45561 | 1600000 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1600000 | 0 | 1600000 | 0 | [73 empty] | - |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1255 | P | USC2409053A |  | SUS304: NW63 -> 4” | 45560 | 45561 | 509.92 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 509.92 | 644.4 | -134.48 | 0 | [73 empty] | - |  | -
|  |  | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1256 | P | USC2409055A |  | PR-PO for PRPS opening invoice for Foundations | 45562 | 45562 | 12503.77 | [6 empty] | RS PAYROLL SERVICES | PR Approved | PO Approved | [14 empty] | 12503.77 | 1 | 0 | 1328.65 | -1328.65 | 0 | [73 empty] | 12503.77 |  | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1257 | P | USC2409056A |  | 30 ft. Looped End Steel Cable with Resettable Outdoor Combination Lock (Bundle Pack) | 45562 | 45562 | 109.96 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 109.96 | 0 | 109.96 | 0 | [73 empty] | - |  | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1260 | P | USC2409057A |  | 1 1/4IN STR L/T CONN STEEL | 45562 | 45562 | 590.56 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 590.56 | 0 | 590.56 | 0 | [75 empty] | -
Interconnection | Interconnection |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1258 | P | USC2409058A |  | COND EMT3 EMT Steel Material; hot-dip galvanized finish; 10FT; 3.5 Inch outer diameter; UL 797 Approval; ANSI C80.3 Applicable standard; 263 LB Per 100 Ft Weight; 3Inch trade size; 0.072 Inch wal thickness; plain and style | 45562 | 45562 | 1756.4 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1756.4 | 0 | 1756.4 | 0 | [73 empty] | - |  | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1262 | P | USC2409059A |  | M10 ISO flanges Double Wall Clamp Double Claw Clamps Vacuum Fittings Aluminium Semiconductor ISO160-ISO250 (4 Pack) | 45563 | 45562 | 41.78 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 41.78 | 0 | 41.78 | 0 | [75 empty] | 37.98
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1263 | P | USC2410001A |  | REDUCING UNION 1" SWG X 1/2" SWG | 45566 | 45567 | 644.4 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 644.4 | 167666.23 | -167021.83 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1264 | P | USC2410002A |  | Quick-Clamp High-Vacuum Fitting, Wing Nut Clamp for 1" Tube OD | 45567 | 45570 | 1331.88 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1331.88 | 166.75 | 1165.13 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1267 | P | USC2410004A |  | 6" Rigid I.P. Pipe Strut Clamp EG (6 5/8" OD) | 45568 | 45572 | 476.18 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 476.18 | 3085.61 | -2609.43 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1265 | P | USC2410005A |  | Falltech 7445 Strut Anchor | 45568 |  | 104.5 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 104.5 | 0 | 104.5 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1266 | P | USC2410006A |  | SELTERM 25pcs 2 AWG 5/16" Stud Marine Grade Tinned Copper Battery Cable Lugs, 2 Gauge Ring Terminals, UL Wire Lugs Electrical Battery Cable Ends, Tinned Copper Lugs Battery Terminal Connectors | 45569 | 2024/10/5 2024/10/11 | 140.27 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 140.27 | 0 | 140.27 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1267 | P | USC2410007A |  | 2-1/2 in. x 20 ft. DUAL-FLEX Locking Vacuum Hose Kit Accessory Shop Vac Attachment for RIDGID Wet Dry Vacuums | 45569 | 45570 | 541.16 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 541.16 | 6190.2 | -5649.04 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1271 | P | USC2410008A |  | KDANTB, P1B, TEL, DIF1 | 45569 | 45575 | 4386593.08 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 4386593.08 | 0 | 4386593.08 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1268 | P | USC2410009A |  | Lock washer 防鬆華司,galvanzied 鍍鋅,3/8" | 45569 | 45574 | 230 | [6 empty] | Zoro Tools, Inc. dba Zoro | PR Approved | PO Approved | [14 empty] | 0 | 0 | 230 | 0 | 230 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1273 | P | USC2410011A |  | B-LINE B1516S 1-IN EMT & 3/4-IN GRC STRUT STRAP 1-PIECE WITH SADDLE | 45569 | 45572 | 3085.61 | [6 empty] | Sonepar Mountain Holdings LLC dba QED | PR Approved | PO Approved | [14 empty] | 0 | 0 | 3085.61 | 0 | 3085.61 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1274 | P | USC2410012A |  | KPE607-S CW Piping Planking Labor | 45570 | 45573 | 7694 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 7694 | 0 | 7694 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1275 | P | USC2410013A |  | HS Extra Long Heavy Duty Zip Tie Straps (50 Pack) Thick 0.35 Inch Plastic Duct Zip Ties Heavy Duty 175 Pounds,Black Large Zip Ties 36 Inch for HVAC,Travel,Packaging,Vessel | 45570 | 45572 | 1693.23 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1693.23 | 0 | 1693.23 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1276 | P | USC2410014A |  | STANDARD MOBILE STORAGE CABINET - 36 X 24 X 78", UNASSEMBLED, BLACK ¦ INDUSTRIAL STORAGE CABINET - 36 X 24 X 72", UNASSEMBLED, BLACK ¦ CABINET DOLLY - 36 X 24", BLACK PART OF KIT | 45571 | 45574 | 6190.2 | [6 empty] | U-Line Corporation | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6190.2 | 0 | 6190.2 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1277 | P | USC2410016A |  | IR63 MACHINE RENTAL PER MONTH | 45574 | 45575 | 8591 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | [14 empty] | 0 | 0 | 8591 | 0 | 8591 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1278 | P | USC2410017A |  | Lit 3 P1B Tools Saturday Work | 45574 |  | 62050 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 62050 | 0 | 62050 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1279 | P | USC2410018A |  | Lit 1 All P1B Tools Saturday Work | 45574 |  | 26592 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 26592 | 0 | 26592 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1280 | P | USC2410019A |  | Yellow Jacket Heavy Duty Extension Cord, 25Ft, 12 Gauge, 3 Conductor, Lighted End, Weather Resistant, SJTW, Yellow, 2883 | 45574 | 45574 | 39.05 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 39.05 | 0 | 39.05 | 0 | [75 empty] | -
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1281 | P | USC2410020A |  | Labor for Multiple Tool Cabling | 45574 |  | 7004 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 7004 | 0 | 7004 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1288 | P | USC2410021A |  | XLPE/PE電纜,600V,4AWG,4C,1 Ground 接地*1,TCXH | 45575 | 45579 | 40500 | [6 empty] | AUCAN INC. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 40500 | 0 | 40500 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1289 | P | USC2410023A |  | 12/2023 - 8/2024 | 45575 | 45581 | 48.45 | [6 empty] | Linde Gas & Equipment Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 48.45 | 0 | 48.45 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1282 | P | USC2410024A |  | 6AWG CU 1H LUG 1/4" STUD | 45575 | 45576 | 701 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | [14 empty] | 0 | 0 | 701 | 0 | 701 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1283 | P | USC2410025A |  | 606-110*15 25#白特+亮膜管路標籤 110*15mm | 45575 | 45579 | 6746 | [6 empty] | Ever Green Label Prining Co.,LTD | PR Approved | PO Approved | [14 empty] | 0 | 0 | 6746 | 0 | 6746 | 0 | [75 empty] | -
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1292 | P | USC2410026A |  | Conduit fitting 軟管管接,galvanized steel 鍍鋅鋼,2",liquid tight 防水 | 45576 |  | 141645.62 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 141645.62 | 0 | 141645.62 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1293 | P | USC2410027A |  | Clean Room Masking Tape, 2" Wide, 108 Feet Long, Black | 45576 | 45580 | 1909.31 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1909.31 | 0 | 1909.31 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1294 | P | USC2410028A |  | uxcell Rubber Cushion Strut Clamp 4Pcs 2-1/2" Cushioned Clamp Strut Rigid Steel Pipe Clamp for Mounting PEX Pipe Tubing to Strut Channels | 45576 |  | 135.92 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 135.92 | 0 | 135.92 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1295 | P | USC2410029A |  | 1 5/8" Square Post Base (6 x 6 x 3 1/2 Hgt) EG | 45576 |  | 323.44 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 323.44 | 0 | 323.44 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1296 | P | USC2410030A |  | B30C-4000-595-OR B30,B595,ORN,4" X 100 FT FIT | 45577 | 45581 | 2550.1 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approving | [14 empty] | 0 | 0 | 2550.1 | 0 | 2550.1 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1297 | P | USC2410031A |  | steel channel parts,galvanized stee l鍍鋅鋼,E619,3D L-Shape Angle Bracket(18mm hole*1+14mm hole*1) 立體L片(18mm孔*1+14mm孔*1) | 45577 |  | 1589.5 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1589.5 | 0 | 1589.5 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1298 | P | USC2410032A |  | 98010063242 4 THHN STR CU GREEN CUT REEL Cuts: 1 @ 850 ft : 850SQ FT | 45577 | 45581 | 1277.63 | [6 empty] | Sonepar Mountain Holdings LLC dba QED | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1277.63 | 0 | 1277.63 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1299 | P | USC2410033A |  | REED Tool EHTP500 Electric Hydrostatic Test Pump, 110V, Single Phase 50/60 Hz | 45577 | 45581 | 657.64 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 657.64 | 0 | 657.64 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1300 | P | USC2410034A |  | KPE606-S: Whip to Ball Valve Nipples Material | 45577 | 45581 | 899 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | [14 empty] | 0 | 0 | 899 | 0 | 899 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1301 | P | USC2410035A |  | TR Industrial Multi-Purpose UV Resistant Black Cable Ties, 12 inches, 100 Pack | 45578 | 45581 | 428.67 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 428.67 | 0 | 428.67 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1302 | P | USC2410036A |  | GREENBERRY BLANKET PO FOR C/O CABLE CRIMPING | 45579 | 45582 | 200000 | [7 empty] | PR Approved | PO Approving | [14 empty] | 0 | 0 | 200000 | 0 | 200000 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1303 | P | USC2410037A |  | 3/8 -2 meter hose PVC pressure: P-TIC-MKS-HO-009-L-2M | 45580 |  | 11416.72 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 11416.72 | 0 | 11416.72 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1304 | P | USC2410038A |  | XLPE/PE電纜,600V,250kcmil,4C,1 Ground 接地*1,TCXH | 45581 |  | 6683.6 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 6683.6 | 179053.05 | -172369.45 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1305 | P | USC2410039A |  | M12 Fuel 12V 1/4" Lithium-ion Cordless Impact Driver Kit - with 2 Batteries, Charger, and Tool Case | 45581 | 45582 | 152.88 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approving | [14 empty] | 0 | 0 | 152.88 | 0 | 152.88 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1306 | P | USC2410041A |  | Klein Tools 56334 Electrical Fish Tape, 240-Foot Steel Wire Puller with Double Loop Tip, Optimized Housing and Handle, For Heavy Duty Wire Pulls | 45581 | 45581 | 510.3 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 510.3 | 0 | 510.3 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1307 | P | USC2410042A |  | 32625T163: Strut-Mount Vibration-Damping Routing Clamp with TPE Rubber Cushion, Zinc-Plated Steel, 4-1/2" ID | 45581 | 45581 | 1620.57 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved | [14 empty] | 0 | 0 | 1620.57 | 0 | 1620.57 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1308 | P | USC2410043A |  | Utility Cart with Cabinet | 45581 |  | 819.7 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 819.7 | 146375 | -145555.3 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1309 | P | USC2410044A |  | HANDI-MOVER - 23 X 35" | 45581 |  | 470.41 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 470.41 | 50000 | -49529.59 | 0
|  |  | USC24C015 | TSMC Fab 21 P1B Tool Hook Up | 1310 | P | USC2410045A |  | Size: 0.25” x 0.75” (6.35mm x 19 mm) | 45582 | 45581 | 4275 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approving | [14 empty] | 0 | 0 | 4275 | 0 | 4275 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1311 | P | USC2410049A |  | 1IN CONN KIT | 45582 |  | 1441.65 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 1441.65 | 11500 | -10058.35 | 0
|  |  | USC24B002 | Tool Interconnection Project (Main Tool & Other Vendors) | 1312 | P | USC2410051A |  | KPAN02-S SUS Rework Labor | 45583 |  | 3401 | [7 empty] | PR Approved | PO Processing | [14 empty] | 0 | 0 | 3401 | 0 | 3401 | 0
Base-Build | CCTV |  | USC21C001 | tsmc AZ Temporary Office Physical Security | 1231 | C | USCSB2102001A |  | AZ temporary office CCTV installation | 44243 | 44245 | 21171 | [6 empty] | B&D Industries, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 21171 | 0 | 21171 | 0 | [73 empty] | - |  | -
Base-Build | CCTV |  | USC21C001 | tsmc AZ Temporary Office Physical Security | 1232 | C | USCSB2102002A |  | Metal gate installation | 44243 | 44245 | 15248 | [6 empty] | B&D Industries, Inc. | PR Approved | PO Approved | [14 empty] | 0 | 0 | 15248 | 0 | 15248 | 0 | [73 empty] | - |  | -
Base-Build | Speed Gate | Equipment | USC21C002 | TSMC AZ Temp Office Speed Gate | 1315 | C | USCSB2103005A |  | tsmc AZ office speed gate engineering | 44278 | 44279 | 85570 | [6 empty] | B&D Industries, Inc. | PR Approved | PO Approved |  | 100% by progress , T/T 7 Days | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | NA |  | Henry |  | N | NA |  | 85570 | 1 | 0 | 0 | 0 | 0 | 85570 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Speed Gate | Equipment | USC21C002 | TSMC AZ Temp Office Speed Gate | 1316 | C | USCSB2105001A |  | Speed gate opeing cover and install | 44324 | 44327 | 1825 | [6 empty] | B&D Industries, Inc. | PR Approved | PO Approved |  | 100% by progress , T/T 30 Days | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | NA |  | Henry |  | N | NA |  | 1825 | 1 | 0 | 0 | 0 | 0 | 1825 | - | - | [25 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 1317 | C | USCSB2108001A |  | Mechanical works for UPW package | 44427 | 44435 | 86000000 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Chia-Yi Chang | Cherry Chang | UPW | 44461 | Matt |  | Y | 5005 |  | 85961575 | 0.99955 | 38425 | 0 | 38425 | 0 |  | 2466924 | 982645 | 3906729 | 2943825 |  | 2276834 | 4461100 | 450026 | 6877712 |  | 5267057 |  | 2091083 |  | 2215396.33 |  |  | 2511386 | 6073662 |  | 4453731 |  | 4081416 |  | 8156020.16 |  | 4183951.51 | 0 | 2540935 |  | 4203592 |  | 0 | 2367969 | 3457032 |  | 1526847 |  | 2971422 | 0 | 1217312 | 0 | 2315152 |  | 0 | 1635302 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 364939 | [6 empty] | 326514 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 1318 | C | USCSB2108003A |  | Modular Site Office | 44433 | 44441 | 700000 | [6 empty] | Design Modulars Inc. | PR Approved | PO Approved |  | 80% upon delivery and completion of DMI’s scope of work.Net 30 days 20% upon final occupancy and inspection final.Net 30 days | Cherry Chang |  |  | Yi-Hsin Lee | Cherry Chang | N | 44456 | Matt |  | N | 5005 |  | 700000 | 1 | 0 | 0 | 0 | 0 | [5 empty] | 560000 |  | 140000 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 1319 | C | USCSB2108004A |  | tsmc Basement Equipment Mezzanines | 44439 | 44445 | 3000000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% Progress payment T/T-30Days (After Acceptance); 5% Final payment T/T-30 Days(After Acceptance) | York Yeh |  |  | Yi-Hsin Lee | York Yeh | N |  | Matt |  | N | 5005 |  | 2850000 | 0.95 | 150000 | 0 | 150000 | 0 |  | 50000 | 300000 | 300000 | 300000 |  | 100000 |  | 144186 |  | 144333 |  | 219711 |  | 491417 |  |  |  | 247297 |  | 283000 |  | 221265 | [5 empty] | 48791 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 1320 | C | USCSB2109001A |  | tsmc 43rd Ave Sewer Line Extension | 44440 | 44445 | 2000000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | UPW(N) |  | Matt |  | Y | 5005 |  | 2000000 | 1 | 0 | 0 | 0 | 0 |  | 300000 | 1315157.69 | 384842.31 | [24 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | LPS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1321 | C | USCSB2109003A | -03 | Mechanical/Installation w/Engineering Support | 44443 | 44462 | 24675557.76 | -3324442.24 | 28000000 |  | V |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | 2/2 contract terminate 7/11 change order (remove equipment rigging scope) 9/2 scope reduction | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Rui Ma | Cherry Chang | WWT | 44515 | Henry |  | Y | 5005 |  | 24675557.76 | 1 | 0 | 0 | 0 | 0 |  |  | 905030 | 521272.65 |  | 276903.42 | 921068.63 | 4146903.13 | 603353.33 |  | 1036753.1 |  |  |  | 1050957.87 | 1402278.28 |  | 1611859.33 | 1847484.66 |  | 102100 | 1675184.02 | 2017484.57 | 6556924.77 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | LPS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1322 | C | USCSB2109004A | -01 | Front-End Engineering Support Service | 44443 | 44462 | 599155.6 | -844.4 | 600000 |  |  |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | Rev01-According to PM indication:Terminating LPS from the project | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Rui Ma | Cherry Chang | WWT |  | Henry |  | Y | 5005 |  | 599155.6 | 1 | 0 | 0 | 0 | 0 |  |  | 100000 | 150000 |  |  |  |  | 0 |  | 100000 |  | 0 |  |  |  |  | 129536 | 119619.6 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Slurry | Southland | USC21C006 | F21P1 Slurry package | 1323 | C | USCSB2109005A | -01 | Slurry Mechanical Work | 2021/9/4 2022/1/7 | 2021/9/16 2022/1/7 | 15420592.14 | 702235.1 | 14718357.04 | V | V | V |  | Southland Industries | PR Approved | PO Approved | 標單需求澄清後，報價調整 please provide final quotation. | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang | DDP | 1 year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | Cherry Chang | Slurry | 44482 | Henry | Mechanical Work | Y | 5005 |  | 15420592.14 | 1 | 0 | 0 | 0 | 0 |  |  | 295000 | 98325.7 |  | 166911 |  |  | 356242.29 | [5 empty] | 237492 |  | 44441 |  | 247418 |  | 1056003.31 |  |  |  | 2869640 |  | 995571 |  | 1544044 |  |  |  |  | 0 | 2103594 |  | 504716 | 1256712 | 1370141 |  | 1008145.59 | 0 | 0 | 0 |  | 0 | 0 | 457460.42 | 0 | 210200.32 |  |  | 270090 | 328444.51 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 1324 | C | USCSB2109006A | -01 | Slurry Mechanical Instrument Air | 2021/9/4 2023/12/11 | 2021/9/14 2023/12/13 | 0 | -1258610 | 1258610 |  | V |  |  | Prime Mechanical, Inc. | PR Approved | PO Approved | PO R1:arrcording to PM indication :Close Out PO | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Slurry |  | Henry |  | Y |  |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Labor | USC21C006 | F21P1 Slurry package | 1325 | C | USCSB2109007A | -05 | Slurry Electrical | 2021/9/4 2021/12/14 2022/6/15 2023/5/17 2023/4/19 | 2021/9/14 2021/12/20 2022/6/17 2023/4/26 2023/5/19 2023/11/23 | 892286.55 | -210232.36 | 1102518.91 |  | V |  | V | Climatec, LLC | PR Approved | PO Approved | PO R5:According to PM indication:Closing out Climatec from the project per request. Scope Changed after reviewing rev02-6/17 scope changed (material raised up ) from 2467383 to 2485140.6 rev03-4/26 cancelling climatatec rev04-5/19 adjust PR amount to issue the same work scope to Hua Yi | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Slurry (Y) |  | Henry |  | Y | 5005 |  | 892286.55 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 892286.55 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 1326 | C | USCSB2109008A | -01 | VOC Mechanical Work | 2021/9/4 2021/9/24 | 2021/9/14 2021/9/30 | 8497604.48 | 523677.36 | 7973927.12 | V |  |  |  | Southland Industries | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | VOC | 44482 | Martin |  | Y | 5005 |  | 8497604.22 | 1 | 0.26 | 0 | 0.26 | 0 |  |  | 169260 | [11 empty] | 815419 |  |  |  | 216808 |  | 1355044.9 |  | 1638388 |  | 864412 |  | 984866 |  | 271272 |  |  | 1067861 |  | 0 |  |  | 129885 | 343592 | 570874 |  | 69922.32 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | - |  | - |  | 0
Base-Build | Chemical | Southland | USC21C005 | F21P1 Chemical & WCCS package | 1327 | C | USCSB2109009A | -02 | WCCS Mechanical Work | 2021/9/4 2021/9/24 2022/1/13 | 2021/9/14 2021/9/30 2022/1/18 | 15735376.61 | 4773066.55 | 10962310.06 | V | V | V |  | Southland Industries | PR Approved | PO Approved | Rev02-Scope change after clarification Rev01-Raw material price increase of Mechanical work | 95% by progress, 5% after acceptance, T/T 30 days | York Yeh |  |  | Yi-Hsin Lee | York Yeh | CHEM | 44482 | Henry |  | Y | 5005 |  | 15735376.61 | 1 | 0 | 0 | 0 | 0 |  |  | 219248 |  |  | 303687.4 |  | 315820 | 176363.06 |  | 38550 |  |  |  | 330017 |  | 76014 |  |  |  | 1151755 |  | 297435 |  | 1238784 |  | 1594990 |  | 1598093 |  |  |  |  | 0 | 1344047 |  | 886899 | 537594 | 2559300 |  | 0 | 1628857.64 | 0 | 0 | 1086956.64 | 0 | 0 | 0 | 251604.22 | 0 |  |  | 0 | 0 | 99361.65 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC21C007 | F21P1 VOC package （Installation ) | 1328 | C | USCSB2109010A |  | VOC Electrical & Controls | 44460 | 44490 | 4099969.21 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | Cherry Chang |  |  | Yi-Hsin Lee | Cherry Chang | VOC | 44494 | Martin |  | Y | 5005 | Y | 4099969.21 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 23400.08 |  | 675199.77 | 536571.24 | 27265.04 |  | 19396.52 |  | 19396.52 |  |  |  |  | 19396.52 | 39468.12 |  | 19396.52 |  | 129064.89 |  | 194482.17 |  | 263346.54 |  | 0 | 210688.68 |  |  | 368774.47 | 0 | 215564.41 |  | 258018.11 |  | 311614.45 |  | 271232.22 | 0 | 170536.5 | 0 |  | 160544.35 | 105931.05 | 29310.45 | 0 | 31370.59 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1329 | C | USCSB2109011A | -01 | UPW Tank Inspection | 2021/9/21 2021/11/2 | 2021/9/30 2021/11/4 | 0 | -119244 | 119244 |  |  | V |  | Technical Inspections Group | PR Approved | PO Approved | MICU 10/27提出， 執行異動結案 | PR取消 | York Yeh | DDP | 1year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | York Yeh | N | x | Matt |  | N | NA |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 1330 | C | USCSB2109012A |  | Chemical Storage Design, PE Stamp and onsite Work | 44460 | 44463 | 1060000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by Progress-T/T 30 days, 5% after final acceptance - T/T 30 days | Cherry Chang |  |  | Rui Ma | Cherry Chang | Y | 44468 | Henry |  | N | 5005 |  | 1060000 | 1 | 0 | 0 | 0 | 0 |  | 30000 |  | 30000 | 30000 |  | 30000 |  | 135000 | [7 empty] | 72500 |  | 265834 |  | 240819 |  | 120829 | [5 empty] | 0 |  |  |  | 50233 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 54785 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1331 | C | USCSB2109013A | -01 | WWT Tank Inspection | 2021/9/21 2021/11/02 | 2021/9/28 2021/11/4 | 0 | -191946 | 191946 |  |  | V |  | Technical Inspections Group | PR Approved | PO Approved | MICU 10/27提出， 執行異動結案。 | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | x | Henry |  | N | NA |  | 0 | 1 | 0 | 0 | 0 | 0 |  | - | [26 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 1332 | C | USCSB2109014A |  | CDS Mechancial Work Pre-constru Indirect Labor | 44462 | 44468 | 274050 | [6 empty] | Harder Mechanical Contractors, Inc | PR Approved | PO Approved |  | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | CHEM |  | Henry |  | Y | 5005 |  | 274050 | 1 | 0 | 0 | 0 | 0 |  | 61335 | 67920.9 | 101908.9 | 42885.2 | [23 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Rosendin | USC21C005 | F21P1 Chemical & WCCS package | 1333 | C | USCSB2109015A |  | CDS & WCCS Electrical | 44463 | 44469 | 17593400.53 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days | York Yeh |  |  | Yi-Hsin Lee | York Yeh | CHEM |  | Henry |  | Y | 5005 |  | 17414347.5 | 0.98982 | 179053.03 | 0 | 179053.03 | 0 | [8 empty] | 149405.43 |  | 683579.07 |  | 683579.07 |  | 683579.07 |  | 138108.51 |  | 285535.39 |  | 683467.33 |  | 784663.64 |  |  | 652556.18 |  |  | 0 | 1035342.01 |  | 1004716.07 |  | 823696.8 | 1286168.86 | 173493.75 |  |  | 1918232.22 |  | 1595328.69 | 0 | 1254380.34 | 0 |  | 0 | 1409135.26 | 0 | 154611.25 | 600482.93 | 197726.22 |  | 354477.45 | 862081.96 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC21C008 | F21P1 CCTV & Security | 1334 | C | USCSB2109016A | -01 | CCTV Electrical Field Work | 2021/9/25 2023/6/16 | 2021/9/30 2023/6/19 | 3465068.83 | -1250000 | 4715068.83 |  |  |  |  | BPG Technologies, LLC | PR Approved | PO Approved | Adjusting this PR amount based on PM's request. BPG will be expel from the work recently. | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | CCTV |  | Martin |  | Y | *5005 |  | 3465068.83 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 46952 |  | 15651 |  |  |  | 290381 |  | 127431 |  | 236976 |  |  |  | 321867 |  |  |  | 312234 |  | 712582 |  | 466621 |  | 198124 |  |  | 0 |  |  |  | 736249.83 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 1335 | C | USCSB2110001A |  | DIA 200M, Pole, Extension, CPE | 44470 | 44477 | 86667 | [6 empty] | Chunghwa Telecom Global, Inc | PR Approved | PO Approved |  | 100% after completion (Net 30 Days). | York Yeh | Deliver on Site | 1 year hardware warranty, 8x5xNBD, is included. | Ka In Wong Lane | York Yeh | N | 44519 | Matt |  | N | NA |  | 86667 | 1 | 0 | 0 | 0 | 0 |  |  |  | 86667 | [24 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC21C007 | F21P1 VOC package （Installation ) | 1336 | C | USCSB2110002A |  | Pre-construction | 44471 | 44475 | 199950 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  | 100% by progress, T/T 30 days. | York Yeh |  |  | Rui Ma | York Yeh | VOC | 44490 | Martin |  | Y | 5005 |  | 199950 | 1 | 0 | 0 | 0 | 0 |  | 66650 | 66650 | 66650 | [24 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Material | USC21C013 | F21P1 AMC THC Monitoring System | 1337 | C | USCSB2110004A |  | AMC THC Monitoring System Package Rack & Accessories | 44477 | 44487 | 2668000 | [6 empty] | Weltall Technology Corporation | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Martin |  | ? | NA |  | 2401200 | 0.9 | 266800 | 0 | 266800 | 266800 |  |  |  |  | 400200 | [13 empty] | 2001000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - |  | 0 | 266800
Base-Build | AMC THC | Material | USC21C013 | F21P1 AMC THC Monitoring System | 1338 | C | USCSB2110005A | -01 | AMC THC Monitoring System Package Host Equipment | 44477 | 2021/10/18 2021/10/20 | 1000000 | [6 empty] | Weltall Technology Corporation | PR Approved | PO Approved | 修正貿易條款，原CIF to LAX修改為DDP on site. | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Martin |  | ? | NA |  | 900000 | 0.9 | 100000 | 0 | 100000 | 100000 |  |  |  |  | 150000 | [13 empty] | 750000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - |  | 0 | 100000
Base-Build | Barcode | Labor | USC21C012 | F21 Barcode RFID System | 1339 | C | USCSB2110006A | -02 | F21P1 Barcode & RFID System Electrical | 2021/10/8 2023/6/16 2023/8/24 | 2021/10/14 2023/6/19 2023/10/25 | 4002.14 | -95997.86 | 100000 |  |  |  |  | BPG Technologies, LLC | PR Approved | PO Approved | R2: BPG is expelled from MICU recently and the PR needs to be adjusted to actual payment amount according to PM. R1: Adjusting this PR amount based on PM's request. BPG will be expel from the work recently. | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | BARCODE | 44517 | Martin |  | Y | *5005 |  | 4002.14 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 4002.14 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 1340 | C | USCSB2110007A |  | 帆宣_tsmc F21P1 轉輪中THC建置六點 | 44477 | 44487 | 230000 | [6 empty] | Weltall Technology Corporation | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Martin |  | ? | NA |  | 207000 | 0.9 | 23000 | 0 | 23000 | 23000 |  |  |  |  | 34500 | [13 empty] | 172500 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - |  | 0 | 23000
Base-Build | Pipeline | MMI | USC21C010 | tsmc AZ sewer and water pipeline installation | 1341 | C | USCSB2110008A |  | TSMC Frontage Water Main | 44477 | 44490 | 5655525.57 | 300000 | 5355525.57 |  | V |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | 10/13 專案告知因scope增加故請購異動增加300,000(未成立PO前異動) | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | Cherry Chang |  |  | Rui Ma | Cherry Chang | Y |  | Martin |  | N | 5005 |  | 5655525.57 | 1 | 0 | 0 | 0 | 0 |  |  |  | 1335745.69 | 1354538.74 |  | 1005317.72 | 1215860 | 297604.21 |  | 63682.93 | [9 empty] | 382776.28 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1342 | C | USCSB2110009A | -01 | Outsourcing Service | 2021/10/12 2022/3/9 | 2021/10/18 2022/3/11 | 0 | -329604 | 329604 |  |  | V |  | World Wide Professional Solutions, LLC | PR Approved | PO Approved | MICU 3/11提出， 執行異動結案。 | 100% by Progress-T/T 30 day (Monthly payment) | Cherry Chang |  |  | Rui Ma | Cherry Chang | N |  | Henry |  | N | NA |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1343 | C | USCSB2110010A |  | Site 3rd Party QC Service | 44482 | 44484 | 500000 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | 44488 | Paul |  | N | NA |  | 500000 | 1 | 0 | 307650 | -307650 | 0 |  |  |  | 8011.58 |  |  | 14956.14 | 23951.01 | 26369.79 |  | 35869.2 |  |  |  | 77159.16 |  |  | 23071.19 | 45497.18 |  | 50831.94 |  | 41878.65 |  | 46076.51 | 36415.05 | 47188.39 |  | 22724.21 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1344 | C | USCSB2110011A |  | WWT CS Tank Inspection | 44482 | 44484 | 24306 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | 44488 | Henry |  | N | NA |  | 24306 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 24306 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Barcode | Material | USC21C012 | F21 Barcode RFID System | 1345 | C | USCSB2110012A |  | F21P1 Barcode & RFID System | 44482 | 44491 | 1550000 | [6 empty] | Ying Pao Technology Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | N | 44502 | Martin |  | ? | NA |  | 1017474.56 | 0.65644 | 532525.44 | 0 | 532525.44 | 155000 | [8 empty] | 109781.26 | [9 empty] | 555701.81 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 109130.1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 238700 | 242861.39 | [10 empty] | - |  | - |  | 77500 | 77500
Base-Build | CCTV | Equipment | USC21C008 | F21P1 CCTV & Security | 1346 | C | USCSB2110013A |  | F21P1 FAB Secruity& CCTV System | 44483 | 44491 | 2272119 | [6 empty] | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Martin |  | ? | 5000 |  | 2021968 | 0.8899 | 250151 | 0 | 250151 | 0 |  |  |  |  | 340818 |  | 77252 | 36354 |  | 454423 |  |  | 454425 |  | 181769 |  | 90884 | [5 empty] | 68183 |  |  |  | 47958 |  | 0 | 86748 |  |  |  | 0 | [5 empty] | 32792 | 0 | 0 | 0 | 0 |  | 0 | 0 | 122303 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 28059 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1347 | C | USCSB2110014A | -01 | Outsourcing Service QA/QC Manager | 2021/10/14 2022/3/9 | 2021/10/22 2022/3/11 | 0 | -281604 | 281604 |  |  | V |  | World Wide Professional Solutions, LLC | PR Approved | PO Approved | MICU 3/11提出， 執行異動結案。 | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N |  | Henry |  | N | NA |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1348 | C | USCSB2110015A | -01 | Outsourcing Service Master Scheduler | 2021/10/14 2022/7/19 | 2021/10/22 2022/7/27 | 0 | -52500 | 52500 |  |  |  |  | World Wide Professional Solutions, LLC | PR Approved | PO Approved | 7/27 manpower shortage ,change odrder to 0 | 100% by progress, T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N |  | Henry |  | N | NA |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 1349 | C | USCSB2110016A |  | UPW common Rack | 44488 | 44495 | 1085250 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y | 44501 | Matt / Martin |  | N | 5005 |  | 1085250 | 1 | 0 | 0 | 0 | 0 |  |  |  | 40000 | 150000 |  | 100000 |  | 30000 |  | 66800 | [5 empty] | 45500 |  | 368771 |  |  |  | 80259 |  | 100335 |  |  |  | 49322.5 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 54262.5 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Labor | USC21C014 | F21P1 WH2SO4 | 1350 | C | USCSB2111002A | -01 | W-H2SO4 Electrical Work | 44509 | 2021/11/15 2023/6/8 | 0 | -583750 | 583750 |  |  |  | v | Climatec, LLC | PR Approved | PO Approved | Termination with Climatec | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | Y |  | Henry |  | Y | 5005 |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | LPS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1351 | C | USCSB2111003A | -01 | WWT Pipe Rack | 2021/11/9 2022/5/21 | 2021/11/15 2022/5/24 | 2000000 | -6500000 | 8500000 | V |  |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | 更換廠商(因LPS下包無法出工) | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | N | 44524 | Henry |  | N | 5005 |  | 2000000 | 1 | 0 | 0 | 0 | 0 |  |  |  | 1700000 |  |  |  |  | 0 |  |  |  |  | 300000 | [14 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Speed Gate | Material | USC21C001 | tsmc AZ Temporary Office Physical Security | 1352 | C | USCSB2111004A |  | CCTV System | 44517 | 44522 | 24299 | [6 empty] | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved |  | 100% by progress, T/T 30 days. | York Yeh | DDP | 1 year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | York Yeh | NA | 44525 | Henry/Martin |  | N | NA |  | 24299 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 24299 | [23 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Speed Gate | Equipment | USC21C002 | TSMC AZ Temp Office Speed Gate | 1353 | C | USCSB2111005A |  | Access Systrm | 44517 | 44522 | 23843 | [6 empty] | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved |  | 100% by progress, T/T 30 days. | York Yeh | DDP | 1 year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | York Yeh | NA | 44525 | Henry/Martin |  | N | NA |  | 23843 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 23843 | [23 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1354 | C | USCSB2111006A |  | Cold Storage | 2021/11/19 2023/12/1 | 44524 | 2780000 | [6 empty] | UHO TECHNIQUE & ENGINEERING CO., LTD. | PR Approved | PO Approved | PR R1: Adjusting the PR amount to align with the actual PO; to release the budget for the project per request. 待專案確認FOB港口 | 90% by progress, net 30 days (20% equipment purchased, 20% delivery F.O.B, 50% by site progress) 10% after acceptance, net 30 days | York Yeh | FOB Keelung port | 1year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | York Yeh | CHEM (Y) | 44533 | Henry |  | Y | NA |  | 2780000 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 556000 | [13 empty] | 834000 |  | 417000 |  |  |  | 417000 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 278000 | 278000 |  | 278000 | 278000 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1355 | C | USCSB2111007A | -01 | UPW Electrical work | 2021/11/30 2021/12/17 | 2021/12/2 2021/12/21 | 16493658 | -78210.4 | 16571868.4 | V |  |  |  | Rosendin Electric, Inc. | PR Approved | PO Approved | Price Discount | 95%by progress, net 30days; 5%after final acceptance, net 30days. | York Yeh |  |  | Yi-Hsin Lee | York Yeh | UPW | 44568 | Matt |  | Y | 5005 |  | 16493657.94 | 1 | 0.06 | 0 | 0.06 | 210372.96 | [7 empty] | 175540 | 244362 |  | 814522.15 |  | 581188.84 |  | 523223.98 |  | 573781.57 |  | 1221976.93 |  | 1387027.55 |  |  |  | 1016428.81 | 1474307.02 | 1490175.67 |  | 1300288.28 |  | 1067689.7 |  | 585665.41 | 0 | 562607.38 |  | 700988.73 |  | 204131.48 |  | 388556.82 | 0 | 430638.74 | 0 |  | 281851.06 | 0 | 0 | 423015.33 | 0 |  |  | 0 | 158870.07 | 280400.29 |  | 125798.18 |  | 417870.24 |  |  | 300000 | 62751.71 |  |  | 250000 |  |  |  | 100000 |  | 105186.48 |  | - | 0 | - | 105186.48 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1356 | C | USCSB2111008A | -01 | UPW civil work (Housekeeping Pad) | 2021/11/30 2021/12/21 | 2021/12/15 2021/12/29 | 1495365.57 | -224391.43 | 1719757 | V |  |  |  | Degan Construction LLC | PR Approved | PO Approved | 批量議價 | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | York Yeh |  |  | Yi-Hsin Lee | York Yeh | N |  | Matt / Martin |  | N | 5005 |  | 1493744.85 | 0.99892 | 1620.72 | 0 | 1620.72 | 0 |  |  |  |  | 299073.11 |  |  | 299073.11 | [6 empty] | 312531.4 |  |  |  | 235077.29 | 347989.94 | [8 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC21C008 | F21P1 CCTV & Security | 1357 | C | USCSB2112001A |  | tsmc security 4th floor | 44531 | 44539 | 31129 | [6 empty] | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days. | York Yeh |  |  | Hsiang Cheng Lee | York Yeh | N |  | Martin |  | N | NA |  | 31129 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 31129 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | LPS | USC21C011 | F21 TMAH System | 1358 | C | USCSB2112002A | -01 | TMAH Mechanical | 2021/12/9 2023/4/5 | 2021/12/27 2023/4/7 | 171351.52 | -1401707.98 | 1573059.5 | V |  |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | 4/7 Adjusting the amount due to the termination with LPS | 95% by progress, 5% after acceptance, T/T 30 days. | Cherry Chang |  |  | Yi-Hsin Lee | Cherry Chang | TMAH | 44564 | Henry |  | Y | 5005 |  | 171351.52 | 1 | 0 | 0 | 0 | 0 | [21 empty] | 171351.52 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | LPS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1359 | C | USCSB2112003A | -02 | WWT Mechanical #2 | 2021/12/10 2022/11/9 | 2021/12/15 2022/11/15 2023/02/02 | 8912174.27 | -455398.34 | 9367572.61 | v |  |  |  | Lasco Process Systems, LLC. | PR Approved | PO Approved | 2/2 contract terminate 11/15 sope transfer to PSS | 95% by Progress-T/T 30 days, 5% after final acceptance -T/T 30 days | York Yeh |  |  | Rui Ma | York Yeh | WWT |  | Henry |  | Y | 5005 |  | 7748947.02 | 0.86948 | 0 | 0 | 0 | 0 | [5 empty] | 88892.31 | 520927.25 | 431799.72 | 569982.36 |  | 133266.67 |  | 0 |  | 133266.67 | 1543872.33 |  | 776196.52 | 774924.81 |  |  | 2556036.71 | 219781.67 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 1360 | C | USCSB2112004A |  | Shane's Grading & Paving | 2021/12/14 2022/2/5 | x | 0 | -170335 | 170335 | [5 empty] | PR Approved | PO Approved | 1/18 MICU weekly neeting ask for cancelation *Already returned to PM side | PR取消 | York Yeh |  |  | Shannon Pulcifer | York Yeh | N |  | Matt |  | N | X |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 1361 | C | USCSB2112005A |  | UPW A-G pipe rack | 2021/12/15 2021/12/22 | 44558 | 769545 | 374850 | 394695 |  | V |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | added scope | 95% by Progress, T/T30 days 5%after final acceptance,T/T 30 days | Cherry Chang |  |  | Yi-Hsin Lee | Cherry Chang | N | 44573 | Matt / Martin |  | N | 5005 |  | 769545 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 50000 |  | 30000 |  | 25000 |  | 116000 |  | 115793 |  | 401667 | [5 empty] | 31085 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1362 | C | USCSB2112006A | -01 | Module office cabling Work | 2021/12/17 2022/1/27 | 2022/1/21 2022/2/9 | 15956.13 | 998.13 | 14958 | V |  | V |  | Galaxy3 LLC | PR Approved | PO Approved | Revise the previous quote and price with the new one due to additional internet AP | 100% by progress, Net 30days (after acceptance). | York Yeh |  |  | Yi-Hsin Lee | York Yeh | N |  | Matt |  | N | NA |  | 15956.13 | 1 | 0 | 10944.8 | -10944.8 | 0 | [7 empty] | 15956.13 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 1363 | C | USCSB2201002A |  | UPW blue, purple ,yellow area pipe rack | 44574 | 44578 | 744188 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress, 5% after acceptance, T/T 30 days | Yi En Wong | DDP | 1 year after the acceptance is completed and transferred to the owner | Yi-Hsin Lee | Yi En Wong | Y | 44581 | Martin | Steel Work | N | 5005 |  | 744188 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 30000 |  | 90000 |  | 192000 |  | 112720 |  |  |  | 88381.04 |  | 80033.86 |  | 104866.6 |  | 8977.1 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 37209.4 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1364 | C | USCSB2201003A | -01 | Equipment install supervision | 2022/1/14 2023/03/23 | 2022/1/20 2023/03/23 | 0 | -800000 | 800000 |  |  |  | V | Marketech International Corp. | PR Approved | PO Approved | tsmc F21P1 MIC 出差人力 Reorganized M4 WO (03/24/2023) | 100% by progress, T/T 45 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT |  |  |  | Y | NA |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1365 | C | USCSB2201004A | -01 | CDS Equipment | 2022/1/14 2023/3/23 | 2022/1/24 2023/3/23 | 0 | -3000000 | 3000000 |  |  |  | V | Marketech International Corp. | PR Approved | PO Approved | tsmc F21P1 MIC 設備費用 Quotation clarifying Reorganize M4 WO (03/24/2023) | 100% by progress, T/T 45 days (after acceptance) | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | N |  |  |  |  | NA |  | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1366 | C | USCSB2201005A | -01 | WWT Platform | 2022/1/18 2022/2/2 | 2022/1/27 2022/2/8 | 3530956 | 689364 | 2841592 | V | V |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | Scope increase with tanks setup and freight | 95% by progress-T/T 30 Days-after acceptance; 5% by final acceptance-T/T 30 Days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y |  |  |  | N | 5005 | Y | 3354408.2 | 0.95 | 176547.8 | 0 | 176547.8 | 167720.41 | [6 empty] | 35000 |  | 35000 |  | 35000 | [11 empty] | 50000 |  | 250000 |  | 310900.4 |  | 895630 |  | 808623.07 |  | 542255.23 | 0 | 391999.5 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 167720.41
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1367 | C | USCSB2201006A | -01 | Modular Pipe Support Assembly Design | 2022/1/19 2022/2/25 | 2022/1/27 2022/2/25 | 17494.8 | 6394.8 | 11100 | V | V |  | V | The Blackfin Group | PR Approved | PO Approved | Scope increase because of TSMC design change | 25% at kickoff-net 30 days; 75% submission of draft report-net 30 days-after acceptance; T&M billed on a monthly basis (with supporting timesheets) | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT |  |  |  | Y |  |  | 17494.8 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 17494.8 | [21 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 1368 | C | USCSB2201007A | -04 | Chemical Mechanical Work #1 & #2 | 2022/1/20 2024/1/12 2024/2/6 2024/6/13 | 2022/1/25 2023/1/8 2024/1/15 2024/2/13 2024/6/13 | 94143616.47 | -1578248.72 | 95721865.19 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R4: As per engineer Johnny to cancel all Harder orders. R3: As per Johnny Wan,Due to Harder will leave this month on 2/23.So we need to remove the amount from Harder's project. R2: As per Engineer Johhny Wan to change the scope for Harder, but do not release until all contract is finalized | According to contract 95% by progress-T/T 30 days-after acceptance; 5% as-built drawing & punch list-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | CHEM |  |  |  |  | 5005 |  | 94143616.47 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 2094129 | 2704016.22 | 4040544.33 |  | 417465.07 | 0 | 1781642.51 |  | 4216462.61 |  | 3064264.82 |  | 3572903.14 |  | 5786891.65 |  | 8297322.7 |  | 11850710.2 |  | 4008521.26 |  | 1601905.82 |  | 4809804.55 |  | 6771650.72 | 0 | 3721362.34 |  | 2554883.36 |  | 3727093.67 |  | 3847670.9 | 0 | 0 | 0 |  | 301793 | 2844224.5 | 2000000 | 4206602.82 | 0 | 2220598.35 |  | 0 | 2535701.9 | 423796 |  | 741655.03 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 1369 | C | USCSB2201008A |  | tsmc F21P1 VOC 雜項工程 | 44587 | 44589 | 100000 | [6 empty] | Desiccant Technology Corporation | PR Approved | PO Approved |  | 100% upon receipt- T/T 30 days (after acceptance) | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y |  |  |  |  | NA |  | 100000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 100000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Material | USC21C008 | F21P1 CCTV & Security | 1370 | C | USCSB2201009A | -01 | Access Control/Wifi/CCTV in new Office/Warehouse | 44589 | 44602 | 92382.74 | 3946.98 | 88435.76 | V | V |  |  | Galaxy3 LLC | PR Approved | PO Approved | Some material/work was not necessary/changed, so the price has been reduced | According to Contract 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | N | [6 empty] | 92382.74 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 92382.74 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1371 | C | USCSB2201010A |  | WWT Housekeeping Pad | 44592 | 44601 | 1950339.22 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N | 5005 |  | 1950339.22 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 682618.73 | [6 empty] | 156027.14 |  |  |  | 103367.98 | 865622.23 |  |  | 26819.63 |  | 18144 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 97739.51 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | MIMO/Rigging | USC21C005 | F21P1 Chemical & WCCS package | 1372 | C | USCSB2202001A |  | Rigging for UPW & Chemical Package | 44594 | 44609 | 6153000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y |  |  |  |  | 5005 |  | 5845350 | 0.95 | 307650 | 0 | 307650 | 0 | [8 empty] | 360800 |  | 295200 |  | 105600 |  |  |  | 194400 |  |  |  | 1505200 |  | 1845900 |  |  |  | 615300 |  | 746825 |  | 176125 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 307650 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1373 | C | USCSB2202002A |  | WWT electrical work | 44599 | 44602 | 15871093.37 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT (Y) |  |  |  | Y | 5005 |  | 15734929.07 | 0.99142 | 136164.3 | 0 | 136164.3 | 0 | [7 empty] | 1509883 | 993313 |  | 795344 |  | 1704977 |  | 1025087 |  | 1042971 |  | 290381.16 |  | 360140 |  | 2055066.93 |  | 382982 |  | 293847.84 |  | 616577.75 |  | 549609.84 |  | 630151 | 0 |  |  | 1773188.26 |  | 381176 |  | 273929.94 | 0 | 337714.85 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 718588.5 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | Material | USC22C001 | F21 P1 Office and WH Security and CCTV | 1374 | C | USCSB2202003A | -01 | CCTV Warehouse Building | 44600 | 44602 | 344373.73 | -655626.27 | 1000000 |  |  |  | V | Galaxy3 LLC | PR Approved | PO Approved | Adjusting the amount due to the termination with Galaxy3. | 95% by progress-after acceptance-net 40 days; 5% after final acceptance-net 40 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | NA | [6 empty] | 344373.73 | 1 | 0 | 0 | 0 | 0 | [13 empty] | 104196.09 | [14 empty] | 0 | 240177.64 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | CCE | USC21C008 | F21P1 CCTV & Security | 1375 | C | USCSB2202006A | -01 | MIC TURNSTILES ON DUNLAP AVENUE | 44604 | 44609 | 0 | -12062.22 | 12062.22 | V | V |  |  | Commercial Comm and Electric Inc | PR Approved | PO Approved | 取消此單並用BPG，PM忘記在2月已有開給CCE，但SCOPE已變，所以交由BPG處理 | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N? | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1376 | C | USCSB2202007A |  | CS Tank changed order work | 44607 | 44615 | 236820.52 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved | 原PO:USC2109014A追加(CS Tank changed order work) | 5% upon submittal IFA's-Net 30 Days; 5% upon submittal IFC's-Net 30 Days; 35% upon submittal detail drawings approved by the client-Net 30 Days; 50% upon ready to ship status-Net 30 Days; 5% after delivered and acceptance-Net 30 Days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N |  |  | 189638.7 | 0.80077 | 47181.82 | 0 | 47181.82 | 37927.74 | [6 empty] | 133758.7 | [9 empty] | 55880 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 11841.026 |  |  |  | 11841.026 |  |  |  | 11841.026 |  | 9481.935 |  | - | 9481.935 | - | 9481.935 | 9481.935 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1377 | C | USCSB2202008A |  | FRP Tank Color work | 44607 | 44615 | 45125 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 25% upon all submittals approved-Net 30 Days; 20% upon receipt of materials-Net 30 Days; 50% upon ready to ship status; 5% upon commissioning & acceptance-within 60 days cap from shipping date or the product commission date, whichever is earlier-Net 30 Days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N |  |  | 45125 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 45125 | [17 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1378 | C | USCSB2202009A |  | FRP Tank Changed Order Work | 44607 | 44615 | 117484 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 25% upon all submittals approved-Net 30 Days; 20% upon receipt of materials-Net 30 Days; 50% upon ready to ship status-Net 30 Days; 5% upon commissioning and acceptance-within 60 days cap from shipping date or the product commission date, whichever is earlier-Net 30 Days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N |  |  |  | N |  |  | 0 | 0 | 117484 | 9500.4 | 107983.6 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1379 | C | USCSB2202011A |  | Modular pipe support assembly design (Tunnel section) | 44617 | 44623 | 31200 | [6 empty] | The Blackfin Group | PR Approved | PO Approved |  | 25% at kickoff-net 30 days-after acceptance; 75% submission of draft report-net 30 days-after acceptance; T&M billed on a monthly basis (with supporting timesheets) | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT |  |  |  | Y |  |  | 31200 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 7800 |  | 23400 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Material | USC22C001 | F21 P1 Office and WH Security and CCTV | 1380 | C | USCSB2203001A | -01 | Office Building Security & CCTV Electrical Work | 2022/3/1 2023/12/27 | 2022/3/3 2023/12/29 | 1367378.8 | -1422569.88 | 2789948.68 |  |  |  | V | Norstan Communications, Inc.dba Black Box Network Services | PR Approved | PO Approved | R1: As per Paul:the vendor has exited, and the account is settled. | 95% by progress-after acceptance-net 40 days; 5% after final acceptance-net 40 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | NA |  |  |  |  | 5005 |  | 1367378.8 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 811269.29 |  |  |  | 556109.51 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1381 | C | USCSB2203002A |  | CO2 Bottle Racks | 44621 | 44637 | 40194.97 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  | 20% upon received material and approved submittal-Net 45 days; 60% due on delivery with evidence-Net 45 days; 20% by received and after acceptance-Net 45 days | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | N | [6 empty] | 40194.96 | 1 | 0.01 | 0 | 0.01 | 0 | [7 empty] | 8038.99 |  |  | 24116.98 |  | 8038.99 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1382 | C | USCSB2203003A | -01 | VMB rack | 2022/3/1 2022/4/12 | 2022/3/17 2022/4/12 | 169587.62 | 16287.07 | 153300.55 |  |  |  |  | Pure Plastics, LLC | PR Approved | PO Approved | Rev01-Add additional material/ Labor | 20% upon received material and approved submittal-Net 45 days; 60% due on delivery with evidence-Net 45 days; 20% by received and after acceptance-Net 45 days | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | N | [6 empty] | 169587.61 | 1 | 0.01 | 0 | 0.01 | 0 | [7 empty] | 33917.52 |  |  | 101752.57 |  | 33917.52 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1383 | C | USCSB2203004A |  | FRP/PP Tank Change Order | 44621 | 44624 | 71730 | [6 empty] | An-Cor Industrial Plastics, Inc. | PR Approved | PO Approved | PO USC2110015A異動追加 | Based on T&C 25% upon all submittals approved-net 45 days; 20% upon the order-net 45 days; 50% upon fabrication completion of the tanks-net 45 days; 5% due within 60 days after delivery on site-net 45 days) | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N |  |  |  | N |  |  | 71730 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 14346 | 8966.25 | 8966.25 | [19 empty] | 0 |  |  |  |  | 0 |  |  |  | 32926.3 | 6525.2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 1384 | C | USCSB2203005A |  | 轉輪及煙囪預組裝費用 | 44624 | 44627 | 90000 | [6 empty] | Desiccant Technology Corporation | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | VOC(N) | [6 empty] | 85500 | 0.95 | 4500 | 0 | 4500 | 4500 | [26 empty] | 85500 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 4500
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1385 | C | USCSB2203006A |  | Tanks freight | 44625 | 44629 | 630878 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  | 100% by progress-Net 30 Days-After Acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N |  |  |  | N |  |  | 630878 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 630878 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1386 | C | USCSB2203007A |  | Tanks freight | 44625 | 44631 | 880212 | 103498 | 776714 | V |  | V |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Vendor recounts tank amounts for delivery | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N |  |  | 880212 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 845517 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 34695 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1387 | C | USCSB2203008A |  | Lorry Box | 44635 | 44637 | 39900 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  | 20% upon received material and approved submittal-Net 45 days; 60% due on delivery with evidence-Net 45 days; 20% by received and after acceptance-Net 45 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N |  |  |  | N |  |  | 39900 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 7980 |  | 31920 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1388 | C | USCSB2203009A |  | Outsourcing Service Superintendent Lead | 44635 | 44641 | 100800 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-after acceptance-T/T 30 days (paid as salary based on agreement) | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y |  |  |  | Y |  |  | 100800 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 9495.36 | 16800 |  | 16800 |  | 16800 |  | 16800 |  | 16800 |  | 7304.64 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 1389 | C | USCSB2203010A | -01 | Mechanical CDS Field Work | 2022/3/17 2023/3/23 | 2022/3/21 2023/3/24 | 0 | -1150000 | 1150000 |  |  |  | V | Marketech International Corp. | PR Approved | PO Approved | Reorganize M4 WO (03/24/2023) | 90% by progress, T/T 30 days. 10% after acceptance or 90 days after shipping which ever is early. | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | CHEM | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1390 | C | USCSB2203011A |  | Outsourcing Service General Worker | 44638 | 44641 | 22016 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 21764.47 | 0.98858 | 251.53 | 0 | 251.53 | 0 | [7 empty] | 1263.38 | 1633.97 | 1579.61 | 2539.64 | 14747.87 | [16 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 1391 | C | USCSB2203012A |  | AMC THC mechanic work | 44638 | 44641 | 547240 | [6 empty] | Southland Industries | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 Days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | VOC? | [6 empty] | 536295.54 | 0.98 | 10944.46 | 0 | 10944.46 | 10944.8 | [16 empty] | 9546 | [7 empty] | 7201 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 112991 | 0 | 0 | 0 | 24155 | 0 | 0 | 91331 | 47532 | 0 | 85867.3 |  | 89065.92 | 0 | 0 |  | 0 | [9 empty] | 68606.32 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0 | 10944.8
Base-Build | WWT | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1392 | C | USCSB2203013A |  | TSMC Trench Cover Plates | 44644 | 44645 | 48390 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | WWT (N) | [6 empty] | 48390 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 34790 |  |  |  | 13600 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1393 | C | USCSB2203014A |  | Mechanical | 44644 | 44650 | 0 | -47706 | 47706 | [5 empty] | PR Approved | PO Approved | 報價單調整，重新開請購單USCSB2204001A | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1394 | C | USCSB2203015A |  | TSMC Water Frontage Main & 43rd Avenue Sewer Line Extension | 2022/3/28 2022/4/9 | 44657 | 239659.84 | -37517 | 277176.84 |  | V |  |  | Degan Construction LLC | PR Approved | PO Approved | Rev01-removed item 1-Bond Payment. Bond is paid by AP note. 廠商修改報價單 | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 239659.84 | 1 | 0 | 0 | 0 | 0 | [7 empty] | 239659.84 | [20 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1395 | C | USCSB2204001A |  | Additional Submain 01 | 44652 | 44657 | 47674 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved | 原PO:USCSB2203014A異動 | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 47674 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 19162.62 |  |  |  | 28511.38 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1396 | C | USCSB2204002A |  | MICU人力支援 | 44652 | 44657 | 100000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 100000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1397 | C | USCSB2204003A |  | Activated Carbon | 44655 | 44662 | 987756 | [6 empty] | Calgon Carbon Corporation | PR Approved | PO Approved |  | 90% by shipment-net 60 days-after acceptance; 10% final acceptance-net 60 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 987756 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 661340.68 | [6 empty] | 239279.04 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 87136.28 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | CCE | USC21C013 | F21P1 AMC THC Monitoring System | 1398 | C | USCSB2204004A | -01 | AMC/THC electric and low voltage | 2022/4/6 2023/6/20 2024/9/25 | 2022/4/25 2023/6/26 2024/10/8 | 853014.9 | -14944.69 | 867959.59 |  |  |  | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | Per user's instruction to cancel CCE's AMC/THC scope | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [5 empty] | 5005 | Y | 853014.89 | 1 | 0.01 | 0 | 0.01 | 0 | [10 empty] | 137809 |  | 128830.61 | [5 empty] | 193245.91 | [5 empty] | 91192.7 |  |  |  | 0 |  | 176144.15 |  |  | 0 | [6 empty] | 125792.52 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 1399 | C | USCSB2204006A |  | Slurry system panels | 44665 | 44666 | 32427 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved | 原PO:USC2112003A異動為0 | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 32427 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 16213.5 | [10 empty] | 12970.8 |  |  | 3242.7 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 1400 | C | USCSB2204007A |  | Lorry building engineering services | 44669 | 44679 | 581700 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  | 100% Progress Payment-Net 30 days-After acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 581700 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 232680 |  |  |  | 122000 | [5 empty] | 164706 |  | 25000 |  |  |  | 18657 |  | 0 |  |  |  |  | 0 |  |  | 8000 |  | 9500 |  | 0 | 0 | 1157 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1401 | C | USCSB2204008A |  | MIC trailer office network | 44670 | 44672 | 46538.7 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 46538.7 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 46538.7 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 1402 | C | USCSB2204009A |  | TSMC F21 AZ Structure Design and PE Stamp | 44677 | 44679 | 200000 | [6 empty] | SYNERGY Engineering Consultants | PR Approved | PO Approved | Project Code changed from USC21C003 to USC22C006 (WO USCSB2205018A) | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y | [6 empty] | 95880 | 0.4794 | 104120 | 0 | 104120 | 0 | [28 empty] | 0 |  | 95880 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 87600 | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 1403 | C | USCSB2204010A |  | Project Management Software | 44677 | 44683 | 129799.8 | [6 empty] | Procore Technologies, Inc. | PR Approved | PO Approved |  | 100% due upon receipt-After acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 129799.8 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 129799.8 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC21C008 | F21P1 CCTV & Security | 1404 | C | USCSB2204011A |  | TSMC - CCTV Panel Builds | 44679 | 44680 | 50600 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 50600 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 40986 | 0 |  | 9614 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC21C007 | F21P1 VOC package （Installation ) | 1405 | C | USCSB2204012A |  | Change Order (for VOC Cable Tray) | 44679 | 44680 | 154671 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved | USCSB2109010A的Change order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 154671 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 146937.45 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 7733.55 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Labor | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 1406 | C | USCSB2204013A |  | TSMC Fab21 Project Phase 1 EDG Package | 44679 | 44680 | 473540 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 473540 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 355933.5 |  |  | 14944 |  |  | 21623.5 |  |  |  | 37681.5 |  |  |  | 12821 |  | 6721 |  |  |  | 0 |  | 5515.5 |  | 9460.5 | 0 | 8839.5 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1407 | C | USCSB2204014A | -02 | Tool Hook up Material (UPW & Chemical) | 2022/4/28 2022/6/14 2022/6/28 | 2022/5/2 2022/6/16 2022/7/2 | 3024944.33 | -148256.15 | 3173200.48 | V | V |  |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | Rev02-6 UPW Part No. Changed Rev01-12 UPW Items changed 原開單專案編號USC21C009 | 100% Arrival(delivery) after shipping-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 3024944.33 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 71135.03 |  | 251959.52 |  | 151600.16 | 307483.19 | 558308.8 | 460127.35 | 52.56 |  | 83940.3 |  | 1687.55 | 428643.66 |  |  | 307970.77 | 40789.6 | 0 | 0 | 0 | 15042.3 | 0 | 224734.52 | 0 | 31713.22 | 0 |  |  | 24252.39 | 0 | 0 |  | 0 | [7 empty] | 65503.41 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1408 | C | USCSB2204015A |  | Added Order (Nagano Adapter) | 44679 | 44683 | 2057.4 | [6 empty] | Ashcroft Inc. | PR Approved | PO Approved | USC2111018A的Change Order | 100% After shipment-Net 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 2057.4 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 2057.4 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 1409 | C | USCSB2205001A |  | TSMC UPW Common Supports for Area B of FAB Building | 44684 | 44685 | 3804475 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y | [6 empty] | 3690340.75 | 0.97 | 114134.25 | 0 | 114134.25 | 0 | [10 empty] | 45000 |  | 15000 |  | 10000 |  | 192000 |  | 446481 |  |  |  | 1630382.25 |  | 65275 |  | 206790 |  | 295950 |  | 253400 |  | 25975 | 0 |  |  | 333971.75 |  |  |  | 32272.5 | 0 | 52000 | 0 |  | 9453.76 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 76389.49 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C008 | F21P1 CCTV & Security | 1410 | C | USCSB2205002A |  | MIC Modular Office Fiber | 44685 | 44692 | 21616 | [6 empty] | Chunghwa Telecom Global, Inc | PR Approved | PO Approved |  | 100% after completion-after acceptance-net 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 21616 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 21616 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1411 | C | USCSB2205003A |  | CDS/WCCS/SDS/WWT/UPW/VOC/THC/Cold storage housekeeping pad & Dike | 44686 | 44706 | 842152.03 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 842152.03 | 1 | 0 | 0 | 0 | 0 | [19 empty] | 100078.6 |  |  | 292963.56 |  | 70353.34 |  | 44291.42 |  | 0 |  | 103859.68 |  | 33165.82 | 0 |  |  |  | 197439.61 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C006 | F21P1 Slurry package | 1412 | C | USCSB2205004A |  | 台積電(美國)F21P1防火填塞工程 | 44686 | 44692 | 1247244.64 | [6 empty] | Kinpo Co. | PR Approved | PO Approved |  | 30% Prepayment-Net 30 days; 28% by progress to Kinpo Taiwan-after acceptance-net 30 days; 42% by progress to Kinpo USA-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y | [6 empty] | 374173 | 0.3 | 873071.64 | 0 | 873071.64 | 62362.23 | [11 empty] | 374173 | [16 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 374173.39 |  |  |  | 436535.62 |  | 0 |  | - | 0 | - | 0 | 62362.23
Base-Build | Base-Build | Scaffolding | USC21C003 | F21P1 UPW | 1413 | C | USCSB2205005A |  | Scaffold for F21 MEP Scaffold work | 44686 | 44691 | 2000000 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 1999976 | 0.99999 | 24 | 0 | 24 | 0 | [13 empty] | 285972 |  | 1384578 | 85380 |  | 244046 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1414 | C | USCSB2205006A |  | SUNDT ICW Tank Piping | 44688 | 44693 | 242719 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [5 empty] | 5005 |  | 242719 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 181634 |  |  |  | 0 |  |  |  |  | 0 | 48932.66 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 12152.34 | [8 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 1415 | C | USCSB2205007A | -01 | Interior Building Scan and Model | 2022/5/9 2022/5/20 | 2022/5/11 2022/5/24 | 434113 | 76560 | 357553 | V | V |  |  | Zelus USA, LLC | PR Approved | PO Approved |  | 20% upfront; 80% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 434113 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 151939.55 | 72038.2 | [9 empty] | 78800.63 |  |  |  | 78801 | 26267 | 26266.62 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC22C001 | F21 P1 Office and WH Security and CCTV | 1416 | C | USCSB2205008A | -02 | CCTV Office Design and equipment | 2022/5/10 2023/8/15 | 2022/5/11 2023/8/15 2023/9/ 9 | 1670175 | -730573 | 2400748 | V |  |  | V | AEGISTEK SYSTEMS CO., LTD. | PR Approved | PO Approved | Swap the balance to Aegis USA because of 30% withholding tax issue | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | N | [6 empty] | 1670175 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 480150 |  | 144045 |  | 144045 |  | 72023 |  | 120036 |  |  |  | 504140 |  |  |  | 108912 |  | 0 | 96824 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Site Expense | USC21C003 | F21P1 UPW | 1417 | C | USCSB2205009A |  | Modular Office Miscellaneous Works | 44691 | 44692 | 3825 | [6 empty] | Design Modulars Inc. | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 3825 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 3825 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1418 | C | USCSB2205010A |  | Modular Pipe Support Assembly Design change order | 44691 | x | 0 | -11000 | 11000 | [5 empty] | PR Approved | PO Approved | 因Item Description錯誤且無法異動修改，已請專案刪除結案(USCSB2205014A取代) | 取消PR | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1419 | C | USCSB2205011A |  | Outsourcing Foreman | 44692 | 44692 | 1089600 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1089600 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 28971.72 | 57454.65 |  | 157433.05 | 85602.27 | 24722.38 | 2912 | 138322.64 |  | 26247.22 | 103463 |  |  |  | 294956.76 |  | 169514.31 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 1420 | C | USCSB2205012A |  | General Laborer and Housekeeping Service | 44692 | 44697 | 300000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | Y | [6 empty] | 255464 | 0.85155 | 44536 | 0 | 44536 | 0 | [8 empty] | 1800 | 1755 |  | 24915 | 25455 | 24832.5 | 52050 | 27419 | 29130 | 68107.5 | [10 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1421 | C | USCSB2205014A |  | Modular Pipe Support Assembly Design change order | 44694 | 44697 | 11000 | [6 empty] | The Blackfin Group | PR Approved | PO Approved |  | 100% by progress-after acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 11000 | 1 | 0 | 0 | 0 | 0 | [8 empty] | 11000 | [19 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC22C001 | F21 P1 Office and WH Security and CCTV | 1422 | C | USCSB2205015A |  | F21 Warehouse CCTV equipment | 44694 | 44697 | 207173 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [5 empty] | 5000 |  | 189878 | 0.91652 | 17295 | 0 | 17295 | 0 | [14 empty] | 68368 |  |  |  | 55935 |  |  |  | 31077 | [5 empty] | 0 |  | 18784 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 15714 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Southland | USC21C005 | F21P1 Chemical & WCCS package | 1423 | C | USCSB2205016A |  | WCCS additional material for LB1 & LB2 | 44694 | 44697 | 37158.01 | [6 empty] | Southland Industries | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 37158 | 1 | 0.01 | 0 | 0.01 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 37158 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EUV Overhead Crane | Labor | USC22C006 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1424 | C | USCSB2205017A |  | TSMC EUV OVERHEAD CRANES in Area A of FAB Building | 44694 | 44697 | 2500000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 2500000 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 404000 | [5 empty] | 276560 |  | 122250 |  | 134387.5 |  | 153525 |  | 61250 |  | 230080 |  | 381577.5 |  | 420935 |  | 65435 | 0 | 125000 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 125000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC22C006 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1425 | C | USCSB2205018A |  | TSMC F21 AZ Structure Design and PE Stamp | 44695 | 44696 | 200000 | [6 empty] | SYNERGY Engineering Consultants | PR Approved | PO Approved | Project Code changed from USC21C003 to USC22C006 (Original WO USCSB2204009A) | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | N | [6 empty] | 154000 | 0.77 | 46000 | 0 | 46000 | 0 | [8 empty] | 104000 | [7 empty] | 50000 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1426 | C | USCSB2205020A |  | WWT Hopper and Piping Header | 44697 | 44700 | 960814.29 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  | 95% by shipment-Net 30 days-after acceptance, 5% after function tested-Net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 960814.29 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 713320 | [12 empty] | 24000 | 0 | 59994.29 |  |  | 163500 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | LPS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1427 | C | USCSB2205021A |  | Simona PVDF material for WWT | 44698 | 44706 | 1337939.49 | [6 empty] | Lasco Process Systems, LLC. | PR Approved | PO Approved | USCSB2109003A change order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1321837.89 | 0.98797 | 16101.6 | 0 | 16101.6 | 0 | [12 empty] | 267587.9 |  |  |  |  | 869338.1 | 177296.59 |  |  | 7615.3 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Greenberry | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1428 | C | USCSB2205022A | -01 | Tunnel Common Supports | 2022/5/18 2022/6/25 | 2022/5/24 2022/6/27 | 3200000 | 1600000 | 1600000 | V | V | V |  | Greenberry Industrial | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y |  |  |  |  | 5005 |  | 3040000 | 0.95 | 160000 | 0 | 160000 | 152000 | [20 empty] | 2163771.28 |  |  | 876228.72 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 152000
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1429 | C | USCSB2205023A |  | CDS T-box | 44699 | 44704 | 1442704.28 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  | 20% upon received material and approved submittal-Net 45 days; 60% due on delivery with evidence-net 45 days; 20% by received and after acceptance-net 45 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 1442704.28 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 288540.86 |  |  |  | 66179.35 |  | 181354.29 |  | 182599.74 |  | 157941.7 |  | 153670.67 |  | 147796.07 |  | 0 |  |  |  |  | 0 | [5 empty] | 61871.76 | 0 | 0 | 202749.84 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1430 | C | USCSB2205024A | -01 | WWT FRP tanks | 2022/5/19 2022/6/15 | 2022/5/23 2022/6/16 | 1633000 | -437000 | 2070000 |  |  |  |  | Shanghai Mega Union Environmental Technology Co., LTD | PR Approved | PO Approved | 取消7個桶槽 | 25% Prepayment-T/T 30 days; 70% by shipment-after acceptance-t/t 30 days; 5% after final acceptance-t/t 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1551350 | 0.95 | 81650 | 0 | 81650 | 77567.5 | [9 empty] | 408250 | [6 empty] | 387021 |  |  | 756079 | [8 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 77567.5
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1431 | C | USCSB2205025A |  | Outsourcing (area superintendent) | 44701 | 44704 | 192000 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 192000 | 1 | 0 | 0 | 0 | 0 | [10 empty] | 14879.91 |  | 28190.4 |  | 31200 |  | 28482.97 |  | 34956.8 |  | 38395.2 |  |  | 15894.72 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 1432 | C | USCSB2205026A | -01 | CDS Change Order for UPW at Lorry | 2022/5/22 2024/6/13 | 2022/5/24 2024/6/13 | 51232.6 | -204930.4 | 256163 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny to cancel all Harder orders. R0: USCSB2201007A的Change Order | 95% by progress-T/T 30 days-after acceptance; 5% as-built drawing & punch list-T/T 30 days-after acceptance | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 51232.6 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 51232.6 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1433 | C | USCSB2205027A | -01 | SYNERGY/MICU tsmc F21 Arizona On-site Engineer | 2022/5/26 2024/5/7 | 2022/5/27 2024/5/7 | 91640 | -8360 | 100000 | V |  |  |  | SYNERGY Engineering Consultants | PR Approved | PO Approved | R1: As per SYNERGY:Ting Sheng Wang to closed out the PR | 100% by progress(after design documents hand over)-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 91640 | 1 | 0 | 1124 | -1124 | 0 | [24 empty] | 50000 |  |  |  | 0 |  | 41640 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | FMCS | Material | USC22C007 | TSMC F21 FMCS Installation | 1434 | C | USCSB2205028A |  | TSMC F21 FMCS Installation | 44707 | 44708 | 970000 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  | 90% by progress-after acceptance-net 30 days; 10% after final acceptance-net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [5 empty] | 5005 |  | 952462.29 | 0.98192 | 17537.71 | 0 | 17537.71 | 0 | [19 empty] | 137016.94 |  |  |  | 55484.1 | 62126.6 |  | 81800.85 |  | 0 |  |  |  | 293817.5 | 0 | 107801.4 |  |  |  | 88836 |  | 0 | 0 | 39369.8 | 0 |  | 0 | 0 | 0 | 0 | 0 | 32363.1 |  | 0 | 0 | 27826 |  | 0 |  | 26020 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1435 | C | USCSB2205029A | -01 | Hard support for electrical scope | 2022/5/27 2022/6/4 | 2022/5/31 2022/6/13 | 220448.25 | -319320.99 | 539769.24 | V |  | V |  | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A-1的Change Order; 數量從555減少到225 | 95% by progress-net 30 days-after acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Yi-Hsin Lee | Yi En Wong | [7 empty] | 220447.85 | 1 | 0.4 | 0 | 0.4 | 0 | [14 empty] | 19595 |  | 22534.71 |  | 19595.4 |  | 85239.99 |  |  |  | 24494.25 |  |  |  | 0 |  | 24494.25 |  |  | 0 | [6 empty] | 0 | 0 | 12737.01 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 11757.24 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 1436 | C | USCSB2205030A |  | Lorry Building Rack Design | 44709 | 44712 | 30450 | [6 empty] | The Blackfin Group | PR Approved | PO Approved |  | 25% at kickoff-net 30 days-after acceptance; 75% after acceptance of submission-net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 30450 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 7612.5 |  |  | 22837.5 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1437 | C | USCSB2206001A |  | MICU Glendale Warehouse Project Management Service | 44714 | 44718 | 60000 | [6 empty] | Pivotal Project Management LLC | PR Approved | PO Approved |  | 100%-by progress-net 30 days (There has been made an additional $10,000 deposit) | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 50000 | 0.83333 | 10000 | 0 | 10000 | 0 | [9 empty] | 10000 |  | 10000 |  |  | 10000 |  | 10000 |  | 10000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1438 | C | USCSB2206002A |  | TOC Analyzer and portable | 44714 | 44719 | 721645 | [6 empty] | Veolia WTS Analytical Instruments, Inc. | PR Approved | PO Approved |  | 100% by shipment-net 30 days-after accpetance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | Y | [6 empty] | 707497.95 | 0.9804 | 14147.05 | 0 | 14147.05 | 0 | [16 empty] | 294406.35 |  |  |  | 377349.6 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 13844 | 0 | 14986 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 6912 | - | 0 | 14147.05 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1439 | C | USCSB2206003A |  | GF Chlorine Instrument | 44715 | 44719 | 5188.48 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  | Arrival (delivery) 100%-net 30 days-after acceptance/shipping | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 5188.48 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 5188.48 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Labor | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 1440 | C | USCSB2206005A |  | TSMC F21P1 EDG Package Additional City Requirements | 44715 | 44718 | 16600 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 16600 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 6721 |  | 5515.5 |  |  |  |  | 0 | 621 |  |  | 3742.5 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Equipment | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 1441 | C | USCSB2206006A | -01 | TSMC Fuel Oil System Long Lead Items | 2022/6/3 2022/9/30 | 2022/6/22 2022/10/10 | 0 | -857319 | 857319 |  | V |  |  | W.D. Manor Mechanical Contractors, Inc. | PR Approved | PO Approved | We send PO to WD Manor in the beginning for EDG mechanical work. However, their delivery date cannot meet our requirement. After meeting with Fu Energy, we decide to transfer the whole scope to Sundt. | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1442 | C | USCSB2206007A |  | DOCK COORDINATOR | 44715 | 44725 | 85200 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 85200 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 12170.82 |  | 14200 |  | 14200 |  | 12170.82 |  | 16330 |  | 15265 |  | 863.36 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 1443 | C | USCSB2206008A |  | Insulation spec change | 44720 | 44726 | 63250 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | USCSB2108001A的Change Order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 0 | 0 | 63250 | 0 | 63250 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1444 | C | USCSB2206009A |  | Commissioning Chemicals | 44720 | 44727 | 571949.64 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | Y | [6 empty] | 571786.07 | 0.99971 | 163.57 | 0 | 163.57 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 7284.8 |  |  | 5309.2 | 5595.2 | 0 | 11065.6 | 0 | 5210.4 | 53158.25 | 5733 | 60838.09 | 103206.08 | 0 | 116016.46 |  | 22129.28 | 33109.9 | 89273.84 |  | 13804.7 |  | 17765.04 |  | 8700 | [5 empty] | 10425.6 |  | 3160.63 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1445 | C | USCSB2206011A |  | Safety Coordinators and Site Cleanup | 44721 | 44725 | 220000 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 219648.49 | 0.9984 | 351.51 | 0 | 351.51 | 0 | [12 empty] | 66197.89 | 14554.85 | 24156.02 | 4816 | 5474 | 6048 | 7196 | [9 empty] | 0 |  | 83397.4 |  |  | 0 | [6 empty] | 0 | 0 | 7808.33 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1446 | C | USCSB2206012A |  | X1 cable tray hanger re-install | 44722 | 44725 | 37047.6 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 37047.6 | 1 | 0 | 294440.45 | -294440.45 | 0 | [12 empty] | 37047.6 | [15 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1447 | C | USCSB2206014A |  | UPW tray model | 44723 | 44739 | 155528.35 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 155528.35 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 49146.96 |  | 49146.96 |  | 49146.96 |  | 8087.47 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Oil drain pipe work | Labor | USC22C009 | F21P1 230kV MTR Oil and Drain Pipe work | 1448 | C | USCSB2206015A |  | F21P1 230kV MTR waste oil drain pipe | 44723 | 44725 | 223292 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 100% by progress-t/t 30 days-after acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 212039.37 | 0.94961 | 11252.63 | 0 | 11252.63 | 10601.9685 | [24 empty] | 85942 |  |  |  | 47210.37 |  |  |  |  | 0 | [6 empty] | 78887 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 10601.9685
Base-Build | WWT | LPS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1449 | C | USCSB2206016A |  | WWT add BOM on March | 44725 | 44727 | 1756177.47 | [6 empty] | Lasco Process Systems, LLC. | PR Approved | PO Approved | USCSB2109003A Change order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [5 empty] | 5005 |  | 1352739.95 | 0.77028 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 351235.49 |  | 306760.62 |  | 688372.16 | 6371.68 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1450 | C | USCSB2206017A |  | F21 Hook up PFA 管材 | 44726 | 44736 | 2592117 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  | 100% by progress-T/T 30 Dyas-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 0 | 0 | 2592117 | 0 | 2592117 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1451 | C | USCSB2206018A |  | Pallet Storage System | 44727 | 44729 | 818469.26 | [6 empty] | Toyotalift of Arizona, Inc. | PR Approved | PO Approved |  | 30% upfront on material cost; Remaining 40% by shipment-Net 30 days-after acceptance; Remaining balance due-net 30 days-after final acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [5 empty] | 5005 |  | 803346.37 | 0.98152 | 15122.89 | 0 | 15122.89 | 0 | [10 empty] | 211524.98 | [5 empty] | 327387.6 | 264433.79 | [10 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1452 | C | USCSB2206019A |  | PP materials d225 and d180 | 44728 | 44733 | 1909676.1 | 329504.4 | 1580171.7 | V |  |  |  | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved | 實際需求數量變更, 貿易條件從EXW改FCA | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1909676.1 | 1 | 0 | 0 | 0 | 0 | [15 empty] | 1909676.1 | [12 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | USC21C008 | F21P1 CCTV & Security | 1453 | C | USCSB2206020A |  | GOWN Power Panel | 44729 | 44740 | 29328 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 29328 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 23755.68 | 0 |  | 5572.32 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 1454 | C | USCSB2206021A |  | F21P1 Laboratory scope | 44731 | 44733 | 831105 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 0 | 0 | 831105 | 0 | 831105 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | 5G | Material | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 1455 | C | USCSB2206022A |  | F21 P1 LSC CMS and DPM 5G System | 44735 | 44743 | 5913533 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 5913533 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 2736927 |  |  | 0 | [5 empty] | 3176606 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 1456 | C | USCSB2206023A |  | F21 Raised Floor Pipe engineering | 44735 | 44740 | 9476 | [6 empty] | SDB, Inc. dba SDB Contracting Services | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Chih-Chien Hung | Yi En Wong | [7 empty] | 9476 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 9476 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1457 | C | USCSB2206024A |  | FRP tank Painting | 44741 | 44749 | 72000 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Chengtung Liu | Yi En Wong | Y | [6 empty] | 72000 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 72000 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | LPS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1458 | C | USCSB2206025A |  | WWT Pipe Rack | 44742 | 44743 | 130410.27 | [6 empty] | Lasco Process Systems, LLC. | PR Approved | PO Approved | USCSB2111003A-Rev01 Change order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 130410.27 | 1 | 0 | 0 | 0 | 0 | [15 empty] | 130410.27 | [12 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1459 | C | USCSB2206026A |  | 3rd party QC for CS tanks | 44742 | 44747 | 23901 | [6 empty] | Weld Spec, Inc. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 23764.38 | 0.99428 | 136.62 | 0 | 136.62 | 0 | [13 empty] | 956.5 | 6676.25 |  | 6003.25 |  | 5961.38 |  | 4167 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1460 | C | USCSB2207001A | -01 | Big AZ Tent | 44744 | 44753 | 87671.96 | 3731.96 | 83940 |  | V |  |  | Barton Dynamics, LLC dba Big AZ Tents & Events | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 87671.96 | 1 | 0 | 0 | 0 | 0 | [12 empty] | 87671.96 | [7 empty] | 0 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | MIMO/Rigging | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1461 | C | USCSB2207002A |  | Rigging at new Warehouse | 44744 | 44750 | 100000 | [6 empty] | MEI Rigging & Crating, LLC | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 41132.5 | 0.41132 | 58867.5 | 0 | 58867.5 | 0 | [14 empty] | 15040 |  | 22560 |  | 3532.5 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1462 | C | USCSB2207003A |  | Tool HK Chemical Material PFA Fitting (Semitorr) | 44744 | 44748 | 115889.9 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  | 100% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 115517.9 | 0.99679 | 372 | 0 | 372 | 0 | [25 empty] | 12089.25 |  |  | 0 |  | 72144.35 |  | 11471.65 | 0 |  | 104.85 | 19707.8 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 372 | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1463 | C | USCSB2207004A |  | Tool HK Chemical Material PFA Fitting (Pillar) | 44748 | 44748 | 184930.38 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  | 100% after final acceptance-Net 60 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 184930.38 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 73699.14 | 81308.04 |  |  | 0 | [5 empty] | 29923.2 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1464 | C | USCSB2207005A |  | Tool HK Chemical Material PFA Fitting (Valin) | 44748 | 44754 | 12724.25 | [6 empty] | Valin Corporation | PR Approved | PO Approved |  | 100% after final acceptance-Net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 12717.3 | 0.99945 | 6.95 | 0 | 6.95 | 0 | [14 empty] | 200.26 | [10 empty] | 4637.64 | 2859.95 |  | 0 |  | 5019.45 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 1465 | C | USCSB2207006A |  | Engineering Design Assistance and Engineer of Record Services | 44748 | 44750 | 557900 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 557900 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 200000 |  | 150000 |  |  |  | 139475 |  | 25000 |  | 25000 |  | 6300 |  | 0 |  |  |  |  | 0 | [5 empty] | 12125 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Greenberry | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1466 | C | USCSB2207007A |  | WWT & TMAH pipe rack | 44748 | 44753 | 7994980 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  | 95% by progress-net 30 days-after acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 7814921.78 | 0.97748 | 180058.22 | 0 | 180058.22 | 156298.4356 | [26 empty] | 402071.73 | 1656165.87 | 2536539.27 |  | 1575043.82 |  |  | 0 | 83847.66 |  | 477611.92 |  | 158546.5 |  | 0 | 0 | 0 | 0 |  | 796552.81 | 0 | 0 | 0 | 0 |  |  | 0 | 128542.2 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 156298.4356
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 1467 | C | USCSB2207008A |  | Lorry Common Rack | 44748 | 44762 | 454451 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | Y | [6 empty] | 454451 | 1 | 0 | 0 | 0 | 22722.55 | [16 empty] | 23500 |  | 46725.5 |  | 159725.5 |  | 201774.45 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 22725.55 |  |  |  |  | 0 |  | - | 0 | - | 0 | 22722.55
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1468 | C | USCSB2207009A |  | Kelly outsourcing engineering | 44749 | 44750 | 660920 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  | 100% by progress-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 659932.88 | 0.99851 | 987.12 | 0 | 987.12 | 0 | [14 empty] | 53797.82 |  | 90770.69 |  | 145762.52 |  | 202214.57 |  |  | 167387.28 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C006 | F21P1 Slurry package | 1469 | C | USCSB2207010A |  | Engineering Design Assistance and Engineer of Record Services | 44749 | 44750 | 860400 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Chia-Yi Chang | Yi En Wong | [7 empty] | 848120 | 0.98573 | 12280 | 0 | 12280 | 0 | [14 empty] | 129060 |  | 250000 |  | 200000 |  | 229060 |  | 40000 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1470 | C | USCSB2207011A |  | d225 drain pipe materials | 44750 | 44753 | 670653 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 670653 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 670653 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | VOC | Labor | USC21C007 | F21P1 VOC package （Installation ) | 1471 | C | USCSB2207012A |  | VOC Cable Tray Change Order #2 | 44751 | 44755 | 32497.3 | [6 empty] | Spectra Electrical Services, Inc. | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 32497.3 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 32497.3 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1472 | C | USCSB2207013A | -02 | Internet for Glendale warehouse | 2022/7/9 2022/7/30 2022/11/2 | 2022/7/19 2022/8/5 2022/11/3 | 0 | -59394.6 | 59394.6 |  | V |  |  | Level 3 Communications, LLC, A Lumen Technologies Company | PR Approved | PO Approved | Rev01-add the router to the current order Rev02-change to another company (Transpak) | 100% by progress/distributed monthly-net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1473 | C | USCSB2207014A | -01 | Electrical Superintendent | 2022/7/12 2022/7/22 | 2022/7/18 2022/7/24 | 0 | -99600 | 99600 |  | V |  |  | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 取消 | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | Exterior Pad | Material | USC22C011 | WRC Exterior Pads - NH3 and Diesel System | 1474 | C | USCSB2207015A |  | WRC Exterior Pads - NH3 and Diesel System | 44755 | 44761 | 2223500 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 2112178 | 0.94993 | 111322 | 0 | 111322 | 0 | [22 empty] | 79500 |  | 2032678 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Equipment | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 1475 | C | USCSB2207016A |  | F21 Electrical Generator installation | 44757 | 44761 | 5400000 | [6 empty] | Delta Diversified Enterprises, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [5 empty] | 5005 |  | 5105559.55 | 0.94547 | 294440.45 | 0 | 294440.45 | 0 | [18 empty] | 327278 |  | 508107 |  | 719764 |  | 462251 |  | 686917.45 |  | 0 | 1100327.05 |  | 604485.95 | 696429.1 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MIMO/Rigging | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1476 | C | USCSB2207017A |  | WWT rigging and equipment move in | 44758 | 44761 | 1890000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 1890000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 378000 |  | 378000 |  | 378000 |  | 378000 |  | 283500 |  | 94500 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | MIMO/Rigging | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1477 | C | USCSB2207018A |  | WWT rigging and equipment move in | 44761 | 44762 | 360000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | Related to USCSB2207017A (Seperated into these 2 POs) | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | N | [6 empty] | 360000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 72000 |  | 72000 |  | 72000 |  | 72000 |  | 54000 |  | 18000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | USC21C008 | F21P1 CCTV & Security | 1478 | C | USCSB2207019A |  | TSMC Warehouse Panels | 44763 | 44768 | 13536 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 13536 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 12182.4 |  |  |  |  | 0 |  |  | 1353.6 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Trident | USC21C014 | F21P1 WH2SO4 | 1479 | C | USCSB2207020A | -01 | W-H2SO4 Mechanical Work | 2022/7/23 2022/11/4 | 2022/7/26 2022/11/9 | 1375375 | -44703 | 1420078 |  | V |  |  | Trident Mechanical Services | PR Approved | PO Approved | Trident cannot catch up PFA lead time, so we use our own-purchased PFA (we prepruchase more in M4 order) and cancelled PFA in Trident's double containment | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong | [11 empty] | 1375375 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 167139 | [9 empty] | 587927 |  | 227074 |  | 225416 |  | 153511 |  |  | 14308 | [12 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1480 | C | USCSB2207021A |  | Signal amplify equipment | 44765 | 44768 | 10117.89 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  | 100% by received-Net 30 days-after acceptance | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 10117.89 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 10117.89 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1481 | C | USCSB2207022A |  | Water Systems Superintendent _Rod Copas | 44768 | 44776 | 99600 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After Acceptanc | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 92742.52 | 0.93115 | 6857.48 | 441755.01 | -434897.53 | 0 | [16 empty] | 12991.16 |  | 18855.02 |  | 17845 |  | 17015 |  | 18504.02 |  | 7532.32 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1482 | C | USCSB2207023A |  | Internet for Glendale warehouse | 7/27/2022 10/11/2024 | 8/4/2022 10/11/2024 | 109255.42 | -13594.29 | 122849.71 |  |  |  |  | Galaxy3 LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 109255.42 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 71102.52 |  |  |  | 38152.9 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1483 | C | USCSB2207024A |  | CCE Conduit, Cable Tray and Cable label | 44772 | 44776 | 68000 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | USCSB2202002A Change Order | 95% by progress-T/T 30 days-after acceptance, 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 68000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 68000 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1484 | C | USCSB2208001A |  | Transpak Offsite warehouse (storage & handling) | 44776 | 44782 | 200000 | [6 empty] | Transpak, Inc. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 0 | 0 | 200000 | 0 | 200000 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1485 | C | USCSB2208002A |  | Signal Booster System installation | 44777 | 44778 | 20000 | [6 empty] | Galaxy3 LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance, 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 20000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 20000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1486 | C | USCSB2208004A |  | PFA Tubing | 44783 | 44785 | 18706.07 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved | USCSB2205023A change order | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 18706.07 | 1 | 0 | 0 | 0 | 0 | [14 empty] | 18706.07 | [13 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1487 | C | USCSB2208005A |  | Harrington Ladder Standoff on the Tank | 44784 | 44785 | 5760 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | USC2110005A Change order | 95% by progress-T/T 30 days-After acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Shengxu Yan | Yi En Wong | [7 empty] | 5760 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 5760 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C005 | F21P1 Chemical & WCCS package | 1488 | C | USCSB2208007A |  | Chemical Superintendent Outsourcing | 44784 | 44785 | 100800 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | Y | [6 empty] | 70047.84 | 0.69492 | 30752.16 | 0 | 30752.16 | 0 | [16 empty] | 8033.76 |  | 16126.56 |  | 17808 |  | 15960 |  | 12119.52 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Equipment | USC22C014 | F21P1 AMHS Power Panel | 1489 | C | USCSB2208008A | -01 | AMHS Typical Panel | 44786 | 44816 | 237481 | -1345729 | 1583210 |  |  |  | V | Main Electric Supply Co, LLC | PR Approved | PO Approved | cancelled the PO because of lead time issue | 15% Prepayment; 85% by progress-Net 45 days-after acceptance | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 237481 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 237481 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1490 | C | USCSB2208009A |  | Drill and Epoxy Rebar Hooks for Curb Based on Detail Provided | 44790 | 44795 | 169260 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved | USCSB2111008A-01 change order | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Chiahsuan Ho | Yi En Wong | [7 empty] | 130732.31 | 0.77238 | 38527.69 | 0 | 38527.69 | 0 | [19 empty] | 15840 |  |  | 114892.31 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1491 | C | USCSB2208010A |  | UPW Prominent H2O2 Analyzer | 44793 | 44799 | 12903.68 | [6 empty] | Precision Integrated Systems, LLC | PR Approved | PO Approved | related to USC2111034A | 100% by received-net 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 12903.68 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 12903.68 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1492 | C | USCSB2208011A |  | UPW MABAT SDI Filter Paper | 44796 | 44803 | 1136 | [6 empty] | MABAT Chemical systems Ltd | PR Approved | PO Approved | related to USC2112005A (original forgets to purchase filter paper) | 100% before shipping | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 1136 | 1 | 0 | 0 | 0 | 0 | [17 empty] | 1136 | [10 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1493 | C | USCSB2208012A |  | MICU Glendale Warehouse Project Management Service (Extension) | 44798 | 44803 | 60000 | [6 empty] | Pivotal Project Management LLC | PR Approved | PO Approved | USCSB2206001A extension order | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Hsin-Lin Lu | Yi En Wong | [7 empty] | 30000 | 0.5 | 30000 | 0 | 30000 | 0 | [20 empty] | 10000 |  | 10000 |  | 10000 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1494 | C | USCSB2208013A |  | TSMC Phoenix Fab Advantech Design Services | 44799 | 44805 | 49350 | [6 empty] | Advantech Facility Design Inc. | PR Approved | PO Approved | Previously paid by APN, but rejected by accounting, so issue PO | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 49350 | 1 | 0 | 0 | 0 | 0 | [16 empty] | 49350 | [11 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1495 | C | USCSB2208014A |  | ABB 150A Circuit Breakers | 44799 | 44804 | 11000 | [6 empty] | Kelso-Burnett Co. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 11000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 8910 |  |  |  |  | 0 | 2090 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1496 | C | USCSB2208015A | -02 | UPW 500 MCM Cable | 2022/8/26 2022/12/09 2022/12/20 | 2022/8/31 2022/12/14 2022/12/21 | 190627.32 | -3038.52 | 193665.84 |  |  | V |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Quantities change/need to be added 100 pcs per first three items | 100% by shipment-after acceptance-net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 190626.69 | 1 | 0.63 | 0 | 0.63 | 0 | [23 empty] | 190626.69 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | 5G | CCE | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 1497 | C | USCSB2208016A |  | F21P1 PDS Cabling and equipment installation | 8/27/2022 9/25/2024 | 9/12/2022 10/8/2024 | 304827.48 | -569.72 | 305397.2 |  |  |  |  | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 95% progress payment-Net 30 days-after acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Mirielli Terres | Yi En Wong | [6 empty] | Y | 304827.48 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 76349.3 |  | 114069.02 |  | 45809.58 |  | 32649.72 |  | 35949.86 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | - |  | -
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1498 | C | USCSB2208018A | -01 | Horiba Conductivity/Resistivity Meter | 44804 | 44810 | 0 | -53532 | 53532 | V |  |  |  | HORIBA Taiwan, Inc. | PR Approved | PO Approved | JPY 6,691,500; ERP不能直接更改幣值，因需重開而異動為0 | 100% by shipment-after acceptance-net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1499 | C | USCSB2209001A |  | Tunnel GF fix point fitting | 44806 | 44816 | 13115.52 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 13115.52 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 13115.52 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1500 | C | USCSB2209003A |  | WRC Chemical Room Chemical Resistant Coating | 44806 | x | 0 | -300000 | 300000 | [5 empty] | PR Approved | PO Approved | Scope changed |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1501 | C | USCSB2209004A |  | PSS-WWT mechanic work scope cut from LPS – Part#1 | 44812 | 44816 | 12000000 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Replace LPS USCSB2109003A-02 deducted Scope | 95% by progress-Net 45 days-after acceptance; 5% after final acceptance-Net 45 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 12000000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 2916925.18 |  | 3179605.05 |  | 4765534.89 |  | 1137934.88 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1502 | C | USCSB2209005A |  | MRT Design-Additional Services amendment | 44813 | 44816 | 30000 | [6 empty] | MRT DESIGN LLC | PR Approved | PO Approved | 原都以APN請款，因財務要求而轉開PO | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 27500 | 0.91667 | 2500 | 0 | 2500 | 0 | [16 empty] | 15000 |  | 12500 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1503 | C | USCSB2209006A |  | MMF media procurement | 44813 | 44816 | 45237.65 | [6 empty] | Northern Filter Media, Inc. | PR Approved | PO Approved |  | 100% by progress-net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 44665.25 | 0.98735 | 572.4 | 0 | 572.4 | 0 | [20 empty] | 3538.35 |  |  | 41126.9 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 1504 | C | USCSB2209007A |  | Lorry Building Module Rack - change order | 44813 | 44816 | 3000 | [6 empty] | The Blackfin Group | PR Approved | PO Approved | USCSB2205030A change order | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 3000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 3000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1505 | C | USCSB2209008A |  | UPW Resin temporary storage | 44814 | 44831 | 0 | [7 empty] | PR Approved | PO Approved | Returned, paid storage fee for Hankyu Hanshin (Membrane storage) |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Equipment | USC21C007 | F21P1 VOC package （Installation ) | 1506 | C | USCSB2209009A |  | MIC-TSMC-F21P1- VOC DCS SCADA | 44814 | 44818 | 130000 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved |  | 15% Prepayment; 35% by progress-Net 30 days-after acceptance (FAT); 40% by progress-Net 30 days-after acceptance (SAT); 10% After final acceptance-Net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 117000 | 0.9 | 13000 | 0 | 13000 | 52000 | [20 empty] | 19500 | [7 empty] | 0 |  |  |  |  | 0 |  |  | 45500 |  |  |  | 0 | 0 | 0 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 13000 |  | 39000 | 39000 | - |  | - |  | 0 | 13000
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1507 | C | USCSB2209011A |  | Horiba Conductivity/Resistivity Meter | 44818 | 44819 | 48140 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved | 此張單因貨幣關係重開以美金計價(原單為USCSB2208018A以日幣計價) | 100% after goods arrival date-T/T 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 48140 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 38470.45 |  | 9669.55 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1508 | C | USCSB2209012A |  | WWT tank welding | 44819 | 44825 | 64660.89 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  | 100% upon completion of work-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 61427.85 | 0.95 | 3233.04 | 0 | 3233.04 | 0 | [20 empty] | 34427.85 |  | 27000 | [5 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | Labor | USC21C008 | F21P1 CCTV & Security | 1509 | C | USCSB2209013A |  | TSMC Dunlap Office turnstile and metal detector installation | 9/15/2022 9/14/2024 | 9/20/2022 9/26/2024 | 22499.56 | -0.44 | 22500 |  |  |  |  | BPG Technologies, LLC | PR Approved | PO Approved | 替代CCE USCSB2202006A-1 R1: As per PM Paul and Debby to close out this PO. | 95% by progress-T/T 30 days-After Acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Eric Lin | Yi En Wong | [7 empty] | 22499.56 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 22499.56 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | - |  | -
Non-TSMC | EDG | Equipment | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 1510 | C | USCSB2209014A |  | SUNDT-Generator Fuel and Exhaust Piping | 44819 | 44847 | 8800000 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  | 95% by progress, 5% after final acceptance, T/T 35 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 8358244.99 | 0.9498 | 441755.01 | 0 | 441755.01 | 0 | [22 empty] | 1271769.47 |  | 1887512.99 |  |  |  | 0 | 1388654.35 |  |  | 2798825.22 | 0 | 711001.5 | [5 empty] | 300481.46 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C006 | F21P1 Slurry package | 1511 | C | USCSB2209015A | -01 | TSMC MIC Fab Chemical, Piping and Electrical Design | 2022/9/15 2023/2/1 | 2022/9/19 2023/2/6 | 100000 | 90000 | 10000 | V |  |  |  | KAEKO, Inc | PR Approved | PO Approved | USCSB2207010A Change order | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 96990 | 0.9699 | 3010 | 0 | 3010 | 0 | [25 empty] | 30000 |  |  | 66990 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1512 | C | USCSB2209016A |  | Horiba SLIA Reagent | 44820 | 44826 | 55125 | [6 empty] | HORIBA Instruments Incorporated | PR Approved | PO Approved |  | 100% by received-Net 30 days-After acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [5 empty] | 5000 |  | 55125 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 55125 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | CCE | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1513 | C | USCSB2209017A |  | site Temp power from UIS panel to sub work area | 44821 | 44824 | 112010.28 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 95% progress payment-Net 30 days-after acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 112010.28 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 112010.28 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC22C006 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1514 | C | USCSB2209018A | -01 | TSMC AZ F21P2 EUV crane structural calculation/design/PE stamp | 2022/9/17 2024/5/7 | 2022/9/21 2024/5/7 | 160000 | -90000 | 250000 | V |  |  |  | SYNERGY Engineering Consultants | PR Approved | PO Approved | R1: As per SYNERGY:Ting Sheng Wang to closed out the PR.(see the email) | 100% after design documents handover-T/T 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 160000 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 118000 |  |  |  | 0 |  | 42000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1515 | C | USCSB2209019A | -01 | CWS-TSMC AZ Phase 1 | 44821 | 2022/9/20 2023/10/27 | 222645 | -350000 | 572645 |  |  |  | V | Commercial Wallboard Systems, Inc | PR Approved | PO Approved | CWS cannot satisfy the workers' training for level 3 and 4./The rest of the work will goes to PCI. | 95% by progress-Net 30 days-After acceptance; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [5 empty] | Y | 166473.9 | 0.74771 | 56171.1 | 0 | 56171.1 | 0 | [28 empty] | 19076.4 |  | 58036.5 |  |  | 0 | 89361 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1516 | C | USCSB2209020A |  | Logistics coordinator/superintendent(took Hookup focus) | 44821 | 44824 | 182400 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 182395.11 | 0.99997 | 4.89 | 0 | 4.89 | 0 | [16 empty] | 6599.16 |  | 28810.54 |  | 31803.42 |  | 29775 |  | 29413.64 |  |  |  | 21596.24 |  |  |  | 34397.11 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC22C013 | F21P1 QR Lab Security & CCTV | 1517 | C | USCSB2209021A |  | F21P1 QR Lab_Security&CCTV Package | 44824 | 44830 | 61618.95 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 50569 | 0.82067 | 11049.95 | 0 | 11049.95 | 0 | [28 empty] | 0 |  |  |  | 50569 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC22C013 | F21P1 QR Lab Security & CCTV | 1518 | C | USCSB2209022A |  | F21P1 OWMC_Security&CCTV Package | 44824 | 44830 | 15393.94 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 15393.94 | 0 | 15393.94 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC22C013 | F21P1 QR Lab Security & CCTV | 1519 | C | USCSB2209023A |  | F21P1 MFG_Security&CCTV Package | 44824 | 44830 | 102627.93 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 83421 | 0.81285 | 19206.93 | 0 | 19206.93 | 0 | [28 empty] | 0 |  |  |  | 83421 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC22C013 | F21P1 QR Lab Security & CCTV | 1520 | C | USCSB2209024A |  | F21P1 FAB_Security&CCTV Package - 01 | 44824 | 44830 | 6025.84 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  | 95% by progress-after acceptance-net 30 days; 5% after final acceptance-net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 6025.84 | 0 | 6025.84 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Frontage Line Hydrant | Material | USC22C018 | US Fab Frontage line hydrants | 1521 | C | USCSB2209025A |  | TSMC 16" Water Line Re-Chlorination | 44827 | 44836 | 42000 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-After Acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 42000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 42000 | [9 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Frontage Line Hydrant | Material | USC22C018 | US Fab Frontage line hydrants | 1522 | C | USCSB2209026A |  | TSMC Hydrant Proposal | 44827 | 44836 | 1045000 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-After acceptance; 5% after final completion-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1045000 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 88267.12 | [5 empty] | 474750 |  | 81600 |  | 61850 |  |  |  |  | 0 | 338532.88 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | 光阻櫃 | Equipment | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1523 | C | USCSB2209027A |  | F21 Large Stainless cabinet&Photo resist cabinet Seismic 材料 | 44828 | 44832 | 25806.45 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved |  | 100% after shipped-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 11557.36 | 0.44785 | 14249.09 | 0 | 14249.09 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 11557.36 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | 5G | Material | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 1524 | C | USCSB2209028A | -01 | GLA CMS project | 2022/9/27 2023/11/23 | 2022/10/3 2023/11/27 | 461201.41 | -1209566.59 | 1670768 |  |  |  | V | GLA Arizona, LLC | PR Approved | PO Approved | PO R1:Cutting off GLA from the project per request by PM./ The rest of work will goes to Hua Yi in the future. | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 461201.41 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 112933.4 | [5 empty] | 0 |  |  |  |  | 0 | 236136.24 |  |  |  | 112131.77 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C017 | AMHS MML Power Design | 1525 | C | USCSB2209029A |  | AMHS Power Panel Design | 44831 | 44832 | 154685 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 154685 | 1 | 0 | 0 | 0 | 0 | [18 empty] | 109553 |  | 22769 |  |  |  | 18423.5 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 3939.5 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 1526 | C | USCSB2209030A | -01 | AMC Gas Cylinders | 44832 | 2022/10/8 2022/12/2 | 0 | -10942.4 | 10942.4 |  | V |  |  | Matheson Tri-Gac Inc. | PR Approved | PO Approved | Desciption cannot be changed, so close this and open new one because of new scope and quotation | 100% by received-Net 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Penetration Pipe | Material | USC22C020 | F21P1 Penetration Pipe | 1527 | C | USCSB2209031A |  | Core Drill and Grouting with Rebar | 44834 | 44847 | 38750 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 38750 | 1 | 0 | 0 | 0 | 1840.625 | [22 empty] | 33950 | [5 empty] | 0 |  |  |  | 2862.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 1937.5 | - | 0 | - | 0 | 0 | 1840.625
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 1528 | C | USCSB2209032A |  | Slurry VMBs | 44834 | 44838 | 97367 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | USC2112014A Change Order (credit $45,408) | 30%-30%-30% by progress-Net 30days-After acceptance; 10% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 74961.12 | 0.76988 | 22405.88 | 0 | 22405.88 | 22405.88 | [20 empty] | 74961.12 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 22405.88 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1529 | C | USCSB2209033A |  | Manifold Boxes | 44834 | 44852 | 308016.58 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  | 20% upon received material and approved submittal-Net 30 days-after acceptance; 60% on delivery with evidence-Net 30 days-after acceptance; 20% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 305637.1 | 0.99227 | 2379.48 | 0 | 2379.48 | 0 | [26 empty] | 305637.1 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 2379.48 |  | 0 |  | - | 0 | - | 0 | 0
Others | 光阻櫃 | Equipment | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1530 | C | USCSB2210002A | -01 | 宇承_工作桌&推車 | 2022/10/1 2023/4/18 | 2022/10/3 2023/4/19 | 22348 | 3735 | 18613 |  |  |  | V | Yu Cheng Kid Enterprise Co., | PR Approved | PO Approved | Adding $3,735 overtime pay in (originally should be in USCSB2210003A) | 100% by received-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 22348 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 22348 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | 光阻櫃 | Equipment | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1531 | C | USCSB2210003A | -01 | 宇承_光阻推車&推酸車 | 2022/10/1 2023/4/1 | 2022/10/3 2023/4/4 | 0 | -10302 | 10302 |  |  |  | V | Yu Cheng Kid Enterprise Co., | PR Approved | PO Approved | Cancelling this PR due to the rush of manufacture Combine this overtime pay into USCSB2210002A | 100% by received-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | 5G | Material | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 1532 | C | USCSB2210004A |  | TSMC-F21P1-Temporary outfall monitoring | 44835 | 44842 | 47294.07 | [6 empty] | ACME Control System Corporation | PR Approved | PO Approved | TSMC hasn't issued PO to us. Once TSMC issues, we will back charge this portion with profit markup. The reason why it uses the budget here is simply because we have sufficient room in this project | 15% prepayment-Net 30 days; 75% by progress-Net 30 days-after acceptance; 10% after final acceptance (site acceptable test)-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [5 empty] | 5000 |  | 44882.71 | 0.94901 | 2411.36 | 0 | 2411.36 | 2364.7 | [22 empty] | 33600.84 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 11281.87 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 2364.7
Base-Build | VOC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 1533 | C | USCSB2210005A |  | VOC project Added insulation per Bill of Materials | 44835 | 44841 | 569074 | [6 empty] | Southland Industries | PR Approved | PO Approved | USCSB2109008A-1 change order (TSMC will pay) | 95% by progress-T/T 30 days-after acceptance; 5% after final acceptance-T/T 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 569074 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 54574 | [7 empty] | 0 |  |  |  | 42315 | 0 |  |  |  | 177364 |  |  | 84630 | 0 | 0 | 0 |  | 0 | 50778 | 79129 | 0 | 0 | 80284 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1534 | C | USCSB2210006A |  | Horiba Conductivity/Resistivity Meter Batch 2 | 44838 | 44838 | 11545.85 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved | Replace part of USC2111003A scope (same request for USCSB2209011A but different batch because of lead time) | 100% after goods arrival date-T/T 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 11545.85 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 11545.85 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1535 | C | USCSB2210007A |  | Horiba Conductivity/Resistivity Meter Batch 3 | 44838 | 44838 | 19391.15 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved | Replace part of USC2111003A scope (same request for USCSB2209011A but different batch because of lead time) | 100% after goods arrival date-T/T 30 days-after acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 19391.15 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 19391.15 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1536 | C | USCSB2210008A |  | UPW A Side Disconnect Switch Change Order | 44839 | 44852 | 113273.07 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A-01 Change Order (Disconnect Switch) | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 113273.07 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 35681.02 |  | 35681.02 |  | 22654.61 |  | 19256.42 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1537 | C | USCSB2210009A |  | UPW A Side Disconnect Switch Stands Change Order | 44839 | 44852 | 30498.48 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A-01 Change Order (Disconnect Switch Stand) | 95% by progress-Net 30 days-After acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 30498.48 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 9607.02 |  | 9607.02 |  | 9607.02 |  | 1677.42 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | 光阻櫃 | Equipment | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1538 | C | USCSB2210010A |  | Rich - Stainless steel mask bank room shelf and cart | 44839 | 44844 | 278064.52 | [6 empty] | RUI QI STAINLESS STEEL FIRM | PR Approved | PO Approved |  | 100% by received-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 278064.52 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 278064.52 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1539 | C | USCSB2210012A |  | F21P1 – WSR-S H2S04 Steel supports | 44840 | 44846 | 355000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-after acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 355000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 6500 | [5 empty] | 87965.5 |  | 163873.5 |  |  |  | 16436.5 | 0 |  |  | 41809.5 |  |  |  | 20644 | 0 | 17771 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1540 | C | USCSB2210013A |  | F21P1 WWT urgent Hardware | 44840 | 44848 | 16496.16 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  | 100% by received-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 16496.16 | 1 | 0 | 0 | 0 | 0 | [19 empty] | 16496.16 | [8 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Penetration Pipe | UMEC | USC22C020 | F21P1 Penetration Pipe | 1541 | C | USCSB2210014A |  | FAB L10, L20 HPM Drain Piping Penetration | 44841 | 44909 | 249618 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  | 95% by progress-Net 30 days-After acceptance; 5% after final completion-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 249618 | 0 | 249618 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | AMC THC | Material | USC22C019 | AMC monitor 595T0 | 1542 | C | USCSB2210015A |  | MICU-TSMC F21P1 Litho AMC 64CH online monitoring system | 44841 | 44848 | 600000 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  | 95% by shipping-Net 30 days-After acceptance; 5% after final acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 600000 | 1 | 0 | 0 | 0 | 30000 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 104264.5 | 378222.5 | 0 | 0 |  |  | 87513 | 0 | 0 |  | 0 | [14 empty] | 0 | 30000 | - | 0 | - | 0 | 0 | 30000
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 1543 | C | USCSB2210016A | -01 | CED Wire | 44841 | 44847 | 179999.59 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Qty and Price adjustment according to the quote (incorrect UOM) | 100% by shipment-After Acceptance-Net 30 days | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 179999.59 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 179999.59 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical Lab | Labor | USC22C021 | F21P1 Chemical Lab setup | 1544 | C | USCSB2210017A |  | FAB L10, L20 HPM Drain Piping Penetration | 44845 | 44847 | 77055 | [6 empty] | Silicone Future Manufacturing Company Ltd | PR Approved | PO Approved |  | 100% by received-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 77055 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 77055 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC22C024 | UIS Scaffolding | 1545 | C | USCSB2210018A |  | Liberty Industrial Group Scaffold | 44845 | 44851 | 1500000 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | Open PO | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 1490921.08 | 0.99395 | 9078.92 | 0 | 9078.92 | 0 | [26 empty] | 1490921.08 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1546 | C | USCSB2210019A |  | Material Coordinator/Superintendent(Tool Hookup Focus/Tool Hookup Focus Track/Tool Hookup Focus DUV) | 44845 | 44846 | 398400 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 398400 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 44398.98 |  | 66400 |  | 61371.86 |  | 76063.76 |  | 66926.36 |  | 67313.52 |  | 15925.52 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C008 | F21P1 CCTV & Security | 1547 | C | USCSB2210020A |  | Sunrise Phoenix housekeeping services | 44845 | 44846 | 500000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 457477.5 | 0.91495 | 42522.5 | 0 | 42522.5 | 0 | [18 empty] | 21525 | 99892.5 | 71137.5 | 36357.5 | 69712.5 | 113525 | 45327.5 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1548 | C | USCSB2210021A |  | Nagano JM31-1L3 | 44847 | 44848 | 9449.04 | [6 empty] | Ashcroft Inc. | PR Approved | PO Approved | USC2111018A-01 misorder JM31 | 100% by progress-Net 30 days-After Acceptance | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 9449.04 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 7086.78 |  | 2362.26 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | GF Agru Material | Material | USC22C023 | AZ GF Agru Material | 1549 | C | USCSB2210022A |  | GF PP&PVDF Material Organo | 44847 | 44852 | 2298.12 | [6 empty] | Organo Technology CO., LTD | PR Approved | PO Approved |  | 100% by progress-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 2298.12 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 2298.12 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | GF Agru Material | Material | USC22C023 | AZ GF Agru Material | 1550 | C | USCSB2210023A |  | GF PP&PVDF Material UANGYIH | 44847 | 44851 | 52079.75 | [6 empty] | Uangyih-Tech Industrial Co., LTD | PR Approved | PO Approved |  | 100% by progress-Net 60 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 52079.75 | 1 | 0 | 0 | 0 | 0 | [21 empty] | 52079.75 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | GF Agru Material | Material | USC22C023 | AZ GF Agru Material | 1551 | C | USCSB2210024A |  | GF PP&PVDF Material Mega union | 44847 | 44851 | 353593.12 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  | 100% by shipping-Net 30 days-After acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 353593.12 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 117840 |  | 13533.33 | 0 |  | 111561.19 |  |  | 0 | 110658.6 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | GF Agru Material | Material | USC22C023 | AZ GF Agru Material | 1552 | C | USCSB2210025A |  | GF PP&PVDF Material Li Jie | 44848 | 44851 | 1129032.26 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved |  | 100% by shipping-Net 30 days-After Acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1129032.26 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 1129032.26 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | MIMO/Rigging | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1553 | C | USCSB2210026A |  | WWT-Panel Move-In and installation | 44848 | 44852 | 761100 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  | 100% by progress-Net 30 days-after acceptance | Yi En Wong |  |  | Rui Ma | Yi En Wong | [6 empty] | Y | 641145 | 0.84239 | 119955 | 0 | 119955 | 102583.2 | [20 empty] | 188800 |  | 41300 |  | 7945 |  | 120980 |  | 0 |  |  |  |  | 0 |  |  | 64900 |  |  |  | 143232.5 | 0 | 0 | 0 | 73987.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 38055 |  |  |  | 22833 |  |  |  | 22833 |  | 32057.25 |  | - | 32057.25 | - | 19234.35 | 19234.35 | 0
Hookup | Hookup | Material | USC22C026 | F21P1-0423_H_Unistrut Support Frame_MICU | 1554 | C | USCSB2210027A | -01 | MISC BOM-1 STRUCTURE | 44853 | 44858 | 3521842.92 | -415763.5 | 3937606.42 |  | V |  |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Cannot revise description and cannot add new item, so we can only cancel this PO and get a new one, which is super redundant and a waste of time |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 3521362.18 | 0.99986 | 480.74 | 0 | 480.74 | 0 | [23 empty] | 967990.42 |  | 583071.47 | 843709.61 |  | 0 | 422610.08 | 693994.15 |  |  | 0 | [6 empty] | 0 | 0 | 9986.45 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C026 | F21P1-0423_H_Unistrut Support Frame_MICU | 1555 | C | USCSB2210028A |  | MISC UNDERFLOOR/RAISED UNDERFLOOR PREFAB | 44853 | 44858 | 290183.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 290183.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 290183.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C026 | F21P1-0423_H_Unistrut Support Frame_MICU | 1556 | C | USCSB2210029A | -01 | MISC BOM-3 CLAMPS | 2022/10/19 2022/11/16 | 2022/10/24 2022/11/16 | 0 | -4772888.51 | 4772888.51 | V | V |  |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Price changed & item number changed, but PR cannot revise, so close this and open new one Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1557 | C | USCSB2210030A |  | Harrington-Chemical PVC | 44853 | 44855 | 252900.42 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 252900.42 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 252900.42 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | GF Agru Material | Material | USC22C023 | AZ GF Agru Material | 1558 | C | USCSB2210031A |  | Harrington-8" PVDF STUB END | 2022/10/19 2022/12/1 | x | 0 | -23440 | 23440 | [5 empty] | PR Approved | PO Approved | scope change to open PO |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1559 | C | USCSB2210032A |  | PHP-Tank Painting | 44853 | 44855 | 52000 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved | Harrington Paint white (incorrect), PHP repaint and Harrington will pay 50% |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 52000 | 1 | 0 | 0 | 0 | 0 | [20 empty] | 52000 | [7 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1560 | C | USCSB2210033A |  | commissioning chemical purchase | 44853 | 44858 | 180187.87 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 176384.38 | 0.97889 | 3803.49 | 0 | 3803.49 | 3527.6876 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 11583.25 | 7720.65 |  | 8288 | 9891.37 | 0 | 0 | 0 | 5345.34 | 56038.11 | 0 | 7794.86 | 16364.66 | 0 |  |  | 15597.12 | 0 | 0 |  | 26199.12 |  |  |  |  | 9009.3935 |  |  | 11561.9 | 9009.3935 |  |  |  | 9009.3935 |  | 0 |  | - | 0 | - | 0 | 0 | 3527.6876
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1561 | C | USCSB2210034A |  | Confined Space Entry manwatch | 44854 | 44867 | 47962.09 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 40802.09 | 0.85072 | 0 | 0 | 0 | 0 | [26 empty] | 40802.09 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1438.8627 |  |  |  | 1438.8627 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1562 | C | USCSB2210035A |  | PVC SCH80 Fittings Litho Fab Spears | 44854 | 44855 | 25364.67 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 25364.67 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 25364.67 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1563 | C | USCSB2210036A |  | PVC SCH80 Pipes-Litho Fab GF/RHFS | 44854 | 44855 | 38265.86 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 38265.86 | 0 | 38265.86 | 38265.86 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 5739.879 |  |  |  | 5739.879 |  |  |  | 5739.879 |  | 9566.465 |  | - | 9566.465 | - | 9566.465 | 9566.465 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1564 | C | USCSB2210038A |  | Lab Drainpipe installation | 44854 | 44960 | 3243647.71 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 3058089.79 | 0.94279 | 185557.92 | 0 | 185557.92 | 0 | [28 empty] | 324364.77 | 2468779.31 |  |  |  | 0 | [6 empty] | 264945.71 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1565 | C | USCSB2210039A |  | Tank blinding and davit arm weld | 44855 | 44867 | 44368.92 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 44368.92 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 44368.92 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1566 | C | USCSB2210040A |  | Blind Flanges for Hydrostatic Testing | 44855 | 44859 | 18500 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 18500 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 17575 |  | 925 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
AMHS | AMHS |  | USC22C027 | CAP_E_F21P1 Autoshelf Installation 4 set | 1387 | C | USCSB2210041A |  | Autoshelf installation | 44859 | 44860 | 168000 | [6 empty] | GLA Arizona, LLC | PR Approved | PO Approved | [14 empty] | 0 | 0 | 168000 | 0 | 168000 | 0 | [73 empty] | - |  | - |  | 0
Hookup | Foundation | Labor | USC22C028 | CAP_E_F21P1 Autoshelf Foundation | 1568 | C | USCSB2210042A |  | auto shelf foundation installation | 44859 | 44859 | 20638 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 11578 | 0.561 | 9060 | 0 | 9060 | 0 | [24 empty] | 8180 |  | 3398 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Triazole | Material | USC22C022 | F21P1 Triazole treatment system | 1569 | C | USCSB2210043A |  | MU-Triazole System | 44859 | 44861 | 1794999.84 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | MICU joint project with MU Taiwan, TSMC bargained the project altogether directly with both parties |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 784435.72 | 0.43701 | 1010564.12 | 0 | 1010564.12 | 439284.0032 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 455035.72 |  |  |  | 329400 | [6 empty] | 94132.2864 |  | - | 94132.2864 | - | 94132.2864 | 78443.572 | 78443.572
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1570 | C | USCSB2210044A |  | FAB Sump Pit Pump RT Fitting | 44860 | 44861 | 58232.1 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 58232.1 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 58232.1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1571 | C | USCSB2210045A |  | TUNNEL Sump Pit Pump RT Fitting | 44860 | 44861 | 7926.2 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 7926.2 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 7926.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1572 | C | USCSB2210046A |  | WRC Sump Pit Pump RT Fitting | 44860 | 44861 | 44343.4 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 44343.4 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 44343.4 |  |  | 6651.51 |  |  |  | 6651.51 |  |  |  | 6651.51 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS | Labor | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 1573 | C | USCSB2210047A |  | AMHS electric project | 2022/10/26 2023/03/21 | 2022/11/17 2023/03/21 | 8057264.13 | -10291428.52 | 18348692.65 |  |  |  | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | Separate scope for TSMC and MURATECH; this is for TSMC |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 8057264.13 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 3669738.53 |  | 0 |  | 2704632.5 |  | 425348.38 | 0 | 1257544.72 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1574 | C | USCSB2210048A |  | HK UPW material (20k) | 2022/10/26 2023/3/28 | x | 0 | -824533.51 | 824533.51 | [5 empty] | PR Approved | PO Approved | scope changed, void this PR |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1575 | C | USCSB2210049A |  | CCE Redesign Change Order | 44860 | x | 0 | -916925 | 916925 | [5 empty] | PR Approved | PO Approved | Under wrong project |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 1576 | C | USCSB2210050A |  | L30 Raised Floor Pipe Channel | 44862 | 44867 | 254247.61 | [6 empty] | SDB, Inc. dba SDB Contracting Services | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [5 empty] | 5005 | Y | 254247.61 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 79800 |  | 161735.23 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 12712.38 |  | 0 | [8 empty] | 228822.85 |  |  |  | 12712.38 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 1577 | C | USCSB2210051A |  | F21P1-FAB LB2-LOOP 2 STAGE modifications | 44862 | 44867 | 20000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 20000 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 19000 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 1000 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Equipment | USC21C008 | F21P1 CCTV & Security | 1578 | C | USCSB2210052A |  | Radio Rental | 44862 | 44867 | 34272 | [6 empty] | Code Red Safety & Rental, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 32009.13 | 0.93397 | 2262.87 | 0 | 2262.87 | 0 | [23 empty] | 3424.92 | 2856 |  | 2856 |  | 2856 |  | 2880.21 |  | 2856 | 0 | 2856 |  |  | 2856 | 5712 |  | 0 | 2856 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1579 | C | USCSB2210053A |  | 7 Davit Arms and Manways Install | 44863 | 44867 | 15402.62 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 14632.49 | 0.95 | 770.13 | 0 | 770.13 | 0 | [24 empty] | 14632.49 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1580 | C | USCSB2210054A |  | Distribution Panels | 2022/10/29 2022/11/10 | x | 0 | -4963.2 | 4963.2 | [5 empty] | PR Approved | PO Approved | Under wrong project |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1581 | C | USCSB2211001A |  | WWT adapter | 44866 | 44867 | 2971.5 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 2971.5 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 2971.5 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1582 | C | USCSB2211003A |  | Tool Team PVD/CVD Project Coordinator/ Superintendent | 2022/11/2 2022/11/8 | 44874 | 337906.32 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 324180.38 | 0.95938 | 13725.94 | 0 | 13725.94 | 0 | [19 empty] | 13875.36 | 19230.96 |  |  | 16600 | 44267.22 |  | 50655 |  | 49339.9 |  | 49748.9 |  | 48396.82 | 0 | 32066.22 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1583 | C | USCSB2211004A |  | WWT Discharge box adding | 44868 | 44870 | 203447.19 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved | TSMC has reviewed MU costs directly, so MICU just adds up margin |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 203447.19 | 0 | 203447.19 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 30517.0785 |  |  |  | 30517.0785 |  |  |  | 30517.0785 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Site Expense | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1584 | C | USCSB2211005A |  | TSMC-Grounding & Permitting Herc/MIC Rentals | 44869 | 44897 | 14770 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 14770 | 0 | 14770 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 2215.5 |  |  |  | 2215.5 |  |  |  | 2215.5 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | USC22C006 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1585 | C | USCSB2211006A |  | TSMC F21 AZ On-site Construction Coordination | 44869 | 44873 | 100000 | [6 empty] | SYNERGY Engineering Consultants | PR Approved | PO Approved | extension order for USCSB2205027A |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 100000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1586 | C | USCSB2211007A |  | Lorry Bridge brackets Fabrication | 44869 | 44902 | 211094.27 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 211094.27 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 211094.27 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1587 | C | USCSB2211008A |  | 4 Trips Plainview, TX | 2022/11/4 2022/12/2 | 44902 | 187120.14 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 187120.14 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 187120.14 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C006 | F21P1 Slurry package | 1588 | C | USCSB2211009A |  | F21 General Labor and Housekeeping Service | 44873 | 44875 | 300000 | [6 empty] | BHTC Arizona, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 300000 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 2340 | 29967.5 | 27462.5 |  | 75527.5 | 81917.5 | 54698.75 |  | 28086.25 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 1589 | C | USCSB2211010A |  | WRC control room raised floor | 2022/11/8 2022/11/23 | 44900 | 171436.4 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 171436.4 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 26961.8 |  | 0 |  |  |  | 101615.5 | 0 |  | 42859.1 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Equipment | USC21C011 | F21 TMAH System | 1590 | C | USCSB2211011A |  | LC/MS/MS System for TSMC Project | 44873 | 44886 | 496063.78 | [6 empty] | Agilent Technologies, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 496063.78 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 496063.78 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | CCE | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1591 | C | USCSB2211012A |  | CCE Redesign Change Order | 44874 | 44875 | 916925 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved | USCSB2202002A Change Order |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 916925 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 183385 |  | 687693.75 |  | 45846.25 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1592 | C | USCSB2211013A |  | Distribution Panels | 44875 | 44875 | 4963.2 | [6 empty] | Larson Electronics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 0 | 4963.2 | 0 | 4963.2 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 744.48 |  |  |  | 744.48 |  |  |  | 744.48 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | GF Agru Material | Material | USC22C023 | AZ GF Agru Material | 1593 | C | USCSB2211015A |  | AZ GF Material Summary Table | 44876 | 44881 | 774105 | [6 empty] | SWIFT ENGINEERING CO., LTD. | PR Approved | PO Approved | TSMC Nego already |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 774105 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 774105 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1594 | C | USCSB2211016A |  | Ebro Butterfly Valve | 44877 | 44896 | 3408 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 3408 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 3408 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1595 | C | USCSB2211017A | -01 | Protego-Flame Arrestors | 2022/11/12 2023/1/12 | 2022/11/30 2023/1/18 | 0 | -134500 | 134500 |  |  |  | V | BERMINGHAM CONTROLS, INC. | PR Approved | PO Approved | Cancelled, used Catrol |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1596 | C | USCSB2211018A |  | Custom flanges and bolts | 44881 | 44881 | 12549 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 12549 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 11921.55 |  | 627.45 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1597 | C | USCSB2211019A |  | Embedded pipes fire sealants | 2022/11/16 2023/2/17 | 44994 | 96460 | [6 empty] | Kinpo Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 0 | 0 | 96460 | 0 | 96460 | 57876 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 48230 | [5 empty] | 0 |  | - | 28938 | - | 0 | 28938
Hookup | Hookup | Material | USC22C026 | F21P1-0423_H_Unistrut Support Frame_MICU | 1598 | C | USCSB2211020A |  | MISC BOM-3 CLAMPS | 44882 | 44895 | 4766818.83 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Replace USCSB2210029A |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 4766661.4 | 0.99997 | 157.43 | 0 | 157.43 | 0 | [23 empty] | 176648.56 |  | 1181514.54 | 109093.39 |  | 0 |  | 1596119.92 |  | 1359670.44 | 0 |  |  |  |  | 236118.9 |  | 0 | 0 | 107495.65 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | PSS | USC21C003 | F21P1 UPW | 1599 | C | USCSB2211021A |  | Litho Embedded Pipes installation | 44882 | 44896 | 223915 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 210793.75 | 0.9414 | 13121.25 | 0 | 13121.25 | 0 | [26 empty] | 22391.5 |  | 44782.99 |  |  |  |  | 0 | 33648.58 |  | 106946.36 |  |  |  | 0 | 0 | 3024.32 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1600 | C | USCSB2211022A |  | WWT welding machines rentals from Megaunion | 44883 | 44886 | 104000 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 104000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 104000 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1601 | C | USCSB2211023A |  | WWT welding machines rentals from Harrington | 44883 | 44886 | 26884.38 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 25162.11 | 0.93594 | 1722.27 | 0 | 1722.27 | 1509.7266 | [28 empty] | 0 |  | 11754.45 |  | 4469.22 | 3060.25 | 4469.22 | 1408.97 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 537.6876 |  | 0 |  | - | 0 | - | 0 | 0 | 1509.7266
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1602 | C | USCSB2211024A |  | Temp Power Supplier | 44883 | 44886 | 87049.1 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 86027.8 | 0.98827 | 1021.3 | 0 | 1021.3 | 0 | [23 empty] | 86027.8 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | CCE | USC21C003 | F21P1 UPW | 1603 | C | USCSB2211025A |  | X line Temp Power RFQ 11_16 | 44883 | 44924 | 230320 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 230320 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 218804 |  | 0 |  | 11516 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 1604 | C | USCSB2211027A |  | F21P1 TMAH | 44884 | 44886 | 1305645.46 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 580012.96 | 0.44423 | 725632.5 | 0 | 725632.5 | 324807.2576 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 119512.96 |  | 150000 | [7 empty] | 310500 |  |  |  |  | 69601.5552 |  | - | 69601.5552 | - | 69601.5552 | 58001.296 | 58001.296
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1605 | C | USCSB2211028A |  | UPW WRC Chemical room ball valves (1-1/2”) | 44884 | 44886 | 779.52 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Engineering contracting review (~20000)-second-level supervisor |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 779.52 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 779.52 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Material | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 1606 | C | USCSB2211029A |  | APK & UPK Iron Plates | 44887 | 44897 | 37847.64 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 37847.64 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 20817 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 17030.64 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1607 | C | USCSB2211030A |  | Portable Cleanroom Material - Copper State | 2022/11/22 2023/2/2 | x | 0 | -967.46 | 967.46 | [5 empty] | PR Approved | PO Approved | go through APN (non-material) for card purchase |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | ESP | Equipment | USC22C033 | F21 ESP equipment(include labor fee) | 1608 | C | USCSB2211031A |  | F21 ISEP ESP system implementation and hardware equipment purchase | 44887 | 44897 | 7480 | [6 empty] | Ying Pao Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 7480 | 0 | 7480 | 7106 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 7106 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1609 | C | USCSB2211032A |  | UPW Mark-up RO skids limit switch | 44888 | 44894 | 136 | [6 empty] | Azbil North America, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 136 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 136 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Material | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 1610 | C | USCSB2211033A |  | AMHS APK&UPK iron plate | 44889 | 44895 | 104295 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 104295 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 12605.5 |  | 29781 |  | 37667 |  |  | 0 | 19026.75 | [5 empty] | 0 | 0 | 0 | 0 |  | 5214.75 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1611 | C | USCSB2211034A |  | F21-P0176 Foundation Reorder | 44889 | 44894 | 9600 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved | Damaged Foundation because of 3PL wrongly handling; we will back charge to 3PL |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 9600 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 9600 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C034 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/N2/APK/UPK/ASRS | 1612 | C | USCSB2211035A |  | TSMC F21P1 FAB and HPM AMHS Infrastructure GEX and PV Hook-up | 44889 | 44894 | 39600 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 33720 | 0.85152 | 5880 | 0 | 5880 | 0 | [26 empty] | 33720 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C034 | CAP_E_F21P1 SP2 Power Design and GEX/PV/CV CAD design forsorter/BWBS/N2/APK/UPK/ASRS | 1613 | C | USCSB2211036A |  | TSMC F21P1 FAB and HPM AMHS Infrastructure Non-AMHS Device Power Hook-up | 44889 | 44894 | 54320 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 54320 | 1 | 0 | 664482.58 | -664482.58 | 0 | [26 empty] | 25487 |  | 20975 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 7247 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 611 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1614 | C | USCSB2211037A |  | PP Material | 44895 | 44897 | 39537.5 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 39537.5 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 39537.5 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1615 | C | USCSB2211038A |  | Cantilever Arms | 44895 | 44897 | 15565.24 | [6 empty] | Toyotalift of Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 15565.24 | 1 | 0 | 0 | 0 | 0 | [22 empty] | 8910.62 | [5 empty] | 0 | 6654.62 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 1616 | C | USCSB2211039A |  | SLURRY VMB INSTALL KIT - SIDE A | 44895 | 44897 | 4491.74 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 4491.74 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 4491.74 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1617 | C | USCSB2211040A |  | wastewater adapter | 44895 | 44897 | 747.8 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 747.8 | 0 | 747.8 | 747.8 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 112.17 |  |  |  | 112.17 |  |  |  | 112.17 |  | 747.8 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1618 | C | USCSB2212001A |  | UPW BIM Modeling of Conduit | 44896 | 44897 | 170580.48 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A(Rev01) change order |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 170580.48 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 107465.7 |  |  |  | 0 |  | 20469.66 |  | 6823.22 | 0 |  |  | 10234.83 |  | 3411.61 |  | 13646.44 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 8529.02 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1619 | C | USCSB2212002A |  | UPW 4C Wire | 44896 | x | 0 | [7 empty] | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1620 | C | USCSB2212003A |  | FRP Tank Repairs | 44896 | 44897 | 10000 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Open PO |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 5647 | 0.5647 | 4353 | 0 | 4353 | 451.76 | [28 empty] | 0 |  | 200 |  |  | 4394 | [6 empty] | 0 | 0 | 0 | 0 |  | 1053 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 500 |  |  |  | 500 |  |  |  | 1000 |  | 0 |  | - | 0 | - | 0 | 0 | 451.76
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1621 | C | USCSB2212004A |  | Alliance - trucking cost | 44896 | 44900 | 137912 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 137912 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 137912 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1622 | C | USCSB2212005A |  | Alliance - trucking cost 910AA/AB TANKS | 44896 | 44900 | 34810 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 34810 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 34810 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | Labor | USC21C008 | F21P1 CCTV & Security | 1623 | C | USCSB2212006A | -01 | Power Cable | 2022/12/2 2023/12/27 | 2022/12/14 2023/12/27 | 0 | -147000 | 147000 |  |  |  | V | Alvarado Electric LLC. | PR Approved | PO Approved | R1: Canceled Scope and already PO to other sub |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1624 | C | USCSB2212007A |  | WWT CDA cooper tube and fittings | 44898 | 44909 | 26000 | [6 empty] | Chien Tai Valves & Pipe Fittings Co. Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 26000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 26000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1625 | C | USCSB2212008A |  | sample box 640 & 645 | 44898 | 44900 | 8977 | [6 empty] | Collabratech Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 8977 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 8977 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1626 | C | USCSB2212009A |  | Mechanical Dock and Uni-chock | 44902 | 44909 | 41110 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 41110 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 41110 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1627 | C | USCSB2212010A |  | WRC CCB camlocks | 44902 | 44909 | 1216.4 | [6 empty] | CamlockDirect | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1216.4 | 1 | 0 | 0 | 0 | 0 | [23 empty] | 1216.4 |  |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1628 | C | USCSB2212011A | -01 | UPW-MMF-Anthracite procurement | 44902 | 44935 | 0 | -6080 | 6080 |  | V |  |  | Northern Filter Media, Inc. | PR Approved | PO Approved | Cannot revise description and cannot add new item, so we can only cancel this PO and get a new one, which is super redundant and a waste of time |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1629 | C | USCSB2212012A |  | Flange Gaskets | 44902 | 44902 | 1350 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 1350 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | Liquid Penetrant | Material | USC22C035 | CAP_A_90772_F21 Phone call base build and Liquid penetrant testing system | 1630 | C | USCSB2212013A |  | F21 Phone call base build and Liquid penetrant testing system | 44902 | 44909 | 105516.7 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 105516.7 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 105516.7 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | 5G | Material | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 1631 | C | USCSB2212014A |  | DPM Connection Project | 44904 | 44909 | 14000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 14000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 14000 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 1632 | C | USCSB2212015A |  | UPW LB2 & X1-Y Line Redesign and Network & Com | 44904 | x | 0 | [7 empty] | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 1633 | C | USCSB2212016A |  | TSMC F21P1 MIC | 44904 | 44909 | 10181 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 10181 | 0 | 10181 | 10181 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 10181
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1634 | C | USCSB2212017A |  | UPW 4C Wire & Disconnect Switch | 44906 | 44916 | 364908.17 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A-01 Change order (4C cable+disconnect switch) |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 364908.16 | 1 | 0.01 | 0 | 0.01 | 0 | [26 empty] | 114946.07 |  | 114946.07 |  | 135016.02 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1635 | C | USCSB2212018A |  | Security Services | 44908 | 44917 | 232780 | [6 empty] | Allied Universal Security Services | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 215248.56 | 0.92469 | 17531.44 | 0 | 17531.44 | 0 | [23 empty] | 1389.48 |  | 17827.12 |  |  | 17431.68 | 22288.6 |  |  |  | 0 | 35861.36 |  | 22158.9 |  |  |  | 22288.6 | 17930.68 | 0 | 0 | 17852.86 | 0 | 0 | 22288.6 | 17930.68 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Site Expense | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1636 | C | USCSB2212019A |  | WRC Generator Grounding & Permitting | 44908 | 44909 | 4260 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved | USCSB2211005A CHANGE ORDER |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 4260 | 0 | 4260 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 639 |  |  |  | 639 |  |  |  | 639 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Site Expense | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1637 | C | USCSB2212020A |  | Grounding for generator and fuel cube | 44908 | 44909 | 1850 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1850 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 1850 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | VOC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 1638 | C | USCSB2212021A |  | VOC Duct/Pipe Labels | 44908 | 44923 | 52049.16 | [6 empty] | Southland Industries | PR Approved | PO Approved | USCSB2109008A-1 change order |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 52049.16 | 0 | 52049.16 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 13013 |  |  |  | - |  | - |  | 0
Base-Build | VOC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 1639 | C | USCSB2212022A |  | 2 months rental-Light tower | 44908 | 44909 | 1595 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 1595 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 1595 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1640 | C | USCSB2212023A |  | UPW-Design tanks repair | 44908 | 44910 | 5100 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 5100 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5100 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1641 | C | USCSB2212024A |  | WWT Mini Line missing material | 44908 | 44914 | 15545.13 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 15520.28 | 0.9984 | 24.85 | 0 | 24.85 | 0 | [28 empty] | 0 |  |  |  |  | 15520.28 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1642 | C | USCSB2212025A |  | WWT Lab drain pipe materials | 44909 | 44916 | 665277.46 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 665277.46 | 0 | 665277.46 | 665277.46 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 99791.619 |  |  |  | 99791.619 |  |  |  | 99791.619 |  | 133055.492 |  | - | 133055.492 | - | 133055.492 | 133055.492 | 133055.492
Base-Build | WWT | MMI | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1643 | C | USCSB2212026A |  | T-125 tank flanges and gaskets | 44910 | 44910 | 5789 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 5789 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 5789 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1644 | C | USCSB2212027A |  | 1st Set of Clamps | 44911 | 44916 | 93422.41 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 85363.72 | 0.91374 | 0 | 0 | 0 | 0 | [26 empty] | 83828.73 |  | 1534.99 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 3736.8964 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1645 | C | USCSB2212028A |  | 2nd Set of Clamps | 44911 | 44916 | 401347.41 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 362097.67 | 0.90221 | 0 | 0 | 0 | 0 | [26 empty] | 354621.53 |  | 7476.14 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8026.9482 |  |  |  | 12040.4223 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1646 | C | USCSB2212029A |  | Clamps Lorry – L10-20-30 | 44911 | 44916 | 1104701 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 899102.27 | 0.81389 | 0 | 0 | 0 | 0 | [26 empty] | 843029.89 |  | 56072.38 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 55235.05 |  |  |  | 55235.05 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | 5G | Material | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 1647 | C | USCSB2212030A |  | TSMC New FAB Building - KINEMETRICS earthquake instruments | 44911 | 45006 | 121950 | [6 empty] | Kinemetrics, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 66265 | 0.54338 | 55685 | 0 | 55685 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 66265 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1648 | C | USCSB2212032A |  | WRC WWT Stripper Side Foundation | 44912 | 44916 | 44435 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 42196.05 | 0.94961 | 2238.95 | 0 | 2238.95 | 2109.8025 | [28 empty] | 42196.05 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 2109.8025
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 1649 | C | USCSB2212033A |  | Lorry Vertical Support | 44912 | 44916 | 50858 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 50858 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 3950 |  | 21488.5 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 50858 |  |  |  |  | 25419.5 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 1650 | C | USCSB2212034A |  | WRC C,7-D,8 UMEC Pipe Support | 44912 | 44916 | 44320 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | Y | [6 empty] | 42104 | 0.95 | 2216 | 0 | 2216 | 0 | [26 empty] | 42104 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | 2216 | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1651 | C | USCSB2212035A |  | CO MIC BIM Support | 44915 | x | 0 | -358560 | 358560 |  | V |  |  |  | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1652 | C | USCSB2212037A |  | WWT- Na2SO3-Formaldehyde | 44915 | 44916 | 137212 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 137212 | 1 | 0 | 0 | 0 | 33475.68 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 20581.8 |  |  | 59778 | 20581.8 |  |  |  | 20581.8 |  | 11955.6 |  | 77434 | 11955.6 | - | 9564.48 | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1653 | C | USCSB2212038A |  | LB2 Wall Redesign Cable Tray Changes | 44915 | 44916 | 101342.71 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A(Rev01) change order (Wall Redesign LB2 Cable Tray Change) |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 101342.71 | 1 | 0 | 0 | 0 | 10134.28 | [26 empty] | 32964.24 |  | 3896.57 |  | 55919.77 |  |  | 0 |  |  | 3494.99 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 5067.14 | 0 |  | - | 5067.14 | - | 0 | 5067.14
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1654 | C | USCSB2212039A |  | X1_Y Line Changes | 44915 | 44916 | 325446.02 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A(Rev01) change order (X1-Y Line) |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 325436.01 | 0.99997 | 10.01 | 0 | 10.01 | 0 | [26 empty] | 118263.61 |  | 78641.21 |  | 128531.19 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1655 | C | USCSB2212040A |  | Network & Com | 44915 | 2022/12/26 | 341555.2 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | USCSB2111007A(Rev01) change order (Network & Communication) |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 317646.34 | 0.93 | 23908.86 | 0 | 23908.86 | 47817.72 | [26 empty] | 107589.89 |  | 34155.52 |  | 68311.04 |  | 107589.89 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 23908.86 | - | 0 | 23908.86
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1656 | C | USCSB2212041A |  | MIC Water Tanks Painting | 44916 | 44916 | 8000 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | N | [6 empty] | 8000 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 8000 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1657 | C | USCSB2212042A |  | CCE Gaskets | 44917 | 44924 | 5342.85 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 5342.85 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 4854.25 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 488.6 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1658 | C | USCSB2212043A |  | XHHW 1/0 STR GRN | 44918 | 44924 | 15105 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 15105 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 15105 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1659 | C | USCSB2212044A |  | UB Box | 44918 | 44924 | 434494 | [6 empty] | Collabratech Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 434494 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 103941 |  | 250721 |  | 32872 | 0 | 46960 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 1660 | C | USCSB2212045A |  | F21P1 MIC foot fixed steel | 44918 | 44924 | 34760 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 0 | 0 | 34760 | 0 | 34760 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1661 | C | USCSB2212046A |  | WWT- DCR-Sulfate analyzer | 44923 | 44943 | 41388.06 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 41388.06 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  | 41388.06 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1662 | C | USCSB2212047A |  | WWT mini line material | 44923 | 44923 | 26056.92 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 21255.49 | 0.81573 | 4801.43 | 0 | 4801.43 | 3825.9882 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 21255.49 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 781.7076 |  |  |  | 781.7076 |  |  |  | 781.7076 |  | 1062.7745 |  | - | 1062.7745 | - | 1700.4392 | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 1663 | C | USCSB2212048A | -01 | Dual-Stage Pressure Regulator | 2022/12/29 2023/3/2 | 2023/1/3 2023/3/3 | 0 | -22552.6 | 22552.6 |  | V |  |  | Matheson Tri-Gac Inc. | PR Approved | PO Approved | Item changes that cannot be added on this PR; need to void this one and create a new PR |  | Yuanyuan Liang |  |  | Rui Ma | Yuanyuan Liang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1664 | C | USCSB2212049A |  | F21P1 MIC CDS Plastic Box | 44924 | 44931 | 178255 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 0 | 0 | 178255 | 0 | 178255 | 178255 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 178255
Base-Build | CCTV | Equipment | USC22C013 | F21P1 QR Lab Security & CCTV | 1665 | C | USCSB2212050A |  | F21P1 CCD_Security&CCTV Package | 44924 | 44948 | 46502.72 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 35915 | 0.77232 | 10587.72 | 0 | 10587.72 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 8185 | 0 |  | 0 | [7 empty] | 27730 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Southland | USC21C005 | F21P1 Chemical & WCCS package | 1666 | C | USCSB2212051A |  | PTFE Lined Pipe - change order | 44924 | 44932 | 402922.04 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 402922 | 1 | 0.04 | 0 | 0.04 | 0 | [26 empty] | 317597 |  | 0 |  |  |  |  | 0 |  |  |  |  | 85325 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1667 | C | USCSB2212052A |  | 12/3C w/ Ground BOYG | 44926 | 44926 | 18929.75 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Chih-Hao Ting | Yi En Wong | [7 empty] | 18929.75 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 18929.75 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1668 | C | USCSB2301001A |  | UPW Copper Connector Bars for MCP | 44930 | 44937 | 856.02 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Chih-Hao Ting | Tiong Sheng Poh | [7 empty] | 856.02 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 856.02 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1669 | C | USCSB2301002A | -01 | Swagelok ASML Project | 44931 | 2023/1/9 2023/2/1 | 44907.78 | 3166.46 | 41741.32 | v | v |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 44907.78 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 41906.33 |  |  |  | 0 | [6 empty] | 3001.45 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1670 | C | USCSB2301003A |  | Armaflex Insulation | 44931 | 44944 | 21413.59 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 21413.59 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 21413.59 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1671 | C | USCSB2301004A |  | Harrington PVC&PVDF MICU F21 TOOL | 44931 | 44937 | 17936.33 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 17936.33 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 17936.33 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1672 | C | USCSB2301005A |  | Teesing - ASML Tool | 44931 | 44937 | 5076 | [6 empty] | Teesing USA, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 3225.6 | 0.63546 | 1850.4 | 0 | 1850.4 | 0 | [28 empty] | 0 |  |  | 3225.6 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1673 | C | USCSB2301006A |  | Harrington PVC&PVDF MICU F21 TOOL NXT | 44931 | 44935 | 10157.5 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 10157.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 10157.5 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1674 | C | USCSB2301007A |  | Harrington PVC&PVDF MICU F21 TOOL XT | 44931 | 44935 | 7478.05 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 7478.05 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 3418.05 | 4060 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C026 | F21P1-0423_H_Unistrut Support Frame_MICU | 1675 | C | USCSB2301008A |  | UPDATED BOM-1 10.26 | 44931 | 44935 | 421832.3 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | USCSB2210027A change order |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 421827.84 | 0.99999 | 4.46 | 0 | 4.46 | 0 | [28 empty] | 0 |  | 413063.79 |  |  | 0 | [6 empty] | 0 | 0 | 8764.05 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1676 | C | USCSB2301009A |  | UPW TempCP-2” HP-PP pipes | 44932 | 44935 | 12401.41 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 12401.41 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 12401.41 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1677 | C | USCSB2301010A |  | UPW-skids cover replacement | 44932 | 44937 | 7051.64 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 7051.64 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 7051.64 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1678 | C | USCSB2301011A |  | Minor Works CCB-MU | 44932 | 44937 | 121205 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  | Rui Ma | Yi En Wong | [7 empty] | 68285.93 | 0.56339 | 52919.07 | 0 | 52919.07 | 30045.8092 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 18180.75 |  |  | 68285.93 | 18180.75 |  |  |  | 18180.75 |  | 10242.8895 |  | - | 10242.8895 | - | 9560.0302 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 1679 | C | USCSB2301012A |  | TW Supporting Piping Materials | 44932 | 44960 | 1492567.83 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 1492567.83 | 0 | 1492567.83 | 1492567.83 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 1492567.83
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1680 | C | USCSB2301013A |  | UPW-MMF-Anthracite procurement | 44933 | 44935 | 7496.5 | [6 empty] | Northern Filter Media, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7496.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 1132.5 |  |  |  | 6364 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1681 | C | USCSB2301014A |  | Mini Line Hardware | 44933 | 44935 | 6368.07 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6368.07 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 6368.07 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1682 | C | USCSB2301016A |  | FRP Tanks samples | 44936 | 44944 | 9000 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6000 | 0.66667 | 3000 | 0 | 3000 | 480 | [28 empty] | 0 |  | 6000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 450 |  |  |  | 900 |  |  |  | 450 |  | 0 |  | - | 0 | - | 0 | 0 | 480
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1683 | C | USCSB2301017A |  | CCB DCR pipe materials | 2023/1/10 2023/2/2 | x | 0 | -13467.49 | 13467.49 | [5 empty] | PR Approved | PO Approved | This PR has been cancelled by PM |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1684 | C | USCSB2301018A |  | ClearPVC shortage | 44936 | 44944 | 10990 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 10990 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 10990 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC22C037 | F21P1 Screen Main tool interconnection | 1685 | C | USCSB2301019A |  | WET Tool Interconnect | 44935 | 44935 | 6080000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6080000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 6080000 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1686 | C | USCSB2301020A |  | ASML Tool Interconnection | 44935 | 44935 | 2520000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1040401 | 0.41286 | 1479599 | 0 | 1479599 | 0 | [28 empty] | 0 |  | 1040401 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1687 | C | USCSB2301021A |  | PDP panel | 44936 | 44945 | 1500000 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1500000 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 686057 | 0 |  |  |  | 813943 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1688 | C | USCSB2301022A |  | CO for WWT CDA cooper tube and fittings | 2023/1/11 2023/12/2 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Purchaser's request: Wrong packaging, please void this PR |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | VEX duct | Material | USC22C038 | MISC_(21417931_522/T0)VEX duct adaptor | 1689 | C | USCSB2301023A |  | VEX SUS adaptor | 44937 | 44948 | 62527.54 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 62527.54 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 62527.54 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1690 | C | USCSB2301024A |  | Flame Arrester | 44937 | 44950 | 51498.43 | [6 empty] | Caltrol Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 51498.43 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 13701.28 |  | 37797.15 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1691 | C | USCSB2301025A |  | CO Sticker Installation | 44937 | 44960 | 109698 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 85788.6 | 0.78204 | 0 | 0 | 0 | 0 | [28 empty] | 85788.6 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3290.94 |  |  |  | 5484.9 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 1692 | C | USCSB2301026A |  | Upsizing conductors | 44937 | 44944 | 105938.22 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 105938.22 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 105938.22 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1693 | C | USCSB2301027A |  | F18P4 Switch Box | 44938 | 44949 | 4562.91 | [6 empty] | Clayton Controls | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 4562.91 | 0 | 4562.91 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 4562.91 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1694 | C | USCSB2301029A |  | Third - Breaker | 44938 | 44944 | 24616 | [6 empty] | Third Enterprise | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 24616 | 1 | 0 | 0 | 0 | 0 | [25 empty] | 24616 |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C037 | F21P1 Screen Main tool interconnection | 1695 | C | USCSB2301030A |  | DIF LA3000U Exhaust material | 44938 | 44948 | 11248.44 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11248.44 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 10123.6 | 0 | [5 empty] | 1124.84 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1696 | C | USCSB2301031A |  | Harrington Pipe | 44939 | 44945 | 71287.6 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 71287.6 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 71287.6 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1697 | C | USCSB2301032A |  | LB2-Area A-ACF media loading | 44939 | 44949 | 112011 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 112011 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 112011 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1698 | C | USCSB2301033A |  | Tank Painting | 44943 | 44948 | 380441.05 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 359334.87 | 0.94452 | 21106.18 | 0 | 21106.18 | 0 | [24 empty] | 189671.16 |  |  |  | 71566.65 |  |  |  |  | 0 |  |  | 74153.19 |  | 23943.87 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1699 | C | USCSB2301034A |  | PP Material - fittings | 44943 | 44959 | 9326 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 9326 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 9326 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | CCE | USC21C008 | F21P1 CCTV & Security | 1700 | C | USCSB2301035A |  | F21P1 Office Secruity CCTV System | 1/18/2023 9/25/2024 | 1/22/2023 10/8/2024 | 777831.12 | -122168.88 | 900000 |  |  |  |  | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  | Rui Ma | Tiong Sheng Poh | [7 empty] | 715880 | 0.92035 | 61951.12 | 0 | 61951.12 | 0 | [26 empty] | 540000 |  | 0 |  | 175880 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1701 | C | USCSB2301036A |  | PSS - Drain system and piping work #2 | 44944 | 44965 | 8858760.4 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8858760.4 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 1167159.59 |  | 4907230.06 | 549357.89 | 0 | 2235012.86 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1702 | C | USCSB2301037A |  | F21P1 PSS WWT system #1 | 44944 | 44959 | 2632901 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2632901 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 2632901 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS | Labor | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 1703 | C | USCSB2301042A | -01 | Tubing hook up for AMHS GEX and PV | 2023/1/10 2024/6/15 | 2023/1/25 2024/6/18 | 0 | -70000 | 70000 |  |  | V |  | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Cancellation of scope as requested by PM | 100% by progress-Net 30 days-After acceptance | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 1704 | C | USCSB2301043A |  | Reducing Assembly | 2023/1/20 2024/6/13 | 2023/2/2 2023/7/4 | 0 | -55756 | 55756 |  |  |  |  | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | R1: As per Martin to cancel the PSS PR. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | temp PVC curtain | Material | USC22C030 | F21_AZCHAD_Hookup_ temp PVC curtain | 1705 | C | USCSB2301044A |  | PVC Curtain for TSMC F21 | 44947 | 44958 | 14000 | [6 empty] | LI YEI Enterprise Co | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 14000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 14000 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | PSS | USC21C005 | F21P1 Chemical & WCCS package | 1706 | C | USCSB2301045A | -01 | PVDFxPVC & PPxPVC Double Contained Drain Scope Per BOQ 82 | 2023/1/20 2023/3/7 | 2023/1/25 2024/3/8 | 373750 | -201250 | 575000 |  |  |  |  | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Amount is adjusted for work completed and final settlement of scope. Scope to be continued by University Mechanical Engineers (UMEC) | 100% by progress-Net 30 days-After acceptance | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 373750 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 86250 | 0 | 143750 |  | 57500 |  |  |  | 86250 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1707 | C | USCSB2301046A |  | WWT WRC Mini Line D75 fitting/ PVC bushing material | 44950 | 2023/1/26 | 2609.62 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2609.62 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 2609.62 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 1708 | C | USCSB2301047A |  | Seismic installation labor service | 44951 | 44966 | 238910 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 73425 | 0.30733 | 165485 | 0 | 165485 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 23891 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3634 | 12725 |  | 0 |  |  |  | 8825 |  | 16150 |  |  |  | 4900 |  |  |  |  | 0 | 3300 | - | 0 | - | 0 | 0
Hookup | Foundation | MIMO/Rigging | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1709 | C | USCSB2301048A |  | 600pcs hallway iron plates for move-in | 44951 | 44967 | 230000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 230000 | 0 | 230000 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Material | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 1710 | C | USCSB2301049A |  | Tubing and fittings materials for AMHS GEX | 44956 | 44958 | 187223.56 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 187223.56 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 163073.63 | 22802.9 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1347.03 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Oil drain pipe work | Material | USC22C009 | F21P1 230kV MTR Oil and Drain Pipe work | 1711 | C | USCSB2301050A |  | Electrical room level gauge | 1/25/2023 9/25/2024 | 1/29/2023 10/8/2024 | 57975 | -19325 | 77300 |  |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 57975 | 1 | 0 | 0 | 0 | 14493.75 | [27 empty] | 38650 | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 19325 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 2898.75 |  | - | 2898.75 | - | 2898.75 | 2898.75 | 2898.75
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1712 | C | USCSB2301051A |  | T1021C handrail replacement | 44953 | 44953 | 1360 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1360 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 1360 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1713 | C | USCSB2301052A |  | Foundation Modification | 44953 | 44964 | 3940 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3940 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 1955 |  | 1955 | 0 |  |  | 30 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C001 | TEL Main Tool Interconnection | 1714 | C | USCSB2301053A |  | KLA interconnect flex hose and duct | 44953 | 44964 | 27957.8 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27957.8 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 27957.8 | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1715 | C | USCSB2301054A |  | Anchor sensor plates | 44953 | 44963 | 7770 | [6 empty] | An-Cor Industrial Plastics, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7770 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 7770 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC22C024 | UIS Scaffolding | 1716 | C | USCSB2301055A |  | Action scaffolding | 44954 | 44957 | 367625.5 | [6 empty] | Action Equip & Scaffold Co. Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 367625.5 | 1 | 0 | 0 | 0 | 0 | [24 empty] | 367625.5 |  |  |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1717 | C | USCSB2301056A |  | Weld Spec inspection | 44954 | 44957 | 12000 | [6 empty] | Weld Spec, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 9496.5 | 0.79138 | 2503.5 | 0 | 2503.5 | 1994.265 | [24 empty] | 8650.5 |  | 846 |  | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 600 |  |  |  | 600 |  | 949.65 |  | - | 1044.615 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1718 | C | USCSB2301058A |  | Lab spectraphotometer | 2023/1/28 2023/10/20 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1Replaced with USCSB2306019 |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 1719 | C | USCSB2301059A |  | Temp CP piping labor | 44954 | 44967 | 85302 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 85302 | 0 | 85302 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 1720 | C | USCSB2301060A |  | VOC Duct / Pipe Lables | 44954 | 44970 | 52049.16 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 52048.77 | 0.99999 | 0.39 | 0 | 0.39 | 0 | [28 empty] | 0 |  |  |  | 28721 | 0 | [6 empty] | 10151 | 0 | 0 | 0 |  | 0 | 0 | 3581 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 9595.77 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Material | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 1721 | C | USCSB2301061A |  | AHMS DP 600 amp ABB | 2023/1/28 2023/2/3 | x | 0 | -1150585 | 1150585 |  |  |  |  | Main Electric Supply Co, LLC | PR Approved | PO Approved | PM Instruction Supplier cannot meet schedule |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1722 | C | USCSB2301062A |  | Gas line VCR connector & fitting | 44957 | 44964 | 14815.62 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 14814.44 | 0.99992 | 1.18 | 0 | 1.18 | 0 | [28 empty] | 0 | 14814.44 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1723 | C | USCSB2301063A |  | ASM tool interconnect semic | 44957 | 44964 | 26380 | [6 empty] | Jeou Fwu Metallic Enterprise Co., LTD | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 26380 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 26380 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1724 | C | USCSB2301064A |  | AMAT Olympia glass fiber insulation | 44957 | 44980 | 28050 | [6 empty] | Astro Thermal Technology Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 28050 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 28050 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 1725 | C | USCSB2301065A |  | ETC E-sensor cable material | 44957 | 44957 | 9000.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9000.09 | 0.99999 | 0.11 | 0 | 0.11 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 818.19 | 8181.9 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | CCE | USC21C003 | F21P1 UPW | 1726 | C | USCSB2302001A |  | X1 Line Temp Power Cable Relocation | 44959 | 44966 | 52780 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 52780 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 52780 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1727 | C | USCSB2302002A | -01 | Camera and access control for Glendale warehouse | 2023/2/2 2023/6/2 | 2023/2/6 2023/6/13 | 58817 | 2000 | 56817 |  |  |  |  | Bay Alarm Company | PR Approved | PO Approved | dding additional $2000 to the CCTV system due to the change order. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 58817 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 8522.55 |  | 0 |  |  |  |  | 48294.45 |  |  | 2000 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1728 | C | USCSB2302003A |  | Camera and access control for Surprise warehouse | 2023/2/2 2023/2/8 | x | 0 | -29200 | 29200 | [5 empty] | PR Approved | PO Approved | Incorrect project code, it should be USC23C001 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1729 | C | USCSB2302004A |  | Teardown and relocation | 44959 | 44963 | 17800 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 17800 | 0 | 17800 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Equipment | USC21C014 | F21P1 WH2SO4 | 1730 | C | USCSB2302005A |  | W-H2SO4 2X4 Center rings - Pure Plastix | 44959 | 44963 | 5527.5 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5527.5 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 1105.5 |  | 0 | 30.15 | 4391.85 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1731 | C | USCSB2302006A |  | Stripper Pad Dike Modification | 44960 | 44972 | 16264 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 15428 | 0.9486 | 836 | 0 | 836 | 771.4 | [28 empty] | 0 |  |  |  |  | 0 | 15428 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 771.4
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1732 | C | USCSB2302007A | -01 | Tool Hookup Material (UPW 23k) | 2023/2/3 2023/3/2 | 2023/2/8 2023/3/3 | 485560.79 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved | Price change |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 485560.79 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 950.3 | 15474.95 | 2956.03 | 43783.97 | 82105.25 |  | 12978.52 | 14840.5 | 97084.75 |  |  | 97738.94 | 0 | 2983.44 | 0 |  | 55766.9 | 40526.9 | 0 | 10063.66 | 0 |  |  | 0 | 0 | 8306.68 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 1733 | C | USCSB2302008A |  | stand alone track blower air duct | 44964 | 44978 | 149904.15 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 149904.03 | 1 | 0.12 | 0 | 0.12 | 0 | [28 empty] | 0 |  |  |  | 89171 | 0 | 45742.63 |  |  |  |  | 14990.4 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 1734 | C | USCSB2302009A |  | EBARA chiller line hose material x 25 set | 44964 | 44965 | 20229.5 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20229.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 18206.55 | 0 | [5 empty] | 2022.95 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 1735 | C | USCSB2302010A |  | DI Max chiller line 20 set (include connector ) | 44964 | 44965 | 57838.09 | [6 empty] | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 57838.09 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 52054.28 | 0 | [5 empty] | 5783.81 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | PSS | USC21C003 | F21P1 UPW | 1736 | C | USCSB2302011A |  | WRC media loading | 44964 | 44980 | 417086.58 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 417086.58 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 417086.58 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1737 | C | USCSB2302012A |  | Chemical enclosures installation | 44964 | 44999 | 138900 | [6 empty] | Scenic Industries, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 138900 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 118065 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 20835 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1738 | C | USCSB2302013A |  | Tanks water test | 44964 | 45033 | 49000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 49000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 49000 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1739 | C | USCSB2302014A |  | 40 pic battery charge | 44964 | 44972 | 9000 | [6 empty] | Gruber Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 9000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 9000 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1740 | C | USCSB2302015A |  | PVC from Harrington | 44965 | 44971 | 9088.5 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 9088.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 9088.5 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS | Equipment | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 1741 | C | USCSB2302016A |  | AMHS Power Panel Construction | 44965 | 44965 | 2253000 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved | To replace Main Electric USCSB2208008A (should be canceled) |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2019000 | 0.89614 | 234000 | 0 | 234000 | 0 | [28 empty] | 0 |  | 606000 |  |  | 0 |  |  | 393470 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 1019530 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1742 | C | USCSB2302017A |  | UPW-Seal pot replacement | 44965 | 44970 | 10383 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10383 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 10383 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C001 | TEL Main Tool Interconnection | 1743 | C | USCSB2302018A |  | Camera and access control for Surprise warehouse | 44965 | 44984 | 29200 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 29200 | 1 | 0 | 0 | 0 | 0 | [27 empty] | 4380 | 0 |  |  |  | 24820 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1744 | C | USCSB2302019A |  | Hander bolt | 44966 | 44988 | 5088.75 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5088.75 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 5088.75 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1745 | C | USCSB2302020A |  | Tank Diamond labels | 2023/2/9 2023/3/1 | x | 0 | -4874.6 | 4874.6 | [5 empty] | PR Approved | PO Approved | Supplier unable to accept payment methods. This will be resubmitted through a distributor of the supplier. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 1746 | C | USCSB2302021A |  | MRT Design- Additional Service amendment | 44967 | 44978 | 47500 | [6 empty] | MRT DESIGN LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 30000 | 0.63158 | 17500 | 0 | 17500 | 0 | [26 empty] | 10000 |  | 5000 |  |  | 5000 | 7500 | 0 |  |  | 2500 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1747 | C | USCSB2302022A |  | CCB-adding material | 44967 | 44978 | 4141.93 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4141.93 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 1678.74 | 2463.19 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1748 | C | USCSB2302023A |  | 600Kits urgent ABglue for foundation | 44967 | 44974 | 91234 | [6 empty] | White Cap, LP | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 91234 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 91234 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1749 | C | USCSB2302024A |  | 1500Kits ABglue for foundation | 44967 | 44974 | 143565 | [6 empty] | White Cap, LP | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 143565 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 54076.15 |  |  | 89488.85 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1750 | C | USCSB2302025A |  | Wet foundation modification | 44967 | 44985 | 18480 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 18480 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 9240 |  |  | 0 |  |  |  | 9240 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1751 | C | USCSB2302026A |  | Barricade material | 44967 | 44972 | 269319.5 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 269319.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 201989.62 | 0 | [6 empty] | 67329.88 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Speed Gate | Material | USC21C008 | F21P1 CCTV & Security | 1752 | C | USCSB2302027A |  | Speed Gate/Turnstile | 2023/2/11 2023/2/11 | 44994 | 10800 | [6 empty] | TUV SUD America, Inc | PR Approved | PO Approved | PR:adding additional scope to this PR |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 10800 | 0 | 10800 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - |  | - | 0 | 0
Base-Build | AMC THC | Material | USC21C013 | F21P1 AMC THC Monitoring System | 1753 | C | USCSB2302028A | -01 | Electrician from Hua Yi | 2023/2/11 2023/12/28 | 2023/4/17 2024/1/1 | 0 | -103000 | 103000 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | Redundant job scope |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1754 | C | USCSB2302029A |  | PVC fittings for 6.5 | 44971 | 45063 | 54673.09 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 53741.24 | 0.98296 | 931.85 | 0 | 931.85 | 1074.8248 | [28 empty] | 0 |  |  |  |  | 0 | 51680.44 |  | 2060.8 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 1074.8248
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1755 | C | USCSB2302030A |  | Spot prime and painting of 30 steel header supports | 44971 | 44985 | 2250 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2250 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 2250 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1756 | C | USCSB2302031A |  | T-130AA/AB Agitator Chemical Coating | 44971 | 44979 | 7013.5 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7013.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 7013.5 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1757 | C | USCSB2302032A |  | Tool Hookup Material (UPW 20k) | 44971 | 44979 | 867838.53 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 867838.53 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 82927.31 | 5775.33 | 29251.83 | 247721.9 |  | 45116.28 |  | 160759.44 |  |  | 226750.52 | 0 | 1819.57 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 67716.35 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1758 | C | USCSB2302033A |  | HK Chemical Bushing | 44971 | 44978 | 94400 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 94400 | 0 | 94400 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1759 | C | USCSB2302034A |  | Office Interiors and Fabrication Clean Room Tenant Improvement | 44971 | 44960 | 158453 | [6 empty] | M. Arthur Gensler Jr. & Associates, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 158453 | 1 | 0 | 0 | 0 | 0 | [26 empty] | 84551 |  | 0 |  | 26480.5 |  | 16895 | 0 |  |  | 23988.17 |  |  |  | 2200 | 0 | 0 | 0 | 4338.33 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1760 | C | USCSB2302035A |  | Hookup EUV Foundation installation | 44973 | 44974 | 375113.92 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | Y | [6 empty] | 280369.67 | 0.74743 | 94744.25 | 0 | 94744.25 | 0 | [28 empty] | 0 |  | 203286 |  | 49047.61 | 0 | 28036.06 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1761 | C | USCSB2302036A |  | Hookup DUV Foundation Installation | 44973 | 44974 | 58406.39 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 40826.56 | 0.69901 | 17579.83 | 0 | 17579.83 | 0 | [28 empty] | 0 |  | 36871 |  |  | 0 | 3955.56 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1762 | C | USCSB2302037A |  | Lam interconnect cable material | 44973 | 45013 | 164269.99 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 164269.98 | 1 | 0.01 | 0 | 0.01 | 0 | [28 empty] | 0 |  |  |  | 150991.17 | 13278.81 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C001 | TEL Main Tool Interconnection | 1763 | C | USCSB2302038A |  | Shelving for tool interconnect | 44974 | 44980 | 88946.51 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 88946.51 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 66709.88 | 22236.63 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Southland | USC21C005 | F21P1 Chemical & WCCS package | 1764 | C | USCSB2302039A |  | M1, M2, H2SO4 Design Change | 44975 | 44981 | 6886 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6886 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 6886 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Southland | USC21C006 | F21P1 Slurry package | 1765 | C | USCSB2302040A |  | Slurry L10 Model Change | 44975 | 44993 | 144491 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 144491 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 144491 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 1766 | C | USCSB2302041A | -01 | L20 VMB Design Change | 2023/2/18 2023/12/12 | 2023/2/22 2024/1/4 | 0 | -109807 | 109807 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | Scope is completed and therefore no requirement |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 1767 | C | USCSB2302042A |  | Labels | 44978 | 44999 | 4268.64 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4264.12 | 0.99894 | 4.52 | 0 | 4.52 | 0 | [28 empty] | 0 |  |  | 2944 |  | 1274.64 | 45.48 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | - |  | -
Base-Build | WWT | Material | USC21C003 | F21P1 UPW | 1768 | C | USCSB2302043A |  | LPS RH materials #1 | 44980 | 44986 | 117147.53 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 117147.53 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 115074.15 |  | 0 |  |  |  | 2001.38 |  | 72 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C003 | F21P1 UPW | 1769 | C | USCSB2302044A |  | LPS RH materials #2 | 44980 | 44986 | 595649.07 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 595649.07 | 1 | 0 | 0 | 0 | 11615.4726 | [28 empty] | 0 |  |  | 59660.15 |  | 0 |  | 188422.24 |  | 79808.76 |  |  | 0 | 0 | 0 | 0 |  | 252882.48 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 14875.44 |  |  | 0 |  | - | 0 | - | 0 | 0 | 11615.4726
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1770 | C | USCSB2302045A |  | Flange fittings | 44980 | 44992 | 73260 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 73260 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 60826.46 |  | 0 | [6 empty] | 12433.54 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1771 | C | USCSB2302046A |  | TSMC F21 Stainless steel plate | 2023/2/23 2023/6/14 | 45001 | 476190 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | Adjusting this PR to align with already issued PO. (PR 509,699.00) |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 476190 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 476190 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1772 | C | USCSB2302047A |  | EMMA Heater Band | 44981 | 44999 | 66000 | [6 empty] | Astro Thermal Technology Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 66000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 66000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1773 | C | USCSB2302048A |  | Mithril Heater Band | 44981 | 44999 | 69910 | [6 empty] | Astro Thermal Technology Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 69910 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 69910 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1774 | C | USCSB2302049A |  | Organo Freight and Forwarding Charges/Expenses | 44981 | 44984 | 2451 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2451 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 2451 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Hot DI | Equipment | USC23C012 | F21P1 Hot DI Machine Hookup | 1775 | C | USCSB2302050A | -01 | Hot DI BOX make | 2/25/2023 2024/5/8 | 3/17/2023 2024/5/15 | 27484.71 | 4995.55 | 22489.16 |  |  |  |  | FusionHPX LLC | PR Approved | PO Approved | R2: As per engineer TJ to update the quote. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 27484.71 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 27484.71 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1776 | C | USCSB2302051A | -01 | Type B and Type E foundations installation | 2023/2/25 2023/4/22 | 2023/3/17 2023/4/27 | 0 | -10650000 | 10650000 |  |  |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | PO cancelled by engineer due to scope change |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1777 | C | USCSB2302052A |  | Type A, Type C and Type D foundations installation | 2023/2/25 2023/4/29 | x | 0 | -12424568 | 12424568 | [5 empty] | PR Approved | PO Approved | Return requested by Martin due to Scope Change |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 1778 | C | USCSB2302053A |  | Crating Service and Delivery | 2023/2/25 2023/4/29 | x | 0 | -2374 | 2374 | [5 empty] | PR Approved | PO Approved | The invoice for this PR has already been paid via APN. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1779 | C | USCSB2302054A |  | Recurring Fee (revised) | 44972 | 44984 | 2200 | [6 empty] | Lee Collins Air Conditioning | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1606.45 | 0.7302 | 593.55 | 0 | 593.55 | 0 | [28 empty] | 0 |  |  |  | 550 | 0 |  |  |  |  | 550 |  | 0 | 0 | 0 | 0 |  | 506.45 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1780 | C | USCSB2302055A |  | New box PP make | 44985 | 44993 | 22070.94 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 22070.94 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 22070.94 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1781 | C | USCSB2302056A |  | PP&M EST 8501 MIC NE Replacement Tube | 44985 | 44993 | 29552.21 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 26883.57 | 0.9097 | 2668.64 | 0 | 2668.64 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  | 26883.57 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 2659.7 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1782 | C | USCSB2302057A |  | Adapters for Circuit Breakers in uis Panel | 44985 | 44992 | 2652 | [6 empty] | LayerZero Power Systems, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2652 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 2652 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 1783 | C | USCSB2302058A |  | UPW B Side Disconnect Switch & Stand | 44985 | 45008 | 76700.22 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 76700.22 | 1 | 0 | 0 | 0 | 7819.82 | [28 empty] | 0 |  | 13963.98 |  | 58648.72 | 0 |  |  | 177.61 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 3909.91 | 3909.91 | - | 0 | 3909.91
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 1784 | C | USCSB2302059A | -01 | 14652 - H10A at X1,7 module clash with square duct | 2023/2/28 2023/12/11 | 2023/3/15 2023/1/4 | 0 | -6080 | 6080 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Work done before turning T&M, Paid in Orginal PO |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 1785 | C | USCSB2302060A | -01 | About Bridge to L20 HPM | 2023/2/28 2023/12/12 | 2023/3/15 2024/1/4 | 0 | -6160 | 6160 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Work done before turning T&M, Paid in Orginal PO |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 1786 | C | USCSB2302061A | -01 | EWO-018 Lorry A,B E. room hanger re-work proposal | 2023/2/28 2023/12/11 | 2023/3/21 2024/1/4 | 0 | -102991 | 102991 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Work done before turning T&M, Paid in Orginal PO |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 1787 | C | USCSB2303001A |  | TSMC F21P1 WRC UPW MCP-21 Temp Feed | 44986 | 44986 | 3280 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3280 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 3280 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1788 | C | USCSB2303002A |  | Tank Diamond Labels | 44986 | 44992 | 4874.6 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4874.6 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 4874.6 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1789 | C | USCSB2303003A |  | Remove and Replace Light Pole Heads | 44986 | 44999 | 5000 | [6 empty] | Graylo Construction, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 5000 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1790 | C | USCSB2303004A |  | Block wall Repair | 44986 | 44999 | 1300 | [6 empty] | Graylo Construction, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1300 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 1300 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1791 | C | USCSB2303005A |  | 2 Clean Room | 44986 | 44988 | 113266.1 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 113266.1 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 35326.28 | 26961.8 | 0 |  | 39651.41 |  |  | 11326.61 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1792 | C | USCSB2303006A |  | 2 Portable Bathrooms | 44986 | 44991 | 3060 | [6 empty] | National Construction Rentals, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 3060 | 0 | 3060 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1793 | C | USCSB2303007A |  | F21P1 CG300 cabinet & e-sensor cable (22AWG/2C, 22AWG/4C) | 44987 | 45001 | 74357.27 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 74357.27 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  | 11259.99 |  |  | 63097.28 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1794 | C | USCSB2303008A |  | LSC cabinet signal cable (22AWG/2C, 22AWG/4C) | 44987 | 45012 | 53403.33 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 53403.33 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 53403.33 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1795 | C | USCSB2303009A |  | F21P1 DIF1 3 layer containmnet pipe and gas line pipe | 44987 | 45005 | 210133 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 210133 | 0 | 210133 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1796 | C | USCSB2303010A |  | F21P1 CVD1 gas line pipe | 44987 | 45005 | 112194 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 112194 | 0 | 112194 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 1797 | C | USCSB2303011A |  | F21P1 ETC pumping and gas line | 44987 | 45005 | 38613 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 38613 | 0 | 38613 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1798 | C | USCSB2303012A |  | 20" stub end | 44987 | 45005 | 27164.13 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 27164.13 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 14879.49 | 0 | 12284.64 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1799 | C | USCSB2303013A |  | CO for Alliance | 44987 | 45001 | 295810 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 295810 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 295810 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1800 | C | USCSB2303014A |  | UPW tank sight glasses and angle stops | 44987 | 45000 | 3344.96 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3344.96 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 3344.96 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | CCE | USC21C003 | F21P1 UPW | 1801 | C | USCSB2303015A |  | UPW system panels installation and linking | 44987 | 45014 | 502320 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 408480 | 0.81319 | 93840 | 0 | 93840 | 0 | [28 empty] | 0 | 257600 | 84640 |  |  | 0 | 5520 | [5 empty] | 12880 | 0 | 47840 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1802 | C | USCSB2303016A |  | Two type waffle slabs | 44988 | 45007 | 146984.87 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 146984.87 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 146984.87 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1803 | C | USCSB2303017A |  | Thick waffle slab | 44988 | 45033 | 78960 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 64580 | 0.81788 | 14380 | 0 | 14380 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 64580 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1804 | C | USCSB2303018A |  | Protection material management | 44988 | 45034 | 274752 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 274752 | 0 | 274752 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1805 | C | USCSB2303019A |  | 10 single barricade | 44988 | 45013 | 15617 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 15617 | 0 | 15617 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1806 | C | USCSB2303020A |  | 2nd EUV foundation | 44988 | 44995 | 375113.92 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 280369.56 | 0.74743 | 94744.36 | 0 | 94744.36 | 0 | [28 empty] | 0 |  |  |  | 252332.6 | 0 | 28036.96 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1807 | C | USCSB2303021A |  | 2nd DUV foundation | 44988 | 44995 | 58406.39 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 40826.56 | 0.69901 | 17579.83 | 0 | 17579.83 | 0 | [28 empty] | 0 |  | 36871 |  |  | 0 | 3955.56 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 1808 | C | USCSB2303022A |  | Dual-Stage Pressure Regulator | 44988 | 44991 | 22552.6 | [6 empty] | Matheson Tri-Gac Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 22552.6 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 22552.6 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1809 | C | USCSB2303023A |  | 8-400A breakers in UIS' panels for CDS and SDS PPBs. | 44988 | 45001 | 33476 | [6 empty] | LayerZero Power Systems, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [5 empty] | Y |  | 33476 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 33476 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | Leak Panel | Material | USC23C013 | Hookup Leak Panel for AZQR&EBO | 1810 | C | USCSB2303024A | -01 | QR Leak Panel | 2023/3/4 2024/5/13 | 2023/4/18 2024/5/13 | 0 | -2112800 | 2112800 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | Descope order |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | Leak Panel | Material | USC23C013 | Hookup Leak Panel for AZQR&EBO | 1811 | C | USCSB2303025A |  | EBO Leak Panel | 44989 | 45034 | 304000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 60800 | 0.2 | 243200 | 0 | 243200 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 60800 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1812 | C | USCSB2303026A |  | F21P1 DIF1 3 VMB cable and ethernet cable | 44992 | 45007 | 18182.84 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 18182.84 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 9750 |  | 8432.84 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1813 | C | USCSB2303027A |  | DIF pliot run machine gas line | 44992 | 44998 | 2580 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2580 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 2580 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 1814 | C | USCSB2303028A |  | QR-lab adaptor | 44992 | 45001 | 1450 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1450 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 1450 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1815 | C | USCSB2303029A |  | Swagelok consume material gasket/nut/gland | 44992 | 45007 | 74449.5 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 74449.5 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 32521 | 29181.5 | 3518 |  | 0 | 2355 | 6874 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1816 | C | USCSB2303030A |  | Build VMB support frame | 44992 | 45007 | 6000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 6000 | 0 | 6000 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1817 | C | USCSB2303031A |  | DIF swagelok SWG connector | 44992 | 45007 | 24723 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 24723 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 20128 |  | 0 | 4595 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 1818 | C | USCSB2303032A |  | 16AWG-3/C 600V Shielded wire | 44993 | 45006 | 13736.09 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 13736.09 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 13736.09 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1819 | C | USCSB2303033A |  | Agitator Chemical Coating | 44993 | 44999 | 45000 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 45000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 27000 |  |  | 0 |  |  |  | 18000 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1820 | C | USCSB2303034A |  | TEM LAB PP 90 Elbows Fittings | 44993 | 45007 | 119.2 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 119.2 | 0 | 119.2 | 119.2 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 17.88 |  |  |  | 17.88 |  |  |  | 17.88 |  | 119.2 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1821 | C | USCSB2303035A |  | Bushings for 6.5 LB2 | 44993 | 45008 | 757.58 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 757.58 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 757.58 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1822 | C | USCSB2303036A |  | UPW Panel Material | 44993 | 45006 | 7238 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7238 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 7238 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1823 | C | USCSB2303037A |  | UPW Panel Material | 44993 | 44999 | 57263.7 | [6 empty] | Service Construction Supply - Division of Darragh Company | PR Approved | PO Approved | Need TSMC Additional PO |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 51051.54 | 0.89152 | 6212.16 | 0 | 6212.16 | 0 | [28 empty] | 0 |  |  |  | 39716.11 | 0 | 11335.43 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1824 | C | USCSB2303038A |  | Low Voltage MCC Special Inspection Testing | 44993 | 44999 | 4420 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4420 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 4420 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1825 | C | USCSB2303039A |  | UPW Pressure indicator | 44994 | 45014 | 859.8 | [6 empty] | Hwa Chi Technology Co., Ltd | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 859.8 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 |  |  |  | 859.8 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1826 | C | USCSB2303040A |  | T140 discharge loop | 44994 | 45091 | 16297.34 | [6 empty] | Mega Union Technology Global Pte Ltd | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16297.34 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 16297.34 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1827 | C | USCSB2303041A |  | UPW Panel Material | 44994 | 45011 | 12682.26 | [6 empty] | Avex-SG Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12682.07 | 0.99999 | 0.19 | 0 | 0.19 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 12682.07 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1828 | C | USCSB2303042A |  | Bolts/Gaskets for 6.5 LB2 | 44994 | 44998 | 976.84 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 976.84 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 976.84 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1829 | C | USCSB2303043A |  | DIF pliot run machine 1/2" gas line | 44994 | 44998 | 1450 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1450 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 1450 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1830 | C | USCSB2303044A |  | Litho Drain Bolts and Gaskets | 44994 | 44998 | 1956.36 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1956.36 | 1 | 0 | 1779817.44 | -1779817.44 | 0 | [28 empty] | 0 |  |  |  | 1956.36 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1831 | C | USCSB2303045A |  | Gaskets | 44995 | 44998 | 856.92 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 856.92 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 856.92 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 1832 | C | USCSB2303046A |  | GF material raise | 44996 | 45029 | 1192357 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1072152 | 0.89919 | 120205 | 0 | 120205 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 1072152 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Outsourcing | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1833 | C | USCSB2303047A |  | Tool Hookup staffing needs | 44999 | 45000 | 1300000 | [6 empty] | Westerwood Global USA Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1092823.97 | 0.84063 | 207176.03 | 0 | 207176.03 | 0 | [28 empty] | 0 |  |  |  | 13031.89 | 47105.98 | 24314.19 | 147319.76 | 184293.85 |  | 147186.03 |  | 0 | 0 | 0 | 0 |  | 529572.27 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C008 | F21P1 CCTV & Security | 1834 | C | USCSB2303048A |  | Sunrise Phoenix housekeeping services | 44999 | 45000 | 101729.26 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 101415 | 0.99691 | 314.26 | 0 | 314.26 | 0 | [28 empty] | 0 | 24240 | 77175 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C008 | F21P1 CCTV & Security | 1835 | C | USCSB2303049A |  | Sunrise Phoenix housekeeping services | 44999 | 45000 | 398270.74 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 368432.5 | 0.92508 | 29838.24 | 0 | 29838.24 | 0 | [28 empty] | 0 | 131365 | 78875 | 158192.5 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C011 | F21 TMAH System | 1836 | C | USCSB2303050A | -01 | F21 General Labor and Housekeeping Service | 2023/3/14 2023/4/17 | 2023/3/15 2023/4/17 | 0 | -300000 | 300000 |  |  |  |  | BHTC Arizona, LLC | PR Approved | PO Approved | BHTC's performance is not good, cancelled and shifted to HuaYi |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 1837 | C | USCSB2303051A |  | TSMC F21P1 WRC UPW Special Inspections | 44999 | 45007 | 1640 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1640 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 820 |  |  |  | 820 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C006 | F21P1 Slurry package | 1838 | C | USCSB2303054A |  | Slurry L10 Model Change | 44999 | 45011 | 287100 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 279960 | 0.97513 | 7140 | 0 | 7140 | 0 | [28 empty] | 0 | 47850 | 38280 |  |  | 0 |  |  |  |  | 133980 |  | 59850 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1839 | C | USCSB2303055A |  | CCB DCR piping | 44999 | 45015 | 224570 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 213342 | 0.95 | 11228 | 0 | 11228 | 10667.1 | [28 empty] | 0 |  |  | 67371 |  | 0 |  | 101057 |  | 44914 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 10667.1
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1840 | C | USCSB2303056A |  | UPW EQ labels | 2023/3/15 2023/4/21 | x | 0 | -10440.67 | 10440.67 | [5 empty] | PR Approved | PO Approved | Order cancelled and replaced with another vendor |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 1841 | C | USCSB2303057A |  | Skid repair & membrane installtion | 45000 | 45035 | 280793 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 280793 | 0 | 280793 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 280793 |  |  |  | 280793 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1842 | C | USCSB2303059A |  | IA copper tubing | 45000 | 45013 | 220244 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 209230 | 0.94999 | 11014 | 4060 | 6954 | 10461.5 | [28 empty] | 0 |  |  |  |  | 0 |  | 88097 |  |  |  | 46251 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 30834 | 0 |  |  | 0 | 0 | 0 |  | 22024 |  |  |  |  | 11012.2 |  |  | 22024 | 11012.2 |  |  |  | 11012.2 |  | 0 |  | - | 0 | - | 0 | 0 | 10461.5
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1843 | C | USCSB2303060A |  | Tanks aeration pipe | 45000 | 45008 | 11900 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11900 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 11900 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 1844 | C | USCSB2303061A |  | UPW MCP-1, 4 Engineering Design | 45000 | 45008 | 3280 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3280 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 3280 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1845 | C | USCSB2303062A |  | One-Line Power REV 1 | 45000 | 45015 | 138326 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 136095 | 0.98387 | 2231 | 0 | 2231 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 122485.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 13609.5 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1846 | C | USCSB2303063A |  | MIC West Wall Power Outlet | 45001 | 45015 | 25254 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25253.84 | 0.99999 | 0.16 | 0 | 0.16 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 5872.84 | 19381 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1847 | C | USCSB2303064A |  | WWT Lab funiture | 2023/3/16 2023/4/12 | x | 0 | -40316.43 | 40316.43 | [5 empty] | PR Approved | PO Approved | To adjust for new items and lower labor cost |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Equipment | USC23C003 | F21P1 Module Tool Interconnection CVD | 1848 | C | USCSB2303065A |  | O3 detector | 45001 | 45029 | 100000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 100000 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 1849 | C | USCSB2303066A |  | TSMC Machine panel fabrication ( cut the hole ) | 45001 | 45012 | 3300 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 3300 | 0 | 3300 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1850 | C | USCSB2303067A |  | QR lab cable tray | 2023/3/16 2023/3/24 | x | 0 | -15058.8 | 15058.8 | [5 empty] | PR Approved | PO Approved | APEX cannot complete this order/Giving the scope to CED |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 1851 | C | USCSB2303068A |  | Add side B slurry box ingredients | 45001 | 45006 | 4438.85 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4438.85 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 4438.85 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1852 | C | USCSB2303069A |  | Bolts/Gaskets | 45001 | 45006 | 756.73 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 756.73 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 756.73 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1853 | C | USCSB2303070A |  | Waterfall Bolts/Gaskets | 45001 | 45006 | 1317.58 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1317.57 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [28 empty] | 0 |  |  |  | 1317.57 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1854 | C | USCSB2303071A |  | Bolts/Gaskets | 45002 | 45008 | 18068.39 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 16095.52 | 0.89081 | 1972.87 | 0 | 1972.87 | 1770.5072 | [28 empty] | 0 | 4256.94 |  |  |  | 0 | 11838.58 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 542.0517 |  |  |  | 542.0517 |  | 804.776 |  | - | 965.7312 | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | USC22C001 | F21 P1 Office and WH Security and CCTV | 1855 | C | USCSB2303073A |  | Security & CCTV Electrical Work | 45002 | 45009 | 927440.77 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved | Replace Galaxy3 USCSB2202003A |  | Yi En Wong |  |  |  | Yi En Wong | Y | [6 empty] | 927440.77 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 110620 | 349396.94 |  | 425210 | 0 |  | 42213.83 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 1856 | C | USCSB2303074A |  | 90 degree PCW welding elbow | 45002 | 45057 | 5122 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 5122 | 0 | 5122 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1857 | C | USCSB2303075A |  | QR/EBO foundation | 45003 | 45013 | 642756.2 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 338859.97 | 0.5272 | 303896.23 | 0 | 303896.23 | 0 | [28 empty] | 0 |  |  |  |  | 0 | 30530.92 |  | 189291.63 |  |  |  | 42743.36 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 8021.9 |  | 0 | 0 | 0 |  | 0 |  | 34136.08 | [5 empty] | 34136.08 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Material | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 1858 | C | USCSB2303076A |  | Fitting and Reducing Union | 45003 | 45007 | 530.28 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 530.28 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [5 empty] | 530.28 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 1859 | C | USCSB2303078A | -01 | AMHS Project Labor - Muratec | 2023/3/21 2024/3/29 | 2023/3/28 2024/4/2 | 15748423.99 | -3775261.34 | 19523685.33 |  |  |  | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | R1: As per BD team Debby, MICU will decrease the amount of lien, $3,775,261.34, from AMHS Murata labor PO and pay the lien . |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8764942.66 | 0.55656 | 6983481.33 | 0 | 6983481.33 | 1181131.8 | [28 empty] | 0 |  |  |  |  | 0 |  | 403134.6 | 659384.8 |  | 974866.6 |  | 0 | 1321505.64 | 0 | 0 | 1202146.64 | 0 | 1199144.06 | 1148633.1 | 1483876.4 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 204729.5 |  |  |  | 944905 |  |  |  | 944905.4 | 5947.5 |  |  | 366303.32 |  | - |  | 1181131.8
Non-TSMC | AMHS | Material | USC23C015 | F21P1 AMHS Wiring Work Outline | 1860 | C | USCSB2303079A |  | AMHS Project Material - MURATA BRANCH CIRCUITS | 45006 | 45006 | 10291428.24 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 10291428.24 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 3878836.8 |  |  |  | 6412591.44 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Site Expense | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 1861 | C | USCSB2303080A |  | UPW Temporary Power | 45006 | 45008 | 153140 | [6 empty] | MMR Constructors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 69046.08 | 0.45087 | 84093.92 | 0 | 84093.92 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 29293.34 | [5 empty] | 39752.74 | [8 empty] | 0 |  | - | 0 | 3634 | 0 | 0
Base-Build | Base-Build | Labor | USC21C011 | F21 TMAH System | 1862 | C | USCSB2303081A |  | Mechanical Inspection | 45006 | 45008 | 12650.88 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12650.88 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 12650.88 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C005 | F21P1 Chemical & WCCS package | 1863 | C | USCSB2303082A |  | UPW Panel design change (FUSE AND BREAKER) | 45007 | 45014 | 375154.38 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 103710.44 | 0.27645 | 271443.94 | 0 | 271443.94 | 0 | [28 empty] | 0 |  | 4801.56 |  |  | 0 | 98908.88 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1864 | C | USCSB2303083A |  | QR lab SWG adaptor | 45007 | 45008 | 1289.86 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1289.86 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 | 1289.86 |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1865 | C | USCSB2303084A |  | KE air duct x19 | 45008 | 45013 | 20005.85 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20005.85 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 20005.85 | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 1866 | C | USCSB2303085A | -01 | Gas cylinders | 2023/3/23 2023/4/14 | 2023/3/30 2023/4/14 | 0 | -19845.6 | 19845.6 |  |  |  | V | Matheson Tri-Gac Inc. | PR Approved | PO Approved | Cancelled because of lead time |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | 200 Plate | Equipment | USC22C006 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 1867 | C | USCSB2303086A |  | 200 Distribution Plates | 45009 | 45016 | 93360 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 93360 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 93360 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1868 | C | USCSB2303087A |  | CDS system Added BOX Items | 45009 | 45028 | 37536 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 37536 | 0 | 37536 | 37536 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 37536
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 1869 | C | USCSB2303088A |  | L20 Unistruts Rack | 45009 | 45016 | 269367 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 269367 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  | 248037 | 0 | 21330 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 1870 | C | USCSB2303089A |  | Chemical Tank Bottom Plate | 45009 | 45016 | 7511 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7511 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  | 7511 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC23C011 | F21P1 AMHS MML Power Design - Muratech | 1871 | C | USCSB2303090A |  | LSW Design for Murata | 45009 | 45016 | 124115 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 113755 | 0.91653 | 10360 | 0 | 10360 | 0 | [28 empty] | 0 |  | 32106.5 |  |  | 0 |  |  |  |  | 3772.5 |  | 0 | 0 | 0 | 0 | 2867 | 0 | 0 | 0 | 0 | 3699 |  |  | 2867 | 0 | 0 |  | 17006 |  | 12785 |  |  |  | 13869 |  |  |  | 11455 |  | 9168 |  |  | 0 |  | 4160 | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1872 | C | USCSB2303091A |  | QR lab cable tray | 45009 | 45013 | 15370.4 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 15370.4 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  | 15370.4 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 1873 | C | USCSB2303092A |  | gas line pipe and manual valve | 2023/3/24 2023/8/1 | x | 0 | -31180 | 31180 | [5 empty] | PR Approved | PO Approved | PR R1:Per purchaser's request, this PR had been replaced with USC2305002, USC2305003 and USC2305004 to cut 50% cost of purchase. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1874 | C | USCSB2303093A |  | Glendale Warehouse Office TI | 3/25/2023 10/4/2024 | 4/18/2023 10/11/2024 | 1742807.08 | -757192.92 | 2500000 |  |  |  |  | Brycon Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1742807.08 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 416473.69 |  | 234316.93 |  | 215063.16 |  | 397639.82 | 0 | 0 | 0 |  | 146315.4 | 3049 | 0 | 215133.54 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 114815.54 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1875 | C | USCSB2303094A |  | HK Chemical PFA Tee | 45013 | 45019 | 4773 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4773 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1670.55 |  |  |  | 0 | 0 | 0 | 0 |  | 3102.45 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1876 | C | USCSB2303095A |  | DG tower pressure gauge | 45013 | 45016 | 73.4 | [6 empty] | Hwa Chi Technology Co., Ltd | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 73.4 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 73.4 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | NUUO | USC21C006 | F21P1 Slurry package | 1877 | C | USCSB2303096A |  | F21P1 Slurry Instrument air | 45013 | 45019 | 336392.16 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 320757.55 | 0.95352 | 15634.61 | 0 | 15634.61 | 0 | [33 empty] | 0 |  |  |  |  | 108705.6 |  | 0 | 0 | 0 | 0 |  | 212051.95 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 15642.24 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1878 | C | USCSB2303097A |  | Prominent backpressure valve | 45013 | 45014 | 453 | [6 empty] | Prominent Fluid Controls (Taiwan) Co. Ltd. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 453 | 1 | 0 | 0 | 0 | 0 | [28 empty] | 453 |  |  |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1879 | C | USCSB2303098A |  | Glendale Warehouse OSC Office Construction | 45014 | 45020 | 22491.13 | [6 empty] | Western Slope Signs and Service LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 22491.12 | 1 | 0.01 | 0 | 0.01 | 0 | [29 empty] | 11245.56 |  |  |  | 0 | [5 empty] | 11245.56 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1880 | C | USCSB2303099A |  | 20% bulk order - rush order | 45015 | 45026 | 161360.62 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 158411.19 | 0.98172 | 2949.43 | 0 | 2949.43 | 3168.2238 | [31 empty] | 53429.32 |  | 0 |  |  | 212.96 | 2011.62 |  |  | 2750.2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 100007.09 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 3168.2238
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1881 | C | USCSB2303100A |  | Litho adding Tee material | 45015 | 45019 | 1861.86 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 1861.86 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1861.86 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1882 | C | USCSB2303101A |  | NFPA labels | 45015 | 45019 | 619.44 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 619.44 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 619.44 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1883 | C | USCSB2303102A |  | Triazole FRP tanks | 2023/3/30 2023/4/22 | x | 0 | -290349.47 | 290349.47 | [5 empty] | PR Approved | PO Approved | Cancelling this PR based on PM's request |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1884 | C | USCSB2303103A |  | WWT SUS CDA TPC port | 45015 | 45023 | 573.84 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 546.78 | 0.95284 | 27.06 | 0 | 27.06 | 27.339 | [33 empty] | 0 |  |  | 546.78 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 27.339
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1885 | C | USCSB2303104A | -01 | UPW Panel design change (Fuse holder) | 2023/3/30 2023/4/8 | 2023/4/3 2023/4/10 | 0 | -41131.38 | 41131.38 |  |  |  |  | Radwell International LLC | PR Approved | PO Approved | UPW Plan C Fuse Holder, TSMC additional PO requested 2023/04/10 Cancelled by TSMC |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC23C014 | F21P1 Labor incentive program-MICU | 1886 | C | USCSB2304001A |  | 2022 holiday incentive (Nov, Dec) | 45017 | 45022 | 651855 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 632823 | 0.9708 | 19032 | 0 | 19032 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 632823 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1887 | C | USCSB2304002A |  | Sump pump/SUS bolt | 45017 | 45020 | 342.3 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 0 | 0 | 342.3 | 0 | 342.3 | 342.3 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 51.345 |  |  |  | 51.345 |  |  |  | 51.345 |  | 342.3 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1888 | C | USCSB2304003A |  | CDS system Added BOX Items | 45017 | 45020 | 2993 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 2257.5 | 0.75426 | 735.5 | 0 | 735.5 | 0 | [32 empty] | 2257.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 735.5 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C011 | F21 TMAH System | 1889 | C | USCSB2304004A |  | MIC MAU Generator | 45017 | 45020 | 84250 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 84250 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 84250 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Labor Incentive | Greenberry | USC23C014 | F21P1 Labor incentive program-MICU | 1890 | C | USCSB2304005A |  | 2022, 2023 holiday incentive (Nov, Dec, Jan) | 45022 | 45042 | 23225 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 23225 | 0 | 23225 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1891 | C | USCSB2304006A |  | HK Chemical PFA Reducer | 45022 | 45033 | 174330.18 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 174330.18 | 0 | 174330.18 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1892 | C | USCSB2304007A |  | (2) Sediment Tank Boxes for Sandblasting Lab | 45022 | 45027 | 11402.54 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 11402.54 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 2280.51 | 0 | [5 empty] | 9122.03 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1893 | C | USCSB2304008A |  | Gasket for WRC mini line | 45022 | 45026 | 136 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 136 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 136 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1894 | C | USCSB2304009A |  | 360 pic battery charge | 45022 | 45033 | 68400 | [6 empty] | Gruber Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 68400 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 45600 |  | 22800 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1895 | C | USCSB2304010A |  | DUV foundation installation | 2023/4/6 2023/5/11 | 45033 | 0 | [7 empty] | PR Approved | PO Approved | There is a change of supplier for this work. This PR needs to be cancelled. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1896 | C | USCSB2304011A |  | EUV foundation Installation | 45022 | 45033 | 437346.32 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 437346.32 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 114180.3 |  |  |  | 258621.82 |  | 0 | 0 | 64544.2 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1897 | C | USCSB2304012A |  | X-B3-EUV foundation installation | 2023/4/6 2023/5/11 | 45041 | 0 | [7 empty] | PR Approved | PO Approved | There is a change of supplier for this work. This PR needs to be cancelled. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1898 | C | USCSB2304013A |  | WWT SUS CDA all A side material (requested by PSS) | 45023 | 45037 | 68009.6 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 66984.15 | 0.98492 | 1025.45 | 0 | 1025.45 | 1339.683 | [33 empty] | 0 |  | 61931.15 | 5053 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 1339.683
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1899 | C | USCSB2304014A |  | WRC Bolt-PSS request (100% paid by Jim) | 45023 | 45030 | 1224.85 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1224.85 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 1224.85 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1900 | C | USCSB2304015A |  | WWT Center rings extra for A+B (total) | 45023 | 45035 | 38334 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 38333.4 | 0.99998 | 0.6 | 0 | 0.6 | 0 | [32 empty] | 11500.11 | 0 |  |  |  | 26833.29 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | MIMO/Rigging | USC21C005 | F21P1 Chemical & WCCS package | 1901 | C | USCSB2304016A |  | Additional Rigging work in the Phase A for UPW scope | 45023 | 45030 | 1400000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | This change order is corresponding to USCSB2202001A |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1400000 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 1000000 | 0 | 400000 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | MIMO/Rigging | USC21C006 | F21P1 Slurry package | 1902 | C | USCSB2304017A |  | Additional Rigging work in the Phase A for Chemical scope | 45023 | 45030 | 1000000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | This change order is corresponding to USCSB2202001A |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 1000000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MIMO/Rigging | USC21C011 | F21 TMAH System | 1903 | C | USCSB2304018A |  | Additional Rigging work in the Phase A for WWT scope | 45023 | 45030 | 800000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | This change order is corresponding to USCSB2202001A |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 800000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 200000 |  | 600000 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1904 | C | USCSB2304019A |  | CCB Box Label | 45023 | 45027 | 337 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 312 | 0.92582 | 25 | 0 | 25 | 21.84 | [32 empty] | 312 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 10.11 |  | 0 |  | - | 0 | - | 0 | 0 | 21.84
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1905 | C | USCSB2304020A |  | PVC Reducers and Elbows | 45026 | 45026 | 2066.73 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2066.73 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2066.73 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1906 | C | USCSB2304021A |  | SST316 EP 1" 90-degree elbows and SST316 1" Tees and 22 of each | 45024 | 45027 | 2502.5 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2502.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2502.5 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 1907 | C | USCSB2304022A |  | TSMC F21P1 AMHS On-Call Support | 45024 | 45026 | 13500 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12300 | 0.91111 | 1200 | 0 | 1200 | 0 | [33 empty] | 0 | 2310 |  | 7560 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2430 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1908 | C | USCSB2304023A |  | Flanges for the Chem Lab connection from L10 to LB2 | 45027 | 45043 | 2259.02 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2259.02 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 1710.68 | 490.74 | 57.6 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1909 | C | USCSB2304025A | -02 | Dock signal light hook up and outlet install | 2023/4/11 2023/5/4 2023/5/12 | 2023/4/20 2023/5/5 2023/5/16 | 5830 | 1300 | 4530 | V |  |  | V | RMJ Electrical Contractors Inc | PR Approved | PO Approved | Camera Power Rate Increase |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2540 | 0.43568 | 3290 | 0 | 3290 | 0 | [33 empty] | 0 |  |  | 2540 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1910 | C | USCSB2304026A |  | Small pipe reinforcement | 45028 | 45043 | 3423.5 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 3423.5 | 0 | 3423.5 | 3765.85 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 513.525 |  |  |  | 513.525 |  |  |  | 513.525 |  | 3423.5 |  | - | 342.35 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1911 | C | USCSB2304027A |  | NFPA labels | 45028 | 45030 | 235.2 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 235.2 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 235.2 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | TMAH | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1912 | C | USCSB2304028A |  | TMAH bolts / Small size bolts | 45029 | 45042 | 8624.85 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8624.6 | 0.99997 | 0.25 | 0 | 0.25 | 0 | [33 empty] | 0 | 3009.2 |  |  |  | 5615.4 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1913 | C | USCSB2304029A |  | Stainless Steel Pipe in Lorry | 45029 | 45047 | 9108.04 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 9108.04 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 9108.04 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 1914 | C | USCSB2304030A |  | MCP-1,4 Special Inspection | 45029 | 45035 | 3575 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3575 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 3575 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1915 | C | USCSB2304031A |  | UPW Bussman 170M6013 Fuse | 45029 | 45033 | 58931 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 58931 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 58931 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1916 | C | USCSB2304032A |  | 780/120 Header Bolts | 45031 | 45034 | 1379.84 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1379.84 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 1379.84 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1917 | C | USCSB2304033A |  | TSMC EMERGENCY TFMB | 45031 | 45124 | 49464.61 | [6 empty] | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 49464.61 | 1 | 0 | 0 | 0 | 0 | [35 empty] | 37830.06 | 8972.12 |  |  |  | 2662.43 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1918 | C | USCSB2304034A |  | T4A-0S-00500-049B0, 1/2" Valex Tube, EP .049 316L 401 10Ra | 45031 | 45037 | 41250 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 41242.5 | 0.99982 | 7.5 | 0 | 7.5 | 0 | [32 empty] | 41242.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1919 | C | USCSB2304035A |  | WWT Activated carbon | 45031 | 45050 | 466583.7 | [6 empty] | Calgon Carbon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 355635.5 | 0.76221 | 110948.2 | 0 | 110948.2 | 116227.265 | [33 empty] | 0 |  |  | 208991.75 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 28206.75 | 0 | 0 |  | 0 |  |  |  |  | 46658.37 |  |  |  | 46658.37 |  |  |  | 46658.37 |  | 23719.85 |  | 118437 | 23719.85 | - | 23719.85 | 23719.85 | 21347.865
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1920 | C | USCSB2304036A |  | Dock seals and lights | 45031 | 45044 | 6875.9 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6875.9 | 1 | 0 | 1681668.84 | -1681668.84 | 0 | [33 empty] | 0 | [6 empty] | 6875.9 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1921 | C | USCSB2304037A |  | WWT Lab Funiture | 45033 | 45033 | 39892.89 | [6 empty] | LabTech Supply Company Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 39892.89 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 7978.58 |  | 31914.31 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 1922 | C | USCSB2304038A |  | Seismic snubber YS-90EA | 45033 | 45043 | 318.7 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 318.7 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 318.7 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C001 | TEL Main Tool Interconnection | 1923 | C | USCSB2304039A |  | Cable ties | 45033 | 45033 | 28000 | [6 empty] | Kai Suh Suh Enterprise Co., LTD. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 28000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 14000 |  | 14000 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1924 | C | USCSB2304040A |  | WWT lab quality analyzer | 2023/4/17 2023/6/14 | x | 0 | -6555 | 6555 | [5 empty] | PR Approved | PO Approved | Cancelling this PR per Kate Wu's request, this item will be added to the quote of another vendor. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1925 | C | USCSB2304041A | -01 | WWT NH4 analyzer | 2023/4/17 2023/6/6 | 2023/5/25 2023/6/7 | 12854.23 | -1016.26 | 13870.49 | V |  |  | V | Winn Marion Barber, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 12854.23 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 12854.23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1926 | C | USCSB2304042A |  | Cubicle Partitions for Tool Team | 2023/4/18 2023/4/28 | x | 0 | -15000 | 15000 | [5 empty] | PR Approved | PO Approved | Change of source of funding from Subcontract budget to USH |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 1927 | C | USCSB2304043A |  | Gas Cylinder | 45034 | 45035 | 18531 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18531 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 9295 | 0 | [5 empty] | 2480 | 0 | 0 | 5706 | 0 |  | 0 | 1050 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 1928 | C | USCSB2304044A |  | Regulator | 45034 | 45035 | 19170 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 19170 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 3220 | 0 | 0 | 6220 | 0 | 9155 | 0 | 575 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC21C011 | F21 TMAH System | 1929 | C | USCSB2304045A |  | F21 General Labor and Housekeeping Service | 45034 | 45037 | 300000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 300000 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 292800 |  | 0 |  | 7200 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1930 | C | USCSB2304046A |  | Small pipe reinforcement | 45035 | 45049 | 418692.97 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 418372.23 | 0.99923 | 320.74 | 0 | 320.74 | 0 | [33 empty] | 0 | 268083.3 |  | 17184.06 |  | 73334.68 |  | 0 | 0 | 574.5 | 0 |  | 1376.32 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 57819.37 |  | 0 | [8 empty] | 12560.7891 |  |  |  | 12560.7891 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1931 | C | USCSB2304047A | -01 | WWT Tanks tags | 2023/4/19 2024/1/10 | 2023/4/21 2023/1/12 | 14878.3 |  |  |  | V |  |  | PostNet of Anthem, LLC | PR Approved | PO Approved | Payment term change from 100% Upon Receipt -Net 30 Days- After Final Acceptance to 20% in Advance - Net 30 Days - After Acceptance. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11361.32 | 0.76362 | 3516.98 | 0 | 3516.98 | 730.3456 | [33 empty] | 0 | [6 empty] | 0 | 0 | 993.98 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 | 5902.71 | 0 |  | 0 |  |  |  |  | 446.349 | 2079.71 |  |  | 743.915 | 152.92 |  |  | 743.915 |  | 0 |  | 2232 | 0 | - | 0 | 0 | 730.3456
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1932 | C | USCSB2304048A |  | UPW Tomoe angle adjuster | 45035 | 45043 | 667 | [6 empty] | Tomoe USA, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 667 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 667 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1933 | C | USCSB2304049A |  | HK UPW PVDF Flare Transition Fittings | 45035 | 45042 | 49206.08 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 49206.08 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 12249.04 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 36957.04 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1934 | C | USCSB2304050A |  | Equalization Line Bolts/Gaskets | 45035 | 45043 | 2393.6 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2372.22 | 0.99107 | 21.38 | 674330 | -674308.62 | 23.7222 | [33 empty] | 0 |  |  |  |  | 2372.22 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 23.7222
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 1935 | C | USCSB2304051A |  | Tanks underlayment | 45035 | 45055 | 49452 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 49452 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 49452 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 1936 | C | USCSB2304053A |  | LOW NOX VOC Burner Change Out & Clean Harbor | 45036 | 45061 | 308247.04 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 308247.04 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 54415 |  | 102998 | 0 | 0 | 0 |  | 0 | 78818 | 9337.14 | 0 | 0 | 3501.41 |  | 0 | 0 | 0 |  | 0 |  | 59177.49 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1937 | C | USCSB2304054A |  | HK Chemical C-PVC-Adaptor | 45036 | 45040 | 19844.7 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | Replace item #1 & #2 in Harrington WO USCSB2210030A |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 19844.7 | 0 | 19844.7 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Greenberry | USC21C014 | F21P1 WH2SO4 | 1938 | C | USCSB2304055A |  | WSR tank Install | 45036 | 45078 | 66708 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 66708 | 0 | 66708 | 66708 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 10006.2 |  |  |  | 10006.2 |  |  |  | 10006.2 |  | 16677 |  | - | 16677 | - | 16677 | 16677 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 1939 | C | USCSB2304056A |  | CDS Additional EQ Relocation | 45036 | 45054 | 25626 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25626 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 25626 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 1940 | C | USCSB2304057A |  | F21P1 CDS-01-FNN Integration | 45036 | 45055 | 11803.71 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 11803.71 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 8853.77 |  |  |  |  | 0 | 0 | 2949.94 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 1941 | C | USCSB2304058A |  | AMHS Project Labor - TSMC | 2023/4/20 2024/8/8 | 2023/4/24 2024/8/8 | 8052087.54 | -3790638.71 | 11842726.25 |  |  |  | V | Commercial Comm and Electric Inc | PR Approved | PO Approved | R1: Adjusting the PR amount to close out this PO per David Short. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7924848.54 | 0.9842 | 127239 | 0 | 127239 | 592136.31 | [33 empty] | 277997.7 |  | 871704.6 | 1711059 |  | 1536686.85 |  | 543152.7 | 0 | 980759.6 | 0 |  | 0 | 647971.6 | 301163.86 | 0 | 0 |  |  | 0 | 0 | 0 |  | 127239 |  |  |  |  | 592136.31 | 927113.63 | [6 empty] | 473709.05 |  |  |  | - |  | - |  | 592136.31
Base-Build | Base-Build | Housekeeping | USC21C012 | F21 Barcode RFID System | 1942 | C | USCSB2304059A | -01 | General labor and Housekeeping Service/Superintendent Service | 2023/4/20 2023/12/28 | 2023/4/25 2023/12/28 | 468465 | -31535 | 500000 | V |  |  |  | Handy Technology Corp. | PR Approved | PO Approved | Scope was completed for final total of $468,465. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 468465 | 1 | 0 | 821322.69 | -821322.69 | 0 | [32 empty] | 268670 | 0 | 199795 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1943 | C | USCSB2304060A |  | Cable pulls for interconnection - KPE601-S | 45037 | 45054 | 371116.2 | [6 empty] | Corbins, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 263946.93 | 0.71122 | 107169.27 | 0 | 107169.27 | 0 | [33 empty] | 0 | [6 empty] | 263946.93 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1944 | C | USCSB2304061A |  | KXME02 Foundation Installation | 45037 | 45051 | 17304.2 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 16438.99 | 0.95 | 865.21 | 0 | 865.21 | 0 | [33 empty] | 0 | [6 empty] | 16438.99 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | MIMO/Rigging | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1945 | C | USCSB2304062A |  | KPE601-S MMI RIGGING AND DELIVERY | 2023/4/22 2023/8/1 | 45054 | 0 | -24500 | 24500 |  |  |  |  | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1946 | C | USCSB2304063A |  | KPE601-S TRIDENT MECHANICAL | 2023/4/22 2023/5/11 | x | 0 | -161673.85 | 161673.85 | [5 empty] | PR Approved | PO Approved | The budget number is incorrect/ Need to recalculate again. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1947 | C | USCSB2304064A |  | KPE601-S STREIMER EXHAUST | 2023/4/22 2024/9/10 | 2023/5/4 2024/9/10 | 12608.5 | -816.14 | 13424.64 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PO R1: Case Closed -- adjust the PO amount to reflect the actual total |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12608.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 6211.88 | 0 | 0 | 0 | 0 |  | 0 | 0 | 6396.62 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1948 | C | USCSB2304065A |  | WWT Lab Drain design-MU | 45038 | 45055 | 226738.04 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 226738.04 | 0 | 226738.04 | 226738.04 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 34010.706 |  |  |  | 34010.706 |  |  |  | 34010.706 |  | 45347.608 |  | - | 45347.608 | - | 45347.608 | 45347.608 | 45347.608
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1949 | C | USCSB2304066A |  | PCI Foundation Installation | 45038 | 45051 | 6831432.84 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3658062.26 | 0.53548 | 3173370.58 | 0 | 3173370.58 | 0 | [33 empty] | 0 |  |  |  | 187742 | 245860.45 |  | 0 | 0 | 0 | 0 | 386468 | 516258 | 0 | 715153 | 221114.15 | 0 |  | 169653.35 | 0 | 0 | 230270.61 |  | 0 |  |  |  | 349498.51 |  | 161796.67 |  |  |  | 52889.1 |  |  |  | 421358.42 | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 1950 | C | USCSB2304067A |  | QR Special Adaptors Harrington | 45038 | 45040 | 253.08 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 253.08 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 16.88 |  | 236.2 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 1951 | C | USCSB2304068A |  | QR LABS Swagelok Adaptors #2 | 45038 | 45040 | 712.56 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 712.56 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 712.56 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1952 | C | USCSB2304069A |  | Change Order for Marketech Fab and Office TI | 45041 | 45047 | 12708.2 | [6 empty] | M. Arthur Gensler Jr. & Associates, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7038.29 | 0.55384 | 5669.91 | 0 | 5669.91 | 0 | [32 empty] | 5200 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 1838.29 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1953 | C | USCSB2304070A | -01 | Starlink installation at TransPak warehouse for OSC | 2023/4/25 2023/05/09 | 2023/4/28 2023/05/10 | 0 | -4761 | 4761 |  | V |  |  | GeoTech Enterprises LLC | PR Approved | PO Approved | Cannot add new item, so cancel this PO to generate a new one |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1954 | C | USCSB2304071A |  | Starlink upgrade at Glendale Warehouse | 45041 | 45044 | 1250 | [6 empty] | GeoTech Enterprises LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1250 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 1250 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1955 | C | USCSB2304072A |  | Sump pipe PVC | 45041 | 45048 | 11591.07 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 11591.07 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 10812.07 | 779 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Triazole | Material | USC22C022 | F21P1 Triazole treatment system | 1956 | C | USCSB2304073A |  | Triazole Poly/PVC material | 45042 | 45051 | 65023.22 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 65023.22 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 30703.79 | 2901.97 |  | 533.63 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 30883.83 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Triazole | Material | USC22C022 | F21P1 Triazole treatment system | 1957 | C | USCSB2304074A |  | Triazole SUS material | 45042 | 45051 | 12154.62 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 12154.62 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 12154.62 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 1958 | C | USCSB2304076A |  | Tamper evident seal/label | 45043 | 45051 | 261 | [6 empty] | HMT System USA LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 261 | 0 | 261 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 1959 | C | USCSB2304077A | -01 | F21P1 Slurry A Electrical/Controls | 2023/4/27 2024/5/14 | 2023/6/5 2024/5/14 | 1299998.2 | -1.8 | 1300000 | V |  |  |  | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | Finalized and closing order |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1299998.2 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 500032.12 | 0 |  |  | 294000 |  | 357504.98 |  | 0 | 0 | 148461.1 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1960 | C | USCSB2304078A |  | WWT Triazole tanks | 45043 | 45054 | 298813.47 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 298813.47 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 298813.47 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1961 | C | USCSB2304079A |  | Cubicles for lobby- Glendale | 45043 | 45048 | 2200 | [6 empty] | TCS Solutions, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2200 | 1 | 0 | 0 | 0 | 0 | [31 empty] | 2200 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 1962 | C | USCSB2304080A |  | ORGANO temp resin | 45044 | 45051 | 71927.12 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 71927.12 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 71927.12 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1963 | C | USCSB2304081A |  | MMI foundation installation | 45044 | 45048 | 7997860 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5524411.6 | 0.69074 | 2473448.4 | 0 | 2473448.4 | 0 | [32 empty] | 1060892 | 0 | 538680 |  | 1199818 |  | 738364 |  | 654718 | 0 | 347879.6 | 0 |  | 0 | 143520 | 0 | 114940 | 0 |  | 19000 | 26500 | 0 | 0 |  | 0 | [9 empty] | 354250 |  |  |  | 325850 | 0 |  | - | 0 | 665635 | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 1964 | C | USCSB2304082A |  | QR HARRINGTON ICPMS PIPING | 45044 | 45047 | 486 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 486 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 486 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 1965 | C | USCSB2304083A |  | QR SWAGELOK ICPMS PIPING CONX | 2023/4/28 2023/5/16 | 45047 | 349.44 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | PR-R1:The quantity changed from 7 sets to 14 sets |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 349.44 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 349.44 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 1966 | C | USCSB2304083B |  | QR SWAGELOK ICPMS PIPING CONX | 45044 | 45302 | 349.44 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 349.44 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 0 | 0 | 349.44 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | 光阻櫃 | Labor | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 1967 | C | USCSB2304084A |  | F21 Transportation | 45044 | 45061 | 60470 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 54423 | 0.9 | 6047 | 0 | 6047 | 0 | [33 empty] | 0 |  |  | 24188 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 24228.5 |  |  |  |  | 0 |  | 6006.5 | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 1968 | C | USCSB2304085A |  | Control wire for VOC 2 & 3 | 45045 | 45048 | 7939.06 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7939.06 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 7939.06 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1969 | C | USCSB2305001A |  | EBO UPW DP Parts | 45048 | 45143 | 28724.82 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 28724.81 | 1 | 0.01 | 0 | 0.01 | 0 | [33 empty] | 0 |  |  |  | 2624.84 |  |  | 24111.01 | 0 | 1988.96 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1970 | C | USCSB2305002A |  | WWT material for drain & system | 45048 | 45058 | 31941.1 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31941.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 25784.8 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 638.822 |  |  | 6156.3 | 958.233 |  |  |  | 1597.055 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 1971 | C | USCSB2305003A |  | Greenberry Foundation Installation | 45048 | 45050 | 7782795 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4735129.56 | 0.60841 | 3047665.44 | 0 | 3047665.44 | 0 | [33 empty] | 0 | 532343.19 | [5 empty] | 576705.1 | 1926995.07 | 391389.99 | 0 |  | 0 | 0 | 0 | 3795.91 | 468696.91 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 245021.72 |  |  |  |  | 0 | 314785.73 | 275395.94 | 0 | - | 0 | 0
Interconnection | Interconnection | Site Expense | USC22C037 | F21P1 Screen Main tool interconnection | 1972 | C | USCSB2305004A |  | ESD Jumpsuit with Hood | 45048 | 45048 | 3300 | [6 empty] | Super Starnix SDN BHD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3300 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 3300 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection |  | USC23C036 | F21P1 AMAT Interconnection | 1973 | C | USCSB2305005A |  | AMAT Interconnect Mechanical | 2023/5/3 2023/6/10 | x | 0 | -208944 | 208944 | [5 empty] | PR Approved | PO Approved | Cancelled to substitute with another contractor and same work scope. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1974 | C | USCSB2305006A |  | KPE602-S Trident | 2023/5/3 2023/5/4 2023/5/11 2023/5/25 | x | 0 | -161673.85 | 161673.85 | [5 empty] | PR Approved | PO Approved | R3:Budget isn't correct/ Need to be revised. R2:VOID PR Request USCSB2305006per Scott Weary. Budget numbers are being corrected to be correct. R1:Adjustment due to Tool KPE601-1 &Tool KPE602-2S are the same. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1975 | C | USCSB2305007A |  | KPE602-S MMI Industrial & Steel | 45049 | 45054 | 24500 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2937 | 0.11988 | 21563 | 0 | 21563 | 0 | [33 empty] | 0 | [6 empty] | 2937 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1976 | C | USCSB2305008A |  | EUV interconnect cable tie | 2023/5/3 2023/8/1 | x | 0 | -9050 | 9050 | [5 empty] | PR Approved | PO Approved | PR R1:Supply is purchased online |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 1977 | C | USCSB2305009A |  | TSMC AZ F21 DI MAX | 45049 | 2023/5/6 2023/6/17 | 0 | -94680 | 94680 |  |  |  |  | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved | R1:Vendor formed a US-based company and requested for new entity to be trading counterparty |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 1978 | C | USCSB2305009B |  | TSMC AZ F21 DI MAX | 45049 | 2023/5/11 2023/6/16 | 94680 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 94680 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 85212 | 0 | 0 | 0 | 0 |  | 0 | 0 | 9468 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1979 | C | USCSB2305010A |  | Lighting for warehouse | 45049 | 45063 | 64375.51 | [6 empty] | Red Mountain Lighting | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 64375.51 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 9656.32 | 0 | [5 empty] | 54719.19 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 1980 | C | USCSB2305011A |  | AMAT Interconnect Electrical | 45049 | 45051 | 400656 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 400656 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 6428.72 |  | 19189.36 | 0 | 8782.95 | 0 | 7538.05 | 0 | 0 | 45452.84 | 29147.14 | 0 | 22935.81 |  | 0 | 0 | 132563.97 |  | 128617.16 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 1981 | C | USCSB2305012A |  | PSS 11M CO 1/4 batch | 45049 | 45054 | 1000000 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Lorry Support Installation (14.1) & Lorry Pipe Material+Installation (14.2) & Mobilization (18.2) & RFI additional material (18.3) |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 1000000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C006 | F21P1 Slurry package | 1982 | C | USCSB2305013A |  | PSS 11M CO 2/4 batch | 45049 | 45054 | 2000000 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | Package 3 A side-4.08, 4.11, 4.14 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 2000000 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C011 | F21 TMAH System | 1983 | C | USCSB2305014A |  | PSS 11M CO 3/4 batch | 45049 | 45054 | 4000000 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | WWT Package 3 A side-4.02, 4.03, 4.04, 4.06, 4.07, 4.09, 4.10, 4.12, 4.13, 4.15 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 3000000 |  |  | 0 | [6 empty] | 1000000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | PSS | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 1984 | C | USCSB2305015A |  | PSS 11M CO 4/4 batch | 45049 | 45054 | 4000000 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | WWT Package 3 A side: 4.01, 4.16, 4.17 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4000000 | 1 | 0 | 0 | 0 | 0 | [30 empty] | 4000000 |  |  | 0 | [7 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1985 | C | USCSB2305016A |  | KPE602-S Streimers | 2023/5/4 2023/5/11 2024/9/9 | 2023/10/17 2024/9/17 | 12830.19 | -3244.05 | 16074.24 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | R1:Scott Weary increased amount due to revaluation of budget numbers. PO R1: Case Closed -- adjust the PO amount to reflect the actual total. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12830.19 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 12830.19 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1986 | C | USCSB2305018A |  | Outlets for overflow warehouse | 45050 | 45056 | 2095 | [6 empty] | RMJ Electrical Contractors Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2095 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 2095 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C001 | TEL Main Tool Interconnection | 1987 | C | USCSB2305020A |  | KPOCT3 LIT 3 Hua Yi | 45051 | 45055 | 36400 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36400 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 34580 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 1820 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C001 | TEL Main Tool Interconnection | 1988 | C | USCSB2305021A |  | KPOCT3 LIT 3 UMEC | 45051 | 45055 | 29227.2 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 29227 | 0.99999 | 0.2 | 0 | 0.2 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 29227 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C001 | TEL Main Tool Interconnection | 1989 | C | USCSB2305022A |  | KPOCT3 LIT3 MMI | 45051 | 45055 | 6240 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 6240 | 0 | 6240 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C001 | TEL Main Tool Interconnection | 1990 | C | USCSB2305023A |  | KPOCT3 LIT 3 Streimers | 2023/5/5 2024/9/9 | 2023/10/17 2024/9/17 | 29187.07 | -4627.83 | 33814.9 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PO R1: Case Closed -- adjust the PO amount to reflect the actual total |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 29187.07 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 29187.07 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1991 | C | USCSB2305024A |  | Glendale Office West Side - Alarm and Surveillance | 45051 | 45054 | 7350 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7350 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 1102.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 6247.5 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 1992 | C | USCSB2305025A |  | Glendale Office West Side - Alarm and Surveillance | 45051 | 45054 | 3550 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3550 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 532.5 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 3017.5 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 1993 | C | USCSB2305026A |  | Fiber Splicing | 45052 | 45061 | 2756 | [6 empty] | Cannon & Wendt Electric | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2756 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 2756 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 1994 | C | USCSB2305027A | -01 | QR Lab UPW DP Material | 2023/5/6 2023/5/17 | 2023/5/15 2023/5/19 | 102810.49 | -90282.21 | 193092.7 |  |  | V |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | There was a decrease in the quantity required by TSMC |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 102810.49 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 91386.79 |  |  | 1925.6 | 0 | 0 | 0 |  | 0 | 9498.1 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C001 | TEL Main Tool Interconnection | 1995 | C | USCSB2305028A |  | Electrical cable routing labor | 45052 | 45078 | 39000 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 39000 | 17463.18 | 21536.82 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C029 | EBO21- Tool interconnection | 1996 | C | USCSB2305029A |  | EBO-SUSS-ZASC5-Gas System 1/4" Valex Tube | 45052 | 45055 | 450 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 450 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 450 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 1997 | C | USCSB2305030A |  | UPW CO-PVDF0025 clash | 45056 | 45057 | 32388 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 32388 | 0 | 32388 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 1998 | C | USCSB2305031A |  | QR - NPT to NW/KF flange | 45056 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 1999 | C | USCSB2305032A |  | KPAE01-S LIT 1 MMI | 45056 | 45159 | 1232.5 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1232.5 | 1 | 0 | 26914.26 | -26914.26 | 0 | [33 empty] | 0 | [6 empty] | 1232.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2000 | C | USCSB2305033A |  | KPAP01 S LIT 1 MMI | 45056 | 45159 | 1232.5 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1232.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 1232.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C025 | F21P1 Lam Interconnection | 2001 | C | USCSB2305034A |  | Wire lugs/Terminals | 45056 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2002 | C | USCSB2305035A |  | Shermco Special Inspection | 45056 | 45061 | 20000 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved | This is an open PO |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18895 | 0.94475 | 1105 | 0 | 1105 | 0 | [33 empty] | 1950 |  | 8700 |  | 8245 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2003 | C | USCSB2305036A |  | 20" EP+PTFE gaskets | 45056 | 45061 | 8948 | [6 empty] | Yingsheng Applied Materials Co., Ltd | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8762 | 0.97921 | 186 | 0 | 186 | 175.24 | [33 empty] | 0 | [6 empty] | 8593.18 | 0 | 168.82 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 175.24
Interconnection | Interconnection | Equipment | USC23C029 | EBO21- Tool interconnection | 2004 | C | USCSB2305037A |  | Armaflex 3/8 x 1/2 | 45057 | 45071 | 846 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 846 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 846 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2005 | C | USCSB2305038A | -01 | 3/8" HT PVC Pressure hose (8M) | 45057 | 2023/5/16 2023/6/17 | 0 | -414 | 414 |  |  |  |  | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved | Vendor requested change to a US subsidiary for US transactions. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2006 | C | USCSB2305038B |  | 3/8" HT PVC Pressure hose (8M) | 45057 | 2023/5/15 2023/6/16 | 414 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 414 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 372.6 | 0 | 0 | 0 | 0 |  | 0 | 0 | 41.4 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2007 | C | USCSB2305039A |  | Armaflex 7/8 x1/2 | 45057 | 45070 | 0 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2008 | C | USCSB2305039B |  | Armaflex 7/8 x1/2 | 45057 | 45071 | 778.26 | [6 empty] | Bay Insulation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 778.26 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 778.26 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2009 | C | USCSB2305040A |  | EBO-ZFP3 | 45057 | 45068 | 4362.14 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4362.14 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 4362.14 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical Lab | MIMO/Rigging | USC22C021 | F21P1 Chemical Lab setup | 2010 | C | USCSB2305041A |  | GC Lab Move-in | 45057 | 45068 | 18220 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 18220 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 18220 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2011 | C | USCSB2305042A |  | KPE601-S LIT 2 MMI | 45057 | 45159 | 11042 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8105 | 0.73402 | 2937 | 0 | 2937 | 0 | [33 empty] | 0 | [6 empty] | 8105 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C037 | F21P1 Screen Main tool interconnection | 2012 | C | USCSB2305043A |  | Electric Interconnection | 45057 | 45083 | 11520 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 11520 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 11520 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C037 | F21P1 Screen Main tool interconnection | 2013 | C | USCSB2305044A | -01 | Mechanical Interconnect | 45057 | 45099 | 48283.4 | 0 | 48283.4 |  |  |  |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | Better payment terms |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 48283.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 6071.76 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 42211.64 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Scaffolding | USC21C007 | F21P1 VOC package （Installation ) | 2014 | C | USCSB2305045A |  | Scaffold for WWT | 45057 | 45078 | 10428 | [6 empty] | BrandSafway Solutions, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10428 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 10428 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2015 | C | USCSB2305046A |  | ORGANO isolation valves | 45057 | 45061 | 342.13 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 342.13 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 342.13 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2016 | C | USCSB2305047A |  | Stainless Steel Pipe in Lorry | 45057 | 45061 | 1820.62 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1820.62 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 1820.62 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | MIMO/Rigging | USC21C003 | F21P1 UPW | 2017 | C | USCSB2305048A |  | MMI temp resin move-in | 45057 | 45069 | 5300 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5300 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 3180 |  |  |  | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2018 | C | USCSB2305049A |  | KPE601 S LIT 2 TRIDENT- TIME AND MATERIAL | 45057 | 45069 | 470099.35 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 470099.35 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 369338.46 | 0 |  |  | 100760.89 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | MA-TEK | Labor | USC23C037 | MA-TEK AZ Lab Project | 2019 | C | USCSB2305050A |  | Design Build for MA-TEK | 45058 | 45063 | 227190 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 199494 | 0.87809 | 27696 | 0 | 27696 | 0 | [33 empty] | 0 | 53688 |  | 53688 |  | 84249 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 7869 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2020 | C | USCSB2305051A |  | KPAP01-S LIT 1 UMEC | 2023/5/12 2024/9/9 | 2023/5/17 2024/9/17 | 0 | -87904.5 | 87904.5 | V |  |  |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | PO R1: Case Closed. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2021 | C | USCSB2305054A |  | Starlink installation at TransPak warehouse for OSC | 45058 | 45061 | 6801 | [6 empty] | GeoTech Enterprises LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6801 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 6801 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2022 | C | USCSB2305055A |  | KPAP01-S LIT 1 Hua Yi | 45058 | 45068 | 62400 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 62400 | 0 | 62400 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2023 | C | USCSB2305056A |  | KPAP01-S LIT 1 STREIMERS | 2023/5/12 2024/9/9 | 2023/7/21 2024/9/17 | 37455.11 | -29238.09 | 66693.2 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PO R1: Case Closed -- adjust the PO amount to reflect the actual total |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 37455.11 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 37455.11 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 2024 | C | USCSB2305058A |  | FAB Grounding | 45059 | 45091 | 349263.68 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 331800.5 | 0.95 | 17463.18 | 0 | 17463.18 | 174631.84 | [33 empty] | 0 |  |  | 174631.84 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 87315.92 | 157168.66 | 87315.92 |  | - | 0 | - | 87315.92 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 2025 | C | USCSB2305059A |  | WRC Grounding | 45059 | 45091 | 200218.1 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 200218.1 | 1 | 0 | 0 | 0 | 20021.8 | [33 empty] | 0 |  |  | 190207.2 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 10010.9 | [8 empty] | 0 |  | - | 10010.9 | - | 0 | 10010.9
Non-TSMC | Heating Jacket | Material | USC23C035 | TSMC F21 Heating Jacket Installation | 2026 | C | USCSB2305060A | -01 | Heating Jacket | 2023/5/13 2024/2/16 | 2023/8/4 2024/2/17 | 15598.88 | -2834401.12 | 2850000 |  |  | V | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | Descope and to be replaced by Kinpo Order for the same scope |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 15598.88 | 0 | 15598.88 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2027 | C | USCSB2305061A |  | 2nd batch Waffle covers | 45059 | 45069 | 174742 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 174742 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 174742 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2028 | C | USCSB2305062A |  | 3rd, 4th X-B3-EUV and DUV foundation installation | 45059 | 45064 | 550898.8 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 217179.5 | 0.39423 | 333719.3 | 0 | 333719.3 | 0 | [33 empty] | 0 | [6 empty] | 217179.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2029 | C | USCSB2305063A |  | 27 single barricades | 45059 | 45069 | 33102 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 33102 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 33102 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | NUUO | USC21C007 | F21P1 VOC package （Installation ) | 2030 | C | USCSB2305064A |  | F21 VOC Low nox Electrical Work | 2023/5/13 2024/8/1 | 2023/5/23 2024/8/1 | 271432.4 | -16567.6 | 288000 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | R1: Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 271432.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 173036 | 87861.4 |  |  | 0 | 0 | 0 | 0 | 10535 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 2160 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2031 | C | USCSB2305065A |  | Preventive Maintenance on dock doors | 5/16/2023 8/19/2024 | 5/19/2023 8/24/2024 | 2132 | -636 | 2768 |  |  |  |  | Raymond West Intralogistics Solutions | PR Approved | PO Approved | R1: The amount has been adjusted from $2,768 to $2,132 due to the expiration of the contract period. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2132 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 186 |  | 319 | 0 | 0 | 346 | 454 | 0 | 0 | 0 | 0 | 0 |  | 27 | 0 | 0 | 0 |  | 0 |  | 454 |  |  |  | 346 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2032 | C | USCSB2305066A |  | 9 type B foundations from MMI to Greenberry | 45062 | 45076 | 129675.6 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 123191.82 | 0.95 | 6483.78 | 0 | 6483.78 | 0 | [33 empty] | 0 | [6 empty] | 123191.82 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2033 | C | USCSB2305067A |  | Stripper Platform and F21P1 FRP Works | 45062 | 45083 | 490292.57 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 490292.57 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 235372.57 | 73543.8855 |  |  | 254920 | 73543.8855 |  |  |  | 73543.8855 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2034 | C | USCSB2305068A |  | UPW pipe pressure test nitrogen | 45062 | 45065 | 3348.64 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3348.64 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 1330.88 | 612.52 | 888.76 | 273.18 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 243.3 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2035 | C | USCSB2305069A |  | TSMC F21P1 Items | 45062 | 45069 | 3355 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 0 | 0 | 3355 | 0 | 3355 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2036 | C | USCSB2305070A |  | TSMC F21 Solvent room vent | 45062 | 45097 | 161517.16 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 112072.33 | 0.69387 | 49444.83 | 0 | 49444.83 | 161517.16 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 112072.33 | - | 0 | - | 0 | 161517.16
Base-Build | CCTV | Labor | USC22C001 | F21 P1 Office and WH Security and CCTV | 2037 | C | USCSB2305071A |  | TSMC F21P1 Site Security Electronics Permit Assistance | 45062 | 45065 | 135180 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 135180 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 5260 |  |  |  | 118382.5 |  | 0 | 0 | 7975 | 3562.5 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2038 | C | USCSB2305072A |  | QR - NPT to NW/KF flange | 2023/5/16 2023/6/15 | x | 0 | -1258.11 | 1258.11 | [5 empty] | PR Approved | PO Approved | Identical to USCSB2305031 |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2039 | C | USCSB2305073A |  | QR - 6mm & 8mm PFA Tubing | 45062 | 45063 | 970.32 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 970.32 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 970.32 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2040 | C | USCSB2305075A |  | UPW skids cover replacement | 45063 | 45065 | 975.1 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 975.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 975.1 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2041 | C | USCSB2305076A |  | WWT Tanks hydrotest | 5/17/2023 8/17/2024 | 6/6/2023 8/24/2024 | 9900 | -89100 | 99000 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: As per Jim to closeout the PO. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9900 | 1 | 0 | 0 | 0 | 792 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 14850 | 9900 |  |  | 14850 |  |  |  | 14850 |  | 0 |  | - | 0 | - | 0 | 0 | 792
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2042 | C | USCSB2305077A |  | UPW AGRU check valves | 45063 | 45065 | 544.38 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 544.38 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 544.38 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C007 | F21P1 VOC package （Installation ) | 2043 | C | USCSB2305078A |  | BHTC housekeeping | 45063 | 45077 | 26070.88 | [6 empty] | BHTC Arizona, LLC | PR Approved | PO Approved | Extension for USCSB2211009A for paying final invoice |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 26070.88 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 26070.88 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C005 | F21P1 Chemical & WCCS package | 2044 | C | USCSB2305079A |  | BHTC housekeeping | 45063 | 45077 | 53099.12 | [6 empty] | BHTC Arizona, LLC | PR Approved | PO Approved | Extension for USCSB2211009A for paying final invoice |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 53099.12 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 53099.12 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Rosendin | USC21C006 | F21P1 Slurry package | 2045 | C | USCSB2305080A |  | CDS Solvent Room Conduit & Updated Cable Tray/Supports Constructible BIM Model | 45063 | 45079 | 590648 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 590648 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 389547.79 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 201100.21 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2046 | C | USCSB2305081A |  | Modify CDS DHL EQ caster wheels | 45064 | 45071 | 18824 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 18824 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 18824 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2047 | C | USCSB2305082A | -01 | Lorry B RM 16 high zone clear PVC re-work due to clash with AAS duct main | 2023/5/19 2023/12/11 | 2023/5/24 2023/12/29 | 0 | -7920 | 7920 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2048 | C | USCSB2305083A | -01 | Lorry A & B sump pit piping re-work due to concrete pit elevation issue | 2023/5/19 2023/12/11 | 2023/6/2 2023/12/29 | 0 | -13032 | 13032 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2049 | C | USCSB2305084A | -01 | LB2 NaOH system cpvc damage | 2023/5/19 2023/12/11 | 2023/5/24 2023/12/29 | 0 | -5520 | 5520 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2050 | C | USCSB2305085A | -01 | Lorry B Room 40 Sump Pump missing PVDF spool to sump pit | 2023/5/19 2023/12/11 | 2023/5/24 2023/12/29 | 0 | -1187 | 1187 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2051 | C | USCSB2305086A | -01 | Bridge pull box removal request by MIC | 2023/5/19 2023/12/11 | 2023/5/24 2023/12/29 | 0 | -3510 | 3510 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2052 | C | USCSB2305087A | -01 | 4mm PFA Pulls | 2023/5/19 2023/12/11 | 2023/6/20 2023/12/29 | 0 | -35407 | 35407 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2053 | C | USCSB2305088A |  | MIC F21 Commission Requirements-Swagelok | 45065 | 45077 | 14045.1 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 14045.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 11599.1 | 2446 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2054 | C | USCSB2305089A |  | EW NEW BOX ADD | 45065 | 45077 | 3325.52 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3325.52 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 3325.52 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2055 | C | USCSB2305090A | -01 | F21P1-U-CDS-LB2-MIC-HARDER-R6 | 45065 | 2023/6/2 2023/12/29 | 0 | -5520 | 5520 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2056 | C | USCSB2305091A | -01 | Tunnel to Lorry transition Pipe Routing Design Change | 45065 | 2023/6/2 2023/12/29 | 0 | -8280 | 8280 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2057 | C | USCSB2305092A |  | TSMC EMERGENCY TFMB #2 | 45065 | 45124 | 53862.4 | [6 empty] | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 49010.75 | 0.90993 | 4851.65 | 0 | 4851.65 | 0 | [35 empty] | 25059.38 | 15484.18 |  |  |  | 5824.93 | 2642.26 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC22C036 | F21P1 ASML NXE3600/Yieldstar/NXT/XT Main tool interconnection | 2058 | C | USCSB2305093A | -01 | KPE601-S LIT 2 Streimers Exhaust-Revised Labor Pricing | 45066 | 2023/9/19 2023/9/22 | 0 | -21245.1 | 21245.1 |  |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | R1:PO USC23B002 Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Housekeeping | USC21C005 | F21P1 Chemical & WCCS package | 2059 | C | USCSB2305094A |  | Detail Clean | 45066 | 45289 | 600000 | [6 empty] | SD Engineering Technology LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 477767.25 | 0.79628 | 122232.75 | 0 | 122232.75 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 131437.5 | 0 | 0 |  |  | 63156.25 | 0 | 87343.75 |  | 0 |  | 63281.25 | [11 empty] | 85668.5 | 0 |  | 46880 | 0 | 120093.75 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2060 | C | USCSB2305095A |  | Eaton Broken | 45066 | 45070 | 935.14 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 935.14 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 935.14 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2061 | C | USCSB2305096A |  | UPW test pump | 45066 | 45079 | 1836 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1836 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 1836 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2062 | C | USCSB2305097A |  | UPW T1035B ladder | 45066 | 45079 | 4400 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4400 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 4400 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2063 | C | USCSB2305098A |  | UPW sight glass | 45066 | 45079 | 1224.7 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1224.7 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 1224.7 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 2064 | C | USCSB2305099A | -02 | FAB A PVDF | 2023/5/20 2023/6/13 | 2023/5/30 2023/6/27 2023/7/4 | 74708.31 | -79927.69 | 154636 | V |  |  |  | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R2:The trade terms should be FOB R1:Adjusting the amount based on the new quotation. (USD 134,608.66+119.2-60,019.55(PO USCSB2306042) ) |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 71476.47 | 0.95674 | 3231.84 | 0 | 3231.84 | 2859.0588 | [33 empty] | 0 |  | 18373.53 | 50456.44 |  |  |  | 0 | 2096.5 | 0 | 0 |  | 550 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 2859.0588
Base-Build | Base-Build | Housekeeping | USC23C040 | TSMC F21 Clean Room Suit | 2065 | C | USCSB2305100A |  | Industrial Coverall with Hood | 45069 | 45070 | 23981.12 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 23981.12 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 23981.12 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC23C040 | TSMC F21 Clean Room Suit | 2066 | C | USCSB2305101A | -01 | Open PO for Clean Room Suits | 2023/5/23 2023/8/2 | 2023/5/24 2023/8/9 | 115269.06 | -184730.94 | 300000 |  |  |  | V | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved | Open PO for disposable cleanroom jumsuits; 10500 pcs every other week and additional requests |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 115269.06 | 1 | 0 | 0 | 0 | 0 | [32 empty] | 11954.6 | 83282.01 | 20032.45 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C008 | F21P1 Module Tool Interconnection LIT2-3 | 2067 | C | USCSB2305102A |  | KPE602-S EUV_ASML_NXE3600D | 45069 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2068 | C | USCSB2305103A |  | UPW CO-Distribution | 45070 | 45076 | 131403 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 131403 | 0 | 131403 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 131403 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C006 | F21P1 Module Tool Interconnection EPI | 2069 | C | USCSB2305108A | -01 | Swagelok for AMAT EPI | 2023/5/24 2024/6/11 | 2023/5/30 2024/6/11 | 4906.98 | -23498.25 | 28405.23 |  | V |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | Lower final order amount due to partial cancellation of items from total order. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4906.98 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 4906.98 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Material | USC21C014 | F21P1 WH2SO4 | 2070 | C | USCSB2305109A |  | Hardware for Dosing Boxes | 45070 | 45071 | 339.73 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 339.73 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 339.73 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | EDG | Labor | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 2071 | C | USCSB2305110A |  | LSW Change Orders | 45072 | 45078 | 22570 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 16570 | 0.73416 | 6000 | 0 | 6000 | 0 | [33 empty] | 0 |  |  |  | 398 | 7891 |  | 0 | 0 | 780 | 0 |  | 0 | 3750.5 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 3750.5 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 2072 | C | USCSB2305111A |  | WWT T196AA | 45072 | 45079 | 39040.44 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 39040.44 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 39040.44 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C003 | F21P1 UPW | 2073 | C | USCSB2305112A |  | WWT CCB materials | 45072 | 45083 | 11084.61 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 11024.98 | 0.99462 | 59.63 | 0 | 59.63 | 110.2498 | [33 empty] | 0 |  | 3304.26 | 7606.93 |  | 113.79 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 110.2498
Others | Tiger Team | Site Expense | USC23C043 | TSMC F21 Electric Tiger Team Fisk Support & Temp Power | 2074 | C | USCSB2305114A |  | Tiger Team-Wilson Electric | 45073 | 45100 | 366651 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 366651 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 366651 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2075 | C | USCSB2305115A |  | EBO - SWAGELOK INTERCONNECT MATERIALS FOR ZASC5-1 | 45077 | 45079 | 94.4 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 94.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 94.4 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2076 | C | USCSB2305116A |  | MOUSER ELEC: QR LABS - QE43620 SENSING BAND & SENSOR | 45077 | 45113 | 2884.28 | [6 empty] | Mouser Electronics | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2884.28 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2884.28 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 2077 | C | USCSB2305117A |  | Dosing Box Installation | 2023/5/31 2023/6/3 | 45079 | 1500 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1500 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1500 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2078 | C | USCSB2305119A |  | Additional outlet | 45077 | 45091 | 8085 | [6 empty] | RMJ Electrical Contractors Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8085 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 8085 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2079 | C | USCSB2305120A |  | UPW Ebro | 45077 | 45097 | 2785 | [6 empty] | Engineered Process Controls, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2785 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 2785 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2080 | C | USCSB2306001A |  | Brycon Cleanroom cancelled contract | 45078 | 45097 | 100000 | [6 empty] | Brycon Corporation | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 62288.08 |  |  |  |  | 0 | 24454.75 | 0 | 0 |  | 13257.17 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2081 | C | USCSB2306002A |  | AMAT Interconnect Labor | 45079 | 45090 | 1000000 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1000000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 27565.48 |  | 66715.84 | 0 | 48837.72 | 0 | 57263.36 | 0 | 0 | 137864.49 | 0 | 107659.6 | 63752.78 |  | 0 | 0 | 197357.59 |  | 292983.14 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2082 | C | USCSB2306003A |  | 瑭承實業有限公司: QR LAB - UNISTRUT MATERIALS | 45079 | 45079 | 2240.6 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2240.6 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 2240.6 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2083 | C | USCSB2306005A |  | CED: PES/FAD - KXF/KXP WIRE XHHW 10/12 AWG INTERCONNECT MATERIALS | 45079 | 45082 | 1144.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1144.2 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 1144.2 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2084 | C | USCSB2306006A |  | IDEAL VACUUM: QR LABS - NPT TO NW/KF FLANGE | 45079 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2085 | C | USCSB2306007A |  | CED: QR LABS - CABLE TRAY FIXTURE - FAD LALBS | 45080 | 45082 | 193.57 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 193.57 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 193.57 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2086 | C | USCSB2306008A |  | SWAGELOK: DIF2-INTERCONNECT MATERIAL FOR 03 DETECTOR | 45080 | 45083 | 2403.5 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2403.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 2403.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | Tiger Team | Labor | USC23C041 | TSMC F21 HK Tiger Team | 2087 | C | USCSB2306009A |  | HK Tiger Team NETcom | 45080 | 45104 | 108960 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 108960 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 108960 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Material | USC21C014 | F21P1 WH2SO4 | 2088 | C | USCSB2306010A |  | WRC Material final from Harrington | 45080 | 45089 | 25937.61 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25937.61 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 25671.91 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 265.7 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Material | USC21C014 | F21P1 WH2SO4 | 2089 | C | USCSB2306011A |  | WRC Material temp use + [CO] Sluge expansion Hopper out | 45080 | 45089 | 37066.92 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 32171.04 | 0.86792 | 4895.88 | 0 | 4895.88 | 4182.2352 | [33 empty] | 0 |  |  | 13757.7 |  |  |  | 0 | 0 | 0 | 18413.34 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1112.0076 |  |  |  | 1112.0076 |  |  |  | 1112.0076 |  | 1608.552 |  | - | 1608.552 | - | 965.1312 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2090 | C | USCSB2306012A |  | Flame arresters | 45080 | 45090 | 227783.78 | [6 empty] | Caltrol Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 227783.78 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 227783.78 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2091 | C | USCSB2306013A |  | NFPA Diamond Signs for chemical tanks | 45080 | 45089 | 8012.83 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8012.83 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 8012.83 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 2092 | C | USCSB2306014A |  | Motor Rewire | 45083 | 45100 | 8892.58 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 8892.58 | 0 | 8892.58 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C007 | F21P1 VOC package （Installation ) | 2093 | C | USCSB2306015A |  | TIG 3rd party inspections | 45083 | 45089 | 35689.15 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 35689.15 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 35689.15 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2094 | C | USCSB2306016A |  | TIG 3rd party inspections | 45083 | 45089 | 106082.4 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 106082.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 106082.4 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 2095 | C | USCSB2306017A |  | All-thread stud | 45083 | 45091 | 3987.42 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3987.39 | 0.99999 | 0.03 | 0 | 0.03 | 0 | [33 empty] | 0 |  |  |  |  | 3987.39 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2096 | C | USCSB2306018A |  | UPW Degan tank HKP rev&clean | 45083 | 45100 | 7150 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7150 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 7150 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 2097 | C | USCSB2306019A |  | WWT -HACH-lab | 45083 | 45096 | 22178.07 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 22178.07 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 22178.07 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 2098 | C | USCSB2306020A | -03 | WWT-Lab oven & scale | 2023/6/6 2024/1/13 2024/3/23 | 2023/7/17 2024/1/13 2024/2/21 2024/3/26 | 1844 | 151.05 | 1692.95 |  |  |  |  | Global Equipment Company Inc. | PR Approved | PO Approved | PO R1:revise price R2: Quote Update R3: The Supplier increased price again… |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 1844 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 276.6 |  |  |  | 276.6 | 1844 |  |  | 276.6 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 2099 | C | USCSB2306021A | -02 | WWT - Lab glassware | 2023/6/6 2023/12/5 | 2023/7/28 2023/7/29 2023/12/5 | 0 | -2777.15 | 2777.15 | V |  |  |  | Laboratory Sales and Service | PR Approved | PO Approved | R1: Correction (ITEM 019 QTY to 0) |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 2100 | C | USCSB2306021B |  | WWT - Lab glassware (LS-1030070 FILTER SYSTEM, FRITTED GLASS) | 45083 | 45145 | 0 | [6 empty] | Laboratory Sales and Service | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C004 | F21P1 WWT package （USA EQ-FRP tank) | 2101 | C | USCSB2306021C |  | WWT - Lab glassware | 45083 | 45135 | 0 | [6 empty] | Laboratory Sales and Service | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | Tiger Team | Labor | USC23C041 | TSMC F21 HK Tiger Team | 2102 | C | USCSB2306022A | -01 | TSMC F21 HK TIGER TEAM | 45083 | 45090 | 67881.05 | -11584 | 79465.05 |  |  |  |  | Onsight Live, LLC | PR Approved | PO Approved | The PR needs to revised due to the amount change/The sub has reduced the labor hours. The labor rate does not change. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 67881.05 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 67881.05 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | Tiger Team | Labor | USC23C041 | TSMC F21 HK Tiger Team | 2103 | C | USCSB2306023A |  | TSMC F21 HK TIGER TEAM(Electric OPS) | 45083 | 45090 | 70638.68 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 50129.49 | 0.70966 | 20509.19 | 0 | 20509.19 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 22135.1 |  |  |  | 1484.63 |  | 7861.76 |  | 18648 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2104 | C | USCSB2306025A |  | Argon for Chemical welding | 45084 | 45125 | 680.02 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 612.52 | 0.90074 | 67.5 | 0 | 67.5 | 0 | [33 empty] | 0 |  |  | 612.52 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 67.5 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2105 | C | USCSB2306026A |  | Particle Test Service | 45084 | 45092 | 14100 | [6 empty] | Propersys Corp | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 14100 | 1 | 0 | 0 | 0 | 705 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 13395 | 14100 | 0 |  | - | 0 | - | 705 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 2106 | C | USCSB2306027A |  | MMI -ORGANO-RO Re-rotate | 45085 | 45100 | 10691 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10691 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 10691 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Material | USC21C014 | F21P1 WH2SO4 | 2107 | C | USCSB2306028A |  | PVDF Material for Vertical Rack | 45085 | 45090 | 10764.51 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10764.51 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 10764.51 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C005 | F21P1 Chemical & WCCS package | 2108 | C | USCSB2306029A |  | Housekeeping for WRC, Lorry A & B | 45086 | 45090 | 661000 | [6 empty] | Handy Technology Corp. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 594065.02 | 0.89874 | 66934.98 | 0 | 66934.98 | 0 | [33 empty] | 0 |  | 169920 | 248601.07 | 2718.21 |  | 172825.74 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2109 | C | USCSB2306030A |  | TSMC Offload | 45086 | 45091 | 383185 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 383185 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 383185 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC23C045 | WWT Change Order (Piping) | 2110 | C | USCSB2306031A |  | PSS WWT Project for invoice SW-23-0086 Final | 45086 | 45090 | 2880222.72 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2880222.72 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 2880222.72 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Scaffolding | USC21C006 | F21P1 Slurry package | 2111 | C | USCSB2306032A |  | Liberty scaffolding | 45086 | 45090 | 2720533 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 2720533 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 2300000 |  | 420533 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2112 | C | USCSB2306033A |  | DIFF: STAINLESS STEEL TUBING FOR DOUBLE CASING CONNECTION | 45086 | 45101 | 20600 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20600 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 11200 |  | 9400 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C006 | F21P1 Module Tool Interconnection EPI | 2113 | C | USCSB2306034A |  | CEU/RK4.5T-10/S90 | 2023/6/9 2023/10/31 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1:Unresponsive supplier. Replaced with Motion Intelligence Automation USCSB2309083A per purchaser. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2114 | C | USCSB2306035A |  | DIF: PFA TUBING FOR DOUBLE CASING CONNECTION ONLY ITEM 1 AND 2 ARE REQIRED FOR PURCHASE. | 2023/6/10 2023/6/21 2024/8/6 | 2023/7/20 2024/8/7 | 0 | -7832.92 | 7832.92 |  |  | V |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | PR R1:The amount is lower from $21K to $7K & only the first 2 materials,not the whole order and cancelled subsequently | PR R1:The amount is lower from $21K to $7K & only the first 2 materials,not the whole order. | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2115 | C | USCSB2306036A |  | Bay Alarm Company | 45087 | 45104 | 7100 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7100 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 7100 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2116 | C | USCSB2306038A |  | Welder equipment for Chemical welding | 45087 | 45099 | 4075 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4075 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 4075 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC23C045 | WWT Change Order (Piping) | 2117 | C | USCSB2306039A |  | PSS WWT Project. For invoice SW-23-0065 Final | 45087 | 45090 | 3730153.88 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3730153.88 | 1 | 0 | 3147 | -3147 | 0 | [33 empty] | 3730153.88 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | UMEC | USC23C014 | F21P1 Labor incentive program-MICU | 2118 | C | USCSB2306040A |  | UMEC-2022 labor and Veterans holiday | 45087 | 45090 | 326375 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 326375 | 10739.9 | 315635.1 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 326375 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 2119 | C | USCSB2306041A |  | Scissor lift for Chemical welding | 45090 | 45210 | 2084.61 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 2084.61 | 0 | 2084.61 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 2084.61 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 2120 | C | USCSB2306042A | -01 | FAB A PVDF - 02 | 45090 | 2023/6/26 2023/7/4 | 60019.55 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | R1:The trade terms need to be FOB. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 47634.98 | 0.79366 | 12384.57 | 0 | 12384.57 | 10003.3458 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 47634.98 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 2381.749 |  | - | 2381.749 | - | 2381.749 | 2858.0988 | 0
Base-Build | Base-Build | Housekeeping | USC21C005 | F21P1 Chemical & WCCS package | 2121 | C | USCSB2306043A |  | Supervisor, safety, and housekeeping manpower | 45090 | 45098 | 850000 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 850000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 719303.93 |  |  | 127128.9 |  |  | 0 | 0 | 3567.17 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2122 | C | USCSB2306044A |  | WWT-CCB dry-run | 45090 | 45092 | 350 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 350 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 350 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2123 | C | USCSB2306045A |  | UPW Train-A-GF valves | 45090 | 45103 | 4243.4 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4243.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 681.29 | 0 |  |  | 3562.11 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2124 | C | USCSB2306046A |  | WWT Tanks diamond labels | 45090 | 45104 | 21074.6 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 21074.6 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 21074.6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2125 | C | USCSB2306047A |  | AMAT Interconnect- Greenberry Mechanical Labor | 45090 | 45097 | 200000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 164308.2 | 0.82154 | 35691.8 | 0 | 35691.8 | 0 | [33 empty] | 0 |  |  |  |  | 53930.55 |  | 110377.65 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2126 | C | USCSB2306048A |  | DIF2: WIRE AF825001 & WIRE AF34/003 FOR POWER TRANSFORMER CONNECTION | 45090 | 45124 | 151960 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 151960 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 151960 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MIMO/Rigging | USC21C005 | F21P1 Chemical & WCCS package | 2127 | C | USCSB2306049A |  | 2 Tank &1 EQ Move in CO 9 | 45091 | 45113 | 13930 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 13930 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 13930 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2128 | C | USCSB2306050A | -01 | DIFF: ELECTRICAL TRADE - KDAPK3 | 2023/6/14 2024/6/5 | 2023/7/27 2024/6/7 | 4160 | -25840 | 30000 |  |  | V | V | Onsight Live, LLC | PR Approved | PO Approved | Order is adjusted to settle completed work only |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4160 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 4160 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2129 | C | USCSB2306051A |  | DIFF: ELECTRICAL TRADE - KDAPK2 & KDAPK3 | 45091 | 45137 | 10384 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 10384 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 10384 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2130 | C | USCSB2306052A |  | DIFF: ELECTRICAL TRADE - ALL TOOLS SEE ATTACHED | 45091 | 45134 | 250000 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 248046.38 | 0.99219 | 1953.62 | 0 | 1953.62 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 24081 | 0 |  | 0 | [9 empty] | 32154 |  | 6399.75 |  | 185411.63 | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2131 | C | USCSB2306053A |  | WWT NH4 analyzer (Chemical Only) | 45091 | 45113 | 443.54 | [6 empty] | Winn Marion Barber, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 443.54 | 0 | 443.54 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 66.531 |  |  |  | 66.531 |  |  |  | 66.531 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | MIMO/Rigging | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2132 | C | USCSB2306054A |  | Foundation accessory move-in labor | 45091 | 45135 | 500000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 395220 | 0.79044 | 104780 | 0 | 104780 | 0 | [33 empty] | 0 | [6 empty] | 0 | 112960 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 282260 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2133 | C | USCSB2306055A |  | A1 Locksmith & Security Center | 45091 | 45113 | 1742.14 | [6 empty] | A1 Locksmith & Security Center Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 1742.14 | 0 | 1742.14 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 2134 | C | USCSB2306056A |  | Mezzanine Doors and Installation | 45092 | 45106 | 89000 | [6 empty] | Suncoast Glass & Glazing,LLC dba Mirror Works dba Horn Doors | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 89000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 77180 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 11820 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2135 | C | USCSB2306057A |  | AFC-A-02 dismantle and reinstallation | 45092 | 45113 | 4008 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3807.6 | 0.95 | 200.4 | 0 | 200.4 | 0 | [33 empty] | 0 | [6 empty] | 3807.6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2136 | C | USCSB2306058A |  | Hard barricade hardware | 45092 | 45099 | 1826.88 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1826.88 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 1826.88 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2137 | C | USCSB2306059A |  | ATF-D-09 installation | 45092 | 45113 | 21873 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 20779.35 | 0.95 | 1093.65 | 0 | 1093.65 | 0 | [33 empty] | 0 | [6 empty] | 20779.35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2138 | C | USCSB2306060A |  | ADI-C-01 shift 3cm modification | 45092 | 45113 | 601 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 570.95 | 0.95 | 30.05 | 0 | 30.05 | 0 | [33 empty] | 0 | [6 empty] | 570.95 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2139 | C | USCSB2306061A | -01 | Soft barricade | 2023/6/15 2023/7/17 | 2023/6/29 2023/7/18 | 3397 | 255 | 3142 | V |  |  |  | HSIEH SHUN HING CO., LTD. | PR Approved | PO Approved | R1:packing fee |  | Yuanyuan Liang |  |  |  | Yuanyuan Liang | [7 empty] | 1559 | 0.45893 | 1838 | 0 | 1838 | 0 | [33 empty] | 0 |  |  |  |  | 1559 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2140 | C | USCSB2306062A |  | 500pcs grinded iron plate | 2023/6/15 2023/6/27 | 45113 | 6000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  | PR-R1:Revised from 500 to 200 pcs per TSMC's request. | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 6000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C047 | F21P1 HK Seismic Installation | 2141 | C | USCSB2306063A |  | QR Lab cutting tiles | 45092 | 45125 | 33374 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 33374 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 33374 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 2142 | C | USCSB2306065A | -01 | AMAT WIRE FOR POWER TRANSFORMER CONNECTION | 2023/6/16 2023/8/10 | 2023/7/10 2023/12/5 | 0 | -42180 | 42180 |  |  |  | V | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | PO R1: Order is cancelled due to duplicate with USCSB2308053A |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2143 | C | USCSB2306066A |  | CVD2_MACH 1+，Interconnection material KCANN1~7, 7 tools, Male Fujikin 1/2" Diaphragm manual valve | 45093 | 45096 | 1882 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 1882 | 0 | 1882 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | 光阻櫃 | Equipment | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 2144 | C | USCSB2306067A |  | A Side Photoresist Cabinet Exhaust Hookup engineering | 45093 | 45142 | 494371.72 | [6 empty] | MornstAir Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 469653.13 | 0.95 | 24718.59 | 0 | 24718.59 | 0 | [33 empty] | 0 | [6 empty] | 469653.13 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Labor | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 2145 | C | USCSB2306068A |  | TSMC F21P1 (AZ) MICU-LSW CO Upgrade All Gens to Level 1 Emergency Service | 45093 | 45096 | 41040 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | Back Charge to Customer Fu Energy with 8% Mark-up | 100% by progress-net 30 days-after acceptance | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 41040 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 19500 |  | 0 | 0 | 2154 | 0 | 2154 | 0 | 2154 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 2154 | [5 empty] | 2154 | [8 empty] | 0 | 6462 | 4308 | 0 | - | 0 | 0
Non-TSMC | EDG | Labor | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 2146 | C | USCSB2306069A |  | Remove and Replace Discharge Ducts | 45093 | 45096 | 61698 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved | Back Charge to Customer Fu Energy with 10% Mark-up |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 61698 | 0 | 61698 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Equipment | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 2147 | C | USCSB2306070A |  | TSMC F21P1(AZ) MICU-DDE Change Orderx7 | 45093 | 45096 | 214766.65 | [6 empty] | Delta Diversified Enterprises, Inc. | PR Approved | PO Approved | Back Charge to Customer Fu Energy with 10% Mark-up |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 204026.75 | 0.94999 | 10739.9 | 0 | 10739.9 | 0 | [33 empty] | 0 |  |  |  |  | 204026.75 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2148 | C | USCSB2306071A |  | Starlink additional support for OSC | 45093 | 45102 | 5750 | [6 empty] | GeoTech Enterprises LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5750 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 5750 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2149 | C | USCSB2306072A |  | TSMC F21 CDS DC Panel | 45093 | 45099 | 50000 | [6 empty] | UCAN Hong Kong Limited | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 50000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 50000 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Equipment | USC23C015 | F21P1 AMHS Wiring Work Outline | 2150 | C | USCSB2306073A | -01 | TSMC F21 AMHS Panel redesign | 2023/6/16 2023/8/9 | 2023/6/22 2023/8/9 | 0 | -127860 | 127860 |  |  |  |  | Third Enterprise | PR Approved | PO Approved | This PO need to be zero out per PM's instruction./TSMC will buy it from the vendor directly. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC22C001 | F21 P1 Office and WH Security and CCTV | 2151 | C | USCSB2306074A |  | PD Sensor Installation and Transformer Testing | 45093 | 45104 | 29150 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 29150 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 3500 |  |  |  | 25650 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2152 | C | USCSB2306075A |  | WWT ICW-4” SUS flange | 45093 | 2023/6/16 | 210.6 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 210.6 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 210.6 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2153 | C | USCSB2306076A |  | WWT-CCB dry-run CO | 45093 | 45093 | 650 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 650 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C005 | F21P1 Chemical & WCCS package | 2154 | C | USCSB2306077A |  | Sunrise Phoenix housekeeping services | 45094 | 45103 | 500000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 500000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 84410 | 208180 | 126220 | 81190 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2155 | C | USCSB2306078A | -01 | Mezzanines Fireproof Coating #1 & #2 | 45094 | 2023/7/3 2023/7/22 | 735000 | [6 empty] | Alpha Insulation and Waterproofing, Inc | PR Approved | PO Approved | R1:contract name change |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 735000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 403676.42 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 294573.58 |  | 0 | 0 | 0 |  | 0 |  |  |  | 36750 |  |  |  |  | 36750 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Material | USC21C013 | F21P1 AMC THC Monitoring System | 2156 | C | USCSB2306079A |  | F21P1 EBO AMC+TVOC 16CH online monitoring system | 45094 | 45105 | 508710 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 313284 | 0.61584 | 195426 | 0 | 195426 | 195426 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 83942 |  | 229342 |  |  |  |  | 76307 |  |  |  | 93705 |  | 76306.5 |  | - | 66132.3 | 175588.5 | 25435.5 | 25435.5 | 2116.2
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2157 | C0 | USCSB2306080A |  | amazon-hand tool (technician Project) | 45097 | 45105 | 3748.37 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3748.37 | 1 | 0 | 0 | 0 | 0 | 3748.37 | [32 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2158 | C | USCSB2306081A |  | Painting work from PHP T&M work scope (December 2022 to May 2023) | 45097 | 45105 | 348526.86 | [6 empty] | Phoenix House Painting.com LLC dba PHP Commercial Painting | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 348526.86 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 348526.86 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C003 | F21P1 UPW | 2159 | C | USCSB2306082A |  | Forklift for the pipe crating project at the TSMC site | 45097 | 45103 | 950 | [6 empty] | Raymond West Intralogistics Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 950 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 950 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 2160 | C | USCSB2306083A |  | Crating and packing for pipes on site | 45097 | 45103 | 42242 | [6 empty] | Crating Technology, INC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 42242 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 42242 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2161 | C | USCSB2306084A |  | 1000 Series Pump Support Base | 45097 | 45125 | 28251 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25044.75 | 0.88651 | 3206.25 | 0 | 3206.25 | 0 | [33 empty] | 0 |  |  | 19273.5 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 2565 | 0 | 0 |  | 0 | [8 empty] | 6412.5 |  |  |  |  | 3206.25 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2162 | C | USCSB2306085A |  | Slurry Raise Trench Grating | 45097 | 45124 | 67129 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 63772.55 | 0.95 | 3356.45 | 0 | 3356.45 | 3356.45 | [33 empty] | 0 |  |  | 46990.3 |  | 6712.9 |  | 0 | 0 | 0 | 10069.35 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 3356.45
Base-Build | UPW | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2163 | C | USCSB2306086A |  | WRC Acid Zone UPW Stair | 45097 | 45124 | 25630 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25630 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 25630 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2164 | C | USCSB2306087A |  | DIFF1: TLC/VMB FOR DIFF1 | 45098 | 45146 | 472.42 | [6 empty] | Southwest Steel Sales, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 472.42 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 472.42 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | LSC connector | Material | USC23C048 | F21P1-0423_H_LSC connectors_MICU | 2165 | C | USCSB2306088A |  | Pipe Fittings for TSMC/Kanken | 45098 | 45110 | 64498.12 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | Pipe fittings will be delivery to Kanken Warehouse via RTW. TSMC has agreed to be invoiced the full sum upon delivery. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 64498.12 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 64498.12 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2166 | C | USCSB2306089A |  | WWT-PSS-TrainA material | 45098 | 45125 | 303006.77 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 303006.77 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 240098.46 |  | 0 | 9495.82 | 6599.9 | 2234.4 |  | 0 | 0 | 0 | 0 | 0 |  | 44578.19 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Outsourcing | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2167 | C | USCSB2306090A |  | TEOPM | 6/21/2023 10/4/2024 | 6/27/2023 10/11/2024 | 92068.27 | -7531.73 | 99600 |  |  |  |  | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 92068.27 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 16279.65 | 37811 |  | 19785.5 |  | 18192.12 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2168 | C | USCSB2306091A |  | Lorry Pipe Crossover Platform | 45098 | 45125 | 14090 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 14090 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 14090 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2169 | C | USCSB2306092A |  | DIFF1: FLEX METAL CONDUITS, ALUM, TRD SZ 1 IN. | 45098 | 45106 | 1038.11 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1038.11 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 1038.11 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2170 | C | USCSB2306093A |  | WWT-MU-PVC Sparger | 45098 | 45125 | 18948.56 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 18948.56 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 11352.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7596.06 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2171 | C | USCSB2306094A |  | Hand Tool - Home Depot | 45098 | 45118 | 26247.69 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 26247.69 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 22173.27 | 4074.42 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC21C011 | F21 TMAH System | 2172 | C | USCSB2306095A |  | WWT-T665AA relocation | 45098 | 45126 | 27616 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 27616 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 13808 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 13808 |  | 0 | [8 empty] | 2761.6 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Triazole | UMEC | USC22C022 | F21P1 Triazole treatment system | 2173 | C | USCSB2306096A |  | WWT Triazole | 45098 | 45108 | 686619 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 686619 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 102993 |  | 137324 | 0 | 68662 | 0 | 0 |  | 0 | 82394 | 0 | 0 | 0 |  |  | 89260 | 171655 | 0 |  | 0 |  | 34331 | [12 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC21C011 | F21 TMAH System | 2174 | C | USCSB2306097A |  | WWT Tank Agitator Blade Epoxy | 45098 | 45124 | 72000 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 49500 | 0.6875 | 22500 | 0 | 22500 | 3240 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 13500 | 0 |  |  | 15000 | 0 | 0 |  | 0 |  |  |  |  | 7200 | 12000 |  |  | 7200 |  |  |  | 7200 | 9000 | 0 |  | - | 0 | - | 0 | 0 | 3240
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2175 | C | USCSB2306098A |  | UMEC-2022 Sep to Dec incentive | 45098 | 45107 | 931858 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 931858 | 0 | 931858 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Triazole | Material | USC22C022 | F21P1 Triazole treatment system | 2176 | C | USCSB2306099A |  | WWT Triazole pads | 45098 | 45124 | 32381 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 30981 | 0.95676 | 1400 | 0 | 1400 | 1239.24 | [33 empty] | 0 |  |  |  |  | 30981 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 1239.24
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2177 | C | USCSB2306100A |  | WWT-CCB-PVC | 45098 | 45114 | 1989.35 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1989.35 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 1989.35 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Triazole | MIMO/Rigging | USC22C022 | F21P1 Triazole treatment system | 2178 | C | USCSB2306101A |  | WWT Triazole steels and move-in | 45098 | 45126 | 292297 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 292297 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 87689.1 |  | 87689 | 0 | 58549 | 0 |  | 0 | 0 | 0 | 43754 | 0 |  |  | 14615.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2179 | C | USCSB2306102A |  | TSMC F21 PDP Panel Breaker Change | 45099 | 45114 | 29504 | [6 empty] | OEG ISG - Integrated Systems Group | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 29504 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 29504 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2180 | C | USCSB2306103A |  | FAB bolts request #1 | 45099 | 45103 | 2264.28 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2264.28 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 2264.28 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2181 | C | USCSB2306104A |  | FAB bolts request #2 | 45099 | 45103 | 2521.1 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2521.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | 2521.1 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | EDG | Labor | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 2182 | C | USCSB2306105A |  | TSMC Relay Testing | 45099 | 45104 | 19560 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved | Back Charge to Customer with 8% Mark-up |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 19560 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 19560 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2183 | C | USCSB2306106A |  | DIFF1: MECHANICAL LABOR FOR KDAPK2-4 | 45099 | 45114 | 5630.62 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 5630.62 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 5630.62 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2184 | C | USCSB2306107A |  | QR LAB: MECHANICAL LABOR KXAT01 & KXFX01 | 45100 | 45114 | 2000 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2000 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 2000 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Hot DI | UMEC | USC23C012 | F21P1 Hot DI Machine Hookup | 2185 | C | USCSB2306108A | -01 | Hot DI piping | 45100 | 2023/7/6 2023/7/20 | 29119 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | R1:To include WO scope into signed Contract |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27663 | 0.95 | 1456 | 0 | 1456 | 1455.95 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 27663 | [10 empty] | 0 |  | - | 0 | - | 0 | 1455.95
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2186 | C | USCSB2306109A |  | WWT-chemical enclosure | 45100 | 45142 | 141500 | [6 empty] | Scenic Industries, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 127350 | 0.9 | 14150 | 0 | 14150 | 141500 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 21225 |  |  |  | 21225 |  |  |  | 21225 |  | 28300 | 127350 | - | 28300 | - | 28300 | 28300 | 28300
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2187 | C | USCSB2306110A |  | UPW skids cover replacement | 45100 | 20230/7/19 | 1046.87 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1046.87 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 1046.87 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2188 | C | USCSB2306111A |  | UPW-PP-HP-Zewei | 45100 | 45105 | 193.99 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 193.99 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 193.99 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2189 | C | USCSB2306112A |  | UMEC-2022 week 60 hour rate difference | 45100 | 45131 | 1660117 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1256301 | 0.75675 | 403816 | 0 | 403816 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 1256301 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 2190 | C | USCSB2306113A |  | VOC Electrical:TSMC-MIC VOC Pipe -VEX | 45101 | 45126 | 311.1 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 311.1 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 311.1 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2191 | C | USCSB2306114A |  | Hach Start up | 45101 | 45107 | 12216 | [6 empty] | Hach Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 12216 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 12216 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C047 | F21P1 HK Seismic Installation | 2192 | C | USCSB2306115A |  | Additional Items for foundation project_MMI | 45101 | 45132 | 2834400 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2204886 | 0.7779 | 629514 | 0 | 629514 | 0 | [33 empty] | 0 | [6 empty] | 0 | 499583 | 0 | 0 |  | 0 | 0 | 1052163 | 376739 | 0 |  |  | 0 | 0 | 276401 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2193 | C | USCSB2306116A |  | AMHS Grating Floor Opening | 45101 | 45135 | 661015 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 661015 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  | 382020 |  |  | 131790 | 0 | 33310 | 0 |  | 89990 | 23905 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Equipment | USC21C008 | F21P1 CCTV & Security | 2194 | C | USCSB2306117A |  | F21 P1 CCTV & Fiber Engineering | 45104 | 45113 | 423140.27 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 401820.86 | 0.94962 | 21319.41 | 0 | 21319.41 | 0 | [33 empty] | 0 | [6 empty] | 256104.17 | 0 | 0 | 0 | 42910.69 | 0 | 0 | 102806 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Greenberry | USC21C011 | F21 TMAH System | 2195 | C | USCSB2306118A |  | WRC 2nd floor rack (WWT under TMAH) | 45104 | 45140 | 87915 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 83519.25 | 0.95 | 4395.75 | 0 | 4395.75 | 87915 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 13187.25 |  |  |  | 13187.25 |  |  | 83519.25 | 13187.25 |  | 17583 |  | - | 17583 | - | 17583 | 17583 | 17583
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 2196 | C | USCSB2306119A |  | WRC Ammonia nitrogen CO -2 | 45104 | 45104 | 76.67 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 76.67 | 0 | 76.67 | 76.67 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 76.67 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2197 | C | USCSB2306120A |  | MIC / CDS Tank Relocation | 45105 | 45135 | 100429 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 100429 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 100429 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Equipment | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 2198 | C | USCSB2306121A |  | Run & Support 480V Temp Power Feeds in FAB-1 | 45105 | 45113 | 11832 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved | Will charge back to Fu Energy |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11832 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 11832 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | Equipment | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 2199 | C | USCSB2306122A |  | Herc cable rental | 45105 | 45112 | 16009 | [6 empty] | Herc Rentals Inc. | PR Approved | PO Approved | Will be charge back to Fu Energy |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 16009 | 0 | 16009 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | 光阻櫃 | Equipment | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 2200 | C | USCSB2306123A |  | Mask Room A Side Utility | 45105 | 45132 | 149446.89 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 149446.89 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 24952 | 0 | 0 | 0 |  | 0 | 0 | 118412 | 6082.89 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2201 | C | USCSB2306124A | -01 | Pillar tools for flare | 2023/6/28 2023/6/30 | 2023/6/28 2023/6/30 | 1008 | 232 | 776 | V |  |  |  | Nippon Pillar Corporation of America | PR Approved | PO Approved | Price quoted incorrectly |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1008 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 1008 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2202 | C | USCSB2306125A |  | Hand tool - Cintas Fire Extinguisher | 45105 | 45110 | 9442.83 | [6 empty] | Cintas Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 9442.83 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  | 9442.83 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | NUUO | USC21C013 | F21P1 AMC THC Monitoring System | 2203 | C | USCSB2306126A |  | THC electric and low voltage engineering | 45105 | 2023/7/10 2024/8/6 | 653553.4 | -123326.6 | 776880 |  |  |  |  | NUUO US Inc. | PR Approved | PO Approved | PO R1:Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 653553.4 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 49475 | 0 | 0 | 0 |  | 202258.4 | 401820 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 62151 |  |  |  | 22297 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical Lab | MIMO/Rigging | USC22C021 | F21P1 Chemical Lab setup | 2204 | C | USCSB2306127A |  | GC Lab Move-in | 45105 | 45132 | 8988 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8538.6 | 0.95 | 449.4 | 0 | 449.4 | 0 | [33 empty] | 0 | [6 empty] | 8538.6 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 449.4 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2205 | C | USCSB2306128A |  | Grainger Hand tool | 45105 | 45118 | 71296.77 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 71296.77 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 70696.57 | 600.2 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | chemical safety cabinet | MIMO/Rigging | USC23C042 | F21P1 Chemical Safety Cabinet Installation | 2206 | C | USCSB2306129A |  | Safety Cabinet Move-in | 45105 | 45140 | 25007 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25007 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 12503.5 |  | 0 | 0 | 12503.5 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C005 | F21P1 Chemical & WCCS package | 2207 | C | USCSB2306130A |  | Hua Yi housekeeping | 45106 | 45124 | 94800 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 94800 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 94800 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 2208 | C | USCSB2306131A |  | Taiwan D180/225 MU material | 45106 | 45110 | 23500 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 23500 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 |  | 18450.6 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 5049.4 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | MMI | USC21C011 | F21 TMAH System | 2209 | C | USCSB2306132A |  | WWT Repair Leak T-140AA Tank | 45106 | 45140 | 55981 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 55981 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 55981 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2210 | C | USCSB2306133A |  | 6 single barricades | 45106 | 45135 | 6888 | 1148 | [5 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6888 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 6888 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2211 | C | USCSB2306134A | -01 | HSIEH SHUN HING hand tool | 2023/6/29 2023/7/14 | 2023/7/5 2023/7/17 | 7473.5 | 1304.9 | 6168.6 | V |  |  |  | HSIEH SHUN HING CO., LTD. | PR Approved | PO Approved | R1:packing fee |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7473.5 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 7473.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2212 | C | USCSB2306135A |  | TSMC Offload June | 45106 | 45132 | 99625 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 99625 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  |  |  |  | 99625 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2213 | C | USCSB2306136A |  | UPW CO-Add | 45106 | 45133 | 57530 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 57530 | 0 | 57530 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2214 | C | USCSB2306137A |  | QR LAB: MECHANICAL LABOR: 11 TOOLS FOR BOX INSTALL. 2 TO REWORK. | 45106 | 45160 | 6000 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 6000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2215 | C | USCSB2306138A |  | CVD2_MACH 1+ KCANN1~7, 7 tools, Male Fujikin 1/2" Diaphragm manual valve. Interconnect Materials. | 45107 | 45118 | 4508 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4508 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 4508 | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2216 | C | USCSB2306139A | -01 | WWT-PVC blind flange 20” | 2023/6/30 2023/7/17 | 2023/7/13 2023/7/17 | 954.36 | 106.04 | 1060.4 | V |  |  |  | Pure Plastics, LLC | PR Approved | PO Approved | Discount given by vendor. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 954.36 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 | [5 empty] | 954.36 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | NUUO | USC21C008 | F21P1 CCTV & Security | 2217 | C | USCSB2306140A |  | F21 P1 CCTV FAB Camera, Conduit, Cabling and Panel Installation | 45107 | 45117 | 1288488.34 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1288488.34 | 1 | 0 | 0 | 0 | 0 | [33 empty] | 0 |  | 216945.1 | 72644 |  | 998899.24 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2218 | C | USCSB2306142A |  | Duncan Bolt - unpaid invoice | 45107 | 45110 | 475.52 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 475.52 | 1 | 0 | 0 | 0 | 0 | [35 empty] | 475.52 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2219 | C | USCSB2307001A |  | Bay Alarm Company | 45108 | 45114 | 600 | [6 empty] | Bay Alarm Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 600 | 0 | 600 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C006 | F21P1 Module Tool Interconnection EPI | 2220 | C | USCSB2307002A | -01 | Glands and unions for AMAT EPI interconnect materials | 45108 | 2023/8/2 2023/8/15 | 233.76 | -1103.4 | 1337.16 |  | V |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: Change of material requirement by TSMC |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 233.76 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 233.76 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 2221 | C | USCSB2307003A |  | CED (36IN CABLE TIE & INBOUND NSI) | 45108 | 45112 | 370 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 370 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 370 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2222 | C | USCSB2307004A |  | Linde Gas & Equipment Inc. | 45108 | 45138 | 75000.01 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4014.46 | 0.053526 | 70985.55 | 0 | 70985.55 | 0 | [38 empty] | 3926.96 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [13 empty] | 87.5 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical Lab | UMEC | USC22C021 | F21P1 Chemical Lab setup | 2223 | C | USCSB2307006A |  | 8-66 FAB Gas Chem Lab Hook-Up(GC Lab Piping) | 45108 | 45133 | 128754 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 122317 | 0.95001 | 6437 | 0 | 6437 | 6437 | [40 empty] | 0 | 103003 | 0 | 0 |  | 0 | 0 | 0 | 12876 | 0 | 6438 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 6437
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2224 | C | USCSB2307007A |  | WWT-weld machine rental for PSS | 45108 | 45114 | 165672 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 159385.82 | 0.96206 | 6286.18 | 0 | 6286.18 | 6375.4328 | [36 empty] | 94807.66 | 20918.17 | 23010 |  | 0 | 0 | 0 | 0 |  | 0 | 20649.99 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 6375.4328
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2225 | C | USCSB2307008A |  | Remove Water and Chemical from Tanks(UPW Degan tank clean) | 45108 | 45140 | 2500 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 2500 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2226 | C | USCSB2307009A |  | Gensler Minor Changes During Construction | 45111 | 45119 | 15000 | [6 empty] | M. Arthur Gensler Jr. & Associates, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7866.11 | 0.52441 | 7133.89 | 0 | 7133.89 | 0 | [38 empty] | 3612 |  | 0 | 0 | 0 | 0 | 4204.51 | 0 | 49.6 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2227 | C | USCSB2307010A |  | Arbon Equipment Corporation Glendale Warehouse Door Repair | 45111 | 45119 | 5537.74 | [6 empty] | Arbon Equipment Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5537.74 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 5537.74 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2228 | C | USCSB2307011A |  | UPW-TSMC OP material-harrington | 45113 | 45127 | 2788.16 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2361.16 | 0.84685 | 427 | 0 | 427 | 0 | [38 empty] | 2361.16 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C047 | F21P1 HK Seismic Installation | 2229 | C | USCSB2307013A |  | Seismic Sticker | 45113 | 45118 | 322.5 | [6 empty] | DIABASE TECHNOLOGY CO LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 322.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 322.5 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2230 | C | USCSB2307014A |  | 50 single barricades | 45113 | 45127 | 53900 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 53900 | 0 | 53900 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse |  | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2231 | C | USCSB2307015A |  | Bay Alarm Company | 2023/7/6 2023/7/7 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1:This PR needs to be cancel/ APN |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2232 | C | USCSB2307016A |  | CVD HVCR interconnect materials -CVD HVCR connectors for interconnection for tool ID KCANN2, KCANN1, KCANN3, KCSCN3, KDALS2, | 45113 | 45119 | 7878.8 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 7878.8 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 7878.8 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2233 | C | USCSB2307017A |  | FRP Resin for welding FRP pipe | 45113 | 45120 | 5760 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5760 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 5760 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2234 | C | USCSB2307018A |  | Consolidated Electrical Distributors | 45113 | 45133 | 311030 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 311030 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 199122.5 |  | 111907.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2235 | C | USCSB2307019A |  | WWT-CCB dry-run | 45113 | 45187 | 5768.1 | [6 empty] | Clean Harbors Environmental Services Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5745.2 | 0.99603 | 22.9 | 0 | 22.9 | 0 | [40 empty] | 0 | 0 | 0 | 5745.2 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2236 | C | USCSB2307020A |  | 湧心 Hand Tool | 45113 | 45113 | 7734 | [6 empty] | YONGXIN Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 7734 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 7734 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2237 | C | USCSB2307021A |  | 羿軍 hand tool | 45113 | 45113 | 16188.11 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 16188.11 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 16188.11 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2238 | C | USCSB2307022A |  | OSC Contracted Labor Force – 6 months | 45113 | 45119 | 476835.84 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 476835.84 | 1 | 0 | 0 | 0 | 0 | [35 empty] | 70638.68 | 26484.38 |  | 75827.17 |  | 0 | 96116.72 | 0 | 0 |  | 0 | 42223.99 | 10711.5 | 22450.14 | 23876.68 | 20372.63 | 29491.4 | 0 | 0 | 0 |  | 51029.65 |  | 7612.9 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical Lab | MMI | USC22C021 | F21P1 Chemical Lab setup | 2239 | C | USCSB2307023A |  | GC Lab Anchor and Materials | 45113 | 45127 | 26560 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 26560 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 6640 |  | 3623 | 0 | 0 | 0 |  | 0 | 8148.5 | 0 | 8148.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2240 | C | USCSB2307024A |  | L10 Equipment Relocation | 45114 | 45145 | 19539 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19539 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 19539 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2241 | C | USCSB2307025A |  | QR LAB: VNTC-PVC/NYLON INSULATION - PVC JACKET -18 AWG | 45114 | 45127 | 225.6 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 225.6 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 225.6 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2242 | C | USCSB2307026A |  | Purchase and Install Safety Gates on Tanks(UPW swing gate) | 45114 | 45119 | 45500 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 45500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 13325 | 2860 | 0 |  | 0 | 20995 | 0 | 0 | 0 | 3900 | 3510 | 0 | 0 | 0 |  | 0 |  | 910 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2243 | C | USCSB2307027A |  | WRC NaOH Tank Tranfer to Drums (WWT-T615A-empty chemical) | 45114 | 45187 | 6760.1 | [6 empty] | Clean Harbors Environmental Services Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3334.6 | 0.49328 | 3425.5 | 0 | 3425.5 | 266.768 | [40 empty] | 0 | 0 | 0 | 3334.6 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 676.01 |  |  |  | 676.01 |  |  |  | 676.01 |  | 0 |  | - | 0 | - | 0 | 0 | 266.768
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2244 | C | USCSB2307028A |  | UPW sight glass ball valves | 45115 | 45114 | 2190.8 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2190.8 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 2190.8 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC21C008 | F21P1 CCTV & Security | 2245 | C | USCSB2307029A |  | CCTV speed gates UL on-site inspection/evaluation | 45115 | 45119 | 6240 | [6 empty] | TUV SUD America, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 6240 | 0 | 6240 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - |  | - | 0 | 0
Others | cabinet transport | Equipment | USC23C049 | Cabinets transport and installation | 2246 | C | USCSB2307032A |  | F21 Emergency Response Cabinet | 45115 | 45126 | 57546 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 57546 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 31650.3 |  | 0 | 0 | 11509 | 0 |  | 2877.5 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 11509.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2247 | C | USCSB2307033A |  | UPW enclosure flange | 45118 | 45119 | 1345.6 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1345.6 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 1345.6 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2248 | C | USCSB2307034A |  | MIC assistance FusionHPX help Harder job | 2023/7/11 2023/7/13 | 45121 | 3000 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | PR-R1:Add item 2 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3000 | 1 | 0 | 10770.35 | -10770.35 | 0 | [37 empty] | 3000 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2249 | C | USCSB2307035A |  | TSMC UPW Package-CO-Add | 45118 | 45132 | 31004 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 31004 | 0 | 31004 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Southland | USC21C005 | F21P1 Chemical & WCCS package | 2250 | C | USCSB2307037A |  | 5222338-CO #096 Lorry PTFE Drain Redesign-Material | 45118 | 45133 | 48798 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 48798 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 48798 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2251 | C | USCSB2307038A | -01 | L20 GN2 Rework for EMT | 2023/7/11 2023/12/11 | 2023/7/20 2323/12/11 | 0 | -105634 | 105634 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Work done before turning T&M, Paid in Orginal PO 60% |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MIMO/Rigging | USC21C005 | F21P1 Chemical & WCCS package | 2252 | C | USCSB2307039A |  | CO2 Cylinder Move In | 45118 | 45144 | 17300 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 17300 | 1 | 0 | 0 | 0 | 1730 | [38 empty] | 12110 |  | 0 | 0 | 3460 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 1730 | 0 | - | 0 | 1730
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2253 | C | USCSB2307040A |  | Pure Plastics Pipe Supports | 45118 | 45145 | 19961 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19961 | 1 | 0 | 0 | 0 | 998.05 | [38 empty] | 12974.65 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 5988.3 | 0 | 0 | 0 |  | 0 |  |  |  |  | 19961 | 998.05 | [8 empty] | 0 |  | - | 0 | - | 0 | 998.05
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2254 | C | USCSB2307041A |  | AMHS Hole Framing and Cover Removal (AMHS VC L20 Steel Plate Removal) | 45118 | 45127 | 28028 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 28028 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 7007 |  | 0 | 0 | 4204.2 | 0 |  | 0 | 0 | 0 | 11211.2 | 0 |  |  | 0 | 0 | 5605.6 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | PSS | USC21C005 | F21P1 Chemical & WCCS package | 2255 | C | USCSB2307042A | -01 | Additional Scope for Chemical Drain transferred from Harder in Fab and Lorry | 7/11/2023 3/6/2024 | 8/7/2023 3/6/2024 | 0 | -276782.06 | 276782.06 |  |  |  |  | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | R1: As per PM:Johnny Wan,due to the engineering for the chemical system drain has been transferred from PSS to UMEC. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2256 | C | USCSB2307043A | -01 | American Fence Company | 2023/7/11 2023/8/1 | 2023/7/27 2023/8/4 | 0 | -44137.08 | 44137.08 |  |  |  | V | American Fence Company of Arizona, Inc. | PR Approved | PO Approved | R1:Getting materials through Hua Yi Construction |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2257 | C | USCSB2307044A | -01 | MIC CDS HPM-FAB | 2023/7/12 2023/12/12 | 2023/9/14 2023/12/29 | 0 | -30723 | 30723 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | PSS | USC21C005 | F21P1 Chemical & WCCS package | 2258 | C | USCSB2307045A | -01 | Reroute drain lines per MIC (Ben) Sketches dated 5/18/23 | 2023/7/12 2024/6/14 | 2023/7/21 2024/6/14 | 0 | -21100.2 | 21100.2 |  |  |  | V | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | This is a Change Order and corresponds to WO#USCSB2301045A. Design change to reroute and rectify design error. Revision is to cancel scope as requested by PM. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | PSS | USC21C005 | F21P1 Chemical & WCCS package | 2259 | C | USCSB2307046A | -01 | Revised to remove labor cost for piping installed in room 38 & 39 H2O2. | 2023/7/12 2024/6/14 | 2023/8/25 2024/6/14 | 0 | -6444.96 | 6444.96 |  |  |  | V | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved | This is a Change Order and corresponds to WO#USCSB2301045A to settle for wrong material order. Revision is to cancel scope as requested by PM. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | MMI | USC21C006 | F21P1 Slurry package | 2260 | C | USCSB2307047A |  | TSMC FAB L30 Floor penetration supports Per RFI #034 | 45119 | 45145 | 48625 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 48625 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 48625 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2261 | C | USCSB2307048A |  | Global Industrial | 45119 | 45125 | 3409.9 | [6 empty] | Global Equipment Company Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3409.9 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 3409.9 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 2262 | C | USCSB2307049A |  | Big / Small size bolts | 45119 | 45121 | 23119.22 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 23119.22 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 11191.45 |  | 10170.93 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1756.84 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2263 | C | USCSB2307050A |  | AMAT Interconnect- GREENBERRY INDUSTRICAL – MECHANICAL LABOR | 45119 | 45128 | 300000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 263755.23 | 0.87918 | 36244.77 | 0 | 36244.77 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 69298.81 | 0 | 0 | 0 |  |  | 0 | 0 | 194456.42 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | MMI | USC21C011 | F21 TMAH System | 2264 | C | USCSB2307051A |  | Lamella Installation | 45120 | 45126 | 131687 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 131687 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 131687 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2265 | C | USCSB2307052A |  | APH-D-09 shift 4.5cm modification | 45120 | 45145 | 5611 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5330.45 | 0.95 | 280.55 | 0 | 280.55 | 0 | [40 empty] | 5330.45 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 2266 | C | USCSB2307053A | -02 | HK Chemical PFA CAP | 45120 | 2023/7/25 2023/7/26 2023/8/4 | 5145.44 | [6 empty] | Valin Corporation | PR Approved | PO Approved | WO R1:Payment Term Change WO R2:Payment Term Change Again(Remove -After acceptance) |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5145.44 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 4344.64 |  | 0 | 0 | 0 |  | 0 | [5 empty] | 800.8 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2267 | C | USCSB2307055A |  | Argon for Chemical welding. Qty: 2. | 45120 | 45132 | 1102.58 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1102.58 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1102.58 | [8 empty] | 1102.58 | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 2268 | C | USCSB2307056A |  | TSMC UPW – 8-111 WWT WRC L20 Sludge Press System Piping | 45120 | 45121 | 420929 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 420928 | 1 | 1 | 0 | 1 | 0 | [39 empty] | 84186 | 0 | 58930 | 0 | 0 | 193627 | 21046 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 63139 | [6 empty] | 12627.87 |  |  |  | 12627.87 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Equipment | USC21C014 | F21P1 WH2SO4 | 2269 | C | USCSB2307058A | -01 | WH2SO4 HUB BOX | 45120 | 2023/7/25 2023/7/26 | 11000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  | WO R1:Trade Term Change (User Informed) | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 11000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1650 |  |  | 11000 | 1650 |  |  |  | 1650 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2270 | C | USCSB2307059A |  | Argon for Chemical welding. Qty: 2. | 45121 | 45132 | 1102.58 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1099.46 | 0.99717 | 3.12 | 0 | 3.12 | 0 | [39 empty] | 976.46 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 121.28 |  |  |  |  | 123 | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Material | USC21C003 | F21P1 UPW | 2271 | C | USCSB2307060A |  | Crating and packing for pipes on site CO | 45121 | 45132 | 4100.76 | [6 empty] | Crating Technology, INC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4100.76 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 4100.76 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2272 | C | USCSB2307061A |  | CGS Global Support | 45121 | 45128 | 650000 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 650000 | 0 | 650000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | Tiger Team | Material | USC23C051 | F21P1 Cable tray installation-tiger team | 2273 | C | USCSB2307062A |  | F21P1 Cable tray installation-tiger team | 45121 | 45134 | 117700 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 117700 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 117700 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | Tiger Team | Material | USC23C041 | TSMC F21 HK Tiger Team | 2274 | C | USCSB2307063A |  | HK Tiger team Cable tray and AC Box | 45121 | 45134 | 141120 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 141120 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 141120 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2275 | C | USCSB2307064A |  | Cush Clamps for Chemical welding. | 45121 | 45125 | 2788.4 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2788.4 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 2788.4 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Triazole | Scaffolding | USC22C022 | F21P1 Triazole treatment system | 2276 | C | USCSB2307065A |  | TSMC WRC Pump Pads(WWT Triazole epoxy) | 45122 | 45183 | 32051 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 32051 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 32051 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC | EDG | Equipment | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 2277 | C | USCSB2307066A |  | Additional crane cost&mobilization&re-direct unloading&reloading&storage cost for Bragg | 45122 | 45125 | 215440 | [6 empty] | Delta Diversified Enterprises, Inc. | PR Approved | PO Approved | Will charge back to Fu Energy with 15% mgmt fee |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 204668 | 0.95 | 10772 | 0 | 10772 | 0 | [38 empty] | 204668 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | 光阻櫃 | Equipment | USC22C012 | CAP_A_MFG_F21 Transportation_光阻櫃 exhasut | 2278 | C | USCSB2307067A |  | P1A Mask Room Proposal – Side A utility Piping Scaffolding | 45122 | 45125 | 28500 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 28500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 28500 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Outsourcing | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2279 | C | USCSB2307068A |  | TEOPM-Team Member Staffing of Alexander Martinez | 7/15/2023 10/4/2024 | 7/20/2023 10/11/2024 | 87818.18 | -11781.82 | 99600 |  |  |  |  | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 87818.18 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 9183 |  | 16762 | 0 | 16185 | 0 |  | 0 | 15808.18 | 0 | 13280 | 16600 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2280 | C | USCSB2307069A | -01 | Subject install Cable tray dividers and insulated cable clamps to meet NEC Electrical code on took KCBDA1 | 2023/7/15 2023/8/10 | 2023/7/21 2023/8/11 | 0 | -2500 | 2500 |  |  |  | V | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 2281 | C | USCSB2307070A |  | Shermco Special Inspection Test | 45125 | 45128 | 84100 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 23200 | 0.27586 | 60900 | 0 | 60900 | 0 | [37 empty] | 11600 |  |  | 0 | 0 | 0 | 0 |  | 0 | 11600 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | cabinet transport | Equipment | USC23C049 | Cabinets transport and installation | 2282 | C | USCSB2307071A |  | F21 Emergency Cabinets B-1 | 45125 | 45145 | 13811.04 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 13811.04 | 1 | 0 | 0 | 0 | 7805 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3936.14 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 1382 | 9874.9 | 2072 |  | - | 2763 | - | 2970 | 0
Base-Build | chemical safety cabinet | MMI | USC23C042 | F21P1 Chemical Safety Cabinet Installation | 2283 | C | USCSB2307072A |  | F21 Emergency Cabinets B-2 | 45125 | 45145 | 13811.04 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 13811.04 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 13811.04 | [8 empty] | 13811.04 | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Equipment | USC23C052 | F21 P1A AMHS PSP & DP Power source breakers | 2284 | C | USCSB2307073A |  | F21 P1A AMHS PSP & DP Power source breakers | 45125 | 45128 | 407782 | [6 empty] | LayerZero Power Systems, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 407782 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 407782 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2285 | C | USCSB2307074A |  | Tech South Hand Tool | 45125 | 45127 | 4828 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4828 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 4828 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2286 | C | USCSB2307075A |  | Glendale 42 Crates Unpack | 45125 | 45135 | 2360 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2360 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 2360 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 2287 | C | USCSB2307076A |  | F21 P1 THC DPT flow meter installation | 45125 | 45131 | 47000 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 43605 | 0.92777 | 3395 | 0 | 3395 | 940 | [39 empty] | 3420 | 10640 | 0 | 2280 | 0 |  | 0 | 5415 | 0 | 0 | 12255 | 9595 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 940 | - | 0 | 0
Others | AMHS | Material | USC22C014 | F21P1 AMHS Power Panel | 2288 | C | USCSB2307077A |  | AMHS Channel Tray for Muratec Interconnection | 45126 | 45127 | 22345.88 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 22345.88 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 10747.92 |  | 0 | 0 | 0 | 0 |  | 0 | 11597.96 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC21C005 | F21P1 Chemical & WCCS package | 2289 | C | USCSB2307079A |  | Tool Hookup Design/Base Build Design/System/Safety | 45126 | 45132 | 900000 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 900000 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 840331.81 |  |  | 59668.19 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2290 | C | USCSB2307080A |  | DIFF1: DOUBLE CASING CONNECTION FOR DIFF1, KDAPK2-4 | 45126 | 45126 | 1980 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1980 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 1980 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2291 | C | USCSB2307081A | -01 | Southwest Fastener Hand Tool | 2023/7/19 2023/8/7 | 2023/7/20 2023/8/8 | 22389 | -1237.43 | 23626.43 |  |  |  |  | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | R1:007 item changed from model 45 to model 44 |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18595 | 0.83054 | 3794 | 0 | 3794 | 0 | [38 empty] | 15727 | 2868 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2292 | C | USCSB2307082A |  | Pillar hand tool | 45126 | 45127 | 3024 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3024 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 3024 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2293 | C | USCSB2307083A |  | Airgas USA | 45126 | 45142 | 26620 | [6 empty] | Airgas USA, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19809.38 | 0.74415 | 6810.62 | 0 | 6810.62 | 0 | [38 empty] | 3602.76 | 2753.2 | 111.75 | 2347.2 | 0 | 0 | 1349.9 | 3713.21 | 372 | 0 | 285 | 0 | 3321.5 |  | 156.15 | 0 | 0 |  | 1272.86 |  | 408.26 | [9 empty] | 115.59 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2294 | C | USCSB2307084A |  | 8-97 MA-174 Additional Scope L20 to L30 Added Valves | 45127 | 45140 | 33789 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 33789 | 0 | 33789 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 30410.1 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2295 | C | USCSB2307085A |  | WWT -L20 Sludge | 45127 | 45133 | 60948.92 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 60948.92 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 32822.77 | 0 | 3029.85 | 0 | 0 |  | 25096.3 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Hot DI | Material | USC23C012 | F21P1 Hot DI Machine Hookup | 2296 | C | USCSB2307086A | -01 | Hot DI long lead parts from Taiwan | 45135 | 2023/7/28 2023/7/29 | 0 | -5680.5 | 5680.5 |  | V |  |  | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved | R1: Change item 8 size, cancel this PR, and submit a new PR. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 2297 | C | USCSB2307087A |  | O&E Electric labor cable pull for KCANN1 and KCANN2 | 45127 | 45133 | 6680 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1820 | 0.27246 | 4860 | 0 | 4860 | 0 | [40 empty] | 1820 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 2298 | C | USCSB2307088A |  | Alvarado Electric labor Cable Pull Labor for KCANN1 and KCANN2 | 2023/7/20 2024/8/14 | 2023/7/27 2024/8/15 | 3840 | -2840 | 6680 | V |  |  |  | Alvarado Electric LLC. | PR Approved | PO Approved | To release excess budgeted contract sum |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3840 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 2640 | 1200 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2299 | C | USCSB2307089A |  | 8-112 Sight Glass Reinforcement | 45127 | 45142 | 30843 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 30843 | 0 | 30843 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 12337 |  |  |  | 15421 |  |  |  | 27758.7 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2300 | C | USCSB2307090A |  | Aid in Tank Inspection | 45127 | 45131 | 9000 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 9000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 9000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 2301 | C | USCSB2307091A |  | 8-115 WWT & Reclaim System Chemical Scope | 45127 | 45139 | 226927 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 197428 | 0.87001 | 29499 | 0 | 29499 | 25665.64 | [39 empty] | 38626 | 0 | 49876 | 0 | 0 |  | 29501 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 52193 |  | 4539 |  |  |  |  | 22692.7 |  |  | 22693 | 22692.7 |  |  |  | 22692.7 |  | 9871.4 |  | - | 9871.4 | - | 5922.84 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2302 | C | USCSB2307092A | -01 | NFPA Diamond Signs Lorry HPM BSGS CUP | 2023/7/20 2023/7/28 | 2023/7/24 2023/8/4 | 12546.18 | 712.38 | 11833.8 | V |  |  | V | Pensacola Hardware Company | PR Approved | PO Approved | R1:Revise item1/item 2 description and price |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10758.98 | 0.85755 | 1787.2 | 0 | 1787.2 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 10758.98 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical Lab | Material | USC22C021 | F21P1 Chemical Lab setup | 2303 | C | USCSB2307093A |  | GC Lab Valve | 45127 | 45128 | 1144.39 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1144.39 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1144.39 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2304 | C | USCSB2307094A |  | CPVC purchase | 45126 | 45126 | 1408.4 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1408.4 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 1408.4 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2305 | C | USCSB2307095A |  | QR LABS Swagelok Interconnect material for KXIM01-07 | 45127 | 45135 | 390.4 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 390.4 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 255.84 | 134.56 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Barcode | NUUO | USC21C012 | F21 Barcode RFID System | 2306 | C | USCSB2307096A |  | F21 P1 Barcode system Engineering | 45128 | 45138 | 1950462 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1576220.76 | 0.80813 | 374241.24 | 0 | 374241.24 | 273064.67 | [38 empty] | 116113.76 |  | 1040099 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 420008 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 97523.1 | 97523.1 | 78018.47
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2307 | C | USCSB2307097A |  | chemical Room UPW/Tank repairs UPW(sight glass flang) | 45128 | 45145 | 5968.25 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 5968.25 | 0 | 5968.25 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 5669.84 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 2308 | C | USCSB2307098A |  | LV 3 – 3rd Party Inspection - June | 45128 | 45135 | 70219.99 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved | Will be back-charged to TSMC |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 70219.99 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 70219.99 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 2309 | C | USCSB2307099A |  | LV 3 – 3rd Party Inspection - July | 45128 | 45135 | 60083.66 | [6 empty] | Technical Inspections Group | PR Approved | PO Approved | Will be back-charged to TSMC |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 60083.66 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 60083.66 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2310 | C | USCSB2307100A |  | Kcann1 Kcann2 change order 4" flex conduit | 45128 | 45138 | 3249.7 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3249.7 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 3249.7 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | MMI | USC21C011 | F21 TMAH System | 2311 | C | USCSB2307101A |  | MIC T-140AA Lining | 45128 | 45148 | 23810 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 23810 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 23810 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Labor | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2312 | C | USCSB2307102A |  | KPADK2-4: SIGNAL CABLES INSTALLATION | 45129 | 45146 | 3500 | [6 empty] | RL Mechanical LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3500 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 3500 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2313 | C | USCSB2307104A |  | Plastic head of hard barricade | 45129 | 45131 | 660 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 660 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 660 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Material | USC22C001 | F21 P1 Office and WH Security and CCTV | 2314 | C | USCSB2307105A |  | F21 P1 CCTV Power Engineering | 45129 | 45139 | 451916.72 | [6 empty] | JB Group of LA, LLC dba Infrastructure Solutions Group | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 451916.72 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 451916.72 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2315 | C | USCSB2307106A |  | F76mmPedestal/2P Raised Floor F76mmPedestal/1P Raised Floor | 45129 | 45141 | 2600 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2600 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 2600 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | TMAH | Material | USC21C011 | F21 TMAH System | 2316 | C | USCSB2307107A | -02 | (35) Joints PP PN6 D110 for Submains | 2023/7/22 2023/9/19 | 2023/8/13 2023/9/19 2023/9/26 | 7653.9 | -5800 | 13453.9 |  |  |  |  | Ferguson Enterprises, LLC | PR Approved | PO Approved | R2:Freight negotiated with a third party R1:Freight negotiated with a third party |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7653.9 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 7653.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2317 | C | USCSB2307108A | -01 | Forward Tilt | 45129 | 2023/8/1 2023/8/7 | 135395.49 | [6 empty] | Forward Tilt, LLC | PR Approved | PO Approved | R1:Payment Terms Improved |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 125455.45 | 0.92659 | 9940.04 | 0 | 9940.04 | 0 | [36 empty] | 67697.75 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 57757.7 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 2318 | C | USCSB2307110A |  | VOC 1 Ground wire | 45129 | 45132 | 1133 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1133 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 1133 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2319 | C | USCSB2307111A |  | Lorry room 40 CCBTU#1 to room 41 Tank B piping design change | 2023/7/24 2023/8/2 | x | 0 | [6 empty] | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | PO Returned for Cancellation, per PM R1:Johnny Wan say this PO need to be cancel |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2320 | C | USCSB2307112A |  | TSMC Offload July | 45133 | 45149 | 172800 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 172800 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 172800 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 2321 | C | USCSB2307113A |  | Temporary Lighting & Power | 45133 | 45134 | 70264 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 70264 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 70264 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2322 | C | USCSB2307114A | -01 | SINGLE TILE BARRICADE for CMP | 45133 | 2023/8/7 2023/8/31 | 0 | -3225.24 | 3225.24 |  |  |  |  | Metzfab Industries | PR Approved | PO Approved | R1:Superceded and replaced by USCSB2308156A |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC21C006 | F21P1 Slurry package | 2323 | C | USCSB2307115A |  | Liberty March invoice and April invoice | 45133 | 45134 | 1876313.76 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved | Will be covered in the GC of TSMC's PO |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1876313.76 | 1 | 0 | 0 | 0 | 0 | [36 empty] | 1876313.76 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2324 | C | USCSB2307116A |  | WRC Bolt-PSS request (Double Order) | 45133 | 45133 | 1224.85 | [6 empty] | Duncan Bolt Co. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1224.84 | 0.99999 | 0.01 | 0 | 0.01 | 0 | [36 empty] | 1224.84 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2325 | C | USCSB2307117A |  | Welder equipment (pipe saw) for Chemical welding. | 45133 | 45133 | 1650 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 1650 | 0 | 1650 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1650 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2326 | C | USCSB2307118A |  | ZCOAT-1: Interconnection material, Basket Trays, Basket Tray 90 Degree Kit | 45133 | 45142 | 1935.83 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1935.83 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 1935.83 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2327 | C | USCSB2307119A | -01 | WWT-PVC material | 45133 | 2023/7/26 2023/9/14 | 747.8 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved | Trade Terms Changed |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 747.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 747.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C005 | F21P1 Chemical & WCCS package | 2328 | C | USCSB2307120A |  | Sunrise Phoenix housekeeping service | 45134 | 45139 | 500000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 499370.23 | 0.99874 | 629.77 | 0 | 629.77 | 0 | [37 empty] | 144815 | 225345.38 | 39313.25 | 51848.37 | 0 | 38048.23 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC21C005 | F21P1 Chemical & WCCS package | 2329 | C | USCSB2307121A | -01 | General labor and Housekeeping Service/Superintendent Service | 2023/7/27 2023/9/11 | 2023/8/1 2023/9/12 | 500000 | -100000 | 600000 |  |  |  |  | Handy Technology Corp. | PR Approved | PO Approved | Adjusting the amount due to Handy Tech been expelled from TSMC site/The workload will be adding to CGS in the future. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 490308.75 | 0.98062 | 9691.25 | 0 | 9691.25 | 0 | [38 empty] | 95459.4 | 394849.35 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2330 | C | USCSB2307123A |  | WRC Temp Mixed Bed Resin Temp Hose | 45134 | 45156 | 5563 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 5563 | 0 | 5563 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2331 | C | USCSB2307124A |  | KXMS01: Locking Receptacle Mfr. Model L18-30R | 45134 | 45142 | 123.25 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 123.25 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 123.25 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2332 | C | USCSB2307125A |  | P0201 foundation modification | 45134 | 45135 | 2900 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2900 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 2900 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2333 | C | USCSB2307126A |  | Argon for Chemical welding. | 45134 | 45139 | 11025.8 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved | This is a blanket order. Payment will be made based on actual consumption. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10925.64 | 0.99092 | 100.16 | -50757.04 | 50857.2 | 0 | [39 empty] | 1027.58 | 0 | 5982.12 | 611.45 | 544.35 |  | 0 | 1628.94 | 20.2 | 0 | 0 |  | 529.15 | 0 | 0 | 0 |  | 0 |  |  |  |  | 661.55 | 37.5 | [5 empty] | 544.35 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C006 | F21P1 Slurry package | 2334 | C | USCSB2307127A | -01 | Slurry H2O2 VMB | 2023/7/27 2023/9/6 2023/9/6 | 2023/7/28 2023/9/6 | 1180.5 | 826.35 | 354.15 |  |  |  |  | SEMITORR GROUP, LLC | PR Approved | PO Approved | PR R2: Qty :9 to 30 PR R1: Adjusting the amount from 9 to 30 based on request. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1180.5 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 314.8 | 42.42 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 823.28 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2335 | C | USCSB2307129A | -01 | Fall Protection System at Lorry | 2023/7/28 2023/8/30 | 2023/8/3 2023/8/30 | 234226 | -3280 | 237506 | V |  |  |  | Milling Machinery, Inc. | PR Approved | PO Approved | Price Reduced to Honor Previous Discussion |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 234226 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 166644 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 58986.7 | 0 | 8595.3 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 2336 | C | USCSB2307130A |  | 5222329-059- THC Scope_Added Material | 45135 | 45140 | 30080 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 30080 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 9277 | 0 | 0 | 0 | 5609 | 0 | 0 | 15194 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2337 | C | USCSB2307131A |  | Additional for GF price increase | 45135 | 45139 | 7891.61 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7891.6 | 1 | 0.01 | 0 | 0.01 | 0 | [36 empty] | 7891.6 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 2338 | C | USCSB2307132A |  | Di Max pipe threading | 45135 | 45141 | 30916 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4978 | 0.16102 | 25938 | 0 | 25938 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 497.8 | 0 | 1991.2 |  | 0 | [5 empty] | 2489 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2339 | C | USCSB2307133A |  | F21 P1 WWT Electric Engineering | 45135 | 45139 | 199820.95 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 199820.95 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 199820.95 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2340 | C | USCSB2307134A |  | Lorry PFD Appeal Chang Order | 45135 | 45139 | 15000 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 15000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 15000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2341 | C | USCSB2307135A |  | TSMC FAB, Lorry, and WRC Field Observation | 45135 | 45139 | 581400 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 416179 | 0.71582 | 165221 | 0 | 165221 | 0 | [39 empty] | 24500 | 38424 | 0 | 0 | 0 |  | 118430 | 0 | 84775 | 0 | 150050 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2342 | C | USCSB2307136A |  | FAB PFD Appeal Change Order | 45135 | 45139 | 15000 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 15000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 15000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2343 | C | USCSB2307137A | -01 | H20A CDA GN2 changes and additions | 2023/7/29 2023/12/12 | 2023/8/3 2023/12/29 | 0 | -123398 | 123398 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2344 | C | USCSB2307138A | -01 | Sump pits and sump pump processing | 2023/7/29 2023/12/12 | 2023/8/3 2023/12/29 | 0 | -11319 | 11319 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2345 | C | USCSB2307139A |  | TGCM Duty Room items – projector | 45136 | 45140 | 533.43 | [6 empty] | Office Depot Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 533.43 | 0 | 533.43 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 533.43 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2346 | C | USCSB2307140A |  | UPW-CCB dry-run | 45136 | 45136 | 650 | [6 empty] | Univar Solutions USA Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 650 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 650 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2347 | C | USCSB2307141A |  | WWT Stripper-packing | 45136 | 45138 | 43660 | [6 empty] | LICI PLASTIC INDUSTRY CO. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 43660 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 6549 |  |  | 0 | 0 | 0 | 0 |  | 0 | 37111 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Hot DI | Material | USC23C012 | F21P1 Hot DI Machine Hookup | 2348 | C | USCSB2307142A |  | Hot DI long lead parts from Taiwan | 45136 | 45138 | 5887.76 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5887.76 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 5887.76 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2349 | C | USCSB2307143A |  | Harrington solvent cement PVC | 45136 | 45138 | 471.75 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 471.75 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 471.75 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2350 | C | USCSB2308001A |  | WWT Tank Crossover Platform Bracket Bonding (112 Bonds Total) | 45139 | 45151 | 54525 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 54525 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8178.75 |  |  |  | 8178.75 | 54525 |  |  | 8178.75 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | UMEC | USC23C054 | UPW Change Order | 2351 | C | USCSB2308003A |  | UMEC UPW Change Order #1 | 45139 | 45150 | 3678899.78 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3062664 | 0.83249 | 616235.78 | 0 | 616235.78 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1231982 |  | 0 | 1830682 | 0 |  | 0 | [8 empty] | 616235.78 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2352 | C | USCSB2308004A |  | Support for CCB Filling Port (tsmc F21P1 Materials) | 45139 | 45148 | 29946 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 29946 | 0 | 29946 | 29946 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 29946
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 2353 | C | USCSB2308005A |  | Mezzanine Epoxy Coatings (WWT -mezz 4 epoxy) | 45139 | 45146 | 108141 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 108141 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 102733.95 | 0 | 0 | 5407.05 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection |  | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2354 | C | USCSB2308007A |  | PFA reducers for AMAT CMP KMOPA2-C, KMOPA5-C, KMOPAB-C | 2023/8/2 2023/8/9 | x | 0 | [7 empty] | PR Approved | PO Approved | RETURN & CANCEL R1:no Longer need product |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2355 | C | USCSB2308008A |  | AMAT CMP，Interconnection material KMOPA2-C, KMOPA5-C, KMOPAB-C, 3/8'' PFA | 45140 | 45142 | 700 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 700 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 700 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2356 | C | USCSB2308009A | -01 | tsmc Fab21 - AMHS Technical Service | 2023/8/2 2023/8/14 | 2023/8/16 2023/8/18 | 225400 | -96600 | 322000 |  |  |  |  | Marketech International Corp. | PR Approved | PO Approved | R1:Remove Tax Item in WO |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 225400 | 0 | 225400 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 2357 | C | USCSB2308010A | -01 | UPW HP1037 & HP1137 Additional DS(TSMC F21P1 UPW Electrical and Controls) | 45140 | 2023/8/11 2023/9/19 | 31839.45 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved | R1:T & C dispute |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 28655.51 | 0.9 | 3183.94 | 0 | 3183.94 | 31839.44 | [40 empty] | 0 | 0 | 0 | 0 | 15919.73 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 12735.78 | [8 empty] | 15919.72 |  | - | 0 | - | 15919.72 | 0
Base-Build | WWT | Equipment | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2358 | C | USCSB2308012A |  | Fab 21 B LB2 (7 Tank Media Loading) Phoenix, Arizona | 45141 | 45168 | 64096 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 64096 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 38632.86 |  | 0 | 25463.14 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2359 | C | USCSB2308013A |  | WWT 6in CPVC | 45141 | 45149 | 7274 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7274 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 7274 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 2360 | C | USCSB2308014A |  | Modify, orbital weld and install existing spools. Fabricate, orbital weld, and install new spools for KCANN1 and KCANN2 | 45141 | 45141 | 27595 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27595 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 27595 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | MMI | USC21C006 | F21P1 Slurry package | 2361 | C | USCSB2308015A |  | Slurry Room Raised Gratings. | 45141 | 45142 | 4587 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4587 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 4587 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2362 | C | USCSB2308016A |  | CED cable for Hand Tool | 45141 | 45174 | 991453.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 991453.48 | 1 | 0.02 | 0 | 0.02 | 0 | [38 empty] | 436214.59 |  | 0 | 237260.87 | 0 | 0 |  | 0 | 253153.09 | 0 | 0 | 0 |  |  | 0 | 64824.93 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2363 | C | USCSB2308017A |  | TGCM Duty Room items – screen | 45142 | 45142 | 234.78 | [6 empty] | Office Depot Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 234.78 | 0 | 234.78 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 234.78 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2364 | C | USCSB2308018A | -01 | TGCM Duty Room items – white board and cabinets | 2023/8/4 2023/8/22 2024/3/8 | 2023/9/27 2024/3/8 | 1295.98 | [6 empty] | Zoro Tools, Inc. | PR Approved | PO Approved | PR R1:Remove wardrobe locker item WO R1: Revise the amount to align with actual order |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1295.98 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1295.98 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2365 | C | USCSB2308019A | -01 | TGCM Duty Room items – fridge | 45142 | 2023/9/27 2024/3/5 | 2899 | -457.91 | 3356.91 | V |  |  |  | Zoro Tools, Inc. | PR Approved | PO Approved | R1: Change Ship-to Address and lower the amount to align with actual order |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 2899 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2899 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2366 | C | USCSB2308020A |  | TGCM Duty Room items – Microwave | 45142 | 45142 | 154.99 | [6 empty] | The Home Depot, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 154.99 | 0 | 154.99 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 154.99 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2367 | C | USCSB2308021A | -01 | F21 P1 CDS POWER CABLE | 2023/8/4 2023/8/9 | 2023/8/7 2023/8/15 | 53527.38 | 26763.69 | 26763.69 |  |  | V |  | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1:revise QTY and price (Double QTY) |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 53527.38 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 53527.38 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 2368 | C | USCSB2308023A |  | 8-120 WRC NaOH and H2SO4 WWT Chemical Lines | 45142 | 45152 | 440215 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 250923 | 0.57 | 189292 | 0 | 189292 | 20073.84 | [40 empty] | 0 | 61630 | 0 | 66032 |  | 44022 | 0 | 0 | 0 | 0 |  | 79239 | 0 | 0 | 0 |  | 0 |  |  |  |  | 44021.5 |  |  |  | 44021.5 |  |  |  | 44021.5 |  | 0 |  | - | 0 | - | 0 | 0 | 20073.84
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 2369 | C | USCSB2308024A |  | 4” and 6” FNW gaskets | 45142 | 45142 | 179.52 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 179.52 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 179.52 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C006 | F21P1 Module Tool Interconnection EPI | 2370 | C | USCSB2308025A |  | Cable trays and related hardware for AMAT EPI KCENA1 | 45142 | 45145 | 4046.02 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4046.02 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 4046.02 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2371 | C | USCSB2308026A |  | Damaged Instrument Sensors | 45142 | 45142 | 1914 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1914 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1914 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2372 | C | USCSB2308027A |  | EBO: ZASC5，Interconnection material Flange Nut, Washer, Cube nut, Hex screw, Self tapping screw | 45142 | 45156 | 103.41 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 103.41 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 17.19 | 86.22 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2373 | C | USCSB2308028A |  | WWT material for drain & system | 45143 | 45153 | 9066.6 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5855.1 | 0.64579 | 3211.5 | 0 | 3211.5 | 2049.285 | [40 empty] | 0 | 0 | 0 | 0 |  | 5855.1 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 453.33 |  |  |  | 906.66 |  |  |  | 453.33 |  | 2049.285 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | Material | USC23C047 | F21P1 HK Seismic Installation | 2374 | C | USCSB2308029A |  | QR,EBO seismic installation | 2023/8/5 2024/6/7 | 2023/8/11 2024/7/4 | 0 | -70953.81 | 70953.81 |  |  |  |  | Greenberry Industrial | PR Approved | PO Approved | R1: Work area constraint affect quote |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2375 | C | USCSB2308030A | -01 | Hard barricade bolt | 45143 | 2023/8/7 2023/8/8 | 1327.4 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved | R1:remark revised |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1327.4 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1327.4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2376 | C | USCSB2308031A |  | AET-E-13 Rework and Added Supports | 45143 | 45143 | 2024 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1922.8 | 0.95 | 101.2 | 0 | 101.2 | 0 | [40 empty] | 1922.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2377 | C | USCSB2308033A |  | AET-F-05 Rework | 45145 | 45145 | 2004 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1903.8 | 0.95 | 100.2 | 0 | 100.2 | 0 | [40 empty] | 1903.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2378 | C | USCSB2308034A |  | AET-G-05 Rework | 45145 | 45145 | 4609 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4378.55 | 0.95 | 230.45 | 0 | 230.45 | 0 | [40 empty] | 4378.55 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2379 | C | USCSB2308035A |  | MIC - TSMC Tooling Foundations-AET-G-07 Rework | 45145 | 45145 | 2204 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2093.8 | 0.95 | 110.2 | 0 | 110.2 | 0 | [40 empty] | 2093.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2380 | C | USCSB2308038A |  | Added Support Legs, Larger Holes AET-G-14 | 45145 | 45145 | 2104 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1998.8 | 0.95 | 105.2 | 0 | 105.2 | 0 | [40 empty] | 1998.8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | 2D/3D drawing | Labor | USC23C022 | F21P1_H_2D/3D drawing | 2381 | C | USCSB2308039A |  | 3D Drawing Support | 45145 | 45166 | 117660 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 117660 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 117660 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2382 | C | USCSB2308040A |  | Swap 1000 pcs tiles from Greenberry | 45146 | 45149 | 17524.98 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 12852.82 | 0.7334 | 4672.16 | 0 | 4672.16 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 12852.82 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection |  | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2383 | C | USCSB2308041A |  | DIFF1: Orientation Cost for 8395 – 2 HRS & OSIP Orientation – 8 HRS | 2023/8/8 2023/8/24 | x | 0 | [7 empty] | PR Approved | PO Approved | Voided per email dated 8/8 from Rosa Brual. Training cost will not be reimbursed. R1:MICU does not cover 8395 & OSIP orientation |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 2384 | C | USCSB2308042A |  | 250 MULTI CONDUCTOR (F21 P1 VOC2 and 7 wire order) | 45146 | 45148 | 402952.8 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 402952.8 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 402952.8 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2385 | C | USCSB2308043A |  | DIFF1: 16 TOOLS – LABOR/MATERIAL FOR GALVANIZED DUCTS/ELBOWS BLOWER BOX | 2023/8/8 2023/12/5 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1:RESUBMIT AS STREIMER IN POS UNDER USC23B002 |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2386 | C | USCSB2308044A |  | WWT -Sludge/Triazole shortage materials | 45146 | 45153 | 23550.84 | [6 empty] | Ferguson Enterprises, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 13848.24 | 0.58801 | 9702.6 | 0 | 9702.6 | 5677.7784 | [40 empty] | 0 | 0 | 0 | 11035.15 |  | 0 | 0 | 0 | 0 | 0 | 2813.09 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1177.542 |  |  |  | 2355.084 |  |  |  | 2355.084 |  | 2769.648 |  | - | 2908.1304 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2387 | C | USCSB2308045A |  | QR Labs，Interconnection material FAD Lab tools, VCT Series Cable 600A 18 AWG 3C | 45146 | 45147 | 364 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 364 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 364 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2388 | C | USCSB2308046A |  | TSMC UPW – 8-128 WRC HCl Flange Break | 45146 | 45149 | 23172 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 23172 | 0 | 23172 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC23C056 | Fab LB2 Trench Cleaning | 2389 | C | USCSB2308047A | -01 | FAB Building LB2 Trench Clean | 2023/8/8 2024/3/15 | 2023/8/16 2024/3/19 | 0 | -142659.2 | 142659.2 |  |  |  |  | Handy Technology Corp. | PR Approved | PO Approved | PR R1: Handy Tech had been expelled from TSMC site last year and this PO might already billed to another PO due to T&M contract. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2390 | C | USCSB2308048A |  | Techsouth Hand tool 02 | 45146 | 45147 | 565 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 565 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 565 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2391 | C | USCSB2308049A |  | TGCM Duty Room items – Tan lockers (Qty:10) | 45146 | 45152 | 8298.35 | [6 empty] | High Density, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8298.35 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 8298.35 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2392 | C | USCSB2308050A |  | Strut Anchor for construction work.(Qty:90) | 45147 | 45154 | 7475.4 | [6 empty] | Jendco Safety Supply | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7475.4 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 7475.4 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2393 | C | USCSB2308051A |  | QRLAB: Special request per TSMC. Installing conduit/tray for LAN cables for PCs in the QR Labs area. | 45147 | 45164 | 17818.4 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 16339.96 | 0.91703 | 1478.44 | 0 | 1478.44 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 8669.18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 7670.78 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2394 | C | USCSB2308052A |  | Dual Contained Pipe testing(Pressure test tools for Lorry) | 45147 | 45152 | 1972 | [6 empty] | M. Caputo Technical Services, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1972 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1972 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2395 | C | USCSB2308053A |  | AMAT WIRE FOR POWER TRANSFORMER CONNECTION | 45147 | 45153 | 42180 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 42180 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 42180 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2396 | C | USCSB2308054A |  | Power Hardware | 45147 | 45154 | 171508.88 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 171508.88 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 8513.06 | 0 | 0 |  | 0 | 0 | 0 | 162995.82 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Equipment | USC23C036 | F21P1 AMAT Interconnection | 2397 | C | USCSB2308055A |  | Raised Floor For AMAT Tools to Meet NEC Co | 45147 | 45148 | 3700 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3700 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 3700 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Outsourcing | USC22C025 | AMHS TSMC Instrustructure and Branch Circuits | 2398 | C | USCSB2308056A |  | Superintendent staffing | 45147 | 45156 | 193200 | [6 empty] | Teo Services, Inc. DBA TEOPM | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 193200 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 61274.94 |  | 30246.78 | 32813 | 31612.5 | 0 |  | 0 | 24592.39 | 0 | 12660.39 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2399 | C | USCSB2308057A |  | Uline Hand Tool | 45147 | 45152 | 8700 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8700 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 8700 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2400 | C | USCSB2308058A |  | Swagelok Hand Tools | 45147 | 45152 | 1810.72 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1810.72 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 1810.72 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2401 | C | USCSB2308059A |  | 500 MCM B Side | 45147 | 45154 | 172111.26 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 172111.26 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 172111.26 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 2402 | C | USCSB2308060A |  | F21 P1 VOC Engineering | 45148 | 45184 | 257361 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 257361 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 257361 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 2403 | C | USCSB2308061A |  | WRC L20 Lab Island and Fume Hood | 45148 | 45150 | 2647 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2647 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 2647 |  |  | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C053 | AMAT Interconnection (TSMC) | 2404 | C | USCSB2308062A |  | Labor for Rosendin | 45148 | 45151 | 2500 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2500 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 2500 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C046 | F21P1 ATS Interconnection | 2405 | C | USCSB2308063A |  | ATS Chillers for Dry ETC tools | 45148 | 45161 | 159023 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 159023 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 159023 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2406 | C | USCSB2308064A |  | TSMC FAB1 TI Foundations(ABS-A-03 re-work) | 45148 | 45163 | 6706 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6706 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 6706 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Material | USC23C015 | F21P1 AMHS Wiring Work Outline | 2407 | C | USCSB2308065A |  | Channel Tray Elbows and Covers | 45148 | 45152 | 8792.8 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 8792.8 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 8792.8 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C014 | F21P1 WH2SO4 | 2408 | C | USCSB2308066A |  | MIC Three and Seven Trailer Hookup | 45149 | 45153 | 24830 | [6 empty] | Wilson Electric Services Corporation | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 24830 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 24830 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 2409 | C | USCSB2308067A |  | WRC UPW Electrical Permit Drawing Revision | 45149 | 45155 | 12950 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 12900 | 0.99614 | 50 | 0 | 50 | 0 | [39 empty] | 12900 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 2410 | C | USCSB2308068A | -01 | VOC 3 and VOC 2 railing removal | 45149 | 2023/9/15 2023/9/20 | 0 | -4512.09 | 4512.09 |  |  |  |  | Southland Industries | PR Approved | PO Approved | R1:Cancel, per responsible engineer. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2411 | C | USCSB2308069A |  | Lorry PFD Review and S&S Rupture Disk Calculation | 45150 | 45162 | 3000 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 3000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Site Expense | USC21C005 | F21P1 Chemical & WCCS package | 2412 | C | USCSB2308070A |  | Self-Retracting Lifeline for Chemical/TPC work. | 45150 | 45162 | 1218.08 | [6 empty] | Amazon.com, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 1218.08 | 0 | 1218.08 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2413 | C | USCSB2308071A |  | Big Ass Fans Glendale Warehouse Industrial Fans | 45153 | 45163 | 121640.6 | [6 empty] | Delta T, LLC dba Big Ass Fans | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 121640.6 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 78659 | 0 | 0 | 0 | 0 |  | 32896 | 0 | 0 | 0 | 10085.6 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2414 | C | USCSB2308072A |  | Lorry A&B Crossover Steps | 45153 | 45168 | 70136 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 70136 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 52602 | 0 |  | 0 | 14027.7 | 0 | 0 | 0 |  |  | 3506.3 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 2415 | C | USCSB2308073A |  | F21 P1 VOC 2 k-type wire order | 45153 | 45154 | 1615 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1615 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 1615 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2416 | C | USCSB2308074A |  | DIFF1: KDAPK2-4, Install triple layer containment | 45153 | 45216 | 49904 | [6 empty] | Trident Mechanical Services | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 49904 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 49904 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC23C054 | UPW Change Order | 2417 | C | USCSB2308075A | -01 | F21 P1 VOC Extended General Conditions | 2023/8/15 2023/11/6 | 2023/9/13 2023/11/6 | 1290937.49 | 110904.49 | 1180033 |  |  |  |  | Southland Industries | PR Approved | PO Approved | R1: Adjusting the amount for extended GC according to PM's request. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1290937.49 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 865303 | 0 | 104910 | 104910 | 0 | 104910 |  |  | 110904.49 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC23C054 | UPW Change Order | 2418 | C | USCSB2308077A | -01 | F21 P1 UPW/CDS Change Order | 45153 | 2023/8/30 2024/2/23 | 705000 | -295000 | 1000000 |  |  |  |  | Rosendin Electric, Inc. | PR Approved | PO Approved | PO R1 :As per PM:Kate Wu,adjusting the PR amount to align with the actual PO; to release the budget for the project per request. |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards | [7 empty] | 705000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 705000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2419 | C | USCSB2308078A |  | EBO: ZCOAT1 - Interconnection material Pedestal Clamps | 45153 | 45154 | 1216 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1216 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 1216 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2420 | C | USCSB2308079A |  | EBO: ZMERIT1 - Galvanized Steel for F76mmPedestal/1P Raised Floor | 2023/8/15 2024/8/2 | 2023/8/15 2024/8/7 | 0 | -496 | 496 |  |  |  | V | TCELC CO., LTD | PR Approved | PO Approved | R1: VOID - PER PM change scope and PURCHASING |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2421 | C | USCSB2308080A |  | DIF: 21 TOOLS - ?” VCR gland, Female nuts and gasket | 2023/8/15 2024/8/6 | 2023/8/17 2024/8/7 | 6085.75 | -0.05 | 6085.8 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | To revise final invoice amount |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 6085.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 6085.75 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C006 | F21P1 Module Tool Interconnection EPI | 2422 | C | USCSB2308081A |  | EPI: KCEPS1 – CABLE PULLS | 45153 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C006 | F21P1 Module Tool Interconnection EPI | 2423 | C | USCSB2308082A |  | EPI: KCEPS3 – CABLE PULLS | 45153 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C006 | F21P1 Module Tool Interconnection EPI | 2424 | C | USCSB2308083A |  | EPI: KEXR01 – CABLE PULLS | 45153 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 2425 | C | USCSB2308084A |  | BLINE BVT200YZN 2IN PIPE CLMPS for AMAT PVD1&2 DIMAX water hoses | 45154 | 45159 | 919.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 919.2 | 1 | 0 | 113313.6 | -113313.6 | 0 | [40 empty] | 0 | 919.2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2426 | C | USCSB2308085A |  | Swap 1000 pcs tiles from PCI | 45154 | 45168 | 197483 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 160554 | 0.813 | 36929 | 0 | 36929 | 0 | [40 empty] | 0 | 0 | 160554 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C006 | F21P1 Module Tool Interconnection EPI | 2427 | C | USCSB2308086A |  | EPI: KCEPS1 - UNITSTRUT & CONDUIT | 45154 | 45155 | 763.67 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 760.34 | 0.99564 | 3.33 | 0 | 3.33 | 0 | [40 empty] | 682.34 | 0 | 0 | 0 |  | 0 | 0 | 78 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | NUUO | USC23C054 | UPW Change Order | 2428 | C | USCSB2308087A |  | F21 Warehouse CCTV over time and CO | 45154 | 45163 | 670874.78 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 660865.38 | 0.98508 | 10009.4 | 0 | 10009.4 | 6708.75 | [38 empty] | 26262 |  | 0 | 0 | 477987.13 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 156616.25 |  | 0 | [14 empty] | 0 |  | - |  | - | 0 | 0 | 6708.75
Base-Build | UPW | UMEC | USC23C054 | UPW Change Order | 2429 | C | USCSB2308088A |  | UMEC UPW Change Order #2 | 45154 | 45184 | 3202670 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3034614 | 0.94753 | 168056 | 0 | 168056 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1943918 | 0 |  |  | 0 | 0 | 1090696 |  | 0 |  |  |  |  | 168056 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC23C045 | WWT Change Order (Piping) | 2430 | C | USCSB2308089A |  | PSS WWT Project. For invoice SW-23-0131 Final | 45154 | 45154 | 1649670.58 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1649670.58 | 1 | 0 | 0 | 0 | 0 | [37 empty] | 1000000 | 649670.58 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2431 | C | USCSB2308090A |  | Straight connector for liquid tight conduit | 45154 | 45157 | 15105.54 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 15105.54 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 15105.54 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 2432 | C | USCSB2308091A |  | tsmc Fab21 - AMHS Technical Service | 45154 | 45167 | 426380 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 426380 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 426380 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2433 | C | USCSB2308092A |  | Veolia turbo bed-3rd | 45155 | 45157 | 47217.47 | [6 empty] | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 47217.47 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 47217.47 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2434 | C | USCSB2308093A |  | L30 PDP Panel Move to clean room | 45155 | 45168 | 1228 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1228 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1228 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Rosendin | USC21C006 | F21P1 Slurry package | 2435 | C | USCSB2308094A |  | CDS 2” Conduit in Lorry change order | 45155 | 45168 | 898441.26 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 898441.26 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 898441.26 | - | 0 | - | 0 | 0
Base-Build | TMAH | MIMO/Rigging | USC21C011 | F21 TMAH System | 2436 | C | USCSB2308095A |  | MIC-116-23 Equipment Move in FAB LB2 column A.5/10 | 45155 | 45161 | 7796 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7796 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 7796 | [6 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C006 | F21P1 Module Tool Interconnection EPI | 2437 | C | USCSB2308096A |  | EPI: General use - U-Style Crimper & 1/0 U-Style Die | 45155 | 45160 | 2451.75 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2451.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 2451.75 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2438 | C | USCSB2308097A |  | Lorry tank (CDS+WCCS) self-closing swing door. | 45155 | 45169 | 26000 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 26000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 26000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2439 | C | USCSB2308098A |  | Unions to Correct MIC Taiwan M4 cabinets | 45155 | 45157 | 82.4 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 82.4 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 82.4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2440 | C | USCSB2308099A |  | MCP Bottom Plates | 45155 | 45159 | 10119.46 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10119.46 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 10119.46 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2441 | C | USCSB2308100A |  | RFQ – MIC – Stripper System Piping, Pumps, Outside Tanks - Insulation | 45155 | 45205 | 658791.27 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 658791.27 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 284591.39 | 0 | 24904.87 |  | 0 | 129031.91 | 220263.1 |  | 0 | [8 empty] | 32939.5635 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 2442 | C | USCSB2308101A |  | TSMC UPW-8-127 WWT LB2 Chemical Piping-Group 2 | 45156 | 45169 | 294133 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 252955 | 0.86 | 41178 | 0 | 41178 | 35413.7 | [40 empty] | 0 | 0 | 0 | 0 | 73533 | 0 | 0 | 111771 | 0 | 0 |  |  | 0 | 0 | 26472 |  | 0 |  |  |  |  | 14706.65 |  |  | 41179 | 29413.3 |  |  |  | 29413.3 |  | 12647.75 |  | - | 12647.75 | - | 10118.2 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2443 | C | USCSB2308102A |  | WWT-double pipe certification | 45156 | 45168 | 10434.99 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 10234.99 | 0.98083 | 200 | 0 | 200 | 204.6998 | [40 empty] | 0 | 10234.99 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 204.6998
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2444 | C | USCSB2308103A |  | Hua Yi Construction Az On-site Clean Room Construction | 45156 | 45163 | 62000 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 62000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 58900 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 3100 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2445 | C | USCSB2308104A |  | Change order – conduit install for signal cable routing from L20 to L10 for KCANN1 and KCANN2 | 45156 | 45156 | 76.59 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 76.59 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 76.59 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C014 | F21P1 AMHS Power Panel | 2446 | C | USCSB2308105A |  | AMHS L40 Relocation | 45156 | 45162 | 18434.62 | [6 empty] | Marquis Construction Services LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 10529.16 | 0.57116 | 7905.46 | 0 | 7905.46 | 0 | [40 empty] | 10529.16 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 2447 | C | USCSB2308106A |  | BPG termination | 45156 | 45157 | 500000 | [6 empty] | BPG Technologies, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 500000 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 500000 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2448 | C | USCSB2308107A |  | Change order – conduit install for signal cable routing from L20 to L10 KCANN2 | 45157 | 45156 | 116.71 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 116.71 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 116.71 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 2449 | C | USCSB2308108A |  | Page Observation for FAB and WRC UPW | 45157 | 45163 | 92340.75 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 92340.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 92340.75 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 2450 | C | USCSB2308109A |  | Field Observation for FAB UPW | 45157 | 45180 | 41760 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 41760 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 25056 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 16704 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC21C007 | F21P1 VOC package （Installation ) | 2451 | C | USCSB2308110A |  | Field Observation for FAB VOC | 45157 | 45180 | 41760 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 41760 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 41760 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2452 | C | USCSB2308111A |  | Field Observation for FAB WWT & WWD | 45157 | 45180 | 78732 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 47239.2 | 0.6 | 31492.8 | 0 | 31492.8 | 28343.52 | [40 empty] | 0 | 0 | 0 | 47239.2 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3936.6 |  |  |  | 7873.2 |  |  |  | 7873.2 |  | 7085.88 |  | - | 7085.88 | - | 14171.76 | 0 | 0
Interconnection | Interconnection | Labor | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2453 | C | USCSB2308112A |  | Labor for Rosendin DIFF Mainframe Tansformer Power System (Vulcan/Mozart) install a 4/0 4W Tray Cable from the Mainframe tran | 45157 | 45160 | 13713.7 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 6856.85 | 0.5 | 6856.85 | 0 | 6856.85 | 0 | [40 empty] | 0 | 0 | 6856.85 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2454 | C | USCSB2308113A |  | Field Observation for WRC WWT | 45157 | 45180 | 188856 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 56656.8 | 0.3 | 132199.2 | 1490 | 130709.2 | 39659.76 | [40 empty] | 0 | 0 | 0 | 56656.8 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 18885.6 |  |  |  | 18885.6 |  |  |  | 18885.6 |  | 11331.36 |  | - | 11331.36 | - | 11331.36 | 5665.68 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2455 | C | USCSB2308114A |  | 1/2" union Qty 5/1/4" gasket Qty 50 For Chemical welding | 45157 | 45159 | 242.25 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 242.05 | 0.99917 | 0.2 | 0 | 0.2 | 0 | [40 empty] | 242.05 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC21C008 | F21P1 CCTV & Security | 2456 | C | USCSB2308115A |  | F21 P1 CCTV Engineering | 45157 | 45175 | 200000 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 200000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 199875 | 0 | 0 | 0 |  | 0 | 0 | 0 | 125 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC22C001 | F21 P1 Office and WH Security and CCTV | 2457 | C | USCSB2308116A | -01 | F21 P1 CCTV Engineering (San Tan Fire, LLC) | 2023/8/19 2023/12/12 | 2023/9/6 2023/12/29 | 41938 | -158062 | 200000 | V |  |  |  | San Tan Fire, LLC | PR Approved | PO Approved | R1: As per Paul: This order is T&M, and there is no further manpower requirement. |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 41938 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 41938 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2458 | C | USCSB2308117A |  | TOC Replacement Parts | 45157 | 2023/8/23 2023/9/26 | 0 | -10965 | 10965 |  |  |  |  | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2459 | C | USCSB2308117B |  | TOC Replacement Parts | 45157 | 2023/8/22 2023/9/26 2023/9/27 | 10965 | [6 empty] | Veolia WTS Analytical Instruments, Inc. | PR Approved | PO Approved | R1:incorrect Veolia entity |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 10965 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10965 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2460 | C | USCSB2308118A |  | WWT -BMWC Tunnel Trestle r2 | 45157 | 45162 | 590060 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 590060 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 89888.05 | 0 |  | 415522.21 | 55146.76 | 0 | 0 | 0 |  |  | 29502.98 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | W-H2SO4 | Material | USC21C014 | F21P1 WH2SO4 | 2461 | C | USCSB2308119A |  | W-H2SO4 Electrical Work | 8/19/2023 8/17/2024 | 9/21/2023 8/24/2024 | 384750 | -65250 | 450000 |  |  |  | V | Hua Yi Construction AZ, Inc | PR Approved | PO Approved | R1: As per Jim to closeout the PO. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 384750 | 1 | 0 | 0 | 0 | 53865 | [40 empty] | 384750 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 22500 |  |  |  | 22500 | [5 empty] | 19237.5 |  | - | 19237.5 | - | 15390 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2462 | C | USCSB2308121A |  | 15 Pound PVDF and PP Welding Rod Coil, 3mm,standard loose coil | 45157 | 45161 | 1301.75 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1301.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 1301.75 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 2463 | C | USCSB2308122A |  | Greenberry’s Time and Material pricing for work related to the ETC iPUP Mechanical s | 45157 | 45160 | 19131 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 18174.45 | 0.95 | 956.55 | 0 | 956.55 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 13478.6 | 0 | 4695.85 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C006 | F21P1 Module Tool Interconnection EPI | 2464 | C | USCSB2308123A |  | EPI Pump Fore Line Adapter Vent Connection R2 | 45157 | 45160 | 7086 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 7086 | 0 | 7086 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | CCE | USC23C054 | UPW Change Order | 2465 | C | USCSB2308124A |  | F21 P1 WWT Electric Engineering-CCE | 45160 | 45168 | 986866.74 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 986866.74 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 986866.74 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | CCTV | Equipment | USC22C001 | F21 P1 Office and WH Security and CCTV | 2466 | C | USCSB2308125A |  | F21P1 OFFICE Security and CCTV System | 45160 | 45163 | 730573 | [6 empty] | Aegis Technology Inc | PR Approved | PO Approved | Change order for USCSB2205008A because of withholding tax |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 304794 | 0.4172 | 425779 | 0 | 425779 | 0 | [39 empty] | 244171 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 60623 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2467 | C | USCSB2308126A |  | UPW-8/20 Sunday work for commissioning check | 45160 | 45161 | 8802 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 8802 | 0 | 8802 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 8802 | [7 empty] | 8361.9 |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 2468 | C | USCSB2308127A |  | Change order – conduit install for signal cable routing from L20 to L10 KECOT2 | 45160 | 45160 | 398.09 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 235.11 | 0.5906 | 162.98 | 0 | 162.98 | 0 | [40 empty] | 0 | 235.11 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 2469 | C | USCSB2308128A |  | Change order – conduit install for signal cable routing from L20 to L10 KESRT4 | 45160 | 45160 | 398.09 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 389.02 | 0.97722 | 9.07 | 0 | 9.07 | 0 | [40 empty] | 0 | 389.02 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2470 | C | USCSB2308129A |  | TangCheng Hardware | 45160 | 45169 | 303100 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 300100 | 0.9901 | 3000 | 0 | 3000 | 0 | [40 empty] | 0 | 0 | 300100 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2471 | C | USCSB2308132A |  | Lorry A FNDP001 Materials | 45160 | 45162 | 6261.75 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 6261.75 | 0 | 6261.75 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C003 | F21P1 UPW | 2472 | C | USCSB2308133A |  | WWT Lab Furniture Installation | 45161 | x | 0 | [7 empty] | PR Approved | PO Approved | PR Returned - use mic general labor |  | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2473 | C | USCSB2308134A |  | Unions For Chemical welding. | 45161 | 45161 | 72.25 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 72.25 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 72.25 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2474 | C | USCSB2308135A |  | Southwest Fastener Monthly Order | 45161 | 45163 | 12959.18 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12586.95 | 0.97128 | 372.23 | 0 | 372.23 | 0 | [39 empty] | 4733.33 | 7853.62 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 372.23 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2475 | C | USCSB2308136A |  | Additional Dry Type Transformer Testing | 45161 | 45161 | 58000 | [6 empty] | Shermco Industries, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 54157.5 | 0.93375 | 3842.5 | 0 | 3842.5 | 0 | [39 empty] | 7250 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 46907.5 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC21C006 | F21P1 Slurry package | 2476 | C | USCSB2308137A |  | Liberty May 01 | 45161 | 45163 | 116678.45 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 116678.45 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 116678.45 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC21C007 | F21P1 VOC package （Installation ) | 2477 | C | USCSB2308138A |  | Liberty May 02 | 45161 | 45163 | 115322.66 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 115322.66 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 115322.66 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC22C006 | TSMC F21P1 EUV Overhead Cranes in Area A of FAB Building | 2478 | C | USCSB2308139A |  | Liberty May 03 | 45161 | 45163 | 100000 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 100000 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC22C024 | UIS Scaffolding | 2479 | C | USCSB2308140A |  | Liberty May 04 | 45161 | 45163 | 851774.5 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 851774.5 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 851774.5 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC23C045 | WWT Change Order (Piping) | 2480 | C | USCSB2308141A |  | Liberty May 05 | 45161 | 45163 | 82841.89 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 82841.89 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 82841.89 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2481 | C | USCSB2308142A |  | chemical storage platform handrail rework | 45161 | 45163 | 154070 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 154070 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 46221 | 0 |  | 53924.5 | 0 | 0 | 24012 | 0 | 22209 |  | 0 | 0 | 0 |  | 0 | [12 empty] | 7703.5 |  | 0 | 7703.5 | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2482 | C | USCSB2308143A |  | CVD2 Ball valve for interconnection KCANN1, KCANN3, KCANN4, KCANN7 | 45162 | 45163 | 1310.1 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1310.1 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 1310.1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | EDG | MIMO/Rigging | USC22C003 | TSMC Fab21 Project Phase 1 EDG Package | 2483 | C | USCSB2308144A |  | ATS Polisher Change Location | 45162 | 45163 | 29261 | [6 empty] | Sundt Construction, Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 27771 | 0.94908 | 1490 | 0 | 1490 | 0 | [40 empty] | 0 | 0 | 27771 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2484 | C | USCSB2308145A |  | Machine to move personnel and equipment in a vertical direction | 2023/8/24 2023/9/2 | 45238 | 4401.61 | 1275.49 | 3126.12 |  |  |  |  | United Rentals | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 4401.61 | 0 | 4401.61 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C047 | F21P1 HK Seismic Installation | 2485 | C | USCSB2308146A |  | Seismic bracket modification for ME dept. 1st batch | 45161 | 45161 | 679.9 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 679.9 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 679.9 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Southland | USC21C006 | F21P1 Slurry package | 2486 | C | USCSB2308147A |  | Cut slurry CDA/GN2(14 ea) caps and reweld | 45162 | 45188 | 11857.9 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 11857.9 | 12295.2 | -437.3 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C047 | F21P1 HK Seismic Installation | 2487 | C | USCSB2308148A |  | Seismic bracket modification for ME dept. 2nd batch | 45161 | 45161 | 679.9 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 679.9 | 0 | 679.9 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2488 | C | USCSB2308149A |  | Lorry FNDP room parts for Chemical welding. | 45162 | 45163 | 16574.85 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 16256.48 | 0.98079 | 318.37 | 0 | 318.37 | 0 | [40 empty] | 0 | 16256.48 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 318.37 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 2489 | C | USCSB2308150A |  | KESDA1 Time and Material pricing for work related to the ETC iPUP Mechanical scope | 45162 | 45180 | 19131 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19131 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 19131 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C006 | F21P1 Module Tool Interconnection EPI | 2490 | C | USCSB2308151A |  | Greenberry labor- Offsite labor to drill and hand weld SS-8-VCR-3-8MTW to 0050-53004 pumping line adapter | 45162 | 45180 | 7086 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 6731.7 | 0.95 | 354.3 | 0 | 354.3 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 6731.7 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2491 | C | USCSB2308152A |  | Change order for KSSBA3 REI Labor. | 45163 | 45163 | 816 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 816 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 816 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2492 | C | USCSB2308154A |  | CMP: NO TOOL ID: SINGLE TILE BARRICADE | 45162 | 45167 | 3615.06 | [6 empty] | Metzfab Industries | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 3615.06 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 3615.06 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C003 | F21P1 UPW | 2493 | C | USCSB2308155A |  | WWT Testing support | 45163 | 45166 | 126010 | [6 empty] | Jettech System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 126010 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 126010 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2494 | C | USCSB2308156A |  | QR LABS: CHAD/FAD LABS - Lan Cable Tray | 45163 | 45164 | 768.91 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 768.91 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 682.3 | 0 | 0 | 0 |  |  | 0 | 86.61 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC21C007 | F21P1 VOC package （Installation ) | 2495 | C | USCSB2308157A | -01 | F21 P1 VOC Change Order (southland)_1 | 2023/8/26 2023/9/21 | 2023/9/15 2023/9/21 | 225843 | -6580 | 232423 | V | V | V |  | Southland Industries | PR Approved | PO Approved | R1:Request from responsible engineer to omit line 1 |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 225843 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 11292 | 0 | 214551 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 2496 | C | USCSB2308158A |  | F21 P1 VOC Change Order(southland)_2 | 45164 | 45184 | 107443 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 107443 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 5372 | 102071 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2497 | C | USCSB2308159A |  | Horiba Resistivity Meter B Side | 45164 | 45166 | 17850 | [6 empty] | HORIBA Taiwan, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 17850 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 17850 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2498 | C | USCSB2308160A |  | TSMC drum car*5 and Flush car*2 | 2023/8/26 2023/10/17 | 45217 | 16181 | [6 empty] | Yu Cheng Kid Enterprise Co., | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 16181 | 0 | 16181 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2499 | C | USCSB2308161A | -01 | Traffic Cone and Pole Order | 45164 | 2023/8/31 2023/9/6 | 24000 | [6 empty] | HSIEH SHUN HING CO., LTD. | PR Approved | PO Approved | R1:remark not embedded |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 24000 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 4800 |  | 0 | 0 | 0 | 0 |  | 19200 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC21C006 | F21P1 Slurry package | 2500 | C | USCSB2308162A |  | F21 P1 VOC Change Order(southland)_3 | 45164 | 45184 | 62489 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 62489 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 62489 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC21C006 | F21P1 Slurry package | 2501 | C | USCSB2308163A |  | F21 P1 VOC Change Order(southland)_4 | 45164 | 45187 | 8990.85 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 8990.85 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 8990.85 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | EUV Steel Plate | Labor | USC23C058 | F21 EUV Steel Plates | 2502 | C | USCSB2308164A |  | MIC Temp Power Crane ReLocate | 45166 | 45181 | 68860 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 68860 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 68860 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2503 | C | USCSB2308165A |  | Electric OPS | 8/28/2023 10/4/2024 | 9/19/2023 10/11/2024 | 7520.25 | -71838.65 | 79358.9 |  |  |  |  | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7520.25 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 2025.75 | 5494.5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2504 | C | USCSB2308166A |  | Grade Three MIC Laydown Areas / Lots | 45167 | 45169 | 4725 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4725 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 4725 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2505 | C | USCSB2308167A |  | Change order – conduit install for signal cable routing from L20 to L10 for KCOXN4 | 45167 | 45168 | 173.63 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 173.62 | 0.99994 | 0.01 | 0 | 0.01 | 0 | [40 empty] | 0 | 173.62 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2506 | C | USCSB2308168A |  | DIFF2: KDALS1 - ELECTRIC WIRE CONNECTION MATERIALS | 45167 | 45170 | 770.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 770.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 770.5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2507 | C | USCSB2308169A |  | Epoxy Misc Pads in Fab L10 and Lorry 1.5 | 45167 | 45170 | 4125 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4125 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 4125 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | W-H2SO4 | Material | USC21C014 | F21P1 WH2SO4 | 2508 | C | USCSB2308170A |  | WRC Additional Concrete | 45167 | 45181 | 65025.05 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 55025.05 | 0.84621 | 10000 | 0 | 10000 | 8253.7575 | [40 empty] | 0 | 0 | 23825.05 | 0 |  | 0 | 31200 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1950.7515 |  |  |  | 1950.7515 |  |  |  | 2601.002 |  | 2751.2525 |  | - | 2751.2525 | - | 2751.2525 | 0 | 0
Base-Build | W-H2SO4 | Material | USC21C014 | F21P1 WH2SO4 | 2509 | C | USCSB2308171A |  | Modify Trench In WRC L20 | 45167 | 45170 | 3165 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 3165 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 3165 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2510 | C | USCSB2308172A | -01 | HNO3 & ST-250 Cabinet Anchoring | 2023/8/29 2023/11/14 | 2023/9/1 2023/11/17 | 4101 | -16789 | 20890 | V |  | V | V | Milling Machinery, Inc. | PR Approved | PO Approved | PO R1:Renew quotation |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4101 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [9 empty] | 4101 |  |  | 4101 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2511 | C | USCSB2308173A |  | CHU-WEI welding equipment | 45167 | 45174 | 106454.16 | [6 empty] | JUWEI ENGINEERING CO LTD | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 104852 | 0.98495 | 1602.16 | 0 | 1602.16 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 104852 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1602.16 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2512 | C | USCSB2308174A |  | Change Order for KCBDA1 | 45168 | 45168 | 782.58 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 782.58 | 0 | 782.58 | 0 | [52 empty] | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Greenberry | USC23C045 | WWT Change Order (Piping) | 2513 | C | USCSB2308176A |  | WWT-LB2 rack modification | 2023/8/30 2023/9/22 | 45191 | 4272 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved | PR R1:Request to change the price, per engineer. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 4272 | 0 | 4272 | 4272 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 640.8 |  |  |  | 640.8 |  |  |  | 640.8 |  | 2136 |  | - | 2136 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2514 | C | USCSB2308177A |  | Epoxy Misc Pads in Roof | 45168 | 45194 | 54000 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 54000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 54000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2515 | C | USCSB2308178A |  | TW E2 Hookup GF Welding Machine | 45168 | 45169 | 69045.01 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 69045.01 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 3003.02 | 3669 | 0 | 0 | 0 | 44659.7 | 1950 | 11007 | 0 | 0 |  | 0 |  |  |  | 4756.29 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2516 | C | USCSB2308179A |  | WWT -TW-Maxiplast | 2023/8/30 2023/9/6 | 45176 | 55500 | [6 empty] | Widos Taiwan Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 55500 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 31500 | 0 | 0 | 0 | 0 |  | 24000 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2517 | C | USCSB2308180A |  | Pour Additional Pads Not In Scope | 45169 | 45196 | 12997.06 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 12997.06 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 12997.06 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2518 | C | USCSB2308181A | -01 | Connectors for Chemical team to conduct pressure test. | 45169 | 2023/9/1 2023/9/6 | 45.52 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1:Responsible Engineer |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 45.52 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 45.52 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Rosendin | USC21C003 | F21P1 UPW | 2519 | C | USCSB2308182A |  | Repair damages on site | 45169 | 45189 | 75936.12 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 75936.12 | 1 | 0 | 0 | 0 | 7593.62 | [40 empty] | 0 | 0 | 0 | 0 |  | 72139.31 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | 3796.81 | 3796.81 | - | 0 | 3796.81
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 2520 | C | USCSB2308183A |  | Greenberry T&M for CVD Vent Line Retrofit | 45169 | 45187 | 17523 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 17523 | 0 | 17523 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Greenberry | USC22C022 | F21P1 Triazole treatment system | 2521 | C | USCSB2308184A |  | 140 DISCHARGE EXTRA SUPPORT AND T125AC/AD MIS SUPPORT | 45169 | 45197 | 5859 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 5859 | 0 | 5859 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2522 | C | USCSB2308185A |  | Greenberry’s Time and Material pricing for work related to the CMP MKS 1, 2, and 5 Vent Lines | 45169 | 45183 | 4111 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 4111 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 4111 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Pipeline | Material | USC21C010 | tsmc AZ sewer and water pipeline installation | 2523 | C | USCSB2309001A |  | Fire Hydrant Remove and Replace | 45170 | 45197 | 19674 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 19674 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 19674 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Triazole | MMI | USC22C022 | F21P1 Triazole treatment system | 2524 | C | USCSB2309002A |  | Additional Steel for Catwalk to Tank Connection(Triazole Catwalk) | 45170 | 45203 | 5357 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | Additional Steel for Catwalk to Tank Connection(Triazole Catwalk) |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4495 | 0.83909 | 862 | 0 | 862 | 719.2 | [40 empty] | 0 | 0 | 4495 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 719.2 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Pipeline | Material | USC21C010 | tsmc AZ sewer and water pipeline installation | 2525 | C | USCSB2309003A |  | Modify Handrail Base Plates on Mezz 2 and 3 | 45170 | 45197 | 1520 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1520 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 1520 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2526 | C | USCSB2309004A |  | WWT Machine PP D63 12” PN10 pipe to PN6 | 45170 | 45175 | 1350 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 1350 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 1350 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2527 | C | USCSB2309005A |  | TW E2 Hookup Gas hardware YAHO | 45170 | 45180 | 230001.2 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 230001.12 | 1 | 0.08 | 0 | 0.08 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 144605.52 | 0 | 0 | 50865.6 | 0 | 0 |  | 34530 | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2528 | C | USCSB2309006A |  | Mini-Electronic Kit with Threaded Tips & blower | 2023/9/1 2023/9/9 | x | 0 | [7 empty] | PR Approved | PO Approved | Return - No Purchase |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 2529 | C | USCSB2309007A |  | VOC system signal wire termination | 45170 | 45174 | 40 | [6 empty] | Graybar Electric Company, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 40 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 40 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Outsourcing | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2530 | C | USCSB2309008A |  | Project manpower supply for safety, project management and house keeping | 45170 | 45174 | 559797.76 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 559797.76 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 559797.76 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2531 | C | USCSB2309009A |  | WWT missing material found by tsmc thu inventory | 45170 | 45175 | 5051.69 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5051.69 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 4492.71 | 72.82 | 0 |  | 0 | 0 | 0 | 486.16 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2532 | C | USCSB2309010A |  | CDS Southwest Fastener Monthly Order 8/20/23 to 9/20/23 | 45171 | 45224 | 10132.6 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8181.79 | 0.80747 | 1950.81 | 0 | 1950.81 | 0 | [41 empty] | 0 | 7160.31 | 0 |  | 1021.48 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1925.19 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C003 | F21P1 Module Tool Interconnection CVD | 2533 | C | USCSB2309011A |  | Change Order: install under RMF Chamber Junction Boxes for Tool KCBDA1 | 2023/9/2 2023/9/12 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: needed to correct quantity |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Equipment | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2534 | C | USCSB2309012A |  | 3 first floor EUV pump foundations installation | 45175 | 45194 | 92837.8 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 88195.91 | 0.95 | 4641.89 | 0 | 4641.89 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 88195.91 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2535 | C | USCSB2309013A |  | AWT room angle supports installation | 45175 | 45198 | 96801 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 70739.19 | 0.73077 | 26061.81 | 0 | 26061.81 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 22338.69 | 0 |  |  | 0 | 0 | 11169.35 |  | 0 |  |  |  | 37231.15 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2536 | C | USCSB2309014A | -01 | TW E2 Hookup GF Welding Machine part 2 | 2023/9/6 2023/9/22 | 2023/9/14 2023/9/22 | 0 | -138090.06 | 138090.06 |  |  |  |  | Ryan Herco Flow Solutions | PR Approved | PO Approved | R1:The original PO is for rent, and now MICU would like to issue a new PO for purchase. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2537 | C | USCSB2309016A | -02 | Chemical Hookup Material | 45175 | 2023/9/18 2023/9/21 2023/9/25 | 200000 | -48073.72 | 248073.72 |  |  |  |  | Trusval Technology CO., LTD. | PR Approved | PO Approved | Ship-to Location Change; Price Discount due to other service related WO |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 200000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 200000 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2538 | C | USCSB2309017A |  | Flanges used for CDU exhaust drain. | 45175 | 45182 | 2103.75 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 2103.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 2103.75 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2539 | C | USCSB2309018A |  | WWT -LJ-Miniplast | 45176 | 45181 | 18840 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 17064.92 | 0.90578 | 1775.08 | 0 | 1775.08 | 3803.1616 | [40 empty] | 0 | 0 | 0 | 1215.6 |  | 6284.92 | 0 | 0 | 0 | 0 | 6082.2 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 1358.272 | 3482.2 | - | 1358.272 | - | 1086.6176 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2540 | C | USCSB2309019A |  | Change Order for KESDA1 | 45176 | 45177 | 2179.37 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2179.37 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 2179.37 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Greenberry | USC23C045 | WWT Change Order (Piping) | 2541 | C | USCSB2309020A |  | WWT-LB2 rack modification | 45176 | 45180 | 13345 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12677.75 | 0.95 | 667.25 | 0 | 667.25 | 633.8875 | [40 empty] | 0 | 0 | 0 | 0 |  | 12677.75 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 633.8875
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2542 | C | USCSB2309021A |  | Refrigerated Liquid 2.2 & LC230 PSI. Cylinder Rent | 45176 | 45182 | 11025.8 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6463.5 | 0.58622 | 4562.3 | 0 | 4562.3 | 0 | [40 empty] | 0 | 0 | 5921 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 253.75 | 0 | 0 | 0 |  | 0 |  | 288.75 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2543 | C | USCSB2309022A |  | Cable glands and conduit | 45176 | 45182 | 66446.93 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 66446.93 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 66446.93 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC23C045 | WWT Change Order (Piping) | 2544 | C | USCSB2309023A |  | Installation of FRP Membrane (LB2 A side) | 45177 | 45198 | 367375.96 | [6 empty] | OBR Cooling Towers, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 367375.96 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 367375.96 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2545 | C | USCSB2309024A | -01 | 441002-EWO-054-Lorry A & B CDA/GN2 Cap removal and re-install | 2023/9/8 2023/12/12 | 2023/9/12 2023/12/30 | 0 | -32883 | 32883 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO 100% |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2546 | C | USCSB2309025A | -01 | 441002-EWO-091-Bridge IPA UB relocation Bim track 36 Proposal | 2023/9/8 2023/12/12 | 2023/10/1 2023/12/30 | 0 | -39033 | 39033 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO 100% |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2547 | C | USCSB2309026A |  | particle counter for cycle purge | 45177 | 45190 | 14100 | [6 empty] | Propersys Corp | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 14100 | 0 | 14100 | 7050 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 7050 |  | 6345 |  | - | 0 | - | 0 | 705
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2548 | C | USCSB2309027A | -01 | Boxes for bridge/HPM/clean room of CDS system. | 2023/9/8 2023/9/21 | 2023/9/13 2023/9/21 | 0 | -78434.46 | 78434.46 | V | V | V | V | Professional Plastics Inc | PR Approved | PO Approved | This PR will be modified to change the amount and add items, so need cancel this PR and create a new one. |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C047 | F21P1 HK Seismic Installation | 2549 | C | USCSB2309028A |  | MIC-121-23 Metrios Seismic Anchoring | 45177 | 45177 | 850 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 850 | 0 | 850 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | CRG | USC21C005 | F21P1 Chemical & WCCS package | 2550 | C | USCSB2309029A |  | NFPA Diamond Signs support and install | 45177 | 45182 | 10661.19 | [6 empty] | CRG International | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 7343.45 | 0.6888 | 3317.74 | 0 | 3317.74 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 7343.45 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 3304.97 | [5 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2551 | C | USCSB2309030A |  | Manual chemical liquid valve | 45177 | 45197 | 7065.45 | [6 empty] | CKD USA CORPORATION | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 7065.45 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 7065.45 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2552 | C | USCSB2309031A | -01 | DIFF1: 19 TOOLS FOR THE N2 TESTING | 45177 | 45182 | 225.39 | -37.5 | 262.89 |  | V |  |  | Linde Gas and Equipment Inc | PR Approved | PO Approved | PO R1:Invoiced did not include cylinder Rental |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 225.39 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 225.39 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical Lab | Material | USC22C021 | F21P1 Chemical Lab setup | 2553 | C | USCSB2309032A |  | GC Lab Electrical | 45177 | 45217 | 39611.26 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 39611.26 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 39611.26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC23C054 | UPW Change Order | 2554 | C | USCSB2309033A |  | F21 P1 Harder CDS Change Order | 2023/9/8 2023/11/15 |  | 0 | [7 empty] | PR Approved | PO Approved | PR R1: PR to be cancel. / The work with Harder changed to T&M. |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2555 | C | USCSB2309034A |  | Lorry 90 deg Coax elbows | 45177 | 45182 | 5560 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5560 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 5560 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC23C045 | WWT Change Order (Piping) | 2556 | C | USCSB2309035A |  | PSS WWT scope for invoice SW-23-0107 and SW-23-0134 | 45177 | 45176 | 4038170.94 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 4038170.94 | 1 | 0 | 0 | 0 | 0 | [38 empty] | 4038170.94 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 2557 | C | USCSB2309036A |  | 8-129 WWT LSR FAB-LB2 | 45177 | 45191 | 2366258 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2253922 | 0.95253 | 112336 | 0 | 112336 | 112696.1 | [40 empty] | 0 | 0 | 0 | 0 | 449589 | 0 | 0 | 0 | 1064164 | 442371 |  |  | 78963 | 48000 | 0 |  | 0 |  | 170835 |  |  | 70987.74 |  |  |  | 70987.74 | [5 empty] | 0 |  | - | 0 | - | 0 | 0 | 112696.1
Interconnection | Interconnection | Labor | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2558 | C | USCSB2309037A |  | QR: KAX01/KXAT02 – TOOL DEMO LABOR ONLY | 45178 | 45182 | 2400 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2400 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 2400 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2559 | C | USCSB2309038A |  | QR: KAX01/KXAT02 – CABLE INSTALLATION | 45178 | 45182 | 720 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 720 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 720 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2560 | C | USCSB2309039A |  | QR: KXEX01/KXEX02 – INSTALL 1” EMT FOR TOOLS. | 45178 | 45184 | 6201 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6201 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 6201 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2561 | C | USCSB2309040A |  | EBO: NO TOOL ID: Interconnection material Strut channel, SAE washer | 45178 | 45194 | 5071.7 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 5071.7 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 868.37 | 4203.33 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Greenberry | USC23C045 | WWT Change Order (Piping) | 2562 | C | USCSB2309041A |  | WWT FAB Install (16) Agitator Installation | 45180 | 45189 | 72481 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 51375.05 | 0.70881 | 21105.95 | 0 | 21105.95 | 14898.7645 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 51375.05 |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 3624.05 |  |  |  | 3624.05 |  |  |  | 3624.05 |  | 4110.004 |  | - | 4110.004 | - | 4110.004 | 2568.7525 | 0
Base-Build | UPW | MIMO/Rigging | USC21C003 | F21P1 UPW | 2563 | C | USCSB2309042A |  | MMI temp resin move-in | 45181 | 45217 | 19635 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 19635 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 15295 | 0 |  | 4340 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2564 | C | USCSB2309043A |  | NATURAL POLYPRO COVER WITH 1.257" THRU HOLE. | 45181 | 45181 | 1100 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1100 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 1100 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2565 | C | USCSB2309044A |  | 200 ea. CDS Seismic Corner Anchor Brackets. | 45181 | 45195 | 8171 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8171 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 7762.45 | 0 | 0 | 0 |  |  | 408.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 2566 | C | USCSB2309045A |  | MMI-WRC-L20-RO rack modify | 45181 | 45217 | 14472 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 14472 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 5000 | 0 | 0 | 8748.4 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 723.6 |  |  | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C001 | TEL Main Tool Interconnection | 2567 | C | USCSB2309046A |  | KPOCT9 HYC | 45181 | 45216 | 46200 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 46200 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 46200 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C001 | TEL Main Tool Interconnection | 2568 | C | USCSB2309047A | -01 | KPOCT8-T UMEC ADD ON | 2023/9/12 2023/9/28 | 2023/9/22 2023/10/2 | 0 | -2013.45 | 2013.45 |  |  |  | V | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical Lab | UMEC | USC22C021 | F21P1 Chemical Lab setup | 2569 | C | USCSB2309048A |  | 8-134 FAB Gas Chem Lab Hook-Up Reroute(GC Lab Piping Change Order) | 45181 | 45195 | 21374 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 20306 | 0.95003 | 1068 | 0 | 1068 | 1068 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 19237 | 0 | 1069 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 1068
Interconnection | Interconnection | Material | USC23C001 | TEL Main Tool Interconnection | 2570 | C | USCSB2309049A | -03 | KPOCT8-T HYC | 45181 | 45198 | 75600 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 75600 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 75600 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2571 | C | USCSB2309051A |  | Lasair III 110 Particle Counter and HPD II-150 High Pressure Diffuser | 45181 | 45192 | 26304.18 | [6 empty] | Particle Measuring Systems, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 26304.18 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 26304.18 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC23C040 | TSMC F21 Clean Room Suit | 2572 | C | USCSB2309052A |  | Sunrise Phoenix housekeeping services | 45181 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2573 | C | USCSB2309053A |  | Extension cords for welding machines | 45181 | 45189 | 4041.84 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 4041.84 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 4041.84 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2574 | C | USCSB2309054A |  | DIFF/EPI - CABLE TRAY DIVIDER | 45181 | 45184 | 1021.72 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1021.72 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 1021.72 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C001 | TEL Main Tool Interconnection | 2575 | C | USCSB2309055A |  | KPD801-T HYC | 45181 | 45192 | 7600 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6880 | 0.90526 | 720 | 0 | 720 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 6880 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C001 | TEL Main Tool Interconnection | 2576 | C | USCSB2309056A |  | KPI401-T STREIMERS | 2023/9/12 2024/9/17 | 2023/9/27 2024/9/17 | 35552.29 | -8785.31 | 44337.6 | V |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | PR R1: Case Closed -- adjust the PO amount to reflect the actual total |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 35552.29 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 35552.29 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 2577 | C | USCSB2309057A |  | Epoxy Misc Pads in Fab LB2 | 45182 | 45188 | 52125 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 52125 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 52125 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2578 | C | USCSB2309058A |  | Epoxy Pump Pads and Vibration Pads(FAB LB2 and WRC L10) | 45182 | 45216 | 107400 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 107400 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 107400 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS | Material | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2579 | C | USCSB2309060A |  | 50pcs small iron plates to AMHS | 45182 | 45189 | 1342 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 1342 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 1342 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2580 | C | USCSB2309061A |  | Border States Electrical Work Material PreFab Area | 45182 | 45196 | 34116.24 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 34116.24 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 34116.24 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2581 | C | USCSB2309062A | -01 | L20 HPM Transition to Fab pipe redesign rev2 | 2023/9/13 2023/12/12 | 2023/10/10 2024/1/4 | 0 | -35142 | 35142 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per engineer Johnny Wan to cancel PO :Paid in Original PO 50%, MICU only agree to pay design & material |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2582 | C | USCSB2309063A | -01 | Lorry A/B RU&CCBTU to tanks piping re-work due to design change REV 2 | 2023/9/13 2023/12/12 | 2023/10/1 2023/12/30 | 0 | -115200 | 115200 |  |  |  |  | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO 100% |  | Lemar J Edwards Yikang Wang |  |  |  | Lemar J Edwards Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2583 | C | USCSB2309064A | -01 | L20 HPM Bridge Rework | 2023/9/13 2023/12/12 | 2023/10/11 2024/1/4 | 0 | -120000 | 120000 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | R1: As per engineer Johnny Wan to cancel PO: Work done before turning T&M, Paid in Orginal PO 80% |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Harder | USC21C005 | F21P1 Chemical & WCCS package | 2584 | C | USCSB2309065A | -01 | H20A Spec Change from Plastic to Stainless in Solvent room | 2023/9/13 2023/12/11 | 2023/9/21 2023/12/11 | 0 | -76164 | 76164 |  |  |  | V | Harder Mechanical Contractors, Inc | PR Approved | PO Approved | As per Johnny to cancel PO :Work done before turning T&M, Paid in Original PO 60%, should only pay material and design fee |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C006 | F21P1 Module Tool Interconnection EPI | 2585 | C | USCSB2309066A |  | EPI: KEXR01 KCEPS1 KCEPS3 CABLE TRAY DIVIDER | 45182 | 2023/9/15 2024/8/10 | 224.24 | -0.04 | 224.28 |  |  |  |  | Independent Electric Supply, Inc. | PR Approved | PO Approved | PO R1:Updated amount to match the invoice & to close PO. Credited $.04. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 224.24 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 224.24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2586 | C | USCSB2309068A |  | WWT -BMWC mobilization and support | 45182 | 45196 | 34398 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 34398 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 32678.1 | 0 | 0 | 0 |  |  | 1719.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | VOC | Material | USC21C006 | F21P1 Slurry package | 2587 | C | USCSB2309069A |  | F21 P1 VOC Support _material | 2023/9/14 2023/9/16 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled per request by Angelan Hsu via dated 9/15/2023 |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC21C006 | F21P1 Slurry package | 2588 | C | USCSB2309070A |  | F21 P1 VOC Support _Labor | 45183 | x | 0 | [7 empty] | PR Approved | PO Approved | Cancelled |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2589 | C | USCSB2309071A |  | AMAT_CMP_KMOPA2-C / KMOPA5-C / KMOPAB-C_cush clamps, strut channel, strut channel bracket, nut, washers | 45183 | 45191 | 766.43 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 706.84 | 0.92225 | 59.59 | 0 | 59.59 | 0 | [40 empty] | 0 | 0 | 0 | 706.84 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Material | USC21C005 | F21P1 Chemical & WCCS package | 2590 | C | USCSB2309072A |  | Ball valve to work at H20 and slurry sump | 45183 | 45198 | 9599.67 | [6 empty] | Ze-Wei Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9599.67 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 9599.67 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2591 | C | USCSB2309073A |  | TW team material request for LJ | 45183 | 45188 | 57823.5 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 57731.1 | 0.9984 | 92.4 | 0 | 92.4 | 0 | [40 empty] | 0 | 0 | 43254.88 | 14476.22 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2592 | C | USCSB2309074A | -01 | E2 TW Profit - TUN YI | 2023/9/14 2023/12/28 | 2023/9/28 2023/12/28 | 0 | -808220 | 808220 |  |  |  | V | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved | R1: TW Company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2593 | C | USCSB2309075A | -01 | E2 TW Profit - Mao Hsun | 2023/9/14 2023/12/28 | 2023/9/28 2023/12/28 | 0 | -456000 | 456000 |  |  |  | V | SWIFT ENGINEERING CO., LTD. | PR Approved | PO Approved | R1: TW Company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2594 | C | USCSB2309076A | -01 | E2 TW Profit - LI JEI | 2023/9/14 2023/12/28 | 2023/9/28 2023/12/28 | 0 | -1080000 | 1080000 |  |  |  | V | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2595 | C | USCSB2309077A | -01 | E2 TW Profit - Third | 2023/9/14 2023/9/26 | 2023/9/28 2023/10/25 | 0 | -838500 | 838500 |  |  |  |  | Third Enterprise | PR Approved | PO Approved | R1: Will change to another supplier per request. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2596 | C | USCSB2309077B | -01 | E2 TW Profit - Da Yi Cheng | 2023/9/14 2023/12/28 | 2023/10/26 2023/12/28 | 0 | -838500 | 838500 |  |  |  | V | DA YI CHENG Technology Co., Ltd. | PR Approved | PO Approved | Zero out USCSB2309077A and Change to another supplier in USCSB2309077B R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2597 | C | USCSB2309078A | -01 | E2 TW Profit - CHI YI HSIN | 2023/9/14 2023/12/28 | 2023/9/29 2023/12/28 | 0 | -721600 | 721600 |  |  |  | V | Chi Yi Hsin Technology Co., LTD. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC21C014 | F21P1 WH2SO4 | 2598 | C | USCSB2309080A |  | F21 P1 CCTV Engineering | 45184 | 45200 | 85243.41 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 85243.41 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 85243.41 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2599 | C | USCSB2309082A | -01 | Battery Charge B Side 10 Cabinets | 45184 | 2023/9/20 2023/10/10 | 22000 | 3000 | 19000 |  |  |  |  | Gruber Industries | PR Approved | PO Approved | R1:revise price |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 22000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 22000 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C006 | F21P1 Module Tool Interconnection EPI | 2600 | C | USCSB2309083A |  | RKC 4.5T-10/S90 | 45184 | 45192 | 2158.08 | [6 empty] | Motion Automation Intelligence | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2158.08 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 2158.08 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2601 | C | USCSB2309084A |  | QR: LAN CABLE TRAY INSTALL | 45184 | 45197 | 72000 | [6 empty] | Delta Wye Electric, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 72000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 72000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C006 | F21P1 Module Tool Interconnection EPI | 2602 | C | USCSB2309085A | -01 | cabel trays | 2023/9/15 2023/11/20 | 2023/9/20 2023/11/20 | 0 | -2347.34 | 2347.34 |  |  |  | V | Graybar Electric Company, Inc. | PR Approved | PO Approved | PO R1:canceled order (as confirmed by engineering team) |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2603 | C | USCSB2309086A |  | Hardware for Chemical YaoHong work at Lorry FNDP. | 45184 | 45188 | 3889 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3889 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 3889 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 2604 | C | USCSB2309087A |  | Change order – conduit install for signal cable routing from L20 to L10 KECOT2 | 45184 | 45199 | 569.74 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 569.74 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 569.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2605 | C | USCSB2309088A |  | Load cell work at Mixing boxes/tanks | 45184 | 45192 | 26733 | [6 empty] | Michelli Measurement Group, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 26733 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 26733 |  |  | 26733 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2606 | C | USCSB2309089A |  | CMP: MKS1-4: CUSHIONED CLAMPS | 45184 | 45287 | 326.25 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 326.25 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 0 | 326.25 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2607 | C | USCSB2309090A | -01 | Chemical box&box cover for location of support welding & hole location | 2023/9/15 2023/9/19 | 2023/9/19 2023/12/4 | 2098.5 | 470.25 | 1628.25 |  |  | V |  | FusionHPX LLC | PR Approved | PO Approved | Revise quantity of order to add 1 more item |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2098.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2098.5 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC23C058 | F21 EUV Steel Plates | 2608 | C | USCSB2309091A |  | Provide 10lb fire extinguisher and bracket at scaffold entrances (required for fire inspection) | 45184 | 45191 | 9591 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 9591 | 0 | 9591 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2609 | C | USCSB2309092A |  | WWT 20% Fab materials for FAB A side | 45185 | 45195 | 179759.08 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 179736.08 | 0.99987 | 23 | 0 | 23 | 0 | [40 empty] | 0 | 0 | 0 | 27554.91 |  | 101341.97 | 2963.47 | 0 | 47181.81 | 0 | 693.92 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2610 | C | USCSB2309093A |  | UPW-PVDF valve handle | 45185 | 45192 | 73.59 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 73.59 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 24.53 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 49.06 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Site Expense | USC23C045 | WWT Change Order (Piping) | 2611 | C | USCSB2309094A |  | WWT -LJ lift training | 45185 | 45209 | 6238.65 | [6 empty] | United Rentals | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 6238.65 | 0 | 6238.65 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 935.7975 |  |  |  | 935.7975 |  |  |  | 935.7975 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | MMI | USC23C045 | WWT Change Order (Piping) | 2612 | C | USCSB2309095A |  | WWT (118) Tank Crossover Platform Brackets | 45185 | 45191 | 1663 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1663 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 1663 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2613 | C | USCSB2309096A |  | Hand Tool - Mao Hsun | 45185 | 45198 | 1505.97 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1505.97 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 1505.97 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2614 | C | USCSB2309097A |  | Refrigerated Liquid 2.2 & LC230 PSI. Cylinder Rent | 45185 | 45192 | 20890.32 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 20890.32 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 2055.16 | 9725.72 | 0 | 1027.58 | 0 | 0 | 0 | 0 | 0 |  | 2874.7 | 0 | 0 | 0 |  | 2960.5 |  | 2191.26 |  |  |  | 55.4 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 2615 | C | USCSB2309098A |  | TSMC Fab 21 Phase Construction Administration Services | 45185 | 45191 | 247266 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 222694 | 0.90063 | 24572 | 0 | 24572 | 0 | [40 empty] | 0 | 0 | 0 | 49453.2 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 89077.6 |  | 0 |  | 84163.2 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2616 | C | USCSB2309099A |  | Banner Industries Welding Equipment Pre Fab Construction | 45185 | 45196 | 38566.9 | [6 empty] | Banner Industries of N.E. Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 38566.9 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3924.9 | 15220 | 19422 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2617 | C | USCSB2309100A |  | Mini-Line Certificate(batch 1/2) | 45185 | 45191 | 33000 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 8250 | 0.25 | 24750 | 0 | 24750 | 0 | [40 empty] | 0 | 0 | 0 | 8250 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 2618 | C | USCSB2309102A |  | Mini-Line Certificate(batch 2/2) | 45185 | 45191 | 33000 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 33000 | 0 | 33000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2619 | C | USCSB2309103A |  | LB2-UIS A2.5 spool remove | 45187 | 45195 | 6172 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 6172 | 0 | 6172 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 5863.4 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC22C021 | F21P1 Chemical Lab setup | 2620 | C | USCSB2309104A |  | Page Observation for FAB and WRC UPW Reimbursement | 45188 | 45191 | 10000 | [6 empty] | Page Southerland Page, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 10000 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2621 | C | USCSB2309105A |  | DIFF1: 19 TOOLS: REGULATOR FOR THE N2 TESTING | 45188 | 45195 | 230 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 230 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 230 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2622 | C | USCSB2309106A | -01 | WWT -unitstrut_Southwest Fastener | 2023/9/19 2023/10/4 | 2023/9/21 2023/12/5 | 0 | -799.57 | 799.57 |  |  |  | V | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | Order included in WO#USCSB2311025A |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2623 | C | USCSB2309107A |  | CMP: MKS1-4: CLEAR PRIMER DIO3 LINES | 45188 | 45194 | 29.34 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 29.34 | 0 | 29.34 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2624 | C | USCSB2309108A | -01 | CMP: MKS1-4: 1” inch cush clamp for CMP | 45188 | 45195 | 181.6 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | R1:Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 181.6 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 181.6 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2625 | C | USCSB2309109A | -01 | CMP: KMPRE1: 76MM/1P PEDESTAL CLAMPS | 45188 | 2023/9/26 2023/10/4 | 208 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved | PO R1:Trade Term Correction Base on the Quote |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 208 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 208 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC21C011 | F21 TMAH System | 2626 | C | USCSB2309110A |  | F21 WWT system material (Gibabit) | 45188 | 45194 | 7000 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7000 | 1 | 0 | 0 | 0 | 7000 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 1050 |  |  |  | 1050 |  |  |  | 1050 | 7000 | 3500 |  | - | 3500 | - | 0 | 0 | 0
Base-Build | Base-Build | Outsourcing | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2627 | C | USCSB2309111A |  | Tool Hookup Design/Base Build Design/System/Safety | 45188 | 45188 | 500000 | [6 empty] | Kelly Services, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 421156.11 | 0.84231 | 78843.89 | 0 | 78843.89 | 0 | [39 empty] | 36567.56 | 91774.55 | 195712.22 | 96221.77 | 0 | 880.01 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Housekeeping | USC21C005 | F21P1 Chemical & WCCS package | 2628 | C | USCSB2309112A |  | Site Housekeeping | 45188 | 45188 | 100000 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 100000 | 1 | 0 | 0 | 0 | 0 | [39 empty] | 97960 | 2040 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2629 | C | USCSB2309113A | -01 | E2 TW Profit - Laien Parts | 2023/9/19 2023/12/28 | 2023/10/3 2023/12/28 | 0 | -232000 | 232000 |  |  |  | V | Laien Parts Technology Co., Ltd. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2630 | C | USCSB2309114A |  | 90 deg Coax elbows for Chemical team and Harder | 45188 | 45204 | 27588 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 27588 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 27588 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2631 | C | USCSB2309115A |  | FNDP Material request for YaHo work at Lorry FNDP. | 45189 | 45191 | 1745.58 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1745.58 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 1326.41 | 419.17 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C006 | F21P1 Module Tool Interconnection EPI | 2632 | C | USCSB2309116A |  | EPI: KCEPS1: 4 UL LIQ TITE EG UNIVERSDAL CLAMP STEEL | 45189 | 45195 | 581.52 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 581.52 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 575.62 | 0 | 0 | 5.9 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2633 | C | USCSB2309117A |  | Tee and elbow for YaHo at Lorry FNDP. | 45189 | 45192 | 533 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 533 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 533 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2634 | C | USCSB2309118A | -02 | QR LABS: KXAT01, KXAT02, KXEX02 6 & 9-INCH BEND, BLINE 9 ZN-1204NB CLAMPS | 45189 | 2023/9/26 2023/9/30 | 615.96 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved | Supplier (John McDonald) contact on 9/29 6:27 AM to change completion date due to previous shipment negotiation. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 615.96 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 615.96 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2635 | C | USCSB2309119A |  | 90 deg Coax elbows. 2"x 1-1/2" be used by YaHo at Lorry FNDP. | 45189 | 45198 | 15992 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 15992 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 15992 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2636 | C | USCSB2309120A |  | Techsouthinc Hand Tool 3rd batch | 45189 | 45198 | 2803.2 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2803.2 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 2803.2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2637 | C | USCSB2309121A | -01 | E2 TW Profit - Jer Yih | 2023/9/20 2023/12/28 | 2023/10/3 2023/12/28 | 0 | -893000 | 893000 |  |  |  | V | Jer-Yih Electrical Engineering Ltd. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2638 | C | USCSB2309122A | -02 | Genesis Technology Cabling Install OFC Office Build | 2023/9/21 2023/11/30 | 2023/10/3 2023/12/5 2023/12/12 | 19368 | -13263 | 32631 |  |  |  | V | Genesis Technology (USA) Inc. | PR Approved | PO Approved | PO R2:Warranty Correction PO R1: There was a reduced work scope involving the original quote and approved W.O A-02: Change Warranty |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 19368 | 1 | 0 | 45771.6 | -45771.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 19368 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2639 | C | USCSB2309124A |  | Genesis Technology Cabling Install OFC Office Build | 45190 | 45202 | 31864 | [6 empty] | Genesis Technology (USA) Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 31864 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 4779.6 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [7 empty] | 27084.4 | [6 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2640 | C | USCSB2309125A |  | Boxes for bridge/HPM/clean room of CDS system. | 45190 | 45194 | 85355.14 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 85355.14 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 85355.14 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2641 | C | USCSB2309126A |  | TW W1 material 2nd Order | 45190 | 45197 | 114768.28 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 114768.28 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 37605.84 | 46869.58 |  | 483.16 | 29809.7 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2642 | C | USCSB2309127A | -01 | E2 TW Profit - Chuan Ta | 2023/9/21 2023/12/28 | 2023/10/4 2023/12/28 | 0 | -418000 | 418000 |  |  |  | V | Chuan Ta Technology Corp. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2643 | C | USCSB2309128A | -01 | E2 TW Profit - GENIIDEAS | 2023/9/21 2023/12/28 | 2023/10/3 2023/12/28 | 0 | -294000 | 294000 |  |  |  | V | GENII IDEAS Co., Ltd. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2644 | C | USCSB2309129A |  | Swagelok 2nd batch hand tools | 45190 | 45203 | 5432.16 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5432.16 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 5432.16 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2645 | C | USCSB2309130A | -01 | E2 TW Profit - Trusval | 2023/9/21 2023/12/28 | 2023/10/2 2023/12/28 | 0 | -1113900 | 1113900 |  |  |  | V | Trusval Technology CO., LTD. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC23C045 | WWT Change Order (Piping) | 2646 | C | USCSB2309131A |  | WRC Rack 215/220 Modification for PSS Clash | 45190 | 45197 | 6924 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6924 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 6924 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | MIMO/Rigging | USC21C005 | F21P1 Chemical & WCCS package | 2647 | C | USCSB2309132A |  | CDS L30 Panel Move-in and install. | 45190 | 45197 | 16203 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 16203 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 2000 | 0 | 13392.85 | 0 | 0 | 0 |  |  | 810.15 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2648 | C | USCSB2309133A |  | UPW-Nagano Pressure Gauge＆Flow Indicator | 45190 | 45194 | 2611.25 | [6 empty] | Organo USA, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 2611.25 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 212.5 | 0 | 0 | 2398.75 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 2649 | C | USCSB2309134A |  | Cable Pull and 8395 KSMGS1-Pull Vendor supplied cables from L30,L20 QTY 30 | 45190 | 45195 | 5664 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5664 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 5664 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2650 | C | USCSB2309135A |  | Paint for Tank Scratch Repair | 45190 | 45194 | 535 | [6 empty] | Continental Coatings Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 535 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 535 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Southland | USC21C014 | F21P1 WH2SO4 | 2651 | C | USCSB2309136A |  | F21 P1 VOC DPI Added Material | 45190 | 45197 | 54039 | [6 empty] | Southland Industries | PR Approved | PO Approved | Change order corresponds and chargeable against D-Tech (PR Form Note) |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 54038.9 | 1 | 0.1 | 0 | 0.1 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 48635 | 5403.9 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [16 empty] | - |  | -
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2652 | C | USCSB2309137A |  | TW E2 Hookup GF Welding Machine_6 purchase | 45190 | 45195 | 307526.42 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 307526.42 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 307526.42 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2653 | C | USCSB2309138A |  | UPW-CO-trade damage repair | 45191 | 45209 | 166473 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 0 | 166473 | 0 | 166473 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [12 empty] | 158149.35 |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2654 | C | USCSB2309139A | -01 | 90 deg Coax elbows (Spare parts). | 45191 | 2023/10/3 2023/10/10 | 33000 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | PO R1:Change in Net Terms |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 33000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 5280 | 23760 | 3960 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | EUV Steel Plate | Labor | USC23C058 | F21 EUV Steel Plates | 2655 | C | USCSB2309140A |  | EUV Crane electrical disconnect panel and cable tray. | 45191 | 45203 | 188859 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 188859 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 188859 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | MMI | USC22C013 | F21P1 QR Lab Security & CCTV | 2656 | C | USCSB2309141A | -01 | Provide generator rental for temporary power staged outside of Fab building on West side. | 2023/9/22 2023/12/7 | 2023/9/29 2023/12/7 | 0 | -119203 | 119203 |  |  |  | V | Milling Machinery, Inc. | PR Approved | PO Approved | Revise project code,so need to cancel this PR,and issue a new PR for this PR. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2657 | C | USCSB2309142A | -01 | Chemical VMB boxes for Fab B Side of the CDS system. | 45191 | 2023/10/5 2023/11/17 | 106561.5 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved | PO R1:Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 106561.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 100075.45 | 0 |  |  | 0 | 0 | 6486.05 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2658 | C | USCSB2309143A |  | WWT T-260 (8) Epoxy Coating Anchors | 45191 | 45197 | 2500 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1500 | 0.6 | 1000 | 0 | 1000 | 120 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1500 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 125 |  |  |  | 250 |  |  |  | 125 |  | 0 |  | - | 0 | - | 0 | 0 | 120
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2659 | C | USCSB2309144A |  | Circuit Breakers for Fab L10/L20 | 45191 | 45197 | 7184.08 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7184.08 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 7184.08 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C009 | F21P1 Module Tool Interconnection ETC1-3 | 2660 | C | USCSB2309145A |  | / Butterfly Clamp Center Ring Clamp Flange Elbow Bellows | 45191 | 45222 | 4912.93 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4912.93 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 4912.93 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 2661 | C | USCSB2309146A |  | Change Order for KCBDA1 Under RMF Chamber Enclosures | 45191 | 45197 | 2583.6 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 2583.6 | 0 | 2583.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2662 | C | USCSB2309147A | -01 | DIFF1: 25 TOOLS : T&M N2 DIFFUSION LINES | 45192 | 45210 | 0 | -333633 | 333633 |  |  |  |  | Greenberry Industrial | PR Approved | PO Approved | PO R1: VOID - PER TYLER SMITH No longer using subcontractor |  | Yikang Wang (Lemar J Edwards) |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2663 | C | USCSB2309148A |  | Hua Yi Construction Az On-site Clean Room Construction | 45192 | 45203 | 47932.86 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 47932.86 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 47932.86 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Penetration Pipe | PSS | USC22C020 | F21P1 Penetration Pipe | 2664 | C | USCSB2309149A |  | WWT-LB1 embedded pipes | 45192 | 45197 | 13281.46 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 13281.46 | 0 | 13281.46 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2665 | C | USCSB2309150A |  | UPW sight glass PVC-train B | 45192 | 45195 | 1543.05 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1543.05 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 1543.05 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC23C045 | WWT Change Order (Piping) | 2666 | C | USCSB2309151A |  | Provide the manpower only for installation of CCTV on the A side | 45192 | 45202 | 43200 | [6 empty] | Alvarado Electric LLC. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 43200 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 43200 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2667 | C | USCSB2309152A |  | Hardware for CYH (PCW) | 45195 | 45198 | 430380 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 384608.4 | 0.89365 | 45771.6 | 0 | 45771.6 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 384608.4 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2668 | C | USCSB2309153A |  | Hardware for CYH (AIR) | 45195 | 45198 | 145575.68 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 145575.68 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 145575.68 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2669 | C | USCSB2309154A | -01 | E2 TW Profit - Yaho | 2023/9/26 2023/12/28 | 2023/10/4 2023/12/28 | 0 | -1516000 | 1516000 |  |  |  | V | YAHO System Technology Co., Ltd. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | 5G | Material | USC22C010 | F21 P1 LSC CMS and DPM 5G System | 2670 | C | USCSB2309155A |  | 5G CMS material for rubber adhesive cable tie mount | 45195 | 2023/10/9 2024/10/3 | 0 | -2832 | 2832 |  |  |  |  | GLA Arizona, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 98.8 | -98.8 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2671 | C | USCSB2309156A |  | WWT-settle cost for AIG | 45195 | 45197 | 732452.27 | [6 empty] | Alliance Industrial Group, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 732452.27 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 732452.27 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2672 | C | USCSB2309157A |  | Galvanized Tool Install - 6b | 45195 | 45198 | 75652.96 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 75652.96 | 0 | 75652.96 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2673 | C | USCSB2309158A |  | MILWAUKEE Portable Shop Vacuum. | 45195 | 45195 | 196.75 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 196.75 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 196.75 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC21C003 | F21P1 UPW | 2674 | C | USCSB2309160A |  | TW-UPW-Gaskets | 45195 | 45201 | 1334 | [6 empty] | TCELC CO., LTD | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1334 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 1334 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2675 | C | USCSB2309161A |  | Hardware for Tun Yi Pumping Line | 2023/9/26 2023/10/10 | x | 0 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved | Cancel due to wrong currency; Replace with USCSB2310051 |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2676 | C | USCSB2309162A |  | Small order: TW material PVC insert fitting | 45195 | 45202 | 8002.24 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8002.24 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 8002.24 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Foundation | Labor | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2677 | C | USCSB2309163A |  | MMI 0527~0528 overtime for B6-1 foundation | 45196 | 45202 | 51160 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 51160 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 51160 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Helix | USC23C045 | WWT Change Order (Piping) | 2678 | C | USCSB2309165A |  | WWT Support_HELIX | 45196 | 45217 | 1427459.08 | [6 empty] | Okland Construction Company, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1398534.33 | 0.97974 | 28924.75 | 0 | 28924.75 | 27970.6866 | [40 empty] | 0 | 0 | 0 | 0 |  | 1398534.33 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 27970.6866
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2679 | C | USCSB2309166A |  | EBO: CDA Cabinet – NO TOOL ID: Interconnection material - U-bolt | 45196 | 45202 | 64.69 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 64.69 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 64.69 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2680 | C | USCSB2309167A | -02 | VMB-576A for TS-135 at HPM 20. | 45196 | 2023/10/3 2023/10/6 | 10246.5 | [6 empty] | Marketech International Corp. | PR Approved | PO Approved | PO R1:Payment Term and Quotation Number Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 10246.5 | 0 | 10246.5 | 10246.5 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 10246.5
Base-Build | CCTV | NUUO | USC23C045 | WWT Change Order (Piping) | 2681 | C | USCSB2309168A |  | F21 P1 A site Access Control, ACS Panel interconnection | 45197 | 45203 | 1839196.6 | [6 empty] | NUUO US Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1745473.34 | 0.94904 | 93723.26 | 0 | 93723.26 | 175765.81 | [40 empty] | 0 | 0 | 251160 | 0 |  | 0 | 0 | 1064932.07 | 347338.72 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 18392 | [9 empty] | 0 |  | 82042.55 | 36783.93 | - | 36783.93 | 10238.12 | 91959.83
Base-Build | WWT | CCE | USC23C045 | WWT Change Order (Piping) | 2682 | C | USCSB2309169A |  | F21 P1 WWT Electric Engineering-CCE | 45197 | 45209 | 407681.85 | [6 empty] | Commercial Comm and Electric Inc | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 407681.85 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 407681.85 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2683 | C | USCSB2309170A |  | Veolia turbo bed-final | 45197 | 45202 | 73373.74 | [6 empty] | Veolia WTS Services USA, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 73373.74 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 73373.74 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | MMI | USC21C003 | F21P1 UPW | 2684 | C | USCSB2309171A |  | MMI-T1034B-ladder repair | 45197 | 45202 | 3702 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3702 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3516.9 | 0 | 0 | 0 |  |  | 0 | 0 | 185.1 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2685 | C | USCSB2309172A |  | NFPA Diamond Signs for chemical tanks, HPM 20. | 45197 | 45202 | 779.7 | [6 empty] | Pensacola Hardware Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 779.7 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 779.7 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Scaffolding | USC23C045 | WWT Change Order (Piping) | 2686 | C | USCSB2309173A |  | Liberty June Invoice | 45197 | 45203 | 1316565.5 | [6 empty] | J.T. Thorpe Industrial DBA: Liberty Industrial Group | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1316565.5 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 1316565.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2687 | C | USCSB2309174A |  | WWT -Open PO for urgent materials | 45197 | 45202 | 80000 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 79525.73 | 0.99407 | 474.27 | 0 | 474.27 | 795.2573 | [40 empty] | 0 | 0 | 0 | 4751 | 1974 | 2862.02 | 8364.95 | 0 | 32815.64 | 0 | 28758.12 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 795.2573
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2688 | C | USCSB2309175A |  | QR: CHAD/FAD LABS: INTERCONNECT MATERIALS FOR LAN CABLE TRAY | 45197 | 45202 | 3116.25 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3116.25 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 3116.25 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2689 | C | USCSB2309176A |  | WWT -Train A-PVC materials | 45197 | 45204 | 115575.35 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 115575.35 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 115186.55 |  | 388.8 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 2690 | C | USCSB2309177A |  | F21 P1 VOC Cable | 45197 | 45202 | 1918.57 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1918.57 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 1918.57 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2691 | C | USCSB2309178A |  | WWT -MU Train A rest material | 45198 | 45202 | 825000 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 825000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 53997.2 | 36417.6 | 0 | 0 | 116698.7 | 0 |  | 249072.5 | 368814 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2692 | C | USCSB2309179A |  | WWT -Train A-PP/PVDF on hand | 45198 | 45204 | 358306.67 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 358306.2 | 1 | 0.47 | 0 | 0.47 | 0 | [40 empty] | 0 | 0 | 0 | 43767.6 |  | 32065.85 | 196103.55 | 0 | 48870.75 | 0 |  |  | 37498.45 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2693 | C | USCSB2309180A |  | Hardware for Swift(MAO HSUN) 5b | 45197 | 45223 | 451150.2 | [6 empty] | SWIFT ENGINEERING CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 451150.2 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 160110 | 0 |  |  | 0 | 0 | 73835 |  | 132551.2 |  | 84654 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Housekeeping | USC23C045 | WWT Change Order (Piping) | 2694 | C | USCSB2309181A |  | Sunrise Phoenix housekeeping services | 45198 | 45203 | 500000 | [6 empty] | Sunrise Phoenix Hi-Tech LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 488382.87 | 0.97677 | 11617.13 | 0 | 11617.13 | 0 | [40 empty] | 63400.2 | 77352.14 | 77714.67 | 0 |  | 87045.67 | 28918.02 | 87710.52 | 25882.31 | 16621.84 | 9027 | 9306.5 | 5404 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C005 | F21P1 Module Tool Interconnection DIF1-2 | 2695 | C | USCSB2309183A |  | DIFF 1: 25 Tools Swagelok for N2 bottle | 2023/9/29 2024/8/5 | 2023/10/3 2024/8/5 | 0 | -89.08 | 89.08 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1: VOID - Material never ordered. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2696 | C | USCSB2309184A |  | Mobile Bar and Pipe Rack | 45198 | 2023/10/4 2023/11/14 | 0 | 0 | [5 empty] | Uline | PR Approved | PO Approved | PO R1:Supplier Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2697 | C | USCSB2309184B |  | Mobile Bar and Pipe Rack | 9/29/2023 8/22/2024 | 11/16/2023 8/24/2024 | 0 | -10400 | 10400 |  |  |  | V | U-Line Corporation | PR Approved | PO Approved | B PR R1: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2698 | C | USCSB2309185A |  | San Tan Fire LLC Welding Electrical Work | 45198 | 45202 | 25000 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 25000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 25000 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C026 | F21P1-0423_H_Unistrut Support Frame_MICU | 2699 | C | USCSB2309187A |  | New batch of rack use | 45198 | 45212 | 1272328.2 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1272229.2 | 0.99992 | 99 | 0 | 99 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 84639.2 | 0 |  | 74993.95 | 780040 | 326616.05 | 0 |  | 5940 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2700 | C | USCSB2309188A |  | Clamps | 45198 | 45202 | 11024 | [6 empty] | Carson Sales Co Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8880.84 | 0.80559 | 2143.16 | 0 | 2143.16 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 3150.66 | 0 | 0 | 5730.18 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2701 | C | USCSB2309189A |  | OD Tube Strut Clamp EG | 45198 | 45201 | 7516 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7516 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 7516 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Labor | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2702 | C | USCSB2309190A |  | Andys Air Conditioning Installation Glendale and Surprise | 2023/9/29 2023/10/21 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: cancel this PR |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Base-Build | Outsourcing | USC23C002 | F21P1-0404_H_Hallway plate install_MICU | 2703 | C | USCSB2309191A |  | Project manpower supply for safety, project management and house keeping | 45198 | 45201 | 425080 | [6 empty] | CGS Global Support, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 424149.23 | 0.99781 | 930.77 | 0 | 930.77 | 0 | [40 empty] | 423039.23 | 0 | 1110 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2704 | C | USCSB2309192A |  | Hardware for CYH (sea) | 2023/9/29 2023/10/9 | 45209 | 139605 | [6 empty] | CYH TECHNOLOGY USA LLC | PR Approved | PO Approved | PR R1:Adjusting item 041 amount per purchaser's request. |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 139605 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 139605 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2705 | C | USCSB2309193A | -01 | E2 TW Profit - Uangyih | 2023/9/29 2023/12/28 | 2023/10/3 2023/12/28 | 0 | -252000 | 252000 |  |  |  | V | Uangyih-Tech Industrial Co., LTD | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 300000 | -300000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2706 | C | USCSB2309194A | -01 | E2 TW Profit - Huengluei | 2023/9/29 2023/12/28 | 2023/10/3 2023/12/28 | 0 | -661520 | 661520 |  |  |  | V | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved | R1: TW company management fee is contracted by TSMC directly |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2707 | C | USCSB2309195A |  | material for LJ W339 order#3 | 45199 | 45203 | 7129.48 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6082.08 | 0.85309 | 1047.4 | 0 | 1047.4 | 912.312 | [40 empty] | 0 | 0 | 0 | 675.44 |  | 5406.64 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [8 empty] | 213.8844 |  |  |  | 356.474 |  | 912.312 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2708 | C | USCSB2310001A |  | HARDWARE FOR LI JIE | 2023/10/3 2023/10/12 | 45211 | 170000 | [6 empty] | Li Jie Industrial Co.,Ltd | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 170000 | 0 | 170000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2709 | C | USCSB2310002A |  | VMB parts for Chemical team | 45202 | 45206 | 2226.34 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2226.34 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2226.34 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2710 | C | USCSB2310003A | -01 | VMB parts for Chemical team | 45202 | 2023/10/7 2023/10/11 | 1190 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved | PO R1:Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1190 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1190 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2711 | C | USCSB2310004A | -01 | Leveling Foot to support W-IPA WLS at the correct elevations. | 45202 | 2023/10/6 2023/11/7 | 0 | -405.2 | 405.2 |  |  |  |  | WW Grainger Inc | PR Approved | PO Approved | Cancelled the PO |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Triazole | Labor | USC22C022 | F21P1 Triazole treatment system | 2712 | C | USCSB2310005A |  | Triazole pad modification in WRC | 45202 | 45205 | 4050 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4050 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 4050 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Non-TSMC Interconnection | Interconnection | Labor | USC23C036 | F21P1 AMAT Interconnection | 2713 | C | USCSB2310006A |  | Change Order total for KSSBA3 | 45202 | 45206 | 3441.93 | [6 empty] | Rosendin Electric, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 3441.93 | 0 | 3441.93 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2714 | C | USCSB2310007A |  | Galv. st Duct | 2023/10/3 2023/10/17 | 45217 | 104813.23 | [6 empty] | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 104813.23 | 0 | 104813.23 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2715 | C | USCSB2310008A |  | Label | 45202 | 45213 | 25155 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 25155 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 25155 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2716 | C | USCSB2310009A |  | Tool and Material for Taiwan team | 45202 | 45209 | 57021.97 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 56507.17 | 0.99097 | 514.8 | 0 | 514.8 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 46622.05 | 0 | 0 | 9885.12 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2717 | C | USCSB2310010A |  | Bulkhead union | 45202 | 45206 | 30618 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 8570.71 | 0.27992 | 22047.29 | 0 | 22047.29 | 0 | [40 empty] | 0 | 0 | 2447.01 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 6123.7 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC22C005 | Tool Hookup Material (UPW&Chemical) | 2718 | C | USCSB2310011A |  | HK UPW DP Panel additional request | 45202 | 45210 | 479503.83 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 479503.83 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 45555.6 | 284470.61 |  |  | 0 | 82311.54 | 0 |  | 0 |  |  |  | 67166.08 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2719 | C | USCSB2310012A |  | QR: CHAD/FAD LAN CABLE TRAY – INT. MATERIALS | 45202 | 45223 | 36.19 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 36.19 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 36.19 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Equipment | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2720 | C | USCSB2310013A |  | QR: KXAT01, KXAT02, KXFX01, KXPS01: T&M FOR ECONNECTION BOX TERMINATIONS | 2023/10/3 2024/8/5 | 2023/10/26 2024/8/5 | 1911.63 | -1208.37 | 3120 | V |  |  |  | Delta Wye Electric, Inc. | PR Approved | PO Approved | R1: Updated amount to match invoice. Material was not included, so modified line#1 ($744.00 + $271.63 for material)/8 hrs. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1911.63 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 1911.63 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2721 | C | USCSB2310014A |  | EBO: CDA CABINET – INT. MATERIAL 30M COIL 8M PFA TUBING | 45202 | 45226 | 477.41 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 477.41 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 477.41 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C003 | F21P1 Module Tool Interconnection CVD | 2722 | C | USCSB2310015A |  | CVD2: KCANN1/KCANN2: Load Lock Gasline Weldments | 10/3/2023 8/15/2024 | 10/12/2023 8/22/2024 | 0 | -4043 | 4043 |  |  |  |  | Trident Mechanical Services | PR Approved | PO Approved | R1: VOID - PER PM. NO LONGER NEEDED IT. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 3428.8 | -3428.8 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | MMI | USC23C045 | WWT Change Order (Piping) | 2723 | C | USCSB2310016A |  | WWT Flange Level Gauge Platform Mod(MU)( T125AC/AD LG clash) | 45202 | 45206 | 2239 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2239 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 2239 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2724 | C | USCSB2310017A |  | Galvanized Tool | 45203 | 45209 | 126419.7 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 126419.7 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 126419.7 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Equipment | USC23C015 | F21P1 AMHS Wiring Work Outline | 2725 | C | USCSB2310018A |  | 40 beakers purchase from Taiwan | 45203 | 45209 | 12970 | [6 empty] | Third Enterprise | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 12970 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 12970 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2726 | C | USCSB2310019A |  | Pillar hand tool_0828 requirement | 45203 | 45206 | 173.73 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 173.73 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 173.73 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2727 | C | USCSB2310020A |  | Yih Jiun Hand Tool_0828 requirement | 45203 | 45205 | 34009 | [6 empty] | Yih Jiun Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 34009 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 34009 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2728 | C | USCSB2310021A |  | Acrylic boards used in chemical in status and used for every each VMB of A/B side. | 45203 | 45206 | 6290 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6290 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 6290 | 6290 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2729 | C | USCSB2310022A |  | Acrylic boards used in normal status and used for every each VMB of A/B side. | 45203 | 45206 | 44482 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 44482 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 44482 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Labor | USC21C014 | F21P1 WH2SO4 | 2730 | C | USCSB2310023A |  | VOC 02 & VOC 03 resolve moldy by decontaminating the crates. | 45203 | 45206 | 7709.6 | [6 empty] | Clean Harbors Environmental Services Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7709.6 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 7709.6 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2731 | C | USCSB2310024A | -01 | Southwest Hand Tool_0828 requirement | 45203 | 2023/10/10 2023/10/13 | 42268.48 | -16797.14 | 59065.62 |  |  |  |  | Southwest Fastener Division of NEFCO | PR Approved | PO Approved | PO transaction due to pricing change (Zero out Qty for 1 item) |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 37220.66 | 0.88058 | 5047.82 | 0 | 5047.82 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 37220.66 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2732 | C | USCSB2310025A |  | 9/19/23 to 10/20/23 Southwest Fastener Monthly Order for Water Team | 45203 | 45239 | 53075.77 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 53075.77 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 19697.77 | 33378 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2733 | C | USCSB2310026A |  | Coil .093 rd T 316L SS to 1 13/16 od max x 1 17/32 id min 6 pitch for YaHo work at Lorry FNDP. | 45203 | 45212 | 2728.53 | [6 empty] | Chukar PTS LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2728.53 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 2728.53 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2734 | C | USCSB2310027A |  | Hueng Luei Galvanized Dust (Air ship) | 45203 | 2023/10/20 2024/10/15 | 300000 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 300000 | 0 | 300000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 2735 | C | USCSB2310028A |  | WWT -LB2-Lab drain | 45204 | 45212 | 1012845 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 962923 | 0.95071 | 49922 | 0 | 49922 | 48146.15 | [40 empty] | 0 | 0 | 0 | 0 | 324110 | 0 | 0 | 0 | 520838 | 66599 |  |  | 51376 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 48146.15
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2736 | C | USCSB2310029A |  | 45 deg Coax elbows 1 ?” x 1 for Harder work at north mains L20 FAB. | 45204 | 45209 | 5200 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5200 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 5200 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2737 | C | USCSB2310030A |  | Clamps | 45204 | 45211 | 419.03 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 419.03 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 419.03 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2738 | C | USCSB2310031A |  | 9/19/23 to 10/20/23 Southwest Fastener Monthly Order for Chemical Team | 45204 | 45239 | 12581.2 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 11365.23 | 0.90335 | 1215.97 | 0 | 1215.97 | 0 | [43 empty] | 851.42 | 4931.3 | 600 | 0 | 0 | 2505.59 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 2476.92 | 3648.55 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2739 | C | USCSB2310032A |  | Grainger General Electrical Warehouse Crimpers | 45204 | 45209 | 4745.86 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 4745.86 | 0 | 4745.86 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C006 | F21P1 Module Tool Interconnection EPI | 2740 | C | USCSB2310033A |  | KCENA1 & KCEPA1 EPI Pump Fore Line Adapter Modification Proposal | 2023/10/5 2023/11/15 | x | 0 | [7 empty] | PR Approved | PO Approved | PR R1: canceled order |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Equipment | USC21C013 | F21P1 AMC THC Monitoring System | 2741 | C | USCSB2310034A | -01 | F21 P1 IMS Wipe Test | 45204 | 2023/10/10 2023/10/17 | 6400 | [6 empty] | Welmade Technology Corporation | PR Approved | PO Approved | PO R1:Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6400 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2742 | C | USCSB2310035A |  | Label | 45204 | 45211 | 478.27 | [6 empty] | Ryan Herco Flow Solutions | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 478.27 | 1 | 0 | 85000 | -85000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 478.27 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2743 | C | USCSB2310036A |  | Wire THNN | 45204 | 45212 | 187928.47 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 187928.46 | 1 | 0.01 | 0 | 0.01 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 27410.98 | 75693.85 | 0 |  |  | 0 | 84823.63 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2744 | C | USCSB2310037A |  | Cutting in Place for Tile and Partitions | 45204 | 45243 | 314000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 299120 | 0.95261 | 14880 | 0 | 14880 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 199365 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 18775 |  | 0 |  | 16480 |  |  |  | 17720 |  |  |  | 22120 |  |  |  | 24340 | 0 |  | 320 | 0 | - | 0 | 0
Hookup | Warehouse | Material | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2745 | C | USCSB2310039A | -01 | Border States Electrical Work Material PreFab Area | 45205 | 2023/10/10 2023/10/13 | 10121.55 | [6 empty] | Border State Industries, Inc. | PR Approved | PO Approved | Payment Term Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10121.55 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 10118.23 | 3.32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2746 | C | USCSB2310040A |  | Bush | 45205 | 45212 | 12374.74 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 12374.74 | 0 | 12374.74 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2747 | C | USCSB2310041A |  | WWT Drain Pipe PP PN6 | 45205 | 45211 | 11648.26 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 11648.26 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 6070.22 |  | 5578.04 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2748 | C | USCSB2310043A |  | Material for drain PN6 | 45206 | 45211 | 20990.4 | [6 empty] | Mega Union Technology Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 20990.4 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 17990.4 | 0 | 0 | 0 |  | 0 |  |  |  |  | 419.808 |  |  | 3000 | 629.712 |  |  |  | 1049.52 |  | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2749 | C | USCSB2310044A |  | WWT -BMWC -X123(WWT Tunnel Trestle scope - Change order for continuing priority lines) | 45206 | 45216 | 34978 | [6 empty] | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 34978 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 33229.1 | 0 | 0 | 0 |  |  | 1748.9 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2750 | C | USCSB2310045A |  | WWT- hardware for LJ | 45206 | 45209 | 10800.18 | [6 empty] | Copper State Bolt & Nut Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10800.18 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 278.6 | 6398.36 | 4123.22 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Others | AMHS | Material | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2751 | C | USCSB2310046A |  | Distribution Panel Fillers | 45206 | 45209 | 4286 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 4286 | 0 | 4286 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Material | USC23C045 | WWT Change Order (Piping) | 2752 | C | USCSB2310048A |  | Core Drill In Various Areas | 45206 | 45216 | 146485 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Lemar J Edwards |  |  |  | Lemar J Edwards | [7 empty] | 146485 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 146485 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC22C001 | F21 P1 Office and WH Security and CCTV | 2753 | C | USCSB2310049A |  | F21 P1 Security and CCTV Engineering | 45206 | 45216 | 60216 | [6 empty] | Onsight Live, LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 60216 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 60216 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Labor | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2754 | C | USCSB2310050A |  | QR: CHAD/FAD LABS: INTERCONNECT & CHILLERS FOR 9 TOOLS | 45206 | 45212 | 19920 | [6 empty] | Netcom Cabling, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 19920 | 0 | 19920 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2755 | C | USCSB2310051A |  | Hardware for Tun Yi Pumping Line | 45209 | 45216 | 184633.63 | [6 empty] | TUN YI Industrial Co., Ltd. | PR Approved | PO Approved | Wooden Crate fee can only be charged based on actual usage |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 135476.83 | 0.73376 | 49156.8 | 0 | 49156.8 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 86435.89 | 0 | 0 | 49040.94 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2756 | C | USCSB2310052A |  | field labor | 45209 | 45222 | 35606.74 | [6 empty] | IMCOR - Interstate Mechanical | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 35606.74 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 35606.74 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2757 | C | USCSB2310053A | -01 | flowmeter vern | 2023/10/10 2024/3/8 | 2023/11/4 2024/3/28 | 0 | -3636.44 | 3636.44 |  |  |  |  | Vern Lewis Welding Supply, Inc. | PR Approved | PO Approved | R1: duplicate. zero out |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Labor | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2758 | C | USCSB2310054A |  | TSMC High Speed Door Frame at L30 | 45209 | 45212 | 17352 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 17352 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 17352 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2759 | C | USCSB2310055A |  | 1" 316 EP tube for Yaho work at Lorry FNDP | 45210 | 45212 | 7866 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 7752.15 | 0.98553 | 113.85 | 0 | 113.85 | 0 | [40 empty] | 0 | 0 | 0 | 7752.15 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 78.66 | [9 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2760 | C | USCSB2310056A |  | Welder equipment for Chemical welding. | 45210 | 45211 | 8760 | [6 empty] | Tech South, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8760 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 5840 | 2920 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2761 | C | USCSB2310057A |  | FAB B Chemical/ UPW Permitting(batch1/2) | 45210 | 45216 | 30000 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 30000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 30000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C003 | F21P1 UPW | 2762 | C | USCSB2310058A |  | FAB B Chemical/ UPW Permitting(batch2/2) | 45210 | 45216 | 10000 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 10000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 10000 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Base-Build | Labor | USC21C005 | F21P1 Chemical & WCCS package | 2763 | C | USCSB2310059A |  | Lorry additional 16 RU systems | 45210 | 45234 | 10000 | [6 empty] | KAEKO, Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 10000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 10000 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2764 | C | USCSB2310060A | -01 | Material for YaHo at Lorry FNDP. | 45210 | 2023/10/12 2023/12/2 | 977.28 | 90.88 | 886.4 |  |  |  |  | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved | PO R1:Per request by engineer to revise price |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 977.28 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 977.28 |  |  |  |  | 977.28 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2765 | C | USCSB2310061A |  | 2” BA tube for Yaho work at Lorry FNDP | 45210 | 45211 | 996 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 996 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 996 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C004 | F21P1 Module Tool Interconnection CMP1 | 2766 | C | USCSB2310062A |  | CMP Interconnection Material Tubing | 45210 | 45212 | 252.2 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 252.2 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 252.2 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C003 | F21P1 Module Tool Interconnection CVD | 2767 | C | USCSB2310063A |  | AMAT CVD Interconnection material | 45210 | 45212 | 342.42 | [6 empty] | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 342.42 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 342.42 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2768 | C | USCSB2310064A |  | Hansen Quote 10/06 | 45210 | 45224 | 58080 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 58080 | 0 | 58080 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2769 | C | USCSB2310065A | -01 | Hardware for Chemical YaoHong work at Lorry FNDP, CDA at L20. | 2023/10/11 2023/11/14 | 2023/10/13 2023/11/14 | 0 | -77013 | 77013 |  |  |  |  | JUWEI ENGINEERING CO LTD | PR Approved | PO Approved | R1: Will change to another supplier per request |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2770 | C | USCSB2310065B |  | Hardware for Chemical YaoHong work at Lorry FNDP, CDA at L20. | 45245 | 45245 | 77013 | [6 empty] | JUWEI ENGINEERING CO LTD | PR Approved | PO Approved | Originally want to change the supplier name, but the materials have already been shipped out |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 77013 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 36205 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 40808 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2771 | C | USCSB2310066A |  | HK Exhaust Galvanized Hardware | 45210 | 2023/10/10 2024/10/15 | 85000 | [6 empty] | HUENG LUEI PROCESS INDUSTRY CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 0 | 0 | 85000 | 0 | 85000 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2772 | C | USCSB2310067A |  | Hua Yi Construction Az General Labor Costs for Material Handling & Moving Supplies | 45210 | 45212 | 18240 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 18240 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 18240 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Southland | USC21C005 | F21P1 Chemical & WCCS package | 2773 | C | USCSB2310068A |  | Southland Co for Chemical team | 45210 | 45212 | 517921.17 | [6 empty] | Southland Industries | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 517921.17 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 517921.17 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC21C011 | F21 TMAH System | 2774 | C | USCSB2310069A |  | F21 P1 CCTV Engineering | 45210 | 45224 | 200000 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 200000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 200000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Slurry | Equipment | USC21C006 | F21P1 Slurry package | 2775 | C | USCSB2310070A |  | USC21C006 SLURRY B SIDE VMB Production Engineering | 45211 | 45231 | 42959.15 | [6 empty] | FusionHPX LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 42959.15 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 42959.15 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2776 | C | USCSB2310071A |  | WWT FAB/WWT centralizer | 45211 | 45224 | 28785 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 28785 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 28785 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | UPW | UMEC | USC21C003 | F21P1 UPW | 2777 | C | USCSB2310072A |  | UPW-UMEC-L20-Enermech-repair | 45211 | 45218 | 17008 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 17008 | 0 | 17008 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 17008 | [7 empty] | 16157.6 |  | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Labor | USC23C059 | F21P1 Foundation T&M | 2778 | C | USCSB2310073A |  | Tile Alignment | 45211 | 45232 | 320000 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 320000 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 50030 | 122869.28 | 101251 | 0 |  | 42298 | 3551.72 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2779 | C | USCSB2310074A | -01 | CDS Platform 3 Raised Grating | 45211 | 2023/10/19 2023/10/31 | 29376 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved | R1: Quotation No. Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 29376 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10000 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 29376 |  |  |  |  | 19376 |  |  |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | MMI | USC21C005 | F21P1 Chemical & WCCS package | 2780 | C | USCSB2310075A |  | CDS Lorry Crossover Steps. | 45211 | 45217 | 3591 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 3591 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 3411.45 | 0 | 0 | 0 |  |  | 179.55 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2781 | C | USCSB2310076A |  | Hansen label for pumping line | 10/12/2023 8/22/2024 | 10/19/2023 8/24/2024 | 6629.76 | [5 empty] | V | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6629.76 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 6629.76 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2782 | C | USCSB2310077A |  | Label Hansen POWER | 45211 | 45218 | 6851.04 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6836.49 | 0.99788 | 14.55 | 0 | 14.55 | 0 | [41 empty] | 0 | 0 | 0 | 1277.96 | 0 | 0 | 0 | 5558.53 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC22C001 | F21 P1 Office and WH Security and CCTV | 2783 | C | USCSB2310079A |  | Gown Access Control Permit Assistance | 45211 | 45217 | 5260 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 5260 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 3616.5 | 1643.5 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | PSS | USC23C045 | WWT Change Order (Piping) | 2784 | C | USCSB2310080A |  | PSS Per Diem | 45211 | 45211 | 4000000 | [6 empty] | Process Service Specialists, LLC of Delaware | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 3700000 | 0.925 | 0 | 0 | 0 | 0 | [40 empty] | 3700000 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 120000 | [9 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | WWT | Labor | USC23C045 | WWT Change Order (Piping) | 2785 | C | USCSB2310081A |  | Taiwan experienced wrokers-help on WWT pipng fixed in FAB A site. | 45211 | 45223 | 300000 | [6 empty] | Gejinsin Enterprise Co., Ltd. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 300000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 300000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2786 | C | USCSB2310082A |  | Tool Hookup L40 Warehouse | 45212 | 2023/10/19 2023/11/14 | 0 | [6 empty] | Uline | PR Approved | PO Approved | PO R1:Supplier Change |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2787 | C | USCSB2310082B |  | Tool Hookup L40 Warehouse | 45212 | 45246 | 21590 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 8149.98 | 0.37749 | 13440.02 | 0 | 13440.02 | 0 | [43 empty] | 0 |  | 0 | 0 | 8149.98 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2788 | C | USCSB2310083A |  | HK YAHO Accommodation | 45212 | 45222 | 66000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 66000 | 1 | 0 | 0 | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 66000 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 2789 | C | USCSB2310084A |  | VOC Fiber cable for re-pull | 45212 | 45217 | 2943.5 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2943.5 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 2943.5 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C007 | F21P1 VOC package （Installation ) | 2790 | C | USCSB2310085A |  | VOC MC cable for LowNox | 45212 | 45218 | 6330.8 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6087.83 | 0.96162 | 242.97 | 0 | 242.97 | 242.97 | [40 empty] | 0 | 0 | 0 | 0 |  | 6087.83 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 242.97
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2791 | C | USCSB2310086A |  | LABEL | 10/13/2023 8/23/2024 | 2/13/2024 8/29/2024 | 105542.89 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved | R1: To match the requisition amount and the PO amount |  | Jen-Ping Tsai | [11 empty] | 105480.67 | 0.99941 | 62.22 | 0 | 62.22 | 0 | [49 empty] | 104606.89 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 | 873.78 | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2792 | C | USCSB2310087A |  | Hansen LABEL okland | 45212 | 45218 | 1400.57 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1394.33 | 0.99554 | 6.24 | 0 | 6.24 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 1394.33 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup |  | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2793 | C | USCSB2310088A | -01 | Galv. st Duct revision of USCSB2310007 | 2023/10/14 2023/10/27 | 2023/10/19 2023/12/29 | 0 | -104813.23 | 104813.23 |  |  |  |  | Streimer Sheet Metal Works, Inc. | PR Approved | PO Approved | Duplicate USCSB2310007A |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2794 | C | USCSB2310089A |  | wire cable 3/4 WG for Third Industry | 45213 | 45234 | 288348.47 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 81011.79 | 0.28095 | 207336.68 | 0 | 207336.68 | 0 | [42 empty] | 0 | 0 |  | 41392.1 | 0 | 0 | 18017.25 | 0 | 21602.44 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2795 | C | USCSB2310090A |  | CDS Hardware for YaoHong work at Lorry FNDP_2nd | 45213 | 45219 | 16013.95 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 16013.95 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 16013.95 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | MMI | USC21C012 | F21 Barcode RFID System | 2796 | C | USCSB2310091A |  | VOC Unistrut Support | 45213 | 45219 | 17329 | [6 empty] | Milling Machinery, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 17329 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 4750 |  | 7596.91 | 0 | 0 |  | 0 |  | 4982.09 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Others | AMHS | Equipment | USC22C031 | CAP_E_F21P1 AMHS MML Seismic Foundation | 2797 | C | USCSB2310092A |  | TSMC-F21P1 AMHS_Hardware_CT | 45213 | 45219 | 13230 | [6 empty] | Third Enterprise | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 13230 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 13230 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2798 | C | USCSB2310093A |  | H2O2 chemical storage in LB2 | 45213 | 45217 | 4198.32 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 4198.32 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 4198.32 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC Interconnection | Interconnection | Material | USC23C036 | F21P1 AMAT Interconnection | 2799 | C | USCSB2310094A | -01 | AMAT_ME_ Amazon_KKDB04, KKDD03, KKDB05, KKDD04_flexible duct, clamps | 45213 | 2023/10/20 2023/11/8 | 782.66 | -42.14 | 824.8 |  |  |  |  | Amazon.com, Inc. | PR Approved | PO Approved | Amazon order amount was changed due to partial refund/return. |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 782.66 | 0 | 782.66 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2800 | C | USCSB2310095A |  | Linde Liquid Argon | 45213 | 45219 | 20890.32 | [6 empty] | Linde Gas and Equipment Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 20833.42 | 0.99728 | 56.9 | 0 | 56.9 | 0 | [41 empty] | 0 | 0 | 0 | 15224.61 | 2477.27 | 0 | 0 | 0 | 0 |  | 2486.74 | 0 | 0 | 0 |  | 0 | [5 empty] | 644.8 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 2801 | C | USCSB2310096A | -01 | Puressuring testing certificat for THC (A+B) and AMC (B) | 45216 | 2023/10/20 2023/10/23 | 17710 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved | PO R1: Remark Information Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6722 | 0.37956 | 10988 | 0 | 10988 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 1422 |  |  | 0 | 0 | 0 |  | 0 |  | 5300 | [14 empty] | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2802 | C | USCSB2310097A | -02 | Uline security cart | 45216 | 2023/10/26 2024/1/13 2024/1/26 | 0 | -56160 | 56160 |  |  |  |  | U-Line Corporation | PR Approved | PO Approved | PO R2:change supplier from ULINE to Thomas Scientific PO R1:Negotiated Unit Rate |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Site Expense | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2803 | C | USCSB2310097B |  | Uline security cart | 45216 | 2023/10/25 2024/01/12 2024/01/26 | 26066.7 | 26066.7 | 0 | V |  |  |  | Thomas Scientific Holdings LLC | PR Approved | PO Approved | PO B: change supplier to Thomas Scientific PO R2: change supplier from ULINE to Thomas Scientific PO R1: Negotiated Unit Rate |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 26066.7 | 1 | 0 | 0 | 0 | 0 | [48 empty] | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 26066.7 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C025 | F21P1 Lam Interconnection | 2804 | C | USCSB2310098A |  | Cable Tray Divider Supply | 45216 | 45218 | 1246 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1246 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1246 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 2805 | C | USCSB2310099A | -01 | WWT-Suction pipes for train A | 2023/10/17 2023/12/8 | 2023/10/19 2024/1/4 | 644264 | 123508 | 520756 |  |  | V |  | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved | PR R1Renew quotation |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 612083 | 0.95005 | 32181 | 0 | 32181 | 30604.15 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 187472 | 113557 | 37474 |  |  | 69786 | 103234 | 0 |  | 51617 |  |  |  | 48943 | 32213.2 |  |  |  | 32213.2 |  |  |  | 32213.2 |  | 0 |  | - | 0 | - | 0 | 0 | 30604.15
Base-Build | WWT | Equipment | USC23C045 | WWT Change Order (Piping) | 2806 | C | USCSB2310100A |  | WWT-Swing gate | 45216 | 45219 | 91000 | [6 empty] | Degan Construction LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 85670 | 0.94143 | 5330 | 0 | 5330 | 5933.2 | [41 empty] | 0 | 0 | 0 |  | 0 | 41210 | 0 | 0 | 0 |  | 1560 | 0 | 37960 | 2600 |  | 0 |  | 1040 |  |  |  | 390 |  |  | 2730 |  |  |  | 3640 |  | 0 | 910 | - | 0 | - | 0 | 0 | 5933.2
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2807 | C | USCSB2310101A |  | UPW-AnCor-UT2211B,3111B-ladder modify | 45216 | 45224 | 2520 | [6 empty] | An-Cor Industrial Plastics, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2520 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 2520 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C029 | EBO21- Tool interconnection | 2808 | C | USCSB2310102A |  | EBO: PVC CURTAIN - ALUM. MOUNTAIN PLATE | 45216 | 45219 | 441.08 | [6 empty] | McMaster-Carr Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 440.97 | 0.99975 | 0.11 | 0 | 0.11 | 0 | [41 empty] | 0 | 0 | 0 | 440.97 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Equipment | USC21C003 | F21P1 UPW | 2809 | C | USCSB2310103A |  | UPW-NaHSO3 cover repair | 45216 | 45219 | 1017.69 | [6 empty] | Pure Plastics, LLC | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 1017.69 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 1017.69 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Material | USC22C001 | F21 P1 Office and WH Security and CCTV | 2810 | C | USCSB2310104A |  | F21 Warehouse CCTV Engineering | 45216 | 45217 | 34525 | [6 empty] | Hua Yi Construction AZ, Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 34525 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 34525 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | VOC | Material | USC21C012 | F21 Barcode RFID System | 2811 | C | USCSB2310105A |  | F21 P1 VOC WWT line engineering | 45216 | 45222 | 16000 | [6 empty] | YAHO System Technology Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 16000 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 16000 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | UPW | Labor | USC21C003 | F21P1 UPW | 2812 | C | USCSB2310106A | -03 | construction of shaft wall on Mezzanine 1and 2 | 45216 | 2023/10/31 2023/11/6 2024/01/04 | 250000 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved | Change of remark: remove original no. (15) and Liquidated damage - Add time & material R3: Indemnity Change |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 117163.87 | 0.46866 | 132836.13 | 0 | 132836.13 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 117163.87 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | CCTV | Labor | USC22C001 | F21 P1 Office and WH Security and CCTV | 2813 | C | USCSB2310107A |  | F21 CCTV Engineering | 45216 | 45224 | 300000 | [6 empty] | OE Electric | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 300000 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 223563.07 | 3700 | 0 | 72736.93 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 2814 | C | USCSB2310108A |  | MICU Electrical On-Call Support | 45217 | 45219 | 5000 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 2687.5 | 0.5375 | 2312.5 | 0 | 2312.5 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 1035 | 0 | 0 | 0 |  |  | 460 | 0 | 0 |  | 0 |  | 345 |  |  |  | 847.5 | [8 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C001 | TEL Main Tool Interconnection | 2815 | C | USCSB2310109A |  | DRY ETC2: KEPCH2 G.5/3, Conduit install | 45217 | 45220 | 574.62 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 574.62 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 | 574.62 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 2816 | C | USCSB2310111A |  | Tamperproof Tube marker | 45217 | 45220 | 11.87 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 11.87 | 0 | 11.87 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C007 | F21P1 Module Tool Interconnection PVD1-2 | 2817 | C | USCSB2310112A |  | Tamper Evident Tape Red | 45217 | 45220 | 54.18 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 0 | 54.18 | 0 | 54.18 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 2818 | C | USCSB2310113A |  | FAB-1A MML NRTL Nameplate Changes | 45217 | 45220 | 9720 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 9720 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 | 9720 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Non-TSMC | AMHS | Labor | USC23C015 | F21P1 AMHS Wiring Work Outline | 2819 | C | USCSB2310114A |  | FAB-1A Additional Modules M165,M187 | 45217 | 45220 | 14070 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 14070 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 7035 | 0 | 0 |  | 7035 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2820 | C | USCSB2310115A |  | CDS Commission PE tubes requested by Albert Tseng | 45218 | 45218 | 1700 | [6 empty] | Harrington Industrial Plastics LLC | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 1700 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 1700 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2821 | C | USCSB2310116A |  | CDS Eyeball Lorry Thinner Pressure Test | 45218 | 45224 | 37700 | [6 empty] | Eyeball Precision Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 37700 | 0 | 37700 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2822 | C | USCSB2310117A | -01 | CDS Unions to replace all Union Box accessories of Lorry to HPM IPA and PFA to SUS. | 2023/10/19 2023/10/19 | 2023/10/23 2023/10/25 | 3841.6 | 1812.6 | 2029 |  |  |  |  | Arizona/Albuquerque Valve & Fitting Corp. | PR Approved | PO Approved | R1:As per responsible engineer to revise QTY |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 3841.6 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 3841.6 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2823 | C | USCSB2310119A |  | Grainger September monthly order. shared material | 45218 | 45225 | 26474.24 | [6 empty] | WW Grainger Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 24741.8 | 0.93456 | 1732.44 | 0 | 1732.44 | 0 | [42 empty] | 24741.8 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | AMC THC | Labor | USC21C013 | F21P1 AMC THC Monitoring System | 2824 | C | USCSB2310120A |  | FAB A Litho Electrical Permit and CA Service | 45218 | 45219 | 4250 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4250 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 2565 | 0 | 0 | 1685 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C001 | TEL Main Tool Interconnection | 2825 | C | USCSB2310121A |  | 25 cable tray dividers BLN 73A-120 (KCSCS5,KCSCS8,KDCRS3,KDSNB1) | 45218 | 45219 | 622.88 | [6 empty] | Independent Electric Supply, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 622.88 | 1 | 0 | 6888 | -6888 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 622.88 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2826 | C | USCSB2310122A |  | CDS Paint for W-TANK Scratch Repair | 45218 | 45224 | 535 | [6 empty] | Continental Coatings Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 535 | 1 | 0 | 0 | 0 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 535 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Labor | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2827 | C | USCSB2310123A |  | MICU Electrical On-Call Support (UPW amd WWT) | 45218 | 45225 | 5000 | [6 empty] | LSW Engineers Arizona, Inc. | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 4945 | 0.989 | 55 | 0 | 55 | 49.45 | [41 empty] | 0 | 0 | 0 |  | 0 | 2530 | 0 | 0 | 1610 |  |  | 805 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 49.45
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2828 | C | USCSB2310124A |  | CED Clamps for Third | 45218 | 45239 | 42620 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 42620 | 0 | 42620 | 0 | [43 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2829 | C | USCSB2310125A |  | Hand tool - ACME | 45218 | 45224 | 14963.45 | [6 empty] | ACME Construction Supply Co Inc | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 14338.01 | 0.9582 | 625.44 | 0 | 625.44 | 0 | [41 empty] | 0 | 0 | 0 |  | 320 | 463.44 | 0 | 0 | 234.17 | 13320.4 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Interconnection | Interconnection | Material | USC23C032 | F21_AZQR_Hookup_ Interconnection | 2830 | C | USCSB2310127A |  | QR: NO TOOL ID: SPECIAL ADAPTERS - PVDF Reducer 2” to 1-1/4” | 45219 | 45227 | 57.4 | [6 empty] | SEMITORR GROUP, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 57.4 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 57.4 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2831 | C | USCSB2310128A |  | CED Building Wire; THHN STR; 250 kcmil; 1-Conductor; Copper; Black; 500 Ft. for Third | 45219 | 45234 | 47643.57 | [6 empty] | Consolidated Electrical Distributors Inc | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 47643.57 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 47643.57 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2832 | C | USCSB2310129A | -01 | WWT FAB/WWT Valves | 45219 | 2023/10/25 2023/11/1 | 179876.5 | 29348.8 | 150527.7 |  |  |  |  | Mega Union Technology Inc. | PR Approved | PO Approved | R1:As per requester need to renew the quotation price. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 157439.9 | 0.87527 | 22436.6 | 0 | 22436.6 | 18892.788 | [41 empty] | 0 | 0 | 0 |  | 17824.9 | 139615 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 5396.295 |  |  |  | 5396.295 |  |  |  | 3597.53 |  | 7871.995 |  | - | 7871.995 | - | 3148.798 | 0 | 0
Interconnection | Interconnection | Labor | USC23C001 | TEL Main Tool Interconnection | 2833 | C | USCSB2310131A |  | San Tan Fire Warehouse Labor | 45219 | 45223 | 8496 | [6 empty] | San Tan Fire, LLC | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 8496 | 0 | 8496 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2834 | C | USCSB2310133A |  | Shared material. labels and label makers. Open PO October to November | 45219 | 45233 | 100000 | [6 empty] | J A Hansen Company DBA Hansen Supply Company | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 93842.83 | 0.93843 | 6157.17 | 0 | 6157.17 | 0 | [42 empty] | 0 | 0 | 15948 | 0 | 0 | 9778.85 | 36248.54 | 0 | 2473.4 |  | 0 | 0 | 0 |  | 0 | [9 empty] | 6430.84 |  |  |  | 22963.2 | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2835 | C | USCSB2310134A |  | Tool Hook UP Warehouse Storage Tool | 45219 | 45231 | 20724.75 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 0 | 0 | 20724.75 | 0 | 20724.75 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Labor | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2836 | C | USCSB2310135A | -01 | Installer Lead Labor | 45219 | 45224 | 79358.9 | [6 empty] | ELECTRIC OPS LLC DBA E-OPS | PR Approved | PO Approved | R1:Remark Information Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 77658.38 | 0.97857 | 1700.52 | 680 | 1020.52 | 0 | [41 empty] | 0 | 0 | 0 |  | 0 | 11183.25 | 0 | 10933.5 | 11516.25 | 13888.88 |  | 0 | 0 | 13736.25 |  | 4495.5 |  | 11904.75 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2837 | C | USCSB2310136A | -01 | Yaho Hex nut, square nute, washer | 45219 | 2023/11/1 2023/11/7 | 0 | -178286 | 178286 |  |  |  |  | YAHO System Technology Inc. | PR Approved | PO Approved | PO R1:Supplier Correction |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 0 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2838 | C | USCSB2310136B |  | Yaho Hex nut, square nute, washer | 45219 | 45240 | 178286 | [6 empty] | YAHO System Technology Co., Ltd. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 178286 | 1 | 0 | 0 | 0 | 0 | [43 empty] | 0 |  | 0 | 0 | 178286 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Material | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2839 | C | USCSB2310137A |  | Trusval entegris PFA | 45220 | 45223 | 9134.97 | [6 empty] | Trusval Technology CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 9134.97 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [11 empty] | 9134.97 |  |  | 0 |  | - | 0 | - | 0 | 0
Base-Build | Water | Material | USC21C009 | F21P1 WWT package (Installation and 2 batch tanks) | 2840 | C | USCSB2310138A |  | 10/21/23 to 11/20/23 Southwest Fastener Monthly Order for Water Team | 45220 | 45300 | 31920.87 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 31920.87 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 31920.87 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2841 | C | USCSB2310139A |  | 10/21/23 to 11/20/23 Southwest Fastener Monthly Order for Chemical team | 45220 | 45303 | 6507.04 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 6507.04 | 1 | 0 | 0 | 0 | 0 | [45 empty] | 0 |  | 2355.7 | 3026.4 | 0 |  |  | 1124.94 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2842 | C | USCSB2310140A | -01 | MU/Hand welding machines for WWT | 2023/10/21 2023/12/15 | 2023/11/4 2023/12/30 | 167400 | -17619.4 | 185019.4 |  | V |  |  | Mega Union Technology Inc. | PR Approved | PO Approved | Reduction in amount is due to split of order as requested by Responsible Engineer |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 167400 | 0 | 167400 | 167400 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  |  | 25110 |  |  |  | 25110 |  |  |  | 25110 |  | 33480 |  | - | 33480 | - | 33480 | 33480 | 33480
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2843 | C | USCSB2310141A |  | Pillar parts used for VMB of B side. | 45220 | 45224 | 9243.21 | [6 empty] | Nippon Pillar Corporation of America | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 9243.21 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 447.47 | 0 |  |  | 0 | 487.55 | 0 |  | 8308.19 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2844 | C | USCSB2310142A |  | Southwest Fastener Open Statement Orders 08/20/23- 09/20/23 | 45220 | 45225 | 6982.49 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 6778.53 | 0.97079 | 203.96 | 0 | 203.96 | 0 | [42 empty] | 0 | 6685.53 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 93 | [10 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Hookup | Equipment | USC23C055 | F21P1-0404_H_labor for 50 tools_MICU | 2845 | C | USCSB2310143A |  | Uline Pallet Truck lime | 45220 | 45225 | 810 | [6 empty] | U-Line Corporation | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 0 | 0 | 810 | 0 | 810 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 2846 | C | USCSB2310146A |  | WWT-LSRi-uncompleted lines | 45223 | 45225 | 1917083 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 1734669 | 0.90485 | 182414 | 0 | 182414 | 173466.9 | [42 empty] | 0 | 0 |  | 0 | 0 | 443041 | 453152 | 254062 |  |  | 268826 | 162319 | 0 |  | 0 |  | 28057 |  | 125212 | 95854.15 |  |  |  | 95854.15 |  |  |  | 57512.49 |  | 0 |  | - | 0 | - | 0 | 0 | 173466.9
Base-Build | WWT | UMEC | USC23C045 | WWT Change Order (Piping) | 2847 | C | USCSB2310147A |  | WWT-Chad lab drain-6.5 line | 45223 | 45225 | 100297 | [6 empty] | University Mechanical & Engineering Contractors, Inc. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 95282 | 0.95 | 5015 | 0 | 5015 | 4764.1 | [42 empty] | 0 | 0 |  | 0 | 95282 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0 | 4764.1
Base-Build | WWT | Material | USC23C045 | WWT Change Order (Piping) | 2848 | C | USCSB2310148A |  | WWT-BMWC-Litho drain pipe-Train B | 45223 | 45248 | 414578 | -29699 | 444277 | V |  |  | V | BMWC Constructors, INC. | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 414578 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 101724.1 | 0 | 77900 | 0 |  |  | 116850 | 66215 | 0 |  | 0 |  | 31160 |  | 20728.9 | [10 empty] | 0 |  | - | 0 | - | 0 | 0 | 0
Base-Build | Chemical | Material | USC21C005 | F21P1 Chemical & WCCS package | 2849 | C | USCSB2310149A |  | CDS 1-1/2"x2" 45 ELBOW 316LEP/304AP | 45223 | 45223 | 5373 | [6 empty] | GOLD STONE DEVELOPMENT CO., LTD. | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 5373 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 5373 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Base-Build | Chemical | Equipment | USC21C005 | F21P1 Chemical & WCCS package | 2850 | C | USCSB2310150A |  | Professional Plastics custom the parts for VMB of A side | 45223 | 45226 | 55825.84 | [6 empty] | Professional Plastics Inc | PR Approved | PO Approved |  |  | Kuan-Chung Su |  |  |  | Kuan-Chung Su | [7 empty] | 55825.84 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 55825.84 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Warehouse | Equipment | USC22C008 | TSMC F21P1 Tool Hookup Logistic and Warehouse Management | 2851 | C | USCSB2310151A |  | Southwest Hand tool_0828 requirement_2 batch | 45223 | 45223 | 20193.59 | [6 empty] | Southwest Fastener Division of NEFCO | PR Approved | PO Approved |  |  | Tiong Sheng Poh |  |  |  | Tiong Sheng Poh | [7 empty] | 20193.59 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 20193.59 |  | 0 | 0 | 0 |  | 0 | [14 empty] | 0 |  | - | 0 | - | 0 | 0
Others | Liquid Penetrant | Labor | USC22C035 | CAP_A_90772_F21 Phone call base build and Liquid penetrant testing system | 2852 | C | USCSB2310152A |  | F21 Phone call base build and Liquid penetrant testing system engineering | 2023/10/24 2024/8/1 | 2023/10/26 2024/8/7 | 67876.26 | -9290.64 | 77166.9 | V |  |  |  | NUUO US Inc. | PR Approved | PO Approved | R1: Due to the discount provided by the Nuuo for the PO and reducing the PO amount as per PM Paul. |  | Yi En Wong |  |  |  | Yi En Wong | [7 empty] | 67876.26 | 1 | 0 | 0 | 0 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 43096.26 |  | 0 |  | 24780 | [12 empty] | 0 |  | - | 0 | - | 0 | 0
Hookup | Foundation | Material | USC23C059 | F21P1 Foundation T&M | 2853 | C | USCSB2310153A |  | Foundation T&M for Greenberry | 45223 | 45238 | 250000 | [6 empty] | Greenberry Industrial | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 199620.64 | 0.79848 | 50379.36 | 0 | 50379.36 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 4061.25 |  |  |  | 126066.9 |  | 46253.12 | [5 empty] | 23239.37 | 0 |  | - | 0 | 16786.5 | 0 | 0
Hookup | Foundation | Labor | USC23C059 | F21P1 Foundation T&M | 2854 | C | USCSB2310155A |  | Foundation T&M for PCI | 45223 | 45238 | 100000 | [6 empty] | Performance Contracting Inc | PR Approved | PO Approved |  |  | Yikang Wang |  |  |  | Yikang Wang | [7 empty] | 39524 | 0.39524 | 60476 | 0 | 60476 | 0 | [42 empty] | 0 | 0 |  | 0 | 0 | 0 | 3116 | 0 |  |  | 0 | 0 | 2624 |  | 0 |  | 19188 |  | 3444 | [5 empty] | 1312 |  |  |  | 9840 | 0 |  | - | 0 | - | 0 | 0